## Sheet1
JO Tracking Report
Factory: | KAHATEX CIJERAH | Floor | G1,G2,G3,G4,G5,SPL | JO: |  | Style No: |  | Delivery Date: | 16/08/2026 - 15/10/2026 | JO Status: | Uncompleted, Completed, Export | Printed by: | REYNALDI | Print time: | 14/09/2026 13:03:27
Customer Name | Order No. | Color | Lot No | Factory Style | Qty | Delivery Date | Plan Qty | Merchaniser | PO.NO | Line | Product Type | Floor | Fabrics | Auxiliary | JO Remarks | Process Route Name | Cust_Order_No | Pre-production event finish date | Factory | Ship To | Ship Mode | Sewing Start | Style Description | Plan Remarks | Season | SEWING | [8 empty] | COMPLETE ASSEMBLY | [8 empty] | HEAT TRANSFER
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902369757-1 KC4275 | GREY FIVE F17 | 60D | S2608MR0910A | 110 | 20/08/2026 | 110 | SI | SI24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L2+HT SUB PROCESS_V3 | 0902369757 KC4275 | 2026-03-03 | KAHATEX CIJERAH | URUGUAY | SEA | 23/06/2026 | Run Ess BL T M |  | FW26 | 23/06/2026 | 26/06/2026 | 24/06/2026 | 25/06/2026 | 110 | 110 |  |  |  | 18/06/2026 | 23/06/2026 | 25/05/2026 | 2026-05-06 | 110 | 110 |  |  |  | 17/06/2026 | 22/06/2026 | 21/05/2026 | 2026-03-06 | 110 | 110
ADIDAS | 0902369999-1 JD3669 | BLACK | 90D | SMSURBF24BFRNTM | 1 | 21/08/2026 | 1 | SA | SA24/01/2026 | G2M | T-SHIRT | G2 | ok | (11/02/2026) | 21/08: ex-fty 980004 | PRINT L1+PAD SUB PROCESS_V3 | 0902369999 JD3669 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/07/2026 | BF LOGO TEE M |  | FW26 | 15/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 1 | 1 |  |  |  | 2026-10-07 | 15/07/2026 | 17/07/2026 | 17/07/2026 | 1 | 1
ADIDAS | 0902370337-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 4368 | 21/08/2026 | 4368 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 27-feb, 3S actual receives 26-Mar. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370337 JE1309 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 14/07/2026 | 27/07/2026 | 14/07/2026 | 23/07/2026 | 4368 | 4368 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-11-07 | 23/07/2026 | 4368 | 4368
ADIDAS | 0902370353-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 1404 | 21/08/2026 | 1404 | NT | NT24/01/2026 | G1B | SHORTS | G1 | ok | ok | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370353 JE1310 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 21/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 1404 | 1404 |  |  |  | 16/07/2026 | 21/07/2026 | 2026-10-07 | 16/07/2026 | 1404 | 1404
ADIDAS | 0902370399-1 KF8293 | KHAKI SIX F26/WHITE | 90D | S2554WES421WV | 2028 | 21/08/2026 | 2028 | NT | NT24/01/2026 | G1B | SHORTS | G1 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, material quality issues (body: shading), 3S actual receives 26-Mar, Body actual receives 30-Apr. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370399 KF8293 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 15/07/2026 | 24/07/2026 | 15/07/2026 | 24/07/2026 | 2028 | 2028 |  |  |  | 2026-10-07 | 21/07/2026 | 13/07/2026 | 21/07/2026 | 2028 | 2028
ADIDAS | 0902370407-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 375 | 21/08/2026 | 375 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 27-Feb, 3S actual receives 12-Mar. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370407 JE1309 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 22/07/2026 | 23/07/2026 | 375 | 375 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 375 | 375
ADIDAS | 0902370413-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 135 | 21/08/2026 | 135 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | ok | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370413 JE1310 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 23/07/2026 | 27/07/2026 | 135 | 135 |  |  |  | 17/07/2026 | 22/07/2026 | 13/07/2026 | 13/07/2026 | 135 | 135
ADIDAS | 0902370424-1 KF8293 | KHAKI SIX F26/WHITE | 90D | S2554WES421WV | 240 | 21/08/2026 | 240 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, material quality issues (body: shading), 3S actual receives 12-Mar, Body actual receives 30-Apr. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370424 KF8293 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 23/07/2026 | 27/07/2026 | 240 | 240 |  |  |  | 17/07/2026 | 22/07/2026 | 13/07/2026 | 13/07/2026 | 240 | 240
ADIDAS | 0902372182-1 JD3663 | BLACK | 90D | SMSURBF24ABTEEY | 900 | 21/08/2026 | 900 | SI | SI24/01/2026 | G2M | T-SHIRT | G2 | ok | (11/02/2026) | 21/08: ex-fty 980004 | PRINT L2+PAD SUB PROCESS_V3 | 0902372182 JD3663 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 20/07/2026 | AB LOGO TEE Y |  | FW26 | 20/07/2026 | 22/07/2026 | 20/07/2026 | 22/07/2026 | 900 | 900 |  |  |  | 15/07/2026 | 17/07/2026 | 2026-10-07 | 21/07/2026 | 900 | 900
ADIDAS | 0902372325-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 590 | 2026-08-09 | 590 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372325 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 590 | 590 |  |  |  | 2026-03-07 | 15/07/2026 | 29/06/2026 | 2026-09-07 | 590 | 590
ADIDAS | 0902372436-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 124 | 31/08/2026 | 124 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372436 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 124 | 124 |  |  |  | 2026-03-07 | 15/07/2026 | 30/06/2026 | 2026-09-07 | 124 | 124
ADIDAS | 0902372459-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 122 | 31/08/2026 | 122 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Libolon, PI Date 23-Feb, actual receives 26-Feb. 800005T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902372459 JE1310 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26 | 14/07/2026 | 22/07/2026 | 14/07/2026 | 17/07/2026 | 122 | 122 |  |  |  | 2026-09-07 | 17/07/2026 | 13/07/2026 | 13/07/2026 | 122 | 122
ADIDAS | 0902372469-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 104 | 31/08/2026 | 104 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372469 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 104 | 104 |  |  |  | 2026-03-07 | 15/07/2026 | 2026-07-07 | 2026-07-07 | 104 | 104
ADIDAS | 0902372479-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 186 | 2026-08-09 | 186 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372479 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 22/07/2026 | 2026-09-07 | 21/07/2026 | 186 | 186 |  |  |  | 2026-03-07 | 17/07/2026 | 2026-02-07 | 18/07/2026 | 186 | 186
ADIDAS | 0902372487-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 134 | 31/08/2026 | 134 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372487 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 16/07/2026 | 2026-09-07 | 14/07/2026 | 134 | 134 |  |  |  | 2026-03-07 | 13/07/2026 | 30/06/2026 | 2026-07-07 | 134 | 134
ADIDAS | 0902372517-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 120 | 31/08/2026 | 120 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902372517 JE1310 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26 | 14/07/2026 | 22/07/2026 | 14/07/2026 | 17/07/2026 | 120 | 120 |  |  |  | 2026-09-07 | 17/07/2026 | 13/07/2026 | 14/07/2026 | 120 | 120
ADIDAS | 0902497405-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 244 | 2026-08-09 | 244 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497405 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-06-08 | 29/07/2026 | 2026-06-08 | 244 | 244 |  |  |  | 24/07/2026 | 2026-03-08 | 27/07/2026 | 2026-07-08 | 244 | 244
ADIDAS | 0902497408-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2L | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497408 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902497412-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 205 | 2026-08-09 | 205 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497412 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 27/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 205 | 205 |  |  |  | 22/07/2026 | 30/07/2026 | 15/07/2026 | 2026-04-08 | 205 | 205
ADIDAS | 0902497414-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497414 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 100 | 100 |  |  |  | 24/07/2026 | 30/07/2026 | 16/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902545290-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 3000 | 2026-05-09 | 3000 | SA | SA06/02/2026 | G1D,G1K,G3I | PANTS | G1,G3 | ok | ok | 04/09: ex-fty 823016 | EMBRO SUB PROCESS_V1 | 0902545290 GK9267 | 2026-11-03 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 21/07/2026 | M 3S FL O PT |  | FW26 | 21/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 3000 | 3000 |  |  |  | 16/07/2026 | 22/07/2026 | 2026-07-07 | 22/07/2026 | 3000 | 3000
ADIDAS | 0902556131-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1862 | 21/08/2026 | 1862 | SA | SA06/02/2026 | G3C | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, PI Date 02-Mar, actual receives 27-Feb. 960026 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0902556131 JE9016 | 2026-05-05 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/07/2026 | M LIN CHELSEA |  | FW26 | 15/07/2026 | 28/07/2026 | 14/07/2026 | 23/07/2026 | 1862 | 1862 |  |  |  | 2026-10-07 | 23/07/2026 | 2026-08-07 | 20/07/2026 | 1862 | 1862
ADIDAS | 0902557430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 112 | 31/08/2026 | 112 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, PI Date 17-Mar, actual receives 04-Jul (FOC 2147 yd) (switch with fabric from Libolon). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557430 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 20/07/2026 | 23/07/2026 | 112 | 112 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 14/07/2026 | 112 | 112 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 14/07/2026 | 112 | 112
ADIDAS | 0902557495-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 824 | 2026-08-09 | 824 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, using fabric stock (FOC 2147 yd) (switch with fabric from Far Eastern.). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557495 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 15/07/2026 | 23/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824
ADIDAS | 0902557554-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 100 | 31/08/2026 | 100 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, actual receives 04-Jul (FOC 2147 yd) (switch with fabric from Libolon). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557554 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 16/07/2026 | 24/07/2026 | 13/07/2026 | 15/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 15/07/2026 | 100 | 100
ADIDAS | 0902622148-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 4220 | 2026-12-09 | 4220 | AT | AT27/02/2026 | G3J,G3K | PANTS | G3 | ok | (19/03/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902622148 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 27/07/2026 | M 3S FT TC PT |  | FW26 | 27/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 4220 | 4220 |  |  |  | 22/07/2026 | 30/07/2026 | 2026-10-07 | 25/07/2026 | 4220 | 4220
ADIDAS | 0902622190-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 780 | 21/08/2026 | 780 | AT | AT27/02/2026 | G3D | PANTS | G3 | ok | (19/03/2026) | 21/08: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902622190 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 29/07/2026 | 23/07/2026 | 28/07/2026 | 780 | 780 |  |  |  | 16/07/2026 | 24/07/2026 | 2026-04-07 | 13/07/2026 | 780 | 780
ADIDAS | 0902635931-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 602 | 2026-08-09 | 602 | SA | SA27/02/2026 | G2S | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635931 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 20/07/2026 | 602 | 602 |  |  |  | 2026-03-07 | 15/07/2026 | 26/06/2026 | 2026-02-07 | 602 | 602
ADIDAS | 0902635960-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 204 | 31/08/2026 | 204 | SA | SA27/02/2026 | G2E,G2L | T-SHIRT | G2 | ok | (18/03/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635960 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 17/07/2026 | 204 | 204 |  |  |  | 2026-03-07 | 15/07/2026 | 30/06/2026 | 2026-08-07 | 204 | 204
ADIDAS | 0902636875-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2720 | 15/09/2026 | 2720 | AT | AT04/03/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (28/03/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902636875 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-09-09 | 29/08/2026 | 2026-09-09 | 2720 | 2720 |  |  |  | 24/08/2026 | 2026-05-09 | 28/07/2026 | 2026-09-09 | 2720 | 2720
ADIDAS | 0902652229-1 KD5830 | BLACK | 105D | F2525M009 | 154 | 2026-08-09 | 154 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2-SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652229 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 154 | 154 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-01-07 | 2026-10-07 | 154 | 154
ADIDAS | 0902652258-1 KD5830 | BLACK | 105D | F2525M009 | 1514 | 31/08/2026 | 1514 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2 SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652258 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 22/07/2026 | 15/07/2026 | 21/07/2026 | 1514 | 1514 |  |  |  | 2026-10-07 | 17/07/2026 | 2026-01-07 | 17/07/2026 | 1514 | 1514
ADIDAS | 0902652411-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652411 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 24/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652437-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652437 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652462-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 205 | 30/09/2026 | 205 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652462 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 15/07/2026 | 205 | 205
ADIDAS | 0902652495-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 241 | 30/09/2026 | 241 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652495 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 30/07/2026 | 20/07/2026 | 29/07/2026 | 241 | 241 |  |  |  | 15/07/2026 | 27/07/2026 | 15/07/2026 | 23/07/2026 | 241 | 241
ADIDAS | 0902685475-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 780 | 21/08/2026 | 780 | AT | AT04/03/2026 | G2P | SWEATSHIRT | G2 | ok | (28/03/2026) | 21/08: ex-fty 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902685475 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 16/07/2026 | M 3S FT SWT |  | FW26 | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 780 | 780 |  |  |  | 13/07/2026 | 21/07/2026 | 15/07/2026 | 22/07/2026 | 780 | 780
ADIDAS | 0902757486-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1201 | 21/08/2026 | 1201 | SA | SA27/03/2026 | G3D | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 30-Jun, actual receives 31-May. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902757486 JM1775 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M SL WV PT 2 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 1201 | 1201 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-11-07 | 17/07/2026 | 1201 | 1201
ADIDAS | 0902758851-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 370 | 28/08/2026 | 370 | AT | AT27/03/2026 | G3C | PANTS | G3 | ok | (20/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902758851 JD5302 | 16/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S FT CF PT |  | FW26 | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 370 | 370 |  |  |  | 23/07/2026 | 30/07/2026 | 22/07/2026 | 30/07/2026 | 370 | 370
ADIDAS | 0902760350-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 1199 | 21/08/2026 | 1199 | AT | AT27/03/2026 | G1C | JACKET | G1 | ok | (20/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 27-Jun, actual receives 29-Apr. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902760350 JM1772 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M SL WV TT |  | FW26 | 14/07/2026 | 20/07/2026 | 15/07/2026 | 20/07/2026 | 1199 | 1199 |  |  |  | 2026-09-07 | 15/07/2026 | 13/07/2026 | 17/07/2026 | 1199 | 1199
ADIDAS | 0902760456-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 800 | 21/08/2026 | 800 | SA | SA27/03/2026 | G3D | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 30-Jun, actual receives 03-Jun. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902760456 JM1776 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M SL WV PT 2 |  | FW26 | 21/07/2026 | 24/07/2026 | 20/07/2026 | 22/07/2026 | 800 | 800 |  |  |  | 16/07/2026 | 21/07/2026 | 2026-11-07 | 22/07/2026 | 800 | 800
ADIDAS | 0902760499-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1205 | 21/08/2026 | 1205 | SA | SA27/03/2026 | G3F | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902760499 IN6163 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 23/07/2026 | 20/07/2026 | 22/07/2026 | 1205 | 1205 |  |  |  | 15/07/2026 | 20/07/2026 | 2026-06-07 | 14/07/2026 | 1205 | 1205
ADIDAS | 0902763183-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 480 | 21/08/2026 | 480 | SI | SI27/03/2026 | G2T | SWEATSHIRT | G2 | ok | (16/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902763183 JE8949 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M BL FT SWT |  | FW26 | 21/07/2026 | 28/07/2026 | 22/07/2026 | 24/07/2026 | 480 | 480 |  |  |  | 16/07/2026 | 23/07/2026 | 21/07/2026 | 22/07/2026 | 480 | 480
ADIDAS | 0902763228-1 JM1773 | DARK BLUE/WHITE | 90D | F2554MESS712WV-MTF | 799 | 21/08/2026 | 799 | NT | NT27/03/2026 | G1C | JACKET | G1 | ok | (15/04/2026) | 21/08: ex-fty. T2 Libolon, using fabric stock. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902763228 JM1773 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 28/07/2026 | 17/07/2026 | 27/07/2026 | 799 | 799 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 24/07/2026 | 799 | 799
ADIDAS | 0902763261-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 804 | 21/08/2026 | 804 | SA | SA27/03/2026 | G3F | PANTS | G3 | ok | (16/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902763261 JE8969 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 15/07/2026 | M BL FT PT |  | FW26 | 15/07/2026 | 20/07/2026 | 16/07/2026 | 20/07/2026 | 804 | 804 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-02-07 | 2026-11-07 | 804 | 804
ADIDAS | 0902764900-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1G,G1I,G1K | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902764900 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/07/2026 | LFC A F JSY SE |  | FW26-FJ | 23/07/2026 | 21/08/2026 | 23/07/2026 | 14/08/2026 | 15000 | 15000 |  |  |  | 20/07/2026 | 18/08/2026 | 13/07/2026 | 13/08/2026 | 15000 | 15000
ADIDAS | 0902765031-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1O,G1P,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902765031 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/07/2026 | LFC A F JSY SE |  | FW26-FJ | 23/07/2026 | 2026-07-08 | 23/07/2026 | 2026-06-08 | 15000 | 15000 |  |  |  | 20/07/2026 | 2026-04-08 | 18/07/2026 | 13/08/2026 | 15000 | 15000
ADIDAS | 0902767490-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1O,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767490 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/07/2026 | LFC A F JSY SE |  | FW26-FJ | 29/07/2026 | 20/08/2026 | 29/07/2026 | 14/08/2026 | 15000 | 15000 |  |  |  | 24/07/2026 | 14/08/2026 | 20/07/2026 | 14/08/2026 | 15000 | 15000
ADIDAS | 0902767515-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1N,G1O,G1P,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767515 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | LFC A F JSY SE |  | FW26-FJ | 2026-03-08 | 19/08/2026 | 2026-03-08 | 18/08/2026 | 15000 | 15000 |  |  |  | 29/07/2026 | 13/08/2026 | 25/07/2026 | 18/08/2026 | 15000 | 15000
ADIDAS | 0902767538-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1O,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767538 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | LFC A F JSY SE |  | FW26-FJ | 2026-03-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 15000 | 15000 |  |  |  | 29/07/2026 | 13/08/2026 | 25/07/2026 | 19/08/2026 | 15000 | 15000
ADIDAS | 0902767561-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 12788 | 28/08/2026 | 12788 | AT | AT27/03/2026 | G1A,G1E,G1G,G1K,G1M | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767561 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/07/2026 | LFC A F JSY SE |  | FW26-FJ | 28/07/2026 | 18/08/2026 | 24/07/2026 | 18/08/2026 | 12788 | 12788 |  |  |  | 23/07/2026 | 2026-12-08 | 13/07/2026 | 13/08/2026 | 12788 | 12788
ADIDAS | 0902769872-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 4240 | 2026-05-09 | 4240 | AT | AT27/03/2026 | G1P,G1Q,G1R | T-SHIRT | G1 | ok | ok | 04/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902769872 LE8199 | 16/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-08 | LFC A F JSY SE |  | FW26-FJ | 2026-05-08 | 19/08/2026 | 2026-10-08 | 18/08/2026 | 4240 | 4240 |  |  |  | 31/07/2026 | 13/08/2026 | 31/07/2026 | 18/08/2026 | 4240 | 4240
ADIDAS | 0902803294-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV-MTF | 233 | 2026-05-09 | 233 | NT | NT10/04/2026 | G3D | PANTS | G3 | ok | (08/05/2026) | 05/09: ex-fty. T2 Libolon, PI Date 21-Jun, actual receives 22-May. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902803294 JM1778 | 30/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | M SL WV PT 1 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 17/07/2026 | 233 | 233 |  |  |  | 2026-09-07 | 16/07/2026 | 13/07/2026 | 17/07/2026 | 233 | 233
ADIDAS | 0902803647-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 15/09/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 14/09: ex-fty (NYK warehouse). T2 Kahatex, PI Date 09-May, actual reiceves 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803647 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 15/09/2026 | 2026-07-08 | 2026-11-09 | 100 | 90 | 10 |  |  | 2026-03-08 | 2026-11-09 | 22/07/2026 | 2026-05-08 | 100 | 100
ADIDAS | 0902803818-1 KF9922 | TEAM COLL BURGUNDY 2 | 90D | F2606CHMU042 | 377 | 2026-08-09 | 377 | AN | AN10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 08/09: ex-fty (NYK warehouse). T2 Kahatex, material quality issues (creasemark), PI Date 09-May, actual receives 17-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L2+EMBRO SUB PROCESS_V3 | 0902803818 KF9922 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | MUFC LF TEE |  | FW26 | 27/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 377 | 377 |  |  |  | 22/07/2026 | 30/07/2026 | 21/07/2026 | 28/07/2026 | 377 | 377
ADIDAS | 0902803854-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 15/10/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803854 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-04-08 | LFC LF TEE |  | FW26 | 2026-04-08 | 2026-01-09 | 2026-05-08 | 2026-02-09 | 100 | 100 |  |  |  | 30/07/2026 | 28/08/2026 | 22/07/2026 | 2026-02-09 | 100 | 100
ADIDAS | 0902803922-1 KG2924 | BLACK | 90D | F2606CHLF041 | 200 | 15/10/2026 | 200 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803922 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 2026-04-09 | 2026-06-08 | 2026-03-09 | 200 | 200 |  |  |  | 2026-03-08 | 2026-01-09 | 23/07/2026 | 2026-05-08 | 200 | 200
ADIDAS | 0902804254-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 4267 | 2026-05-09 | 4267 | SA | SA10/04/2026 | G2L,G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 04/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804254 LE8211 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 29/08/2026 | 2026-04-09 | 4267 | 4267 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-04-09 | 4267 | 4267
ADIDAS | 0902804280-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 5861 | 28/08/2026 | 5861 | SI | SI10/04/2026 | G2O | T-SHIRT | G2 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804280 LE8190 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 22/07/2026 | 2026-10-08 | 22/07/2026 | 2026-05-08 | 5861 | 5861 |  |  |  | 17/07/2026 | 2026-05-08 | 2026-11-07 | 24/07/2026 | 5861 | 5861
ADIDAS | 0902804314-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 15000 | 28/08/2026 | 15000 | SI | SI10/04/2026 | G2K,G2M,G2O | T-SHIRT | G2 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804314 LE8190 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 22/07/2026 | 13/08/2026 | 22/07/2026 | 2026-12-08 | 15000 | 15000 |  |  |  | 17/07/2026 | 2026-10-08 | 18/07/2026 | 2026-10-08 | 15000 | 15000
ADIDAS | 0902804368-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 12412 | 2026-05-09 | 12412 | AT | AT10/04/2026 | G1Q,G2K,G2L,G2M,G2O | T-SHIRT | G1,G2 | ok | ok | 05/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804368 LE5779 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSY SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 12412 | 12412 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-01-09 | 2026-05-09 | 12412 | 12412
ADIDAS | 0902804483-1 KG2924 | BLACK | 90D | F2606CHLF041 | 1015 | 21/08/2026 | 1015 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 814006 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902804483 KG2924 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 22/07/2026 | LFC LF TEE |  | FW26 | 22/07/2026 | 29/07/2026 | 22/07/2026 | 29/07/2026 | 1015 | 1015 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 29/07/2026 | 1015 | 1015
ADIDAS | 0902806140-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 739 | 21/08/2026 | 739 | AT | AT10/04/2026 | G3D | PANTS | G3 | ok | (29/04/2026) | 21/08: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902806140 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 29/07/2026 | 22/07/2026 | 27/07/2026 | 739 | 739 |  |  |  | 16/07/2026 | 24/07/2026 | 2026-07-07 | 18/07/2026 | 739 | 739
ADIDAS | 0902806727-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 150 | 21/08/2026 | 150 | AT | AT10/04/2026 | G2P | SWEATSHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902806727 KG2925 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 20/07/2026 | LFC LF HD |  | FW26 | 20/07/2026 | 28/07/2026 | 23/07/2026 | 27/07/2026 | 150 | 150 |  |  |  | 15/07/2026 | 23/07/2026 | 20/07/2026 | 27/07/2026 | 150 | 150
ADIDAS | 0902807370-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1F,G1P,G1Q | T-SHIRT | G1 | ok | ok | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902807370 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC H F JSY SE |  | FW26-FJ | 14/07/2026 | 30/07/2026 | 15/07/2026 | 29/07/2026 | 15000 | 15000 |  |  |  | 2026-09-07 | 27/07/2026 | 14/07/2026 | 29/07/2026 | 15000 | 15000
ADIDAS | 0902807414-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 6387 | 21/08/2026 | 6387 | AT | AT10/04/2026 | G2M | T-SHIRT | G2 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902807414 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 31/07/2026 | LFC H F JSY SE |  | FW26-FJ | 31/07/2026 | 20/08/2026 | 31/07/2026 | 14/08/2026 | 6387 | 6387 |  |  |  | 28/07/2026 | 14/08/2026 | 28/07/2026 | 20/08/2026 | 6387 | 6387
ADIDAS | 0902808177-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 3220 | 2026-12-09 | 3220 | AT | AT10/04/2026 | G3C,G3D,G3E | PANTS | G3 | ok | (29/04/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902808177 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 3220 | 3220 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 2026-01-08 | 3220 | 3217 | 3
ADIDAS | 0902808402-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1A,G1G,G1I,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808402 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 30/07/2026 | LFC H F JSY SE |  | FW26-FJ | 30/07/2026 | 21/08/2026 | 2026-06-08 | 21/08/2026 | 15000 | 15000 |  |  |  | 27/07/2026 | 18/08/2026 | 31/07/2026 | 20/08/2026 | 15000 | 15000
ADIDAS | 0902808430-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 11421 | 21/08/2026 | 11421 | AN | AN10/04/2026 | G1F,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808430 LE8192 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-07 | AFC H F JSY SE |  | FW26-FJ | 2026-10-07 | 27/07/2026 | 2026-09-07 | 27/07/2026 | 11421 | 11421 |  |  |  | 2026-07-07 | 22/07/2026 | 2026-06-07 | 24/07/2026 | 11421 | 11421
ADIDAS | 0902808466-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 15000 | 21/08/2026 | 15000 | SI | SI10/04/2026 | G2G,G2K,G2N,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808466 LE8190 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 13/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 13/07/2026 | 2026-03-08 | 2026-10-07 | 29/07/2026 | 15000 | 15000 |  |  |  | 2026-08-07 | 29/07/2026 | 2026-06-07 | 24/07/2026 | 15000 | 15000
ADIDAS | 0902808499-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 6436 | 21/08/2026 | 6436 | SI | SI10/04/2026 | G1A | T-SHIRT | G1 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808499 LE8190 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-07 | MUFC H F JSY SE |  | FW26-FJ | 2026-07-07 | 28/07/2026 | 2026-09-07 | 24/07/2026 | 6436 | 6436 |  |  |  | 2026-02-07 | 23/07/2026 | 2026-03-07 | 17/07/2026 | 6436 | 6436
ADIDAS | 0902808529-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 5899 | 21/08/2026 | 5899 | SA | SA10/04/2026 | G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808529 LE8211 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 31/07/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/07/2026 | 21/08/2026 | 31/07/2026 | 18/08/2026 | 5899 | 5899 |  |  |  | 28/07/2026 | 18/08/2026 | 29/07/2026 | 18/08/2026 | 5899 | 5899
ADIDAS | 0902808575-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 7472 | 21/08/2026 | 7472 | AT | AT10/04/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808575 LE8199 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC A F JSY SE |  | FW26-FJ | 14/07/2026 | 2026-03-08 | 16/07/2026 | 29/07/2026 | 7472 | 7472 |  |  |  | 2026-09-07 | 29/07/2026 | 2026-09-07 | 29/07/2026 | 7472 | 7472
ADIDAS | 0902808623-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | (09/05/2026) | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808623 LE8199 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC A F JSY SE |  | FW26-FJ | 14/07/2026 | 2026-03-08 | 14/07/2026 | 27/07/2026 | 15000 | 15000 |  |  |  | 2026-09-07 | 29/07/2026 | 2026-07-07 | 29/07/2026 | 15000 | 15000
ADIDAS | 0902808893-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 11609 | 28/08/2026 | 11609 | AN | AN10/04/2026 | G1A,G1F,G1I,G1Q | T-SHIRT | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902808893 LE8192 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 27/07/2026 | AFC H F JSY SE |  | FW26-FJ | 27/07/2026 | 14/08/2026 | 21/07/2026 | 14/08/2026 | 11609 | 11609 |  |  |  | 22/07/2026 | 2026-11-08 | 14/07/2026 | 2026-05-08 | 11609 | 11609
ADIDAS | 0902810670-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 28/08/2026 | 15000 | AT | AT10/04/2026 | G2K,G2L,G2M,G2O | T-SHIRT | G2 | ok | (08/05/2026) | 28/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902810670 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-08 | LFC H F JSY SE |  | FW26-FJ | 2026-07-08 | 28/08/2026 | 2026-10-08 | 29/08/2026 | 15000 | 15000 |  |  |  | 2026-04-08 | 24/08/2026 | 2026-06-08 | 28/08/2026 | 15000 | 15000
ADIDAS | 0902847822-1 JE3837 | BLACK/WHITE | 90D | S2554MESS682FT | 1348 | 2026-05-09 | 1348 | AT | AT24/04/2026 | G2T | SWEATSHIRT | G2 | ok | (14/05/2026) | 05/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847822 JE3837 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M FEELCOZY SWT |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 21/07/2026 | 1348 | 1348 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-10-07 | 15/07/2026 | 1348 | 1348
ADIDAS | 0902847867-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 1491 | 2026-05-09 | 1491 | AT | AT24/04/2026 | G1D | PANTS | G1 | ok | ok | 04/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847867 JE3854 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M FEELCOZY PANT |  | FW26 | 21/07/2026 | 2026-05-08 | 23/07/2026 | 31/07/2026 | 1491 | 1491 |  |  |  | 16/07/2026 | 31/07/2026 | 18/07/2026 | 23/07/2026 | 1491 | 1491
ADIDAS | 0902850291-1 KF5291 | MAGIC LILAC S22 | 60D | S2608WR0910 | 144 | 20/08/2026 | 144 | SA | SA24/04/2026 | G2K | T-SHIRT | G2 | ok | ok | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L2+HT SUB PROCESS_V3 | 0902850291 KF5291 | 2026-12-06 | KAHATEX CIJERAH | URUGUAY | SEA | 26/06/2026 | Run Ess BL T W |  | FW26 | 26/06/2026 | 29/06/2026 | 26/06/2026 | 26/06/2026 | 144 | 144 |  |  |  | 23/06/2026 | 24/06/2026 | 2026-11-06 | 24/06/2026 | 144 | 144 |  |  |  | 22/06/2026 | 23/06/2026 | 2026-11-06 | 23/06/2026 | 144 | 144
ADIDAS | 0902853719-1 LE8209 | ACTIVE MAROON F19 | 90D | F2606LHLF101FYL | 5200 | 28/08/2026 | 5200 | SI | SI24/04/2026 | G1A,G1F | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902853719 LE8209 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | LFC HFY JSYL SE |  | FW26-FJ | 20/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 5200 | 5200 |  |  |  | 15/07/2026 | 27/07/2026 | 17/07/2026 | 30/07/2026 | 5200 | 5200
ADIDAS | 0902853964-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 81 | 15/10/2026 | 81 | AT | AT24/04/2026 | G2P | SWEATSHIRT | G2 | (22/05/2026) | (18/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902853964 KG2925 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-09 | LFC LF HD |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 81 | 81 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-11-08 | 2026-10-09 | 81 | 81
ADIDAS | 0902854036-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 29-May, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902854036 KA8777 | 28/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | TIRO26L SHO M |  | FW26-L2L | 14/07/2026 | 17/07/2026 | 14/07/2026 | 17/07/2026 | 132 | 132 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 16/07/2026 | 132 | 132 |  |  |  | 2026-07-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 132 | 132
ADIDAS | 0902854145-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 430 | 2026-05-09 | 430 | SI | SI24/04/2026 | G1D | JACKET | G1 | ok | ok | 04/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902854145 JE0052 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | W 3S FT FZ HD |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-06-08 | 2026-07-08 | 430 | 430 |  |  |  | 31/07/2026 | 2026-04-08 | 31/07/2026 | 2026-06-08 | 430 | 430
ADIDAS | 0902854237-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 481 | 23/09/2026 | 481 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/09: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854237 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 21/07/2026 | 2026-03-08 | 21/07/2026 | 31/07/2026 | 481 | 481 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 30/07/2026 | 481 | 481 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 23/07/2026 | 481 | 481
ADIDAS | 0902854269-1 KS0014 | WHITE | 90D | F26BMGFX210 | 102 | 20/08/2026 | 102 | SI | SI24/04/2026 | G2R | T-SHIRT | G2 | ok | (14/05/2026) | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L3+PAD SUB PROCESS_V3 | 0902854269 KS0014 | 14/07/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-10-07 | WWH UNITED T |  | FW26 | 2026-10-07 | 14/07/2026 | 13/07/2026 | 13/07/2026 | 102 | 102 |  |  |  | 2026-07-07 | 2026-09-07 | 2026-08-07 | 13/07/2026 | 102 | 102
ADIDAS | 0902854292-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 300 | 21/08/2026 | 300 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/08: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854292 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 15/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 300 | 300 |  |  |  | 2026-10-07 | 16/07/2026 | 2026-09-07 | 14/07/2026 | 300 | 300 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-09-07 | 14/07/2026 | 300 | 300
ADIDAS | 0902855664-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 12218 | 28/08/2026 | 12218 | AN | AN24/04/2026 | G1I | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902855664 LE5780 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-07 | LFC H FY JSY SE |  | FW26-FJ | 2026-10-07 | 30/07/2026 | 2026-10-07 | 30/07/2026 | 12218 | 12218 |  |  |  | 2026-07-07 | 27/07/2026 | 2026-10-07 | 30/07/2026 | 12218 | 12218
ADIDAS | 0902856132-1 KE8425 | WHITE | 60D | S2608MR0906A | 264 | 21/08/2026 | 264 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 21/08: ex-fty 516394 | HT+PAD SUB PROCESS_V3 | 0902856132 KE8425 | 2026-12-06 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/07/2026 | Run Ess LS M |  | FW26 | 16/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 264 | 264 |  |  |  | 13/07/2026 | 24/07/2026 | 2026-09-07 | 16/07/2026 | 264 | 264 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-09-07 | 16/07/2026 | 264 | 264
ADIDAS | 0902856344-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 301 | 28/08/2026 | 301 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516343 | EMBRO+HT+PPH L1 SUB PROCESS_V3 | 0902856344 IA7637 | 14/07/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | AFC LF HD |  | FW26 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 301 | 301 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-07-08 | 13/08/2026 | 301 | 301 |  |  |  | 29/07/2026 | 2026-05-08 | 2026-06-08 | 2026-12-08 | 301 | 301
ADIDAS | 0902856437-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 160 | 31/08/2026 | 160 | NT | NT24/04/2026 | G1E | T-SHIRT | G1 | ok | (11/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516443 | HT SUB PROCESS_V1 | 0902856437 IT1824 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 23/07/2026 | 160 | 160 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 20/07/2026 | 160 | 160 |  |  |  | 15/07/2026 | 23/07/2026 | 2026-10-07 | 20/07/2026 | 160 | 160
ADIDAS | 0902857447-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 11170 | 28/08/2026 | 11170 | AN | AN24/04/2026 | G1G,G1I | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902857447 LE8191 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/07/2026 | AFC H FY JSY SE |  | FW26-FJ | 30/07/2026 | 18/08/2026 | 30/07/2026 | 18/08/2026 | 11170 | 11170 |  |  |  | 27/07/2026 | 2026-12-08 | 28/07/2026 | 14/08/2026 | 11170 | 11170
ADIDAS | 0902857603-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 402 | 31/08/2026 | 402 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | EMBRO+HT+PPH L1+PPA SUB PROCESS_V3 | 0902857603 IA7637 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | AFC LF HD |  | FW26 | 24/07/2026 | 2026-07-08 | 24/07/2026 | 2026-04-08 | 402 | 402 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 2026-05-08 | 402 | 402 |  |  |  | 13/07/2026 | 27/07/2026 | 20/07/2026 | 31/07/2026 | 402 | 402
ADIDAS | 0902857630-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 818 | 31/08/2026 | 818 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | EMBRO+HT+PPH L1 SUB PROCESS_V3 | 0902857630 IA7637 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-08 | AFC LF HD |  | FW26 | 2026-07-08 | 18/08/2026 | 2026-10-08 | 18/08/2026 | 818 | 818 |  |  |  | 2026-04-08 | 2026-12-08 | 2026-07-08 | 15/08/2026 | 818 | 818 |  |  |  | 29/07/2026 | 2026-06-08 | 2026-07-08 | 15/08/2026 | 818 | 818
ADIDAS | 0902857874-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 12666 | 28/08/2026 | 12666 | SI | SI24/04/2026 | G1A,G2K,G2O | T-SHIRT | G1,G2 | (22/05/2026) | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902857874 LE8189 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | MUFC HFY JSY SE |  | FW26-FJ | 2026-03-08 | 21/08/2026 | 2026-03-08 | 18/08/2026 | 12666 | 12666 |  |  |  | 29/07/2026 | 18/08/2026 | 28/07/2026 | 15/08/2026 | 12666 | 12666
ADIDAS | 0902857895-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 728 | 31/08/2026 | 728 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Gistex, PI Date 15-Jun, actual receives 24-Jul. T2 Formosa, PI Date 24-May, actual receives 20-Jun. T2 Kahatex, PI Date 22-May, actual receives 12-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902857895 KY4155 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 728 | 728 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-11-08 | 2026-02-09 | 728 | 727 | 1
ADIDAS | 0902857969-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1590 | 31/08/2026 | 1590 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Gistex, PI Date 15-Jun, actual receives 15-Jul. T2 Kahatex, PI Date 22-May, actual receives 02-Jul. T2 Formosa, PI Date 24-May, actual receives 20-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902857969 KY6510 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-08 | M 3S CHELSEA B7 |  | SS27 | 2026-12-08 | 29/08/2026 | 2026-12-08 | 29/08/2026 | 1590 | 1590 |  |  |  | 2026-07-08 | 26/08/2026 | 2026-07-08 | 2026-09-09 | 1590 | 1580 | 10
ADIDAS | 0902858585-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 114 | 2026-08-09 | 114 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858585 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 31/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 31/07/2026 | 2026-07-08 | 31/07/2026 | 2026-03-08 | 114 | 114 |  |  |  | 28/07/2026 | 2026-04-08 | 17/07/2026 | 28/07/2026 | 114 | 114
ADIDAS | 0902858612-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 777 | 30/09/2026 | 777 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858612 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 22/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 22/07/2026 | 2026-07-08 | 22/07/2026 | 2026-03-08 | 777 | 777 |  |  |  | 17/07/2026 | 2026-04-08 | 16/07/2026 | 21/07/2026 | 777 | 777
ADIDAS | 0902858673-1 KE8425 | WHITE | 60D | S2608MR0906A | 458 | 21/08/2026 | 458 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 21/08: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902858673 KE8425 | 2026-12-06 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess LS M |  | FW26 | 22/07/2026 | 29/07/2026 | 20/07/2026 | 27/07/2026 | 458 | 458 |  |  |  | 17/07/2026 | 24/07/2026 | 2026-10-07 | 24/07/2026 | 458 | 458 |  |  |  | 15/07/2026 | 22/07/2026 | 2026-10-07 | 24/07/2026 | 458 | 458
ADIDAS | 0902858704-1 KE8425 | WHITE | 60D | S2608MR0906A | 302 | 31/08/2026 | 302 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | HT+PAD SUB PROCESS_V3 | 0902858704 KE8425 | 2026-12-06 | KAHATEX CIJERAH | ITALY | SEA | 16/07/2026 | Run Ess LS M |  | FW26 | 16/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 302 | 302 |  |  |  | 13/07/2026 | 24/07/2026 | 2026-09-07 | 22/07/2026 | 302 | 302 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-09-07 | 22/07/2026 | 302 | 302
ADIDAS | 0902860131-1 JZ7808 | BLACK | 60D | S2608WR0900 | 341 | 31/08/2026 | 341 | AT | AT24/04/2026 | G2J | T-SHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | HT+PAD SUB PROCESS_V3 | 0902860131 JZ7808 | 2026-12-06 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | Run Ess Tee W |  | FW26 | 20/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 341 | 341 |  |  |  | 15/07/2026 | 22/07/2026 | 14/07/2026 | 22/07/2026 | 341 | 341 |  |  |  | 13/07/2026 | 20/07/2026 | 14/07/2026 | 22/07/2026 | 341 | 341
ADIDAS | 0902860651-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 169 | 28/08/2026 | 169 | SI | SI24/04/2026 | G1L,G3C | SHORTS | G1,G3 | ok | (04/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, PI Date 07-Jun, actual receives 23-Jun. 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902860651 LD5435 | 28/07/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 169 | 169 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 169 | 169
ADIDAS | 0902860692-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 101 | 2026-08-09 | 101 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860692 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 101 | 101 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-10-07 | 14/07/2026 | 101 | 101
ADIDAS | 0902860750-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 486 | 30/09/2026 | 486 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860750 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 486 | 486 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-09-07 | 14/07/2026 | 486 | 486
ADIDAS | 0902860782-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 205 | 2026-08-09 | 205 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860782 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 31/07/2026 | 21/07/2026 | 31/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 28/07/2026 | 17/07/2026 | 21/07/2026 | 205 | 205
ADIDAS | 0902860813-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 104 | 31/08/2026 | 104 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860813 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 22/07/2026 | 20/07/2026 | 21/07/2026 | 104 | 104 |  |  |  | 15/07/2026 | 17/07/2026 | 16/07/2026 | 17/07/2026 | 104 | 104
ADIDAS | 0902861800-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 274 | 31/08/2026 | 274 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok | (04/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902861800 LD5435 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 29/07/2026 | 2026-06-08 | 31/07/2026 | 2026-06-08 | 274 | 274 |  |  |  | 24/07/2026 | 2026-03-08 | 24/07/2026 | 2026-04-08 | 274 | 274
ADIDAS | 0902862442-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 318 | 28/08/2026 | 318 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok | (04/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862442 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-03-08 | 2026-07-08 | 31/07/2026 | 2026-12-08 | 318 | 318 |  |  |  | 29/07/2026 | 2026-04-08 | 23/07/2026 | 2026-11-08 | 318 | 318
ADIDAS | 0902882925-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 317 | 21/08/2026 | 317 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902882925 KD0677 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 317 | 317 |  |  |  | 2026-10-07 | 16/07/2026 | 14/07/2026 | 15/07/2026 | 317 | 317 |  |  |  | 2026-03-07 | 2026-09-07 | 13/07/2026 | 15/07/2026 | 317 | 317
ADIDAS | 0902887724-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 359 | 2026-05-09 | 359 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 28-May, using fabric stock. 516400 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887724 KD0677 | 22/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 359 | 359 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 29/07/2026 | 359 | 359 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 25/07/2026 | 359 | 359
ADIDAS | 0902899919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 502 | 2026-05-09 | 502 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899919 LD0288 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 31/07/2026 | 502 | 502 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502
ADIDAS | 0902899965-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899965 LD0287 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 369 | 369 |  |  |  | 2026-06-08 | 28/08/2026 | 2026-01-08 | 2026-08-08 | 369 | 369 |  |  |  | 2026-04-08 | 26/08/2026 | 27/07/2026 | 2026-07-08 | 369 | 369
ADIDAS | 0902900004-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 2400 | 21/08/2026 | 2400 | AN | AN15/05/2026 | G1H | JACKET | G1 | ok | (05/06/2026) | 21/08: ex-fty. T2 Kahatex, PI Date 13-Jun, actua receives 04-Aug. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902900004 KV8005 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/07/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 30/07/2026 | 19/08/2026 | 30/07/2026 | 20/08/2026 | 2400 | 2400 |  |  |  | 27/07/2026 | 13/08/2026 | 27/07/2026 | 20/08/2026 | 2400 | 2400
ADIDAS | 0902900128-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1800 | 31/08/2026 | 1800 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902900128 LE5390 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/07/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 1800 | 1800 |  |  |  | 13/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 1800 | 1800
ADIDAS | 0902900771-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 327 | 2026-05-09 | 327 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900771 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 327 | 327 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-02-09 | 327 | 327 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-02-09 | 327 | 327
ADIDAS | 0902900873-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 347 | 2026-05-09 | 347 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902900873 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 31/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-05-08 | 347 | 347
ADIDAS | 0902900896-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 326 | 21/08/2026 | 326 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0902900896 LD0285 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 22/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 326 | 326 |  |  |  | 17/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 326 | 326 |  |  |  | 15/07/2026 | 22/07/2026 | 16/07/2026 | 24/07/2026 | 326 | 326
ADIDAS | 0902900910-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 337 | 2026-07-10 | 337 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900910 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 337 |  | 337 |  |  | 25/09/2026 | 26/09/2026 | 2026-04-08 | 2026-10-08 | 337 | 337 |  |  |  | 23/09/2026 | 24/09/2026 | 2026-01-08 | 2026-10-08 | 337 | 337
ADIDAS | 0902900938-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 358 | 30/09/2026 | 358 | AN | AN15/05/2026 | G2E | T-SHIRT | G2 | ok | (05/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900938 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 358 |  | 358 |  |  | 16/09/2026 | 17/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358 |  |  |  | 14/09/2026 | 15/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358
ADIDAS | 0902900970-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 2026-05-09 | 306 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902900970 KG3225 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-06-08 | 306 | 306 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 306 | 306 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 306 | 306
ADIDAS | 0902900989-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 741 | 2026-05-09 | 741 | AN | AN15/05/2026 | G2H | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900989 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 741 | 741 |  |  |  | 31/08/2026 | 2026-02-09 | 28/08/2026 | 2026-04-09 | 741 | 741 |  |  |  | 28/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 741 | 741
ADIDAS | 0902901030-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 309 | 31/08/2026 | 309 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0902901030 KX3650 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 309 | 309 |  |  |  | 16/07/2026 | 23/07/2026 | 16/07/2026 | 27/07/2026 | 309 | 309 |  |  |  | 14/07/2026 | 21/07/2026 | 16/07/2026 | 27/07/2026 | 309 | 309
ADIDAS | 0902901306-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 306 | 26/08/2026 | 306 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 18-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. T2 Libolon, PI Date 19-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901306 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 24/08/2026 | 2026-03-08 | 20/08/2026 | 306 | 306 |  |  |  | 29/07/2026 | 19/08/2026 | 28/07/2026 | 20/08/2026 | 306 | 306
ADIDAS | 0902901357-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 410 | 2026-09-09 | 410 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901357 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-07-08 | 2026-03-09 | 410 | 410 |  |  |  | 2026-03-08 | 2026-04-09 | 2026-04-08 | 2026-03-09 | 410 | 410
ADIDAS | 0902901389-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 377 | 2026-09-09 | 377 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901389 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-06-08 | 2026-03-09 | 377 | 377 |  |  |  | 2026-03-08 | 2026-04-09 | 30/07/2026 | 2026-05-09 | 377 | 377
ADIDAS | 0902901486-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 383 | 26/08/2026 | 383 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901486 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/07/2026 | M 3S WV WB LND |  | FW26 | 30/07/2026 | 24/08/2026 | 30/07/2026 | 20/08/2026 | 383 | 383 |  |  |  | 27/07/2026 | 19/08/2026 | 27/07/2026 | 21/08/2026 | 383 | 383
ADIDAS | 0902901531-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 312 | 2026-09-09 | 312 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | ok | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901531 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 2026-08-09 | 2026-10-08 | 2026-07-09 | 312 | 312 |  |  |  | 2026-05-08 | 2026-04-09 | 2026-05-08 | 2026-01-09 | 312 | 312
ADIDAS | 0902901569-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 507 | 2026-09-09 | 507 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901569 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-08-09 | 507 | 507 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 2026-02-09 | 507 | 507
ADIDAS | 0902901687-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4200 | 21/08/2026 | 4200 | AN | AN15/05/2026 | G3A | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901687 LE7510 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 21/07/2026 | 2026-04-08 | 20/07/2026 | 28/07/2026 | 4200 | 4200 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 28/07/2026 | 4200 | 4200
ADIDAS | 0902901795-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3000 | 21/08/2026 | 3000 | AN | AN15/05/2026 | G3A | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901795 LE7508 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/07/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 27/07/2026 | 14/08/2026 | 24/07/2026 | 2026-12-08 | 3000 | 3000 |  |  |  | 22/07/2026 | 2026-11-08 | 23/07/2026 | 2026-11-08 | 3000 | 3000
ADIDAS | 0902901874-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 6443 | 30/09/2026 | 6443 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 24/09: ex-fty. T2 Libolon, PI Date 09-Jun, actual receives 09-Jul. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901874 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 13/08/2026 | 17/09/2026 | 2026-12-08 | 14/09/2026 | 6443 | 4570 | 1873 |  | 320 | 2026-10-08 | 14/09/2026 | 31/07/2026 | 2026-11-09 | 6443 | 5827 | 616
ADIDAS | 0902901925-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 791 | 31/08/2026 | 791 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 29/08: ex-fty. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 29-May. T2 Libolon, PI Date 09-Jun, actual receives 18-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901925 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 28/07/2026 | 13/08/2026 | 28/07/2026 | 14/08/2026 | 791 | 791 |  |  |  | 23/07/2026 | 2026-10-08 | 25/07/2026 | 15/08/2026 | 791 | 791
ADIDAS | 0902902811-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 317 | 15/09/2026 | 317 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902811 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 317 | 317 |  |  |  | 2026-06-08 | 28/08/2026 | 23/07/2026 | 2026-05-08 | 317 | 317 |  |  |  | 2026-04-08 | 26/08/2026 | 22/07/2026 | 2026-04-08 | 317 | 317
ADIDAS | 0902902836-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 595 | 15/09/2026 | 595 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902836 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 595 | 588 | 7 |  |  | 2026-02-09 | 2026-11-09 | 24/08/2026 | 2026-08-09 | 595 | 595 |  |  |  | 31/08/2026 | 2026-09-09 | 24/08/2026 | 2026-08-09 | 595 | 595
ADIDAS | 0902902865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902902865 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 2026-04-08 | 22/07/2026 | 31/07/2026 | 369 | 369 |  |  |  | 16/07/2026 | 30/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369 |  |  |  | 14/07/2026 | 28/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369
ADIDAS | 0902902891-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 15/09/2026 | 322 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902891 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-10-08 | 2026-01-09 | 322 | 322 |  |  |  | 2026-06-08 | 29/08/2026 | 22/07/2026 | 2026-07-08 | 322 | 322 |  |  |  | 2026-04-08 | 27/08/2026 | 22/07/2026 | 2026-06-08 | 322 | 322
ADIDAS | 0902902948-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1044 | 2026-05-09 | 1044 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902902948 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 1044 | 1044 |  |  |  | 27/08/2026 | 2026-02-09 | 21/08/2026 | 2026-01-09 | 1044 | 1044 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 1044 | 1044
ADIDAS | 0902902967-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 455 | 31/08/2026 | 455 | SI | SI15/05/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902902967 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 455 | 455 |  |  |  | 20/08/2026 | 27/08/2026 | 2026-04-08 | 31/08/2026 | 455 | 455
ADIDAS | 0902902973-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 30/09/2026 | 880 | SA | SA15/05/2026 | G2M | T-SHIRT | G2 | ok | (08/06/2026) | 23/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902902973 KX3655 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 880 |  | 880 |  |  | 19/09/2026 | 21/09/2026 | 26/08/2026 | 2026-09-09 | 880 | 579 | 301 |  |  | 17/09/2026 | 18/09/2026 | 21/08/2026 | 2026-09-09 | 880 | 579 | 301
ADIDAS | 0902903099-1 KE8425 | WHITE | 120D | S2608MR0906A | 305 | 2026-07-10 | 305 | SI | SI15/05/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516333 | HT+PAD SUB PROCESS_V3 | 0902903099 KE8425 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | Run Ess LS M WHITE |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 305 |  | 305 |  |  | 30/09/2026 | 2026-01-10 | 13/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 28/09/2026 | 29/09/2026 | 2026-11-08 | 27/08/2026 | 305 | 305
ADIDAS | 0902904399-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 172 | 31/08/2026 | 172 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 26-Jun, actual receives 18-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. T2 Libolon, PI Date 19-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902904399 KY4221 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 31/08/2026 | 2026-11-08 | 31/08/2026 | 172 | 172 |  |  |  | 2026-05-08 | 27/08/2026 | 2026-06-08 | 31/08/2026 | 172 | 172
ADIDAS | 0902904515-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 339 | 2026-05-09 | 339 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904515 LD0287 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 339 | 339 |  |  |  | 2026-06-08 | 29/08/2026 | 2026-01-08 | 31/08/2026 | 339 | 339 |  |  |  | 2026-04-08 | 27/08/2026 | 27/07/2026 | 31/08/2026 | 339 | 339
ADIDAS | 0902904537-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 329 | 15/09/2026 | 329 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904537 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 329 | 329 |  |  |  | 2026-06-08 | 29/08/2026 | 31/07/2026 | 2026-10-08 | 329 | 329 |  |  |  | 2026-04-08 | 27/08/2026 | 30/07/2026 | 2026-10-08 | 329 | 329
ADIDAS | 0902904602-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 696 | 2026-05-09 | 696 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904602 LD0284 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 696 | 696 |  |  |  | 28/07/2026 | 28/08/2026 | 27/07/2026 | 2026-01-08 | 696 | 696 |  |  |  | 24/07/2026 | 26/08/2026 | 25/07/2026 | 2026-01-08 | 696 | 696
ADIDAS | 0902904645-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 309 | 2026-05-09 | 309 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902904645 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 309 | 309 |  |  |  | 28/07/2026 | 28/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309 |  |  |  | 24/07/2026 | 26/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309
ADIDAS | 0902905667-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 530 | 23/09/2026 | 530 | SA | SA15/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902905667 LD0285 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 27/07/2026 | 21/08/2026 | 27/07/2026 | 20/08/2026 | 530 | 530 |  |  |  | 22/07/2026 | 18/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530 |  |  |  | 20/07/2026 | 13/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530
ADIDAS | 0902905691-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 336 | 2026-12-09 | 336 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902905691 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 24/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 336 | 336 |  |  |  | 21/07/2026 | 24/07/2026 | 16/07/2026 | 23/07/2026 | 336 | 336 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 336 | 336
ADIDAS | 0902906172-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 45 | 28/08/2026 | 45 | AT | AT15/05/2026 | G2P | SWEATSHIRT | G2 | (13/06/2026) | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 839055 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902906172 KG2925 | 31/07/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-08 | LFC LF HD |  | FW26 | 2026-07-08 | 2026-12-08 | 2026-10-08 | 2026-10-08 | 45 | 45 |  |  |  | 2026-04-08 | 2026-07-08 | 2026-08-08 | 2026-10-08 | 45 | 45
ADIDAS | 0902906579-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 15 | 23/09/2026 | 15 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902906579 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15 |  |  |  | 21/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15
ADIDAS | 0902906608-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 1321 | 15/09/2026 | 1321 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿) , PI Date 30-Jun, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902906608 LG9669 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-04-09 | W SL WV SK BLACK |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-04-09 | 2026-07-09 | 1321 | 1136 | 185 |  |  | 2026-01-09 | 2026-11-09 | 22/08/2026 | 2026-11-09 | 1321 | 1276 | 45
ADIDAS | 0902906662-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 324 | 2026-05-09 | 324 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906662 LD0288 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 30/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 30/07/2026 | 20/07/2026 | 31/07/2026 | 324 | 324 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 324 | 324
ADIDAS | 0902906685-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 961 | 30/09/2026 | 961 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906685 LD0287 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 16/09/2026 |  |  | 961 |  | 961 |  |  | 2026-12-09 | 2026-12-09 | 31/07/2026 | 2026-06-08 | 961 | 961 |  |  |  | 2026-10-09 | 2026-10-09 | 30/07/2026 | 2026-06-08 | 961 | 961
ADIDAS | 0902906698-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 3281 | 2026-05-09 | 3281 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0902906698 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 21/08/2026 | 2026-05-09 | 21/08/2026 | 2026-04-09 | 3281 | 3281 |  |  |  | 18/08/2026 | 2026-02-09 | 13/08/2026 | 2026-01-09 | 3281 | 3281 |  |  |  | 13/08/2026 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 3281 | 3281
ADIDAS | 0902906708-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 360 | 15/09/2026 | 360 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902906708 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 2026-09-09 | 360 | 244 | 116 |  |  | 2026-02-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 360 | 360 |  |  |  | 31/08/2026 | 2026-09-09 | 31/07/2026 | 2026-04-08 | 360 | 360
ADIDAS | 0902906721-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 797 | 2026-05-09 | 797 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906721 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 797 | 797 |  |  |  | 2026-12-08 | 29/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797
ADIDAS | 0902906734-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 328 | 2026-05-09 | 328 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902906734 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 328 | 328 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 328 | 328 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 31/07/2026 | 328 | 328
ADIDAS | 0902906748-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 319 | 30/09/2026 | 319 | SA | SA15/05/2026 | G2E | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906748 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 319 |  | 319 |  |  | 15/09/2026 | 16/09/2026 | 26/08/2026 | 2026-02-09 | 319 | 319 |  |  |  | 2026-12-09 | 14/09/2026 | 24/08/2026 | 2026-02-09 | 319 | 319
ADIDAS | 0902906766-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 322 | 28/08/2026 | 322 | AN | AN15/05/2026 | G1E | T-SHIRT | G1 | ok | (05/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, actual receives 29-Apr (PO booking 25063167). T2 Fu Hsun, actual receives 23-Apr (PO booking 25063168). 516342 | HT SUB PROCESS_V1 | 0902906766 IT1824 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 20/07/2026 | 322 | 322 |  |  |  | 14/07/2026 | 16/07/2026 | 14/07/2026 | 17/07/2026 | 322 | 322 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 16/07/2026 | 322 | 322
ADIDAS | 0902906789-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 779 | 2026-05-09 | 779 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906789 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-06-08 | 2026-01-09 | 779 | 779 |  |  |  | 2026-03-08 | 29/08/2026 | 25/07/2026 | 31/08/2026 | 779 | 779 |  |  |  | 30/07/2026 | 27/08/2026 | 22/07/2026 | 31/08/2026 | 779 | 779
ADIDAS | 0902907417-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907417 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 308 | 308 |  |  |  | 23/07/2026 | 30/07/2026 | 18/07/2026 | 24/07/2026 | 308 | 308 |  |  |  | 21/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 308 | 308
ADIDAS | 0902907437-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 332 | 15/09/2026 | 332 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907437 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 29/07/2026 | 2026-03-08 | 332 | 332 |  |  |  | 23/07/2026 | 30/07/2026 | 21/07/2026 | 27/07/2026 | 332 | 332 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 24/07/2026 | 332 | 332
ADIDAS | 0902907453-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 443 | 15/09/2026 | 443 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907453 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-07-09 | 2026-08-09 | 443 | 427 | 16 |  |  | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 14/09/2026 | 443 | 443
ADIDAS | 0902907472-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 812 | 23/09/2026 | 812 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902907472 KX3651 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 812 | 812 |  |  |  | 21/07/2026 | 30/07/2026 | 17/07/2026 | 30/07/2026 | 812 | 812 |  |  |  | 17/07/2026 | 28/07/2026 | 17/07/2026 | 28/07/2026 | 812 | 812
ADIDAS | 0902907504-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 652 | 2026-05-09 | 652 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902907504 KX3654 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-01-09 | 2026-07-08 | 2026-01-09 | 652 | 652 |  |  |  | 2026-03-08 | 28/08/2026 | 25/07/2026 | 2026-05-08 | 652 | 652 |  |  |  | 30/07/2026 | 26/08/2026 | 23/07/2026 | 28/07/2026 | 652 | 652
ADIDAS | 0902907522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 648 | 2026-05-09 | 648 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907522 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/07/2026 | 2026-11-08 | 29/07/2026 | 2026-07-08 | 648 | 648 |  |  |  | 23/07/2026 | 2026-06-08 | 25/07/2026 | 2026-01-08 | 648 | 648 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 28/07/2026 | 648 | 648
ADIDAS | 0902907548-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 671 | 2026-05-09 | 671 | SA | SA15/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907548 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 22/07/2026 | 30/07/2026 | 22/07/2026 | 29/07/2026 | 671 | 671 |  |  |  | 17/07/2026 | 27/07/2026 | 17/07/2026 | 22/07/2026 | 671 | 671 |  |  |  | 15/07/2026 | 23/07/2026 | 17/07/2026 | 28/07/2026 | 671 | 671
ADIDAS | 0902907571-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 12/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907571 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 2026-08-09 | 308 | 254 | 54 |  |  | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-12-09 | 308 | 308 |  |  | 3 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-12-09 | 308 | 308 |  |  | 2
ADIDAS | 0902907642-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 376 | 21/08/2026 | 376 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 21/08: ex-fty (KN GLT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 28-May, actual receives 03-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 25-May (PO NT-351). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902907642 LG9660 | 31/07/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 376 | 376 |  |  |  | 27/07/2026 | 2026-11-08 | 22/07/2026 | 14/08/2026 | 376 | 371 | 5
ADIDAS | 0902908675-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 516 | 21/08/2026 | 516 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | ok | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902908675 LG9660 | 31/07/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 516 | 516 |  |  |  | 27/07/2026 | 2026-11-08 | 24/07/2026 | 30/07/2026 | 516 | 516
ADIDAS | 0902908709-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 684 | 15/09/2026 | 684 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 14-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902908709 LF0726 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 2026-11-09 | 684 | 613 | 71 |  |  | 2026-04-09 | 2026-12-09 | 28/08/2026 | 14/09/2026 | 684 | 610 | 74
ADIDAS | 0902908777-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT15/05/2026 | G3E | SHORTS | G3 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 12-Jun, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902908777 KA8777 | 14/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/07/2026 | TIRO26L SHO M |  | SS27-L2L | 30/07/2026 | 2026-07-08 | 31/07/2026 | 2026-05-08 | 132 | 132 |  |  |  | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 132 | 132 |  |  |  | 23/07/2026 | 31/07/2026 | 13/07/2026 | 13/07/2026 | 132 | 132
ADIDAS | 0902909669-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 30/09/2026 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Jun, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902909669 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 144 | 144 |  |  |  | 29/08/2026 | 2026-04-09 | 26/08/2026 | 2026-07-09 | 144 | 142 | 2
ADIDAS | 0902909771-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902909771 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 13/08/2026 | 14/08/2026 | 8 | 8 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 2026-05-08 | 8 | 8
ADIDAS | 0902909794-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902909794 LG9660 | 31/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 8 | 8 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-11-08 | 18/08/2026 | 8 | 8
ADIDAS | 0902909815-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902909815 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 27/08/2026 | 29/08/2026 | 14/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902910585-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 858 | 2026-05-09 | 858 | SA | SA15/05/2026 | G2G,G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902910585 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 858 | 858 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 2026-03-09 | 858 | 858 |  |  |  | 27/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 858 | 858
ADIDAS | 0902910626-1 KX3712 | LIME TINT S27 | 120D | S2608MR0906A | 420 | 2026-05-09 | 420 | SI | SI15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902910626 KX3712 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess LS M LIME TINT S27 |  | SS27-TI-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 420 | 420 |  |  |  | 27/07/2026 | 2026-11-08 | 17/07/2026 | 24/07/2026 | 420 | 420 |  |  |  | 23/07/2026 | 2026-07-08 | 17/07/2026 | 24/07/2026 | 420 | 420
ADIDAS | 0902911467-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1312 | 23/09/2026 | 1312 | SA | SA15/05/2026 | G2G,G2I,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 834012 | HT+PAD SUB PROCESS_V3 | 0902911467 KF5311 | 14/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-03-08 | 2026-02-09 | 2026-03-08 | 2026-01-09 | 1312 | 1312 |  |  |  | 29/07/2026 | 29/08/2026 | 28/07/2026 | 2026-10-08 | 1312 | 1312 |  |  |  | 27/07/2026 | 27/08/2026 | 25/07/2026 | 2026-10-08 | 1312 | 1312
ADIDAS | 0902911942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 15 | 2026-05-09 | 15 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902911942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI-SPOMA | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 15 | 15 |  |  |  | 27/07/2026 | 30/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15 |  |  |  | 23/07/2026 | 28/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15
ADIDAS | 0902911985-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 351 | 2026-09-09 | 351 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902911985 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 351 | 351 |  |  |  | 29/08/2026 | 2026-01-09 | 13/08/2026 | 2026-07-09 | 351 | 351
ADIDAS | 0902912004-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 652 | 2026-05-09 | 652 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912004 LF0726 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 652 | 652 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 652 | 652
ADIDAS | 0902912022-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 335 | 2026-05-09 | 335 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902912022 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 335 | 335 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 20/08/2026 | 335 | 335
ADIDAS | 0902912038-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1761 | 2026-05-09 | 1761 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912038 LF0727 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 19/08/2026 | 1761 | 1761 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 1761 | 1761
ADIDAS | 0902912063-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 339 | 2026-05-09 | 339 | AN | AN15/05/2026 | G1E | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912063 LF0729 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 18/08/2026 | 339 | 339 |  |  |  | 2026-03-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 339 | 339
ADIDAS | 0902912066-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 544 | 2026-05-09 | 544 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912066 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-07-08 | 2026-12-08 | 544 | 544 |  |  |  | 2026-03-08 | 2026-10-08 | 31/07/2026 | 19/08/2026 | 544 | 544
ADIDAS | 0902912087-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 2026-05-09 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902912087 LG9669 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 144 | 144 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 19/08/2026 | 144 | 144
ADIDAS | 0902912093-1 LG9669 | BLACK | 120D | S2754WAS514C | 789 | 2026-09-09 | 789 | ID | ID15/05/2026 | G3B | SKIRT | G3 | ok | (04/06/2026) | 09/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 659018 | PRINT L3+PPA SUB PROCESS_V3 | 0902912093 LG9669 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 789 | 789 |  |  |  | 27/08/2026 | 2026-04-09 | 13/08/2026 | 2026-07-09 | 789 | 789
ADIDAS | 0902912125-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1399 | 2026-05-09 | 1399 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912125 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 1399 | 1399 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 19/08/2026 | 1399 | 1399
ADIDAS | 0902913684-1 KE8424 | BLACK | 60D | S2608MR0906A-MTF | 304 | 2026-05-09 | 304 | AN | AN15/05/2026 | G2G | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902913684 KE8424 | 2026-02-07 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-09 | Run Ess LS M BLACK |  | FW26 | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 304 | 304 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 304 | 304 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 304 | 304
ADIDAS | 0902913763-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2000 | 2026-12-09 | 2000 | AT | AT15/05/2026 | G3D,G3K | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913763 JD1881 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-08 | M 3S FT TC PT |  | FW26 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 2026-12-08 | 2000 | 2000 |  |  |  | 29/07/2026 | 2026-11-08 | 20/07/2026 | 2026-08-08 | 2000 | 2000
ADIDAS | 0902913788-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 720 | 2026-12-09 | 720 | AT | AT15/05/2026 | G3D | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913788 JE6346 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 720 | 720 |  |  |  | 21/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 720 | 720
ADIDAS | 0902913850-1 KY5990 | OLIVE FOUR S27/SEMI LUCID RED S25 | 105D | S2650MTR436 | 271 | 21/08/2026 | 271 | SA | SA15/05/2026 | G3E | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 516029 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902913850 KY5990 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | WE ALLSET 3S PT OLIVE FOUR S27/SEMI LUCID RED S25 |  | SS27-TI-SPOMA | 2026-12-08 | 14/08/2026 | 14/08/2026 | 14/08/2026 | 271 | 271 |  |  |  | 2026-07-08 | 2026-11-08 | 2026-12-08 | 14/08/2026 | 271 | 271 |  |  |  | 31/07/2026 | 2026-04-08 | 2026-11-08 | 14/08/2026 | 271 | 271
ADIDAS | 0902915780-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 60 | 15/09/2026 | 60 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902915780 LF0729 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-09-09 | 2026-10-09 | 60 | 58 | 2 |  |  | 2026-04-09 | 2026-12-09 | 21/08/2026 | 2026-01-09 | 60 | 60
ADIDAS | 0902915810-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 230 | 2026-05-09 | 230 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902915810 KX3713 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 230 | 230 |  |  |  | 29/08/2026 | 2026-02-09 | 30/07/2026 | 2026-06-08 | 230 | 230 |  |  |  | 27/08/2026 | 31/08/2026 | 27/07/2026 | 2026-04-08 | 230 | 230
ADIDAS | 0902915970-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 105 | 2026-05-09 | 105 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902915970 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI-SPOMA | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 21/07/2026 | 30/07/2026 | 22/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 17/07/2026 | 28/07/2026 | 21/07/2026 | 2026-03-08 | 105 | 105
ADIDAS | 0902916014-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 975 | 2026-05-09 | 975 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902916014 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI-SPOMA | 21/07/2026 | 2026-04-08 | 22/07/2026 | 2026-04-08 | 975 | 975 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 22/07/2026 | 975 | 975 |  |  |  | 14/07/2026 | 28/07/2026 | 15/07/2026 | 21/07/2026 | 975 | 975
ADIDAS | 0902916052-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 588 | 2026-05-09 | 588 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902916052 LD0930 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 588 | 588 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-04-09 | 588 | 588 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 588 | 588
ADIDAS | 0902916115-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 311 | 21/08/2026 | 311 | AN | AN15/05/2026 | G1E | T-SHIRT | G1 | ok | (05/06/2026) | 21/08: ex-fty. T2 Libolon, actual receives 29-Apr (PO booking 25063167). T2 Fu Hsun, actual receives 23-Apr (PO booking 25063168). 516029 | HT SUB PROCESS_V1 | 0902916115 IT1824 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | ADIZERO E TEE |  | FW26-SPOMA | 14/07/2026 | 16/07/2026 | 14/07/2026 | 15/07/2026 | 311 | 311 |  |  |  | 2026-10-07 | 14/07/2026 | 2026-09-07 | 13/07/2026 | 311 | 311 |  |  |  | 2026-09-07 | 13/07/2026 | 2026-09-07 | 2026-10-07 | 311 | 311
ADIDAS | 0902917391-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 327 | 15/09/2026 | 327 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902917391 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 327 | 327 |  |  |  | 2026-03-08 | 29/08/2026 | 30/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 30/07/2026 | 27/08/2026 | 29/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902917424-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 673 | 2026-05-09 | 673 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902917424 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 24/07/2026 | 2026-11-08 | 24/07/2026 | 2026-06-08 | 673 | 673 |  |  |  | 21/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 673 | 673 |  |  |  | 17/07/2026 | 2026-04-08 | 21/07/2026 | 2026-04-08 | 673 | 673
ADIDAS | 0902918914-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2400 | 21/08/2026 | 2400 | AN | AN15/05/2026 | G3G | PANTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902918914 KV7863 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/07/2026 | 24/07/2026 | 15/07/2026 | 24/07/2026 | 2400 | 2400 |  |  |  | 2026-08-07 | 21/07/2026 | 2026-10-07 | 27/07/2026 | 2400 | 2400
ADIDAS | 0902919030-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 5346 | 15/09/2026 | 5346 | AN | AN15/05/2026 | G3A,G3B,G3F,G3H | PANTS | G3 | ok | (13/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902919030 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 15/09/2026 | 14/08/2026 | 2026-08-09 | 5346 | 5235 | 111 |  |  | 2026-11-08 | 2026-11-09 | 2026-06-08 | 2026-10-09 | 5346 | 5273 | 73
ADIDAS | 0902926321-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 321 | 2026-05-09 | 321 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926321 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-11-08 | 321 | 321 |  |  |  | 2026-03-08 | 2026-10-08 | 30/07/2026 | 19/08/2026 | 321 | 321
ADIDAS | 0902926382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 200 | 30/09/2026 | 200 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 23/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926382 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 2026-08-09 | 29/08/2026 | 2026-07-09 | 200 | 200 |  |  |  | 21/08/2026 | 2026-04-09 | 26/08/2026 | 2026-09-09 | 200 | 200
ADIDAS | 0902930255-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 600 | 31/08/2026 | 600 | SI | SI21/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902930255 KX3713 | 21/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 600 | 600 |  |  |  | 30/07/2026 | 2026-11-08 | 28/07/2026 | 2026-07-08 | 600 | 600 |  |  |  | 28/07/2026 | 2026-07-08 | 28/07/2026 | 2026-08-08 | 600 | 600
ADIDAS | 0902930259-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 324 | 2026-07-10 | 324 | SA | SA21/05/2026 | G2Q | T-SHIRT | G2 | ok | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902930259 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 324 |  | 324 |  |  | 26/09/2026 | 28/09/2026 | 14/08/2026 | 2026-08-09 | 324 | 298 | 26 |  |  | 24/09/2026 | 25/09/2026 | 13/08/2026 | 2026-08-09 | 324 | 297 | 27
ADIDAS | 0902931107-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 449 | 31/08/2026 | 449 | SA | SA21/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902931107 LD0285 | 21/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/07/2026 | 29/07/2026 | 21/07/2026 | 28/07/2026 | 449 | 449 |  |  |  | 15/07/2026 | 24/07/2026 | 15/07/2026 | 22/07/2026 | 449 | 449 |  |  |  | 13/07/2026 | 22/07/2026 | 14/07/2026 | 22/07/2026 | 449 | 449
ADIDAS | 0902931109-1 KD0683 | OLIVE STRATA S23/BLACK | 90D | S2650MTR434 | 301 | 21/08/2026 | 301 | SI | SI21/05/2026 | G3E | SHORTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Libolon, PI Date 11-Jun, actual receives 23-Jun. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902931109 KD0683 | 2026-06-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 301 | 301 |  |  |  | 16/07/2026 | 21/07/2026 | 14/07/2026 | 22/07/2026 | 301 | 301 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 22/07/2026 | 301 | 301
ADIDAS | 0902932095-1 KY4154 | OLIVE FOUR S27/BLACK | 105D | F2654MESS608WVB | 113 | 21/08/2026 | 113 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok |  | 21/08: ex-fty. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Formosa, PI Date 07-Jun, using fabric stock. T2 Kahatex, PI Date 10-Jun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902932095 KY4154 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | M 3S CHELSEA B7 |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-03-08 | 2026-12-08 | 113 | 113 |  |  |  | 29/07/2026 | 2026-04-08 | 23/07/2026 | 2026-10-08 | 113 | 113
ADIDAS | 0902933082-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 315 | 28/08/2026 | 315 | AN | AN15/05/2026 | G3H | PANTS | G3 | ok |  | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933082 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/07/2026 | 2026-06-08 | 31/07/2026 | 2026-06-08 | 315 | 315 |  |  |  | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 315 | 315
ADIDAS | 0902933083-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 320 | 28/08/2026 | 320 | SI | SI15/05/2026 | G1H | JACKET | G1 | ok |  | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933083 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 320 | 320 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 320 | 320
ADIDAS | 0902940286-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 30 | 15/09/2026 | 30 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940286 LE0357 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/09/2026 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 14/09/2026 | 14/09/2026 |  |  | 30 |  | 30 |  |  | 2026-10-09 | 2026-10-09 | 26/08/2026 | 2026-04-09 | 30 | 21 | 9
ADIDAS | 0902940338-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 499 | 15/10/2026 | 499 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 31-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940338 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 499 |  | 499 |  |  | 2026-08-10 | 2026-09-10 |  |  | 499 |  | 499
ADIDAS | 0902941400-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941400 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 4800 |  | 4800 |  |  | 22/09/2026 | 26/09/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902941469-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 3000 | 2026-07-10 | 3000 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941469 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 3000 |  | 3000 |  |  | 19/09/2026 | 22/09/2026 |  |  | 3000 |  | 3000
ADIDAS | 0902942438-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 360 | 15/09/2026 | 360 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942438 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 3S CHELSEA B7 |  | FW26 | 17/09/2026 | 17/09/2026 |  |  | 360 |  | 360 |  |  | 14/09/2026 | 14/09/2026 | 2026-10-09 | 2026-11-09 | 360 | 351 | 9
ADIDAS | 0902942448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 05/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942448 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 29/08/2026 | 18/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-10-08 | 2026-04-09 | 450 | 450
ADIDAS | 0902942463-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 465 | 2026-09-09 | 465 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516419 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942463 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 2026-08-09 | 18/08/2026 | 2026-07-09 | 465 | 465 |  |  |  | 2026-11-08 | 2026-04-09 | 2026-11-08 | 2026-07-09 | 465 | 465
ADIDAS | 0902942481-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5600 | 15/09/2026 | 5600 | SI | SI29/05/2026 | G3C,G3E | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942481 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | M 3S CHELSEA B7 |  | FW26 | 2026-08-09 | 14/09/2026 | 2026-04-09 | 14/09/2026 | 5600 | 4466 | 1134 |  | 913 | 2026-04-09 | 2026-10-09 | 2026-03-09 | 2026-11-09 | 5600 | 5548 | 52
ADIDAS | 0902942491-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942491 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-11-09 | 315 | 315
ADIDAS | 0902942496-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942496 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 27/08/2026 | 2026-03-09 | 315 | 315 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-02-09 | 315 | 315
ADIDAS | 0902942511-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942511 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-04-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-04-09 | 29/08/2026 | 2026-07-09 | 400 | 400
ADIDAS | 0902942519-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 390 | 15/09/2026 | 390 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942519 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 3S CHELSEA B7 |  | FW26 | 17/09/2026 | 17/09/2026 |  |  | 390 |  | 390 |  |  | 14/09/2026 | 14/09/2026 | 2026-10-09 | 2026-11-09 | 390 | 303 | 87
ADIDAS | 0902942533-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 2026-09-09 | 900 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942533 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-07-09 | 900 | 900 |  |  |  | 27/08/2026 | 2026-04-09 | 29/08/2026 | 2026-05-09 | 900 | 900
ADIDAS | 0902942573-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 125 | 21/08/2026 | 125 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 830009 | PRINT L3 SUB PROCESS_V3 | 0902942573 IU0217 | 13/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 20/07/2026 | 14/07/2026 | 20/07/2026 | 125 | 125 |  |  |  | 2026-09-07 | 15/07/2026 | 2026-06-07 | 15/07/2026 | 125 | 125
ADIDAS | 0902945010-1 LE8187 | BLACK | 105D | S2754MAS513 | 331 | 15/09/2026 | 331 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945010 LE8187 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 15/09/2026 | 2026-08-09 | 2026-09-09 | 331 | 286 | 45 |  |  | 2026-02-09 | 2026-11-09 | 27/08/2026 | 2026-04-09 | 331 | 292 | 39
ADIDAS | 0902945087-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 401 | 30/09/2026 | 401 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945087 LE8188 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 401 |  | 401 |  |  | 17/09/2026 | 18/09/2026 |  |  | 401 |  | 401
ADIDAS | 0902946696-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 856 | 15/09/2026 | 856 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946696 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 856 |  | 856 |  |  | 2026-11-09 | 2026-12-09 | 20/08/2026 | 2026-09-09 | 856 | 834 | 22
ADIDAS | 0902946778-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 341 | 21/08/2026 | 341 | SI | SI29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946778 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 29/07/2026 | 29/07/2026 | 29/07/2026 | 29/07/2026 | 341 | 341 |  |  |  | 24/07/2026 | 24/07/2026 | 27/07/2026 | 29/07/2026 | 341 | 341
ADIDAS | 0902946844-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 357 | 15/09/2026 | 357 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946844 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 357 |  | 357 |  |  | 2026-11-09 | 2026-12-09 | 2026-01-08 | 2026-10-09 | 357 | 352 | 5
ADIDAS | 0902946897-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 510 | 21/08/2026 | 510 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 10-Jun. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946897 KW2924 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 510 | 510 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 510 | 510
ADIDAS | 0902946950-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 400 | 2026-12-09 | 400 | SI | SI29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946950 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/08/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-11-09 | 400 | 400 |  |  |  | 26/08/2026 | 2026-09-09 | 2026-05-08 | 2026-11-09 | 400 | 399 | 1
ADIDAS | 0902947001-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 324 | 21/08/2026 | 324 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902947001 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 28/07/2026 | 2026-06-08 | 28/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 2026-03-08 | 25/07/2026 | 2026-05-08 | 324 | 324
ADIDAS | 0902947050-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1120 | 15/10/2026 | 1120 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902947050 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 1120 |  | 1120 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902947104-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 1030 | 21/08/2026 | 1030 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902947104 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-05-08 | 1030 | 1030 |  |  |  | 22/07/2026 | 2026-03-08 | 23/07/2026 | 2026-11-08 | 1030 | 1030
ADIDAS | 0902948665-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 219 | 21/08/2026 | 219 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 800187 | PRINT L3 SUB PROCESS_V3 | 0902948665 IU0217 | 13/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 20/07/2026 | 13/07/2026 | 17/07/2026 | 219 | 219 |  |  |  | 2026-09-07 | 15/07/2026 | 2026-06-07 | 17/07/2026 | 219 | 219
ADIDAS | 0902948698-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 561 | 2026-07-10 | 561 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948698 LG9668 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 561 |  | 561 |  |  | 2026-03-10 | 2026-06-10 |  |  | 561 |  | 561
ADIDAS | 0902948720-1 LG9669 | BLACK | 120D | S2754WAS514C | 283 | 30/09/2026 | 283 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902948720 LG9669 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W SL WV SK BLACK |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 283 |  | 283 |  |  | 23/09/2026 | 23/09/2026 | 24/08/2026 | 2026-05-09 | 283 | 240 | 43
ADIDAS | 0902948739-1 LG9669 | BLACK | 120D | S2754WAS514C | 316 | 30/09/2026 | 316 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948739 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV SK BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 316 |  | 316 |  |  | 15/09/2026 | 17/09/2026 | 28/08/2026 | 2026-05-09 | 316 | 307 | 9
ADIDAS | 0902948754-1 LG9669 | BLACK | 120D | S2754WAS514C | 416 | 2026-07-10 | 416 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948754 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W SL WV SK BLACK |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 416 |  | 416 |  |  | 2026-03-10 | 2026-06-10 |  |  | 416 |  | 416
ADIDAS | 0902948775-1 LG9669 | BLACK | 120D | S2754WAS514C | 497 | 30/09/2026 | 497 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948775 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 497 |  | 497 |  |  | 21/09/2026 | 23/09/2026 | 26/08/2026 | 2026-12-09 | 497 | 460 | 37 |  | 18
ADIDAS | 0902949162-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 377 | 15/09/2026 | 377 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949162 LF0725 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 14/09/2026 | 2026-10-09 | 2026-12-09 | 377 | 372 | 5 |  | 37 | 2026-07-09 | 2026-10-09 | 2026-07-09 | 2026-11-09 | 377 | 374 | 3
ADIDAS | 0902949302-1 LF0723 | BLACK | 105D | S2754MAS511B | 402 | 30/09/2026 | 402 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949302 LF0723 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | M SL WV SHO BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 402 |  | 402 |  |  | 17/09/2026 | 18/09/2026 |  |  | 402 |  | 402
ADIDAS | 0902950353-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 300 | 28/08/2026 | 300 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902950353 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV WB |  | SS27 | 2026-03-08 | 24/08/2026 | 2026-03-08 | 24/08/2026 | 300 | 300 |  |  |  | 29/07/2026 | 19/08/2026 | 23/07/2026 | 31/08/2026 | 300 | 300
ADIDAS | 0902951279-1 LH3758 | BLACK | 120D | S2754WAS518B | 500 | 15/10/2026 | 500 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951279 LH3758 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | W SL WV BR PT BLACK |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 500 |  | 500 |  |  | 16/10/2026 | 16/10/2026 |  |  | 500 |  | 500
ADIDAS | 0902951331-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 500 | 30/09/2026 | 500 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951331 LD5446 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 500 |  | 500 |  |  | 21/09/2026 | 23/09/2026 |  |  | 500 |  | 500
ADIDAS | 0902951411-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 302 | 26/08/2026 | 302 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951411 LE4307 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/07/2026 | 14/08/2026 | 28/07/2026 | 18/08/2026 | 302 | 302 |  |  |  | 23/07/2026 | 2026-11-08 | 22/07/2026 | 21/08/2026 | 302 | 302
ADIDAS | 0902951455-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 598 | 21/08/2026 | 598 | AN | AN29/05/2026 | G2I,G2J | T-SHIRT | G2 | ok | (27/06/2026) | 21/08: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0902951455 KX0126 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 29/07/2026 | 31/07/2026 | 28/07/2026 | 30/07/2026 | 598 | 598 |  |  |  | 24/07/2026 | 28/07/2026 | 21/07/2026 | 29/07/2026 | 598 | 598
ADIDAS | 0902951458-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 136 | 31/08/2026 | 136 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty (S4EU). T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951458 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 14/08/2026 | 21/08/2026 | 136 | 136 |  |  |  | 2026-11-08 | 20/08/2026 | 31/07/2026 | 2026-10-08 | 136 | 136
ADIDAS | 0902951503-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 922 | 31/08/2026 | 922 | SI | SI29/05/2026 | G1H,G1L | JACKET | G1 | ok | ok | 29/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951503 LE4307 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 21/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 922 | 922 |  |  |  | 18/08/2026 | 27/08/2026 | 20/08/2026 | 29/08/2026 | 922 | 922
ADIDAS | 0902951560-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 302 | 15/10/2026 | 302 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951560 LG9665 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 302 |  | 302 |  |  | 25/09/2026 | 28/09/2026 |  |  | 302 |  | 302
ADIDAS | 0902951622-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 498 | 15/10/2026 | 498 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951622 LG9661 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 498 |  | 498 |  |  | 28/09/2026 | 2026-01-10 |  |  | 498 |  | 498
ADIDAS | 0902952735-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 318 | 26/08/2026 | 318 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul. T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902952735 KW2909 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | W 3S WV WB |  | SS27 | 24/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 318 | 318 |  |  |  | 21/07/2026 | 2026-03-08 | 20/07/2026 | 28/07/2026 | 318 | 318
ADIDAS | 0902952799-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 598 | 21/08/2026 | 598 | AN | AN29/05/2026 | G2I,G2J | T-SHIRT | G2 | ok | (27/06/2026) | 21/08: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0902952799 LC8884 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M RESORT T BLACK |  | SS27 | 29/07/2026 | 31/07/2026 | 28/07/2026 | 30/07/2026 | 598 | 598 |  |  |  | 24/07/2026 | 28/07/2026 | 24/07/2026 | 30/07/2026 | 598 | 598
ADIDAS | 0902953067-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 327 | 2026-07-10 | 327 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953067 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 327 |  | 327 |  |  | 2026-07-10 | 2026-08-10 |  |  | 327 |  | 327
ADIDAS | 0902953119-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 139 | 31/08/2026 | 139 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953119 LE8181 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 139 | 139 |  |  |  | 21/08/2026 | 27/08/2026 | 13/08/2026 | 20/08/2026 | 139 | 139
ADIDAS | 0902953315-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 307 | 23/09/2026 | 307 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953315 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 14/08/2026 | 2026-01-09 | 307 | 307 |  |  |  | 2026-11-08 | 29/08/2026 | 28/07/2026 | 2026-11-08 | 307 | 307 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 28/07/2026 | 307 | 307
ADIDAS | 0902953364-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 472 | 23/09/2026 | 472 | SA | SA29/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953364 LD0288 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 21/08/2026 | 31/07/2026 | 20/08/2026 | 472 | 472 |  |  |  | 27/07/2026 | 18/08/2026 | 25/07/2026 | 30/07/2026 | 472 | 472 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 29/07/2026 | 472 | 472
ADIDAS | 0902953400-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 312 | 23/09/2026 | 312 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 18/09: ex-fty 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902953400 KY5988 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 312 | 312 |  |  |  | 27/07/2026 | 2026-11-08 | 30/07/2026 | 2026-08-08 | 312 | 312 |  |  |  | 20/07/2026 | 2026-04-08 | 30/07/2026 | 2026-06-08 | 312 | 312
ADIDAS | 0902953446-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 542 | 23/09/2026 | 542 | SA | SA29/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953446 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 542 | 542 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 31/07/2026 | 542 | 542 |  |  |  | 28/07/2026 | 2026-04-08 | 24/07/2026 | 30/07/2026 | 542 | 542
ADIDAS | 0902953533-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 327 | 30/09/2026 | 327 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902953533 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 21/09/2026 | 21/09/2026 |  |  | 327 |  | 327 |  |  | 17/09/2026 | 17/09/2026 | 27/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 15/09/2026 | 15/09/2026 | 25/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902953571-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 479 | 30/09/2026 | 479 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 23/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953571 KX3651 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 479 |  | 479 |  |  | 23/09/2026 | 23/09/2026 | 31/07/2026 | 2026-08-08 | 479 | 479 |  |  |  | 21/09/2026 | 21/09/2026 | 30/07/2026 | 2026-07-08 | 479 | 479
ADIDAS | 0902953689-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 130 | 21/08/2026 | 130 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953689 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-10-08 | 13/08/2026 | 130 | 130 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 20/08/2026 | 130 | 130
ADIDAS | 0902953736-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 305 | 28/08/2026 | 305 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953736 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-05-08 | 29/08/2026 | 305 | 305
ADIDAS | 0902953783-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 370 | 21/08/2026 | 370 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953783 KV7963 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 370 | 370 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 370 | 370
ADIDAS | 0902953842-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 26/08/2026 | 300 | AN | AN29/05/2026 | G1L | JACKET | G1 | ok | (27/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun (PO NT-353). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953842 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-06-08 | 2026-07-08 | 2026-07-08 | 14/08/2026 | 300 | 300 |  |  |  | 2026-03-08 | 2026-04-08 | 30/07/2026 | 22/08/2026 | 300 | 300
ADIDAS | 0902953974-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 305 | 28/08/2026 | 305 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953974 KV7963 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 305 | 305 |  |  |  | 22/07/2026 | 2026-03-08 | 23/07/2026 | 2026-05-08 | 305 | 305
ADIDAS | 0902954045-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954045 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 313 |  | 313 |  |  | 25/09/2026 | 25/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902954068-1 KT7552 | BLACK | 60D | F26FBGFXP104 | 1344 | 21/08/2026 | 1344 | SI | SI29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902954068 KT7552 | 15/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/07/2026 | SOC CAT GFX T BLACK |  | SS27 | 31/07/2026 | 2026-06-08 | 30/07/2026 | 2026-05-08 | 1344 | 1344 |  |  |  | 28/07/2026 | 2026-03-08 | 21/07/2026 | 2026-05-08 | 1344 | 1344
ADIDAS | 0902954088-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 246 | 15/09/2026 | 246 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954088 LG9661 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 246 | 172 | 74 |  | 79 | 2026-04-09 | 2026-11-09 | 28/08/2026 | 2026-11-09 | 246 | 212 | 34
ADIDAS | 0902954666-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 2026-07-10 | 200 | SA | SA29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954666 LE8181 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 200 |  | 200 |  |  | 2026-09-10 | 2026-10-10 |  |  | 200 |  | 200
ADIDAS | 0902954719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 162 | 15/09/2026 | 162 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954719 LE8186 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 2026-09-09 | 16/09/2026 |  |  | 162 |  | 162 |  |  | 2026-05-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 162 | 101 | 61 |  | 9
ADIDAS | 0902954826-1 LE8187 | BLACK | 105D | S2754MAS513 | 152 | 15/09/2026 | 152 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954826 LE8187 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-09 | M SL WV TP PT BLACK |  | SS27 | 2026-12-09 | 15/09/2026 |  |  | 152 |  | 152 |  |  | 2026-09-09 | 2026-11-09 |  |  | 152 |  | 152
ADIDAS | 0902954882-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 174 | 15/09/2026 | 174 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954882 LE8188 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 174 | 42 | 132 |  |  | 2026-10-09 | 2026-11-09 | 2026-11-09 | 2026-11-09 | 174 | 128 | 46
ADIDAS | 0902954999-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 609 | 2026-07-10 | 609 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954999 LF0726 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 609 |  | 609 |  |  | 29/09/2026 | 2026-01-10 |  |  | 609 |  | 609
ADIDAS | 0902955058-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 206 | 23/09/2026 | 206 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955058 LF0727 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 206 | 206 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-07-08 | 31/08/2026 | 206 | 206
ADIDAS | 0902955123-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 356 | 15/09/2026 | 356 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (S4EU). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955123 LF0726 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 16/09/2026 | 2026-04-09 | 2026-12-09 | 356 | 334 | 22 |  | 1 | 2026-01-09 | 2026-12-09 | 27/08/2026 | 2026-10-09 | 356 | 326 | 30
ADIDAS | 0902955656-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 590 | 30/09/2026 | 590 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955656 KX3655 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 590 |  | 590 |  |  | 21/09/2026 | 22/09/2026 | 2026-07-09 | 2026-11-09 | 590 | 566 | 24 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-09 | 14/09/2026 | 590 | 567 | 23
ADIDAS | 0902955699-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 441 | 30/09/2026 | 441 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955699 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-12-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 441 | 196 | 245 |  |  | 2026-09-09 | 2026-11-09 | 2026-10-08 | 26/08/2026 | 441 | 441 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-10-08 | 24/08/2026 | 441 | 441
ADIDAS | 0902955746-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 324 | 30/09/2026 | 324 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902955746 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-09 | 14/09/2026 | 2026-07-09 | 2026-08-09 | 324 | 278 | 46 |  |  | 2026-04-09 | 2026-10-09 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1 |  |  | 2026-02-09 | 2026-08-09 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1
ADIDAS | 0902955843-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 30/09/2026 | 301 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955843 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M SL WV SHO BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 17/09/2026 | 18/09/2026 | 2026-10-09 | 2026-10-09 | 301 | 120 | 181
ADIDAS | 0902955890-1 LF0723 | BLACK | 105D | S2754MAS511B | 137 | 2026-09-09 | 137 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955890 LF0723 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | M SL WV SHO BLACK |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 137 | 137 |  |  |  | 29/08/2026 | 2026-03-09 | 18/08/2026 | 28/08/2026 | 137 | 137
ADIDAS | 0902955942-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 417 | 2026-07-10 | 417 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955942 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 417 |  | 417 |  |  | 16/10/2026 | 17/10/2026 |  |  | 417 |  | 417
ADIDAS | 0902955987-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 322 | 22/09/2026 | 322 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955987 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-08-09 | 2026-10-09 | 322 | 322 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-08-09 | 322 | 314 | 8
ADIDAS | 0902956072-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 187 | 2026-05-09 | 187 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956072 LD5446 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 187 | 187 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 187 | 187
ADIDAS | 0902956169-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 302 | 15/09/2026 | 302 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956169 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | M SL WV TT BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 2026-12-09 | 302 | 263 | 39 |  | 1 | 2026-04-09 | 2026-12-09 | 2026-06-08 | 14/09/2026 | 302 | 284 | 18
ADIDAS | 0902956226-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 645 | 2026-07-10 | 645 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956226 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M SL WV TT BLACK |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 645 |  | 645 |  |  | 2026-01-10 | 2026-05-10 |  |  | 645 |  | 645
ADIDAS | 0902956293-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 203 | 23/09/2026 | 203 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956293 LF0729 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 203 | 203 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 203 | 202 | 1
ADIDAS | 0902956352-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 177 | 15/09/2026 | 177 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956352 LF0726 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 16/09/2026 | 2026-04-09 | 2026-11-09 | 177 | 154 | 23 |  |  | 27/08/2026 | 2026-12-09 | 13/08/2026 | 14/09/2026 | 177 | 180 | -3 | 3 | 5
ADIDAS | 0902956415-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 605 | 2026-07-10 | 605 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956415 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 605 |  | 605 |  |  | 28/09/2026 | 29/09/2026 | 2026-04-09 | 2026-11-09 | 605 | 216 | 389
ADIDAS | 0902956471-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 305 | 2026-07-10 | 305 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956471 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 305 |  | 305 |  |  | 2026-07-10 | 2026-08-10 |  |  | 305 |  | 305
ADIDAS | 0902956523-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 301 | 28/08/2026 | 301 | SI | SI29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902956523 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-07-08 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 301 | 301 |  |  |  | 2026-04-08 | 20/08/2026 | 2026-05-08 | 26/08/2026 | 301 | 301
ADIDAS | 0902956639-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 747 | 28/08/2026 | 747 | SI | SI29/05/2026 | G3B,G3E | PANTS | G3 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902956639 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 28/08/2026 | 2026-07-08 | 27/08/2026 | 747 | 747 |  |  |  | 2026-03-08 | 24/08/2026 | 2026-05-08 | 26/08/2026 | 747 | 747
ADIDAS | 0902956678-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 599 | 15/09/2026 | 599 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956678 LG9661 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 599 | 400 | 199 |  | 41 | 28/08/2026 | 2026-11-09 | 26/08/2026 | 2026-08-09 | 599 | 447 | 152
ADIDAS | 0902956729-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 438 | 2026-07-10 | 438 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956729 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 438 |  | 438 |  |  | 25/09/2026 | 28/09/2026 |  |  | 438 |  | 438
ADIDAS | 0902956767-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 133 | 15/09/2026 | 133 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 24/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956767 LG9664 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 133 |  | 133 |  |  | 2026-12-09 | 15/09/2026 | 2026-10-09 | 2026-10-09 | 133 | 109 | 24
ADIDAS | 0902956798-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 310 | 15/09/2026 | 310 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956798 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 310 |  | 310 |  |  | 2026-11-09 | 2026-12-09 | 2026-01-09 | 2026-08-09 | 310 | 242 | 68
ADIDAS | 0902956842-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 710 | 30/09/2026 | 710 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956842 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 710 |  | 710 |  |  | 15/09/2026 | 17/09/2026 | 29/08/2026 | 2026-07-09 | 710 | 599 | 111
ADIDAS | 0902956973-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 139 | 30/09/2026 | 139 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956973 LG9666 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 139 |  | 139 |  |  | 15/09/2026 | 17/09/2026 | 31/08/2026 | 2026-04-09 | 139 | 138 | 1
ADIDAS | 0902957021-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 495 | 2026-07-10 | 495 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957021 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 495 |  | 495 |  |  | 2026-12-10 | 14/10/2026 |  |  | 495 |  | 495
ADIDAS | 0902957107-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 334 | 2026-07-10 | 334 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957107 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 334 |  | 334 |  |  | 2026-10-10 | 2026-12-10 |  |  | 334 |  | 334
ADIDAS | 0902957145-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 300 | 30/09/2026 | 300 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957145 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902958225-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 270 | 28/08/2026 | 270 | AN | AN29/05/2026 | G3E | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 05-Jun (PO NT-347). 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958225 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-10-08 | 270 | 270 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 2026-10-08 | 270 | 270
ADIDAS | 0902958280-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 262 | 31/08/2026 | 262 | SI | SI29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958280 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 2026-12-08 | 2026-06-08 | 2026-11-08 | 262 | 262 |  |  |  | 30/07/2026 | 2026-07-08 | 29/07/2026 | 2026-11-08 | 262 | 262
ADIDAS | 0902958335-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 239 | 28/08/2026 | 239 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958335 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-08 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 239 | 239 |  |  |  | 2026-04-08 | 20/08/2026 | 2026-07-08 | 24/08/2026 | 239 | 239
ADIDAS | 0902958409-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 608 | 31/08/2026 | 608 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 29-May (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958409 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-10-08 | 608 | 608 |  |  |  | 29/07/2026 | 2026-07-08 | 27/07/2026 | 2026-05-08 | 608 | 608
ADIDAS | 0902958471-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 747 | 28/08/2026 | 747 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 27-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958471 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-05-08 | 14/08/2026 | 747 | 747 |  |  |  | 29/07/2026 | 2026-10-08 | 31/07/2026 | 2026-05-08 | 747 | 747
ADIDAS | 0902958524-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 28/08/2026 | 313 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958524 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 2026-06-08 | 2026-04-08 | 2026-06-08 | 313 | 313 |  |  |  | 29/07/2026 | 2026-03-08 | 31/07/2026 | 13/08/2026 | 313 | 313
ADIDAS | 0902958584-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 303 | 31/08/2026 | 303 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958584 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-05-08 | 2026-07-08 | 303 | 303 |  |  |  | 29/07/2026 | 2026-07-08 | 27/07/2026 | 2026-01-08 | 303 | 303
ADIDAS | 0902959184-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 201 | 30/09/2026 | 201 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959184 LG9673 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 201 |  | 201 |  |  | 22/09/2026 | 22/09/2026 |  |  | 201 |  | 201
ADIDAS | 0902959230-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 428 | 2026-07-10 | 428 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959230 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 428 |  | 428 |  |  | 2026-12-10 | 14/10/2026 |  |  | 428 |  | 428
ADIDAS | 0902959276-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 205 | 30/09/2026 | 205 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959276 LG9675 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | W SL WV PT BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 205 |  | 205 |  |  | 24/09/2026 | 25/09/2026 |  |  | 205 |  | 205
ADIDAS | 0902959319-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959319 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W SL WV PT BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959364-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 308 | 2026-07-10 | 308 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959364 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | W SL WV PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 308 |  | 308 |  |  | 2026-10-10 | 2026-12-10 |  |  | 308 |  | 308
ADIDAS | 0902959405-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 356 | 2026-09-09 | 356 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959405 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-02-09 | 356 | 356 |  |  |  | 20/08/2026 | 31/08/2026 | 2026-12-08 | 2026-07-09 | 356 | 356
ADIDAS | 0902959452-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1380 | 30/09/2026 | 1380 | SI | SI29/05/2026 | G3D | SHORTS | G3 | (12/07/2026) | ok | Waiting fabric. DRC 0002-T2 Gistex, material delayed, PI Date 12-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959452 KY4155 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 14/09/2026 | 16/09/2026 |  |  | 1380 |  | 1380 |  |  | 2026-10-09 | 2026-12-09 |  |  | 1380 |  | 1380
ADIDAS | 0902959473-1 LH3758 | BLACK | 120D | S2754WAS518B | 182 | 30/09/2026 | 182 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959473 LH3758 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | W SL WV BR PT BLACK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 182 |  | 182 |  |  | 18/09/2026 | 19/09/2026 |  |  | 182 |  | 182
ADIDAS | 0902959508-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 3010 | 15/09/2026 | 3010 | SI | SI29/05/2026 | G3B | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959508 KY6510 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | M 3S CHELSEA B7 |  | FW26 | 15/09/2026 | 18/09/2026 |  |  | 3010 |  | 3010 |  |  | 2026-11-09 | 15/09/2026 | 2026-10-09 | 2026-12-09 | 3010 | 2707 | 303 |  | 361
ADIDAS | 0902959557-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 419 | 2026-09-09 | 419 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959557 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 |  | FW26 | 29/08/2026 | 2026-08-09 | 29/08/2026 | 2026-07-09 | 419 | 419 |  |  |  | 26/08/2026 | 2026-04-09 | 13/08/2026 | 2026-07-09 | 419 | 419
ADIDAS | 0902959562-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 134 | 30/09/2026 | 134 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959562 LH3761 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 134 |  | 134 |  |  | 22/09/2026 | 23/09/2026 |  |  | 134 |  | 134
ADIDAS | 0902959597-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 799 | 15/09/2026 | 799 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959597 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 3S CHELSEA B7 |  | FW26 | 17/09/2026 | 18/09/2026 |  |  | 799 |  | 799 |  |  | 14/09/2026 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 799 | 735 | 64
ADIDAS | 0902959610-1 LH3758 | BLACK | 120D | S2754WAS518B | 640 | 2026-07-10 | 640 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959610 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W SL WV BR PT BLACK |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 640 |  | 640 |  |  | 14/10/2026 | 15/10/2026 |  |  | 640 |  | 640
ADIDAS | 0902959964-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516461 | HT+PAD SUB PROCESS_V3 | 0902959964 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 300 | 294 | 6 |  |  | 2026-05-09 | 2026-11-09 | 2026-10-08 | 15/08/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-10-08 | 14/08/2026 | 300 | 300
ADIDAS | 0902960005-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902960005 KX3655 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 320 |  | 320 |  |  | 2026-03-10 | 2026-03-10 |  |  | 320 |  | 320 |  |  | 2026-01-10 | 2026-01-10 |  |  | 320 |  | 320
ADIDAS | 0902960049-1 LF0723 | BLACK | 105D | S2754MAS511B | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902960049 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | M SL WV SHO BLACK |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 420 |  | 420 |  |  | 17/10/2026 | 19/10/2026 |  |  | 420 |  | 420
ADIDAS | 0902960084-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 2026-03-09 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960084 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 29/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-04-08 | 2026-12-08 | 300 | 300
ADIDAS | 0902960126-1 JZ7808 | BLACK | 120D | S2608WR0900 | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902960126 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-08 | 15/08/2026 | 313 | 312 | 1 |  |  | 16/09/2026 | 17/09/2026 | 2026-07-08 | 14/08/2026 | 313 | 313
ADIDAS | 0902960651-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 480 | 2026-05-09 | 480 | SI | SI29/05/2026 | G3A,G3C | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960651 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 480 | 480 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-04-08 | 13/08/2026 | 480 | 480
ADIDAS | 0902960711-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 500 | 15/09/2026 | 500 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960711 LH4535 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 500 | 455 | 45 |  |  | 2026-05-09 | 2026-11-09 | 13/08/2026 | 2026-03-09 | 500 | 497 | 3
ADIDAS | 0902960763-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 244 | 15/09/2026 | 244 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960763 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 244 | 238 | 6 |  |  | 2026-05-09 | 2026-11-09 | 15/08/2026 | 28/08/2026 | 244 | 234 | 10
ADIDAS | 0902960819-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 306 | 28/08/2026 | 306 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | (25/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960819 LH4535 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 2026-03-08 | 2026-07-08 | 306 | 306 |  |  |  | 24/07/2026 | 2026-05-08 | 28/07/2026 | 2026-07-08 | 306 | 306
ADIDAS | 0902961677-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 309 | 2026-07-10 | 309 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961677 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 309 |  | 309 |  |  | 14/10/2026 | 15/10/2026 |  |  | 309 |  | 309
ADIDAS | 0902961728-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 887 | 30/09/2026 | 887 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902961728 LH3759 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 887 |  | 887 |  |  | 21/09/2026 | 22/09/2026 |  |  | 887 |  | 887
ADIDAS | 0902961768-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 313 | 30/09/2026 | 313 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961768 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 313 |  | 313 |  |  | 21/09/2026 | 22/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902961819-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 341 | 2026-07-10 | 341 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961819 LH3761 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 341 |  | 341 |  |  | 14/10/2026 | 15/10/2026 |  |  | 341 |  | 341
ADIDAS | 0902962271-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 3004 | 28/08/2026 | 3004 | SI | SI29/05/2026 | G1H,G1L | JACKET | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 20-Aug. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962271 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-12-08 | 28/08/2026 | 14/08/2026 | 28/08/2026 | 3004 | 3004 |  |  |  | 2026-07-08 | 24/08/2026 | 2026-07-08 | 2026-07-09 | 3004 | 3004
ADIDAS | 0902962301-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 500 | 2026-03-09 | 500 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962301 KV7963 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 500 | 500 |  |  |  | 22/07/2026 | 30/07/2026 | 23/07/2026 | 2026-05-08 | 500 | 500
ADIDAS | 0902962328-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962328 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-05-09 | 300 | 292 | 8 |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 300 | 290 | 10
ADIDAS | 0902962445-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962445 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-08-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-04-09 | 2026-02-09 | 2026-08-09 | 400 | 400
ADIDAS | 0902962469-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962469 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-02-09 | 315 | 315 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-02-09 | 315 | 315
ADIDAS | 0902962488-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 390 | 2026-09-09 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962488 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-08-09 | 2026-07-09 | 2026-08-09 | 390 | 390 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-03-09 | 2026-09-09 | 390 | 390
ADIDAS | 0902962541-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962541 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 330 | 330 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-08-09 | 330 | 330
ADIDAS | 0902962571-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516241 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962571 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-08-09 | 330 | 330 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-02-09 | 2026-09-09 | 330 | 330
ADIDAS | 0902962600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962600 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 450 | 450 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0902962624-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 3000 | 2026-12-09 | 3000 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 27-Aug. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962624 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-11-09 | 3000 | 3000 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 3000 | 3000
ADIDAS | 0902962644-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962644 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-02-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 315 | 315
ADIDAS | 0902966036-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966036 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-08-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 65 | 63 | 2
ADIDAS | 0902966052-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966052 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 27 |  | 27 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 27 | 20 | 7
ADIDAS | 0902966064-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966064 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-08-09 | 65 | 65 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-04-09 | 65 | 65
ADIDAS | 0902966089-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966089 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-12-09 | 2026-08-09 | 2026-10-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-07-09 | 2026-10-09 | 22 | 22 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-05-09 | 2026-10-09 | 22 | 22
ADIDAS | 0902966098-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966098 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 65 | 65 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 65 | 63 | 2
ADIDAS | 0902966111-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 27 | 30/09/2026 | 27 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902966111 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 27 |  | 27 |  |  | 22/09/2026 | 22/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902966123-1 KY5991 | PURE BLUE S27/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 20-Aug. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966123 KY5991 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 35SSHO PURE BLUE S27/WHITE |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 2026-07-09 | 22 | 22 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-05-09 | 2026-05-09 | 22 | 22
ADIDAS | 0902966135-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 50 | 21/08/2026 | 50 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902966135 LG9660 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 2026-03-08 | 50 | 50 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 28/07/2026 | 50 | 50
ADIDAS | 0902970651-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 992 | 15/09/2026 | 992 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. T2 Kahatex, PI Date 06-Aug, actual receives 25-Jun. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902970651 KA2571 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-09-09 | 2026-12-09 | 2026-08-09 | 2026-12-09 | 992 | 992 |  |  | 37 | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-11-09 | 992 | 992 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-07-09 | 2026-10-09 | 992 | 992
ADIDAS | 0902970663-1 LG9669 | BLACK | 120D | S2754WAS514C | 27 | 30/09/2026 | 27 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970663 LG9669 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 27 |  | 27 |  |  | 21/09/2026 | 23/09/2026 | 29/08/2026 | 2026-01-09 | 27 | 17 | 10
ADIDAS | 0902970676-1 LE0355 | BLACK | 105D | S2754MAS514 | 65 | 30/09/2026 | 65 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970676 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/09/2026 | M SL WV CU PT BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 65 |  | 65 |  |  | 25/09/2026 | 28/09/2026 | 2026-01-09 | 2026-01-09 | 65 | 61 | 4
ADIDAS | 0902970685-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970685 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-08-09 | 65 | 65
ADIDAS | 0902970699-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970699 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 27 |  | 27 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-09 | 14/09/2026 | 27 | 23 | 4
ADIDAS | 0902970711-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 27 | 30/09/2026 | 27 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | ok | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970711 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/09/2026 | W SL WV PT BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 27 |  | 27 |  |  | 24/09/2026 | 25/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902970727-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 54 | 30/09/2026 | 54 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970727 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 54 |  | 54 |  |  | 15/09/2026 | 17/09/2026 | 2026-01-09 | 2026-03-09 | 54 | 47 | 7
ADIDAS | 0902970843-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 23/09/2026 | 322 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970843 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-06-08 | 2026-11-08 | 322 | 322 |  |  |  | 2026-03-08 | 2026-06-08 | 29/07/2026 | 31/07/2026 | 322 | 322 |  |  |  | 30/07/2026 | 2026-04-08 | 24/07/2026 | 28/07/2026 | 322 | 322
ADIDAS | 0902970859-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 462 | 30/09/2026 | 462 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970859 KX3654 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-07-09 | 2026-08-09 | 462 | 416 | 46 |  |  | 2026-02-09 | 2026-10-09 | 2026-08-08 | 15/08/2026 | 462 | 462 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-08-08 | 14/08/2026 | 462 | 462
ADIDAS | 0902970876-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 503 | 15/10/2026 | 503 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970876 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 503 |  | 503 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 24/08/2026 | 503 | 503 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 503 | 503
ADIDAS | 0902970893-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 433 | 15/10/2026 | 433 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970893 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 433 |  | 433 |  |  | 25/09/2026 | 26/09/2026 |  |  | 433 |  | 433 |  |  | 23/09/2026 | 24/09/2026 |  |  | 433 |  | 433
ADIDAS | 0902970931-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 365 | 23/09/2026 | 365 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970931 LD0285 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/08/2026 | 24/08/2026 | 24/08/2026 | 24/08/2026 | 365 | 365 |  |  |  | 14/08/2026 | 19/08/2026 | 29/07/2026 | 2026-01-08 | 365 | 365 |  |  |  | 2026-12-08 | 14/08/2026 | 25/07/2026 | 2026-01-08 | 365 | 365
ADIDAS | 0902970945-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 479 | 2026-05-09 | 479 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty 684009 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902970945 KC8152 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 31/08/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 479 | 479 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-09 | 2026-10-09 | 479 | 479 |  |  |  | 19/08/2026 | 27/08/2026 | 2026-03-09 | 2026-07-09 | 479 | 479
ADIDAS | 0902970957-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 658 | 30/09/2026 | 658 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902970957 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 658 |  | 658 |  |  | 2026-12-09 | 14/09/2026 | 31/07/2026 | 2026-05-08 | 658 | 658 |  |  |  | 2026-10-09 | 2026-11-09 | 30/07/2026 | 2026-05-08 | 658 | 658
ADIDAS | 0902970975-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 322 | 30/09/2026 | 322 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970975 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 322 |  | 322 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-09 | 2026-09-09 | 322 | 320 | 2 |  |  | 18/09/2026 | 19/09/2026 | 2026-03-09 | 14/09/2026 | 322 | 322
ADIDAS | 0902970994-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 65 | 15/09/2026 | 65 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970994 LE0357 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 14/09/2026 | 14/09/2026 |  |  | 65 |  | 65 |  |  | 2026-10-09 | 2026-10-09 | 24/08/2026 | 2026-09-09 | 65 | 47 | 18
ADIDAS | 0902971007-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 325 | 30/09/2026 | 325 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902971007 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 325 |  | 325 |  |  | 2026-12-09 | 14/09/2026 | 2026-03-08 | 2026-12-08 | 325 | 325 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-12-08 | 325 | 325
ADIDAS | 0902971009-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 433 | 30/09/2026 | 433 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902971009 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 15/09/2026 |  |  | 433 |  | 433 |  |  | 2026-10-09 | 2026-11-09 | 2026-10-08 | 20/08/2026 | 433 | 433 |  |  |  | 2026-08-09 | 2026-09-09 | 2026-10-08 | 19/08/2026 | 433 | 433
ADIDAS | 0902971034-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902971034 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 24/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 65 | 65 |  |  |  | 19/08/2026 | 27/08/2026 | 31/07/2026 | 26/08/2026 | 65 | 65
ADIDAS | 0902971040-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 674 | 30/09/2026 | 674 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902971040 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 674 |  | 674 |  |  | 21/09/2026 | 22/09/2026 |  |  | 674 |  | 674 |  |  | 18/09/2026 | 19/09/2026 |  |  | 674 |  | 674
ADIDAS | 0902971044-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 54 | 30/09/2026 | 54 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902971044 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 54 |  | 54 |  |  | 21/09/2026 | 22/09/2026 |  |  | 54 |  | 54
ADIDAS | 0902971059-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 562 | 15/09/2026 | 562 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902971059 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-11-09 | 562 | 562 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-11-09 | 562 | 562 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-08-09 | 2026-11-09 | 562 | 562
ADIDAS | 0902971713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1094 | 23/09/2026 | 1094 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902971713 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-12-08 | 1094 | 1094 |  |  |  | 2026-03-08 | 2026-10-08 | 2026-04-08 | 14/08/2026 | 1094 | 1094
ADIDAS | 0902972065-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 514 | 30/09/2026 | 514 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972065 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 514 |  | 514 |  |  | 21/09/2026 | 23/09/2026 |  |  | 514 |  | 514
ADIDAS | 0902972095-1 LE8187 | BLACK | 105D | S2754MAS513 | 320 | 15/09/2026 | 320 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972095 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-09 | M SL WV TP PT BLACK |  | SS27 | 2026-08-09 | 14/09/2026 | 2026-11-09 | 14/09/2026 | 320 | 168 | 152 |  | 153 | 2026-04-09 | 2026-10-09 | 29/08/2026 | 2026-12-09 | 320 | 291 | 29 |  | 10
ADIDAS | 0902972345-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 503 | 28/08/2026 | 503 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516400 | EMBRO SUB PROCESS_V1 | 0902972345 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | M FEELCOZY PANT |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-05-08 | 2026-07-08 | 503 | 503 |  |  |  | 31/07/2026 | 2026-04-08 | 21/07/2026 | 30/07/2026 | 503 | 503
ADIDAS | 0902972376-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 4291 | 2026-05-09 | 4291 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 04/09: ex-fty 516400 | EMBRO SUB PROCESS_V1 | 0902972376 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | M FEELCOZY PANT |  | FW26 | 27/07/2026 | 2026-07-08 | 27/07/2026 | 2026-07-08 | 4291 | 4291 |  |  |  | 22/07/2026 | 2026-04-08 | 18/07/2026 | 2026-05-08 | 4291 | 4291
ADIDAS | 0902972647-1 KY7166 | BLACK | 75D | S2706CHCC008-MTF | 865 | 21/08/2026 | 865 | AN | AN29/05/2026 | G2Q | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902972647 KY7166 | 16/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 21/07/2026 | CC DNA SHO BLACK |  | SS27 | 21/07/2026 | 2026-03-08 | 23/07/2026 | 29/07/2026 | 865 | 865 |  |  |  | 16/07/2026 | 29/07/2026 | 16/07/2026 | 28/07/2026 | 865 | 865
ADIDAS | 0902972659-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1 | 2026-05-09 | 1 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972659 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1 |  |  |  | 24/08/2026 | 27/08/2026 | 14/08/2026 | 14/08/2026 | 1 | 1
ADIDAS | 0902972672-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1 | 23/09/2026 | 1 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972672 LF0726 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 1 |  | 1 |  |  | 2026-12-09 | 15/09/2026 |  |  | 1 |  | 1
ADIDAS | 0902972688-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 803 | 21/08/2026 | 803 | ID | ID29/05/2026 | G2Q | SHORTS | G2 | ok | (02/07/2026) | 21/08: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902972688 KY7184 | 16/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 27/07/2026 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 27/07/2026 | 2026-03-08 | 27/07/2026 | 2026-03-08 | 803 | 803 |  |  |  | 22/07/2026 | 29/07/2026 | 18/07/2026 | 2026-03-08 | 803 | 803
ADIDAS | 0902972711-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 56 | 2026-05-09 | 56 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | ok | 04/09: ex-fty 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902972711 KY5988 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-08 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-07-08 | 56 | 56 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 31/07/2026 | 56 | 56 |  |  |  | 22/07/2026 | 31/07/2026 | 30/07/2026 | 30/07/2026 | 56 | 56
ADIDAS | 0902972724-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 349 | 15/10/2026 | 349 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972724 LG9666 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | W SL WV TT BLACK |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 349 |  | 349 |  |  | 2026-01-10 | 2026-01-10 |  |  | 349 |  | 349
ADIDAS | 0902972758-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 330 | 15/10/2026 | 330 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972758 LG9661 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 330 |  | 330 |  |  | 28/09/2026 | 2026-01-10 |  |  | 330 |  | 330
ADIDAS | 0902972883-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 480 | 15/09/2026 | 480 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972883 LF0727 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 16/09/2026 | 27/08/2026 | 2026-10-09 | 480 | 479 | 1 |  |  | 19/08/2026 | 2026-12-09 | 24/08/2026 | 2026-09-09 | 480 | 480
ADIDAS | 0902972938-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 486 | 23/09/2026 | 486 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902972938 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 486 | 486 |  |  |  | 2026-12-08 | 29/08/2026 | 29/07/2026 | 31/07/2026 | 486 | 486 |  |  |  | 2026-10-08 | 27/08/2026 | 28/07/2026 | 31/07/2026 | 486 | 486
ADIDAS | 0902973524-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1200 | 15/10/2026 | 1200 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 19-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902973524 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902973619-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 1000 | 23/09/2026 | 1000 | AN | AN29/05/2026 | G3G,G3H,G3J | PANTS | G3 | ok | (19/06/2026) | 18/09: ex-fty. T2 Libolon, PI Date 31-May, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973619 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-04-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 1000 | 1000 |  |  |  | 30/07/2026 | 13/08/2026 | 31/07/2026 | 15/08/2026 | 1000 | 1000
ADIDAS | 0902973747-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 356 | 21/08/2026 | 356 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973747 KV7863 | 13/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 20/07/2026 | 24/07/2026 | 356 | 356 |  |  |  | 15/07/2026 | 21/07/2026 | 16/07/2026 | 24/07/2026 | 356 | 356
ADIDAS | 0902973776-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 23/09/2026 | 300 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902973776 KF5311 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 300 | 300 |  |  |  | 2026-03-08 | 29/08/2026 | 29/07/2026 | 30/07/2026 | 300 | 300 |  |  |  | 30/07/2026 | 27/08/2026 | 27/07/2026 | 29/07/2026 | 300 | 300
ADIDAS | 0902973810-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 399 | 2026-05-09 | 399 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902973810 LE5609 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/07/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 31/08/2026 | 31/07/2026 | 31/08/2026 | 399 | 399 |  |  |  | 27/07/2026 | 27/08/2026 | 30/07/2026 | 2026-07-08 | 399 | 399 |  |  |  | 20/07/2026 | 19/08/2026 | 30/07/2026 | 2026-06-08 | 399 | 399
ADIDAS | 0902973847-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (07/07/2026) |  | 07/09: ex-fty. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock, T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973847 LC5741 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902973850-1 LF0723 | BLACK | 105D | S2754MAS511B | 433 | 15/09/2026 | 433 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902973850 LF0723 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | M SL WV SHO BLACK |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 433 | 433 |  |  |  | 2026-02-09 | 2026-09-09 | 15/08/2026 | 2026-11-09 | 433 | 433
ADIDAS | 0902973860-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (29/06/2026) | ok | 07/09: ex-fty. T2 Kahatex, using fabric stock. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973860 KY6616 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 3S WV WB LND |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 26/08/2026 | 1 | 1 |  |  |  | 19/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 1 | 1
ADIDAS | 0902973878-1 LC5739 | OLIVE FOUR S27/BLACK | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (10/07/2026) |  | 07/09: ex-fty. T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 01-Jul, actual receives 09-Jul. T2 Kahatex, PI Date 07-Jul, using fabric stock. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973878 LC5739 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 3S WV WB LND OLIVE FOUR S27/BLACK |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902974162-1 LE8187 | BLACK | 105D | S2754MAS513 | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974162 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-11-08 | 2026-11-08 | 8 | 8 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-08-08 | 2026-11-08 | 8 | 8
ADIDAS | 0902974179-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974179 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902974202-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 542 | 2026-05-09 | 542 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974202 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 542 | 542 |  |  |  | 29/08/2026 | 2026-02-09 | 14/08/2026 | 28/08/2026 | 542 | 542
ADIDAS | 0902974244-1 LE8187 | BLACK | 105D | S2754MAS513 | 311 | 2026-05-09 | 311 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974244 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-09 | M SL WV TP PT BLACK |  | SS27 | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 311 | 311 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-05-08 | 2026-04-09 | 311 | 311
ADIDAS | 0902974263-1 LE8187 | BLACK | 105D | S2754MAS513 | 1425 | 2026-05-09 | 1425 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974263 LE8187 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 1425 | 1425 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-06-08 | 2026-11-09 | 1425 | 1405 | 20
ADIDAS | 0902974284-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1436 | 15/09/2026 | 1436 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974284 LD5446 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-07-09 | 14/09/2026 | 2026-07-09 | 2026-12-09 | 1436 | 1414 | 22 |  | 15 | 2026-03-09 | 2026-10-09 | 2026-12-08 | 2026-08-09 | 1436 | 1432 | 4
ADIDAS | 0902974308-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 353 | 2026-09-09 | 353 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974308 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-07-09 | 353 | 353 |  |  |  | 29/08/2026 | 2026-03-09 | 13/08/2026 | 2026-02-09 | 353 | 353
ADIDAS | 0902974332-1 LE8187 | BLACK | 105D | S2754MAS513 | 370 | 2026-05-09 | 370 | SI | SI29/05/2026 | G3D,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974332 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-03-09 | 14/08/2026 | 2026-01-09 | 370 | 370 |  |  |  | 2026-03-08 | 31/08/2026 | 2026-05-08 | 2026-04-09 | 370 | 368 | 2
ADIDAS | 0902975286-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 29 | 23/09/2026 | 29 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975286 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-10-08 | 2026-10-08 | 29 | 29 |  |  |  | 2026-03-08 | 2026-06-08 | 2026-01-08 | 2026-01-08 | 29 | 29 |  |  |  | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 29 | 29
ADIDAS | 0902975694-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1272 | 30/09/2026 | 1272 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902975694 LD0287 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 1272 |  | 1272 |  |  | 16/09/2026 | 17/09/2026 | 2026-05-09 | 2026-10-09 | 1272 | 1268 | 4 |  |  | 14/09/2026 | 15/09/2026 | 2026-04-09 | 2026-10-09 | 1272 | 1268 | 4
ADIDAS | 0902975717-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1200 | 2026-07-10 | 1200 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902975717 LE5390 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 1200 |  | 1200 |  |  | 26/09/2026 | 26/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902975773-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902975773 LE5391 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27 | 30/09/2026 | 2026-05-10 |  |  | 4800 |  | 4800 |  |  | 26/09/2026 | 2026-01-10 |  |  | 4800 |  | 4800
ADIDAS | 0902975811-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 80 | 30/09/2026 | 80 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975811 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 80 |  | 80 |  |  | 2026-12-09 | 14/09/2026 | 2026-04-08 | 2026-04-08 | 80 | 80 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 80 | 80
ADIDAS | 0902975837-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 20 | 21/08/2026 | 20 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975837 LG9660 | 13/08/2026 | KAHATEX CIJERAH | PERU | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 2026-03-08 | 20 | 20 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 2026-03-08 | 20 | 20
ADIDAS | 0902975855-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 31 | 30/09/2026 | 31 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975855 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 31 | 31 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 31/07/2026 | 31 | 31 |  |  |  | 31/08/2026 | 2026-03-09 | 27/07/2026 | 28/07/2026 | 31 | 31
ADIDAS | 0902975887-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 2400 | 2026-07-10 | 2400 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975887 LE7510 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-07-10 | 2026-10-10 |  |  | 2400 |  | 2400
ADIDAS | 0902975946-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | 23/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Sep. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975946 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 21/09/2026 | 28/09/2026 |  |  | 2400 |  | 2400 |  |  | 17/09/2026 | 24/09/2026 | 26/08/2026 | 2026-07-09 | 2400 | 1864 | 536
ADIDAS | 0902975975-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975975 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-09 | 17/09/2026 | 2026-03-09 | 2026-07-09 | 2400 | 1410 | 990 |  |  | 2026-02-09 | 14/09/2026 | 22/08/2026 | 2026-08-09 | 2400 | 2356 | 44
ADIDAS | 0902976008-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3600 | 2026-07-10 | 3600 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976008 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 15/10/2026 | 20/10/2026 |  |  | 3600 |  | 3600 |  |  | 2026-12-10 | 16/10/2026 |  |  | 3600 |  | 3600
ADIDAS | 0902976049-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 2026-07-10 | 6000 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976049 LE7509 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 17/10/2026 |  |  | 6000 |  | 6000 |  |  | 2026-05-10 | 14/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0902976088-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 2026-07-10 | 8400 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976088 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 17/10/2026 | 29/10/2026 |  |  | 8400 |  | 8400 |  |  | 14/10/2026 | 26/10/2026 |  |  | 8400 |  | 8400
ADIDAS | 0902976952-1 LG9669 | BLACK | 120D | S2754WAS514C | 8 | 15/10/2026 | 8 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902976952 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-09-10 | W SL WV SK BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 8 |  | 8 |  |  | 2026-06-10 | 2026-07-10 |  |  | 8 |  | 8
ADIDAS | 0902976974-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 8 | 15/10/2026 | 8 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902976974 LF0726 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 16/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 8 |  | 8 |  |  | 2026-12-09 | 15/09/2026 |  |  | 8 |  | 8
ADIDAS | 0902977037-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 508 | 21/08/2026 | 508 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902977037 KV7863 | 13/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 508 | 508 |  |  |  | 15/07/2026 | 21/07/2026 | 17/07/2026 | 28/07/2026 | 508 | 508
ADIDAS | 0902977144-1 LE8187 | BLACK | 105D | S2754MAS513 | 342 | 2026-05-09 | 342 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902977144 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 14/08/2026 | 342 | 342 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-05-08 | 2026-04-09 | 342 | 342
ADIDAS | 0902977685-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1796 | 30/09/2026 | 1796 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 29/09: ex-fty (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902977685 KX3655 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 23/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 23/09/2026 | 25/09/2026 |  |  | 1796 |  | 1796 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1796 |  | 1796 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1796 |  | 1796
ADIDAS | 0902977729-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 466 | 15/10/2026 | 466 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | HT+PAD SUB PROCESS_V3 | 0902977729 LD0288 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 466 | 466 |  |  |  | 2026-12-08 | 29/08/2026 | 25/07/2026 | 2026-06-08 | 466 | 466 |  |  |  | 2026-10-08 | 27/08/2026 | 24/07/2026 | 2026-05-08 | 466 | 466
ADIDAS | 0902977769-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 497 | 30/09/2026 | 497 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977769 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 497 |  | 497 |  |  | 17/09/2026 | 18/09/2026 |  |  | 497 |  | 497 |  |  | 15/09/2026 | 16/09/2026 |  |  | 497 |  | 497
ADIDAS | 0902977806-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 198 | 23/09/2026 | 198 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977806 LD0288 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 198 | 198 |  |  |  | 2026-12-08 | 29/08/2026 | 30/07/2026 | 2026-07-08 | 198 | 198 |  |  |  | 2026-10-08 | 27/08/2026 | 29/07/2026 | 2026-06-08 | 198 | 198
ADIDAS | 0902977843-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 200 | 15/10/2026 | 200 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902977843 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 200 |  | 200 |  |  | 22/09/2026 | 22/09/2026 |  |  | 200 |  | 200 |  |  | 19/09/2026 | 19/09/2026 |  |  | 200 |  | 200
ADIDAS | 0902977919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 154 | 30/09/2026 | 154 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977919 LD0288 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 154 | 154 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 2026-01-08 | 154 | 154 |  |  |  | 31/08/2026 | 2026-03-09 | 30/07/2026 | 2026-01-08 | 154 | 154
ADIDAS | 0902977969-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 879 | 30/09/2026 | 879 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977969 KX3655 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 879 |  | 879 |  |  | 18/09/2026 | 19/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879
ADIDAS | 0902978212-1 LE0355 | BLACK | 105D | S2754MAS514 | 2156 | 30/09/2026 | 2156 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978212 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/09/2026 | M SL WV CU PT BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 2156 |  | 2156 |  |  | 25/09/2026 | 28/09/2026 | 2026-01-09 | 2026-12-09 | 2156 | 2044 | 112 |  | 1
ADIDAS | 0902978235-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 2398 | 30/09/2026 | 2398 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978235 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 15/09/2026 | 17/09/2026 |  |  | 2398 |  | 2398 |  |  | 2026-11-09 | 14/09/2026 | 2026-11-08 | 20/08/2026 | 2398 | 2398 |  |  |  | 2026-09-09 | 2026-11-09 | 2026-11-08 | 19/08/2026 | 2398 | 2398
ADIDAS | 0902978263-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1644 | 30/09/2026 | 1644 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978263 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 1644 |  | 1644 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1557 | 87 |  |  | 16/09/2026 | 17/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1556 | 88
ADIDAS | 0902978291-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 2268 | 30/09/2026 | 2268 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978291 LD0287 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 2268 |  | 2268 |  |  | 17/09/2026 | 18/09/2026 | 2026-07-09 | 2026-11-09 | 2268 | 2133 | 135 |  |  | 15/09/2026 | 16/09/2026 | 2026-07-09 | 2026-10-09 | 2268 | 2133 | 135
ADIDAS | 0902978328-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1623 | 30/09/2026 | 1623 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978328 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 1623 |  | 1623 |  |  | 25/09/2026 | 29/09/2026 |  |  | 1623 |  | 1623
ADIDAS | 0902978352-1 LF0718 | BLACK | 105D | S2754MAS512B | 1886 | 15/09/2026 | 1886 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978352 LF0718 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/09/2026 | M SL WV OH PT BLACK |  | SS27 | 17/09/2026 | 21/09/2026 |  |  | 1886 |  | 1886 |  |  | 14/09/2026 | 17/09/2026 |  |  | 1886 |  | 1886
ADIDAS | 0902978382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1442 | 15/09/2026 | 1442 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978382 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 16/09/2026 | 2026-02-09 | 2026-11-09 | 1442 | 1423 | 19 |  |  | 27/08/2026 | 2026-12-09 | 28/08/2026 | 2026-10-09 | 1442 | 1435 | 7
ADIDAS | 0902978413-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 1394 | 15/09/2026 | 1394 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978413 LG9670 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | W SL WV PT AURORA COFFEE S26 |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1394 | 1100 | 294 |  | 216 | 2026-05-09 | 2026-10-09 | 2026-07-09 | 2026-10-09 | 1394 | 1338 | 56
ADIDAS | 0902978440-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 767 | 30/09/2026 | 767 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978440 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 767 |  | 767 |  |  | 22/09/2026 | 24/09/2026 | 14/09/2026 | 14/09/2026 | 767 | 261 | 506
ADIDAS | 0902978469-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 491 | 30/09/2026 | 491 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978469 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 491 |  | 491 |  |  | 19/09/2026 | 21/09/2026 |  |  | 491 |  | 491
ADIDAS | 0902978495-1 LE8187 | BLACK | 105D | S2754MAS513 | 1353 | 15/09/2026 | 1353 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978495 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 15/09/2026 | 2026-04-09 | 2026-09-09 | 1353 | 1115 | 238 |  |  | 2026-02-09 | 2026-11-09 | 28/08/2026 | 2026-10-09 | 1353 | 1232 | 121
ADIDAS | 0902978547-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1342 | 15/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978547 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 16/09/2026 | 26/08/2026 | 14/09/2026 | 1342 | 1134 | 208 |  | 81 | 19/08/2026 | 2026-12-09 | 21/08/2026 | 2026-11-09 | 1342 | 1174 | 168
ADIDAS | 0902978578-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 870 | 30/09/2026 | 870 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 20-Jun, actual receives 06-AUg (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978578 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 870 |  | 870 |  |  | 15/09/2026 | 19/09/2026 | 28/08/2026 | 2026-03-09 | 870 | 537 | 333
ADIDAS | 0902978593-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 655 | 21/08/2026 | 655 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902978593 JE6372 | 13/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/07/2026 | M 3S FT SWT |  | FW26 | 20/07/2026 | 2026-07-08 | 21/07/2026 | 31/07/2026 | 655 | 655 |  |  |  | 15/07/2026 | 2026-04-08 | 15/07/2026 | 31/07/2026 | 655 | 655
ADIDAS | 0902978632-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2607 | 21/08/2026 | 2607 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902978632 KV7863 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/07/2026 | 13/08/2026 | 23/07/2026 | 2026-12-08 | 2607 | 2607 |  |  |  | 20/07/2026 | 2026-10-08 | 21/07/2026 | 2026-12-08 | 2607 | 2607
ADIDAS | 0902978872-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 339 | 2026-09-09 | 339 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978872 LD5446 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-03-09 | 339 | 339 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 20/08/2026 | 339 | 339
ADIDAS | 0902978908-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 2026-05-09 | 300 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978908 LE8181 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-03-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0902978941-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 23/09/2026 | 300 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978941 LF0729 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 18/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0902978973-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 347 | 15/09/2026 | 347 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual recieves 27-Jun (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978973 LF0726 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 16/09/2026 | 2026-07-09 | 2026-12-09 | 347 | 343 | 4 |  | 3 | 2026-01-09 | 2026-12-09 | 31/08/2026 | 2026-11-09 | 347 | 347
ADIDAS | 0902978999-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1030 | 2026-12-09 | 1030 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902978999 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 31/08/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1030 | 1030 |  |  |  | 27/08/2026 | 2026-04-09 | 31/07/2026 | 2026-07-08 | 1030 | 1030 |  |  |  | 24/08/2026 | 2026-02-09 | 31/07/2026 | 2026-06-08 | 1030 | 1030
ADIDAS | 0902979020-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 1006 | 2026-12-09 | 1006 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979020 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-05-09 | 2026-08-09 | 1006 | 1006 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-03-08 | 13/08/2026 | 1006 | 1006 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-01-08 | 2026-12-08 | 1006 | 1006
ADIDAS | 0902979047-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 339 | 21/08/2026 | 339 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902979047 KV7863 | 13/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 22/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 22/07/2026 | 28/07/2026 | 339 | 339 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 27/07/2026 | 339 | 339
ADIDAS | 0902979072-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 408 | 31/08/2026 | 408 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979072 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 21/08/2026 | 2026-10-08 | 21/08/2026 | 408 | 408 |  |  |  | 2026-06-08 | 18/08/2026 | 29/07/2026 | 31/07/2026 | 408 | 408 |  |  |  | 2026-04-08 | 13/08/2026 | 24/07/2026 | 28/07/2026 | 408 | 408
ADIDAS | 0902979096-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 495 | 31/08/2026 | 495 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979096 KX3655 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 28/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/08/2026 | 29/08/2026 | 28/08/2026 | 29/08/2026 | 495 | 495 |  |  |  | 24/08/2026 | 26/08/2026 | 21/08/2026 | 29/08/2026 | 495 | 495 |  |  |  | 20/08/2026 | 21/08/2026 | 21/08/2026 | 27/08/2026 | 495 | 495
ADIDAS | 0902979127-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 530 | 31/08/2026 | 530 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979127 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 18/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 530 | 530 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-10-08 | 18/08/2026 | 530 | 530 |  |  |  | 2026-10-08 | 18/08/2026 | 2026-10-08 | 14/08/2026 | 530 | 530
ADIDAS | 0902979825-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 2026-12-09 | 123 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902979825 LD5446 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 123 | 123 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 123 | 123
ADIDAS | 0902980168-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 574 | 30/09/2026 | 574 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980168 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 574 |  | 574 |  |  | 18/09/2026 | 21/09/2026 |  |  | 574 |  | 574
ADIDAS | 0902980203-1 LE8187 | BLACK | 105D | S2754MAS513 | 812 | 15/09/2026 | 812 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980203 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | M SL WV TP PT BLACK |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 812 |  | 812 |  |  | 2026-11-09 | 14/09/2026 | 2026-05-09 | 2026-12-09 | 812 | 462 | 350 |  | 459
ADIDAS | 0902980238-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 521 | 21/08/2026 | 521 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 28-May. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980238 KZ3205 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/07/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 17/07/2026 | 2026-07-08 | 20/07/2026 | 2026-06-08 | 521 | 521 |  |  |  | 14/07/2026 | 2026-04-08 | 15/07/2026 | 19/08/2026 | 521 | 521
ADIDAS | 0902980266-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 612 | 21/08/2026 | 612 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 12-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980266 KZ3198 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 27/07/2026 | 14/08/2026 | 28/07/2026 | 13/08/2026 | 612 | 612 |  |  |  | 22/07/2026 | 2026-11-08 | 24/07/2026 | 14/08/2026 | 612 | 612
ADIDAS | 0902980284-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 356 | 26/08/2026 | 356 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980284 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 2026-10-08 | 21/08/2026 | 356 | 356 |  |  |  | 2026-11-08 | 20/08/2026 | 27/07/2026 | 2026-01-09 | 356 | 356
ADIDAS | 0902980314-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 324 | 21/08/2026 | 324 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980314 KV7963 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 23/07/2026 | 28/07/2026 | 324 | 324 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 29/07/2026 | 324 | 324
ADIDAS | 0902980345-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 334 | 26/08/2026 | 334 | SI | SI29/05/2026 | G1H | JACKET | G1 | (29/06/2026) | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 12-Aug. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980345 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 334 | 334 |  |  |  | 13/08/2026 | 20/08/2026 | 14/08/2026 | 24/08/2026 | 334 | 334
ADIDAS | 0902980371-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 317 | 26/08/2026 | 317 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980371 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 2026-12-08 | 24/08/2026 | 317 | 317 |  |  |  | 2026-11-08 | 20/08/2026 | 29/07/2026 | 2026-12-08 | 317 | 317
ADIDAS | 0902980401-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 318 | 26/08/2026 | 318 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980401 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/07/2026 | 19/08/2026 | 29/07/2026 | 19/08/2026 | 318 | 318 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 21/08/2026 | 318 | 318
ADIDAS | 0902980431-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 26/08/2026 | 344 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980431 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 13/08/2026 | 21/08/2026 | 344 | 344 |  |  |  | 2026-11-08 | 20/08/2026 | 22/07/2026 | 21/08/2026 | 344 | 344
ADIDAS | 0902980461-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 895 | 15/09/2026 | 895 | AN | AN29/05/2026 | G3B,G3E,G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980461 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 14/09/2026 | 895 | 713 | 182 |  | 7 | 20/08/2026 | 2026-11-09 | 2026-06-08 | 26/08/2026 | 895 | 864 | 31
ADIDAS | 0902980492-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1236 | 15/09/2026 | 1236 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980492 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1236 | 1191 | 45 |  | 41 | 2026-05-09 | 2026-11-09 | 2026-11-08 | 2026-10-09 | 1236 | 1214 | 22
ADIDAS | 0902980497-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1200 | 30/09/2026 | 1200 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902980497 LD0287 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 17/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1200 |  | 1200 |  |  | 14/09/2026 | 15/09/2026 | 2026-03-08 | 2026-12-09 | 1200 | 1189 | 11 |  | 16 | 2026-11-09 | 2026-12-09 | 2026-01-08 | 2026-10-09 | 1200 | 1189 | 11
ADIDAS | 0902980530-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 901 | 15/09/2026 | 901 | AN | AN29/05/2026 | G1B,G1J | JACKET | G1 | ok | (19/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980530 LG9666 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-09 | W SL WV TT BLACK |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 901 | 710 | 191 |  | 60 | 2026-04-09 | 2026-11-09 | 22/08/2026 | 2026-08-09 | 901 | 805 | 96
ADIDAS | 0902980559-1 LH3758 | BLACK | 120D | S2754WAS518B | 800 | 30/09/2026 | 800 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980559 LH3758 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | W SL WV BR PT BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 800 |  | 800 |  |  | 19/09/2026 | 21/09/2026 |  |  | 800 |  | 800
ADIDAS | 0902980595-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 1066 | 15/09/2026 | 1066 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980595 LG9664 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 1066 |  | 1066 |  |  | 2026-11-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 1066 | 816 | 250 |  | 17
ADIDAS | 0902980626-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 1094 | 30/09/2026 | 1094 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980626 LH3761 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 25/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 1094 |  | 1094 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1094 |  | 1094
ADIDAS | 0902980662-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1530 | 15/09/2026 | 1530 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980662 LE8181 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-12-09 | 17/09/2026 | 2026-12-09 | 2026-12-09 | 1530 | 105 | 1425 |  | 105 | 2026-09-09 | 14/09/2026 | 2026-11-09 | 13/09/2026 | 1530 | 575 | 955 |  | 441
ADIDAS | 0902980942-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 2026-07-10 | 300 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980942 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M SL WV TT BLACK |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-05-10 |  |  | 300 |  | 300
ADIDAS | 0902980969-1 LE8187 | BLACK | 105D | S2754MAS513 | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980969 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M SL WV TP PT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 420 |  | 420 |  |  | 2026-10-10 | 13/10/2026 |  |  | 420 |  | 420
ADIDAS | 0902981008-1 LE8187 | BLACK | 105D | S2754MAS513 | 300 | 2026-07-10 | 300 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 08-Jul. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981008 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M SL WV TP PT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0902981035-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 360 | 2026-07-10 | 360 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981035 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-10-09 | 16/09/2026 | 2026-11-09 | 2026-12-09 | 360 | 210 | 150 |  | 135 | 2026-07-09 | 2026-12-09 | 2026-04-09 | 2026-04-09 | 360 | 293 | 67
ADIDAS | 0902981042-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 120 | 2026-09-09 | 120 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981042 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 120 | 120 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 14/08/2026 | 120 | 120
ADIDAS | 0902981068-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 532 | 2026-05-09 | 532 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 672027 | HT+PAD SUB PROCESS_V3 | 0902981068 KX3650 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 2026-05-08 | 30/07/2026 | 2026-05-08 | 532 | 532 |  |  |  | 27/07/2026 | 31/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532 |  |  |  | 23/07/2026 | 29/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532
ADIDAS | 0902981069-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 300 | 28/08/2026 | 300 | AN | AN29/05/2026 | G3E | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981069 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 300 | 300 |  |  |  | 29/07/2026 | 2026-11-08 | 31/07/2026 | 21/08/2026 | 300 | 300
ADIDAS | 0902981094-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 21/08/2026 | 390 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516406 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981094 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 23/07/2026 | 2026-03-08 | 24/07/2026 | 31/07/2026 | 390 | 390 |  |  |  | 20/07/2026 | 29/07/2026 | 22/07/2026 | 2026-05-08 | 390 | 390
ADIDAS | 0902981100-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 672027 | HT+PAD SUB PROCESS_V3 | 0902981100 KX3655 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 | 2026-10-09 | 2026-12-09 | 300 | 240 | 60 |  | 1 | 15/09/2026 | 16/09/2026 | 2026-09-09 | 2026-12-09 | 300 | 240 | 60 |  | 1
ADIDAS | 0902981242-1 LG9669 | BLACK | 120D | S2754WAS514C | 15 | 30/09/2026 | 15 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902981242 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 15 |  | 15 |  |  | 21/09/2026 | 23/09/2026 | 29/08/2026 | 2026-01-09 | 15 | 15
ADIDAS | 0902981276-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 3 | 21/08/2026 | 3 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (KN GLT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981276 LG9660 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 30/07/2026 | 3 | 3 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 28/07/2026 | 3 | 3
ADIDAS | 0902981317-1 LD0282 | OLIVE TWO S27 | 120D | S2608WR0900 | 185 | 30/09/2026 | 185 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). 1st Art (TC 10 pcs) 650010 | HT+PAD SUB PROCESS_V3 | 0902981317 LD0282 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/09/2026 | Run Ess Tee W OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 17/09/2026 |  |  | 185 |  | 185 |  |  | 14/09/2026 | 14/09/2026 | 2026-01-08 | 2026-08-08 | 185 | 185 |  |  |  | 2026-11-09 | 2026-11-09 | 31/07/2026 | 2026-07-08 | 185 | 185
ADIDAS | 0902981358-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 10 | 15/10/2026 | 10 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0902981358 LD0285 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10
ADIDAS | 0902981395-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 21 | 30/09/2026 | 21 | SI | SI29/05/2026 | G3A | SHORTS | G3 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981395 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-09-09 | 2026-09-09 | 21 | 21 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 21 | 21
ADIDAS | 0902981438-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 30/09/2026 | 120 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0902981438 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27-SPOMA | 24/09/2026 | 26/09/2026 |  |  | 120 |  | 120 |  |  | 21/09/2026 | 23/09/2026 | 28/08/2026 | 2026-05-09 | 120 | 114 | 6
ADIDAS | 0902981654-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 384 | 26/08/2026 | 384 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902981654 LD0287 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 18/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 384 | 384 |  |  |  | 2026-12-08 | 20/08/2026 | 31/07/2026 | 2026-12-08 | 384 | 384 |  |  |  | 2026-10-08 | 18/08/2026 | 29/07/2026 | 2026-12-08 | 384 | 384
ADIDAS | 0902981678-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 553 | 26/08/2026 | 553 | SA | SA29/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902981678 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-04-08 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-04-08 | 21/08/2026 | 2026-04-08 | 20/08/2026 | 553 | 553 |  |  |  | 30/07/2026 | 18/08/2026 | 30/07/2026 | 2026-01-08 | 553 | 553 |  |  |  | 28/07/2026 | 13/08/2026 | 27/07/2026 | 2026-01-08 | 553 | 553
ADIDAS | 0902981755-1 LF0723 | BLACK | 105D | S2754MAS511B | 1697 | 30/09/2026 | 1697 | SI | SI29/05/2026 | G3D | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Kahatex, PI Date 28-Jul, actual 10-Aug. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981755 LF0723 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | M SL WV SHO BLACK |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 1697 |  | 1697 |  |  | 15/09/2026 | 18/09/2026 |  |  | 1697 |  | 1697
ADIDAS | 0902981783-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 1824 | 23/09/2026 | 1824 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902981783 LD0288 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 18/08/2026 | 2026-01-09 | 1824 | 1824 |  |  |  | 2026-11-08 | 29/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824
ADIDAS | 0902981811-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 712 | 15/09/2026 | 712 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981811 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 16/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 712 |  | 712 |  |  | 2026-12-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 712 | 598 | 114 |  | 54
ADIDAS | 0902981835-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 1342 | 30/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981835 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/08/2026 | 2026-10-09 | 20/08/2026 | 2026-10-09 | 1342 | 1342 |  |  |  | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-03-09 | 1342 | 1342
ADIDAS | 0902981856-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 1297 | 15/09/2026 | 1297 | SI | SI29/05/2026 | G3A,G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981856 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 1297 | 1245 | 52 |  | 241 | 2026-07-09 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 1297 | 1270 | 27 |  | 10
ADIDAS | 0902981919-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 425 | 15/09/2026 | 425 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981919 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 425 | 133 | 292 |  | 61 | 2026-04-09 | 2026-11-09 | 2026-01-09 | 2026-07-09 | 425 | 356 | 69
ADIDAS | 0902981952-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 300 | 30/09/2026 | 300 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902981952 LG9668 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 26/09/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 24/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902981983-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 619 | 15/09/2026 | 619 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981983 LG9661 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 619 | 139 | 480 |  | 36 | 2026-09-09 | 2026-11-09 | 26/08/2026 | 2026-10-09 | 619 | 545 | 74
ADIDAS | 0902982011-1 KZ3229 | GREY FIVE F17/WHITE | 90D | S2754WESS703WV-MTF | 744 | 21/08/2026 | 744 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun (PO NT-351). T2 Libolon, PI Date 28-May, actual receives 28-May. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982011 KZ3229 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 13S WV BER SHO GREY FIVE F17/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 30/07/2026 | 14/08/2026 | 744 | 744 |  |  |  | 27/07/2026 | 2026-11-08 | 25/07/2026 | 13/08/2026 | 744 | 744
ADIDAS | 0902982057-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 1502 | 21/08/2026 | 1502 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 12-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982057 KZ3198 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 28/07/2026 | 19/08/2026 | 29/07/2026 | 18/08/2026 | 1502 | 1502 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 14/08/2026 | 1502 | 1502
ADIDAS | 0902982085-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 814 | 30/09/2026 | 814 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902982085 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/09/2026 | W SL WV PT BLACK |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 814 |  | 814 |  |  | 25/09/2026 | 26/09/2026 |  |  | 814 |  | 814
ADIDAS | 0902982124-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 577 | 21/08/2026 | 577 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 28-May. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982124 KZ3205 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/07/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 22/07/2026 | 14/08/2026 | 24/07/2026 | 14/08/2026 | 577 | 577 |  |  |  | 17/07/2026 | 2026-11-08 | 15/07/2026 | 20/08/2026 | 577 | 577
ADIDAS | 0902982159-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 10 | 2026-05-09 | 10 | AN | AN29/05/2026 | G1E | T-SHIRT | G1 | ok | ok | 04/09: ex-fty (KN GLT). T2 Libolon, actual receives 29-Apr (PO 25063167). T2 Fu Hsun, actual receives 23-Apr (PO 25063168). 650010 | HT SUB PROCESS_V1 | 0902982159 IT1824 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 10 | 10 |  |  |  | 14/07/2026 | 16/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10
ADIDAS | 0902982649-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 300 | 21/08/2026 | 300 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 18-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 29-May (PO NT-347). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982649 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 28/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 300 | 300 |  |  |  | 23/07/2026 | 2026-11-08 | 27/07/2026 | 2026-10-08 | 300 | 300
ADIDAS | 0902982718-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 400 | 2026-03-09 | 400 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | ok | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982718 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-07-08 | 400 | 400 |  |  |  | 24/07/2026 | 2026-05-08 | 27/07/2026 | 29/08/2026 | 400 | 400
ADIDAS | 0902982800-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902982800 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902982852-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982852 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 320 |  | 320 |  |  | 21/09/2026 | 22/09/2026 | 2026-07-08 | 15/08/2026 | 320 | 320 |  |  |  | 18/09/2026 | 19/09/2026 | 2026-07-08 | 14/08/2026 | 320 | 320
ADIDAS | 0902982880-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982880 LD0287 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 19/09/2026 | 21/09/2026 |  |  | 350 |  | 350 |  |  | 17/09/2026 | 18/09/2026 |  |  | 350 |  | 350
ADIDAS | 0902982910-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982910 LD0285 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 19/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902982939-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982939 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 350 |  | 350 |  |  | 21/09/2026 | 22/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350 |  |  |  | 18/09/2026 | 19/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350
ADIDAS | 0902982968-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 414 | 30/09/2026 | 414 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982968 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 21/09/2026 | 21/09/2026 |  |  | 414 |  | 414 |  |  | 17/09/2026 | 17/09/2026 | 25/07/2026 | 2026-01-08 | 414 | 414 |  |  |  | 15/09/2026 | 15/09/2026 | 25/07/2026 | 31/07/2026 | 414 | 414
ADIDAS | 0902983088-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 320 | 30/09/2026 | 320 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516254 | HT+PAD SUB PROCESS_V3 | 0902983088 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 15/09/2026 | 15/09/2026 |  |  | 320 |  | 320 |  |  | 2026-11-09 | 2026-11-09 | 26/08/2026 | 2026-05-09 | 320 | 320 |  |  |  | 2026-09-09 | 2026-09-09 | 26/08/2026 | 2026-05-09 | 320 | 320
ADIDAS | 0902983300-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983300 KX3651 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 108 |  | 108 |  |  | 23/09/2026 | 23/09/2026 | 25/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 21/09/2026 | 21/09/2026 | 24/07/2026 | 31/07/2026 | 108 | 108
ADIDAS | 0902983336-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983336 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 15/09/2026 | 15/09/2026 |  |  | 108 |  | 108 |  |  | 2026-11-09 | 2026-11-09 | 26/08/2026 | 2026-08-09 | 108 | 108 |  |  |  | 2026-09-09 | 2026-09-09 | 26/08/2026 | 2026-08-09 | 108 | 108
ADIDAS | 0902983370-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 108 | 23/09/2026 | 108 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983370 KF5311 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 108 | 108 |  |  |  | 2026-06-08 | 29/08/2026 | 30/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 2026-04-08 | 27/08/2026 | 29/07/2026 | 30/07/2026 | 108 | 108
ADIDAS | 0902983535-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F,G3K | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902983535 JE8969 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 1200 | 1200 |  |  |  | 15/07/2026 | 2026-03-08 | 2026-09-07 | 2026-05-08 | 1200 | 1200
ADIDAS | 0902983568-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902983568 JE6346 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 1201 | 1201 |  |  |  | 16/07/2026 | 29/07/2026 | 18/07/2026 | 22/07/2026 | 1201 | 1201
ADIDAS | 0902983877-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 408 | 2026-05-09 | 408 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983877 LE8181 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 408 | 408 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-05-09 | 408 | 408
ADIDAS | 0902983897-1 LE8187 | BLACK | 105D | S2754MAS513 | 1822 | 2026-05-09 | 1822 | SI | SI29/05/2026 | G3D,G3I,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983897 LE8187 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-05-09 | 2026-12-08 | 2026-04-09 | 1822 | 1822 |  |  |  | 2026-03-08 | 2026-02-09 | 2026-07-08 | 2026-04-09 | 1822 | 1820 | 2
ADIDAS | 0902983913-1 LF0718 | BLACK | 105D | S2754MAS512B | 647 | 2026-05-09 | 647 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983913 LF0718 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT BLACK |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 647 | 647 |  |  |  | 27/08/2026 | 2026-02-09 | 14/08/2026 | 2026-04-09 | 647 | 647
ADIDAS | 0902983933-1 LF0723 | BLACK | 105D | S2754MAS511B | 471 | 2026-12-09 | 471 | SI | SI29/05/2026 | G3D,G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983933 LF0723 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO BLACK |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 471 | 471 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-09-09 | 471 | 471
ADIDAS | 0902983951-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 15/09/2026 | 100 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983951 LG9664 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 100 |  | 100 |  |  | 2026-12-09 | 15/09/2026 | 2026-11-09 | 2026-11-09 | 100 | 40 | 60
ADIDAS | 0902983960-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 100 | 2026-12-09 | 100 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983960 LF0725 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-12-08 | 2026-03-09 | 100 | 100
ADIDAS | 0902983978-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983978 LG9673 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 22/09/2026 | 22/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902983990-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983990 LG9674 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 24/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 21/09/2026 | 22/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902984005-1 LH3758 | BLACK | 120D | S2754WAS518B | 400 | 30/09/2026 | 400 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902984005 LH3758 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | W SL WV BR PT BLACK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 400 |  | 400 |  |  | 18/09/2026 | 19/09/2026 |  |  | 400 |  | 400
ADIDAS | 0902984019-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902984019 LG9666 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 19/09/2026 | 31/08/2026 | 2026-03-09 | 300 | 267 | 33
ADIDAS | 0902985687-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985687 JE6374 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 29/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 2026-06-08 | 2026-02-09 | 1201 | 1201
ADIDAS | 0902985715-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 1200 | 15/09/2026 | 1200 | SI | SI29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902985715 JE8949 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-01-09 | M BL FT SWT |  | FW26 | 2026-01-09 | 2026-12-09 | 2026-01-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 28/08/2026 | 2026-09-09 | 29/07/2026 | 2026-03-09 | 1200 | 1200
ADIDAS | 0902985747-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902985747 IN6163 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 23/07/2026 | M BL FT PT |  | FW26 | 23/07/2026 | 2026-03-08 | 22/07/2026 | 30/07/2026 | 1200 | 1200 |  |  |  | 20/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 1200 | 1200
ADIDAS | 0902985818-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1201 | 2026-12-09 | 1201 | AT | AT29/05/2026 | G3C,G3D | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902985818 JD1881 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/07/2026 | M 3S FT TC PT |  | FW26 | 28/07/2026 | 2026-12-08 | 29/07/2026 | 2026-10-08 | 1201 | 1201 |  |  |  | 23/07/2026 | 2026-07-08 | 20/07/2026 | 2026-01-08 | 1201 | 1201
ADIDAS | 0902985896-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 1970 | 21/08/2026 | 1970 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0902985896 IU0217 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-10-07 | IN RANGE |  | FW26 | 2026-10-07 | 23/07/2026 | 2026-09-07 | 22/07/2026 | 1970 | 1970 |  |  |  | 2026-07-07 | 20/07/2026 | 2026-03-07 | 21/07/2026 | 1970 | 1970
ADIDAS | 0902985931-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985931 JE6372 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 15/07/2026 | 18/08/2026 | 1201 | 1201
ADIDAS | 0902986122-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 112 | 2026-07-10 | 112 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902986122 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 112 |  | 112 |  |  | 2026-03-10 | 2026-03-10 |  |  | 112 |  | 112 |  |  | 2026-01-10 | 2026-01-10 |  |  | 112 |  | 112
ADIDAS | 0902987661-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 615 | 21/08/2026 | 615 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 838103 | PRINT L3 SUB PROCESS_V3 | 0902987661 IU0217 | 13/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 23/07/2026 | 13/07/2026 | 22/07/2026 | 615 | 615 |  |  |  | 2026-09-07 | 20/07/2026 | 2026-03-07 | 20/07/2026 | 615 | 615
ADIDAS | 0902987761-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 540 | 15/10/2026 | 540 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987761 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 540 |  | 540 |  |  | 24/09/2026 | 25/09/2026 |  |  | 540 |  | 540 |  |  | 22/09/2026 | 23/09/2026 |  |  | 540 |  | 540
ADIDAS | 0902987861-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 529 | 15/10/2026 | 529 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987861 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 529 |  | 529 |  |  | 24/09/2026 | 25/09/2026 |  |  | 529 |  | 529 |  |  | 22/09/2026 | 23/09/2026 |  |  | 529 |  | 529
ADIDAS | 0902987900-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902987900 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 22/09/2026 | 2026-12-08 | 13/08/2026 | 300 | 244 | 56 |  |  | 2026-05-08 | 18/09/2026 | 2026-10-08 | 31/08/2026 | 300 | 266 | 34
ADIDAS | 0902987944-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 28/08/2026 | 300 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902987944 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 13/08/2026 | 2026-10-08 | 14/08/2026 | 300 | 300 |  |  |  | 2026-05-08 | 2026-10-08 | 2026-01-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902988860-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 231 | 2026-07-10 | 231 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988860 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 231 |  | 231 |  |  | 16/10/2026 | 17/10/2026 |  |  | 231 |  | 231 |  |  | 2026-10-10 | 2026-12-10 |  |  | 231 |  | 231
ADIDAS | 0902988896-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 481 | 15/09/2026 | 481 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 14/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988896 KC8152 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-05-09 | 2026-11-09 | 481 | 433 | 48 |  |  | 2026-02-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 481 | 481 |  |  |  | 27/08/2026 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 481 | 481
ADIDAS | 0902990795-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 302 | 21/08/2026 | 302 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 839055 | PRINT L3 SUB PROCESS_V3 | 0902990795 IU0217 | 13/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 23/07/2026 | 14/07/2026 | 22/07/2026 | 302 | 302 |  |  |  | 2026-09-07 | 20/07/2026 | 2026-04-07 | 20/07/2026 | 302 | 302
ADIDAS | 0902990885-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 110 | 15/10/2026 | 110 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990885 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 110 |  | 110 |  |  | 24/09/2026 | 24/09/2026 |  |  | 110 |  | 110 |  |  | 22/09/2026 | 22/09/2026 |  |  | 110 |  | 110
ADIDAS | 0902993705-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 2026-12-09 | 368 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (19/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993705 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-06-08 | 368 | 368 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 19/08/2026 | 368 | 368
ADIDAS | 0902993733-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 371 | 28/08/2026 | 371 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516240 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993733 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 371 | 371 |  |  |  | 24/07/2026 | 2026-11-08 | 29/07/2026 | 13/08/2026 | 371 | 371
ADIDAS | 0902993759-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 405 | 15/09/2026 | 405 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902993759 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 405 | 391 | 14 |  | 22 | 2026-01-09 | 2026-11-09 | 2026-10-08 | 2026-10-09 | 405 | 405
ADIDAS | 0902993780-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 600 | 2026-05-09 | 600 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993780 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-03-08 | 2026-11-08 | 600 | 600 |  |  |  | 29/07/2026 | 2026-10-08 | 28/07/2026 | 2026-10-08 | 600 | 600
ADIDAS | 0902997572-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 621 | 28/08/2026 | 621 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902997572 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 14/08/2026 | 2026-10-08 | 14/08/2026 | 621 | 621 |  |  |  | 2026-05-08 | 2026-11-08 | 27/07/2026 | 24/08/2026 | 621 | 621
ADIDAS | 0902997625-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 28/08/2026 | 368 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902997625 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 2026-07-08 | 31/07/2026 | 2026-07-08 | 368 | 368 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-07-08 | 368 | 368
ADIDAS | 0902997868-1 KB5960 | WHITE | 120D | S2608MR0900A | 524 | 15/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902997868 KB5960 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 524 |  | 524 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 27/08/2026 | 524 | 524 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 26/08/2026 | 524 | 524
ADIDAS | 0902999653-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 330 | 21/08/2026 | 330 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999653 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 20/07/2026 | 24/07/2026 | 330 | 330 |  |  |  | 15/07/2026 | 21/07/2026 | 16/07/2026 | 29/07/2026 | 330 | 330
ADIDAS | 0902999704-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 563 | 28/08/2026 | 563 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999704 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 563 | 563 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 14/08/2026 | 563 | 563
ADIDAS | 0902999743-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 255 | 31/08/2026 | 255 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999743 KV7863 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 255 | 255 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-01-08 | 31/08/2026 | 255 | 255
ADIDAS | 0903014150-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 120 | 21/08/2026 | 120 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 516029 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903014150 LG9660 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 120 | 120 |  |  |  | 27/07/2026 | 2026-11-08 | 27/07/2026 | 14/08/2026 | 120 | 120
ADIDAS | 0903014154-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 778 | 21/08/2026 | 778 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jun. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903014154 KV7863 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/07/2026 | 2026-06-08 | 24/07/2026 | 2026-05-08 | 778 | 778 |  |  |  | 21/07/2026 | 2026-03-08 | 20/07/2026 | 2026-05-08 | 778 | 778
ADIDAS | 0903017607-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 1100 | 2026-05-09 | 1100 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok |  | 05/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903017607 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV WB |  | SS27 | 29/07/2026 | 31/08/2026 | 29/07/2026 | 31/08/2026 | 1100 | 1100 |  |  |  | 24/07/2026 | 27/08/2026 | 22/07/2026 | 2026-01-09 | 1100 | 1100
ADIDAS | 0903031703-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 2026-05-09 | 313 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031703 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 313 | 313 |  |  |  | 29/07/2026 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 313 | 313
ADIDAS | 0903031747-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 352 | 2026-05-09 | 352 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031747 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 352 | 352 |  |  |  | 24/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 352 | 352
ADIDAS | 0903031828-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 1176 | 30/09/2026 | 1176 | AN | AN12/06/2026 | G1E | T-SHIRT | G1 | ok | (02/07/2026) | 22/09: ex-fty. T2 Libolon, PI Date 29-Aug, actual receives 30-Jul. T2 Fu Hsun, actual receives 14-Jan (PO 25063168). 600000 | HT SUB PROCESS_V1 | 0903031828 IT1824 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 1176 |  | 1176 |  |  | 18/09/2026 | 19/09/2026 | 2026-09-09 | 2026-12-09 | 1176 | 1133 | 43 |  | 8 | 17/09/2026 | 18/09/2026 | 2026-09-09 | 2026-10-09 | 1176 | 1138 | 38
ADIDAS | 0903031894-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 7560 | 2026-05-09 | 7560 | AN | AN12/06/2026 | G3A,G3B,G3C,G3E,G3F,G3G,G3H,G3J | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jul. T2 Libolon, PI Date 06-Jul, actual receives 22-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031894 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-04-08 | 19/08/2026 | 7560 | 7560 |  |  |  | 29/07/2026 | 18/08/2026 | 30/07/2026 | 20/08/2026 | 7560 | 7560
ADIDAS | 0903031957-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 540 | 2026-12-09 | 540 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903031957 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 540 | 540 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 18/08/2026 | 540 | 540
ADIDAS | 0903032010-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | ok | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 17-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903032010 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-10-08 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 332 | 332 |  |  |  | 2026-05-08 | 13/08/2026 | 2026-11-08 | 18/08/2026 | 332 | 332
ADIDAS | 0903042722-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 2026-09-09 | 344 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903042722 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 344 | 344 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 344 | 344
ADIDAS | 0903042749-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 300 | 30/09/2026 | 300 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903042749 LE5389 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 19/09/2026 | 2026-11-08 | 26/08/2026 | 300 | 300
ADIDAS | 0903043439-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 15/10/2026 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903043439 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 4002 |  | 4002 |  |  | 2026-03-10 | 2026-07-10 |  |  | 4002 |  | 4002
ADIDAS | 0903043644-1 KB5965 | BLACK | 120D | S2608MR0900A | 1380 | 30/09/2026 | 1380 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 23/09: ex-fty. DRC 0090-early shipment customer (BTP_23_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903043644 KB5965 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | Run Ess Tee M |  | SS27-TI | 24/09/2026 | 26/09/2026 |  |  | 1380 |  | 1380 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1380 |  | 1380 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903045739-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 984 | 2026-12-09 | 984 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903045739 KB5960 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | Run Ess Tee M |  | SS27-TI | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-03-09 | 2026-07-09 | 2026-08-09 | 2026-10-09 | 984 | 984
ADIDAS | 0903045869-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 2026-07-10 | 12000 | AN | AN12/06/2026 | G3A,G3B,G3C | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045869 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 2026-01-10 | 20/10/2026 |  |  | 12000 |  | 12000 |  |  | 28/09/2026 | 16/10/2026 | 28/07/2026 | 28/07/2026 | 12000 | 1 | 11999
ADIDAS | 0903045909-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 2026-07-10 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045909 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 4002 |  | 4002 |  |  | 2026-01-10 | 2026-03-10 |  |  | 4002 |  | 4002
ADIDAS | 0903046028-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 15/10/2026 | 12000 | AN | AN12/06/2026 | G3D,G3E,G3F | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046028 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 26/10/2026 | 2026-06-11 |  |  | 12000 |  | 12000 |  |  | 22/10/2026 | 2026-03-11 |  |  | 12000 |  | 12000
ADIDAS | 0903046531-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 301 | 30/09/2026 | 301 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046531 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 301 |  | 301 |  |  | 29/09/2026 | 29/09/2026 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903046557-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 121 | 2026-12-09 | 121 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046557 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 121 | 121 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 31/08/2026 | 121 | 121
ADIDAS | 0903046577-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 414 | 2026-12-09 | 414 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046577 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 414 | 414 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 2026-10-09 | 414 | 414
ADIDAS | 0903046607-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 360 | 2026-09-09 | 360 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046607 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 360 | 360 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 360 | 360
ADIDAS | 0903046624-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 2083 | 15/09/2026 | 2083 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046624 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 15/09/2026 | 2026-10-08 | 27/08/2026 | 2083 | 1632 | 451 |  |  | 2026-04-08 | 2026-11-09 | 28/07/2026 | 2026-12-09 | 2083 | 2071 | 12 |  | 2
ADIDAS | 0903046936-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 200 | 23/09/2026 | 200 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route. DRC 0010-hold shipment customer (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 1st Art (TC 10 pcs) 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046936 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 15/08/2026 | 200 | 200
ADIDAS | 0903046982-1 KB5965 | BLACK | 120D | S2608MR0900A | 1010 | 30/09/2026 | 1010 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903046982 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 1010 |  | 1010 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1010 |  | 1010 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1010 |  | 1010
ADIDAS | 0903047029-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_02_07_2026 EARLY HOLD SHIPMENT). 516240 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903047029 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 | 2026-12-09 | 13/09/2026 | 300 | 133 | 167 |  | 44 | 2026-05-09 | 2026-07-09 | 2026-11-09 | 14/09/2026 | 300 | 289 | 11 |  | 167
ADIDAS | 0903047077-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 350 | 2026-07-10 | 350 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516461 | HT+PAD SUB PROCESS_V3 | 0903047077 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 21/09/2026 | 21/09/2026 |  |  | 350 |  | 350 |  |  | 18/09/2026 | 18/09/2026 |  |  | 350 |  | 350
ADIDAS | 0903047104-1 KB5960 | WHITE | 120D | S2608MR0900A | 634 | 30/09/2026 | 634 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903047104 KB5960 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | Run Ess Tee M |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 634 |  | 634 |  |  | 23/09/2026 | 24/09/2026 | 2026-05-08 | 2026-10-09 | 634 | 614 | 20 |  |  | 21/09/2026 | 22/09/2026 | 2026-01-08 | 2026-10-09 | 634 | 615 | 19
ADIDAS | 0903047150-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516433 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047150 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 | 28/08/2026 | 2026-04-09 | 301 | 14 | 287
ADIDAS | 0903047185-1 JZ7808 | BLACK | 120D | S2608WR0900 | 803 | 15/10/2026 | 803 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047185 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 803 |  | 803 |  |  | 26/09/2026 | 26/09/2026 |  |  | 803 |  | 803 |  |  | 24/09/2026 | 24/09/2026 |  |  | 803 |  | 803
ADIDAS | 0903047214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 2411 | 15/10/2026 | 2411 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047214 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 2411 |  | 2411 |  |  | 26/09/2026 | 28/09/2026 |  |  | 2411 |  | 2411 |  |  | 24/09/2026 | 25/09/2026 |  |  | 2411 |  | 2411
ADIDAS | 0903047216-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 431 | 30/09/2026 | 431 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047216 KY6616 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 431 |  | 431 |  |  | 18/09/2026 | 19/09/2026 |  |  | 431 |  | 431
ADIDAS | 0903047241-1 KB5965 | BLACK | 120D | S2608MR0900A | 4136 | 15/10/2026 | 4136 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047241 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-10 | Run Ess Tee M |  | SS27-TI | 2026-03-10 | 2026-08-10 |  |  | 4136 |  | 4136 |  |  | 30/09/2026 | 2026-05-10 |  |  | 4136 |  | 4136 |  |  | 28/09/2026 | 2026-02-10 |  |  | 4136 |  | 4136
ADIDAS | 0903047261-1 LG9675 | BLACK | 120D | S2754WAS513C | 301 | 15/10/2026 | 301 | SI | SI12/06/2026 | G3G | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047261 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | W SL WV PT BLACK |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 301 |  | 301 |  |  | 30/10/2026 | 31/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903047275-1 LE8201 | BLACK | 90D | F2606LHLF103FY-MTF | 14000 | 15/09/2026 | 14000 | AN | AN12/06/2026 | G2K,G2L | T-SHIRT | G2 | ok | (02/07/2026) | 15/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047275 LE8201 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 14000 | 12268 | 1732 |  | 1516 | 2026-02-09 | 2026-11-09 | 2026-01-09 | 2026-12-09 | 14000 | 13815 | 185 |  | 109
ADIDAS | 0903047299-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2O | T-SHIRT | G2 | ok | (02/07/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047299 LE8208 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 F JSYL SE BLACK |  | FW26-FJ | 2026-05-09 | 14/09/2026 | 2026-05-09 | 14/09/2026 | 3500 | 3458 | 42 |  | 92 | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-09-09 | 3500 | 3436 | 64
ADIDAS | 0903047330-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1I,G1M | T-SHIRT | G1 | ok | (04/07/2026) | 14/09: ex-fty 1st Art (TC 20 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047330 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-02-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 15000 | 13366 | 1634 |  | 807 | 29/08/2026 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 15000 | 14852 | 148 |  | 25
ADIDAS | 0903047342-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047342 LE8210 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 3500 | 3148 | 352 |  | 748 | 2026-05-09 | 2026-10-09 | 2026-05-09 | 14/09/2026 | 3500 | 3426 | 74 |  | 10
ADIDAS | 0903047363-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 3678 | 2026-12-09 | 3678 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 11/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047363 LE8194 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL HFY JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 3678 | 3678 |  |  |  | 27/08/2026 | 2026-05-09 | 20/08/2026 | 2026-04-09 | 3678 | 3678
ADIDAS | 0903047388-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1G,G1I,G1M,G1O,G1Q,G1R,G2M | T-SHIRT | G1,G2 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047388 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-02-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 15000 | 10776 | 4224 |  | 4045 | 29/08/2026 | 2026-11-09 | 2026-05-09 | 14/09/2026 | 15000 | 14533 | 467 |  | 1340
ADIDAS | 0903047414-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 5500 | 15/09/2026 | 5500 | SA | SA12/06/2026 | G1G | T-SHIRT | G1 | ok | (04/07/2026) | 09/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047414 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 5500 | 5143 | 357 |  | 452 | 2026-05-09 | 2026-10-09 | 31/08/2026 | 2026-12-09 | 5500 | 5483 | 17 |  | 47
ADIDAS | 0903047417-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 121 | 15/10/2026 | 121 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047417 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 121 |  | 121 |  |  | 2026-01-10 | 2026-02-10 |  |  | 121 |  | 121
ADIDAS | 0903047441-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 249 | 15/09/2026 | 249 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903047441 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 249 | 239 | 10 |  | 231 | 2026-09-09 | 2026-11-09 | 2026-11-08 | 26/08/2026 | 249 | 249
ADIDAS | 0903047468-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 150 | 15/09/2026 | 150 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047468 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 2026-12-09 | 150 | 107 | 43 |  | 107 | 2026-09-09 | 2026-11-09 | 22/08/2026 | 2026-04-09 | 150 | 118 | 32
ADIDAS | 0903047497-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 15/09/2026 | 101 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047497 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 101 |  | 101 |  |  | 2026-11-09 | 2026-12-09 | 26/08/2026 | 2026-05-09 | 101 | 101
ADIDAS | 0903047521-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047521 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-01-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903048420-1 KB5965 | BLACK | 120D | S2608MR0900A | 456 | 30/09/2026 | 456 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048420 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 456 |  | 456 |  |  | 22/09/2026 | 22/09/2026 |  |  | 456 |  | 456 |  |  | 19/09/2026 | 19/09/2026 |  |  | 456 |  | 456
ADIDAS | 0903048444-1 JZ7808 | BLACK | 120D | S2608WR0900 | 420 | 15/10/2026 | 420 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516461 | HT+PAD SUB PROCESS_V3 | 0903048444 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 420 |  | 420 |  |  | 22/09/2026 | 22/09/2026 |  |  | 420 |  | 420 |  |  | 19/09/2026 | 19/09/2026 |  |  | 420 |  | 420
ADIDAS | 0903048469-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1100 | 15/10/2026 | 1100 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903048469 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 25/09/2026 | 28/09/2026 |  |  | 1100 |  | 1100 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1100 |  | 1100 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1100 |  | 1100
ADIDAS | 0903048502-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1004 | 2026-07-10 | 1004 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048502 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 1004 |  | 1004 |  |  | 2026-05-10 | 2026-05-10 |  |  | 1004 |  | 1004 |  |  | 2026-02-10 | 2026-02-10 |  |  | 1004 |  | 1004
ADIDAS | 0903048576-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 112 | 15/09/2026 | 112 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048576 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 |  |  | 112 |  | 112 |  |  | 2026-09-09 | 2026-11-09 |  |  | 112 |  | 112
ADIDAS | 0903048604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN12/06/2026 | G3F,G3G | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903048604 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 300 | 275 | 25 |  | 31 | 2026-01-09 | 2026-11-09 | 2026-10-08 | 13/08/2026 | 300 | 300
ADIDAS | 0903048647-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 434 | 2026-09-09 | 434 | AN | AN12/06/2026 | G1H,G1L | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 14-Aug. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048647 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/08/2026 | 2026-08-09 | 24/08/2026 | 2026-05-09 | 434 | 434 |  |  |  | 18/08/2026 | 2026-04-09 | 18/08/2026 | 2026-07-09 | 434 | 434
ADIDAS | 0903049187-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 376 | 15/10/2026 | 376 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903049187 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 376 |  | 376 |  |  | 2026-08-10 | 2026-09-10 |  |  | 376 |  | 376 |  |  | 2026-06-10 | 2026-07-10 |  |  | 376 |  | 376
ADIDAS | 0903049270-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 450 | 21/08/2026 | 450 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049270 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 21/08/2026 | 2026-06-08 | 20/08/2026 | 450 | 450 |  |  |  | 2026-04-08 | 18/08/2026 | 30/07/2026 | 2026-06-08 | 450 | 450
ADIDAS | 0903049350-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 414 | 21/08/2026 | 414 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (02/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049350 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | LA PALMS TEE |  | SS27 | 14/08/2026 | 21/08/2026 | 14/08/2026 | 21/08/2026 | 414 | 414 |  |  |  | 2026-11-08 | 18/08/2026 | 2026-06-08 | 20/08/2026 | 414 | 414
ADIDAS | 0903049383-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049383 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | PIZZA TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-08-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-07-08 | 2026-07-09 | 450 | 450
ADIDAS | 0903049419-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 341 | 2026-09-09 | 341 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 08/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049419 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M TATTOO SPRT T BLACK |  | SS27 | 2026-03-09 | 2026-09-09 | 2026-04-09 | 2026-08-09 | 341 | 341 |  |  |  | 31/08/2026 | 2026-05-09 | 24/08/2026 | 2026-07-09 | 341 | 341
ADIDAS | 0903049448-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 301 | 30/09/2026 | 301 | AN | AN12/06/2026 | G2N | T-SHIRT | G2 | ok | (02/07/2026) | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049448 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/09/2026 | LA PALMS TEE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 301 |  | 301 |  |  | 2026-12-09 | 14/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903049516-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 301 | 23/09/2026 | 301 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049516 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 301 | 301 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 2026-10-08 | 301 | 300 | 1
ADIDAS | 0903049556-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 141 | 21/08/2026 | 141 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049556 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 21/08/2026 | 2026-06-08 | 20/08/2026 | 141 | 141 |  |  |  | 2026-04-08 | 18/08/2026 | 31/07/2026 | 31/07/2026 | 141 | 141
ADIDAS | 0903049584-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049584 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | PIZZA TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 301 |  | 301 |  |  | 26/09/2026 | 28/09/2026 | 2026-07-08 | 19/08/2026 | 301 | 293 | 8
ADIDAS | 0903049615-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 24/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049615 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | HOU COLL TEE |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 301 |  | 301 |  |  | 28/09/2026 | 28/09/2026 | 2026-10-08 | 2026-07-09 | 301 | 301
ADIDAS | 0903050997-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 558 | 30/09/2026 | 558 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 1st Art (TC 12 pcs) 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903050997 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 558 |  | 558 |  |  | 18/09/2026 | 19/09/2026 | 2026-04-09 | 2026-08-09 | 558 | 195 | 363
ADIDAS | 0903051027-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 236 | 30/09/2026 | 236 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903051027 LE0358 | 2026-11-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 236 |  | 236 |  |  | 24/09/2026 | 25/09/2026 | 2026-04-09 | 2026-11-09 | 236 | 123 | 113
ADIDAS | 0903051147-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 230 | 21/08/2026 | 230 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (02/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903051147 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | LA PALMS TEE |  | SS27 | 14/08/2026 | 21/08/2026 | 14/08/2026 | 21/08/2026 | 230 | 230 |  |  |  | 2026-11-08 | 18/08/2026 | 2026-06-08 | 19/08/2026 | 230 | 230
ADIDAS | 0903051176-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903051176 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | HOU COLL TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-08-08 | 2026-12-09 | 450 | 449 | 1 |  | 4
ADIDAS | 0903051217-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 417 | 26/08/2026 | 417 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 24/08: ex-fty 600000 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903051217 KY1361 | 29/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 417 | 417 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 22/08/2026 | 417 | 417
ADIDAS | 0903051428-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/09/2026 | 18 | SA | SA12/06/2026 | G3J | SHORTS | G3 | ok |  | 14/09: ex-fty. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. T2 Formosa, PI Date 20-Jul, actual receives 07-Jul. 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903051428 KZ0925 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 18 | 18 |  |  | 18 | 2026-05-09 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 18 | 18 |  |  | 18
ADIDAS | 0903051498-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 40 | 15/10/2026 | 40 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051498 LD0283 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 40 |  | 40 |  |  | 26/09/2026 | 28/09/2026 |  |  | 40 |  | 40 |  |  | 24/09/2026 | 25/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903051523-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051523 KX3651 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 50 |  | 50 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 2026-08-08 | 50 | 50 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 50 | 50
ADIDAS | 0903051563-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 40 | 15/10/2026 | 40 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051563 LD0284 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 40 |  | 40 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40
ADIDAS | 0903051592-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 18 | 30/09/2026 | 18 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903051592 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 18 |  | 18 |  |  | 14/09/2026 | 15/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903051620-1 KA0227 | MEDIUM GREY HEATHER | 120D | S2608WR0900 | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0903051620 KA0227 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | Run Ess Tee W MEDIUM GREY HEATHER |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 50 | 50 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-11-08 | 50 | 50
ADIDAS | 0903052489-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 379 | 2026-09-09 | 379 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052489 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-07-09 | 379 | 379 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 31/08/2026 | 379 | 379
ADIDAS | 0903052531-1 LE5038 | BLACK | 105D | S2750MTR104A | 387 | 15/10/2026 | 387 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | (NYK warehouse). T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 1st Art (TC 10 pcs) 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903052531 LE5038 | 2026-11-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-07-10 | D4T AOP GFX T BLACK |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 387 |  | 387 |  |  | 2026-03-10 | 2026-03-10 |  |  | 387 |  | 387 |  |  | 2026-02-10 | 2026-02-10 |  |  | 387 |  | 387
ADIDAS | 0903052564-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 414 | 21/08/2026 | 414 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052564 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 20/08/2026 | 414 | 414 |  |  |  | 29/07/2026 | 18/08/2026 | 31/07/2026 | 19/08/2026 | 414 | 414
ADIDAS | 0903052598-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 135 | 2026-05-09 | 135 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 05/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052598 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-05-08 | 2026-06-08 | 135 | 135 |  |  |  | 29/07/2026 | 2026-04-08 | 28/07/2026 | 31/07/2026 | 135 | 135
ADIDAS | 0903052654-1 KB5960 | WHITE | 120D | S2608MR0900A | 459 | 15/10/2026 | 459 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0903052654 KB5960 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 459 |  | 459 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 2026-07-08 | 459 | 459 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 2026-07-08 | 459 | 459
ADIDAS | 0903052671-1 KB5965 | BLACK | 120D | S2608MR0900A | 282 | 15/10/2026 | 282 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903052671 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess Tee M |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 282 |  | 282 |  |  | 28/09/2026 | 29/09/2026 |  |  | 282 |  | 282 |  |  | 25/09/2026 | 26/09/2026 |  |  | 282 |  | 282
ADIDAS | 0903052708-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 365 | 22/09/2026 | 365 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052708 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 365 | 365 |  |  |  | 2026-03-09 | 2026-09-09 | 20/08/2026 | 2026-10-09 | 365 | 365
ADIDAS | 0903052721-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 459 | 15/09/2026 | 459 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903052721 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 459 | 459 |  |  |  | 27/08/2026 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 459 | 459
ADIDAS | 0903052745-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 305 | 2026-05-09 | 305 | AN | AN12/06/2026 | G3A,G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052745 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 18/08/2026 | 305 | 305 |  |  |  | 29/07/2026 | 18/08/2026 | 2026-03-08 | 14/08/2026 | 305 | 305
ADIDAS | 0903052755-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 633 | 15/09/2026 | 633 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052755 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-07-09 | 2026-12-09 | 633 | 607 | 26 |  | 3 | 2026-03-09 | 2026-11-09 | 20/08/2026 | 2026-01-09 | 633 | 609 | 24
ADIDAS | 0903052784-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 15/09/2026 | 390 | AN | AN12/06/2026 | G3C,G3F | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052784 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 28/08/2026 | 390 | 204 | 186 |  |  | 20/08/2026 | 2026-11-09 | 2026-06-08 | 2026-12-09 | 390 | 380 | 10 |  | 160
ADIDAS | 0903052813-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903052813 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903053034-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 1170 | 15/09/2026 | 1170 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903053034 KD4899 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 15/09/2026 | 2026-01-09 | 2026-12-09 | 1170 | 1170 |  |  | 40 | 27/08/2026 | 2026-11-09 | 2026-01-09 | 2026-05-09 | 1170 | 1170
ADIDAS | 0903053050-1 KH0396 | DARK BLUE | 90D | F26SPRMGFX910-MTF | 641 | 2026-12-09 | 641 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty 516318 | PRINT L2+PAD+PPH L1 SUB PROCESS_V3 | 0903053050 KH0396 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | M HIGHLITE T1 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-10-09 | 641 | 641 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 641 | 641
ADIDAS | 0903053086-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 912 | 2026-12-09 | 912 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 10/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053086 KF2398 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV TT |  | FW26 | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-02-09 | 912 | 912 |  |  |  | 27/08/2026 | 2026-04-09 | 22/08/2026 | 2026-09-09 | 912 | 912
ADIDAS | 0903053111-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 5386 | 2026-12-09 | 5386 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053111 JN1956 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT QZ HD |  | SS27 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-10-09 | 5386 | 5386 |  |  |  | 24/08/2026 | 2026-09-09 | 24/08/2026 | 2026-09-09 | 5386 | 5386
ADIDAS | 0903053136-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 780 | 15/09/2026 | 780 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903053136 KD4899 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 15/09/2026 | 31/08/2026 | 2026-12-09 | 780 | 780 |  |  | 20 | 27/08/2026 | 2026-11-09 | 23/07/2026 | 2026-03-09 | 780 | 780
ADIDAS | 0903053424-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 493 | 31/08/2026 | 493 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053424 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 493 | 493 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 24/08/2026 | 493 | 493
ADIDAS | 0903053462-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 603 | 2026-05-09 | 603 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053462 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 603 | 603 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-07-09 | 603 | 603
ADIDAS | 0903053919-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 782 | 2026-09-09 | 782 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 08/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0903053919 KE8424 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-09 | Run Ess LS M BLACK |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 782 | 782 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-05-09 | 2026-08-09 | 782 | 782 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-04-09 | 2026-08-09 | 782 | 782
ADIDAS | 0903054030-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 468 | 2026-05-09 | 468 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903054030 KX0123 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 468 | 468 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-01-08 | 2026-02-09 | 468 | 468
ADIDAS | 0903054066-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 410 | 2026-05-09 | 410 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 05/09: ex-fty 980004 | PRINT L3+PAD SUB PROCESS_V3 | 0903054066 LC8882 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/08/2026 | M ADI RETRO T BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 410 | 410 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 410 | 410
ADIDAS | 0903054127-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 408 | 2026-07-10 | 408 | SA | SA12/06/2026 | G3K | SHORTS | G3 | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-Jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054127 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/10/2026 | W 3S WV SHO 74 WHITE/BLACK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 408 |  | 408 |  |  | 13/10/2026 | 14/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903054613-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1450 | 15/09/2026 | 1450 | SA | SA12/06/2026 | G1A | T-SHIRT | G1 | ok | (04/07/2026) | 14/09: ex-fty 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903054613 LE8202 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1450 | 1295 | 155 |  | 1066 | 2026-09-09 | 2026-11-09 | 2026-04-09 | 2026-09-09 | 1450 | 1429 | 21
ADIDAS | 0903054711-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 508 | 15/10/2026 | 508 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054711 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 508 |  | 508 |  |  | 25/09/2026 | 26/09/2026 |  |  | 508 |  | 508 |  |  | 23/09/2026 | 24/09/2026 |  |  | 508 |  | 508
ADIDAS | 0903054732-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 127 | 30/09/2026 | 127 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903054732 LE0358 | 2026-11-09 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 127 |  | 127 |  |  | 24/09/2026 | 25/09/2026 |  |  | 127 |  | 127
ADIDAS | 0903054737-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 426 | 26/08/2026 | 426 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 26/08: ex-fty (Mexico). 652001 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903054737 KY1361 | 29/07/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 426 | 426 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 21/08/2026 | 426 | 426
ADIDAS | 0903054739-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 132 | 15/10/2026 | 132 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054739 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 132 |  | 132 |  |  | 24/09/2026 | 24/09/2026 |  |  | 132 |  | 132 |  |  | 22/09/2026 | 22/09/2026 |  |  | 132 |  | 132
ADIDAS | 0903054752-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 290 | 2026-12-09 | 290 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054752 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 290 | 290 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-09-09 | 290 | 290
ADIDAS | 0903054814-1 JZ7808 | BLACK | 120D | S2608WR0900 | 151 | 15/10/2026 | 151 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 857010 | HT+PAD SUB PROCESS_V3 | 0903054814 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 151 |  | 151 |  |  | 22/09/2026 | 22/09/2026 |  |  | 151 |  | 151 |  |  | 19/09/2026 | 19/09/2026 |  |  | 151 |  | 151
ADIDAS | 0903054871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2292 | 30/09/2026 | 2292 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty 857010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903054871 KC8152 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 22/09/2026 |  |  | 2292 |  | 2292 |  |  | 15/09/2026 | 18/09/2026 |  |  | 2292 |  | 2292 |  |  | 2026-09-09 | 2026-12-09 | 2026-08-09 | 2026-12-09 | 2292 | 1152 | 1140 |  | 76
ADIDAS | 0903055171-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 607 | 15/09/2026 | 607 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 14/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055171 KF2398 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 13/08/2026 | 22/07/2026 | 14/08/2026 | 607 | 607 |  |  |  | 15/07/2026 | 2026-10-08 | 21/07/2026 | 29/07/2026 | 607 | 607
ADIDAS | 0903055195-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 371 | 15/09/2026 | 371 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055195 KV7963 | 28/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 371 | 371 |  |  |  | 22/07/2026 | 2026-03-08 | 22/07/2026 | 2026-05-08 | 371 | 371
ADIDAS | 0903055207-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 3592 | 15/09/2026 | 3592 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 14/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055207 JN1956 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W 3S FT QZ HD |  | SS27 | 2026-08-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 3592 | 3507 | 85 |  | 433 | 2026-04-09 | 2026-10-09 | 27/08/2026 | 2026-09-09 | 3592 | 3540 | 52
ADIDAS | 0903055240-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 879 | 23/09/2026 | 879 | AN | AN12/06/2026 | G3J,G3K | SHORTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055240 KV7963 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-10-08 | 879 | 879 |  |  |  | 24/07/2026 | 2026-05-08 | 25/07/2026 | 2026-07-08 | 879 | 879
ADIDAS | 0903056002-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 472 | 15/10/2026 | 472 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903056002 LD0287 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 25/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 472 |  | 472 |  |  | 22/09/2026 | 22/09/2026 | 2026-05-08 | 29/08/2026 | 472 | 472 |  |  |  | 19/09/2026 | 19/09/2026 | 2026-05-08 | 28/08/2026 | 472 | 472
ADIDAS | 0903056023-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 797 | 23/09/2026 | 797 | SA | SA12/06/2026 | G2T | JACKET | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056023 JE6338 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 3S FT FZ HD |  | SS27 | 28/07/2026 | 28/08/2026 | 29/07/2026 | 31/08/2026 | 797 | 797 |  |  |  | 23/07/2026 | 24/08/2026 | 23/07/2026 | 15/08/2026 | 797 | 797
ADIDAS | 0903056094-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 161 | 15/10/2026 | 161 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (02/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056094 KX3653 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 13/10/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 161 |  | 161 |  |  | 2026-09-10 | 2026-10-10 | 2026-10-09 | 2026-10-09 | 161 | 138 | 23 |  |  | 2026-07-10 | 2026-08-10 | 2026-09-09 | 2026-09-09 | 161 | 138 | 23
ADIDAS | 0903056095-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1009 | 30/09/2026 | 1009 | SA | SA12/06/2026 | G2B | JACKET | G2 | ok | (03/07/2026) | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056095 JD1877 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1009 |  | 1009 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903056120-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 427 | 30/09/2026 | 427 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (03/07/2026) | 24/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903056120 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 427 |  | 427 |  |  | 15/09/2026 | 15/09/2026 | 2026-01-08 | 13/08/2026 | 427 | 421 | 6
ADIDAS | 0903056133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 939 | 15/10/2026 | 939 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903056133 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-12-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 939 |  | 939 |  |  | 2026-08-10 | 2026-09-10 |  |  | 939 |  | 939 |  |  | 2026-06-10 | 2026-07-10 |  |  | 939 |  | 939
ADIDAS | 0903056160-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 521 | 2026-05-09 | 521 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903056160 LC8882 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T BLACK |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 521 | 521 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-05-08 | 26/08/2026 | 521 | 521
ADIDAS | 0903056304-1 KX8877 | WHITE | 90D | S27GMGFX100 | 376 | 30/09/2026 | 376 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903056304 KX8877 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M CHIP T WHITE |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 376 |  | 376 |  |  | 17/09/2026 | 17/09/2026 | 22/08/2026 | 24/08/2026 | 376 | 45 | 331
ADIDAS | 0903056585-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 110 | 30/09/2026 | 110 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056585 KY5988 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 110 |  | 110 |  |  | 2026-11-09 | 2026-12-09 |  |  | 110 |  | 110 |  |  | 2026-05-09 | 2026-07-09 |  |  | 110 |  | 110
ADIDAS | 0903056609-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 320 | 2026-07-10 | 320 | SA | SA12/06/2026 | G3E | PANTS | G3 | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056609 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 320 |  | 320 |  |  | 2026-07-10 | 2026-08-10 |  |  | 320 |  | 320 |  |  | 2026-01-10 | 2026-02-10 |  |  | 320 |  | 320
ADIDAS | 0903056658-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 208 | 30/09/2026 | 208 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903056658 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 208 |  | 208 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-09 | 2026-11-09 | 208 | 186 | 22
ADIDAS | 0903056767-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 311 | 15/10/2026 | 311 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056767 KX3654 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 311 |  | 311 |  |  | 2026-07-10 | 2026-08-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102 |  |  | 2026-05-10 | 2026-06-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102
ADIDAS | 0903056781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 444 | 30/09/2026 | 444 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 21/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056781 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | M 3S CHELSEA B7 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 444 |  | 444 |  |  | 16/09/2026 | 17/09/2026 |  |  | 444 |  | 444
ADIDAS | 0903056795-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 402 | 15/10/2026 | 402 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516343 | HT+PAD SUB PROCESS_V3 | 0903056795 KX3654 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 402 |  | 402 |  |  | 2026-07-10 | 2026-08-10 | 27/08/2026 | 2026-10-09 | 402 | 371 | 31 |  |  | 2026-05-10 | 2026-06-10 | 27/08/2026 | 2026-09-09 | 402 | 371 | 31
ADIDAS | 0903056811-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1919 | 30/09/2026 | 1919 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 23/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056811 KY6510 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | M 3S CHELSEA B7 |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 1919 |  | 1919 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1919 |  | 1919
ADIDAS | 0903056816-1 KE8424 | BLACK | 120D | S2608MR0906A | 321 | 15/10/2026 | 321 | SI | SI12/06/2026 | G2N | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056816 KE8424 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 321 |  | 321 |  |  | 2026-03-10 | 2026-05-10 |  |  | 321 |  | 321 |  |  | 2026-01-10 | 2026-02-10 |  |  | 321 |  | 321
ADIDAS | 0903056835-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 351 | 30/09/2026 | 351 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056835 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 351 |  | 351 |  |  | 2026-11-09 | 2026-12-09 |  |  | 351 |  | 351 |  |  | 2026-05-09 | 2026-07-09 |  |  | 351 |  | 351
ADIDAS | 0903056841-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 119 | 30/09/2026 | 119 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056841 KC8152 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 119 |  | 119 |  |  | 2026-11-09 | 2026-12-09 |  |  | 119 |  | 119 |  |  | 2026-05-09 | 2026-07-09 |  |  | 119 |  | 119
ADIDAS | 0903056853-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1356 | 2026-05-09 | 1356 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056853 KV7863 | 28/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 21/08/2026 | 30/07/2026 | 18/08/2026 | 1356 | 1356 |  |  |  | 23/07/2026 | 18/08/2026 | 27/07/2026 | 20/08/2026 | 1356 | 1356
ADIDAS | 0903056865-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 443 | 23/09/2026 | 443 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056865 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 443 |  | 443 |  |  | 2026-11-09 | 2026-12-09 |  |  | 443 |  | 443 |  |  | 2026-05-09 | 2026-07-09 |  |  | 443 |  | 443
ADIDAS | 0903056887-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 30/09/2026 | 300 | AN | AN12/06/2026 | G1H | JACKET | G1 | (13/07/2026) | (03/07/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056887 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 28/09/2026 | 2026-05-09 | 2026-05-09 | 300 | 97 | 203
ADIDAS | 0903056914-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 314 | 2026-12-09 | 314 | AN | AN12/06/2026 | G1G,G1H | JACKET | G1 | ok | (03/07/2026) | 10/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056914 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-10-09 | 314 | 314 |  |  |  | 27/08/2026 | 2026-05-09 | 27/08/2026 | 2026-07-09 | 314 | 314
ADIDAS | 0903056942-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 304 | 2026-09-09 | 304 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056942 KV8005 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 304 | 304 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-09-09 | 304 | 304
ADIDAS | 0903056963-1 JZ7808 | BLACK | 120D | S2608WR0900 | 312 | 15/10/2026 | 312 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056963 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 312 |  | 312 |  |  | 26/09/2026 | 28/09/2026 |  |  | 312 |  | 312 |  |  | 24/09/2026 | 25/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903057469-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 323 | 15/10/2026 | 323 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903057469 LD0285 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 323 |  | 323 |  |  | 19/09/2026 | 19/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323 |  |  |  | 17/09/2026 | 17/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323
ADIDAS | 0903057500-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 30/09/2026 | 123 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 24/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 19-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057500 LD5446 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 123 |  | 123 |  |  | 18/09/2026 | 21/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903057529-1 LE8187 | BLACK | 105D | S2754MAS513 | 385 | 30/09/2026 | 385 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 13-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057529 LE8187 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 21/09/2026 | M SL WV TP PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 385 |  | 385 |  |  | 17/09/2026 | 18/09/2026 |  |  | 385 |  | 385
ADIDAS | 0903057535-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 30/09/2026 | 512 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057535 LF0718 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 17/09/2026 | M SL WV OH PT BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 512 |  | 512 |  |  | 14/09/2026 | 15/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903057574-1 LF0723 | BLACK | 105D | S2754MAS511B | 221 | 30/09/2026 | 221 | SI | SI12/06/2026 | G3F | SHORTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057574 LF0723 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | M SL WV SHO BLACK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 221 |  | 221 |  |  | 18/09/2026 | 18/09/2026 |  |  | 221 |  | 221
ADIDAS | 0903057608-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 379 | 15/10/2026 | 379 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057608 LF0726 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 16/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 379 |  | 379 |  |  | 2026-12-09 | 15/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903057614-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 653 | 15/10/2026 | 653 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057614 LH3759 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 653 |  | 653 |  |  | 15/10/2026 | 16/10/2026 |  |  | 653 |  | 653
ADIDAS | 0903057632-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 309 | 15/10/2026 | 309 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057632 LH3761 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 309 |  | 309 |  |  | 16/10/2026 | 16/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903058035-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 292 | 2026-12-09 | 292 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903058035 LE8194 | 28/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-12-09 | 2026-07-09 | 2026-10-09 | 292 | 292 |  |  |  | 29/08/2026 | 2026-09-09 | 24/08/2026 | 2026-12-09 | 292 | 292 |  |  | 2
ADIDAS | 0903058049-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 320 | 31/08/2026 | 320 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058049 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 24/08/2026 | 31/08/2026 | 24/08/2026 | 29/08/2026 | 320 | 320 |  |  |  | 19/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 320 | 320
ADIDAS | 0903058072-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 402 | 30/09/2026 | 402 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058072 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 402 |  | 402 |  |  | 14/09/2026 | 15/09/2026 |  |  | 402 |  | 402
ADIDAS | 0903058091-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 597 | 15/10/2026 | 597 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058091 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 597 |  | 597 |  |  | 22/09/2026 | 23/09/2026 | 2026-04-08 | 20/08/2026 | 597 | 399 | 198
ADIDAS | 0903058157-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 900 | 15/10/2026 | 900 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058157 KX3650 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 13/10/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 900 |  | 900 |  |  | 2026-09-10 | 2026-10-10 | 31/08/2026 | 2026-04-09 | 900 | 360 | 540 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-04-09 | 900 | 360 | 540
ADIDAS | 0903058652-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 216 | 26/08/2026 | 216 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 24/08: ex-fty 1st Art (TC 10 pcs) 516333 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903058652 KY1361 | 29/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 216 | 216 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 21/08/2026 | 216 | 216
ADIDAS | 0903058691-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 415 | 15/10/2026 | 415 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903058691 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 415 |  | 415 |  |  | 24/09/2026 | 24/09/2026 |  |  | 415 |  | 415 |  |  | 22/09/2026 | 22/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903058943-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 331 | 2026-07-10 | 331 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058943 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 21/08/2026 | 331 | 331 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-05-08 | 20/08/2026 | 331 | 331
ADIDAS | 0903058963-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 539 | 30/09/2026 | 539 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058963 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 539 | 539 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-03-08 | 2026-06-08 | 539 | 539
ADIDAS | 0903058992-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jul (PO NT-351). T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058992 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 332 | 332 |  |  |  | 27/07/2026 | 2026-11-08 | 28/07/2026 | 2026-04-08 | 332 | 332
ADIDAS | 0903059036-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 355 | 2026-05-09 | 355 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059036 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 19/08/2026 | 31/07/2026 | 18/08/2026 | 355 | 355 |  |  |  | 24/07/2026 | 13/08/2026 | 29/07/2026 | 2026-11-08 | 355 | 355
ADIDAS | 0903059059-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 306 | 2026-05-09 | 306 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059059 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 306 | 306 |  |  |  | 2026-04-08 | 2026-11-08 | 29/07/2026 | 2026-11-08 | 306 | 306
ADIDAS | 0903059081-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 519 | 15/10/2026 | 519 | SI | SI12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059081 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 519 |  | 519 |  |  | 2026-05-10 | 2026-07-10 |  |  | 519 |  | 519
ADIDAS | 0903059085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/09/2026 | 300 | AN | AN12/06/2026 | G3A | PANTS | G3 | ok | (03/07/2026) | 21/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059085 KV7863 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 300 | 300 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-01-08 | 14/08/2026 | 300 | 300
ADIDAS | 0903059107-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 253 | 2026-07-10 | 253 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059107 LE4307 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 253 |  | 253 |  |  | 28/09/2026 | 2026-01-10 | 2026-04-09 | 2026-07-09 | 253 | 27 | 226
ADIDAS | 0903059113-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 1150 | 15/09/2026 | 1150 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 14/09: ex-fty 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903059113 LE8210 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-11-09 | 2026-12-09 | 1150 | 1150 |  |  | 169 | 2026-05-09 | 2026-10-09 | 2026-07-09 | 2026-12-09 | 1150 | 1139 | 11 |  | 23
ADIDAS | 0903059133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059133 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 27/08/2026 | 29/08/2026 | 300 | 295 | 5
ADIDAS | 0903059183-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516403 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903059183 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 | 13/09/2026 | 13/09/2026 | 300 | 196 | 104 |  |  | 2026-05-09 | 2026-07-09 | 2026-12-09 | 14/09/2026 | 300 | 293 | 7 |  | 196
ADIDAS | 0903059345-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 147 | 15/09/2026 | 147 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (02/07/2026) | 14/09: ex-fty. T2 Libolon, using PO 26000011, body actual receives 11-Feb, 3S actual receives 10-Feb. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059345 JE1309 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | W 3S WV SHO |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-09-09 | 2026-11-09 | 147 | 147 |  |  |  | 2026-02-09 | 2026-09-09 | 24/07/2026 | 2026-10-09 | 147 | 147
ADIDAS | 0903059367-1 KB5965 | BLACK | 120D | S2608MR0900A | 360 | 15/10/2026 | 360 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903059367 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess Tee M |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 360 |  | 360 |  |  | 28/09/2026 | 29/09/2026 |  |  | 360 |  | 360 |  |  | 25/09/2026 | 26/09/2026 |  |  | 360 |  | 360
ADIDAS | 0903059372-1 LE8187 | BLACK | 105D | S2754MAS513 | 170 | 2026-07-10 | 170 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059372 LE8187 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | M SL WV TP PT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 170 |  | 170 |  |  | 2026-10-10 | 13/10/2026 |  |  | 170 |  | 170
ADIDAS | 0903059402-1 LE8187 | BLACK | 105D | S2754MAS513 | 494 | 2026-07-10 | 494 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059402 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M SL WV TP PT BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 494 |  | 494 |  |  | 2026-08-10 | 2026-10-10 |  |  | 494 |  | 494
ADIDAS | 0903059416-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 111 | 15/10/2026 | 111 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059416 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 111 |  | 111 |  |  | 23/10/2026 | 24/10/2026 |  |  | 111 |  | 111
ADIDAS | 0903059460-1 LE8187 | BLACK | 105D | S2754MAS513 | 465 | 2026-07-10 | 465 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059460 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M SL WV TP PT BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 465 |  | 465 |  |  | 2026-08-10 | 2026-10-10 |  |  | 465 |  | 465
ADIDAS | 0903059491-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 362 | 15/10/2026 | 362 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059491 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 27/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 362 |  | 362 |  |  | 23/10/2026 | 24/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903059522-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 218 | 15/10/2026 | 218 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059522 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 218 |  | 218 |  |  | 23/10/2026 | 24/10/2026 |  |  | 218 |  | 218
ADIDAS | 0903059553-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059553 LF0718 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M SL WV OH PT BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 100 |  | 100 |  |  | 14/09/2026 | 15/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903059578-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (13/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059578 LG9669 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 2026-09-10 | W SL WV SK BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300
ADIDAS | 0903059583-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 309 | 15/10/2026 | 309 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059583 LF0726 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 309 |  | 309 |  |  | 2026-12-09 | 15/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903059626-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 299 | 15/10/2026 | 299 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059626 LF0726 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 299 |  | 299 |  |  | 2026-07-10 | 2026-10-10 |  |  | 299 |  | 299
ADIDAS | 0903059656-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 457 | 15/10/2026 | 457 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059656 LF0727 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | M SL WV TT BLACK |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 457 |  | 457 |  |  | 2026-05-10 | 2026-07-10 |  |  | 457 |  | 457
ADIDAS | 0903059680-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 283 | 15/10/2026 | 283 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059680 LF0729 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 283 |  | 283 |  |  | 2026-10-10 | 2026-12-10 | 2026-07-09 | 2026-07-09 | 283 | 200 | 83
ADIDAS | 0903059710-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/10/2026 | 100 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059710 LH3759 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 15/10/2026 | 16/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903059734-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/10/2026 | 200 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059734 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-01-10 | Run Ess Tee M |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 28/09/2026 | 29/09/2026 |  |  | 200 |  | 200 |  |  | 25/09/2026 | 26/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903059757-1 JZ7808 | BLACK | 120D | S2608WR0900 | 811 | 15/10/2026 | 811 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059757 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 811 |  | 811 |  |  | 26/09/2026 | 28/09/2026 |  |  | 811 |  | 811 |  |  | 24/09/2026 | 25/09/2026 |  |  | 811 |  | 811
ADIDAS | 0903059786-1 KB5965 | BLACK | 120D | S2608MR0900A | 1790 | 15/10/2026 | 1790 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059786 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-10 | Run Ess Tee M |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 1790 |  | 1790 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1790 |  | 1790 |  |  | 26/09/2026 | 28/09/2026 |  |  | 1790 |  | 1790
ADIDAS | 0903060200-1 LF0723 | BLACK | 105D | S2754MAS511B | 552 | 15/10/2026 | 552 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060200 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M SL WV SHO BLACK |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 552 |  | 552 |  |  | 19/10/2026 | 22/10/2026 |  |  | 552 |  | 552
ADIDAS | 0903060220-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 309 | 2026-07-10 | 309 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 30/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060220 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 309 |  | 309 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-08 | 20/08/2026 | 309 | 198 | 111
ADIDAS | 0903060841-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 455 | 2026-07-10 | 455 | AN | AN12/06/2026 | G3K | SHORTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903060841 KV7963 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 455 |  | 455 |  |  | 13/10/2026 | 14/10/2026 |  |  | 455 |  | 455
ADIDAS | 0903060907-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 819 | 30/09/2026 | 819 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 1st Art (TC 10 pcs) 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060907 LD6542 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 819 |  | 819 |  |  | 15/09/2026 | 18/09/2026 |  |  | 819 |  | 819
ADIDAS | 0903060936-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060936 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | M SL WV OH PT BLACK |  | SS27-SPOMA | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 25/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903060943-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 200 | 30/09/2026 | 200 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060943 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 200 |  | 200 |  |  | 14/09/2026 | 15/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903060967-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 77 | 15/10/2026 | 77 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903060967 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | W SL WV PT BLACK |  | SS27-SPOMA | 2026-03-11 | 2026-04-11 |  |  | 77 |  | 77 |  |  | 30/10/2026 | 31/10/2026 |  |  | 77 |  | 77
ADIDAS | 0903060981-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 117 | 30/09/2026 | 117 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060981 LD6542 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 117 |  | 117 |  |  | 14/09/2026 | 15/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903061148-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 100 | 15/09/2026 | 100 | SI | SI12/06/2026 | G1G | T-SHIRT | G1 | ok | (02/07/2026) | 14/09: ex-fty 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903061148 LE8194 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-05-09 | 21/08/2026 | 2026-03-09 | 100 | 100
ADIDAS | 0903061664-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 303 | 15/10/2026 | 303 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061664 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TT BLACK |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 303 |  | 303 |  |  | 2026-05-10 | 2026-07-10 |  |  | 303 |  | 303
ADIDAS | 0903061878-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 816 | 15/10/2026 | 816 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (01/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061878 LF0726 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 2026-10-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 816 |  | 816 |  |  | 2026-07-10 | 2026-10-10 |  |  | 816 |  | 816
ADIDAS | 0903061908-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1613 | 30/09/2026 | 1613 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 25/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 20-Aug. 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061908 LD5446 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 26/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 1613 |  | 1613 |  |  | 23/09/2026 | 25/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903061936-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 559 | 30/09/2026 | 559 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903061936 LE0358 | 2026-11-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 22/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 559 |  | 559 |  |  | 18/09/2026 | 19/09/2026 | 2026-05-09 | 2026-11-09 | 559 | 451 | 108
ADIDAS | 0903062303-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5037 | 30/09/2026 | 5037 | SI | SI12/06/2026 | G1Q | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062303 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M 3S CHELSEA B7 |  | SS27 | 14/09/2026 | 23/09/2026 |  |  | 5037 |  | 5037 |  |  | 2026-10-09 | 19/09/2026 |  |  | 5037 |  | 5037
ADIDAS | 0903062323-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 857 | 2026-09-09 | 857 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (03/07/2026) | 09/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903062323 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 857 | 857 |  |  |  | 2026-01-09 | 2026-05-09 | 30/07/2026 | 2026-04-09 | 857 | 857
ADIDAS | 0903062337-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 6000 | 30/09/2026 | 6000 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062337 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M 3S CHELSEA B7 |  | SS27 | 23/09/2026 | 2026-02-10 |  |  | 6000 |  | 6000 |  |  | 19/09/2026 | 29/09/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903063242-1 KX8877 | WHITE | 90D | S27GMGFX100 | 191 | 2026-12-09 | 191 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903063242 KX8877 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | M CHIP T WHITE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 191 | 191 |  |  |  | 2026-05-09 | 2026-09-09 | 22/08/2026 | 2026-10-09 | 191 | 191
ADIDAS | 0903063361-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 301 | 15/10/2026 | 301 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063361 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | W SL WV SK BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 301 |  | 301 |  |  | 2026-07-10 | 2026-08-10 |  |  | 301 |  | 301
ADIDAS | 0903063503-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 310 | 15/10/2026 | 310 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063503 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | W SL WV SK BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 310 |  | 310 |  |  | 2026-07-10 | 2026-08-10 |  |  | 310 |  | 310
ADIDAS | 0903086049-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 752 | 15/09/2026 | 752 | SA | SA17/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903086049 LE8193 | 2026-01-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-08-09 | 752 | 752 |  |  |  | 27/08/2026 | 2026-04-09 | 26/08/2026 | 2026-08-09 | 752 | 752
ADIDAS | 0903086050-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 459 | 15/09/2026 | 459 | SA | SA17/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903086050 LE8193 | 2026-01-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-09 | REAL H F JSY SE WHITE |  | FW26-FJ | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-11-09 | 459 | 459 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-01-09 | 2026-10-09 | 459 | 459
ADIDAS | 0903089629-1 LF0718 | BLACK | 105D | S2754MAS512B | 301 | 2026-07-10 | 301 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089629 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 301 |  | 301 |  |  | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301
ADIDAS | 0903089630-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 2026-07-10 | 301 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089630 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | M SL WV SHO BLACK |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 301 |  | 301 |  |  | 17/10/2026 | 19/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903089631-1 LF0723 | BLACK | 105D | S2754MAS511B | 17 | 2026-07-10 | 17 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089631 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | M SL WV SHO BLACK |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 17 |  | 17 |  |  | 17/10/2026 | 19/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903089632-1 LF0718 | BLACK | 105D | S2754MAS512B | 59 | 2026-07-10 | 59 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089632 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 59 |  | 59 |  |  | 2026-09-10 | 2026-10-10 |  |  | 59 |  | 59
ADIDAS | 0903091452-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 808 | 23/09/2026 | 808 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903091452 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 17/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 808 |  | 808 |  |  | 14/09/2026 | 15/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903093104-1 JZ7711 | BLACK | 120D | S2608MR0202 | 149 | 2026-07-10 | 149 | SA | SA23/06/2026 | G3E | SHORTS | G3 | ok | (04/08/2026) | T2 Hua Feng, PI Date 31-Jul, actual receives 04-Sep. T2 Far Easten, PI Date 14-Aug, actual receives 03-Sep. 1st Art (TC 10 pcs) 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093104 JZ7711 | 21/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 149 |  | 149 |  |  | 29/09/2026 | 30/09/2026 |  |  | 149 |  | 149 |  |  | 25/09/2026 | 26/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903093145-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 392 | 15/10/2026 | 392 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903093145 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 392 |  | 392 |  |  | 2026-02-10 | 2026-03-10 |  |  | 392 |  | 392 |  |  | 2026-01-10 | 2026-02-10 |  |  | 392 |  | 392
ADIDAS | 0903093460-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 481 | 15/10/2026 | 481 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093460 KY9384 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 481 |  | 481 |  |  | 21/10/2026 | 23/10/2026 |  |  | 481 |  | 481 |  |  | 17/10/2026 | 20/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903093463-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 600 | 15/10/2026 | 600 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093463 KY9384 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 600 |  | 600 |  |  | 21/10/2026 | 23/10/2026 |  |  | 600 |  | 600 |  |  | 17/10/2026 | 20/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903093466-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 300 | 15/10/2026 | 300 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093466 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 20/10/2026 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903093469-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 579 | 15/10/2026 | 579 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093469 KD3854 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 579 |  | 579 |  |  | 17/10/2026 | 19/10/2026 |  |  | 579 |  | 579 |  |  | 14/10/2026 | 15/10/2026 |  |  | 579 |  | 579
ADIDAS | 0903093480-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 350 | 15/10/2026 | 350 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 24-Jul, ETD ?? 516241 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093480 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX | 20/10/2026 | 21/10/2026 |  |  | 350 |  | 350 |  |  | 16/10/2026 | 17/10/2026 |  |  | 350 |  | 350 |  |  | 13/10/2026 | 14/10/2026 |  |  | 350 |  | 350
ADIDAS | 0903093503-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 5119 | 15/10/2026 | 5119 | SI | SI23/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | 28/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093503 KC9082 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 15/10/2026 | 24/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-12-10 | 21/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-08-10 | 17/10/2026 |  |  | 5119 |  | 5119
ADIDAS | 0903093882-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1600 | 30/09/2026 | 1600 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903093882 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | VIETNAM | SEA | 17/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/09/2026 | 18/09/2026 |  |  | 1600 |  | 1600 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1600 |  | 1600 |  |  | 2026-12-09 | 14/09/2026 |  |  | 1600 |  | 1600
ADIDAS | 0903093883-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 500 | 30/09/2026 | 500 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 839055 | PRINT L2+HT SUB PROCESS_V3 | 0903093883 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 19/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/09/2026 | 19/09/2026 |  |  | 500 |  | 500 |  |  | 16/09/2026 | 16/09/2026 |  |  | 500 |  | 500 |  |  | 15/09/2026 | 15/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903093884-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 250 | 23/09/2026 | 250 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093884 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 16/09/2026 | 17/09/2026 |  |  | 250 |  | 250 |  |  | 2026-12-09 | 14/09/2026 |  |  | 250 |  | 250 |  |  | 2026-11-09 | 2026-12-09 |  |  | 250 |  | 250
ADIDAS | 0903093889-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 157 | 23/09/2026 | 157 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093889 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 15/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 157 |  | 157 |  |  | 2026-11-09 | 2026-12-09 |  |  | 157 |  | 157 |  |  | 2026-10-09 | 2026-11-09 |  |  | 157 |  | 157
ADIDAS | 0903093890-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 403 | 23/09/2026 | 403 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093890 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 16/09/2026 | 17/09/2026 |  |  | 403 |  | 403 |  |  | 2026-12-09 | 14/09/2026 |  |  | 403 |  | 403 |  |  | 2026-11-09 | 2026-12-09 |  |  | 403 |  | 403
ADIDAS | 0903093891-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 533 | 23/09/2026 | 533 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093891 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 15/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 533 |  | 533 |  |  | 2026-11-09 | 2026-12-09 |  |  | 533 |  | 533 |  |  | 2026-10-09 | 2026-11-09 |  |  | 533 |  | 533
ADIDAS | 0903093893-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 107 | 22/09/2026 | 107 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 08-Sep. 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093893 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 15/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 107 |  | 107 |  |  | 2026-11-09 | 2026-12-09 |  |  | 107 |  | 107 |  |  | 2026-10-09 | 2026-11-09 |  |  | 107 |  | 107
ADIDAS | 0903093895-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 583 | 15/10/2026 | 583 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093895 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 583 |  | 583 |  |  | 2026-10-10 | 2026-12-10 |  |  | 583 |  | 583 |  |  | 2026-09-10 | 2026-10-10 |  |  | 583 |  | 583
ADIDAS | 0903093906-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 559 | 15/10/2026 | 559 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093906 KV0333 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 559 |  | 559 |  |  | 19/09/2026 | 21/09/2026 |  |  | 559 |  | 559 |  |  | 18/09/2026 | 19/09/2026 |  |  | 559 |  | 559
ADIDAS | 0903093907-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 309 | 15/10/2026 | 309 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093907 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309 |  |  | 18/09/2026 | 19/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903093908-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 345 | 15/10/2026 | 345 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903093908 LG1784 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 24/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 345 |  | 345 |  |  | 21/09/2026 | 22/09/2026 |  |  | 345 |  | 345 |  |  | 19/09/2026 | 21/09/2026 |  |  | 345 |  | 345
ADIDAS | 0903093909-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 158 | 15/10/2026 | 158 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093909 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 158 |  | 158 |  |  | 21/09/2026 | 22/09/2026 |  |  | 158 |  | 158 |  |  | 19/09/2026 | 21/09/2026 |  |  | 158 |  | 158
ADIDAS | 0903093910-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 425 | 15/10/2026 | 425 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093910 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 425 |  | 425 |  |  | 22/09/2026 | 23/09/2026 |  |  | 425 |  | 425 |  |  | 21/09/2026 | 22/09/2026 |  |  | 425 |  | 425
ADIDAS | 0903093911-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 354 | 15/10/2026 | 354 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093911 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 354 |  | 354 |  |  | 22/09/2026 | 23/09/2026 |  |  | 354 |  | 354 |  |  | 21/09/2026 | 22/09/2026 |  |  | 354 |  | 354
ADIDAS | 0903093912-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 105 | 15/10/2026 | 105 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093912 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 105 |  | 105 |  |  | 21/09/2026 | 22/09/2026 |  |  | 105 |  | 105 |  |  | 19/09/2026 | 21/09/2026 |  |  | 105 |  | 105
ADIDAS | 0903095162-1 KE9656 | BLACK | 105D | S2608WR0201A | 7 | 15/10/2026 | 7 | SI | SI23/06/2026 | G3D | SHORTS | G3 | ok |  | 23/09: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 22-Aug, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 10-Sep. T2 Y.R.C, PI Date 15-Aug, actual receives 03-Sep (using fabric from TRAX). T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095162 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 7 |  | 7 |  |  | 2026-09-10 | 2026-10-10 |  |  | 7 |  | 7 |  |  | 2026-08-10 | 2026-09-10 |  |  | 7 |  | 7
ADIDAS | 0903095174-1 KE9656 | BLACK | 105D | S2608WR0201A | 5411 | 15/10/2026 | 5411 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (15/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095174 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 14/10/2026 | 26/10/2026 |  |  | 5411 |  | 5411 |  |  | 2026-10-10 | 22/10/2026 |  |  | 5411 |  | 5411 |  |  | 2026-09-10 | 21/10/2026 |  |  | 5411 |  | 5411
ADIDAS | 0903095176-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 503 | 15/10/2026 | 503 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095176 LC6791 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX | 23/10/2026 | 24/10/2026 |  |  | 503 |  | 503 |  |  | 20/10/2026 | 21/10/2026 |  |  | 503 |  | 503 |  |  | 16/10/2026 | 17/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903095186-1 KA6229 | BLACK | 120D | S2608WR0202 | 448 | 23/09/2026 | 448 | SA | SA23/06/2026 | G1N | SHORTS | G1 | ok | ok | 21/09: ex-fty. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095186 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 448 |  | 448 |  |  | 22/09/2026 | 23/09/2026 |  |  | 448 |  | 448 |  |  | 18/09/2026 | 19/09/2026 |  |  | 448 |  | 448
ADIDAS | 0903095189-1 KA6229 | BLACK | 120D | S2608WR0202 | 301 | 22/09/2026 | 301 | SA | SA23/06/2026 | G1P | SHORTS | G1 | ok | ok | 21/09: ex-fty. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual recieves 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Aug (switch fabric from TREX). 1st Art (TC 10 pcs) 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095189 KA6229 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 23/09/2026 |  |  | 301 |  | 301 |  |  | 15/09/2026 | 19/09/2026 |  |  | 301 |  | 301 |  |  | 2026-11-09 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 301 | 229 | 72
ADIDAS | 0903095193-1 KA6229 | BLACK | 120D | S2608WR0202 | 339 | 15/10/2026 | 339 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | 21/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Easten, PI Date 07-Sep, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095193 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 339 |  | 339 |  |  | 2026-07-10 | 2026-08-10 |  |  | 339 |  | 339 |  |  | 2026-03-10 | 2026-05-10 | 2026-09-09 | 2026-09-09 | 339 | 322 | 17
ADIDAS | 0903095197-1 KA6229 | BLACK | 120D | S2608WR0202 | 765 | 22/09/2026 | 765 | SA | SA23/06/2026 | G1P | SHORTS | G1 | (14/08/2026) | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095197 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 23/09/2026 |  |  | 765 |  | 765 |  |  | 15/09/2026 | 19/09/2026 |  |  | 765 |  | 765 |  |  | 2026-11-09 | 16/09/2026 |  |  | 765 |  | 765
ADIDAS | 0903095199-1 KA6229 | BLACK | 120D | S2608WR0202 | 277 | 15/10/2026 | 277 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095199 KA6229 | 21/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-10-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 277 |  | 277 |  |  | 2026-07-10 | 2026-08-10 |  |  | 277 |  | 277 |  |  | 2026-03-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903095204-1 KC4947 | BLACK | 105D | S2608WR0216 | 523 | 15/10/2026 | 523 | SA | SA23/06/2026 | G3G | PANTS | G3 | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903095204 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/10/2026 | adi365 Astro W |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 523 |  | 523 |  |  | 17/10/2026 | 20/10/2026 |  |  | 523 |  | 523 |  |  | 16/10/2026 | 19/10/2026 |  |  | 523 |  | 523
ADIDAS | 0903110856-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1103 | 26/09/2026 | 1103 | SI | SI26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 22-Jul, ETD ?? Waiting fabric. T2 Formosa, PI Date 26-Jul, ETD 03-Aug, ETA-Kaha 14-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110856 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 17/09/2026 | 22/09/2026 |  |  | 1103 |  | 1103 |  |  | 14/09/2026 | 18/09/2026 |  |  | 1103 |  | 1103
ADIDAS | 0903110887-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 5118 | 15/10/2026 | 5118 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110887 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-10-10 | 30/10/2026 |  |  | 5118 |  | 5118 |  |  | 2026-07-10 | 27/10/2026 |  |  | 5118 |  | 5118
ADIDAS | 0903128588-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903128588 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-09-09 | 420 | 420
ADIDAS | 0903129093-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 792 | 15/09/2026 | 792 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129093 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 15/09/2026 | 2026-02-09 | 2026-08-09 | 792 | 786 | 6 |  |  | 27/08/2026 | 2026-11-09 | 2026-05-08 | 22/08/2026 | 792 | 792
ADIDAS | 0903129353-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 497 | 26/08/2026 | 497 | SI | SI26/06/2026 | G2L,G2O | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129353 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 497 | 497 |  |  |  | 18/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 497 | 497
ADIDAS | 0903129376-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 550 | 15/10/2026 | 550 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129376 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 550 |  | 550 |  |  | 2026-06-10 | 2026-07-10 |  |  | 550 |  | 550
ADIDAS | 0903129505-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 303 | 15/10/2026 | 303 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129505 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 15/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-12-10 | 13/10/2026 | 2026-02-09 | 2026-02-09 | 303 | 19 | 284
ADIDAS | 0903129548-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 350 | 28/08/2026 | 350 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3 SUB PROCESS_V3 | 0903129548 LI2667 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 350 | 350 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-12-08 | 350 | 350
ADIDAS | 0903129731-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 471 | 26/08/2026 | 471 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129731 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 471 | 471 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 29/08/2026 | 471 | 471
ADIDAS | 0903129796-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 432 | 28/08/2026 | 432 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129796 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 432 | 432 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 29/08/2026 | 432 | 432
ADIDAS | 0903129828-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 458 | 28/08/2026 | 458 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129828 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 458 | 458 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 458 | 458
ADIDAS | 0903129915-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 350 | 28/08/2026 | 350 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129915 LI2668 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-04-08 | 2026-10-08 | 350 | 350 |  |  |  | 30/07/2026 | 2026-06-08 | 2026-03-08 | 2026-07-08 | 350 | 350
ADIDAS | 0903129964-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 4 | 28/08/2026 | 4 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129964 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 4 | 4 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 18/08/2026 | 4 | 4
ADIDAS | 0903130488-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 2026-07-10 | 103 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130488 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 103 |  | 103 |  |  | 28/09/2026 | 29/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903130527-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130527 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 500 |  | 500 |  |  | 2026-03-10 | 2026-05-10 |  |  | 500 |  | 500
ADIDAS | 0903130582-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 106 | 2026-07-10 | 106 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130582 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 106 |  | 106 |  |  | 2026-01-10 | 2026-02-10 | 20/08/2026 | 29/08/2026 | 106 | 34 | 72
ADIDAS | 0903130615-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130615 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0903130649-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 234 | 31/08/2026 | 234 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903130649 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 234 | 234 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-10-08 | 234 | 234
ADIDAS | 0903130700-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 680 | 28/08/2026 | 680 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903130700 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 27/08/2026 | 21/08/2026 | 27/08/2026 | 680 | 680 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-03-08 | 2026-10-08 | 680 | 680
ADIDAS | 0903130740-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 325 | 30/09/2026 | 325 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130740 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | W 3S FT OH PT |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 325 |  | 325 |  |  | 2026-07-10 | 2026-07-10 | 14/08/2026 | 2026-07-09 | 325 | 294 | 31
ADIDAS | 0903130742-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 208 | 15/09/2026 | 208 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130742 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 2026-03-09 | 24/08/2026 | 2026-03-09 | 208 | 208 |  |  |  | 19/08/2026 | 31/08/2026 | 2026-07-08 | 2026-11-08 | 208 | 208
ADIDAS | 0903130761-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 550 | 15/10/2026 | 550 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130761 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 550 |  | 550 |  |  | 21/10/2026 | 22/10/2026 | 2026-03-09 | 2026-09-09 | 550 | 85 | 465
ADIDAS | 0903130786-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 101 | 2026-07-10 | 101 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130786 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 101 |  | 101 |  |  | 2026-11-09 | 2026-12-09 | 2026-02-09 | 2026-02-09 | 101 | 101
ADIDAS | 0903130838-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 358 | 31/08/2026 | 358 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130838 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 358 | 358 |  |  |  | 14/08/2026 | 27/08/2026 | 2026-04-08 | 2026-07-08 | 358 | 358
ADIDAS | 0903130929-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 15/10/2026 | 103 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130929 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 103 |  | 103 |  |  | 2026-06-10 | 2026-06-10 |  |  | 103 |  | 103
ADIDAS | 0903130982-1 LF0723 | BLACK | 105D | S2754MAS511B | 308 | 15/10/2026 | 308 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130982 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | M SL WV SHO BLACK |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 308 |  | 308 |  |  | 19/10/2026 | 22/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903130983-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 147 | 31/08/2026 | 147 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903130983 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 147 | 147 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-04-08 | 2026-08-08 | 147 | 147
ADIDAS | 0903131013-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 120 | 31/08/2026 | 120 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131013 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 120 | 120 |  |  |  | 18/08/2026 | 20/08/2026 | 2026-05-08 | 2026-08-08 | 120 | 120
ADIDAS | 0903131041-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 343 | 23/09/2026 | 343 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131041 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 343 |  | 343 |  |  | 2026-11-09 | 2026-12-09 | 31/08/2026 | 2026-03-09 | 343 | 292 | 51
ADIDAS | 0903131046-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 103 | 15/10/2026 | 103 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131046 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 103 |  | 103 |  |  | 21/10/2026 | 22/10/2026 | 2026-02-09 | 2026-10-09 | 103 | 103
ADIDAS | 0903131085-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 31/08/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131085 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 31/08/2026 | 249 | 249 |  |  |  | 18/08/2026 | 27/08/2026 | 2026-04-08 | 2026-07-08 | 249 | 249
ADIDAS | 0903131111-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 254 | 30/09/2026 | 254 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903131111 LE4307 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 254 |  | 254 |  |  | 21/09/2026 | 23/09/2026 |  |  | 254 |  | 254
ADIDAS | 0903131134-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 115 | 31/08/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903131134 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 115 | 115 |  |  |  | 24/08/2026 | 27/08/2026 | 2026-06-08 | 24/08/2026 | 115 | 115
ADIDAS | 0903131303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 221 | 28/08/2026 | 221 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903131303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 221 | 221 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-01-09 | 221 | 221
ADIDAS | 0903131630-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 236 | 28/08/2026 | 236 | AN | AN26/06/2026 | G1G,G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131630 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 236 | 236 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-04-08 | 2026-06-08 | 236 | 236
ADIDAS | 0903131716-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131716 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 303 |  | 303 |  |  | 2026-09-10 | 2026-09-10 |  |  | 303 |  | 303
ADIDAS | 0903131801-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 744 | 15/10/2026 | 744 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131801 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 744 |  | 744 |  |  | 16/10/2026 | 19/10/2026 |  |  | 744 |  | 744
ADIDAS | 0903131901-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131901 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 18/08/2026 | 2026-07-08 | 14/08/2026 | 150 | 150 |  |  |  | 30/07/2026 | 2026-12-08 | 2026-04-08 | 2026-12-08 | 150 | 150
ADIDAS | 0903132014-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 225 | 28/08/2026 | 225 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132014 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 225 | 225 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-07-08 | 19/08/2026 | 225 | 225
ADIDAS | 0903132049-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 270 | 15/10/2026 | 270 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132049 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 270 |  | 270 |  |  | 19/10/2026 | 19/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903132063-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 28/08/2026 | 150 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132063 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 150 | 150 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 29/08/2026 | 150 | 150
ADIDAS | 0903132086-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 250 | 28/08/2026 | 250 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132086 LI2646 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 250 | 250 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 20/08/2026 | 250 | 250
ADIDAS | 0903132121-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 190 | 28/08/2026 | 190 | SA | SA26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132121 LI2671 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 27/08/2026 | 26/08/2026 | 26/08/2026 | 190 | 190 |  |  |  | 20/08/2026 | 21/08/2026 | 20/08/2026 | 2026-01-09 | 190 | 190
ADIDAS | 0903132226-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 225 | 28/08/2026 | 225 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903132226 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 225 | 225 |  |  |  | 2026-12-08 | 19/08/2026 | 2026-06-08 | 2026-12-08 | 225 | 225
ADIDAS | 0903132278-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 315 | 28/08/2026 | 315 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132278 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 315 | 315 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 28/08/2026 | 315 | 315
ADIDAS | 0903132419-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 106 | 2026-07-10 | 106 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132419 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 106 |  | 106 |  |  | 2026-03-10 | 2026-05-10 |  |  | 106 |  | 106
ADIDAS | 0903132455-1 LD5424 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS614WVB | 331 | 15/10/2026 | 331 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Formosa, PI Date 12-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 12-Aug, actual receives 28-Aug. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132455 LD5424 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | M 95S WV WB LND OLIVE FOUR S27/OFF WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 331 |  | 331 |  |  | 13/10/2026 | 15/10/2026 |  |  | 331 |  | 331
ADIDAS | 0903132482-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 150 | 2026-12-09 | 150 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132482 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 150 | 150 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-03-09 | 150 | 150
ADIDAS | 0903132526-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 250 | 28/08/2026 | 250 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 1st Art (TC 10 pcs) 512106 | PRINT L3 SUB PROCESS_V3 | 0903132526 LI2667 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 14/08/2026 | 2026-12-08 | 2026-12-08 | 250 | 250 |  |  |  | 2026-07-08 | 2026-11-08 | 2026-04-08 | 2026-06-08 | 250 | 250
ADIDAS | 0903132534-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 255 | 15/09/2026 | 255 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132534 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-03-09 | 2026-04-09 | 255 | 255 |  |  |  | 29/08/2026 | 2026-01-09 | 15/08/2026 | 24/08/2026 | 255 | 255
ADIDAS | 0903132553-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132553 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-02-09 | 200 | 200 |  |  |  | 29/08/2026 | 2026-01-09 | 20/08/2026 | 22/08/2026 | 200 | 200
ADIDAS | 0903132567-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 350 | 28/08/2026 | 350 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132567 LI2645 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 26/08/2026 | 350 | 350 |  |  |  | 19/08/2026 | 24/08/2026 | 14/08/2026 | 21/08/2026 | 350 | 350
ADIDAS | 0903132571-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 704 | 30/09/2026 | 704 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132571 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 704 |  | 704 |  |  | 17/09/2026 | 18/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903132573-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132573 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 2026-01-09 | 20/08/2026 | 27/08/2026 | 200 | 200
ADIDAS | 0903132592-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 170 | 2026-12-09 | 170 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132592 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 170 | 170 |  |  |  | 29/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 170 | 170
ADIDAS | 0903132602-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 100 | 31/08/2026 | 100 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132602 LI2668 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-10-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-10-08 | 2026-12-08 | 2026-10-08 | 2026-11-08 | 100 | 100 |  |  |  | 2026-05-08 | 2026-07-08 | 2026-03-08 | 2026-04-08 | 100 | 100
ADIDAS | 0903132697-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 691 | 15/09/2026 | 691 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132697 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 2026-03-09 | 24/08/2026 | 2026-01-09 | 691 | 691 |  |  |  | 18/08/2026 | 31/08/2026 | 2026-04-08 | 2026-07-08 | 691 | 691
ADIDAS | 0903132705-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 170 | 30/09/2026 | 170 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 22/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132705 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 170 |  | 170 |  |  | 21/09/2026 | 23/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903132709-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 15/10/2026 | 600 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132709 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 600 |  | 600 |  |  | 2026-12-10 | 13/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903132743-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 226 | 31/08/2026 | 226 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903132743 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 226 | 226 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-03-08 | 2026-07-08 | 226 | 226
ADIDAS | 0903132754-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 278 | 15/10/2026 | 278 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132754 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 278 |  | 278 |  |  | 2026-09-10 | 2026-09-10 |  |  | 278 |  | 278
ADIDAS | 0903132786-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 369 | 15/10/2026 | 369 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132786 KY6510 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | M 3S CHELSEA B7 |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 369 |  | 369 |  |  | 29/09/2026 | 2026-01-10 |  |  | 369 |  | 369
ADIDAS | 0903132803-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132803 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-09-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 266 |  | 266 |  |  | 2026-06-10 | 2026-06-10 |  |  | 266 |  | 266
ADIDAS | 0903132827-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132827 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 271 |  | 271 |  |  | 2026-03-10 | 2026-05-10 | 28/08/2026 | 2026-03-09 | 271 | 268 | 3
ADIDAS | 0903132837-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 143 | 2026-07-10 | 143 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132837 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 143 |  | 143 |  |  | 30/09/2026 | 2026-02-10 | 2026-01-09 | 2026-04-09 | 143 | 36 | 107
ADIDAS | 0903132864-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 15/10/2026 | 316 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132864 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 20/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 316 |  | 316 |  |  | 16/10/2026 | 19/10/2026 |  |  | 316 |  | 316
ADIDAS | 0903132871-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 358 | 15/10/2026 | 358 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Kahatex, PI Date 12-Aug, actual receives 05-Sep. T2 Formosa, PI Date 12-Aug, actual receives 03-Sep. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132871 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 358 |  | 358 |  |  | 15/10/2026 | 16/10/2026 |  |  | 358 |  | 358
ADIDAS | 0903132881-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 180 | 28/08/2026 | 180 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132881 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 21/08/2026 | 20/08/2026 | 21/08/2026 | 180 | 180 |  |  |  | 14/08/2026 | 18/08/2026 | 2026-04-08 | 2026-07-08 | 180 | 180
ADIDAS | 0903132916-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 900 | 15/10/2026 | 900 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132916 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 900 |  | 900 |  |  | 19/10/2026 | 21/10/2026 |  |  | 900 |  | 900
ADIDAS | 0903132931-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 308 | 2026-07-10 | 308 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132931 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 308 |  | 308 |  |  | 2026-01-10 | 2026-02-10 | 27/08/2026 | 29/08/2026 | 308 | 308
ADIDAS | 0903132955-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132955 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 266 |  | 266 |  |  | 2026-09-10 | 2026-09-10 |  |  | 266 |  | 266
ADIDAS | 0903132969-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132969 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 1000 |  | 1000 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1000 |  | 1000
ADIDAS | 0903132997-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132997 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-01-09 | 2026-10-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-09-09 | 2026-04-08 | 26/08/2026 | 420 | 420
ADIDAS | 0903133002-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1375 | 2026-07-10 | 1375 | SI | SI26/06/2026 | G1H | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133002 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 1375 |  | 1375 |  |  | 28/09/2026 | 29/09/2026 | 2026-07-08 | 24/08/2026 | 1375 | 1293 | 82
ADIDAS | 0903133009-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133009 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 14/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 1000 |  | 1000 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1000 |  | 1000
ADIDAS | 0903133055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1218 | 2026-07-10 | 1218 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 1218 |  | 1218 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1218 |  | 1218
ADIDAS | 0903133059-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 367 | 15/10/2026 | 367 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133059 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 367 |  | 367 |  |  | 13/10/2026 | 14/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903133104-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 2450 | 2026-07-10 | 2450 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133104 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 2450 |  | 2450 |  |  | 2026-02-10 | 2026-05-10 | 26/08/2026 | 28/08/2026 | 2450 | 2432 | 18
ADIDAS | 0903133114-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 282 | 15/09/2026 | 282 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133114 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 2026-07-09 | 282 | 277 | 5 |  |  | 29/08/2026 | 2026-11-09 | 20/08/2026 | 24/08/2026 | 282 | 282
ADIDAS | 0903133128-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 500 | 15/10/2026 | 500 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133128 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 500 |  | 500 |  |  | 2026-08-10 | 2026-09-10 |  |  | 500 |  | 500
ADIDAS | 0903133146-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133146 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903133194-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 103 | 2026-07-10 | 103 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133194 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 103 |  | 103 |  |  | 30/09/2026 | 2026-02-10 | 31/08/2026 | 2026-05-09 | 103 | 101 | 2
ADIDAS | 0903133260-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 194 | 2026-07-10 | 194 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133260 LI2646 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 194 |  | 194 |  |  | 28/09/2026 | 28/09/2026 | 28/08/2026 | 28/08/2026 | 194 | 181 | 13
ADIDAS | 0903133331-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133331 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 500 |  | 500 |  |  | 30/09/2026 | 2026-02-10 | 31/08/2026 | 2026-04-09 | 500 | 484 | 16
ADIDAS | 0903133357-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 675 | 2026-02-09 | 675 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133357 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 675 | 675 |  |  |  | 27/08/2026 | 28/08/2026 | 21/08/2026 | 2026-03-09 | 675 | 675
ADIDAS | 0903133374-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 143 | 2026-07-10 | 143 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133374 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 143 |  | 143 |  |  | 28/09/2026 | 29/09/2026 |  |  | 143 |  | 143
ADIDAS | 0903133397-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 115 | 2026-02-09 | 115 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133397 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 115 | 115 |  |  |  | 27/08/2026 | 28/08/2026 | 26/08/2026 | 2026-01-09 | 115 | 115
ADIDAS | 0903133440-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 347 | 31/08/2026 | 347 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133440 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 347 | 347 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 2026-02-09 | 347 | 346 | 1
ADIDAS | 0903133475-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133475 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903133506-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E,G2R | ACCESSORIES | G1,G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133506 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-03-09 | 24/08/2026 | 31/08/2026 | 420 | 420
ADIDAS | 0903133517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133517 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 19/08/2026 | 26/08/2026 | 220 | 220
ADIDAS | 0903133575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 220 | 220 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 220 | 220
ADIDAS | 0903133589-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 586 | 23/09/2026 | 586 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133589 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 586 |  | 586 |  |  | 2026-12-09 | 14/09/2026 | 2026-01-09 | 2026-04-09 | 586 | 393 | 193
ADIDAS | 0903133603-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 84 | 15/10/2026 | 84 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133603 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 84 | 84 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 84 | 84
ADIDAS | 0903133644-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133644 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 28/08/2026 | 2026-03-09 | 27/08/2026 | 2026-02-09 | 295 | 295
ADIDAS | 0903133706-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 251 | 15/10/2026 | 251 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133706 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 251 |  | 251 |  |  | 2026-06-10 | 2026-06-10 |  |  | 251 |  | 251
ADIDAS | 0903133759-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 15/09/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133759 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-01-09 | 249 | 249 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-04-08 | 2026-05-08 | 249 | 249
ADIDAS | 0903133823-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1008 | 28/08/2026 | 1008 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133823 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 1008 | 1008 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-04-08 | 26/08/2026 | 1008 | 1008
ADIDAS | 0903133849-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 423 | 2026-07-10 | 423 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133849 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 423 |  | 423 |  |  | 29/09/2026 | 30/09/2026 |  |  | 423 |  | 423
ADIDAS | 0903133851-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 2026-07-10 | 156 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133851 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 156 |  | 156 |  |  | 2026-11-09 | 2026-12-09 | 31/08/2026 | 31/08/2026 | 156 | 150 | 6
ADIDAS | 0903133871-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133871 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 234 | 234 |  |  |  | 28/08/2026 | 31/08/2026 | 26/08/2026 | 2026-03-09 | 234 | 234
ADIDAS | 0903133936-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 358 | 2026-07-10 | 358 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133936 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 358 |  | 358 |  |  | 28/09/2026 | 28/09/2026 | 15/08/2026 | 2026-10-09 | 358 | 349 | 9
ADIDAS | 0903133965-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133965 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-08 | 2026-10-08 | 420 | 420
ADIDAS | 0903134033-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 284 | 15/09/2026 | 284 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134033 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 2026-05-09 | 284 | 284 |  |  |  | 29/08/2026 | 2026-11-09 | 19/08/2026 | 2026-09-09 | 284 | 284
ADIDAS | 0903134047-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2000 | 2026-07-10 | 2000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134047 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-10 | 14/10/2026 |  |  | 2000 |  | 2000 |  |  | 2026-06-10 | 2026-10-10 |  |  | 2000 |  | 2000
ADIDAS | 0903134049-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 980 | 15/10/2026 | 980 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134049 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 980 |  | 980 |  |  | 14/10/2026 | 16/10/2026 |  |  | 980 |  | 980
ADIDAS | 0903134052-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 119 | 31/08/2026 | 119 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134052 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 119 | 119 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 119 | 119
ADIDAS | 0903134065-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 31/08/2026 | 160 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134065 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 160 | 160 |  |  |  | 24/08/2026 | 27/08/2026 | 15/08/2026 | 28/08/2026 | 160 | 160
ADIDAS | 0903134093-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 204 | 31/08/2026 | 204 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903134093 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 204 | 204 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 204 | 202 | 2
ADIDAS | 0903134104-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 142 | 2026-02-09 | 142 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134104 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 142 | 142 |  |  |  | 27/08/2026 | 29/08/2026 | 18/08/2026 | 27/08/2026 | 142 | 142
ADIDAS | 0903134120-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1000 | 2026-07-10 | 1000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134120 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1000 |  | 1000 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1000 |  | 1000
ADIDAS | 0903134126-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 203 | 15/10/2026 | 203 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134126 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 203 |  | 203 |  |  | 2026-03-10 | 2026-05-10 | 19/08/2026 | 31/08/2026 | 203 | 203
ADIDAS | 0903134127-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 912 | 26/08/2026 | 912 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134127 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 13/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 13/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 912 | 912 |  |  |  | 2026-10-08 | 20/08/2026 | 2026-06-08 | 19/08/2026 | 912 | 912
ADIDAS | 0903134177-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 190 | 28/08/2026 | 190 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 1st Art (TC 10 pcs) 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134177 LI2668 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 190 | 190 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-03-08 | 2026-05-08 | 190 | 190
ADIDAS | 0903134200-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 225 | 15/09/2026 | 225 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134200 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 225 | 225 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-07-09 | 225 | 225
ADIDAS | 0903134339-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 210 | 2026-12-09 | 210 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134339 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-02-09 | 2026-05-09 | 210 | 210 |  |  |  | 29/08/2026 | 2026-03-09 | 31/08/2026 | 2026-10-09 | 210 | 210
ADIDAS | 0903134348-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 150 | 31/08/2026 | 150 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3 SUB PROCESS_V3 | 0903134348 LI2667 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 150 | 150 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-05-08 | 150 | 150
ADIDAS | 0903134404-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134404 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 100 | 100 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-04-09 | 100 | 100
ADIDAS | 0903134412-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 150 | 31/08/2026 | 150 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134412 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 150 | 150 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-10-08 | 29/08/2026 | 150 | 150
ADIDAS | 0903134448-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134448 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 28/08/2026 | 31/08/2026 | 27/08/2026 | 2026-07-09 | 100 | 100
ADIDAS | 0903134454-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 31/08/2026 | 100 | SA | SA26/06/2026 | G1M,G1O | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134454 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 100 | 100 |  |  |  | 21/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 100 | 100
ADIDAS | 0903134486-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134486 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 29/08/2026 | 2026-02-09 | 28/08/2026 | 2026-12-09 | 295 | 295 |  |  | 1
ADIDAS | 0903134488-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 425 | 26/08/2026 | 425 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 848012 | PRINT L3 SUB PROCESS_V3 | 0903134488 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 425 | 425 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-04-08 | 2026-11-08 | 425 | 425
ADIDAS | 0903134529-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134529 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-03-09 | 2026-04-09 | 220 | 220 |  |  |  | 28/08/2026 | 2026-03-09 | 2026-02-09 | 2026-10-09 | 220 | 220
ADIDAS | 0903134584-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 690 | 28/08/2026 | 690 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134584 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 690 | 690 |  |  |  | 19/08/2026 | 20/08/2026 | 13/08/2026 | 26/08/2026 | 690 | 690
ADIDAS | 0903134690-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 150 | 2026-12-09 | 150 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134690 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-02-09 | 150 | 150 |  |  |  | 29/08/2026 | 2026-01-09 | 31/08/2026 | 2026-02-09 | 150 | 150
ADIDAS | 0903134709-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 2191 | 15/10/2026 | 2191 | AN | AN26/06/2026 | G1B | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. T2 Formosa, PI Date 26-Jul, actual receives 27-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134709 KW2909 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 26/09/2026 | 2026-02-10 |  |  | 2191 |  | 2191 |  |  | 23/09/2026 | 29/09/2026 |  |  | 2191 |  | 2191
ADIDAS | 0903134753-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 265 | 15/09/2026 | 265 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134753 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 265 | 265 |  |  |  | 29/08/2026 | 2026-03-09 | 22/08/2026 | 27/08/2026 | 265 | 265
ADIDAS | 0903134766-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 355 | 28/08/2026 | 355 | SA | SA26/06/2026 | G1C | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134766 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 355 | 355 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 31/08/2026 | 355 | 355
ADIDAS | 0903134783-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 225 | 15/09/2026 | 225 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134783 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 2026-07-09 | 225 | 148 | 77 |  |  | 2026-01-09 | 2026-11-09 | 2026-03-09 | 2026-04-09 | 225 | 216 | 9
ADIDAS | 0903134821-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134821 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 15/08/2026 | 29/08/2026 | 220 | 220
ADIDAS | 0903134827-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (15/08/2026(10)) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134827 KS1804 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 28/09/2026 | 2026-07-08 | 20/08/2026 | 1072 | 334 | 738 |  |  | 2026-04-08 | 24/09/2026 | 2026-01-08 | 2026-07-09 | 1072 | 1056 | 16
ADIDAS | 0903134852-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 355 | 26/08/2026 | 355 | AN | AN26/06/2026 | G1G,G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134852 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 26/08/2026 | 18/08/2026 | 24/08/2026 | 355 | 355 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-03-08 | 28/08/2026 | 355 | 355
ADIDAS | 0903134857-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 67 | 15/10/2026 | 67 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134857 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 67 | 67 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-08-09 | 67 | 67
ADIDAS | 0903134891-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 490 | 28/08/2026 | 490 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134891 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 490 | 490 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 29/08/2026 | 490 | 490
ADIDAS | 0903134905-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 56 | 15/10/2026 | 56 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134905 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 56 | 56 |  |  |  | 29/08/2026 | 2026-03-09 | 31/08/2026 | 13/09/2026 | 56 | 55 | 1
ADIDAS | 0903134982-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 105 | 30/09/2026 | 105 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134982 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 105 |  | 105 |  |  | 29/09/2026 | 29/09/2026 |  |  | 105 |  | 105
ADIDAS | 0903135001-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1500 | 26/08/2026 | 1500 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135001 LI2668 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 1500 | 1500 |  |  |  | 30/07/2026 | 2026-06-08 | 2026-03-08 | 27/08/2026 | 1500 | 1500
ADIDAS | 0903135003-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 634 | 2026-08-09 | 634 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135003 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 634 | 634 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 634 | 634
ADIDAS | 0903135049-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 744 | 2026-08-09 | 744 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135049 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 744 | 744 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 744 | 744
ADIDAS | 0903135083-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 26/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135083 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 1072 |  | 1072 |  |  | 29/09/2026 | 30/09/2026 | 26/08/2026 | 2026-02-09 | 1072 | 1067 | 5
ADIDAS | 0903135108-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 642 | 2026-08-09 | 642 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135108 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 642 | 642 |  |  |  | 2026-10-08 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 642 | 642
ADIDAS | 0903135135-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 2000 | 29/08/2026 | 2000 | SA | SA26/06/2026 | G2R | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135135 LI2670 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 2000 | 2000 |  |  |  | 18/08/2026 | 24/08/2026 | 19/08/2026 | 2026-03-09 | 2000 | 2000
ADIDAS | 0903135147-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 270 | 15/09/2026 | 270 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135147 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 270 | 270 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-08 | 2026-12-08 | 270 | 270
ADIDAS | 0903135149-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 168 | 31/08/2026 | 168 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135149 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 168 | 168 |  |  |  | 20/08/2026 | 27/08/2026 | 21/08/2026 | 2026-02-09 | 168 | 168
ADIDAS | 0903135150-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 125 | 2026-07-10 | 125 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135150 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 125 |  | 125 |  |  | 28/09/2026 | 28/09/2026 | 28/08/2026 | 29/08/2026 | 125 | 125
ADIDAS | 0903135184-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135184 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/08/2026 | 2026-12-09 | 29/08/2026 | 2026-10-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-09-09 | 20/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135185-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 15/10/2026 | 259 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135185 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 29/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 259 |  | 259 |  |  | 26/10/2026 | 26/10/2026 | 2026-02-09 | 2026-12-09 | 259 | 228 | 31 |  | 16
ADIDAS | 0903135215-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 258 | 15/10/2026 | 258 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135215 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 258 |  | 258 |  |  | 2026-03-10 | 2026-05-10 | 15/08/2026 | 2026-01-09 | 258 | 252 | 6
ADIDAS | 0903135238-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 112 | 31/08/2026 | 112 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135238 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 112 | 112 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 26/08/2026 | 112 | 112
ADIDAS | 0903135251-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 233 | 15/10/2026 | 233 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135251 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 233 |  | 233 |  |  | 13/10/2026 | 14/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903135255-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 301 | 28/08/2026 | 301 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903135255 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-05-08 | 301 | 301
ADIDAS | 0903135286-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135286 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 230 |  | 230 |  |  | 29/09/2026 | 30/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903135308-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 101 | 28/08/2026 | 101 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903135308 LI2669 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 101 | 101 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-04-08 | 2026-08-08 | 101 | 101
ADIDAS | 0903135352-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 310 | 2026-07-10 | 310 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135352 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 310 |  | 310 |  |  | 29/09/2026 | 30/09/2026 |  |  | 310 |  | 310
ADIDAS | 0903135416-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 241 | 31/08/2026 | 241 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135416 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 241 | 241 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 28/08/2026 | 241 | 241
ADIDAS | 0903135464-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 160 | 31/08/2026 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135464 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 19/08/2026 | 20/08/2026 | 160 | 160 |  |  |  | 2026-11-08 | 13/08/2026 | 14/08/2026 | 14/08/2026 | 160 | 160
ADIDAS | 0903135472-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 115 | 15/09/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135472 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 115 | 115 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-10-08 | 115 | 115
ADIDAS | 0903135480-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 148 | 15/10/2026 | 148 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135480 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 29/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 148 |  | 148 |  |  | 26/10/2026 | 26/10/2026 | 31/08/2026 | 2026-09-09 | 148 | 148
ADIDAS | 0903135497-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 496 | 31/08/2026 | 496 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135497 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 496 | 496 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 28/08/2026 | 496 | 496
ADIDAS | 0903135498-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 980 | 15/10/2026 | 980 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135498 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 980 |  | 980 |  |  | 2026-09-10 | 2026-10-10 |  |  | 980 |  | 980
ADIDAS | 0903135520-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 493 | 26/08/2026 | 493 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135520 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 493 | 493 |  |  |  | 14/08/2026 | 19/08/2026 | 15/08/2026 | 26/08/2026 | 493 | 493
ADIDAS | 0903135538-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 165 | 31/08/2026 | 165 | SI | SI26/06/2026 | G2K | ACCESSORIES | G2 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135538 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 165 | 165 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 165 | 165
ADIDAS | 0903135544-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 169 | 2026-07-10 | 169 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135544 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 169 |  | 169 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 2026-07-09 | 169 | 169
ADIDAS | 0903135569-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 189 | 2026-07-10 | 189 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135569 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 189 |  | 189 |  |  | 2026-05-10 | 2026-06-10 | 29/08/2026 | 2026-07-09 | 189 | 188 | 1
ADIDAS | 0903135588-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135588 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 29/08/2026 | 2026-01-09 | 20/08/2026 | 29/08/2026 | 420 | 420
ADIDAS | 0903135590-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 811 | 15/10/2026 | 811 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135590 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 811 |  | 811 |  |  | 2026-05-10 | 2026-06-10 | 28/08/2026 | 2026-09-09 | 811 | 779 | 32
ADIDAS | 0903135591-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 688 | 28/08/2026 | 688 | SA | SA26/06/2026 | G1B,G1C | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135591 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 24/08/2026 | 28/08/2026 | 28/08/2026 | 28/08/2026 | 688 | 688 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 31/08/2026 | 688 | 688
ADIDAS | 0903135621-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2439 | 28/08/2026 | 2439 | SA | SA26/06/2026 | G1B,G1E,G1G,G1I,G1J,G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135621 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 2439 | 2439 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 2026-01-09 | 2439 | 2439
ADIDAS | 0903135624-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 263 | 31/08/2026 | 263 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135624 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 263 | 263 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 24/08/2026 | 263 | 263
ADIDAS | 0903135646-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 84 | 15/10/2026 | 84 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135646 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 84 | 84 |  |  |  | 29/08/2026 | 2026-01-09 | 19/08/2026 | 26/08/2026 | 84 | 84
ADIDAS | 0903135659-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135659 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135683-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 67 | 15/10/2026 | 67 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135683 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 67 | 67 |  |  |  | 27/08/2026 | 2026-01-09 | 26/08/2026 | 28/08/2026 | 67 | 67
ADIDAS | 0903135694-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 160 | 31/08/2026 | 160 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135694 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 160 | 160 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 2026-01-09 | 160 | 160
ADIDAS | 0903135743-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 282 | 15/09/2026 | 282 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135743 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 282 | 282 |  |  |  | 27/08/2026 | 31/08/2026 | 24/08/2026 | 2026-03-09 | 282 | 282
ADIDAS | 0903135819-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 122 | 2026-02-09 | 122 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135819 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 122 | 122 |  |  |  | 27/08/2026 | 29/08/2026 | 26/08/2026 | 2026-04-09 | 122 | 122
ADIDAS | 0903135839-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135839 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 19/08/2026 | 24/08/2026 | 18/08/2026 | 2026-07-09 | 660 | 660
ADIDAS | 0903135961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 292 | 15/09/2026 | 292 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 292 | 292 |  |  |  | 29/08/2026 | 2026-01-09 | 21/08/2026 | 31/08/2026 | 292 | 292
ADIDAS | 0903136044-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136044 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 660 | 660
ADIDAS | 0903136117-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 778 | 2026-08-09 | 778 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136117 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 778 | 778 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 28/08/2026 | 778 | 778
ADIDAS | 0903136141-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 119 | 2026-02-09 | 119 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136141 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 119 | 119 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-03-09 | 119 | 119
ADIDAS | 0903136170-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 225 | 31/08/2026 | 225 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136170 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 225 | 225 |  |  |  | 20/08/2026 | 24/08/2026 | 2026-12-08 | 28/08/2026 | 225 | 225
ADIDAS | 0903136217-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1700 | 28/08/2026 | 1700 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136217 LI2645 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 19/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1700 | 1700 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 1700 | 1700
ADIDAS | 0903136285-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1500 | 28/08/2026 | 1500 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136285 LI2647 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1500 | 1500 |  |  |  | 20/08/2026 | 24/08/2026 | 26/08/2026 | 31/08/2026 | 1500 | 1500
ADIDAS | 0903136324-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2100 | 31/08/2026 | 2100 | SA | SA26/06/2026 | G1G,G1I,G1K | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136324 LI2671 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 2100 | 2100 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 2100 | 2100
ADIDAS | 0903136369-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 2000 | 26/08/2026 | 2000 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903136369 LI2667 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 20/08/2026 | 2000 | 2000 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-01-08 | 26/08/2026 | 2000 | 2000
ADIDAS | 0903136429-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1200 | 29/08/2026 | 1200 | SA | SA26/06/2026 | G1B,G1C,G2I,G2M,G2R | ACCESSORIES | G1,G2 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136429 LI2672 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 1200 | 1200 |  |  |  | 14/08/2026 | 26/08/2026 | 21/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903136661-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 800 | 2026-07-10 | 800 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136661 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 14/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 800 |  | 800 |  |  | 2026-10-10 | 2026-12-10 | 31/08/2026 | 2026-12-09 | 800 | 791 | 9 |  | 48
ADIDAS | 0903136678-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 536 | 31/08/2026 | 536 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136678 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 536 | 536 |  |  |  | 24/08/2026 | 27/08/2026 | 22/08/2026 | 2026-03-09 | 536 | 536
ADIDAS | 0903136726-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 308 | 2026-07-10 | 308 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136726 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 308 |  | 308 |  |  | 29/09/2026 | 30/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903136772-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1540 | 31/08/2026 | 1540 | SA | SA26/06/2026 | G1J,G1K,G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136772 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 1540 | 1540 |  |  |  | 21/08/2026 | 27/08/2026 | 21/08/2026 | 2026-01-09 | 1540 | 1540
ADIDAS | 0903136816-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 278 | 31/08/2026 | 278 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136816 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 278 | 278 |  |  |  | 24/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 278 | 278
ADIDAS | 0903136925-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 104 | 2026-07-10 | 104 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136925 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 104 |  | 104 |  |  | 2026-05-10 | 2026-06-10 |  |  | 104 |  | 104
ADIDAS | 0903136927-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 666 | 31/08/2026 | 666 | SA | SA26/06/2026 | G1M,G1O | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136927 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 666 | 666 |  |  |  | 21/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 666 | 666
ADIDAS | 0903136961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 422 | 2026-07-10 | 422 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 422 |  | 422 |  |  | 2026-05-10 | 2026-06-10 | 29/08/2026 | 2026-07-09 | 422 | 419 | 3
ADIDAS | 0903136977-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 620 | 26/08/2026 | 620 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136977 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 620 | 620 |  |  |  | 2026-11-08 | 19/08/2026 | 15/08/2026 | 26/08/2026 | 620 | 620
ADIDAS | 0903136996-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 277 | 15/09/2026 | 277 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136996 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-05-09 | 277 | 277 |  |  |  | 29/08/2026 | 2026-03-09 | 21/08/2026 | 26/08/2026 | 277 | 277
ADIDAS | 0903137012-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 478 | 26/08/2026 | 478 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137012 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 478 | 478 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 28/08/2026 | 478 | 478
ADIDAS | 0903137023-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 201 | 31/08/2026 | 201 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137023 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 201 | 201 |  |  |  | 2026-11-08 | 24/08/2026 | 15/08/2026 | 28/08/2026 | 201 | 201
ADIDAS | 0903137027-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137027 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903137031-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 772 | 28/08/2026 | 772 | SI | SI26/06/2026 | G2L,G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137031 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 772 | 772 |  |  |  | 19/08/2026 | 24/08/2026 | 14/08/2026 | 31/08/2026 | 772 | 772
ADIDAS | 0903137049-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 117 | 15/09/2026 | 117 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137049 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 117 | 117 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-12-09 | 117 | 117 |  |  | 1
ADIDAS | 0903137055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 235 | 26/08/2026 | 235 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 235 | 235 |  |  |  | 18/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 235 | 235
ADIDAS | 0903137069-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1245 | 31/08/2026 | 1245 | SA | SA26/06/2026 | G1G,G1J,G1K,G1Q,G2I,G2M,G2R | ACCESSORIES | G1,G2 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137069 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 31/08/2026 | 29/08/2026 | 29/08/2026 | 1245 | 1245 |  |  |  | 19/08/2026 | 27/08/2026 | 28/08/2026 | 2026-01-09 | 1245 | 1245
ADIDAS | 0903137098-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1416 | 28/08/2026 | 1416 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137098 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1416 | 1416 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 1416 | 1416
ADIDAS | 0903137102-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 638 | 28/08/2026 | 638 | SA | SA26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137102 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 638 | 638 |  |  |  | 18/08/2026 | 24/08/2026 | 14/08/2026 | 31/08/2026 | 638 | 638
ADIDAS | 0903137111-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 194 | 15/09/2026 | 194 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137111 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-09 | 15/09/2026 |  |  | 194 |  | 194 |  |  | 2026-09-09 | 2026-11-09 | 2026-03-09 | 2026-10-09 | 194 | 163 | 31
ADIDAS | 0903137134-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 358 | 15/09/2026 | 358 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137134 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 16/09/2026 | 2026-03-09 | 2026-07-09 | 358 | 349 | 9 |  |  | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-07-09 | 358 | 358
ADIDAS | 0903137137-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1735 | 31/08/2026 | 1735 | SA | SA26/06/2026 | G1I,G1J,G1K,G1M,G1O,G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137137 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 29/08/2026 | 29/08/2026 | 1735 | 1735 |  |  |  | 21/08/2026 | 27/08/2026 | 28/08/2026 | 2026-03-09 | 1735 | 1741 | -6 | 6
ADIDAS | 0903137299-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1152 | 26/08/2026 | 1152 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137299 LI2668 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-07-08 | 20/08/2026 | 1152 | 1152 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-03-08 | 24/08/2026 | 1152 | 1152
ADIDAS | 0903137310-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 382 | 30/09/2026 | 382 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137310 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 382 |  | 382 |  |  | 17/09/2026 | 18/09/2026 |  |  | 382 |  | 382
ADIDAS | 0903137336-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 784 | 28/08/2026 | 784 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137336 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 784 | 784 |  |  |  | 13/08/2026 | 20/08/2026 | 18/08/2026 | 2026-03-09 | 784 | 784
ADIDAS | 0903137376-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1488 | 28/08/2026 | 1488 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137376 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1488 | 1488 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 29/08/2026 | 1488 | 1488
ADIDAS | 0903137413-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1458 | 28/08/2026 | 1458 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137413 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 2026-12-08 | 20/08/2026 | 1458 | 1458 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-10-08 | 21/08/2026 | 1458 | 1458
ADIDAS | 0903137434-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 4525 | 15/10/2026 | 4525 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137434 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/10/2026 | 2026-02-11 |  |  | 4525 |  | 4525 |  |  | 15/10/2026 | 29/10/2026 |  |  | 4525 |  | 4525
ADIDAS | 0903137493-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 1143 | 26/08/2026 | 1143 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 1st Art (TC 10 pcs) 652001 | PRINT L3 SUB PROCESS_V3 | 0903137493 LI2669 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-10-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 1143 | 1143 |  |  |  | 2026-05-08 | 14/08/2026 | 2026-01-08 | 2026-12-08 | 1143 | 1143
ADIDAS | 0903137501-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 320 | 30/09/2026 | 320 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137501 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 320 |  | 320 |  |  | 23/09/2026 | 28/09/2026 | 28/08/2026 | 2026-01-09 | 320 | 51 | 269
ADIDAS | 0903137531-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 656 | 28/08/2026 | 656 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137531 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 21/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 656 | 656 |  |  |  | 18/08/2026 | 20/08/2026 | 20/08/2026 | 28/08/2026 | 656 | 656
ADIDAS | 0903137540-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 401 | 15/10/2026 | 401 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137540 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 401 |  | 401 |  |  | 2026-02-10 | 2026-03-10 |  |  | 401 |  | 401
ADIDAS | 0903137570-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 592 | 26/08/2026 | 592 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 652001 | PRINT L3 SUB PROCESS_V3 | 0903137570 LI2667 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 592 | 592 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-04-08 | 2026-12-08 | 592 | 592
ADIDAS | 0903137595-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 290 | 28/08/2026 | 290 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137595 LI2645 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 290 | 290 |  |  |  | 19/08/2026 | 20/08/2026 | 13/08/2026 | 26/08/2026 | 290 | 290
ADIDAS | 0903137631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 370 | 28/08/2026 | 370 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3 SUB PROCESS_V3 | 0903137631 LI2667 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 18/08/2026 | 18/08/2026 | 370 | 370 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-01-08 | 2026-07-08 | 370 | 370
ADIDAS | 0903137651-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 153 | 28/08/2026 | 153 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137651 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 153 | 153 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 15/08/2026 | 153 | 153
ADIDAS | 0903137665-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 2268 | 28/08/2026 | 2268 | SA | SA26/06/2026 | G1O,G1Q | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137665 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 2268 | 2268 |  |  |  | 20/08/2026 | 24/08/2026 | 18/08/2026 | 29/08/2026 | 2268 | 2268
ADIDAS | 0903137727-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 132 | 2026-07-10 | 132 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137727 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 132 |  | 132 |  |  | 28/09/2026 | 28/09/2026 | 27/08/2026 | 2026-07-09 | 132 | 132
ADIDAS | 0903137746-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1612 | 28/08/2026 | 1612 | SA | SA26/06/2026 | G2I | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137746 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 1612 | 1612 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 29/08/2026 | 1612 | 1612
ADIDAS | 0903137792-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 168 | 31/08/2026 | 168 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137792 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 168 | 168 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 168 | 168
ADIDAS | 0903137840-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 851 | 31/08/2026 | 851 | SA | SA26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137840 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 851 | 851 |  |  |  | 24/08/2026 | 27/08/2026 | 26/08/2026 | 31/08/2026 | 851 | 851
ADIDAS | 0903137916-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 268 | 31/08/2026 | 268 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137916 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 268 | 268 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 31/08/2026 | 268 | 268
ADIDAS | 0903137964-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 326 | 31/08/2026 | 326 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137964 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 21/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 326 | 326 |  |  |  | 18/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 326 | 326
ADIDAS | 0903137967-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1104 | 28/08/2026 | 1104 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137967 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 1104 | 1104 |  |  |  | 14/08/2026 | 24/08/2026 | 15/08/2026 | 28/08/2026 | 1104 | 1104
ADIDAS | 0903138012-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1750 | 31/08/2026 | 1750 | SA | SA26/06/2026 | G1B,G1C,G1E,G1O,G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138012 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 1750 | 1750 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 2026-08-09 | 1750 | 1728 | 22
ADIDAS | 0903138028-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138028 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 420 | 420 |  |  |  | 29/08/2026 | 2026-09-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903138055-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1430 | 28/08/2026 | 1430 | SA | SA26/06/2026 | G1B,G1E,G1G,G1I,G1Q,G2R | ACCESSORIES | G1,G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138055 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 29/08/2026 | 28/08/2026 | 28/08/2026 | 1430 | 1430 |  |  |  | 20/08/2026 | 26/08/2026 | 15/08/2026 | 31/08/2026 | 1430 | 1430
ADIDAS | 0903138063-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 137 | 2026-07-10 | 137 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138063 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 137 |  | 137 |  |  | 29/09/2026 | 30/09/2026 |  |  | 137 |  | 137
ADIDAS | 0903138090-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1318 | 28/08/2026 | 1318 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903138090 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 1318 | 1318 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-01-08 | 2026-11-08 | 1318 | 1318
ADIDAS | 0903138123-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1750 | 26/08/2026 | 1750 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138123 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-11-08 | 18/08/2026 | 2026-11-08 | 18/08/2026 | 1750 | 1750 |  |  |  | 2026-06-08 | 2026-12-08 | 2026-04-08 | 24/08/2026 | 1750 | 1750
ADIDAS | 0903138138-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 156 | 31/08/2026 | 156 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138138 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 156 | 156 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 156 | 156
ADIDAS | 0903138177-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 760 | 31/08/2026 | 760 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138177 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 760 | 760 |  |  |  | 20/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 760 | 760
ADIDAS | 0903138297-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 266 | 2026-02-09 | 266 | SA | SA26/06/2026 | G1B,G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138297 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 266 | 266 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 266 | 266
ADIDAS | 0903138373-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 542 | 26/08/2026 | 542 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138373 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 542 | 542 |  |  |  | 13/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 542 | 542
ADIDAS | 0903138385-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 174 | 31/08/2026 | 174 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138385 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 174 | 174 |  |  |  | 24/08/2026 | 27/08/2026 | 28/08/2026 | 2026-01-09 | 174 | 174
ADIDAS | 0903138432-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 158 | 2026-02-09 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138432 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 158 | 158 |  |  |  | 27/08/2026 | 28/08/2026 | 22/08/2026 | 29/08/2026 | 158 | 158
ADIDAS | 0903138434-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 650 | 28/08/2026 | 650 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138434 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 28/08/2026 | 18/08/2026 | 27/08/2026 | 650 | 650 |  |  |  | 2026-10-08 | 24/08/2026 | 13/08/2026 | 2026-02-09 | 650 | 650
ADIDAS | 0903138439-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1991 | 29/08/2026 | 1991 | SI | SI26/06/2026 | G2K,G2L,G2N | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138439 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 29/08/2026 | 27/08/2026 | 29/08/2026 | 1991 | 1991 |  |  |  | 19/08/2026 | 26/08/2026 | 15/08/2026 | 31/08/2026 | 1991 | 1991
ADIDAS | 0903138477-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 545 | 26/08/2026 | 545 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138477 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 545 | 545 |  |  |  | 14/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 545 | 545
ADIDAS | 0903138483-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 296 | 28/08/2026 | 296 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138483 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 296 | 296 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 296 | 296
ADIDAS | 0903138496-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 129 | 26/08/2026 | 129 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138496 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 129 | 129 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 26/08/2026 | 129 | 129
ADIDAS | 0903138514-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1366 | 28/08/2026 | 1366 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138514 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1366 | 1366 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1366 | 1366
ADIDAS | 0903138552-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 526 | 28/08/2026 | 526 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138552 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 526 | 526 |  |  |  | 13/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 526 | 526
ADIDAS | 0903138575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 276 | 15/10/2026 | 276 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 22/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 276 |  | 276 |  |  | 19/10/2026 | 19/10/2026 |  |  | 276 |  | 276
ADIDAS | 0903138583-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 562 | 26/08/2026 | 562 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138583 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 562 | 562 |  |  |  | 19/08/2026 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 562 | 562
ADIDAS | 0903138590-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 189 | 26/08/2026 | 189 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138590 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 189 | 189 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 24/08/2026 | 189 | 189
ADIDAS | 0903138615-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 158 | 2026-07-10 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138615 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 14/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 158 |  | 158 |  |  | 2026-10-10 | 2026-12-10 | 31/08/2026 | 2026-07-09 | 158 | 155 | 3
ADIDAS | 0903138621-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 851 | 26/08/2026 | 851 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138621 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 851 | 851 |  |  |  | 18/08/2026 | 20/08/2026 | 20/08/2026 | 29/08/2026 | 851 | 851
ADIDAS | 0903139152-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 124 | 31/08/2026 | 124 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139152 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 124 | 124 |  |  |  | 13/08/2026 | 24/08/2026 | 18/08/2026 | 19/08/2026 | 124 | 124
ADIDAS | 0903139189-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 188 | 31/08/2026 | 188 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139189 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 188 | 188 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 29/08/2026 | 188 | 188
ADIDAS | 0903139269-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 563 | 2026-07-10 | 563 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139269 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 563 |  | 563 |  |  | 29/09/2026 | 29/09/2026 | 15/08/2026 | 2026-07-09 | 563 | 550 | 13
ADIDAS | 0903139272-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 181 | 31/08/2026 | 181 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139272 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 181 | 181 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 2026-01-09 | 181 | 181
ADIDAS | 0903139328-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 707 | 23/09/2026 | 707 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139328 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 707 |  | 707 |  |  | 14/09/2026 | 16/09/2026 | 27/08/2026 | 31/08/2026 | 707 | 706 | 1
ADIDAS | 0903139350-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1855 | 26/08/2026 | 1855 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139350 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 18/08/2026 | 1855 | 1855 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-11-08 | 1855 | 1855
ADIDAS | 0903139367-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 851 | 26/08/2026 | 851 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903139367 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 851 | 851 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-05-08 | 2026-12-08 | 851 | 851
ADIDAS | 0903139370-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 437 | 31/08/2026 | 437 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139370 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 29/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 29/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 437 | 437 |  |  |  | 26/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 437 | 437
ADIDAS | 0903139403-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 112 | 2026-02-09 | 112 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139403 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 112 | 112 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-03-09 | 112 | 112
ADIDAS | 0903139409-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 493 | 26/08/2026 | 493 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139409 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 493 | 493 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-05-08 | 493 | 493
ADIDAS | 0903139439-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 584 | 23/09/2026 | 584 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139439 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 584 |  | 584 |  |  | 2026-11-09 | 2026-12-09 | 31/08/2026 | 2026-04-09 | 584 | 580 | 4
ADIDAS | 0903139469-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 105 | 2026-07-10 | 105 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139469 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 105 |  | 105 |  |  | 2026-10-10 | 2026-12-10 | 31/08/2026 | 2026-07-09 | 105 | 105
ADIDAS | 0903139495-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 28/08/2026 | 156 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139495 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 19/08/2026 | 21/08/2026 | 156 | 156 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-04-08 | 26/08/2026 | 156 | 156
ADIDAS | 0903139498-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 478 | 26/08/2026 | 478 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139498 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 18/08/2026 | 13/08/2026 | 18/08/2026 | 478 | 478 |  |  |  | 2026-07-08 | 2026-12-08 | 2026-03-08 | 28/08/2026 | 478 | 478
ADIDAS | 0903139533-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1104 | 26/08/2026 | 1104 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139533 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 1104 | 1104 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 2026-07-08 | 1104 | 1104
ADIDAS | 0903139570-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 523 | 26/08/2026 | 523 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903139570 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 14/08/2026 | 18/08/2026 | 523 | 523 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 523 | 523
ADIDAS | 0903139649-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1921 | 29/08/2026 | 1921 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139649 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 29/08/2026 | 1921 | 1921 |  |  |  | 20/08/2026 | 24/08/2026 | 26/08/2026 | 2026-03-09 | 1921 | 1921
ADIDAS | 0903139660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139660 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-04-09 | 234 | 234 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-02-09 | 234 | 234
ADIDAS | 0903139688-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 485 | 26/08/2026 | 485 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139688 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 485 | 485 |  |  |  | 18/08/2026 | 19/08/2026 | 14/08/2026 | 28/08/2026 | 485 | 485
ADIDAS | 0903139741-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1214 | 28/08/2026 | 1214 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139741 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1214 | 1214 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1214 | 1214
ADIDAS | 0903139767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 136 | 2026-02-09 | 136 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 136 | 136 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 136 | 136
ADIDAS | 0903139780-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 336 | 26/08/2026 | 336 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3 SUB PROCESS_V3 | 0903139780 LI2669 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 20/08/2026 | 336 | 336 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 19/08/2026 | 336 | 336
ADIDAS | 0903139907-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 432 | 26/08/2026 | 432 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139907 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 20/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 432 | 432 |  |  |  | 14/08/2026 | 20/08/2026 | 13/08/2026 | 27/08/2026 | 432 | 432
ADIDAS | 0903139930-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 307 | 26/08/2026 | 307 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139930 LI2668 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 307 | 307 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-05-08 | 2026-05-08 | 307 | 307
ADIDAS | 0903139936-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 236 | 28/08/2026 | 236 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903139936 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 236 | 236 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 26/08/2026 | 236 | 236
ADIDAS | 0903139968-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 404 | 26/08/2026 | 404 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139968 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 24/08/2026 | 404 | 404 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-10-08 | 19/08/2026 | 404 | 404
ADIDAS | 0903140000-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 405 | 26/08/2026 | 405 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140000 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 405 | 405 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 405 | 405
ADIDAS | 0903140004-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 432 | 26/08/2026 | 432 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140004 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 432 | 432 |  |  |  | 19/08/2026 | 20/08/2026 | 20/08/2026 | 2026-03-09 | 432 | 432
ADIDAS | 0903140046-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 156 | 28/08/2026 | 156 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903140046 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 156 | 156 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-10-08 | 156 | 156
ADIDAS | 0903140069-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 28/08/2026 | 316 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 684009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140069 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 316 | 316 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 28/08/2026 | 316 | 316
ADIDAS | 0903140106-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 340 | 28/08/2026 | 340 | SA | SA26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140106 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 27/08/2026 | 26/08/2026 | 27/08/2026 | 340 | 340 |  |  |  | 20/08/2026 | 21/08/2026 | 20/08/2026 | 2026-01-09 | 340 | 340
ADIDAS | 0903140109-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 320 | 26/08/2026 | 320 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140109 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 19/08/2026 | 20/08/2026 | 320 | 320 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-07-08 | 21/08/2026 | 320 | 320
ADIDAS | 0903140137-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 28/08/2026 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140137 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 100 | 100 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 100 | 100
ADIDAS | 0903140150-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1245 | 26/08/2026 | 1245 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140150 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-05-08 | 21/08/2026 | 1245 | 1245 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-01-08 | 24/08/2026 | 1245 | 1245
ADIDAS | 0903140177-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 267 | 31/08/2026 | 267 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443e | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140177 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 267 | 267 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 31/08/2026 | 267 | 267
ADIDAS | 0903140270-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 506 | 26/08/2026 | 506 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903140270 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 14/08/2026 | 19/08/2026 | 506 | 506 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 506 | 506
ADIDAS | 0903140301-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1170 | 28/08/2026 | 1170 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903140301 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 1170 | 1170 |  |  |  | 14/08/2026 | 24/08/2026 | 2026-04-08 | 28/08/2026 | 1170 | 1170
ADIDAS | 0903140693-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 409 | 28/08/2026 | 409 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 684009 | PRINT L3 SUB PROCESS_V3 | 0903140693 LI2667 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 409 | 409 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-03-08 | 27/08/2026 | 409 | 409
ADIDAS | 0903140729-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 26/08/2026 | 420 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140729 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 420 | 420 |  |  |  | 19/08/2026 | 20/08/2026 | 14/08/2026 | 26/08/2026 | 420 | 420
ADIDAS | 0903140767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 28/08/2026 | 259 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 27/08/2026 | 26/08/2026 | 26/08/2026 | 259 | 259 |  |  |  | 19/08/2026 | 21/08/2026 | 18/08/2026 | 28/08/2026 | 259 | 259
ADIDAS | 0903140818-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 300 | 28/08/2026 | 300 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140818 LI2670 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 28/08/2026 | 21/08/2026 | 27/08/2026 | 300 | 300 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 27/08/2026 | 300 | 300
ADIDAS | 0903140868-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 371 | 26/08/2026 | 371 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140868 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 371 | 371 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 371 | 371
ADIDAS | 0903141670-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 292 | 28/08/2026 | 292 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141670 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 292 | 292 |  |  |  | 18/08/2026 | 20/08/2026 | 14/08/2026 | 26/08/2026 | 292 | 292
ADIDAS | 0903141841-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 455 | 28/08/2026 | 455 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141841 LI2645 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 455 | 455 |  |  |  | 19/08/2026 | 24/08/2026 | 13/08/2026 | 27/08/2026 | 455 | 455
ADIDAS | 0903141927-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 421 | 26/08/2026 | 421 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141927 LI2647 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 421 | 421 |  |  |  | 18/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 421 | 421
ADIDAS | 0903141933-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141933 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 200 | 200
ADIDAS | 0903141960-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 472 | 26/08/2026 | 472 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903141960 LI2667 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 21/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 21/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 472 | 472 |  |  |  | 18/08/2026 | 20/08/2026 | 2026-01-08 | 2026-11-08 | 472 | 472
ADIDAS | 0903141964-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141964 LI2668 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 21/08/2026 | 21/08/2026 | 21/08/2026 | 150 | 150 |  |  |  | 14/08/2026 | 18/08/2026 | 2026-05-08 | 2026-07-08 | 150 | 150
ADIDAS | 0903142009-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 363 | 26/08/2026 | 363 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142009 LI2670 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 363 | 363 |  |  |  | 2026-10-08 | 14/08/2026 | 2026-12-08 | 27/08/2026 | 363 | 363
ADIDAS | 0903142071-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 280 | 26/08/2026 | 280 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142071 LI2672 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 280 | 280 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 2026-03-09 | 280 | 280
ADIDAS | 0903142076-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 960006 | PRINT L3 SUB PROCESS_V3 | 0903142076 LI2669 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 150 | 150 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 150 | 150
ADIDAS | 0903142132-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 250 | 2026-12-09 | 250 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142132 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 250 | 250 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 250 | 250
ADIDAS | 0903142187-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 344 | 28/08/2026 | 344 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142187 LI2671 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 344 | 344 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 344 | 344
ADIDAS | 0903142240-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 305 | 28/08/2026 | 305 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142240 LI2647 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 305 | 305 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 305 | 305
ADIDAS | 0903142291-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 349 | 26/08/2026 | 349 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142291 LI2668 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 349 | 349 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-07-08 | 349 | 349
ADIDAS | 0903142317-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 360 | 26/08/2026 | 360 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142317 LI2646 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 24/08/2026 | 360 | 360 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-06-08 | 19/08/2026 | 360 | 360
ADIDAS | 0903142327-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 100 | 28/08/2026 | 100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142327 LI2668 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 20/08/2026 | 19/08/2026 | 20/08/2026 | 100 | 100 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-07-08 | 100 | 100
ADIDAS | 0903142410-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 380 | 26/08/2026 | 380 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903142410 LI2669 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 18/08/2026 | 2026-12-08 | 14/08/2026 | 380 | 380 |  |  |  | 2026-07-08 | 2026-12-08 | 2026-01-08 | 2026-05-08 | 380 | 379 | 1
ADIDAS | 0903142438-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142438 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 28/08/2026 | 24/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142461-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142461 LI2647 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 24/08/2026 | 19/08/2026 | 28/08/2026 | 200 | 200
ADIDAS | 0903142489-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 200 | 28/08/2026 | 200 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960006 | PRINT L3 SUB PROCESS_V3 | 0903142489 LI2667 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 27/08/2026 | 24/08/2026 | 24/08/2026 | 200 | 200 |  |  |  | 19/08/2026 | 21/08/2026 | 2026-03-08 | 2026-11-08 | 200 | 200
ADIDAS | 0903142499-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 895 | 28/08/2026 | 895 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3 SUB PROCESS_V3 | 0903142499 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 895 | 895 |  |  |  | 2026-12-08 | 19/08/2026 | 2026-04-08 | 2026-10-08 | 895 | 895
ADIDAS | 0903142507-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 100 | 26/09/2026 | 100 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142507 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 100 | 100 |  |  |  | 2026-05-09 | 2026-11-09 | 13/08/2026 | 13/08/2026 | 100 | 100
ADIDAS | 0903142516-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142516 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 21/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142526-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142526 LI2645 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 14/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 14/09/2026 | 22/09/2026 |  |  | 8900 |  | 8900 |  |  | 2026-10-09 | 18/09/2026 |  |  | 8900 |  | 8900
ADIDAS | 0903142529-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 926 | 28/08/2026 | 926 | SI | SI26/06/2026 | G2K | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142529 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 926 | 926 |  |  |  | 20/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 926 | 926
ADIDAS | 0903142537-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 24/09: ex-fty. Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142537 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 150 |  | 150 |  |  | 23/09/2026 | 28/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903142557-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 507 | 28/08/2026 | 507 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3 SUB PROCESS_V3 | 0903142557 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 20/08/2026 | 507 | 507 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 28/08/2026 | 507 | 507
ADIDAS | 0903142558-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142558 LI2646 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 21/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 200 | 200 |  |  |  | 18/08/2026 | 24/08/2026 | 18/08/2026 | 20/08/2026 | 200 | 200
ADIDAS | 0903142574-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142574 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | M 3S CHELSEA B7 |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903142580-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 2026-12-09 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142580 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 160 | 160 |  |  |  | 27/08/2026 | 2026-01-09 | 26/08/2026 | 2026-04-09 | 160 | 160
ADIDAS | 0903142585-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 855 | 28/08/2026 | 855 | SA | SA26/06/2026 | G1I,G1O,G1Q | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142585 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 855 | 855 |  |  |  | 20/08/2026 | 24/08/2026 | 15/08/2026 | 29/08/2026 | 855 | 855
ADIDAS | 0903142605-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142605 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 30/09/2026 | 2026-02-09 | 2026-02-09 | 100 | 2 | 98
ADIDAS | 0903142609-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 566 | 28/08/2026 | 566 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142609 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 21/08/2026 | 26/08/2026 | 566 | 566 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-10-08 | 19/08/2026 | 566 | 566
ADIDAS | 0903142628-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 170 | 28/08/2026 | 170 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142628 LI2668 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 27/08/2026 | 21/08/2026 | 27/08/2026 | 170 | 170 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-04-08 | 2026-05-08 | 170 | 170
ADIDAS | 0903142631-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 2950 | 30/09/2026 | 2950 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 24/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142631 LI2647 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 28/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 2950 |  | 2950 |  |  | 24/09/2026 | 26/09/2026 |  |  | 2950 |  | 2950
ADIDAS | 0903142639-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 560 | 28/08/2026 | 560 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142639 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 560 | 560 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-03-08 | 2026-05-08 | 560 | 560
ADIDAS | 0903142841-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | (08/08/2026) | ok | 22/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903142841 JD1877 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1759 |  | 1759 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903142873-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 30/09/2026 | 1079 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142873 JD5302 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/09/2026 | W 3S FT CF PT |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 1079 |  | 1079 |  |  | 2026-10-09 | 2026-11-09 |  |  | 1079 |  | 1079
ADIDAS | 0903142903-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142903 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 400 |  | 400 |  |  | 17/09/2026 | 18/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903142926-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 399 | 30/09/2026 | 399 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142926 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 399 | 111 | 288 |  |  | 27/08/2026 | 15/09/2026 | 22/08/2026 | 2026-09-09 | 399 | 399
ADIDAS | 0903142998-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 718 | 30/09/2026 | 718 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516204 | EMBRO SUB PROCESS_V1 | 0903142998 JE6419 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-05-09 | 2026-08-09 | 718 | 718 |  |  |  | 31/08/2026 | 2026-04-09 | 15/08/2026 | 2026-07-09 | 718 | 718
ADIDAS | 0903143026-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 899 | 2026-02-09 | 899 | SA | SA26/06/2026 | G2D,G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903143026 GK8824 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 29/08/2026 | 2026-01-09 | 899 | 899 |  |  |  | 24/08/2026 | 28/08/2026 | 21/08/2026 | 31/08/2026 | 899 | 899
ADIDAS | 0903143086-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 719 | 30/09/2026 | 719 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143086 JE1309 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | W 3S WV SHO |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 719 |  | 719 |  |  | 14/09/2026 | 16/09/2026 |  |  | 719 |  | 719
ADIDAS | 0903143118-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903143118 JE6419 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 1318 | 1318 |  |  |  | 31/08/2026 | 2026-04-09 | 29/08/2026 | 31/08/2026 | 1318 | 1318
ADIDAS | 0903143145-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, PI Date 26-Jul, actual receives 17-Jul. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143145 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S WV SHO |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 16/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903143171-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 300 | 28/08/2026 | 300 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3 SUB PROCESS_V3 | 0903143171 LI2669 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 20/08/2026 | 300 | 300 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 2026-04-08 | 300 | 300
ADIDAS | 0903143196-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 28/08/2026 | 300 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143196 LI2647 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 300 | 300 |  |  |  | 13/08/2026 | 19/08/2026 | 19/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0903143227-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 320 | 28/08/2026 | 320 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143227 LI2671 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 320 | 320 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 28/08/2026 | 320 | 320
ADIDAS | 0903143256-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 28/08/2026 | 300 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143256 LI2645 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 300 | 300 |  |  |  | 18/08/2026 | 19/08/2026 | 13/08/2026 | 20/08/2026 | 300 | 300
ADIDAS | 0903143278-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 370 | 28/08/2026 | 370 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143278 LI2646 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 370 | 370 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 21/08/2026 | 370 | 370
ADIDAS | 0903143303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 600 | 23/09/2026 | 600 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 600 | 600 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 600 | 600
ADIDAS | 0903143351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143351 LI2669 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 800 | 800 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 800 | 800
ADIDAS | 0903143380-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 23/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143380 LI2646 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-04-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-04-09 | 28/09/2026 | 2026-04-09 | 2026-07-09 | 8900 | 1996 | 6904 |  |  | 2026-01-09 | 24/09/2026 | 15/08/2026 | 2026-08-09 | 8900 | 8886 | 14
ADIDAS | 0903143435-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1100 | 30/09/2026 | 1100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143435 LI2668 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-09 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-05-09 | 15/09/2026 | 2026-05-09 | 2026-08-09 | 1100 | 1085 | 15 |  |  | 2026-02-09 | 2026-11-09 | 19/08/2026 | 2026-03-09 | 1100 | 1091 | 9
ADIDAS | 0903143462-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3900 | 30/09/2026 | 3900 | SA | SA26/06/2026 | G1E,G1I,G1O | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143462 LI2670 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-09 | 21/09/2026 | 2026-03-09 | 2026-07-09 | 3900 | 2209 | 1691 |  |  | 29/08/2026 | 17/09/2026 | 24/08/2026 | 2026-10-09 | 3900 | 2354 | 1546
ADIDAS | 0903143489-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 5100 | 30/09/2026 | 5100 | SA | SA26/06/2026 | G1E,G1I | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143489 LI2671 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-09 | 2026-01-10 | 2026-07-09 | 2026-07-09 | 5100 | 367 | 4733 |  |  | 2026-03-09 | 28/09/2026 | 24/08/2026 | 14/09/2026 | 5100 | 5101 | -1 | 1 | 14
ADIDAS | 0903144181-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-02-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144181 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 28/08/2026 | 20/08/2026 | 2026-01-09 | 220 | 220
ADIDAS | 0903144227-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 375 | 31/08/2026 | 375 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144227 LI2646 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 29/08/2026 | 375 | 375 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 19/08/2026 | 375 | 375
ADIDAS | 0903144303-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144303 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 200 | 195 | 5
ADIDAS | 0903144665-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 244 | 31/08/2026 | 244 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144665 LI2671 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 244 | 244 |  |  |  | 20/08/2026 | 27/08/2026 | 20/08/2026 | 29/08/2026 | 244 | 244
ADIDAS | 0903144673-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144673 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 26/08/2026 | 200 | 200
ADIDAS | 0903144697-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 456 | 28/08/2026 | 456 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144697 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 456 | 456 |  |  |  | 20/08/2026 | 24/08/2026 | 18/08/2026 | 27/08/2026 | 456 | 456
ADIDAS | 0903144719-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 230 | 28/08/2026 | 230 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3 SUB PROCESS_V3 | 0903144719 LI2667 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 230 | 230 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-03-08 | 2026-05-08 | 230 | 230
ADIDAS | 0903144744-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 180 | 28/08/2026 | 180 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3 SUB PROCESS_V3 | 0903144744 LI2669 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 180 | 180 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-03-08 | 180 | 180
ADIDAS | 0903144771-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 250 | 31/08/2026 | 250 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144771 LI2647 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 250 | 250 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 250 | 250
ADIDAS | 0903144813-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 260 | 2026-02-09 | 260 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144813 LI2672 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 260 | 260 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-05-09 | 260 | 260
ADIDAS | 0903145175-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO SUB PROCESS_V1 | 0903145175 JE6414 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 1319 |  | 1319 |  |  | 14/09/2026 | 16/09/2026 |  |  | 1319 |  | 1319
ADIDAS | 0903145234-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 1050 | 2026-12-09 | 1050 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 12/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145234 IM0081 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | U FI LOGO PT |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050 |  |  | 146 | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050 |  |  | 69
ADIDAS | 0903145265-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 480 | 30/09/2026 | 480 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145265 JE6341 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 480 |  | 480 |  |  | 22/09/2026 | 23/09/2026 |  |  | 480 |  | 480
ADIDAS | 0903145293-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903145293 JE6419 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 2026-10-09 | 1318 | 1082 | 236 |  |  | 2026-04-09 | 2026-11-09 | 29/08/2026 | 2026-02-09 | 1318 | 1294 | 24
ADIDAS | 0903145318-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 499 | 30/09/2026 | 499 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145318 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 499 |  | 499 |  |  | 17/09/2026 | 18/09/2026 |  |  | 499 |  | 499
ADIDAS | 0903145343-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 451 | 2026-09-09 | 451 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145343 IM0081 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | U FI LOGO PT |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 451 | 451 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-07-09 | 451 | 451
ADIDAS | 0903145368-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 450 | 2026-09-09 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145368 IS4395 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 450 | 450
ADIDAS | 0903145380-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 15/10/2026 | 315 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145380 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | M 3S CHELSEA B7 |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 315 |  | 315 |  |  | 29/09/2026 | 2026-01-10 |  |  | 315 |  | 315
ADIDAS | 0903145392-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145392 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M 3S CHELSEA B7 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 330 |  | 330 |  |  | 2026-01-10 | 2026-02-10 |  |  | 330 |  | 330
ADIDAS | 0903145395-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 09/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145395 IS4395 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-09-09 | 1051 | 1051 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-03-09 | 1051 | 1051
ADIDAS | 0903145433-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 15/10/2026 | 450 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145433 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M 3S CHELSEA B7 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 450 |  | 450 |  |  | 2026-01-10 | 2026-02-10 |  |  | 450 |  | 450
ADIDAS | 0903145448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145448 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 420 |  | 420 |  |  | 2026-02-10 | 2026-03-10 |  |  | 420 |  | 420
ADIDAS | 0903145462-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145462 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 345 |  | 345 |  |  | 2026-02-10 | 2026-03-10 |  |  | 345 |  | 345
ADIDAS | 0903145473-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145473 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 420 |  | 420 |  |  | 2026-03-10 | 2026-05-10 |  |  | 420 |  | 420
ADIDAS | 0903145504-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 960 | 30/09/2026 | 960 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 25/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145504 JD1877 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 960 |  | 960 |  |  | 17/09/2026 | 19/09/2026 |  |  | 960 |  | 960
ADIDAS | 0903145534-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 401 | 30/09/2026 | 401 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145534 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 401 |  | 401 |  |  | 28/09/2026 | 29/09/2026 | 28/08/2026 | 2026-11-09 | 401 | 386 | 15
ADIDAS | 0903145568-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145568 JE6340 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 14/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903145571-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145571 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 435 |  | 435 |  |  | 2026-03-10 | 2026-05-10 |  |  | 435 |  | 435
ADIDAS | 0903145627-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 30/09/2026 | 359 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145627 JE6340 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 359 |  | 359 |  |  | 16/09/2026 | 18/09/2026 |  |  | 359 |  | 359
ADIDAS | 0903146197-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 30/09/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903146197 LC8884 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M RESORT T BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 128 |  | 128 |  |  | 15/09/2026 | 15/09/2026 | 28/07/2026 | 2026-11-08 | 128 | 99 | 29
ADIDAS | 0903146288-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 222 | 30/09/2026 | 222 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (07/08/2026) | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146288 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 18/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 222 |  | 222 |  |  | 15/09/2026 | 15/09/2026 |  |  | 222 |  | 222
ADIDAS | 0903146309-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Cargoport). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146309 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 150 |  | 150 |  |  | 26/09/2026 | 28/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903146354-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 215 | 23/09/2026 | 215 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903146354 KX0126 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 16/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 215 |  | 215 |  |  | 2026-12-09 | 15/09/2026 | 2026-05-08 | 2026-12-08 | 215 | 205 | 10
ADIDAS | 0903146398-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Cargoport). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146398 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 174 |  | 174 |  |  | 21/10/2026 | 22/10/2026 |  |  | 174 |  | 174 |  |  | 15/10/2026 | 16/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146484-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 308 | 15/10/2026 | 308 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146484 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 20/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 308 |  | 308 |  |  | 16/10/2026 | 17/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903146520-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 274 | 15/10/2026 | 274 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146520 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 274 |  | 274 |  |  | 22/10/2026 | 23/10/2026 |  |  | 274 |  | 274
ADIDAS | 0903146532-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146532 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 174 |  | 174 |  |  | 24/10/2026 | 26/10/2026 |  |  | 174 |  | 174 |  |  | 19/10/2026 | 20/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146599-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 895 | 15/10/2026 | 895 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903146599 KY5988 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-12-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 895 |  | 895 |  |  | 2026-08-10 | 2026-09-10 |  |  | 895 |  | 895 |  |  | 2026-02-10 | 2026-03-10 |  |  | 895 |  | 895
ADIDAS | 0903146738-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 126 | 30/09/2026 | 126 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903146738 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 19/09/2026 |  |  | 126 |  | 126 |  |  | 15/09/2026 | 16/09/2026 |  |  | 126 |  | 126 |  |  | 14/09/2026 | 15/09/2026 |  |  | 126 |  | 126
ADIDAS | 0903146791-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 15/10/2026 | 100 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 512108 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903146791 KX7715 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 18/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 18/09/2026 | 22/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 18/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903146836-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 174 | 30/09/2026 | 174 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Damco offline). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 688010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146836 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 174 |  | 174 |  |  | 26/09/2026 | 28/09/2026 | 26/08/2026 | 31/08/2026 | 174 | 151 | 23
ADIDAS | 0903147020-1 KT4840 | ONIX | 90D | S2408MR1600 | 386 | 15/10/2026 | 386 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903147020 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 386 |  | 386 |  |  | 2026-12-10 | 13/10/2026 |  |  | 386 |  | 386 |  |  | 2026-10-10 | 2026-12-10 |  |  | 386 |  | 386
ADIDAS | 0903147025-1 KE6712 | BLACK | 105D | S2608MR0601A | 448 | 15/10/2026 | 448 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147025 KE6712 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 448 |  | 448 |  |  | 17/10/2026 | 19/10/2026 |  |  | 448 |  | 448 |  |  | 16/10/2026 | 17/10/2026 |  |  | 448 |  | 448
ADIDAS | 0903147045-1 JD0957 | BLACK | 60D | S25ORISW311 | 800 | 15/10/2026 | 800 | ID | ID26/06/2026 | G3J | SHORTS | G3 | ok | ok | T2 Fu Hsun, PI Date 29-Jul, actual receives 14-Aug. T2 Libolon, PI Date 29-Jul, actual receives 09-Jul. 960006 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903147045 JD0957 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIC SWIMSH 5IN |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 800 |  | 800 |  |  | 2026-06-10 | 2026-07-10 |  |  | 800 |  | 800
ADIDAS | 0903147053-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 382 | 15/10/2026 | 382 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147053 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 19/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 19/10/2026 | 21/10/2026 |  |  | 382 |  | 382 |  |  | 15/10/2026 | 17/10/2026 |  |  | 382 |  | 382 |  |  | 14/10/2026 | 16/10/2026 |  |  | 382 |  | 382
ADIDAS | 0903147253-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147253 KD3911 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 881 |  | 881 |  |  | 2026-11-09 | 2026-12-09 | 13/09/2026 | 13/09/2026 | 881 | 824 | 57
ADIDAS | 0903147280-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1560 | 30/09/2026 | 1560 | SI | SI26/06/2026 | G3E | PANTS | G3 | (29/07/2026) | ok | 25/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903147280 HK7317 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | ESS SWTP |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 1560 |  | 1560 |  |  | 19/09/2026 | 23/09/2026 |  |  | 1560 |  | 1560
ADIDAS | 0903147309-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147309 JW7177 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 30/09/2026 | W 3S FT OH PT |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1541 |  | 1541 |  |  | 26/09/2026 | 29/09/2026 | 2026-07-09 | 14/09/2026 | 1541 | 1340 | 201 |  | 863
ADIDAS | 0903147338-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903147338 HK7319 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | ESS SWTP |  | SS27 | 23/09/2026 | 29/09/2026 |  |  | 2641 |  | 2641 |  |  | 19/09/2026 | 25/09/2026 |  |  | 2641 |  | 2641
ADIDAS | 0903147369-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 599 | 2026-02-09 | 599 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147369 HL2270 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | IN RANGE |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 599 | 599 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 599 | 599
ADIDAS | 0903147397-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 2101 | 28/08/2026 | 2101 | SA | SA26/06/2026 | G2D,G2F,G2S | PANTS | G2 | (29/07/2026) | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903147397 GK8824 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | M 3S FL TC PT |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 2101 | 2101 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-12-08 | 19/08/2026 | 2101 | 2101
ADIDAS | 0903147489-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 597 | 2026-02-09 | 597 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147489 H57046 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 2026-01-09 | 26/08/2026 | 29/08/2026 | 597 | 597 |  |  |  | 20/08/2026 | 28/08/2026 | 22/08/2026 | 27/08/2026 | 597 | 597
ADIDAS | 0903147513-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903147513 KD3911 | 2026-10-08 | KAHATEX CIJERAH | SPAIN | SEA | 16/09/2026 | RELEASED |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 881 |  | 881 |  |  | 2026-12-09 | 14/09/2026 | 13/09/2026 | 14/09/2026 | 881 | 725 | 156
ADIDAS | 0903147547-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 1400 | 28/08/2026 | 1400 | SA | SA26/06/2026 | G2D,G2F,G2S | PANTS | G2 | (29/07/2026) | ok | 28/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903147547 GK8823 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | M 3S FL TC PT |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1400 | 1400 |  |  |  | 19/08/2026 | 24/08/2026 | 26/08/2026 | 28/08/2026 | 1400 | 1400
ADIDAS | 0903147569-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 601 | 2026-02-09 | 601 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147569 GK8823 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 601 | 601 |  |  |  | 24/08/2026 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 601 | 601
ADIDAS | 0903147631-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3E | PANTS | G3 | (29/07/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903147631 HK7317 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | ESS SWTP |  | SS27 | 26/09/2026 | 2026-02-10 |  |  | 2860 |  | 2860 |  |  | 23/09/2026 | 29/09/2026 |  |  | 2860 |  | 2860
ADIDAS | 0903147665-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516442 | EMBRO SUB PROCESS_V1 | 0903147665 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1320 |  | 1320 |  |  | 15/09/2026 | 17/09/2026 | 2026-11-08 | 31/08/2026 | 1320 | 1320
ADIDAS | 0903147675-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 895 | 30/09/2026 | 895 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903147675 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 895 |  | 895 |  |  | 16/09/2026 | 17/09/2026 |  |  | 895 |  | 895 |  |  | 15/09/2026 | 16/09/2026 |  |  | 895 |  | 895
ADIDAS | 0903147741-1 GV5295 | BLACK/WHITE | 45D | F213CSIM109FL | 899 | 31/08/2026 | 899 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 |  |  | 31/08: ex-fty (S4EU). DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903147741 GV5295 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/07/2026 | M FEELCOZY SWT |  | SS27 | 23/07/2026 | 28/07/2026 | 23/07/2026 | 28/07/2026 | 899 | 899 |  |  |  | 20/07/2026 | 23/07/2026 | 20/07/2026 | 24/07/2026 | 899 | 899
ADIDAS | 0903147765-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 900 | 30/09/2026 | 900 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147765 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | W 3S FT FZ HD |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 900 |  | 900 |  |  | 18/09/2026 | 19/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903147789-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 30/09/2026 | 720 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903147789 JE6414 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 720 |  | 720 |  |  | 2026-11-09 | 14/09/2026 | 29/08/2026 | 2026-01-09 | 720 | 634 | 86
ADIDAS | 0903147800-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 838 | 15/10/2026 | 838 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147800 KX7716 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 14/10/2026 | 19/10/2026 |  |  | 838 |  | 838 |  |  | 2026-10-10 | 15/10/2026 |  |  | 838 |  | 838
ADIDAS | 0903147835-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 675 | 15/10/2026 | 675 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516443 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147835 KX7716 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 26/09/2026 | 2026-01-10 |  |  | 675 |  | 675 |  |  | 23/09/2026 | 28/09/2026 |  |  | 675 |  | 675
ADIDAS | 0903147850-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903147850 JE6340 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 14/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903147881-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147881 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 1319 |  | 1319 |  |  | 16/09/2026 | 19/09/2026 | 2026-11-08 | 2026-01-09 | 1319 | 493 | 826
ADIDAS | 0903147929-1 GN4054 | BLACK/WHITE | 60D | S211CSIG213 | 901 | 31/08/2026 | 901 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | HT SUB PROCESS_V1 | 0903147929 GN4054 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | IN RANGE |  | SS27 | 26/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 901 | 901 |  |  |  | 21/08/2026 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 901 | 901 |  |  |  | 20/08/2026 | 24/08/2026 | 2026-07-08 | 26/08/2026 | 901 | 901
ADIDAS | 0903147940-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 241 | 15/09/2026 | 241 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903147940 LE8193 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 241 | 241 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-07-09 | 241 | 241
ADIDAS | 0903147956-1 GN4054 | BLACK/WHITE | 60D | S211CSIG213 | 2100 | 26/08/2026 | 2100 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 26/08: ex-fty 516318 | HT SUB PROCESS_V1 | 0903147956 GN4054 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | IN RANGE |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 2100 | 2100 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-05-08 | 2026-11-08 | 2100 | 2100 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-05-08 | 2026-10-08 | 2100 | 2100
ADIDAS | 0903147997-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 335 | 23/09/2026 | 335 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903147997 LC8884 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 16/09/2026 | M RESORT T BLACK |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 335 |  | 335 |  |  | 2026-12-09 | 15/09/2026 | 28/07/2026 | 2026-11-08 | 335 | 335
ADIDAS | 0903148037-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 1321 | 30/09/2026 | 1321 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148037 JE1309 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV SHO |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 1321 |  | 1321 |  |  | 16/09/2026 | 18/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903148066-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903148066 JE6338 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | M 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1760 |  | 1760 |  |  | 26/09/2026 | 29/09/2026 | 2026-03-09 | 2026-05-09 | 1760 | 486 | 1274
ADIDAS | 0903148083-1 LC6583 | GREY | 105D | S2750MTR051 | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 830009 | HT SUB PROCESS_V1 | 0903148083 LC6583 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | D4T ESS T GREY |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 110 |  | 110 |  |  | 28/09/2026 | 29/09/2026 |  |  | 110 |  | 110 |  |  | 26/09/2026 | 28/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903148089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 719 | 30/09/2026 | 719 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903148089 JE6417 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 719 |  | 719 |  |  | 22/09/2026 | 23/09/2026 | 2026-11-08 | 2026-01-09 | 719 | 715 | 4
ADIDAS | 0903148210-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 15/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516471 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148210 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 300 | 263 | 37 |  | 47 | 2026-05-09 | 2026-11-09 | 26/08/2026 | 2026-11-09 | 300 | 300
ADIDAS | 0903148776-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 561 | 15/10/2026 | 561 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148776 KY5988 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-10-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 561 |  | 561 |  |  | 2026-07-10 | 2026-08-10 |  |  | 561 |  | 561 |  |  | 2026-01-10 | 2026-02-10 |  |  | 561 |  | 561
ADIDAS | 0903148797-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 603 | 30/09/2026 | 603 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903148797 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 15/09/2026 | 14/08/2026 | 2026-03-09 | 603 | 603 |  |  |  | 2026-11-08 | 2026-12-09 | 30/07/2026 | 2026-06-08 | 603 | 603 |  |  |  | 2026-10-08 | 2026-11-09 | 29/07/2026 | 13/08/2026 | 603 | 603
ADIDAS | 0903148818-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 318 | 23/09/2026 | 318 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148818 LE8181 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 318 |  | 318 |  |  | 15/09/2026 | 15/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903148821-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 443 | 15/09/2026 | 443 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903148821 LE8193 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-02-09 | 443 | 443
ADIDAS | 0903148878-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148878 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 19/10/2026 | W 3S FT OH PT |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 437 |  | 437 |  |  | 15/10/2026 | 16/10/2026 |  |  | 437 |  | 437
ADIDAS | 0903148893-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 312 | 23/09/2026 | 312 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148893 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 22/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 312 |  | 312 |  |  | 18/09/2026 | 18/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903148948-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 142 | 15/10/2026 | 142 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903148948 LD6542 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 142 |  | 142 |  |  | 13/10/2026 | 15/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903148963-1 LE8187 | BLACK | 105D | S2754MAS513 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148963 LE8187 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | M SL WV TP PT BLACK |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 174 |  | 174 |  |  | 22/10/2026 | 23/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903148974-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 948 | 2026-02-10 | 948 | SI | SI26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903148974 LD0930 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-10 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 948 |  | 948 |  |  | 28/09/2026 | 29/09/2026 |  |  | 948 |  | 948 |  |  | 25/09/2026 | 26/09/2026 |  |  | 948 |  | 948
ADIDAS | 0903148990-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 455 | 15/10/2026 | 455 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148990 LF0718 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 455 |  | 455 |  |  | 2026-10-10 | 2026-12-10 |  |  | 455 |  | 455
ADIDAS | 0903148994-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903148994 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-10 | M 3S FT TC PT |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 437 |  | 437 |  |  | 2026-07-10 | 2026-08-10 |  |  | 437 |  | 437
ADIDAS | 0903149007-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 101 | 30/09/2026 | 101 | SA | SA26/06/2026 | G2J | T-SHIRT | G2 | (28/08/2026) | ok | 23/09: ex-fty 838103 | PAD+HT SUB PROCESS_V3 | 0903149007 JG5832 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/09/2026 | SQUA133 JSY M BLACK/WHITE |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 101 |  | 101 |  |  | 23/09/2026 | 24/09/2026 |  |  | 101 |  | 101 |  |  | 22/09/2026 | 23/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903149019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Aug. T2 Libolon, PI Date 22-Jul, actual receives 25-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149019 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 |  |  | 1 |  | 1
ADIDAS | 0903149036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 660 | 15/10/2026 | 660 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903149036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 660 |  | 660 |  |  | 19/10/2026 | 20/10/2026 |  |  | 660 |  | 660 |  |  | 13/10/2026 | 14/10/2026 |  |  | 660 |  | 660
ADIDAS | 0903149043-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149043 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 1 |  | 1 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149056-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 1 | 30/09/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149056 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 1 |  | 1 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1 |  | 1
ADIDAS | 0903149090-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3H | PANTS | G3 | ok | (07/08/2026(3)) | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149090 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 | 2026-07-08 | 2026-07-08 | 1 | 1
ADIDAS | 0903149104-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149104 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 17/09/2026 | 22/09/2026 |  |  | 1 |  | 1 |  |  | 14/09/2026 | 18/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149132-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 387 | 29/09/2026 | 387 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149132 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 22/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 387 |  | 387 |  |  | 18/09/2026 | 19/09/2026 | 26/08/2026 | 2026-03-09 | 387 | 369 | 18
ADIDAS | 0903149247-1 KT4840 | ONIX | 90D | S2408MR1600 | 150 | 15/10/2026 | 150 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903149247 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 150 |  | 150 |  |  | 2026-12-10 | 13/10/2026 | 2026-12-09 | 2026-12-09 | 150 | 2 | 148 |  | 2 | 2026-10-10 | 2026-12-10 | 2026-05-09 | 2026-05-09 | 150 | 2 | 148
ADIDAS | 0903149419-1 KT4840 | ONIX | 90D | S2408MR1600 | 2315 | 23/09/2026 | 2315 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903149419 KT4840 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 18/09/2026 |  |  | 2315 |  | 2315 |  |  | 2026-12-09 | 16/09/2026 | 2026-08-09 | 2026-11-09 | 2315 | 1946 | 369 |  |  | 2026-11-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 2315 | 1961 | 354
ADIDAS | 0903149526-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 399 | 31/08/2026 | 399 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L2+PAD SUB PROCESS_V3 | 0903149526 KU2430 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/08/2026 | M FB NOVELTY T WHITE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 399 | 399 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-11-08 | 22/08/2026 | 399 | 399
ADIDAS | 0903149560-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 329 | 26/08/2026 | 329 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903149560 KU2430 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | M FB NOVELTY T WHITE |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 329 | 329 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-11-08 | 21/08/2026 | 329 | 329
ADIDAS | 0903149656-1 HK7319 | BLACK | 90D | F2225M403 | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149656 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ESS SWTP |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 400 |  | 400 |  |  | 18/09/2026 | 19/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903149744-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149744 HK7319 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-05-10 |  |  | 2641 |  | 2641 |  |  | 25/09/2026 | 2026-01-10 |  |  | 2641 |  | 2641
ADIDAS | 0903149771-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 600 | 30/09/2026 | 600 | SI | SI26/06/2026 | G3D | PANTS | G3 | (29/07/2026) | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149771 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ESS SWTP |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 600 |  | 600 |  |  | 18/09/2026 | 21/09/2026 |  |  | 600 |  | 600
ADIDAS | 0903149799-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 601 | 31/08/2026 | 601 | SA | SA26/06/2026 | G3I | PANTS | G3 | (29/07/2026(9)) |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903149799 GK9267 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/07/2026 | M 3S FL O PT |  | SS27 | 22/07/2026 | 30/07/2026 | 24/07/2026 | 28/07/2026 | 601 | 601 |  |  |  | 17/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 601 | 601
ADIDAS | 0903149833-1 HZ0747 | BLACK | 90D | F2325M414 | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903149833 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 399 |  | 399 |  |  | 2026-11-09 | 2026-12-09 | 31/08/2026 | 2026-02-09 | 399 | 398 | 1
ADIDAS | 0903149866-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149866 HR8583 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | ESS SWTP |  | SS27 | 2026-05-10 | 2026-10-10 |  |  | 3300 |  | 3300 |  |  | 2026-01-10 | 2026-07-10 |  |  | 3300 |  | 3300
ADIDAS | 0903149894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 25/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149894 IB8686 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | ESS TEE |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 2200 |  | 2200 |  |  | 2026-11-09 | 14/09/2026 | 2026-12-08 | 2026-12-09 | 2200 | 2187 | 13 |  | 194
ADIDAS | 0903149921-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 1398 | 28/08/2026 | 1398 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903149921 HL2270 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | IN RANGE |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1398 | 1398 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 24/08/2026 | 1398 | 1398
ADIDAS | 0903149953-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903149953 IB8686 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/09/2026 | ESS TEE |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 1200 |  | 1200 |  |  | 2026-10-09 | 2026-11-09 | 26/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903149971-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 820 | 15/10/2026 | 820 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903149971 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 26/10/2026 | 28/10/2026 |  |  | 820 |  | 820 |  |  | 23/10/2026 | 26/10/2026 |  |  | 820 |  | 820 |  |  | 22/10/2026 | 24/10/2026 |  |  | 820 |  | 820
ADIDAS | 0903149978-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149978 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | PL TEE |  | SS27 | 19/09/2026 | 25/09/2026 |  |  | 4543 |  | 4543 |  |  | 16/09/2026 | 22/09/2026 |  |  | 4543 |  | 4543
ADIDAS | 0903150021-1 KA0246 | BLACK | 90D | S2608WR0902 | 399 | 2026-07-10 | 399 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903150021 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 399 |  | 399 |  |  | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 24/09/2026 | 26/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903150041-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 900 | 2026-02-09 | 900 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903150041 GK8821 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 900 | 900 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 2026-02-09 | 900 | 900
ADIDAS | 0903150068-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150068 IB8686 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | ESS TEE |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 2200 |  | 2200 |  |  | 14/09/2026 | 16/09/2026 | 2026-11-08 | 31/08/2026 | 2200 | 2200
ADIDAS | 0903150072-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 1200 | 2026-07-10 | 1200 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516260 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903150072 KY5988 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 1200 |  | 1200 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1200 |  | 1200 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1200 |  | 1200
ADIDAS | 0903150101-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 360 | 30/09/2026 | 360 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903150101 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 360 |  | 360 |  |  | 23/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 360 | 332 | 28
ADIDAS | 0903150103-1 HZ0747 | BLACK | 90D | F2325M414 | 2478 | 30/09/2026 | 2478 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903150103 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 19/09/2026 |  |  | 2478 |  | 2478 |  |  | 2026-12-09 | 16/09/2026 | 2026-01-09 | 13/09/2026 | 2478 | 2472 | 6 |  | 314
ADIDAS | 0903150130-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1800 | 30/09/2026 | 1800 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903150130 HR8583 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | ESS SWTP |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1800 |  | 1800 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1800 |  | 1800
ADIDAS | 0903150152-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 26/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150152 JE6341 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 30/09/2026 |  |  | 881 |  | 881 |  |  | 23/09/2026 | 26/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150214-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | (08/08/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150214 JD1877 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 1759 |  | 1759 |  |  | 21/09/2026 | 24/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903150242-1 IY9082 | ALUMINA S20 | 45D | F213CSIM109FL | 449 | 31/08/2026 | 449 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903150242 IY9082 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/07/2026 | M FEELCOZY SWT |  | SS27 | 17/07/2026 | 23/07/2026 | 20/07/2026 | 23/07/2026 | 449 | 449 |  |  |  | 14/07/2026 | 20/07/2026 | 17/07/2026 | 20/07/2026 | 449 | 449
ADIDAS | 0903150279-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 901 | 30/09/2026 | 901 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150279 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | W 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 901 |  | 901 |  |  | 29/09/2026 | 2026-01-10 | 28/08/2026 | 2026-11-09 | 901 | 862 | 39
ADIDAS | 0903150304-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150304 JE6338 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1760 |  | 1760 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903150340-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150340 JE6341 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M 3S FT FZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 881 |  | 881 |  |  | 19/09/2026 | 22/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150366-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 959 | 30/09/2026 | 959 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150366 JE6338 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 959 |  | 959 |  |  | 16/09/2026 | 18/09/2026 |  |  | 959 |  | 959
ADIDAS | 0903150392-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1321 | 30/09/2026 | 1321 | SI | SI26/06/2026 | G3J | SHORTS | G3 | (10/08/2026) | ok | 26/09: ex-fty. Waiting fabric. T2 Gistex, (3S) PI Date 10-Aug, ETD ?? T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150392 JE1309 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | W 3S WV SHO |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1321 |  | 1321 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903150471-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 28/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150471 JE6417 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 26/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 26/09/2026 | 30/09/2026 |  |  | 1320 |  | 1320 |  |  | 23/09/2026 | 26/09/2026 | 2026-11-08 | 2026-01-09 | 1320 | 1320
ADIDAS | 0903150495-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150495 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 500 |  | 500 |  |  | 15/09/2026 | 17/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903150517-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 372 | 29/09/2026 | 372 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | ok | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150517 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 372 |  | 372 |  |  | 17/09/2026 | 18/09/2026 |  |  | 372 |  | 372 |  |  | 15/09/2026 | 16/09/2026 |  |  | 372 |  | 372
ADIDAS | 0903150541-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1148 | 14/10/2026 | 1148 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150541 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 1148 |  | 1148 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1148 |  | 1148 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1148 |  | 1148
ADIDAS | 0903150629-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1235 | 14/10/2026 | 1235 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150629 LD0283 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-01-10 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 1235 |  | 1235 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1235 |  | 1235 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1235 |  | 1235
ADIDAS | 0903150630-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 648 | 15/09/2026 | 648 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903150630 LE8210 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 648 | 234 | 414 |  | 222 | 2026-09-09 | 2026-11-09 | 2026-08-09 | 2026-11-09 | 648 | 535 | 113
ADIDAS | 0903150635-1 IS1413 | BLACK | 60D | S2425M405 | 1042 | 26/08/2026 | 1042 | SI | SI26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903150635 IS1413 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 20/08/2026 | IN RANGE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 1042 | 1042 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-04-08 | 24/08/2026 | 1042 | 1042
ADIDAS | 0903150899-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 181 | 30/09/2026 | 181 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903150899 LC6339 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 181 |  | 181 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-09-09 | 181 | 157 | 24
ADIDAS | 0903150944-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 345 | 30/09/2026 | 345 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150944 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 345 |  | 345 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-09-09 | 345 | 335 | 10
ADIDAS | 0903150972-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 126 | 15/10/2026 | 126 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150972 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | M SL WV TP PT BLACK |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 126 |  | 126 |  |  | 22/10/2026 | 23/10/2026 |  |  | 126 |  | 126
ADIDAS | 0903151028-1 IS1413 | BLACK | 60D | S2425M405 | 378 | 2026-12-09 | 378 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903151028 IS1413 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 378 | 378 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-11-08 | 2026-03-09 | 378 | 378
ADIDAS | 0903151088-1 KC4947 | BLACK | 105D | S2608WR0216 | 566 | 15/10/2026 | 566 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903151088 KC4947 | 24/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA | 21/10/2026 | adi365 Astro W |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 566 |  | 566 |  |  | 17/10/2026 | 20/10/2026 |  |  | 566 |  | 566 |  |  | 16/10/2026 | 19/10/2026 |  |  | 566 |  | 566
ADIDAS | 0903151096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903151096 IZ0443 | 28/07/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-02-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903151127-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2C | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903151127 JE6419 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 540 |  | 540 |  |  | 19/09/2026 | 21/09/2026 | 18/08/2026 | 29/08/2026 | 540 | 540
ADIDAS | 0903151171-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151171 LC8884 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 | 2026-11-08 | 2026-11-08 | 100 | 96 | 4
ADIDAS | 0903151219-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 327 | 15/10/2026 | 327 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903151219 LE5609 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/10/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 28/10/2026 | 28/10/2026 |  |  | 327 |  | 327 |  |  | 24/10/2026 | 24/10/2026 |  |  | 327 |  | 327 |  |  | 19/10/2026 | 19/10/2026 |  |  | 327 |  | 327
ADIDAS | 0903151248-1 LF0723 | BLACK | 105D | S2754MAS511B | 373 | 15/10/2026 | 373 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151248 LF0723 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/10/2026 | M SL WV SHO BLACK |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 373 |  | 373 |  |  | 19/10/2026 | 22/10/2026 |  |  | 373 |  | 373
ADIDAS | 0903151295-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151295 KX0126 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 2026-12-10 | 2026-05-08 | 20/08/2026 | 100 | 94 | 6
ADIDAS | 0903151313-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151313 JN1958 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W 3S FT QZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1540 |  | 1540 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151330-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 26/09: ex-fty 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151330 JN1958 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 16/09/2026 | W 3S FT QZ HD |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 1540 |  | 1540 |  |  | 2026-12-09 | 15/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151405-1 H12221 | MEDIUM GREY HEATHER/BLACK | 45D | F213CSIM109FL | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903151405 H12221 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/07/2026 | M FEELCOZY SWT |  | SS27 | 23/07/2026 | 28/07/2026 | 24/07/2026 | 29/07/2026 | 450 | 450 |  |  |  | 20/07/2026 | 23/07/2026 | 24/07/2026 | 27/07/2026 | 450 | 450
ADIDAS | 0903151431-1 H12258 | DARK GREY HEATHER/BLACK | 45D | S211CSIM117FLRO | 598 | 31/08/2026 | 598 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903151431 H12258 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-07 | M 3S FL O PT |  | SS27 | 2026-10-07 | 27/07/2026 | 2026-10-07 | 27/07/2026 | 598 | 598 |  |  |  | 2026-07-07 | 22/07/2026 | 18/07/2026 | 22/07/2026 | 598 | 598
ADIDAS | 0903151460-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 2100 | 28/08/2026 | 2100 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903151460 GK8821 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S FL TC PT |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 2100 | 2100 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-12-08 | 19/08/2026 | 2100 | 2100
ADIDAS | 0903151539-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151539 JN1958 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | W 3S FT QZ HD |  | SS27 | 2026-12-09 | 14/09/2026 | 2026-12-09 | 14/09/2026 | 840 | 543 | 297 |  | 247 | 2026-09-09 | 2026-10-09 | 2026-09-09 | 2026-10-09 | 840 | 758 | 82
ADIDAS | 0903151579-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151579 JW7177 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | W 3S FT OH PT |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 1541 |  | 1541 |  |  | 29/09/2026 | 30/09/2026 | 31/08/2026 | 2026-08-09 | 1541 | 1533 | 8
ADIDAS | 0903151624-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151624 JW7178 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-12-10 | W 3S FT OH PT |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 1431 |  | 1431 |  |  | 2026-08-10 | 2026-10-10 | 2026-12-09 | 13/09/2026 | 1431 | 1195 | 236 |  | 1015
ADIDAS | 0903151645-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 355 | 15/10/2026 | 355 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903151645 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 355 |  | 355 |  |  | 24/10/2026 | 26/10/2026 |  |  | 355 |  | 355 |  |  | 19/10/2026 | 20/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903152156-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1054 | 29/09/2026 | 1054 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152156 KX3650 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1054 |  | 1054 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1054 |  | 1054 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1054 |  | 1054
ADIDAS | 0903152165-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 752 | 15/09/2026 | 752 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152165 LE8201 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 14/09/2026 | 2026-07-09 | 14/09/2026 | 752 | 700 | 52 |  | 138 | 2026-02-09 | 2026-10-09 | 2026-03-09 | 13/09/2026 | 752 | 741 | 11 |  | 3
ADIDAS | 0903152177-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 370 | 29/09/2026 | 370 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152177 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 15/09/2026 | 15/09/2026 |  |  | 370 |  | 370 |  |  | 2026-11-09 | 2026-11-09 |  |  | 370 |  | 370 |  |  | 2026-09-09 | 2026-09-09 |  |  | 370 |  | 370
ADIDAS | 0903152204-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 4012 | 15/09/2026 | 4012 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152204 LE8202 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-05-09 | 14/09/2026 | 2026-07-09 | 14/09/2026 | 4012 | 3503 | 509 |  | 185 | 2026-02-09 | 2026-10-09 | 21/08/2026 | 2026-09-09 | 4012 | 3749 | 263
ADIDAS | 0903152214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 756 | 29/09/2026 | 756 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152214 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 22/09/2026 |  |  | 756 |  | 756 |  |  | 18/09/2026 | 18/09/2026 |  |  | 756 |  | 756 |  |  | 16/09/2026 | 16/09/2026 |  |  | 756 |  | 756
ADIDAS | 0903152235-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 351 | 15/09/2026 | 351 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152235 LE8208 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 15/09/2026 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 15/09/2026 | 15/09/2026 |  |  | 351 |  | 351 |  |  | 2026-11-09 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 351 | 338 | 13 |  | 4
ADIDAS | 0903152275-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 1600 | 30/09/2026 | 1600 | SI | SI26/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152275 LE8194 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 1600 | 1600 |  |  |  | 29/08/2026 | 2026-09-09 | 2026-03-09 | 2026-10-09 | 1600 | 1600
ADIDAS | 0903152279-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 875 | 14/09/2026 | 875 | AN | AN26/06/2026 | G3J,G3K | PANTS | G3 | ok | ok | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152279 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 875 | 419 | 456 |  |  | 2026-05-09 | 2026-11-09 | 2026-10-09 | 2026-12-09 | 875 | 850 | 25 |  | 495 | 31/08/2026 | 2026-05-09 | 2026-08-09 | 14/09/2026 | 875 | 859 | 16 |  | 433
ADIDAS | 0903152318-1 KE6712 | BLACK | 105D | S2608MR0601A | 1026 | 15/10/2026 | 1026 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 678002 | PAD+HT SUB PROCESS_V3 | 0903152318 KE6712 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 22/10/2026 | 26/10/2026 |  |  | 1026 |  | 1026 |  |  | 19/10/2026 | 22/10/2026 |  |  | 1026 |  | 1026 |  |  | 17/10/2026 | 21/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903152321-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 4210 | 15/09/2026 | 4210 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152321 LE8193 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL H F JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 14/09/2026 | 2026-04-09 | 2026-11-09 | 4210 | 3745 | 465 |  |  | 29/08/2026 | 2026-10-09 | 18/08/2026 | 2026-12-09 | 4210 | 4163 | 47 |  | 60
ADIDAS | 0903152351-1 KE6899 | BLACK | 105D | S2608WR0601B | 661 | 15/10/2026 | 661 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903152351 KE6899 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 661 |  | 661 |  |  | 2026-02-11 | 2026-03-11 |  |  | 661 |  | 661 |  |  | 31/10/2026 | 2026-02-11 |  |  | 661 |  | 661
ADIDAS | 0903152382-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 828 | 29/09/2026 | 828 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152382 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 828 |  | 828 |  |  | 2026-11-09 | 2026-12-09 |  |  | 828 |  | 828 |  |  | 2026-09-09 | 2026-10-09 |  |  | 828 |  | 828
ADIDAS | 0903152458-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 396 | 29/09/2026 | 396 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152458 LD0930 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 16/09/2026 | 16/09/2026 |  |  | 396 |  | 396 |  |  | 2026-12-09 | 2026-12-09 |  |  | 396 |  | 396 |  |  | 2026-10-09 | 2026-10-09 |  |  | 396 |  | 396
ADIDAS | 0903152502-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 300 | 29/09/2026 | 300 | SA | SA26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152502 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 2026-12-09 | 14/09/2026 |  |  | 300 |  | 300 |  |  | 2026-07-09 | 2026-08-09 |  |  | 300 |  | 300
ADIDAS | 0903152532-1 LG9669 | BLACK | 120D | S2754WAS514C | 319 | 29/09/2026 | 319 | ID | ID26/06/2026 | G3C | SKIRT | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 12-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152532 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 319 |  | 319 |  |  | 21/09/2026 | 23/09/2026 | 29/08/2026 | 2026-02-09 | 319 | 236 | 83
ADIDAS | 0903152551-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 2026-09-09 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903152551 IS1413 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | IN RANGE |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 300 | 300 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-05-08 | 2026-03-09 | 300 | 300
ADIDAS | 0903152558-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 324 | 29/09/2026 | 324 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152558 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 324 |  | 324 |  |  | 19/09/2026 | 21/09/2026 |  |  | 324 |  | 324
ADIDAS | 0903152588-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 731 | 30/09/2026 | 731 | SI | SI26/06/2026 | G3D | PANTS | G3 | (29/07/2026) | ok | 21/09: ex-fty 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152588 HK7317 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | ESS SWTP |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 731 |  | 731 |  |  | 18/09/2026 | 21/09/2026 |  |  | 731 |  | 731
ADIDAS | 0903152648-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152648 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152660-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152660 HR8583 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 3300 |  | 3300 |  |  | 21/09/2026 | 26/09/2026 |  |  | 3300 |  | 3300
ADIDAS | 0903152687-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 2112 | 15/10/2026 | 2112 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152687 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 20/10/2026 | 26/10/2026 |  |  | 2112 |  | 2112 |  |  | 16/10/2026 | 22/10/2026 |  |  | 2112 |  | 2112
ADIDAS | 0903152692-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3D | PANTS | G3 | (29/07/2026) | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152692 HK7317 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 2860 |  | 2860 |  |  | 21/09/2026 | 26/09/2026 |  |  | 2860 |  | 2860
ADIDAS | 0903152712-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 300 | 2026-07-10 | 300 | AN | AN26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152712 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152716-1 HK7319 | BLACK | 90D | F2225M403 | 1439 | 30/09/2026 | 1439 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 26/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903152716 HK7319 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 1439 |  | 1439 |  |  | 21/09/2026 | 24/09/2026 |  |  | 1439 |  | 1439
ADIDAS | 0903152733-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152733 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152759-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152759 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 330 |  | 330 |  |  | 2026-05-10 | 2026-06-10 |  |  | 330 |  | 330
ADIDAS | 0903152773-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152773 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903152781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152781 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903152787-1 GK9270 | MEDIUM GREY HEATHER | 45D | S211CSIM117FLRO | 600 | 31/08/2026 | 600 | SA | SA26/06/2026 | G3I | PANTS | G3 |  |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903152787 GK9270 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | M 3S FL O PT |  | SS27 | 27/07/2026 | 30/07/2026 | 27/07/2026 | 28/07/2026 | 600 | 600 |  |  |  | 22/07/2026 | 27/07/2026 | 25/07/2026 | 27/07/2026 | 600 | 600
ADIDAS | 0903152816-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 1750 | 26/08/2026 | 1750 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/08: ex-fty 516318 | HT SUB PROCESS_V1 | 0903152816 HU1551 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | IN RANGE |  | SS27 | 2026-06-08 | 26/08/2026 | 2026-06-08 | 20/08/2026 | 1750 | 1750 |  |  |  | 2026-04-08 | 21/08/2026 | 2026-03-08 | 2026-08-08 | 1750 | 1750 |  |  |  | 2026-03-08 | 20/08/2026 | 31/07/2026 | 2026-07-08 | 1750 | 1750
ADIDAS | 0903152843-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 750 | 30/09/2026 | 750 | AT | AT26/06/2026 | G3I | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | HT SUB PROCESS_V1 | 0903152843 HU1551 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | IN RANGE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 750 |  | 750 |  |  | 17/09/2026 | 18/09/2026 | 26/08/2026 | 2026-04-09 | 750 | 739 | 11 |  |  | 16/09/2026 | 17/09/2026 | 24/08/2026 | 2026-04-09 | 750 | 739 | 11
ADIDAS | 0903152870-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903152870 HR6286 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | U FI LOGO PT |  | SS27 | 28/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 1051 | 1051 |  |  |  | 24/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 1051 | 1051
ADIDAS | 0903152901-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | PRINT L3 SUB PROCESS_V3 | 0903152901 HR6286 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | U FI LOGO PT |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0903152957-1 GK9269 | LEGEND INK F17 | 45D | S211CSIM117FLRO | 599 | 31/08/2026 | 599 | SA | SA26/06/2026 | G3I | PANTS | G3 | (29/07/2026(4)) |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903152957 GK9269 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | M 3S FL O PT |  | SS27 | 27/07/2026 | 30/07/2026 | 29/07/2026 | 29/07/2026 | 599 | 599 |  |  |  | 22/07/2026 | 27/07/2026 | 28/07/2026 | 29/07/2026 | 599 | 599
ADIDAS | 0903152983-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903152983 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | PL TEE |  | SS27 | 25/09/2026 | 2026-01-10 |  |  | 4543 |  | 4543 |  |  | 22/09/2026 | 28/09/2026 | 2026-12-09 | 14/09/2026 | 4543 | 1691 | 2852 |  | 804
ADIDAS | 0903153088-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 389 | 30/09/2026 | 389 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153088 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 389 |  | 389 |  |  | 2026-01-10 | 2026-02-10 |  |  | 389 |  | 389
ADIDAS | 0903153111-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 550 | 30/09/2026 | 550 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | ok | 23/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 28-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153111 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 550 |  | 550 |  |  | 24/09/2026 | 26/09/2026 | 28/08/2026 | 2026-08-09 | 550 | 538 | 12
ADIDAS | 0903153147-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153147 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 540 |  | 540 |  |  | 24/09/2026 | 25/09/2026 | 2026-01-08 | 2026-03-09 | 540 | 540
ADIDAS | 0903153178-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 576 | 30/09/2026 | 576 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153178 JE6414 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 576 |  | 576 |  |  | 2026-11-09 | 14/09/2026 | 2026-01-08 | 31/08/2026 | 576 | 555 | 21
ADIDAS | 0903153208-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 414 | 30/09/2026 | 414 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153208 LC6339 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 414 |  | 414 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-09-09 | 414 | 405 | 9
ADIDAS | 0903153249-1 LC6341 | BLACK | 90D | S27GMGFX130 | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153249 LC6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 468 |  | 468 |  |  | 18/09/2026 | 18/09/2026 | 2026-09-09 | 14/09/2026 | 468 | 386 | 82
ADIDAS | 0903153273-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153273 JE0052 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 308 |  | 308 |  |  | 15/09/2026 | 17/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153303-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153303 JE6338 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 468 |  | 468 |  |  | 17/09/2026 | 18/09/2026 |  |  | 468 |  | 468
ADIDAS | 0903153333-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 504 | 30/09/2026 | 504 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153333 JE6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 30/09/2026 |  |  | 504 |  | 504 |  |  | 23/09/2026 | 26/09/2026 |  |  | 504 |  | 504
ADIDAS | 0903153362-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 378 | 23/09/2026 | 378 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153362 JD5302 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 378 | 378 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 378 | 378
ADIDAS | 0903153392-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153392 JE0055 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-01-10 | W 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 308 |  | 308 |  |  | 28/09/2026 | 29/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153425 JD1877 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 540 |  | 540 |  |  | 15/09/2026 | 17/09/2026 |  |  | 540 |  | 540
ADIDAS | 0903153431-1 KC4947 | BLACK | 105D | S2608WR0216 | 1524 | 15/10/2026 | 1524 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 823016 | PAD+HT SUB PROCESS_V3 | 0903153431 KC4947 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 23/10/2026 | adi365 Astro W |  | SS27-TRAX | 23/10/2026 | 28/10/2026 |  |  | 1524 |  | 1524 |  |  | 20/10/2026 | 24/10/2026 |  |  | 1524 |  | 1524 |  |  | 19/10/2026 | 23/10/2026 |  |  | 1524 |  | 1524
ADIDAS | 0903153447-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153447 KA5089 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 2026-04-09 | 2026-12-09 | 266 | 266 |  |  | 2
ADIDAS | 0903153486-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153486 KA5090 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 26/08/2026 | 2026-12-09 | 266 | 266 |  |  | 2
ADIDAS | 0903153557-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 17 | 15/10/2026 | 17 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153557 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 26/10/2026 | 27/10/2026 |  |  | 17 |  | 17 |  |  | 22/10/2026 | 23/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903153563-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 844 | 2026-12-09 | 844 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 688010 | HT+PAD SUB PROCESS_V3 | 0903153563 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 844 | 844 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 844 | 844 |  |  |  | 28/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 844 | 844
ADIDAS | 0903153653-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 780 | 30/09/2026 | 780 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153653 JW7178 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | W 3S FT OH PT |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 780 |  | 780 |  |  | 2026-07-10 | 2026-08-10 | 2026-12-09 | 2026-12-09 | 780 | 698 | 82 |  | 698
ADIDAS | 0903153676-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153676 JW7177 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 840 |  | 840 |  |  | 18/09/2026 | 19/09/2026 | 31/08/2026 | 2026-09-09 | 840 | 798 | 42
ADIDAS | 0903153692-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903153692 KC8152 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903153702-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153702 JW7178 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | W 3S FT OH PT |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 1431 |  | 1431 |  |  | 2026-10-10 | 2026-12-10 | 2026-01-09 | 2026-02-09 | 1431 | 1427 | 4
ADIDAS | 0903153713-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 207 | 2026-05-09 | 207 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 04/09: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153713 IN1172 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 207 | 207 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 23/07/2026 | 207 | 207 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 23/07/2026 | 207 | 207
ADIDAS | 0903153722-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 355 | 15/10/2026 | 355 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153722 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 355 |  | 355 |  |  | 21/10/2026 | 22/10/2026 |  |  | 355 |  | 355 |  |  | 15/10/2026 | 16/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903153754-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 201 | 2026-09-09 | 201 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153754 IN1157 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-04-09 | 201 | 201 |  |  |  | 27/08/2026 | 31/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201 |  |  |  | 26/08/2026 | 29/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201
ADIDAS | 0903153757-1 KA2965 | OFF WHITE | 60D | S26KLKGFX011-MTF | 1200 | 26/08/2026 | 1200 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 516204 | PRINT L2+PAD SUB PROCESS_V3 | 0903153757 KA2965 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/07/2026 | LK TIRONS T |  | SS27 | 29/07/2026 | 21/08/2026 | 29/07/2026 | 20/08/2026 | 1200 | 1200 |  |  |  | 24/07/2026 | 18/08/2026 | 25/07/2026 | 20/08/2026 | 1200 | 1200
ADIDAS | 0903153806-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 |  | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903153806 JP1528 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/07/2026 | M L G ENG TEE |  | SS27 | 22/07/2026 | 30/07/2026 | 23/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 17/07/2026 | 27/07/2026 | 21/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903153843-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 480 | 30/09/2026 | 480 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903153843 KD3911 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | RELEASED |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 480 |  | 480 |  |  | 2026-12-09 | 14/09/2026 | 31/08/2026 | 2026-01-09 | 480 | 405 | 75
ADIDAS | 0903153852-1 KE6899 | BLACK | 105D | S2608WR0601B | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903153852 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 300 |  | 300 |  |  | 2026-02-11 | 2026-03-11 |  |  | 300 |  | 300 |  |  | 31/10/2026 | 2026-02-11 |  |  | 300 |  | 300
ADIDAS | 0903153861-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 906 | 30/09/2026 | 906 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153861 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 906 |  | 906 |  |  | 24/09/2026 | 26/09/2026 | 29/08/2026 | 2026-03-09 | 906 | 360 | 546
ADIDAS | 0903153888-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 364 | 30/09/2026 | 364 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153888 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 364 |  | 364 |  |  | 22/09/2026 | 24/09/2026 | 31/08/2026 | 2026-03-09 | 364 | 255 | 109
ADIDAS | 0903153890-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 1504 | 15/10/2026 | 1504 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153890 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 29/10/2026 | 31/10/2026 |  |  | 1504 |  | 1504 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1504 |  | 1504 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1504 |  | 1504
ADIDAS | 0903153893-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 481 | 15/10/2026 | 481 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 650010 | PAD+HT SUB PROCESS_V3 | 0903153893 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 15/10/2026 | 19/10/2026 |  |  | 481 |  | 481 |  |  | 2026-12-10 | 15/10/2026 |  |  | 481 |  | 481 |  |  | 2026-10-10 | 14/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903153906-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153906 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S FT QZ HD |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 399 |  | 399 |  |  | 2026-12-09 | 2026-12-09 |  |  | 399 |  | 399
ADIDAS | 0903153934-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 |  | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903153934 JP1528 | 28/07/2026 | KAHATEX CIJERAH | SPAIN | SEA | 24/07/2026 | M L G ENG TEE |  | SS27 | 24/07/2026 | 30/07/2026 | 24/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 21/07/2026 | 27/07/2026 | 22/07/2026 | 28/07/2026 | 1321 | 1321
ADIDAS | 0903153996-1 H42002 | LEGEND INK F17/WHITE | 45D | F213CSIM109FL | 899 | 31/08/2026 | 899 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903153996 H42002 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/07/2026 | M FEELCOZY SWT |  | SS27 | 17/07/2026 | 23/07/2026 | 20/07/2026 | 22/07/2026 | 899 | 899 |  |  |  | 14/07/2026 | 20/07/2026 | 16/07/2026 | 20/07/2026 | 899 | 899
ADIDAS | 0903154027-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 23/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154027 JE0052 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 400 |  | 400 |  |  | 15/09/2026 | 17/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903154028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 393 | 30/09/2026 | 393 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154028 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 393 |  | 393 |  |  | 26/09/2026 | 28/09/2026 | 26/08/2026 | 2026-12-09 | 393 | 324 | 69 |  | 3
ADIDAS | 0903154066-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 1951 | 15/10/2026 | 1951 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903154066 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 26/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 26/10/2026 | 29/10/2026 |  |  | 1951 |  | 1951 |  |  | 22/10/2026 | 26/10/2026 |  |  | 1951 |  | 1951 |  |  | 16/10/2026 | 20/10/2026 |  |  | 1951 |  | 1951
ADIDAS | 0903154068-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903154068 JP1527 | 28/07/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/07/2026 | M L G ENG TEE |  | SS27 | 28/07/2026 | 30/07/2026 | 29/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 23/07/2026 | 27/07/2026 | 24/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903154077-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154077 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435 |  |  | 2026-06-10 | 2026-08-10 |  |  | 435 |  | 435
ADIDAS | 0903154087-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 510 | 15/10/2026 | 510 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154087 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 510 |  | 510 |  |  | 2026-08-10 | 2026-09-10 |  |  | 510 |  | 510
ADIDAS | 0903154094-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903154094 JP1527 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | M L G ENG TEE |  | SS27 | 28/07/2026 | 30/07/2026 | 27/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 23/07/2026 | 27/07/2026 | 23/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903154119-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154119 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 19/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903154124-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 533 | 23/09/2026 | 533 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154124 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 533 | 381 | 152 |  | 199 | 2026-09-09 | 2026-11-09 | 2026-11-09 | 13/09/2026 | 533 | 516 | 17
ADIDAS | 0903154136-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154136 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | W 3S FT OH PT |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 399 |  | 399 |  |  | 2026-07-10 | 2026-08-10 | 2026-01-09 | 2026-01-09 | 399 | 351 | 48
ADIDAS | 0903154672-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154672 JE0055 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 2026-02-10 | W 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903154711-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 1265 | 30/09/2026 | 1265 | AN | AN26/06/2026 | G3K | SHORTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154711 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 1265 |  | 1265 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1265 |  | 1265
ADIDAS | 0903154744-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA26/06/2026 | G1G,G1I,G1Q,G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154744 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | LFC 3 F JSY SE |  | SS27-FJ | 31/08/2026 | 14/09/2026 | 31/08/2026 | 14/09/2026 | 15000 | 13829 | 1171 |  | 822 | 27/08/2026 | 2026-10-09 | 21/08/2026 | 14/09/2026 | 15000 | 14499 | 501 |  | 1208
ADIDAS | 0903154788-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 2110 | 2026-12-09 | 2110 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 12/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154788 LE8201 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 2026-12-09 | 2026-07-09 | 2026-12-09 | 2110 | 2110 |  |  | 483 | 2026-02-09 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 2110 | 2047 | 63 |  | 63
ADIDAS | 0903154833-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 6345 | 15/09/2026 | 6345 | SA | SA26/06/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154833 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-08-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 6345 | 5743 | 602 |  | 1097 | 2026-04-09 | 2026-10-09 | 2026-04-09 | 13/09/2026 | 6345 | 6126 | 219 |  | 301
ADIDAS | 0903154839-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 924 | 15/10/2026 | 924 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903154839 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 924 |  | 924 |  |  | 20/10/2026 | 21/10/2026 |  |  | 924 |  | 924 |  |  | 14/10/2026 | 15/10/2026 |  |  | 924 |  | 924
ADIDAS | 0903154867-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3701 | 15/09/2026 | 3701 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154867 LE8208 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 3701 | 3195 | 506 |  | 250 | 2026-05-09 | 2026-10-09 | 2026-07-09 | 13/09/2026 | 3701 | 3626 | 75 |  | 197
ADIDAS | 0903154898-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 760 | 15/09/2026 | 760 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154898 LE8210 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 14/09/2026 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 14/09/2026 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 760 | 40 | 720 |  |  | 2026-10-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 760 | 702 | 58 |  | 662
ADIDAS | 0903154925-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 200 | 2026-12-09 | 200 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903154925 LE8193 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-02-09 | 2026-10-09 | 200 | 200 |  |  |  | 27/08/2026 | 2026-07-09 | 21/08/2026 | 2026-10-09 | 200 | 200
ADIDAS | 0903154950-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 1096 | 2026-12-09 | 1096 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903154950 LE8193 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1096 | 1096 |  |  |  | 27/08/2026 | 2026-07-09 | 20/08/2026 | 2026-10-09 | 1096 | 1096
ADIDAS | 0903154953-1 KA0235 | BLACK | 90D | S2608WR0901 | 1036 | 2026-07-10 | 1036 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 28-Aug. 516276 | PAD+HT SUB PROCESS_V3 | 0903154953 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-02-10 | 2026-06-10 |  |  | 1036 |  | 1036 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1036 |  | 1036 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1036 |  | 1036
ADIDAS | 0903154980-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 14142 | 2026-12-09 | 14142 | SA | SA26/06/2026 | G1I,G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 12/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903154980 LE8193 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-12-09 | 2026-02-09 | 2026-12-09 | 14142 | 14142 |  |  | 331 | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-11-09 | 14142 | 14142
ADIDAS | 0903155196-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G3E | PANTS | G3 | ok | ok | 834012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155196 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 14/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903155361-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 992 | 28/08/2026 | 992 | AN | AN26/06/2026 | G3B,G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155361 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 28/08/2026 | 992 | 992 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-06-08 | 2026-05-09 | 992 | 992
ADIDAS | 0903155389-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 380 | 15/09/2026 | 380 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155389 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-10-09 | 380 | 380 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 380 | 380
ADIDAS | 0903155457-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1114 | 30/09/2026 | 1114 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 25/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 678002 | PRINT L2+HT SUB PROCESS_V3 | 0903155457 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 1114 |  | 1114 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1114 |  | 1114 |  |  | 16/09/2026 | 17/09/2026 |  |  | 1114 |  | 1114
ADIDAS | 0903155494-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 14 | 15/10/2026 | 14 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155494 LE8187 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 24/10/2026 | M SL WV TP PT BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 14 |  | 14 |  |  | 21/10/2026 | 22/10/2026 |  |  | 14 |  | 14
ADIDAS | 0903155496-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 407 | 30/09/2026 | 407 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155496 LG9660 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 407 |  | 407 |  |  | 2026-11-09 | 2026-12-09 |  |  | 407 |  | 407
ADIDAS | 0903155525-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 24 | 15/10/2026 | 24 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155525 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 26/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 24 |  | 24 |  |  | 22/10/2026 | 23/10/2026 |  |  | 24 |  | 24
ADIDAS | 0903155581-1 KB5960 | WHITE | 120D | S2608MR0900A | 3741 | 29/09/2026 | 3741 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155581 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee M |  | SS27-TI | 16/09/2026 | 21/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-12-09 | 17/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-10-09 | 15/09/2026 |  |  | 3741 |  | 3741
ADIDAS | 0903155606-1 KB5965 | BLACK | 120D | S2608MR0900A | 989 | 29/09/2026 | 989 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155606 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | Run Ess Tee M |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 989 |  | 989 |  |  | 21/09/2026 | 21/09/2026 |  |  | 989 |  | 989 |  |  | 18/09/2026 | 18/09/2026 |  |  | 989 |  | 989
ADIDAS | 0903155643-1 KB5965 | BLACK | 120D | S2608MR0900A | 5978 | 29/09/2026 | 5978 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155643 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | Run Ess Tee M |  | SS27-TI | 18/09/2026 | 24/09/2026 |  |  | 5978 |  | 5978 |  |  | 15/09/2026 | 21/09/2026 |  |  | 5978 |  | 5978 |  |  | 2026-12-09 | 18/09/2026 |  |  | 5978 |  | 5978
ADIDAS | 0903155916-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155916 KW9039 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 29/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 29/09/2026 | 30/09/2026 |  |  | 224 |  | 224 |  |  | 25/09/2026 | 26/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903155960-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903155960 JD1877 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 19/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903155978-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 1218 | 2026-09-09 | 1218 | ID | ID26/06/2026 | G2S | SHORTS | G2 | ok | ok | 08/09: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155978 KY7184 | 2026-11-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-09 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 2026-01-09 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1218 | 1218 |  |  |  | 28/08/2026 | 2026-04-09 | 31/08/2026 | 2026-08-09 | 1218 | 1218
ADIDAS | 0903155986-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903155986 KY3734 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 29/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903156009-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903156009 JE6341 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903156065-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 344 | 30/09/2026 | 344 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO SUB PROCESS_V1 | 0903156065 JD1881 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 2026-06-10 | M 3S FT TC PT |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 344 |  | 344 |  |  | 2026-02-10 | 2026-02-10 |  |  | 344 |  | 344
ADIDAS | 0903156157-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 401 | 30/09/2026 | 401 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156157 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 401 |  | 401 |  |  | 18/09/2026 | 19/09/2026 | 14/08/2026 | 2026-08-09 | 401 | 394 | 7
ADIDAS | 0903156162-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156162 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435 |  |  | 2026-06-10 | 2026-08-10 |  |  | 435 |  | 435
ADIDAS | 0903156174-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 938 | 2026-07-10 | 938 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156174 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 938 |  | 938 |  |  | 2026-03-10 | 2026-05-10 |  |  | 938 |  | 938
ADIDAS | 0903156181-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 375 | 15/10/2026 | 375 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156181 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 375 |  | 375 |  |  | 2026-08-10 | 2026-09-10 |  |  | 375 |  | 375
ADIDAS | 0903156184-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 23/09/2026 | 610 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156184 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 610 |  | 610 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-12-09 | 610 | 610 |  |  | 1
ADIDAS | 0903156205-1 H12226 | DARK GREY HEATHER/BLACK | 45D | F213CSIM109FL | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903156205 H12226 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/07/2026 | M FEELCOZY SWT |  | SS27 | 21/07/2026 | 23/07/2026 | 21/07/2026 | 23/07/2026 | 450 | 450 |  |  |  | 16/07/2026 | 20/07/2026 | 20/07/2026 | 23/07/2026 | 450 | 450
ADIDAS | 0903156224-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1251 | 2026-07-10 | 1251 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156224 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 1251 |  | 1251 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1251 |  | 1251
ADIDAS | 0903156225-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 360 | 15/10/2026 | 360 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156225 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 360 |  | 360 |  |  | 2026-09-10 | 2026-10-10 |  |  | 360 |  | 360
ADIDAS | 0903156247-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156247 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 345 |  | 345 |  |  | 2026-09-10 | 2026-10-10 |  |  | 345 |  | 345
ADIDAS | 0903156271-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 1398 | 26/08/2026 | 1398 | SA | SA26/06/2026 | G2F | PANTS | G2 | (29/07/2026) | ok | 24/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903156271 H57046 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | M 3S FL TC PT |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 1398 | 1398 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-10-08 | 15/08/2026 | 1398 | 1398
ADIDAS | 0903156282-1 KA4331 | BLACK | 90D | S2608MR0902 | 399 | 2026-07-10 | 399 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903156282 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 22/09/2026 | 24/09/2026 |  |  | 399 |  | 399 |  |  | 21/09/2026 | 23/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903156297-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156297 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 345 |  | 345 |  |  | 2026-10-10 | 13/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156313-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 525 | 15/10/2026 | 525 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156313 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 525 |  | 525 |  |  | 2026-10-10 | 13/10/2026 |  |  | 525 |  | 525
ADIDAS | 0903156320-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1051 | 30/09/2026 | 1051 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156320 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1051 |  | 1051 |  |  | 2026-01-10 | 2026-02-10 | 2026-11-09 | 2026-12-09 | 1051 | 822 | 229 |  | 229
ADIDAS | 0903156341-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 624 | 30/09/2026 | 624 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156341 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 624 |  | 624 |  |  | 29/09/2026 | 2026-01-10 | 2026-10-09 | 2026-12-09 | 624 | 623 | 1 |  | 207
ADIDAS | 0903156375-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 349 | 30/09/2026 | 349 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156375 KW2924 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 349 |  | 349 |  |  | 17/09/2026 | 18/09/2026 |  |  | 349 |  | 349
ADIDAS | 0903156407-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 741 | 30/09/2026 | 741 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156407 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 16/09/2026 | 17/09/2026 |  |  | 741 |  | 741 |  |  | 2026-12-09 | 14/09/2026 |  |  | 741 |  | 741
ADIDAS | 0903156431-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 1249 | 30/09/2026 | 1249 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156431 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 17/09/2026 | 18/09/2026 |  |  | 1249 |  | 1249 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1249 |  | 1249
ADIDAS | 0903156487-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156487 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 110 |  | 110 |  |  | 30/09/2026 | 30/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903156511-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903156511 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 100 |  | 100 |  |  | 24/09/2026 | 25/09/2026 | 2026-01-09 | 2026-01-09 | 100 | 100
ADIDAS | 0903156518-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 122 | 2026-07-10 | 122 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156518 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 122 |  | 122 |  |  | 24/09/2026 | 24/09/2026 |  |  | 122 |  | 122
ADIDAS | 0903156528-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 451 | 26/08/2026 | 451 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 1st Art (TC 10 pcs) 659018 | HT SUB PROCESS_V1 | 0903156528 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 14/08/2026 | 13/08/2026 | 20/08/2026 | 451 | 451 |  |  |  | 2026-11-08 | 2026-12-08 | 28/07/2026 | 29/07/2026 | 451 | 451 |  |  |  | 2026-10-08 | 2026-11-08 | 28/07/2026 | 29/07/2026 | 451 | 451
ADIDAS | 0903156531-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903156531 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903156547-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 800 | 15/10/2026 | 800 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903156547 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 800 |  | 800 |  |  | 22/10/2026 | 23/10/2026 |  |  | 800 |  | 800 |  |  | 21/10/2026 | 22/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903156570-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 500 | 26/08/2026 | 500 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903156570 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 26/08/2026 | 13/08/2026 | 20/08/2026 | 500 | 500 |  |  |  | 2026-11-08 | 21/08/2026 | 28/07/2026 | 30/07/2026 | 500 | 500 |  |  |  | 2026-10-08 | 20/08/2026 | 28/07/2026 | 30/07/2026 | 500 | 500
ADIDAS | 0903156595-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 150 | 30/09/2026 | 150 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156595 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | W 3S FT OH PT |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 150 |  | 150 |  |  | 2026-07-10 | 2026-07-10 | 20/08/2026 | 28/08/2026 | 150 | 140 | 10
ADIDAS | 0903156613-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 540 | 15/10/2026 | 540 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Mexico). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903156613 KE6716 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 15/10/2026 | 19/10/2026 |  |  | 540 |  | 540 |  |  | 2026-12-10 | 15/10/2026 |  |  | 540 |  | 540 |  |  | 2026-10-10 | 14/10/2026 |  |  | 540 |  | 540
ADIDAS | 0903156885-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 416 | 30/09/2026 | 416 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Airowes). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156885 KV7863 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-01-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 416 |  | 416 |  |  | 28/09/2026 | 29/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903157062-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 124 | 15/10/2026 | 124 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157062 KU8797 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 124 |  | 124 |  |  | 2026-01-10 | 2026-01-10 |  |  | 124 |  | 124
ADIDAS | 0903157093-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 148 | 15/10/2026 | 148 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157093 KW8934 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 148 |  | 148 |  |  | 30/09/2026 | 30/09/2026 |  |  | 148 |  | 148
ADIDAS | 0903157098-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903157098 KX0126 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 15/10/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 128 |  | 128 |  |  | 2026-12-10 | 2026-12-10 | 2026-10-08 | 2026-11-08 | 128 | 84 | 44
ADIDAS | 0903157127-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 273 | 30/09/2026 | 273 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (04/08/2026) | 29/09: ex-fty (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157127 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 18/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 273 |  | 273 |  |  | 15/09/2026 | 15/09/2026 |  |  | 273 |  | 273
ADIDAS | 0903157647-1 KE8424 | BLACK | 120D | S2608MR0906A | 890 | 2026-02-10 | 890 | SI | SI26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903157647 KE8424 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 890 |  | 890 |  |  | 29/09/2026 | 30/09/2026 |  |  | 890 |  | 890 |  |  | 26/09/2026 | 28/09/2026 |  |  | 890 |  | 890
ADIDAS | 0903157667-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 1500 | 2026-12-09 | 1500 | SA | SA26/06/2026 | G2Q,G2S,G2T | SHORTS | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 678002 | PRINT L1 SUB PROCESS_V3 | 0903157667 JC9346 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-09 | M LIN SJ SHO |  | SS27 | 2026-02-09 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1500 | 1500 |  |  |  | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-10-09 | 1500 | 1500
ADIDAS | 0903157692-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1000 | 26/08/2026 | 1000 | SA | SA26/06/2026 | G2S | SHORTS | G2 | (08/08/2026) | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157692 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 1000 | 1000 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-01-08 | 2026-08-08 | 1000 | 1000
ADIDAS | 0903157724-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 800 | 26/08/2026 | 800 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157724 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/08/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 800 | 800 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-01-08 | 19/08/2026 | 800 | 800
ADIDAS | 0903157733-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 198 | 15/10/2026 | 198 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903157733 KD0738 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 198 |  | 198 |  |  | 21/10/2026 | 22/10/2026 |  |  | 198 |  | 198 |  |  | 15/10/2026 | 16/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903157738-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 306 | 23/09/2026 | 306 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157738 JD5302 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 306 | 306 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 27/08/2026 | 306 | 306
ADIDAS | 0903157745-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | SHORTS | G3 | ok | ok | 23/09: ex-fty. T2 Gistex, PI Date 10-Aug, actual receives 22-Aug. 1st Art (TC 10 pcs) 678002 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0903157745 JE9016 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-10 | M LIN CHELSEA |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1500 |  | 1500 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1500 |  | 1500
ADIDAS | 0903157768-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157768 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-10-10 | 13/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903157773-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 2500 | 26/08/2026 | 2500 | AN | AN26/06/2026 | G2E | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | PRINT L1 SUB PROCESS_V3 | 0903157773 JG8639 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W LIN FT SHO |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 2500 | 2500 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-12-08 | 31/08/2026 | 2500 | 2500
ADIDAS | 0903157804-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 118 | 30/09/2026 | 118 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903157804 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 17/09/2026 | 22/09/2026 |  |  | 118 |  | 118 |  |  | 14/09/2026 | 18/09/2026 | 31/08/2026 | 2026-05-09 | 118 | 104 | 14
ADIDAS | 0903157810-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157810 JE0052 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 22/09/2026 | W 3S FT FZ HD |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 19/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903157899-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 108 | 15/10/2026 | 108 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | (Airowes). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157899 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/10/2026 | M SL WV TP PT BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 108 |  | 108 |  |  | 21/10/2026 | 22/10/2026 |  |  | 108 |  | 108
ADIDAS | 0903157953-1 KE8424 | BLACK | 120D | S2608MR0906A | 489 | 29/09/2026 | 489 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903157953 KE8424 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | Run Ess LS M BLACK |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 489 |  | 489 |  |  | 2026-11-09 | 2026-12-09 |  |  | 489 |  | 489 |  |  | 2026-09-09 | 2026-10-09 |  |  | 489 |  | 489
ADIDAS | 0903158261-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G2M | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903158261 JG8639 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | W LIN FT SHO |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-12-09 | 2026-12-09 | 2026-03-08 | 24/08/2026 | 300 | 300
ADIDAS | 0903158265-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 11222 | 30/09/2026 | 11222 | AT | AT26/06/2026 | G2C | T-SHIRT | G2 | ok | (30/07/2026) | 25/09: ex-fty 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903158265 KA5089 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/09/2026 | MINI EMB T |  | SS27 | 14/09/2026 | 23/09/2026 |  |  | 11222 |  | 11222 |  |  | 2026-10-09 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 11222 | 123 | 11099 |  |  | 2026-08-09 | 17/09/2026 | 2026-07-09 | 14/09/2026 | 11222 | 142 | 11080
ADIDAS | 0903158297-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 482 | 15/10/2026 | 482 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158297 JE0052 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-11 | W 3S FT FZ HD |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 482 |  | 482 |  |  | 30/10/2026 | 31/10/2026 |  |  | 482 |  | 482
ADIDAS | 0903158492-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 332 | 15/10/2026 | 332 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158492 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | M SL WV TP PT BLACK |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 332 |  | 332 |  |  | 22/10/2026 | 23/10/2026 |  |  | 332 |  | 332
ADIDAS | 0903158495-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158495 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-10-10 | 30/10/2026 |  |  | 101 |  | 101 |  |  | 2026-07-10 | 27/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903158663-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 107 | 2026-07-10 | 107 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158663 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 107 |  | 107 |  |  | 24/09/2026 | 25/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903158691-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 118 | 2026-07-10 | 118 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158691 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 25/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 118 |  | 118 |  |  | 22/09/2026 | 23/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903158714-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 300 | 29/09/2026 | 300 | AN | AN26/06/2026 | G2R | SHORTS | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158714 LG9660 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 |  |  | 300 |  | 300
ADIDAS | 0903158739-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 332 | 15/10/2026 | 332 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158739 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 332 |  | 332 |  |  | 2026-12-10 | 13/10/2026 |  |  | 332 |  | 332
ADIDAS | 0903158761-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 239 | 23/09/2026 | 239 | SA | SA26/06/2026 | G3C | PANTS | G3 | (08/08/2026(13)) |  | 18/09: ex-fty 806020 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158761 JW7177 | 2026-10-09 | KAHATEX CIJERAH | HONGKONG | SEA | 28/07/2026 | W 3S FT OH PT |  | SS27 | 28/07/2026 | 2026-04-08 | 29/07/2026 | 29/07/2026 | 239 | 239 |  |  |  | 23/07/2026 | 30/07/2026 | 28/07/2026 | 29/07/2026 | 239 | 239
ADIDAS | 0903158798-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 229 | 15/10/2026 | 229 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158798 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 229 |  | 229 |  |  | 2026-12-10 | 13/10/2026 |  |  | 229 |  | 229
ADIDAS | 0903158825-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 451 | 15/10/2026 | 451 | SA | SA26/06/2026 | G3B | PANTS | G3 | (28/08/2026) | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158825 LE8181 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 451 |  | 451 |  |  | 13/10/2026 | 14/10/2026 |  |  | 451 |  | 451
ADIDAS | 0903158829-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | (17/07/2026) | 25/09: ex-fty 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158829 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | DICE TEE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 415 |  | 415 |  |  | 14/09/2026 | 15/09/2026 |  |  | 415 |  | 415 |  |  | 2026-11-09 | 2026-12-09 |  |  | 415 |  | 415
ADIDAS | 0903158907-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 245 | 30/09/2026 | 245 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158907 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | PDX HBR TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 245 |  | 245 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-08 | 2026-11-08 | 245 | 244 | 1
ADIDAS | 0903158935-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158935 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | PIZZA TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 415 |  | 415 |  |  | 26/09/2026 | 28/09/2026 | 2026-07-08 | 19/08/2026 | 415 | 414 | 1
ADIDAS | 0903158955-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 187 | 30/09/2026 | 187 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158955 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | PDX HBR TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 187 |  | 187 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-08 | 15/08/2026 | 187 | 187
ADIDAS | 0903158980-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 1203 | 30/09/2026 | 1203 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158980 KS2152 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/09/2026 | LA PALMS TEE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 1203 |  | 1203 |  |  | 2026-12-09 | 14/09/2026 | 2026-08-09 | 2026-12-09 | 1203 | 1020 | 183 |  | 8
ADIDAS | 0903159040-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 862 | 30/09/2026 | 862 | ID | ID26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159040 KR2006 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | SPORT GOODS T |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 862 |  | 862 |  |  | 15/09/2026 | 15/09/2026 | 2026-08-09 | 2026-11-09 | 862 | 838 | 24
ADIDAS | 0903159157-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159157 KW8932 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 30/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903159180-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 274 | 15/10/2026 | 274 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159180 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 274 |  | 274 |  |  | 2026-01-10 | 2026-02-10 |  |  | 274 |  | 274
ADIDAS | 0903159200-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 346 | 15/10/2026 | 346 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159200 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 346 |  | 346 |  |  | 2026-01-10 | 2026-01-10 |  |  | 346 |  | 346
ADIDAS | 0903159205-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159205 LC8884 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 128 |  | 128 |  |  | 2026-12-10 | 13/10/2026 | 2026-11-08 | 2026-11-08 | 128 | 126 | 2
ADIDAS | 0903159207-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 257 | 15/10/2026 | 257 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Airowes). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903159207 KA2571 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 28/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 257 |  | 257 |  |  | 24/10/2026 | 26/10/2026 |  |  | 257 |  | 257 |  |  | 19/10/2026 | 20/10/2026 |  |  | 257 |  | 257
ADIDAS | 0903159219-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 1058 | 26/08/2026 | 1058 | AN | AN26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159219 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 14/08/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 1058 | 1058 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-12-08 | 2026-05-09 | 1058 | 1058
ADIDAS | 0903159239-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 238 | 15/10/2026 | 238 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159239 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 238 |  | 238 |  |  | 2026-01-10 | 2026-02-10 |  |  | 238 |  | 238
ADIDAS | 0903159248-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 640 | 28/08/2026 | 640 | AN | AN26/06/2026 | G3A,G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159248 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-08 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-11-08 | 19/08/2026 | 2026-11-08 | 20/08/2026 | 640 | 640 |  |  |  | 2026-06-08 | 13/08/2026 | 2026-04-08 | 20/08/2026 | 640 | 640
ADIDAS | 0903159269-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 1861 | 28/08/2026 | 1861 | AN | AN26/06/2026 | G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159269 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 1861 | 1861 |  |  |  | 13/08/2026 | 20/08/2026 | 15/08/2026 | 24/08/2026 | 1861 | 1861
ADIDAS | 0903159282-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 132 | 15/10/2026 | 132 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159282 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 26/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 132 |  | 132 |  |  | 22/10/2026 | 23/10/2026 |  |  | 132 |  | 132
ADIDAS | 0903159299-1 KZ3229 | GREY FIVE F17/WHITE | 90D | S2754WESS703WV-MTF | 597 | 26/08/2026 | 597 | AN | AN26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, actual receives 28-May (PO 26022031). T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159299 KZ3229 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 13S WV BER SHO GREY FIVE F17/WHITE |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 597 | 597 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 21/08/2026 | 597 | 597
ADIDAS | 0903159308-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 102 | 15/10/2026 | 102 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (Cargoport). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159308 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 16/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 102 |  | 102 |  |  | 13/10/2026 | 14/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903159320-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 222 | 30/09/2026 | 222 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650036 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159320 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-01-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 222 |  | 222 |  |  | 28/09/2026 | 28/09/2026 | 28/08/2026 | 28/08/2026 | 222 | 221 | 1
ADIDAS | 0903159340-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 313 | 30/09/2026 | 313 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 838103 | PRINT L1 SUB PROCESS_V3 | 0903159340 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 19/09/2026 | 19/09/2026 |  |  | 313 |  | 313 |  |  | 16/09/2026 | 16/09/2026 |  |  | 313 |  | 313
ADIDAS | 0903159374-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 100 | 15/10/2026 | 100 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903159374 KW8932 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903159551-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159551 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-02-10 | 2026-02-09 | 2026-10-09 | 300 | 92 | 208
ADIDAS | 0903159571-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 2026-12-09 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159571 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 2026-05-09 | 29/08/2026 | 31/08/2026 | 522 | 522 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-08-09 | 522 | 522
ADIDAS | 0903159587-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 30/09/2026 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159587 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 522 | 215 | 307 |  |  | 27/08/2026 | 15/09/2026 | 27/08/2026 | 2026-09-09 | 522 | 518 | 4
ADIDAS | 0903159856-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 606 | 30/09/2026 | 606 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 630001 | PAD+HT SUB PROCESS_V3 | 0903159856 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 18/09/2026 | 19/09/2026 |  |  | 606 |  | 606 |  |  | 15/09/2026 | 16/09/2026 |  |  | 606 |  | 606 |  |  | 14/09/2026 | 15/09/2026 |  |  | 606 |  | 606
ADIDAS | 0903159964-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 607 | 15/10/2026 | 607 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903159964 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M SERENO 3S T BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 607 |  | 607 |  |  | 26/09/2026 | 28/09/2026 |  |  | 607 |  | 607 |  |  | 25/09/2026 | 26/09/2026 |  |  | 607 |  | 607
ADIDAS | 0903159994-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 328 | 15/10/2026 | 328 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159994 KX7716 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 26/09/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 26/09/2026 | 2026-01-10 |  |  | 328 |  | 328 |  |  | 23/09/2026 | 28/09/2026 |  |  | 328 |  | 328
ADIDAS | 0903160003-1 KA3530 | BLACK | 105D | S2650MTR402 | 237 | 15/10/2026 | 237 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903160003 KA3530 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | WE FR T BLACK |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 237 |  | 237 |  |  | 29/09/2026 | 29/09/2026 |  |  | 237 |  | 237 |  |  | 28/09/2026 | 28/09/2026 |  |  | 237 |  | 237
ADIDAS | 0903160021-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 328 | 15/10/2026 | 328 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160021 KX7715 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 22/09/2026 | 26/09/2026 |  |  | 328 |  | 328 |  |  | 18/09/2026 | 23/09/2026 |  |  | 328 |  | 328
ADIDAS | 0903160371-1 KA0246 | BLACK | 90D | S2608WR0902 | 1181 | 15/10/2026 | 1181 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516267 | PAD+HT SUB PROCESS_V3 | 0903160371 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 1181 |  | 1181 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1181 |  | 1181 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1181 |  | 1181
ADIDAS | 0903160415-1 KA0246 | BLACK | 90D | S2608WR0902 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516404 | PAD+HT SUB PROCESS_V3 | 0903160415 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 26/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903160834-1 LE8187 | BLACK | 105D | S2754MAS513 | 217 | 15/10/2026 | 217 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160834 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 24/10/2026 | M SL WV TP PT BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 217 |  | 217 |  |  | 21/10/2026 | 22/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903161081-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (KN GLT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903161081 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903161114-1 KS0802 | TECH INDIGO S20/WHITE | 105D | S2608WR0601B | 7 | 15/10/2026 | 7 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903161114 KS0802 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-11 | adi365 Short W TECH INDIGO S20/WHITE |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 7 |  | 7 |  |  | 2026-02-11 | 2026-03-11 |  |  | 7 |  | 7 |  |  | 31/10/2026 | 2026-02-11 |  |  | 7 |  | 7
ADIDAS | 0903161148-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 5352 | 15/10/2026 | 5352 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Libolon, PI Date 22-Jul. actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 29-Jul. T2 Formosa, PI Date 09-Jun, actual receives 22-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161148 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 28/10/2026 | 2026-05-11 |  |  | 5352 |  | 5352 |  |  | 24/10/2026 | 2026-02-11 |  |  | 5352 |  | 5352
ADIDAS | 0903161212-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 8768 | 30/09/2026 | 8768 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161212 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 26/09/2026 | 2026-08-10 |  |  | 8768 |  | 8768 |  |  | 23/09/2026 | 2026-05-10 |  |  | 8768 |  | 8768
ADIDAS | 0903161277-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 141 | 30/09/2026 | 141 | AN | AN26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 21/09: ex-fty 516342 | PRINT L3+PAD SUB PROCESS_V3 | 0903161277 LC8882 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | M ADI RETRO T BLACK |  | SS27 | 14/09/2026 | 14/09/2026 |  |  | 141 |  | 141 |  |  | 2026-10-09 | 2026-10-09 | 2026-11-08 | 13/08/2026 | 141 | 141
ADIDAS | 0903162196-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 313 | 23/09/2026 | 313 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 23/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162196 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 313 | 313 |  |  |  | 2026-05-09 | 2026-11-09 | 14/08/2026 | 31/08/2026 | 313 | 297 | 16
ADIDAS | 0903162215-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 846 | 30/09/2026 | 846 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162215 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 21/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 846 |  | 846 |  |  | 17/09/2026 | 18/09/2026 |  |  | 846 |  | 846
ADIDAS | 0903162243-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 321 | 15/10/2026 | 321 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162243 LE8188 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 20/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 321 |  | 321 |  |  | 16/10/2026 | 19/10/2026 |  |  | 321 |  | 321
ADIDAS | 0903162307-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162307 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-03-11 | 2026-04-11 |  |  | 153 |  | 153 |  |  | 30/10/2026 | 31/10/2026 |  |  | 153 |  | 153 |  |  | 29/10/2026 | 30/10/2026 |  |  | 153 |  | 153
ADIDAS | 0903162341-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 205 | 15/10/2026 | 205 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162341 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M SERENO 3S T BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 205 |  | 205 |  |  | 26/09/2026 | 28/09/2026 |  |  | 205 |  | 205 |  |  | 25/09/2026 | 26/09/2026 |  |  | 205 |  | 205
ADIDAS | 0903162369-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 1229 | 30/09/2026 | 1229 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162369 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1229 |  | 1229 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1229 |  | 1229
ADIDAS | 0903162420-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 100 | 15/10/2026 | 100 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162420 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M SERENO 3S T BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 26/09/2026 | 28/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 26/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903162500-1 LC6341 | BLACK | 90D | S27GMGFX130 | 246 | 30/09/2026 | 246 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 630001 | PRINT L3+PAD SUB PROCESS_V3 | 0903162500 LC6341 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 246 |  | 246 |  |  | 18/09/2026 | 18/09/2026 | 2026-09-09 | 2026-09-09 | 246 | 226 | 20
ADIDAS | 0903162572-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162572 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 153 |  | 153 |  |  | 21/09/2026 | 22/09/2026 |  |  | 153 |  | 153 |  |  | 19/09/2026 | 21/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903162593-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 624 | 15/10/2026 | 624 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162593 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-03-11 | 2026-04-11 |  |  | 624 |  | 624 |  |  | 30/10/2026 | 31/10/2026 |  |  | 624 |  | 624 |  |  | 29/10/2026 | 30/10/2026 |  |  | 624 |  | 624
ADIDAS | 0903162621-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 512 | 15/10/2026 | 512 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162621 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 512 |  | 512 |  |  | 21/09/2026 | 22/09/2026 |  |  | 512 |  | 512 |  |  | 19/09/2026 | 21/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903162642-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 195 | 30/09/2026 | 195 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 814006 | PRINT L1 SUB PROCESS_V3 | 0903162642 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 19/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 19/09/2026 | 19/09/2026 |  |  | 195 |  | 195 |  |  | 16/09/2026 | 16/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903163142-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 344 | 15/10/2026 | 344 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903163142 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 344 |  | 344 |  |  | 2026-01-10 | 2026-01-10 |  |  | 344 |  | 344
ADIDAS | 0903163156-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 8 | 15/10/2026 | 8 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163156 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 15/10/2026 | 19/10/2026 |  |  | 8 |  | 8 |  |  | 2026-12-10 | 15/10/2026 |  |  | 8 |  | 8 |  |  | 2026-10-10 | 14/10/2026 |  |  | 8 |  | 8
ADIDAS | 0903163494-1 KE6899 | BLACK | 105D | S2608WR0601B | 1139 | 15/10/2026 | 1139 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163494 KE6899 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-06-11 | 2026-10-11 |  |  | 1139 |  | 1139 |  |  | 2026-03-11 | 2026-06-11 |  |  | 1139 |  | 1139 |  |  | 2026-02-11 | 2026-05-11 |  |  | 1139 |  | 1139
ADIDAS | 0903163534-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 688 | 15/10/2026 | 688 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163534 KE6716 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 19/10/2026 | 21/10/2026 |  |  | 688 |  | 688 |  |  | 15/10/2026 | 17/10/2026 |  |  | 688 |  | 688 |  |  | 14/10/2026 | 16/10/2026 |  |  | 688 |  | 688
ADIDAS | 0903163589-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 336 | 30/09/2026 | 336 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric (KN GLT). T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 650010 | PRINT L2+HT SUB PROCESS_V3 | 0903163589 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 19/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 336 |  | 336 |  |  | 16/09/2026 | 17/09/2026 |  |  | 336 |  | 336 |  |  | 15/09/2026 | 16/09/2026 |  |  | 336 |  | 336
ADIDAS | 0903163782-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 1st Art (TC 10 pcs) 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903163782 JM1772 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903164418-1 KW5050 | MAROON | 90D | F2625M101 | 230 | 15/10/2026 | 230 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164418 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | ESS REG |  | SS27-STX | 14/10/2026 | 14/10/2026 |  |  | 230 |  | 230 |  |  | 2026-10-10 | 2026-10-10 |  |  | 230 |  | 230
ADIDAS | 0903164544-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 214 | 15/10/2026 | 214 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164544 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 214 |  | 214 |  |  | 2026-01-10 | 2026-01-10 |  |  | 214 |  | 214
ADIDAS | 0903164569-1 KW5050 | MAROON | 90D | F2625M101 | 170 | 2026-07-10 | 170 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164569 KW5050 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | ESS REG |  | SS27-STX | 2026-06-10 | 2026-06-10 |  |  | 170 |  | 170 |  |  | 2026-02-10 | 2026-02-10 |  |  | 170 |  | 170
ADIDAS | 0903164595-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 416 | 2026-07-10 | 416 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903164595 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 22/09/2026 | 23/09/2026 |  |  | 416 |  | 416 |  |  | 18/09/2026 | 19/09/2026 |  |  | 416 |  | 416 |  |  | 17/09/2026 | 18/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903164629-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 808 | 2026-07-10 | 808 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164629 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 808 |  | 808 |  |  | 24/09/2026 | 25/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903164697-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 133 | 2026-07-10 | 133 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164697 IN1172 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 133 | 133 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 133 | 133 |  |  |  | 2026-11-08 | 26/08/2026 | 15/07/2026 | 23/07/2026 | 133 | 133
ADIDAS | 0903164732-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 264 | 2026-07-10 | 264 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164732 IN1156 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 264 | 264 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 264 | 264 |  |  |  | 2026-11-08 | 26/08/2026 | 13/07/2026 | 27/07/2026 | 264 | 264
ADIDAS | 0903164830-1 KT4840 | ONIX | 90D | S2408MR1600 | 102 | 30/09/2026 | 102 | SA | SA26/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 830009 | HT SUB PROCESS_V1 | 0903164830 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 30/09/2026 |  |  | 102 |  | 102 |  |  | 25/09/2026 | 28/09/2026 |  |  | 102 |  | 102 |  |  | 24/09/2026 | 26/09/2026 |  |  | 102 |  | 102
ADIDAS | 0903164987-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 110 | 2026-07-10 | 110 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 800187 | EMBRO SUB PROCESS_V1 | 0903164987 KT7396 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 110 |  | 110 |  |  | 2026-01-10 | 2026-01-10 |  |  | 110 |  | 110
ADIDAS | 0903165005-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 135 | 15/10/2026 | 135 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165005 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 135 |  | 135 |  |  | 20/10/2026 | 21/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903165033-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 408 | 2026-07-10 | 408 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903165033 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 408 |  | 408 |  |  | 19/09/2026 | 21/09/2026 |  |  | 408 |  | 408 |  |  | 18/09/2026 | 19/09/2026 |  |  | 408 |  | 408
ADIDAS | 0903165054-1 KW5050 | MAROON | 90D | F2625M101 | 447 | 15/10/2026 | 447 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903165054 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | ESS REG |  | SS27-STX | 2026-06-10 | 2026-06-10 |  |  | 447 |  | 447 |  |  | 2026-02-10 | 2026-02-10 |  |  | 447 |  | 447
ADIDAS | 0903165070-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 309 | 30/09/2026 | 309 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903165070 LD0908 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 309 |  | 309 |  |  | 18/09/2026 | 19/09/2026 |  |  | 309 |  | 309 |  |  | 17/09/2026 | 18/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903165109-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 495 | 15/10/2026 | 495 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165109 LE8187 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 495 |  | 495 |  |  | 20/10/2026 | 21/10/2026 |  |  | 495 |  | 495
ADIDAS | 0903165167-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 900 | 30/09/2026 | 900 | SA | SA26/06/2026 | G1C | JACKET | G1 | (29/07/2026) | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903165167 JM1772 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 19/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903165226-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 999 | 30/09/2026 | 999 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165226 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 999 |  | 999 |  |  | 2026-02-10 | 2026-03-10 |  |  | 999 |  | 999
ADIDAS | 0903165306-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 168 | 2026-07-10 | 168 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165306 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 168 |  | 168 |  |  | 2026-12-10 | 13/10/2026 |  |  | 168 |  | 168
ADIDAS | 0903165362-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165362 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903165425-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 315 | 30/09/2026 | 315 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165425 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 315 |  | 315 |  |  | 2026-05-10 | 2026-07-10 |  |  | 315 |  | 315
ADIDAS | 0903165470-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 1248 | 30/09/2026 | 1248 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165470 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 17/09/2026 | 17/09/2026 |  |  | 1248 |  | 1248 |  |  | 14/09/2026 | 14/09/2026 |  |  | 1248 |  | 1248
ADIDAS | 0903165506-1 LC7300 | WHITE | 90D | S2725M926A | 318 | 2026-07-10 | 318 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 |  | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903165506 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | MONO TREFOIL WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 318 |  | 318 |  |  | 21/09/2026 | 22/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903165542-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 517 | 2026-07-10 | 517 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903165542 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 517 |  | 517 |  |  | 24/09/2026 | 25/09/2026 |  |  | 517 |  | 517
ADIDAS | 0903165585-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 1245 | 30/09/2026 | 1245 | SI | SI26/06/2026 | G1K | POLO SHIRT | G1 | (12/08/2026) | ok | 25/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165585 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 17/09/2026 | 21/09/2026 |  |  | 1245 |  | 1245 |  |  | 14/09/2026 | 17/09/2026 |  |  | 1245 |  | 1245
ADIDAS | 0903165644-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 243 | 23/09/2026 | 243 | AN | AN26/06/2026 | G1R | T-SHIRT | G1 | (28/07/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903165644 KX0123 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | M ADI RETRO T WHITE |  | SS27 | 14/09/2026 | 14/09/2026 |  |  | 243 |  | 243 |  |  | 2026-10-09 | 2026-10-09 | 31/07/2026 | 2026-08-08 | 243 | 243
ADIDAS | 0903166391-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903166391 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 2026-12-09 | 300 | 250 | 50 |  | 250 | 2026-09-09 | 2026-11-09 | 29/08/2026 | 2026-10-09 | 300 | 296 | 4
ADIDAS | 0903166456-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 704 | 2026-07-10 | 704 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903166456 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 25/09/2026 |  |  | 704 |  | 704 |  |  | 22/09/2026 | 22/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903166659-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 319 | 2026-07-10 | 319 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 |  | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903166659 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 319 |  | 319 |  |  | 21/09/2026 | 22/09/2026 |  |  | 319 |  | 319
ADIDAS | 0903167086-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 523 | 15/10/2026 | 523 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 516199 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167086 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 523 |  | 523 |  |  | 17/10/2026 | 19/10/2026 |  |  | 523 |  | 523 |  |  | 2026-12-10 | 13/10/2026 |  |  | 523 |  | 523
ADIDAS | 0903167126-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 1460 | 15/10/2026 | 1460 | AN | AN26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167126 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 28/10/2026 | 30/10/2026 |  |  | 1460 |  | 1460 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1460 |  | 1460 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1460 |  | 1460
ADIDAS | 0903167166-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167166 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-01-10 |  |  | 271 |  | 271
ADIDAS | 0903167196-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 182 | 15/10/2026 | 182 | AN | AN26/06/2026 | G1M | T-SHIRT | G1 |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903167196 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/10/2026 | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI | 28/10/2026 | 28/10/2026 |  |  | 182 |  | 182 |  |  | 26/10/2026 | 26/10/2026 |  |  | 182 |  | 182 |  |  | 24/10/2026 | 24/10/2026 |  |  | 182 |  | 182
ADIDAS | 0903167198-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 116 | 15/10/2026 | 116 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167198 LF0718 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 116 |  | 116 |  |  | 2026-10-10 | 2026-12-10 |  |  | 116 |  | 116
ADIDAS | 0903167226-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 331 | 21/08/2026 | 331 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 21/08: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 600000 | HT SUB PROCESS_V1 | 0903167226 IN1172 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 16/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 331 | 331 |  |  |  | 14/07/2026 | 24/07/2026 | 14/07/2026 | 20/07/2026 | 331 | 331 |  |  |  | 13/07/2026 | 23/07/2026 | 14/07/2026 | 20/07/2026 | 331 | 331
ADIDAS | 0903167227-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 410 | 2026-07-10 | 410 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903167227 KT7396 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-05-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 410 |  | 410 |  |  | 2026-01-10 | 2026-02-10 |  |  | 410 |  | 410
ADIDAS | 0903167268-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 415 | 30/09/2026 | 415 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167268 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | LV COLLEGIATE T |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 415 |  | 415 |  |  | 28/09/2026 | 29/09/2026 | 2026-10-09 | 2026-10-09 | 415 | 394 | 21
ADIDAS | 0903167275-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 267 | 2026-07-10 | 267 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167275 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 267 |  | 267 |  |  | 23/09/2026 | 24/09/2026 |  |  | 267 |  | 267
ADIDAS | 0903167287-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 319 | 21/08/2026 | 319 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | (18/04/2026) |  | 21/08: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 600000 | HT SUB PROCESS_V1 | 0903167287 IN1156 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 22/07/2026 | 20/07/2026 | 21/07/2026 | 319 | 319 |  |  |  | 16/07/2026 | 20/07/2026 | 14/07/2026 | 16/07/2026 | 319 | 319 |  |  |  | 15/07/2026 | 17/07/2026 | 13/07/2026 | 16/07/2026 | 319 | 319
ADIDAS | 0903167316-1 KY5866 | BLACK | 90D | S2750MTR052 | 139 | 15/10/2026 | 139 | SI | SI26/06/2026 | G2C | SHORTS | G2 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903167316 KY5866 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | D18T ESS SHORTS BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 139 |  | 139 |  |  | 28/09/2026 | 29/09/2026 |  |  | 139 |  | 139 |  |  | 26/09/2026 | 28/09/2026 |  |  | 139 |  | 139
ADIDAS | 0903167324-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 255 | 15/10/2026 | 255 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903167324 KD0738 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 255 |  | 255 |  |  | 21/10/2026 | 22/10/2026 |  |  | 255 |  | 255 |  |  | 15/10/2026 | 16/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903167339-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 673 | 2026-07-10 | 673 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167339 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 673 |  | 673 |  |  | 24/09/2026 | 24/09/2026 |  |  | 673 |  | 673
ADIDAS | 0903167346-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 1269 | 26/08/2026 | 1269 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 24/08: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). (received qty more than MCAF qty). 600000 | HT SUB PROCESS_V1 | 0903167346 IN1157 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 22/07/2026 | 28/07/2026 | 22/07/2026 | 24/07/2026 | 1269 | 1269 |  |  |  | 20/07/2026 | 24/07/2026 | 21/07/2026 | 22/07/2026 | 1269 | 1269 |  |  |  | 17/07/2026 | 23/07/2026 | 15/07/2026 | 21/07/2026 | 1269 | 1269
ADIDAS | 0903167370-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 210 | 15/10/2026 | 210 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903167370 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 210 |  | 210 |  |  | 2026-01-10 | 2026-02-10 |  |  | 210 |  | 210
ADIDAS | 0903167433-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 501 | 2026-07-10 | 501 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167433 KW8934 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 501 |  | 501 |  |  | 22/09/2026 | 23/09/2026 |  |  | 501 |  | 501
ADIDAS | 0903167457-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 405 | 2026-07-10 | 405 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167457 KW8932 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 26/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 405 |  | 405 |  |  | 23/09/2026 | 24/09/2026 |  |  | 405 |  | 405
ADIDAS | 0903167485-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 130 | 2026-07-10 | 130 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167485 KW9039 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 130 |  | 130 |  |  | 24/09/2026 | 25/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903167564-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 652 | 15/10/2026 | 652 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167564 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 652 |  | 652 |  |  | 19/09/2026 | 21/09/2026 |  |  | 652 |  | 652 |  |  | 18/09/2026 | 19/09/2026 |  |  | 652 |  | 652
ADIDAS | 0903167589-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 554 | 15/10/2026 | 554 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167589 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 554 |  | 554 |  |  | 29/09/2026 | 30/09/2026 |  |  | 554 |  | 554
ADIDAS | 0903167678-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167678 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903167694-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 362 | 15/10/2026 | 362 | SI | SI26/06/2026 | G3I | PANTS | G3 | (28/08/2026) | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 04-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167694 LE8188 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 362 |  | 362 |  |  | 16/10/2026 | 19/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903167696-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/09/2026 | 500 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167696 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 500 |  | 500 |  |  | 28/09/2026 | 29/09/2026 | 2026-12-09 | 2026-12-09 | 500 | 122 | 378 |  | 122
ADIDAS | 0903167722-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 754 | 15/10/2026 | 754 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167722 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 22/09/2026 | 23/09/2026 |  |  | 754 |  | 754 |  |  | 18/09/2026 | 19/09/2026 |  |  | 754 |  | 754 |  |  | 17/09/2026 | 18/09/2026 |  |  | 754 |  | 754
ADIDAS | 0903167723-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 517 | 15/10/2026 | 517 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167723 LE8188 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 517 |  | 517 |  |  | 19/10/2026 | 20/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903167736-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 356 | 2026-07-10 | 356 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877)., ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167736 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 356 |  | 356 |  |  | 2026-05-10 | 2026-06-10 |  |  | 356 |  | 356
ADIDAS | 0903167751-1 KW5050 | MAROON | 90D | F2625M101 | 2163 | 15/09/2026 | 2163 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 15/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO SUB PROCESS_V1 | 0903167751 KW5050 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-09 | ESS REG |  | SS27-STX | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2163 | 674 | 1489 |  | 239 | 2026-09-09 | 2026-11-09 | 2026-09-09 | 13/09/2026 | 2163 | 2126 | 37
ADIDAS | 0903167776-1 KA4331 | BLACK | 90D | S2608MR0902 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 1st Art (TC 10 pcs) 516267 | PAD+HT SUB PROCESS_V3 | 0903167776 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 21/09/2026 | 23/09/2026 |  |  | 1200 |  | 1200 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1200 |  | 1200 |  |  | 16/09/2026 | 18/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903167792-1 KA4331 | BLACK | 90D | S2608MR0902 | 335 | 2026-07-10 | 335 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516400 | PAD+HT SUB PROCESS_V3 | 0903167792 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 335 |  | 335 |  |  | 22/09/2026 | 24/09/2026 |  |  | 335 |  | 335 |  |  | 21/09/2026 | 23/09/2026 |  |  | 335 |  | 335
ADIDAS | 0903167804-1 KW5050 | MAROON | 90D | F2625M101 | 334 | 15/10/2026 | 334 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903167804 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 14/10/2026 | ESS REG |  | SS27-STX | 14/10/2026 | 14/10/2026 |  |  | 334 |  | 334 |  |  | 2026-10-10 | 2026-10-10 |  |  | 334 |  | 334
ADIDAS | 0903167883-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 262 | 15/10/2026 | 262 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167883 LD6542 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 262 |  | 262 |  |  | 13/10/2026 | 15/10/2026 |  |  | 262 |  | 262
ADIDAS | 0903167908-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 627 | 15/10/2026 | 627 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167908 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | W SL WV TT BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 627 |  | 627 |  |  | 20/10/2026 | 22/10/2026 |  |  | 627 |  | 627
ADIDAS | 0903167943-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 555 | 15/10/2026 | 555 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167943 KX7715 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 22/09/2026 | 26/09/2026 |  |  | 555 |  | 555 |  |  | 18/09/2026 | 23/09/2026 |  |  | 555 |  | 555
ADIDAS | 0903168109-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 26/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168109 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 400 | 400 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-11-08 | 2026-07-09 | 400 | 368 | 32
ADIDAS | 0903168275-1 KA0246 | BLACK | 90D | S2608WR0902 | 339 | 2026-07-10 | 339 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 15-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903168275 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 339 |  | 339 |  |  | 25/09/2026 | 28/09/2026 |  |  | 339 |  | 339 |  |  | 24/09/2026 | 26/09/2026 |  |  | 339 |  | 339
ADIDAS | 0903168299-1 KA0246 | BLACK | 90D | S2608WR0902 | 608 | 15/10/2026 | 608 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903168299 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 608 |  | 608 |  |  | 2026-08-10 | 2026-09-10 |  |  | 608 |  | 608 |  |  | 2026-07-10 | 2026-08-10 |  |  | 608 |  | 608
ADIDAS | 0903168302-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168302 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 24/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903168327-1 KA0246 | BLACK | 90D | S2608WR0902 | 301 | 30/09/2026 | 301 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168327 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 |  |  | 301 |  | 301 |  |  | 17/09/2026 | 18/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903168356-1 KA0246 | BLACK | 90D | S2608WR0902 | 314 | 2026-07-10 | 314 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168356 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 314 |  | 314 |  |  | 28/09/2026 | 29/09/2026 |  |  | 314 |  | 314 |  |  | 26/09/2026 | 28/09/2026 |  |  | 314 |  | 314
ADIDAS | 0903168388-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 186 | 30/09/2026 | 186 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168388 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 186 |  | 186 |  |  | 19/09/2026 | 21/09/2026 | 27/08/2026 | 2026-07-09 | 186 | 168 | 18
ADIDAS | 0903168468-1 KA4331 | BLACK | 90D | S2608MR0902 | 364 | 2026-07-10 | 364 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168468 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 364 |  | 364 |  |  | 24/09/2026 | 25/09/2026 |  |  | 364 |  | 364 |  |  | 23/09/2026 | 24/09/2026 |  |  | 364 |  | 364
ADIDAS | 0903169170-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 204 | 15/10/2026 | 204 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516443 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169170 KU8975 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 27/10/2026 | 29/10/2026 |  |  | 204 |  | 204 |  |  | 23/10/2026 | 26/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903169256-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 701 | 15/10/2026 | 701 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169256 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 27/10/2026 | 29/10/2026 |  |  | 701 |  | 701 |  |  | 23/10/2026 | 26/10/2026 |  |  | 701 |  | 701
ADIDAS | 0903169715-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 328 | 15/10/2026 | 328 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169715 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 328 |  | 328 |  |  | 30/09/2026 | 2026-01-10 |  |  | 328 |  | 328
ADIDAS | 0903169772-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169772 KY3734 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903169855-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 150 | 15/10/2026 | 150 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169855 KW9039 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 29/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 29/09/2026 | 30/09/2026 |  |  | 150 |  | 150 |  |  | 25/09/2026 | 26/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903169976-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 259 | 15/10/2026 | 259 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903169976 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 259 |  | 259 |  |  | 30/09/2026 | 2026-01-10 |  |  | 259 |  | 259
ADIDAS | 0903170085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 538 | 14/09/2026 | 538 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 14-Jul. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170085 LD5446 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-09-09 | 2026-12-09 | 538 | 505 | 33 |  | 20 | 2026-02-09 | 2026-09-09 | 2026-05-09 | 2026-11-09 | 538 | 519 | 19
ADIDAS | 0903170105-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 1240 | 14/09/2026 | 1240 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903170105 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-12-09 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1240 | 993 | 247 |  | 485 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 1240 | 1095 | 145 |  | 266 | 2026-03-09 | 2026-05-09 | 2026-09-09 | 14/09/2026 | 1240 | 1215 | 25 |  | 151
ADIDAS | 0903170139-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 574 | 15/09/2026 | 574 | AN | AN26/06/2026 | G3A | PANTS | G3 | ok | ok | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170139 LE8181 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 574 | 574 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-11-09 | 574 | 574
ADIDAS | 0903170160-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 15/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170160 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 400 | 379 | 21 |  | 74 | 2026-05-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 400 | 280 | 120
ADIDAS | 0903170289-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170289 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 14/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903170946-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 260 | 15/10/2026 | 260 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903170946 KD5507 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | WE FR T GREY FIVE F17 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 260 |  | 260 |  |  | 29/09/2026 | 29/09/2026 |  |  | 260 |  | 260 |  |  | 28/09/2026 | 28/09/2026 |  |  | 260 |  | 260
ADIDAS | 0903170993-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 327 | 2026-07-10 | 327 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903170993 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 25/09/2026 |  |  | 327 |  | 327 |  |  | 22/09/2026 | 22/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903171021-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 500 | 15/10/2026 | 500 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903171021 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 500 |  | 500 |  |  | 2026-01-10 | 2026-02-10 |  |  | 500 |  | 500
ADIDAS | 0903172164-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 1591 | 14/09/2026 | 1591 | AN | AN26/06/2026 | G3B,G3J | PANTS | G3 | ok | ok | 14/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 13-Aug. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 13-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903172164 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1591 | 1257 | 334 |  | 97 | 2026-02-09 | 2026-10-09 | 2026-03-09 | 14/09/2026 | 1591 | 1476 | 115
ADIDAS | 0903173197-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 1686 | 30/09/2026 | 1686 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 |  | ok | 23/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903173197 KW8932 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 18/09/2026 | 21/09/2026 |  |  | 1686 |  | 1686 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1686 |  | 1686
ADIDAS | 0903173246-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1225 | 30/09/2026 | 1225 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173246 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1225 |  | 1225 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1225 |  | 1225
ADIDAS | 0903173302-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 410 | 30/09/2026 | 410 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516461 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173302 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 410 |  | 410 |  |  | 29/09/2026 | 2026-01-10 | 2026-12-09 | 2026-12-09 | 410 | 266 | 144 |  | 266
ADIDAS | 0903173331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2400 | 2026-07-10 | 2400 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 24-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173331 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-08-10 | 2026-12-10 |  |  | 2400 |  | 2400
ADIDAS | 0903173353-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173353 KV7863 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1500 |  | 1500 |  |  | 2026-05-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 1500 | 479 | 1021
ADIDAS | 0903173473-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173473 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903173515-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173515 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903173545-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173545 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 800 |  | 800 |  |  | 2026-05-10 | 2026-07-10 |  |  | 800 |  | 800
ADIDAS | 0903173563-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-12-09 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173563 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 300 | 300 |  |  |  | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 300 | 300
ADIDAS | 0903174134-1 KA4331 | BLACK | 90D | S2608MR0902 | 303 | 30/09/2026 | 303 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903174134 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 303 |  | 303 |  |  | 16/09/2026 | 17/09/2026 |  |  | 303 |  | 303 |  |  | 15/09/2026 | 16/09/2026 |  |  | 303 |  | 303
ADIDAS | 0903174475-1 IN1173 | WHITE | 90D | S2408WR1600-SLT | 729 | 26/08/2026 | 729 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 03-Aug, actual receives 03-Aug (using fabric from Y.T.I). T2 Fu Hsun, PI Date 24-Jul, actual receives 03 Aug (using fabric from Y.T.I). (received qty more than MCAF qty). 600000 | HT SUB PROCESS_V1 | 0903174475 IN1173 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 13/08/2026 | 26/08/2026 | 18/08/2026 | 24/08/2026 | 729 | 729 |  |  |  | 2026-11-08 | 21/08/2026 | 2026-10-08 | 24/08/2026 | 729 | 729 |  |  |  | 2026-10-08 | 20/08/2026 | 2026-07-08 | 22/08/2026 | 729 | 729
ADIDAS | 0903176681-1 KA4331 | BLACK | 90D | S2608MR0902 | 371 | 2026-07-10 | 371 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516394 | PAD+HT SUB PROCESS_V3 | 0903176681 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 371 |  | 371 |  |  | 24/09/2026 | 25/09/2026 |  |  | 371 |  | 371 |  |  | 23/09/2026 | 24/09/2026 |  |  | 371 |  | 371
ADIDAS | 0903176702-1 KA4331 | BLACK | 90D | S2608MR0902 | 700 | 30/09/2026 | 700 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903176702 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 700 |  | 700 |  |  | 16/09/2026 | 17/09/2026 |  |  | 700 |  | 700 |  |  | 15/09/2026 | 16/09/2026 |  |  | 700 |  | 700
ADIDAS | 0903176748-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 309 | 15/10/2026 | 309 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176748 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 309 |  | 309 |  |  | 2026-10-10 | 2026-12-10 |  |  | 309 |  | 309 |  |  | 2026-05-10 | 2026-06-10 |  |  | 309 |  | 309
ADIDAS | 0903176770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2305 | 15/10/2026 | 2305 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 30/10/2026 | 2026-03-11 |  |  | 2305 |  | 2305 |  |  | 27/10/2026 | 30/10/2026 |  |  | 2305 |  | 2305 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2305 |  | 2305
ADIDAS | 0903176795-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 459 | 15/10/2026 | 459 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176795 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 459 |  | 459 |  |  | 2026-09-10 | 2026-10-10 |  |  | 459 |  | 459 |  |  | 2026-03-10 | 2026-05-10 |  |  | 459 |  | 459
ADIDAS | 0903176840-1 IN1159 | BLACK | 90D | S2408MR1601 | 223 | 2026-07-10 | 223 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516443 | HT SUB PROCESS_V1 | 0903176840 IN1159 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 223 |  | 223 |  |  | 21/09/2026 | 22/09/2026 |  |  | 223 |  | 223 |  |  | 19/09/2026 | 21/09/2026 |  |  | 223 |  | 223
ADIDAS | 0903176865-1 KA0246 | BLACK | 90D | S2608WR0902 | 450 | 2026-07-10 | 450 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 26-Aug. 516244 | PAD+HT SUB PROCESS_V3 | 0903176865 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 450 |  | 450 |  |  | 28/09/2026 | 29/09/2026 |  |  | 450 |  | 450 |  |  | 26/09/2026 | 28/09/2026 |  |  | 450 |  | 450
ADIDAS | 0903194305-1 IN1156 | BLACK | 90D | S2408MR1600 | 180 | 15/10/2026 | 180 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194305 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 180 |  | 180 |  |  | 22/09/2026 | 23/09/2026 | 2026-09-09 | 2026-12-09 | 180 | 16 | 164 |  | 15 | 21/09/2026 | 22/09/2026 | 31/08/2026 | 2026-10-09 | 180 | 179 | 1
ADIDAS | 0903194307-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194307 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 28/09/2026 | 29/09/2026 | 2026-09-09 | 2026-11-09 | 120 | 119 | 1 |  |  | 26/09/2026 | 28/09/2026 | 2026-03-09 | 2026-10-09 | 120 | 119 | 1
ADIDAS | 0903194308-1 IN1172 | BLACK | 90D | S2408WR1600 | 120 | 15/10/2026 | 120 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194308 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 120 |  | 120 |  |  | 14/10/2026 | 15/10/2026 |  |  | 120 |  | 120 |  |  | 13/10/2026 | 14/10/2026 | 2026-05-09 | 2026-05-09 | 120 | 117 | 3
ADIDAS | 0903194309-1 IN1156 | BLACK | 90D | S2408MR1600 | 1308 | 15/10/2026 | 1308 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194309 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 1308 |  | 1308 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1308 |  | 1308 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1308 |  | 1308
ADIDAS | 0903194311-1 IN1172 | BLACK | 90D | S2408WR1600 | 1174 | 15/10/2026 | 1174 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903194311 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 20/10/2026 |  |  | 1174 |  | 1174 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1174 |  | 1174 |  |  | 14/10/2026 | 16/10/2026 | 2026-03-09 | 2026-12-09 | 1174 | 1146 | 28 |  | 21
ADIDAS | 0903194312-1 IN1157 | WHITE | 90D | S2408MR1600 | 1525 | 15/10/2026 | 1525 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194312 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 1525 |  | 1525 |  |  | 30/09/2026 | 2026-02-10 | 2026-09-09 | 2026-12-09 | 1525 | 696 | 829 |  | 25 | 29/09/2026 | 2026-01-10 | 2026-02-09 | 2026-10-09 | 1525 | 696 | 829
ADIDAS | 0903194314-1 IN1173 | WHITE | 90D | S2408WR1600 | 1776 | 30/09/2026 | 1776 | SI | SI30/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 28/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. 672027 | HT SUB PROCESS_V1 | 0903194314 IN1173 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 26/09/2026 |  |  | 1776 |  | 1776 |  |  | 22/09/2026 | 24/09/2026 | 2026-10-08 | 24/08/2026 | 1776 | 1776 |  |  |  | 21/09/2026 | 23/09/2026 | 2026-08-08 | 24/08/2026 | 1776 | 1776
ADIDAS | 0903194315-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 1508 | 15/10/2026 | 1508 | SA | SA30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903194315 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 1508 |  | 1508 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1508 |  | 1508 |  |  | 30/09/2026 | 2026-03-10 |  |  | 1508 |  | 1508
ADIDAS | 0903194317-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1167 | 15/10/2026 | 1167 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903194317 IT1828 | 14/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 1167 |  | 1167 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1167 |  | 1167 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1167 |  | 1167
ADIDAS | 0903194318-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 443 | 15/10/2026 | 443 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 672027 | PAD+HT SUB PROCESS_V3 | 0903194318 KA0248 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 443 |  | 443 |  |  | 2026-08-10 | 2026-09-10 |  |  | 443 |  | 443 |  |  | 2026-07-10 | 2026-08-10 |  |  | 443 |  | 443
ADIDAS | 0903194321-1 KA4331 | BLACK | 90D | S2608MR0902 | 239 | 15/10/2026 | 239 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194321 KA4331 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 239 |  | 239 |  |  | 2026-05-10 | 2026-06-10 |  |  | 239 |  | 239 |  |  | 2026-03-10 | 2026-05-10 |  |  | 239 |  | 239
ADIDAS | 0903194323-1 IN8707 | BLACK | 90D | S2408WR1601A | 194 | 15/10/2026 | 194 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903194323 IN8707 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 194 |  | 194 |  |  | 13/10/2026 | 14/10/2026 |  |  | 194 |  | 194 |  |  | 2026-12-10 | 13/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903194325-1 IN1156 | BLACK | 90D | S2408MR1600 | 566 | 15/10/2026 | 566 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903194325 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 566 |  | 566 |  |  | 25/09/2026 | 26/09/2026 |  |  | 566 |  | 566 |  |  | 24/09/2026 | 25/09/2026 |  |  | 566 |  | 566
ADIDAS | 0903194326-1 KA0246 | BLACK | 90D | S2608WR0902 | 377 | 15/10/2026 | 377 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | PAD+HT SUB PROCESS_V3 | 0903194326 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 377 |  | 377 |  |  | 30/09/2026 | 2026-02-10 |  |  | 377 |  | 377 |  |  | 29/09/2026 | 2026-01-10 |  |  | 377 |  | 377
ADIDAS | 0903194330-1 KA0235 | BLACK | 90D | S2608WR0901 | 348 | 15/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194330 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 348 |  | 348 |  |  | 22/10/2026 | 24/10/2026 |  |  | 348 |  | 348 |  |  | 21/10/2026 | 23/10/2026 |  |  | 348 |  | 348
ADIDAS | 0903194331-1 IN1156 | BLACK | 90D | S2408MR1600 | 231 | 15/10/2026 | 231 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516343 | HT SUB PROCESS_V1 | 0903194331 IN1156 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 231 |  | 231 |  |  | 22/09/2026 | 23/09/2026 | 2026-08-09 | 2026-11-09 | 231 | 198 | 33 |  |  | 21/09/2026 | 22/09/2026 | 31/08/2026 | 2026-11-09 | 231 | 198 | 33
ADIDAS | 0903194333-1 IN1172 | BLACK | 90D | S2408WR1600 | 423 | 15/10/2026 | 423 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 516443 | HT SUB PROCESS_V1 | 0903194333 IN1172 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 423 |  | 423 |  |  | 14/10/2026 | 15/10/2026 |  |  | 423 |  | 423 |  |  | 13/10/2026 | 14/10/2026 | 2026-07-09 | 2026-12-09 | 423 | 414 | 9 |  | 5
ADIDAS | 0903194340-1 IN1157 | WHITE | 90D | S2408MR1600 | 375 | 15/10/2026 | 375 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 06-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903194340 IN1157 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 375 |  | 375 |  |  | 28/09/2026 | 29/09/2026 | 2026-10-09 | 2026-11-09 | 375 | 373 | 2 |  |  | 26/09/2026 | 28/09/2026 | 2026-07-09 | 2026-10-09 | 375 | 374 | 1
ADIDAS | 0903194361-1 IN1156 | BLACK | 90D | S2408MR1600 | 4002 | 15/10/2026 | 4002 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516438 | HT SUB PROCESS_V1 | 0903194361 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-08-10 |  |  | 4002 |  | 4002 |  |  | 30/09/2026 | 2026-06-10 | 2026-08-09 | 2026-12-09 | 4002 | 3250 | 752 |  | 44 | 29/09/2026 | 2026-05-10 | 29/08/2026 | 2026-11-09 | 4002 | 3259 | 743
ADIDAS | 0903194364-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516404 | HT SUB PROCESS_V1 | 0903194364 IN1172 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903194475-1 KA6229 | BLACK | 120D | S2608WR0202 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194475 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 631 |  | 631 |  |  | 2026-08-10 | 2026-12-10 |  |  | 631 |  | 631 |  |  | 2026-05-10 | 2026-08-10 |  |  | 631 |  | 631
ADIDAS | 0903194486-1 KA6229 | BLACK | 120D | S2608WR0202 | 526 | 15/10/2026 | 526 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194486 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 526 |  | 526 |  |  | 2026-08-10 | 2026-12-10 |  |  | 526 |  | 526 |  |  | 2026-05-10 | 2026-08-10 |  |  | 526 |  | 526
ADIDAS | 0903194488-1 KA6229 | BLACK | 120D | S2608WR0202 | 310 | 15/10/2026 | 310 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194488 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 310 |  | 310 |  |  | 2026-12-10 | 14/10/2026 |  |  | 310 |  | 310 |  |  | 2026-08-10 | 2026-10-10 |  |  | 310 |  | 310
ADIDAS | 0903194490-1 KA6229 | BLACK | 120D | S2608WR0202 | 369 | 15/10/2026 | 369 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194490 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 369 |  | 369 |  |  | 2026-12-10 | 14/10/2026 |  |  | 369 |  | 369 |  |  | 2026-08-10 | 2026-10-10 |  |  | 369 |  | 369
ADIDAS | 0903194492-1 KA6229 | BLACK | 120D | S2608WR0202 | 926 | 30/09/2026 | 926 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194492 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 19/09/2026 | 23/09/2026 |  |  | 926 |  | 926 |  |  | 16/09/2026 | 19/09/2026 |  |  | 926 |  | 926 |  |  | 2026-12-09 | 16/09/2026 |  |  | 926 |  | 926
ADIDAS | 0903194495-1 KA6229 | BLACK | 120D | S2608WR0202 | 321 | 30/09/2026 | 321 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194495 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 321 |  | 321 |  |  | 19/09/2026 | 22/09/2026 |  |  | 321 |  | 321 |  |  | 16/09/2026 | 18/09/2026 |  |  | 321 |  | 321
ADIDAS | 0903194496-1 KA6229 | BLACK | 120D | S2608WR0202 | 779 | 15/10/2026 | 779 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194496 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 17/10/2026 | 20/10/2026 |  |  | 779 |  | 779 |  |  | 14/10/2026 | 16/10/2026 |  |  | 779 |  | 779 |  |  | 2026-10-10 | 13/10/2026 |  |  | 779 |  | 779
ADIDAS | 0903194499-1 KA6229 | BLACK | 120D | S2608WR0202 | 346 | 30/09/2026 | 346 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194499 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 346 |  | 346 |  |  | 19/09/2026 | 22/09/2026 |  |  | 346 |  | 346 |  |  | 16/09/2026 | 18/09/2026 |  |  | 346 |  | 346
ADIDAS | 0903194663-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1069 | 29/09/2026 | 1069 | AN | AN26/06/2026 | G1D | JACKET | G1 | ok | (07/08/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194663 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 16/09/2026 | 2026-10-09 | 14/09/2026 | 1069 | 277 | 792 |  | 12 | 2026-07-09 | 2026-12-09 | 2026-02-09 | 2026-11-09 | 1069 | 383 | 686
ADIDAS | 0903194835-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 623 | 30/09/2026 | 623 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903194835 KV7863 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 623 |  | 623 |  |  | 2026-02-10 | 2026-03-10 | 2026-10-09 | 14/09/2026 | 623 | 609 | 14 |  | 361
ADIDAS | 0903195508-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 471 | 30/09/2026 | 471 | AN | AN30/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903195508 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 19/09/2026 |  |  | 471 |  | 471 |  |  | 15/09/2026 | 16/09/2026 |  |  | 471 |  | 471 |  |  | 14/09/2026 | 15/09/2026 |  |  | 471 |  | 471
ADIDAS | 0903196020-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 891 | 15/10/2026 | 891 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196020 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 891 |  | 891 |  |  | 24/09/2026 | 25/09/2026 |  |  | 891 |  | 891 |  |  | 23/09/2026 | 24/09/2026 |  |  | 891 |  | 891
ADIDAS | 0903196021-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 12 | 15/10/2026 | 12 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196021 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 12 |  | 12 |  |  | 24/09/2026 | 25/09/2026 |  |  | 12 |  | 12 |  |  | 23/09/2026 | 24/09/2026 |  |  | 12 |  | 12
ADIDAS | 0903196022-1 IN1172 | BLACK | 90D | S2408WR1600 | 2616 | 15/10/2026 | 2616 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 823016 | HT SUB PROCESS_V1 | 0903196022 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 23/10/2026 |  |  | 2616 |  | 2616 |  |  | 17/10/2026 | 21/10/2026 |  |  | 2616 |  | 2616 |  |  | 16/10/2026 | 20/10/2026 | 2026-04-09 | 2026-11-09 | 2616 | 2549 | 67
ADIDAS | 0903196023-1 IN1156 | BLACK | 90D | S2408MR1600 | 3287 | 15/10/2026 | 3287 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 823016 | HT SUB PROCESS_V1 | 0903196023 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-02-10 |  |  | 3287 |  | 3287 |  |  | 26/09/2026 | 30/09/2026 |  |  | 3287 |  | 3287 |  |  | 25/09/2026 | 29/09/2026 |  |  | 3287 |  | 3287
ADIDAS | 0903196024-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960006 | HT SUB PROCESS_V1 | 0903196024 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 15/10/2026 | 15/10/2026 | 2026-05-09 | 2026-05-09 | 100 | 97 | 3
ADIDAS | 0903196025-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960006 | HT SUB PROCESS_V1 | 0903196025 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 200 |  | 200 |  |  | 22/09/2026 | 23/09/2026 | 2026-09-09 | 2026-11-09 | 200 | 199 | 1 |  |  | 21/09/2026 | 22/09/2026 | 31/08/2026 | 2026-10-09 | 200 | 199 | 1
ADIDAS | 0903196026-1 IN1172 | BLACK | 90D | S2408WR1600 | 134 | 15/10/2026 | 134 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960026 | HT SUB PROCESS_V1 | 0903196026 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 19/10/2026 |  |  | 134 |  | 134 |  |  | 16/10/2026 | 16/10/2026 |  |  | 134 |  | 134 |  |  | 15/10/2026 | 15/10/2026 | 2026-05-09 | 2026-12-09 | 134 | 134 |  |  | 10
ADIDAS | 0903196027-1 IN1156 | BLACK | 90D | S2408MR1600 | 143 | 15/10/2026 | 143 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960026 | HT SUB PROCESS_V1 | 0903196027 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 143 |  | 143 |  |  | 25/09/2026 | 26/09/2026 | 2026-08-09 | 2026-10-09 | 143 | 142 | 1 |  |  | 24/09/2026 | 25/09/2026 | 29/08/2026 | 2026-10-09 | 143 | 142 | 1
ADIDAS | 0903196028-1 IN1156 | BLACK | 90D | S2408MR1600 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 980004 | HT SUB PROCESS_V1 | 0903196028 IN1156 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 631 |  | 631 |  |  | 28/09/2026 | 29/09/2026 |  |  | 631 |  | 631 |  |  | 26/09/2026 | 28/09/2026 |  |  | 631 |  | 631
ADIDAS | 0903196030-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1200 | 15/10/2026 | 1200 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196030 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 1200 |  | 1200 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1200 |  | 1200 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1200 |  | 1200
ADIDAS | 0903196031-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 1200 | 15/10/2026 | 1200 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196031 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1200 |  | 1200 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1200 |  | 1200
ADIDAS | 0903196032-1 IN1157 | WHITE | 90D | S2408MR1600 | 290 | 15/10/2026 | 290 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | (Damco offline). T2 Y.T.I, body & mesh actual receives 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196032 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 290 |  | 290 |  |  | 29/09/2026 | 30/09/2026 | 2026-09-09 | 2026-12-09 | 290 | 288 | 2 |  | 11 | 28/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 290 | 288 | 2
ADIDAS | 0903196033-1 IN1156 | BLACK | 90D | S2408MR1600 | 236 | 15/10/2026 | 236 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196033 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 236 |  | 236 |  |  | 25/09/2026 | 26/09/2026 |  |  | 236 |  | 236 |  |  | 24/09/2026 | 25/09/2026 | 2026-02-09 | 2026-10-09 | 236 | 197 | 39
ADIDAS | 0903196034-1 IN1173 | WHITE | 90D | S2408WR1600 | 114 | 15/10/2026 | 114 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 01-Aug. 688010 | HT SUB PROCESS_V1 | 0903196034 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 114 |  | 114 |  |  | 2026-06-10 | 2026-07-10 | 13/08/2026 | 26/08/2026 | 114 | 114 |  |  |  | 2026-05-10 | 2026-06-10 | 13/08/2026 | 22/08/2026 | 114 | 114
ADIDAS | 0903196035-1 IN1172 | BLACK | 90D | S2408WR1600 | 528 | 15/10/2026 | 528 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196035 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 528 |  | 528 |  |  | 28/09/2026 | 29/09/2026 |  |  | 528 |  | 528 |  |  | 26/09/2026 | 28/09/2026 | 2026-05-09 | 14/09/2026 | 528 | 516 | 12 |  | 6
ADIDAS | 0903196036-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 144 | 15/10/2026 | 144 | SI | SI30/06/2026 | G1H | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196036 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 144 |  | 144 |  |  | 13/10/2026 | 14/10/2026 |  |  | 144 |  | 144 |  |  | 2026-12-10 | 13/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903196037-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196037 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 248 |  | 248 |  |  | 23/09/2026 | 24/09/2026 |  |  | 248 |  | 248 |  |  | 22/09/2026 | 23/09/2026 |  |  | 248 |  | 248
ADIDAS | 0903197425-1 IN8707 | BLACK | 90D | S2408WR1601A | 156 | 15/10/2026 | 156 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197425 IN8707 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 156 |  | 156 |  |  | 13/10/2026 | 14/10/2026 |  |  | 156 |  | 156 |  |  | 2026-12-10 | 13/10/2026 |  |  | 156 |  | 156
ADIDAS | 0903197427-1 KA0235 | BLACK | 90D | S2608WR0901 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197427 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 24/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903197429-1 KA0246 | BLACK | 90D | S2608WR0902 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197429 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 200 |  | 200 |  |  | 30/09/2026 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 29/09/2026 | 2026-01-10 |  |  | 200 |  | 200
ADIDAS | 0903197431-1 IN8707 | BLACK | 90D | S2408WR1601A | 361 | 15/10/2026 | 361 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903197431 IN8707 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 361 |  | 361 |  |  | 13/10/2026 | 14/10/2026 |  |  | 361 |  | 361 |  |  | 2026-12-10 | 13/10/2026 |  |  | 361 |  | 361
ADIDAS | 0903197433-1 KA0246 | BLACK | 90D | S2608WR0902 | 264 | 15/10/2026 | 264 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 688010 | PAD+HT SUB PROCESS_V3 | 0903197433 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 264 |  | 264 |  |  | 30/09/2026 | 2026-02-10 |  |  | 264 |  | 264 |  |  | 29/09/2026 | 2026-01-10 |  |  | 264 |  | 264
ADIDAS | 0903197435-1 KA0235 | BLACK | 90D | S2608WR0901 | 708 | 15/10/2026 | 708 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197435 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 708 |  | 708 |  |  | 29/10/2026 | 30/10/2026 |  |  | 708 |  | 708 |  |  | 28/10/2026 | 29/10/2026 |  |  | 708 |  | 708
ADIDAS | 0903197436-1 KA0246 | BLACK | 90D | S2608WR0902 | 268 | 15/10/2026 | 268 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197436 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 268 |  | 268 |  |  | 2026-02-10 | 2026-03-10 |  |  | 268 |  | 268 |  |  | 2026-01-10 | 2026-02-10 |  |  | 268 |  | 268
ADIDAS | 0903197439-1 KA0235 | BLACK | 90D | S2608WR0901 | 155 | 15/10/2026 | 155 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197439 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 155 |  | 155 |  |  | 22/10/2026 | 24/10/2026 |  |  | 155 |  | 155 |  |  | 21/10/2026 | 23/10/2026 |  |  | 155 |  | 155
ADIDAS | 0903197440-1 KA4331 | BLACK | 90D | S2608MR0902 | 277 | 15/10/2026 | 277 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197440 KA4331 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 277 |  | 277 |  |  | 2026-05-10 | 2026-06-10 |  |  | 277 |  | 277 |  |  | 2026-03-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903197442-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 335 | 15/10/2026 | 335 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197442 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 335 |  | 335 |  |  | 2026-08-10 | 2026-09-10 |  |  | 335 |  | 335 |  |  | 2026-07-10 | 2026-08-10 |  |  | 335 |  | 335
ADIDAS | 0903197444-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 520 | 15/10/2026 | 520 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 680015 | PAD+HT SUB PROCESS_V3 | 0903197444 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 28/09/2026 | 30/09/2026 |  |  | 520 |  | 520 |  |  | 24/09/2026 | 26/09/2026 |  |  | 520 |  | 520 |  |  | 23/09/2026 | 25/09/2026 |  |  | 520 |  | 520
ADIDAS | 0903197446-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 630 | 15/10/2026 | 630 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197446 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/10/2026 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 630 |  | 630 |  |  | 2026-09-10 | 2026-10-10 |  |  | 630 |  | 630 |  |  | 2026-08-10 | 2026-09-10 |  |  | 630 |  | 630
ADIDAS | 0903197448-1 KA0235 | BLACK | 90D | S2608WR0901 | 675 | 15/10/2026 | 675 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197448 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 675 |  | 675 |  |  | 27/10/2026 | 29/10/2026 |  |  | 675 |  | 675 |  |  | 26/10/2026 | 28/10/2026 |  |  | 675 |  | 675
ADIDAS | 0903197449-1 KA0246 | BLACK | 90D | S2608WR0902 | 547 | 15/10/2026 | 547 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197449 KA0246 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 547 |  | 547 |  |  | 2026-02-10 | 2026-03-10 |  |  | 547 |  | 547 |  |  | 2026-01-10 | 2026-02-10 |  |  | 547 |  | 547
ADIDAS | 0903197451-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197451 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903197453-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 681 | 15/10/2026 | 681 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197453 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 28/09/2026 | 30/09/2026 |  |  | 681 |  | 681 |  |  | 24/09/2026 | 26/09/2026 |  |  | 681 |  | 681 |  |  | 23/09/2026 | 25/09/2026 |  |  | 681 |  | 681
ADIDAS | 0903197455-1 KA4331 | BLACK | 90D | S2608MR0902 | 346 | 15/10/2026 | 346 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903197455 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 346 |  | 346 |  |  | 2026-05-10 | 2026-06-10 |  |  | 346 |  | 346 |  |  | 2026-03-10 | 2026-05-10 |  |  | 346 |  | 346
ADIDAS | 0903197456-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 822 | 15/10/2026 | 822 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 659018 | HT SUB PROCESS_V1 | 0903197456 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 17/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 822 |  | 822 |  |  | 15/10/2026 | 16/10/2026 |  |  | 822 |  | 822 |  |  | 14/10/2026 | 15/10/2026 |  |  | 822 |  | 822
ADIDAS | 0903197458-1 KA0235 | BLACK | 90D | S2608WR0901 | 999 | 15/10/2026 | 999 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903197458 KA0235 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-03-11 | 2026-06-11 |  |  | 999 |  | 999 |  |  | 30/10/2026 | 2026-03-11 |  |  | 999 |  | 999 |  |  | 29/10/2026 | 2026-02-11 |  |  | 999 |  | 999
ADIDAS | 0903197459-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 102 | 15/10/2026 | 102 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903197459 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 102 |  | 102 |  |  | 19/10/2026 | 20/10/2026 |  |  | 102 |  | 102 |  |  | 17/10/2026 | 19/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903197461-1 KA0235 | BLACK | 90D | S2608WR0901 | 420 | 15/10/2026 | 420 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903197461 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 30/10/2026 |  |  | 420 |  | 420 |  |  | 24/10/2026 | 27/10/2026 |  |  | 420 |  | 420 |  |  | 23/10/2026 | 26/10/2026 |  |  | 420 |  | 420
ADIDAS | 0903197465-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 307 | 15/10/2026 | 307 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903197465 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-10 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 307 |  | 307 |  |  | 2026-07-10 | 2026-08-10 |  |  | 307 |  | 307 |  |  | 2026-06-10 | 2026-07-10 |  |  | 307 |  | 307
ADIDAS | 0903197467-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 478 | 15/10/2026 | 478 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 659018 | PAD+HT SUB PROCESS_V3 | 0903197467 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 478 |  | 478 |  |  | 19/09/2026 | 22/09/2026 |  |  | 478 |  | 478 |  |  | 18/09/2026 | 21/09/2026 |  |  | 478 |  | 478
ADIDAS | 0903197472-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 408 | 15/10/2026 | 408 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197472 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 408 |  | 408 |  |  | 19/10/2026 | 20/10/2026 |  |  | 408 |  | 408 |  |  | 17/10/2026 | 19/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903197475-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 498 | 15/10/2026 | 498 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197475 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 498 |  | 498 |  |  | 2026-05-10 | 2026-08-10 |  |  | 498 |  | 498 |  |  | 2026-03-10 | 2026-07-10 |  |  | 498 |  | 498
ADIDAS | 0903197478-1 KA4331 | BLACK | 90D | S2608MR0902 | 18 | 15/10/2026 | 18 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197478 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 18 |  | 18 |  |  | 22/09/2026 | 24/09/2026 |  |  | 18 |  | 18 |  |  | 21/09/2026 | 23/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903197480-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 530 | 15/10/2026 | 530 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197480 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 530 |  | 530 |  |  | 2026-08-10 | 2026-09-10 |  |  | 530 |  | 530 |  |  | 2026-07-10 | 2026-08-10 |  |  | 530 |  | 530
ADIDAS | 0903197482-1 KA0235 | BLACK | 90D | S2608WR0901 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903197482 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197484-1 KA0246 | BLACK | 90D | S2608WR0902 | 611 | 15/10/2026 | 611 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650010 | PAD+HT SUB PROCESS_V3 | 0903197484 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-12-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 611 |  | 611 |  |  | 2026-08-10 | 2026-09-10 |  |  | 611 |  | 611 |  |  | 2026-07-10 | 2026-08-10 |  |  | 611 |  | 611
ADIDAS | 0903197486-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 544 | 15/10/2026 | 544 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197486 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 544 |  | 544 |  |  | 2026-05-10 | 2026-08-10 |  |  | 544 |  | 544 |  |  | 2026-03-10 | 2026-07-10 |  |  | 544 |  | 544
ADIDAS | 0903197487-1 KA0235 | BLACK | 90D | S2608WR0901 | 106 | 15/10/2026 | 106 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197487 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 30/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 106 |  | 106 |  |  | 27/10/2026 | 29/10/2026 |  |  | 106 |  | 106 |  |  | 26/10/2026 | 28/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903197489-1 KA0246 | BLACK | 90D | S2608WR0902 | 204 | 15/10/2026 | 204 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 834012 | PAD+HT SUB PROCESS_V3 | 0903197489 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 204 |  | 204 |  |  | 2026-03-10 | 2026-06-10 |  |  | 204 |  | 204 |  |  | 2026-02-10 | 2026-05-10 |  |  | 204 |  | 204
ADIDAS | 0903197490-1 KA4331 | BLACK | 90D | S2608MR0902 | 790 | 15/10/2026 | 790 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197490 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 790 |  | 790 |  |  | 22/09/2026 | 24/09/2026 |  |  | 790 |  | 790 |  |  | 21/09/2026 | 23/09/2026 |  |  | 790 |  | 790
ADIDAS | 0903197491-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 118 | 15/10/2026 | 118 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197491 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 23/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 118 |  | 118 |  |  | 19/09/2026 | 22/09/2026 |  |  | 118 |  | 118 |  |  | 18/09/2026 | 21/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903197494-1 KA0246 | BLACK | 90D | S2608WR0902 | 772 | 15/10/2026 | 772 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197494 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 772 |  | 772 |  |  | 2026-03-10 | 2026-06-10 |  |  | 772 |  | 772 |  |  | 2026-02-10 | 2026-05-10 |  |  | 772 |  | 772
ADIDAS | 0903197496-1 KA0235 | BLACK | 90D | S2608WR0901 | 6000 | 15/10/2026 | 6000 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197496 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 23/10/2026 | 2026-03-11 |  |  | 6000 |  | 6000 |  |  | 20/10/2026 | 30/10/2026 |  |  | 6000 |  | 6000 |  |  | 19/10/2026 | 29/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903197498-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 636 | 15/10/2026 | 636 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197498 KA0238 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 14/10/2026 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 636 |  | 636 |  |  | 2026-10-10 | 2026-12-10 |  |  | 636 |  | 636 |  |  | 2026-09-10 | 2026-10-10 |  |  | 636 |  | 636
ADIDAS | 0903197499-1 KA0235 | BLACK | 90D | S2608WR0901 | 1428 | 15/10/2026 | 1428 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197499 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-06-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-06-10 | 2026-08-10 |  |  | 1428 |  | 1428 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1428 |  | 1428 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1428 |  | 1428
ADIDAS | 0903197500-1 KA4331 | BLACK | 90D | S2608MR0902 | 1450 | 15/10/2026 | 1450 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197500 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 30/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 30/09/2026 | 2026-02-10 |  |  | 1450 |  | 1450 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1450 |  | 1450 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1450 |  | 1450
ADIDAS | 0903197502-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 653 | 15/10/2026 | 653 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197502 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 653 |  | 653 |  |  | 19/09/2026 | 22/09/2026 |  |  | 653 |  | 653 |  |  | 18/09/2026 | 21/09/2026 |  |  | 653 |  | 653
ADIDAS | 0903197760-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 600 | 15/10/2026 | 600 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903197760 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 600 |  | 600 |  |  | 14/10/2026 | 17/10/2026 |  |  | 600 |  | 600 |  |  | 13/10/2026 | 16/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903197762-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 778 | 15/10/2026 | 778 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (25/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197762 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 778 |  | 778 |  |  | 14/10/2026 | 17/10/2026 |  |  | 778 |  | 778 |  |  | 13/10/2026 | 16/10/2026 |  |  | 778 |  | 778
ADIDAS | 0903197769-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 1700 | 15/10/2026 | 1700 | SI | SI30/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197769 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-10-10 | 15/10/2026 |  |  | 1700 |  | 1700 |  |  | 2026-07-10 | 2026-12-10 |  |  | 1700 |  | 1700 |  |  | 2026-03-10 | 2026-08-10 |  |  | 1700 |  | 1700
ADIDAS | 0903197775-1 KE9656 | BLACK | 105D | S2608WR0201A | 322 | 15/10/2026 | 322 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 27-Jul. 600000 | PAD+HT SUB PROCESS_V3 | 0903197775 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 322 |  | 322 |  |  | 2026-09-10 | 2026-10-10 |  |  | 322 |  | 322 |  |  | 2026-08-10 | 2026-09-10 |  |  | 322 |  | 322
ADIDAS | 0903203166-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 301 | 26/08/2026 | 301 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203166 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 22/07/2026 | 27/07/2026 | 24/07/2026 | 29/07/2026 | 301 | 301 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 27/07/2026 | 301 | 301
ADIDAS | 0903203167-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 447 | 26/08/2026 | 447 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (19/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203167 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 13/08/2026 | 28/07/2026 | 14/08/2026 | 447 | 447 |  |  |  | 23/07/2026 | 2026-10-08 | 23/07/2026 | 21/08/2026 | 447 | 447
ADIDAS | 0903203168-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 186 | 2026-05-09 | 186 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203168 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 186 | 186 |  |  |  | 2026-03-08 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 186 | 186
ADIDAS | 0903203169-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 425 | 30/09/2026 | 425 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok |  | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903203169 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 425 |  | 425 |  |  | 2026-02-10 | 2026-03-10 |  |  | 425 |  | 425
ADIDAS | 0903203170-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 240 | 15/09/2026 | 240 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203170 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-12-09 | 2026-07-09 | 2026-10-09 | 240 | 240 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 240 | 231 | 9 |  |  | 27/08/2026 | 2026-03-09 | 28/07/2026 | 2026-05-09 | 240 | 230 | 10
ADIDAS | 0903203171-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 347 | 15/10/2026 | 347 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203171 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 347 |  | 347 |  |  | 2026-09-10 | 2026-10-10 |  |  | 347 |  | 347 |  |  | 2026-03-10 | 2026-05-10 |  |  | 347 |  | 347
ADIDAS | 0903205276-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516403 | HT SUB PROCESS_V1 | 0903205276 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 19/09/2026 | 19/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 17/09/2026 | 13/08/2026 | 26/08/2026 | 300 | 300 |  |  |  | 16/09/2026 | 16/09/2026 | 13/08/2026 | 24/08/2026 | 300 | 300
ADIDAS | 0903208394-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 152 | 2026-12-09 | 152 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 10/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516342 | HT SUB PROCESS_V1 | 0903208394 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-01-09 | 2026-10-09 | 2026-04-09 | 2026-10-09 | 152 | 152 |  |  |  | 29/08/2026 | 2026-08-09 | 13/08/2026 | 21/08/2026 | 152 | 152 |  |  |  | 28/08/2026 | 2026-07-09 | 13/08/2026 | 20/08/2026 | 152 | 152
ADIDAS | 0903208396-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 459 | 23/09/2026 | 459 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208396 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 16/09/2026 | 16/09/2026 |  |  | 459 |  | 459 |  |  | 14/09/2026 | 14/09/2026 | 19/08/2026 | 2026-01-09 | 459 | 458 | 1 |  |  | 2026-12-09 | 2026-12-09 | 18/08/2026 | 2026-01-09 | 459 | 458 | 1
ADIDAS | 0903208397-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 494 | 15/10/2026 | 494 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903208397 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 24/10/2026 | 26/10/2026 |  |  | 494 |  | 494 |  |  | 22/10/2026 | 23/10/2026 | 19/08/2026 | 2026-12-09 | 494 | 490 | 4 |  | 4 | 21/10/2026 | 22/10/2026 | 18/08/2026 | 2026-02-09 | 494 | 490 | 4
ADIDAS | 0903208398-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 13 | 2026-02-10 | 13 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208398 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-10 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-02-10 | 2026-02-10 |  |  | 13 |  | 13 |  |  | 30/09/2026 | 30/09/2026 |  |  | 13 |  | 13 |  |  | 29/09/2026 | 29/09/2026 |  |  | 13 |  | 13
ADIDAS | 0903208407-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 302 | 30/09/2026 | 302 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903208407 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | ADIZERO E TEE |  | SS27-YTI | 19/09/2026 | 21/09/2026 |  |  | 302 |  | 302 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-12-09 | 302 | 268 | 34 |  | 10 | 16/09/2026 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 296 | 6
ADIDAS | 0903208408-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 597 | 30/09/2026 | 597 | SA | SA03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903208408 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 28/09/2026 |  |  | 597 |  | 597 |  |  | 25/09/2026 | 25/09/2026 | 2026-08-09 | 13/09/2026 | 597 | 588 | 9 |  |  | 24/09/2026 | 24/09/2026 | 2026-08-09 | 14/09/2026 | 597 | 596 | 1 |  | 3
ADIDAS | 0903208410-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 361 | 2026-07-10 | 361 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516443 | HT SUB PROCESS_V1 | 0903208410 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 361 |  | 361 |  |  | 24/09/2026 | 25/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 356 | 5 |  | 3 | 23/09/2026 | 24/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 358 | 3 |  | 3
ADIDAS | 0903208411-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1107 | 15/10/2026 | 1107 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 678002 | HT SUB PROCESS_V1 | 0903208411 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 1107 |  | 1107 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1107 |  | 1107 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1107 |  | 1107
ADIDAS | 0903208412-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1026 | 15/10/2026 | 1026 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug.. 834012 | HT SUB PROCESS_V1 | 0903208412 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 26/10/2026 |  |  | 1026 |  | 1026 |  |  | 22/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903208413-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 266 | 15/10/2026 | 266 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, body & mesh actual receives 12-Aug. 688010 | HT SUB PROCESS_V1 | 0903208413 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 266 |  | 266 |  |  | 2026-06-10 | 2026-07-10 |  |  | 266 |  | 266 |  |  | 2026-05-10 | 2026-06-10 |  |  | 266 |  | 266
ADIDAS | 0903208414-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 415 | 14/10/2026 | 415 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903208414 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 415 |  | 415 |  |  | 23/09/2026 | 24/09/2026 |  |  | 415 |  | 415 |  |  | 22/09/2026 | 23/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903208419-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903208419 KG8548 | 17/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/08/2026 | ADIZERO E TEE |  | SS27-YTI | 27/08/2026 | 2026-01-09 | 27/08/2026 | 2026-01-09 | 300 | 300 |  |  |  | 24/08/2026 | 29/08/2026 | 2026-12-08 | 21/08/2026 | 300 | 300 |  |  |  | 21/08/2026 | 28/08/2026 | 2026-11-08 | 21/08/2026 | 300 | 300
ADIDAS | 0903208420-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 301 | 2026-09-09 | 301 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208420 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-12-08 | 2026-12-08 | 301 | 301 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-11-08 | 20/08/2026 | 301 | 301
ADIDAS | 0903208421-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208421 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-01-09 | 31/08/2026 | 2026-04-09 | 300 | 300 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-10-08 | 2026-12-08 | 300 | 300 |  |  |  | 26/08/2026 | 28/08/2026 | 2026-08-08 | 2026-11-08 | 300 | 300
ADIDAS | 0903208423-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 244 | 30/09/2026 | 244 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 516342 | HT SUB PROCESS_V1 | 0903208423 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 15/09/2026 | 2026-01-09 | 2026-07-09 | 244 | 239 | 5 |  |  | 27/08/2026 | 2026-12-09 | 2026-10-08 | 2026-12-08 | 244 | 244 |  |  |  | 26/08/2026 | 2026-11-09 | 2026-08-08 | 2026-11-08 | 244 | 244
ADIDAS | 0903208424-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 176 | 2026-07-10 | 176 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 814006 | HT SUB PROCESS_V1 | 0903208424 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 176 |  | 176 |  |  | 13/10/2026 | 14/10/2026 | 2026-12-08 | 26/08/2026 | 176 | 176 |  |  |  | 2026-12-10 | 13/10/2026 | 2026-11-08 | 24/08/2026 | 176 | 176
ADIDAS | 0903208425-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 220 | 2026-07-10 | 220 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 838103 | HT SUB PROCESS_V1 | 0903208425 KG8548 | 17/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 220 |  | 220 |  |  | 13/10/2026 | 14/10/2026 | 2026-11-08 | 2026-01-09 | 220 | 220 |  |  |  | 2026-12-10 | 13/10/2026 | 2026-10-08 | 31/08/2026 | 220 | 220
ADIDAS | 0903208426-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 616 | 15/10/2026 | 616 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 800187 | HT SUB PROCESS_V1 | 0903208426 KG8548 | 17/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 616 |  | 616 |  |  | 2026-09-10 | 2026-12-10 | 14/08/2026 | 2026-02-09 | 616 | 616 |  |  |  | 2026-08-10 | 2026-10-10 | 13/08/2026 | 2026-02-09 | 616 | 616
ADIDAS | 0903208427-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 839055 | HT SUB PROCESS_V1 | 0903208427 KG8548 | 17/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 248 |  | 248 |  |  | 2026-09-10 | 2026-12-10 | 15/08/2026 | 26/08/2026 | 248 | 248 |  |  |  | 2026-08-10 | 2026-10-10 | 14/08/2026 | 24/08/2026 | 248 | 248
ADIDAS | 0903208428-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 2070 | 15/10/2026 | 2070 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 678002 | HT SUB PROCESS_V1 | 0903208428 KG8548 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 29/10/2026 |  |  | 2070 |  | 2070 |  |  | 23/10/2026 | 27/10/2026 |  |  | 2070 |  | 2070 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903208429-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 466 | 23/09/2026 | 466 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 680015 | HT SUB PROCESS_V1 | 0903208429 KG8548 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 15/09/2026 |  |  | 466 |  | 466 |  |  | 2026-12-09 | 2026-12-09 | 2026-12-08 | 21/08/2026 | 466 | 465 | 1 |  |  | 2026-11-09 | 2026-11-09 | 2026-12-08 | 21/08/2026 | 466 | 466
ADIDAS | 0903208430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 648 | 15/10/2026 | 648 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208430 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 648 |  | 648 |  |  | 2026-09-10 | 2026-12-10 | 13/08/2026 | 2026-01-09 | 648 | 647 | 1 |  |  | 2026-08-10 | 2026-10-10 | 13/08/2026 | 2026-03-09 | 648 | 648
ADIDAS | 0903208431-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 424 | 15/10/2026 | 424 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, Body & mesh actual receives 05-Aug. s650010 | HT SUB PROCESS_V1 | 0903208431 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 16/10/2026 |  |  | 424 |  | 424 |  |  | 14/10/2026 | 14/10/2026 | 2026-12-08 | 27/08/2026 | 424 | 424 |  |  |  | 13/10/2026 | 13/10/2026 | 2026-12-08 | 26/08/2026 | 424 | 424
ADIDAS | 0903208432-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 550 | 2026-12-09 | 550 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (PODD Improvement Request). T2 Y.T.I, body & mesh actual receives 18-Aug. 688010 | HT SUB PROCESS_V1 | 0903208432 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/08/2026 | ADIZERO E TEE |  | SS27-YTI | 26/08/2026 | 29/08/2026 | 26/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 21/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 20/08/2026 | 26/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903208433-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 240 | 15/10/2026 | 240 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 05-Aug. 688010 | HT SUB PROCESS_V1 | 0903208433 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 240 |  | 240 |  |  | 2026-09-10 | 2026-12-10 | 15/08/2026 | 22/08/2026 | 240 | 240 |  |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 22/08/2026 | 240 | 240
ADIDAS | 0903208434-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 472 | 14/10/2026 | 472 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208434 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 472 |  | 472 |  |  | 2026-10-10 | 2026-12-10 | 18/08/2026 | 29/08/2026 | 472 | 470 | 2 |  |  | 2026-09-10 | 2026-10-10 | 15/08/2026 | 28/08/2026 | 472 | 472
ADIDAS | 0903208435-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1324 | 15/10/2026 | 1324 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 814006 | HT SUB PROCESS_V1 | 0903208435 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 1324 |  | 1324 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1324 |  | 1324 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1324 |  | 1324
ADIDAS | 0903208440-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 456 | 15/10/2026 | 456 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 678002 | HT SUB PROCESS_V1 | 0903208440 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 456 |  | 456 |  |  | 2026-02-10 | 2026-03-10 | 24/08/2026 | 2026-04-09 | 456 | 456 |  |  |  | 2026-01-10 | 2026-02-10 | 24/08/2026 | 2026-04-09 | 456 | 456
ADIDAS | 0903208441-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 459 | 15/10/2026 | 459 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 07-Aug. 650010 | HT SUB PROCESS_V1 | 0903208441 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-05-10 |  |  | 459 |  | 459 |  |  | 2026-02-10 | 2026-02-10 | 28/08/2026 | 13/09/2026 | 459 | 459 |  |  |  | 2026-01-10 | 2026-01-10 | 26/08/2026 | 2026-03-09 | 459 | 459
ADIDAS | 0903208442-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 518 | 15/10/2026 | 518 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 688010 | HT SUB PROCESS_V1 | 0903208442 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 518 |  | 518 |  |  | 2026-02-10 | 2026-03-10 |  |  | 518 |  | 518 |  |  | 2026-01-10 | 2026-02-10 | 31/08/2026 | 14/09/2026 | 518 | 517 | 1
ADIDAS | 0903208443-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 653 | 14/10/2026 | 653 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 684009 | HT SUB PROCESS_V1 | 0903208443 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 653 |  | 653 |  |  | 30/09/2026 | 2026-02-10 |  |  | 653 |  | 653 |  |  | 29/09/2026 | 2026-01-10 | 28/08/2026 | 2026-03-09 | 653 | 653
ADIDAS | 0903209735-1 KT4840 | ONIX | 90D | S2408MR1600 | 1046 | 14/10/2026 | 1046 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 684009 | HT SUB PROCESS_V1 | 0903209735 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 1046 |  | 1046 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1046 |  | 1046 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1046 |  | 1046
ADIDAS | 0903209736-1 KT4840 | ONIX | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug. 650010 | HT SUB PROCESS_V1 | 0903209736 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903209737-1 KT4840 | ONIX | 90D | S2408MR1600 | 2722 | 15/10/2026 | 2722 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, Body: PI Date 21-Sep (2380 yd). Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug, ETD ?? Waiting fabric. T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug (480 yd). 678002 | HT SUB PROCESS_V1 | 0903209737 KT4840 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 21/10/2026 |  |  | 2722 |  | 2722 |  |  | 14/10/2026 | 19/10/2026 |  |  | 2722 |  | 2722 |  |  | 13/10/2026 | 17/10/2026 |  |  | 2722 |  | 2722
ADIDAS | 0903209739-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 15/09/2026 | 324 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903209739 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-03-09 | 2026-05-09 | 324 | 322 | 2 |  |  | 29/08/2026 | 2026-12-09 | 22/08/2026 | 2026-02-09 | 324 | 324 |  |  |  | 28/08/2026 | 2026-11-09 | 22/08/2026 | 2026-11-09 | 324 | 324
ADIDAS | 0903209741-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 30/09/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209741 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-05-09 | 2026-07-09 | 300 | 206 | 94 |  |  | 29/08/2026 | 2026-12-09 | 24/08/2026 | 2026-03-09 | 300 | 300 |  |  |  | 28/08/2026 | 2026-11-09 | 22/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0903209742-1 IN1156 | BLACK | 90D | S2408MR1600 | 319 | 30/09/2026 | 319 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516443 | HT SUB PROCESS_V1 | 0903209742 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-05-09 | 2026-07-09 | 319 | 312 | 7 |  |  | 29/08/2026 | 2026-12-09 | 24/08/2026 | 2026-03-09 | 319 | 319 |  |  |  | 28/08/2026 | 2026-11-09 | 22/08/2026 | 2026-08-09 | 319 | 319
ADIDAS | 0903209744-1 IN1156 | BLACK | 90D | S2408MR1600 | 3278 | 15/10/2026 | 3278 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209744 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 24/10/2026 |  |  | 3278 |  | 3278 |  |  | 19/10/2026 | 22/10/2026 |  |  | 3278 |  | 3278 |  |  | 17/10/2026 | 21/10/2026 |  |  | 3278 |  | 3278
ADIDAS | 0903209745-1 IN1156 | BLACK | 90D | S2408MR1600 | 145 | 23/09/2026 | 145 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209745 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 19/09/2026 |  |  | 145 |  | 145 |  |  | 16/09/2026 | 17/09/2026 |  |  | 145 |  | 145 |  |  | 15/09/2026 | 16/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903209746-1 IN1156 | BLACK | 90D | S2408MR1600 | 726 | 15/10/2026 | 726 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209746 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 726 |  | 726 |  |  | 26/09/2026 | 29/09/2026 |  |  | 726 |  | 726 |  |  | 25/09/2026 | 28/09/2026 |  |  | 726 |  | 726
ADIDAS | 0903209747-1 IN1156 | BLACK | 90D | S2408MR1600 | 6000 | 15/10/2026 | 6000 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209747 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 28/10/2026 |  |  | 6000 |  | 6000 |  |  | 19/10/2026 | 26/10/2026 |  |  | 6000 |  | 6000 |  |  | 17/10/2026 | 24/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903209748-1 IN1156 | BLACK | 90D | S2408MR1600 | 1095 | 15/10/2026 | 1095 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209748 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-06-10 |  |  | 1095 |  | 1095 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1095 |  | 1095 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1095 |  | 1095
ADIDAS | 0903209749-1 IN1156 | BLACK | 90D | S2408MR1600 | 1353 | 15/10/2026 | 1353 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903209749 IN1156 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 1353 |  | 1353 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1353 |  | 1353 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1353 |  | 1353
ADIDAS | 0903209750-1 IN1156 | BLACK | 90D | S2408MR1600 | 1119 | 15/10/2026 | 1119 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209750 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-03-10 |  |  | 1119 |  | 1119 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1119 |  | 1119 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1119 |  | 1119
ADIDAS | 0903209751-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903209751 IN1156 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903209755-1 IN1157 | WHITE | 90D | S2408MR1600 | 2425 | 15/10/2026 | 2425 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209755 IN1157 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-07-10 |  |  | 2425 |  | 2425 |  |  | 2026-02-10 | 2026-05-10 |  |  | 2425 |  | 2425 |  |  | 2026-01-10 | 2026-03-10 |  |  | 2425 |  | 2425
ADIDAS | 0903209756-1 IN1157 | WHITE | 90D | S2408MR1600 | 310 | 15/10/2026 | 310 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Far Eastern, PI Date 21-Sep, actual recieves 06-Aug (using fabric from Y.T.I.) T2 Y.T.I, Mesh: ETD 10-Jul, actual recieves 06-Aug. 650010 | HT SUB PROCESS_V1 | 0903209756 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 310 |  | 310 |  |  | 29/09/2026 | 30/09/2026 | 2026-10-09 | 2026-12-09 | 310 | 302 | 8 |  | 103 | 28/09/2026 | 29/09/2026 | 2026-03-09 | 2026-08-09 | 310 | 302 | 8
ADIDAS | 0903209757-1 IN1157 | WHITE | 90D | S2408MR1600 | 8000 | 30/09/2026 | 8000 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric (Damco offline). T2 Far Eastern, Body: PI Date 21-Sep (1389 yd). Waiting fabric. T2 Y.T.I, body&mesh ETD 10-Jul, ETA-Kaha 08-Aug (body: 6202yd). 688010 | HT SUB PROCESS_V1 | 0903209757 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 30/09/2026 |  |  | 8000 |  | 8000 |  |  | 18/09/2026 | 28/09/2026 |  |  | 8000 |  | 8000 |  |  | 17/09/2026 | 26/09/2026 |  |  | 8000 |  | 8000
ADIDAS | 0903209758-1 IN1157 | WHITE | 90D | S2408MR1600 | 1268 | 14/10/2026 | 1268 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903209758 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 30/09/2026 |  |  | 1268 |  | 1268 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1268 |  | 1268 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903209760-1 IN1172 | BLACK | 90D | S2408WR1600 | 302 | 15/09/2026 | 302 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516406 | HT SUB PROCESS_V1 | 0903209760 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 2026-07-09 | 302 | 302 |  |  |  | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-09-09 | 302 | 302 |  |  |  | 28/08/2026 | 29/08/2026 | 29/08/2026 | 2026-05-09 | 302 | 302
ADIDAS | 0903209762-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209762 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | ADIZERO E TEE |  | SS27-YTI | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 15/09/2026 | 27/08/2026 | 28/08/2026 | 300 | 300 |  |  |  | 2026-12-09 | 14/09/2026 | 26/08/2026 | 28/08/2026 | 300 | 300
ADIDAS | 0903209764-1 IN1172 | BLACK | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516254 | HT SUB PROCESS_V1 | 0903209764 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 19/10/2026 |  |  | 349 |  | 349 |  |  | 16/10/2026 | 16/10/2026 |  |  | 349 |  | 349 |  |  | 15/10/2026 | 15/10/2026 |  |  | 349 |  | 349
ADIDAS | 0903209765-1 IN1172 | BLACK | 90D | S2408WR1600 | 2646 | 15/10/2026 | 2646 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209765 IN1172 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 23/10/2026 |  |  | 2646 |  | 2646 |  |  | 17/10/2026 | 21/10/2026 |  |  | 2646 |  | 2646 |  |  | 16/10/2026 | 20/10/2026 |  |  | 2646 |  | 2646
ADIDAS | 0903209766-1 IN1172 | BLACK | 90D | S2408WR1600 | 428 | 15/10/2026 | 428 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 672027 | HT SUB PROCESS_V1 | 0903209766 IN1172 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 428 |  | 428 |  |  | 13/10/2026 | 14/10/2026 |  |  | 428 |  | 428 |  |  | 2026-12-10 | 13/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903209767-1 IN1172 | BLACK | 90D | S2408WR1600 | 945 | 15/10/2026 | 945 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 680015 | HT SUB PROCESS_V1 | 0903209767 IN1172 |  | KAHATEX CIJERAH | CHILE | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 20/10/2026 |  |  | 945 |  | 945 |  |  | 16/10/2026 | 17/10/2026 |  |  | 945 |  | 945 |  |  | 15/10/2026 | 16/10/2026 |  |  | 945 |  | 945
ADIDAS | 0903209768-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 15/10/2026 | 760 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209768 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 760 |  | 760 |  |  | 14/10/2026 | 16/10/2026 |  |  | 760 |  | 760 |  |  | 13/10/2026 | 15/10/2026 |  |  | 760 |  | 760
ADIDAS | 0903209769-1 IN1172 | BLACK | 90D | S2408WR1600 | 677 | 14/10/2026 | 677 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT SUB PROCESS_V1 | 0903209769 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 677 |  | 677 |  |  | 14/10/2026 | 16/10/2026 |  |  | 677 |  | 677 |  |  | 13/10/2026 | 15/10/2026 |  |  | 677 |  | 677
ADIDAS | 0903209780-1 KG8547 | ONIX | 90D | S2408WR1600 | 278 | 15/10/2026 | 278 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (Damco offline). 688010 | HT SUB PROCESS_V1 | 0903209780 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 278 |  | 278 |  |  | 17/10/2026 | 19/10/2026 |  |  | 278 |  | 278 |  |  | 16/10/2026 | 17/10/2026 |  |  | 278 |  | 278
ADIDAS | 0903209781-1 KG8547 | ONIX | 90D | S2408WR1600 | 532 | 15/10/2026 | 532 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209781 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 532 |  | 532 |  |  | 17/10/2026 | 19/10/2026 |  |  | 532 |  | 532 |  |  | 16/10/2026 | 17/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903209782-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903209782 KG8547 | 21/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903209783-1 KG8547 | ONIX | 90D | S2408WR1600 | 382 | 15/10/2026 | 382 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 960026 | HT SUB PROCESS_V1 | 0903209783 KG8547 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 13/10/2026 |  |  | 382 |  | 382 |  |  | 2026-10-10 | 2026-10-10 |  |  | 382 |  | 382 |  |  | 2026-09-10 | 2026-09-10 |  |  | 382 |  | 382
ADIDAS | 0903209784-1 KG8547 | ONIX | 90D | S2408WR1600 | 902 | 15/10/2026 | 902 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209784 KG8547 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 902 |  | 902 |  |  | 19/10/2026 | 20/10/2026 |  |  | 902 |  | 902 |  |  | 17/10/2026 | 19/10/2026 |  |  | 902 |  | 902
ADIDAS | 0903209785-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 104 | 30/09/2026 | 104 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903209785 KX9838 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 28/09/2026 | 28/09/2026 |  |  | 104 |  | 104 |  |  | 25/09/2026 | 25/09/2026 | 21/08/2026 | 27/08/2026 | 104 | 104 |  |  |  | 24/09/2026 | 24/09/2026 | 15/08/2026 | 26/08/2026 | 104 | 104
ADIDAS | 0903209786-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 3723 | 31/08/2026 | 3723 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209786 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 14/08/2026 | 27/08/2026 | 19/08/2026 | 27/08/2026 | 3723 | 3723 |  |  |  | 2026-12-08 | 24/08/2026 | 18/08/2026 | 26/08/2026 | 3723 | 3723 |  |  |  | 2026-11-08 | 21/08/2026 | 18/08/2026 | 27/08/2026 | 3723 | 3723
ADIDAS | 0903209787-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 512 | 15/10/2026 | 512 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903209787 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 512 |  | 512 |  |  | 23/10/2026 | 24/10/2026 | 21/08/2026 | 31/08/2026 | 512 | 512 |  |  |  | 22/10/2026 | 23/10/2026 | 21/08/2026 | 29/08/2026 | 512 | 512
ADIDAS | 0903209788-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 628 | 15/10/2026 | 628 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903209788 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-12-10 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 2026-12-10 | 2026-12-10 |  |  | 628 |  | 628 |  |  | 2026-09-10 | 2026-09-10 | 21/08/2026 | 31/08/2026 | 628 | 628 |  |  |  | 2026-08-10 | 2026-08-10 | 21/08/2026 | 29/08/2026 | 628 | 628
ADIDAS | 0903209789-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 80 | 31/08/2026 | 80 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209789 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 26/08/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 26/08/2026 | 27/08/2026 | 26/08/2026 | 27/08/2026 | 80 | 80 |  |  |  | 21/08/2026 | 24/08/2026 | 22/08/2026 | 22/08/2026 | 80 | 80 |  |  |  | 20/08/2026 | 21/08/2026 | 22/08/2026 | 22/08/2026 | 80 | 80
ADIDAS | 0903209799-1 KG8547 | ONIX | 90D | S2408WR1600 | 1750 | 30/09/2026 | 1750 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 08-Aug. 672027 | HT SUB PROCESS_V1 | 0903209799 KG8547 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 19/09/2026 |  |  | 1750 |  | 1750 |  |  | 15/09/2026 | 17/09/2026 | 2026-09-09 | 2026-11-09 | 1750 | 1495 | 255 |  |  | 14/09/2026 | 16/09/2026 | 2026-09-09 | 2026-10-09 | 1750 | 1495 | 255
ADIDAS | 0903209801-1 IN1173 | WHITE | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516254 | HT SUB PROCESS_V1 | 0903209801 IN1173 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 349 |  | 349 |  |  | 2026-06-10 | 2026-07-10 | 14/08/2026 | 2026-01-09 | 349 | 349 |  |  |  | 2026-05-10 | 2026-06-10 | 13/08/2026 | 31/08/2026 | 349 | 349
ADIDAS | 0903209802-1 IN1173 | WHITE | 90D | S2408WR1600 | 1288 | 15/10/2026 | 1288 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 678002 | HT SUB PROCESS_V1 | 0903209802 IN1173 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 1288 |  | 1288 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 2026-04-09 | 1288 | 1288 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 31/08/2026 | 1288 | 1288
ADIDAS | 0903209803-1 IN1173 | WHITE | 90D | S2408WR1600 | 550 | 14/10/2026 | 550 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 680015 | HT SUB PROCESS_V1 | 0903209803 IN1173 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 550 |  | 550 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903209804-1 IN1173 | WHITE | 90D | S2408WR1600 | 1445 | 15/10/2026 | 1445 | SI | SI07/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 659018 | HT SUB PROCESS_V1 | 0903209804 IN1173 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 29/09/2026 |  |  | 1445 |  | 1445 |  |  | 24/09/2026 | 26/09/2026 | 19/08/2026 | 2026-02-09 | 1445 | 1445 |  |  |  | 23/09/2026 | 25/09/2026 | 15/08/2026 | 2026-02-09 | 1445 | 1445
ADIDAS | 0903209805-1 IN1173 | WHITE | 90D | S2408WR1600 | 555 | 15/10/2026 | 555 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209805 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 555 |  | 555 |  |  | 29/09/2026 | 30/09/2026 |  |  | 555 |  | 555 |  |  | 28/09/2026 | 29/09/2026 |  |  | 555 |  | 555
ADIDAS | 0903209806-1 IN1173 | WHITE | 90D | S2408WR1600 | 892 | 14/10/2026 | 892 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 684009 | HT SUB PROCESS_V1 | 0903209806 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 892 |  | 892 |  |  | 2026-07-10 | 2026-08-10 | 19/08/2026 | 27/08/2026 | 892 | 890 | 2 |  |  | 2026-06-10 | 2026-07-10 | 15/08/2026 | 27/08/2026 | 892 | 890 | 2
ADIDAS | 0903209808-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 1211 | 30/09/2026 | 1211 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903209808 IT1462 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 24/09/2026 |  |  | 1211 |  | 1211 |  |  | 19/09/2026 | 22/09/2026 | 2026-07-09 | 2026-11-09 | 1211 | 1175 | 36 |  |  | 18/09/2026 | 21/09/2026 | 2026-07-09 | 14/09/2026 | 1211 | 1187 | 24
ADIDAS | 0903209809-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 451 | 15/10/2026 | 451 | SI | SI07/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903209809 IT1462 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 451 |  | 451 |  |  | 13/10/2026 | 14/10/2026 | 2026-09-09 | 2026-11-09 | 451 | 435 | 16 |  |  | 2026-12-10 | 13/10/2026 | 2026-09-09 | 14/09/2026 | 451 | 439 | 12
ADIDAS | 0903245395-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903245395 KA4331 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903245423-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 680015 | HT SUB PROCESS_V1 | 0903245423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0903247791-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 501 | 15/10/2026 | 501 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247791 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 30/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 30/09/2026 | 2026-01-10 |  |  | 501 |  | 501 |  |  | 26/09/2026 | 28/09/2026 |  |  | 501 |  | 501
ADIDAS | 0903247818-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 118 | 15/10/2026 | 118 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 630001 | PRINT L1 SUB PROCESS_V3 | 0903247818 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 118 |  | 118 |  |  | 2026-02-10 | 2026-03-10 |  |  | 118 |  | 118
ADIDAS | 0903247851-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247851 LG8052 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 14/10/2026 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 0903247873-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247873 LI7657 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-03-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903247906-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 630001 | PRINT L3 SUB PROCESS_V3 | 0903247906 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 100 |  | 100 |  |  | 23/09/2026 | 24/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903247928-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 210 | 15/10/2026 | 210 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247928 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 210 |  | 210 |  |  | 29/09/2026 | 2026-01-10 |  |  | 210 |  | 210
ADIDAS | 0903247950-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 377 | 15/10/2026 | 377 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247950 LI7659 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 377 |  | 377 |  |  | 2026-02-10 | 2026-02-10 |  |  | 377 |  | 377
ADIDAS | 0903247975-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 15/10/2026 | 65 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247975 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-10 | 2026-06-10 |  |  | 65 |  | 65 |  |  | 2026-03-10 | 2026-03-10 |  |  | 65 |  | 65 |  |  | 2026-02-10 | 2026-02-10 |  |  | 65 |  | 65
ADIDAS | 0903247991-1 IN1159 | BLACK | 90D | S2408MR1601 | 15 | 15/10/2026 | 15 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247991 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-10 | 2026-06-10 |  |  | 15 |  | 15 |  |  | 2026-03-10 | 2026-03-10 |  |  | 15 |  | 15 |  |  | 2026-02-10 | 2026-02-10 |  |  | 15 |  | 15
ADIDAS | 0903248016-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 14 | 30/09/2026 | 14 | AN | AN10/07/2026 | G1H | JACKET | G1 | (10/08/2026) | ok | 29/09: ex-fty. T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248016 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 14 |  | 14 |  |  | 18/09/2026 | 19/09/2026 |  |  | 14 |  | 14
ADIDAS | 0903248122-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4486 | 31/08/2026 | 4486 | SA | SA10/07/2026 | G3A,G3G | SWEATSHIRT | G3 | ok | ok | 29/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248122 IB8688 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | ESS HDY |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 28/08/2026 | 4486 | 4486 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 4486 | 4486
ADIDAS | 0903248578-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 485 | 15/10/2026 | 485 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903248578 KV7863 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-10-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 485 |  | 485 |  |  | 2026-06-11 | 2026-07-11 |  |  | 485 |  | 485
ADIDAS | 0903248979-1 IN1160 | WHITE | 90D | S2408MR1601 | 1173 | 15/10/2026 | 1173 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903248979 IN1160 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-08-10 | 2026-12-10 |  |  | 1173 |  | 1173
ADIDAS | 0903249675-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249675 JE6338 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | M 3S FT FZ HD |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 1150 |  | 1150 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1150 |  | 1150
ADIDAS | 0903249702-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516442 | PAD+HT SUB PROCESS_V3 | 0903249702 IT3474 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 30/10/2026 | 2026-02-11 |  |  | 1795 |  | 1795 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1795 |  | 1795 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249724-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516318 | PAD+HT SUB PROCESS_V3 | 0903249724 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903249752-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249752 JD1877 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 1610 |  | 1610 |  |  | 2026-03-10 | 2026-07-10 |  |  | 1610 |  | 1610
ADIDAS | 0903249777-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249777 JE6341 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 432 |  | 432 |  |  | 28/09/2026 | 2026-01-10 |  |  | 432 |  | 432
ADIDAS | 0903249802-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 600 | 15/10/2026 | 600 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249802 JE6338 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 600 |  | 600 |  |  | 2026-06-10 | 2026-07-10 |  |  | 600 |  | 600
ADIDAS | 0903249832-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 299 | 15/10/2026 | 299 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249832 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | M SL WV PT 2 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 299 |  | 299 |  |  | 23/10/2026 | 24/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903249858-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249858 JM1776 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | M SL WV PT 2 |  | SS27 | 28/10/2026 | 30/10/2026 |  |  | 575 |  | 575 |  |  | 24/10/2026 | 27/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903249889-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516205 | PAD+HT SUB PROCESS_V3 | 0903249889 IT3474 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-11 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 2026-02-11 | 2026-05-11 |  |  | 1795 |  | 1795 |  |  | 29/10/2026 | 2026-02-11 |  |  | 1795 |  | 1795 |  |  | 28/10/2026 | 31/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249911-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4300 | 31/08/2026 | 4300 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903249911 IB8688 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 19/08/2026 | 29/08/2026 | 4300 | 4300 |  |  |  | 18/08/2026 | 27/08/2026 | 15/08/2026 | 31/08/2026 | 4300 | 4291 | 9
ADIDAS | 0903249935-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4300 | 31/08/2026 | 4300 | SA | SA10/07/2026 | G3A,G3G | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903249935 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 19/08/2026 | ESS HDY |  | SS27 | 19/08/2026 | 31/08/2026 | 21/08/2026 | 29/08/2026 | 4300 | 4300 |  |  |  | 13/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 4300 | 4300
ADIDAS | 0903249963-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/10/2026 | 300 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249963 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 15/10/2026 | 17/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903250004-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 23/09/2026 | 300 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903250004 JG8642 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 300 | 162 | 138
ADIDAS | 0903250015-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250015 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/10/2026 | M SL WV PT 2 |  | SS27 | 28/10/2026 | 30/10/2026 |  |  | 575 |  | 575 |  |  | 24/10/2026 | 27/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903250038-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 326 | 2026-12-09 | 326 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250038 KA0544 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 326 | 326 |  |  |  | 31/08/2026 | 2026-09-09 | 31/08/2026 | 31/08/2026 | 326 | 326
ADIDAS | 0903250043-1 HK7309 | BLACK | 45D | F2225M402 | 1200 | 26/08/2026 | 1200 | SA | SA10/07/2026 | G1N | SWEATSHIRT | G1 | ok |  | 24/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903250043 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 13/08/2026 | ESS HDY |  | SS27 | 13/08/2026 | 21/08/2026 | 13/08/2026 | 21/08/2026 | 1200 | 1200 |  |  |  | 2026-10-08 | 18/08/2026 | 2026-12-08 | 22/08/2026 | 1200 | 1200
ADIDAS | 0903250069-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 304 | 2026-12-09 | 304 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250069 KA0546 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-03-09 | 304 | 304
ADIDAS | 0903250091-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 840 | 15/10/2026 | 840 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250091 JD1877 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 840 |  | 840 |  |  | 24/09/2026 | 26/09/2026 |  |  | 840 |  | 840
ADIDAS | 0903250102-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 378 | 15/10/2026 | 378 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250102 JM1775 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 378 |  | 378 |  |  | 15/10/2026 | 17/10/2026 |  |  | 378 |  | 378
ADIDAS | 0903250117-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250117 JE6341 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 828 |  | 828 |  |  | 28/09/2026 | 2026-01-10 |  |  | 828 |  | 828
ADIDAS | 0903250128-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250128 JM1776 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 27/10/2026 | M SL WV PT 2 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 342 |  | 342 |  |  | 23/10/2026 | 24/10/2026 |  |  | 342 |  | 342
ADIDAS | 0903250411-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 116 | 15/10/2026 | 116 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903250411 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 116 |  | 116 |  |  | 28/09/2026 | 28/09/2026 |  |  | 116 |  | 116
ADIDAS | 0903250503-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903250503 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 24/09/2026 | 25/09/2026 |  |  | 107 |  | 107 |  |  | 21/09/2026 | 22/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903250530-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250530 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 107 |  | 107 |  |  | 2026-05-10 | 2026-06-10 |  |  | 107 |  | 107
ADIDAS | 0903250563-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 449 | 15/10/2026 | 449 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (03/08/2026) | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250563 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 449 |  | 449 |  |  | 19/09/2026 | 21/09/2026 |  |  | 449 |  | 449
ADIDAS | 0903250949-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L1 SUB PROCESS_V3 | 0903250949 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 22/09/2026 | 22/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250973-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903250973 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 100 |  | 100 |  |  | 23/09/2026 | 24/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250977-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250977 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 372 |  | 372 |  |  | 21/09/2026 | 23/09/2026 |  |  | 372 |  | 372
ADIDAS | 0903251020-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251020 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | W 3S FT FZ HD |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 230 |  | 230 |  |  | 30/10/2026 | 31/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903251026-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251026 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | MINI EMB T |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 590 |  | 590 |  |  | 23/09/2026 | 24/09/2026 |  |  | 590 |  | 590 |  |  | 21/09/2026 | 22/09/2026 |  |  | 590 |  | 590
ADIDAS | 0903251047-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903251047 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 396 |  | 396 |  |  | 23/09/2026 | 25/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903251051-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G3D | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 848012 | PAD+HT SUB PROCESS_V3 | 0903251051 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-10 | RUN IT SHORT BLACK |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-03-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903251082-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1720 | 15/10/2026 | 1720 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903251082 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1720 |  | 1720 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1720 |  | 1720
ADIDAS | 0903251111-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1136 | 15/10/2026 | 1136 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251111 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | W 3S FT CF PT |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 1136 |  | 1136 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1136 |  | 1136
ADIDAS | 0903251135-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251135 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1610 |  | 1610 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1610 |  | 1610
ADIDAS | 0903251695-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 714 | 15/10/2026 | 714 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251695 JE0052 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-04-11 | W 3S FT FZ HD |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 714 |  | 714 |  |  | 31/10/2026 | 2026-02-11 |  |  | 714 |  | 714
ADIDAS | 0903251728-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251728 KA5089 | 26/08/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 26/09/2026 | MINI EMB T |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 602 |  | 602 |  |  | 23/09/2026 | 24/09/2026 |  |  | 602 |  | 602 |  |  | 21/09/2026 | 22/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903251751-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 124 | 15/10/2026 | 124 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903251751 IU0217 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/09/2026 | IN RANGE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 124 |  | 124 |  |  | 19/09/2026 | 21/09/2026 | 2026-10-09 | 2026-11-09 | 124 | 20 | 104
ADIDAS | 0903251769-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 890 | 15/10/2026 | 890 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251769 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/10/2026 | W 3S FT FZ HD |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 890 |  | 890 |  |  | 28/10/2026 | 30/10/2026 |  |  | 890 |  | 890
ADIDAS | 0903251842-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1686 | 15/10/2026 | 1686 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251842 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 1686 |  | 1686 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1686 |  | 1686
ADIDAS | 0903251958-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 469 | 15/10/2026 | 469 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 826010 | PRINT L2+PAD SUB PROCESS_V3 | 0903251958 LC8884 |  | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 469 |  | 469 |  |  | 2026-12-10 | 13/10/2026 | 26/08/2026 | 2026-03-09 | 469 | 314 | 155
ADIDAS | 0903252061-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 481 | 15/10/2026 | 481 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252061 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 481 |  | 481 |  |  | 2026-05-11 | 2026-06-11 |  |  | 481 |  | 481
ADIDAS | 0903252085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 354 | 15/10/2026 | 354 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252085 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 354 |  | 354 |  |  | 2026-06-11 | 2026-07-11 |  |  | 354 |  | 354
ADIDAS | 0903252116-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 128 | 15/10/2026 | 128 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903252116 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M ADI RETRO T WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 128 |  | 128 |  |  | 2026-06-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 128 | 110 | 18
ADIDAS | 0903252150-1 HK7309 | BLACK | 45D | F2225M402 | 4488 | 28/08/2026 | 4488 | SA | SA10/07/2026 | G1E,G1F,G1N,G1P | SWEATSHIRT | G1 | ok | ok | 28/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo-capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903252150 HK7309 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/08/2026 | ESS HDY |  | SS27 | 13/08/2026 | 28/08/2026 | 18/08/2026 | 28/08/2026 | 4488 | 4488 |  |  |  | 2026-10-08 | 24/08/2026 | 13/08/2026 | 2026-09-09 | 4488 | 4488
ADIDAS | 0903252175-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252175 JM1775 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | M SL WV PT 2 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 576 |  | 576 |  |  | 19/10/2026 | 20/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903252182-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 360 | 15/10/2026 | 360 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903252182 KX8875 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 360 |  | 360 |  |  | 2026-06-10 | 2026-06-10 |  |  | 360 |  | 360
ADIDAS | 0903252230-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 826010 | HT SUB PROCESS_V1 | 0903252230 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | ADIZERO E TEE |  | SS27-YTI | 23/09/2026 | 24/09/2026 |  |  | 200 |  | 200 |  |  | 21/09/2026 | 22/09/2026 |  |  | 200 |  | 200 |  |  | 19/09/2026 | 21/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903252254-1 IN1156 | BLACK | 90D | S2408MR1600 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903252254 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 590 |  | 590 |  |  | 29/09/2026 | 30/09/2026 |  |  | 590 |  | 590 |  |  | 28/09/2026 | 29/09/2026 |  |  | 590 |  | 590
ADIDAS | 0903252439-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252439 LI7657 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-03-10 |  |  | 101 |  | 101 |  |  | 30/09/2026 | 30/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903252473-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252473 LI7658 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 117 |  | 117 |  |  | 28/09/2026 | 29/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903252503-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252503 LI7656 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 25/09/2026 | 26/09/2026 |  |  | 101 |  | 101 |  |  | 22/09/2026 | 23/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903252539-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252539 LI7659 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 117 |  | 117 |  |  | 2026-02-10 | 2026-02-10 |  |  | 117 |  | 117
ADIDAS | 0903252570-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 230 | 2026-12-09 | 230 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 1st Art (TC 10 pcs) 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903252570 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-04-09 | 2026-09-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-10-09 | 230 | 230
ADIDAS | 0903252644-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/10/2026 | 140 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252644 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 27/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 140 |  | 140 |  |  | 23/10/2026 | 24/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903253096-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 201 | 15/10/2026 | 201 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903253096 KV0458 |  | KAHATEX CIJERAH | THAILAND | SEA | 30/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 201 |  | 201 |  |  | 26/09/2026 | 28/09/2026 |  |  | 201 |  | 201
ADIDAS | 0903253164-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1421 | 15/10/2026 | 1421 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253164 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 1421 |  | 1421 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1421 |  | 1421
ADIDAS | 0903253174-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253174 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | M SL WV PT 2 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 288 |  | 288 |  |  | 23/10/2026 | 24/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903253193-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1909 | 15/10/2026 | 1909 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903253193 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-08-10 | 2026-12-10 |  |  | 1909 |  | 1909 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1909 |  | 1909
ADIDAS | 0903253213-1 HL2236 | BLACK/WHITE | 45D | F224CSIM430 | 14004 | 28/08/2026 | 14004 | AT | AT10/07/2026 | G2E,G2Q,G2T,G3B,G3E | PANTS | G2,G3 | ok | ok | 28/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253213 HL2236 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | IN RANGE |  | SS27 | 14/08/2026 | 28/08/2026 | 2026-12-08 | 28/08/2026 | 14004 | 14004 |  |  |  | 2026-11-08 | 24/08/2026 | 2026-10-08 | 29/08/2026 | 14004 | 14004
ADIDAS | 0903253229-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253229 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 30/10/2026 | M SL WV PT 2 |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 600 |  | 600 |  |  | 27/10/2026 | 29/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253235-1 H12215 | DARK GREY HEATHER/BLACK | 45D | F213CSIM105FL | 1258 | 26/08/2026 | 1258 | AT | AT10/07/2026 | G2T | SWEATSHIRT | G2 | ok |  | 24/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253235 H12215 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | M FEELCOZY HD |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 21/08/2026 | 1258 | 1258 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-11-08 | 21/08/2026 | 1258 | 1258
ADIDAS | 0903253258-1 HL2243 | DARK GREY HEATHER/BLACK | 45D | F224CSIM430 | 11444 | 31/08/2026 | 11444 | AT | AT10/07/2026 | G3F,G3J | PANTS | G3 | ok | ok | 29/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253258 HL2243 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | IN RANGE |  | SS27 | 14/08/2026 | 29/08/2026 | 14/08/2026 | 29/08/2026 | 11444 | 11444 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-08-08 | 2026-07-09 | 11444 | 11444
ADIDAS | 0903253259-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 650 | 15/10/2026 | 650 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253259 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 650 |  | 650 |  |  | 2026-07-10 | 2026-09-10 |  |  | 650 |  | 650
ADIDAS | 0903253275-1 HL2236 | BLACK/WHITE | 45D | F224CSIM430 | 15000 | 31/08/2026 | 15000 | AT | AT10/07/2026 | G3B,G3C,G3E,G3F | PANTS | G3 | ok | ok | 29/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253275 HL2236 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | IN RANGE |  | SS27 | 21/08/2026 | 31/08/2026 | 19/08/2026 | 29/08/2026 | 15000 | 15000 |  |  |  | 18/08/2026 | 27/08/2026 | 13/08/2026 | 29/08/2026 | 15000 | 15000
ADIDAS | 0903253286-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253286 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 29/10/2026 | W 3S FT FZ HD |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 600 |  | 600 |  |  | 26/10/2026 | 27/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253287-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 200 | 15/10/2026 | 200 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903253287 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 15/10/2026 |  |  | 200 |  | 200 |  |  | 2026-12-10 | 2026-12-10 |  |  | 200 |  | 200 |  |  | 2026-10-10 | 2026-10-10 |  |  | 200 |  | 200
ADIDAS | 0903253304-1 H12215 | DARK GREY HEATHER/BLACK | 45D | F213CSIM105FL | 15000 | 28/08/2026 | 15000 | AT | AT10/07/2026 | G2P,G2S,G2T | SWEATSHIRT | G2 | ok | ok | 28/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253304 H12215 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | M FEELCOZY HD |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 15000 | 15000 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-11-08 | 28/08/2026 | 15000 | 15000
ADIDAS | 0903253312-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 374 | 15/10/2026 | 374 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253312 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 374 |  | 374 |  |  | 23/10/2026 | 24/10/2026 |  |  | 374 |  | 374
ADIDAS | 0903253327-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253327 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 23/10/2026 | M SL WV PT 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 600 |  | 600 |  |  | 20/10/2026 | 21/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253337-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 105 | 15/10/2026 | 105 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903253337 KX0123 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-10 | M ADI RETRO T WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 105 |  | 105 |  |  | 2026-06-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 105 | 91 | 14
ADIDAS | 0903253341-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 582 | 15/10/2026 | 582 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253341 JE6341 |  | KAHATEX CIJERAH | UKRAINE | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 582 |  | 582 |  |  | 21/09/2026 | 23/09/2026 |  |  | 582 |  | 582
ADIDAS | 0903253374-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253374 JD5302 |  | KAHATEX CIJERAH | UKRAINE | SEA | 24/10/2026 | W 3S FT CF PT |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 1000 |  | 1000 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903253396-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253396 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 558 |  | 558 |  |  | 24/09/2026 | 24/09/2026 |  |  | 558 |  | 558
ADIDAS | 0903253447-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512110 | PRINT L2+HT SUB PROCESS_V3 | 0903253447 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-10-10 |  |  | 100 |  | 100
ADIDAS | 0903253455-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 191 | 15/10/2026 | 191 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903253455 LD0277 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 23/09/2026 | 23/09/2026 |  |  | 191 |  | 191 |  |  | 19/09/2026 | 19/09/2026 |  |  | 191 |  | 191 |  |  | 18/09/2026 | 18/09/2026 |  |  | 191 |  | 191
ADIDAS | 0903253532-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 20 | 15/10/2026 | 20 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903253532 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 20 |  | 20 |  |  | 2026-10-10 | 2026-12-10 |  |  | 20 |  | 20 |  |  | 2026-09-10 | 2026-10-10 |  |  | 20 |  | 20
ADIDAS | 0903253551-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 637 | 2026-07-10 | 637 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253551 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 637 |  | 637 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-09 | 2026-09-09 | 637 | 525 | 112
ADIDAS | 0903253557-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 268 | 15/10/2026 | 268 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253557 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-06-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 268 |  | 268 |  |  | 2026-02-10 | 2026-05-10 |  |  | 268 |  | 268
ADIDAS | 0903253577-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 347 | 2026-07-10 | 347 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253577 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 347 |  | 347 |  |  | 21/09/2026 | 22/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 192 | 155
ADIDAS | 0903253610-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 351 | 30/09/2026 | 351 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253610 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 351 |  | 351 |  |  | 16/09/2026 | 17/09/2026 | 28/08/2026 | 2026-04-09 | 351 | 294 | 57
ADIDAS | 0903253694-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903253694 JC8238 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903253810-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903253810 KX8875 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 368 |  | 368 |  |  | 2026-06-10 | 2026-06-10 |  |  | 368 |  | 368
ADIDAS | 0903253870-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 936 | 15/10/2026 | 936 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516204 | PAD+HT SUB PROCESS_V3 | 0903253870 IT3474 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 936 |  | 936 |  |  | 26/10/2026 | 27/10/2026 |  |  | 936 |  | 936 |  |  | 24/10/2026 | 26/10/2026 |  |  | 936 |  | 936
ADIDAS | 0903253904-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253904 JE6338 |  | KAHATEX CIJERAH | SPAIN | SEA | 15/10/2026 | M 3S FT FZ HD |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 1150 |  | 1150 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1150 |  | 1150
ADIDAS | 0903253938-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4737 | 31/08/2026 | 4737 | SA | SA10/07/2026 | G1F,G1N,G1P,G3A,G3D | SWEATSHIRT | G1,G3 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253938 HK7311 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 27/08/2026 | ESS HDY |  | SS27 | 27/08/2026 | 31/08/2026 | 26/08/2026 | 31/08/2026 | 4737 | 4737 |  |  |  | 21/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 4737 | 4737
ADIDAS | 0903253967-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253967 JE6341 |  | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 828 |  | 828 |  |  | 23/09/2026 | 25/09/2026 |  |  | 828 |  | 828
ADIDAS | 0903253995-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253995 JD1877 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1610 |  | 1610 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1610 |  | 1610
ADIDAS | 0903254049-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254049 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | W 3S FT FZ HD |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 230 |  | 230 |  |  | 26/10/2026 | 26/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903254053-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 116 | 15/10/2026 | 116 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903254053 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 15/10/2026 |  |  | 116 |  | 116 |  |  | 2026-12-10 | 2026-12-10 |  |  | 116 |  | 116 |  |  | 2026-10-10 | 2026-10-10 |  |  | 116 |  | 116
ADIDAS | 0903254056-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254056 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 576 |  | 576 |  |  | 17/10/2026 | 19/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903254089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903254089 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 396 |  | 396 |  |  | 30/09/2026 | 2026-02-10 |  |  | 396 |  | 396
ADIDAS | 0903254113-1 HK7309 | BLACK | 45D | F2225M402 | 4302 | 31/08/2026 | 4302 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254113 HK7309 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 20/08/2026 | 31/08/2026 | 4302 | 4302 |  |  |  | 18/08/2026 | 27/08/2026 | 18/08/2026 | 2026-02-09 | 4302 | 4302
ADIDAS | 0903254136-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4583 | 31/08/2026 | 4583 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 29/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254136 HK7311 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 28/08/2026 | 4583 | 4583 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 31/08/2026 | 4583 | 4583
ADIDAS | 0903254175-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1182 | 15/10/2026 | 1182 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877).. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254175 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-11 | 14/11/2026 |  |  | 1182 |  | 1182 |  |  | 2026-09-11 | 2026-11-11 |  |  | 1182 |  | 1182
ADIDAS | 0903254325-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903254325 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 24/09/2026 | 25/09/2026 |  |  | 340 |  | 340 |  |  | 21/09/2026 | 22/09/2026 |  |  | 340 |  | 340
ADIDAS | 0903254356-1 KZ3049 | BLACK | 90D | S2762LHMEDR109W | 330 | 15/10/2026 | 330 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903254356 KZ3049 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER GR GFCTP W BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-03-10 |  |  | 330 |  | 330
ADIDAS | 0903254368-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254368 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | J FOOTBALL T |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 | 2026-11-09 | 2026-11-09 | 100 | 8 | 92
ADIDAS | 0903254387-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254387 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 372 |  | 372 |  |  | 2026-05-10 | 2026-06-10 |  |  | 372 |  | 372
ADIDAS | 0903254402-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 130 | 15/10/2026 | 130 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903254402 KV0458 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 30/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 130 |  | 130 |  |  | 26/09/2026 | 28/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903254581-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 457 | 15/10/2026 | 457 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254581 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 457 |  | 457 |  |  | 28/09/2026 | 29/09/2026 |  |  | 457 |  | 457
ADIDAS | 0903254614-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 380 | 15/10/2026 | 380 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L3 SUB PROCESS_V3 | 0903254614 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 380 |  | 380 |  |  | 29/09/2026 | 30/09/2026 |  |  | 380 |  | 380
ADIDAS | 0903254741-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903254741 JD1881 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-12-10 | M 3S FT TC PT |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 1203 |  | 1203 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1203 |  | 1203
ADIDAS | 0903254860-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 229 | 15/10/2026 | 229 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254860 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M ADI RETRO T BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 229 |  | 229 |  |  | 2026-06-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 229 | 201 | 28
ADIDAS | 0903254861-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 312 | 15/10/2026 | 312 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254861 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/10/2026 | W 3S FT FZ HD |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 312 |  | 312 |  |  | 26/10/2026 | 26/10/2026 |  |  | 312 |  | 312
ADIDAS | 0903254872-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903254872 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 558 |  | 558 |  |  | 30/09/2026 | 2026-02-10 |  |  | 558 |  | 558
ADIDAS | 0903254887-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 108 | 15/10/2026 | 108 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254887 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 30/09/2026 | 2026-01-10 |  |  | 108 |  | 108 |  |  | 26/09/2026 | 28/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903254914-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 1750 | 15/10/2026 | 1750 | AN | AN10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 09-Jun, ETD 10-Aug, ETA-Kaha 21-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254914 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 28/10/2026 |  |  | 1750 |  | 1750 |  |  | 19/10/2026 | 24/10/2026 |  |  | 1750 |  | 1750
ADIDAS | 0903254921-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254921 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 288 |  | 288 |  |  | 15/10/2026 | 17/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903254928-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2400 | 31/08/2026 | 2400 | SI | SI10/07/2026 | G2G,G2H,G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903254928 KD4066 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | M BLANK TEE BLACK |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 31/08/2026 | 2400 | 2400 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 31/08/2026 | 2400 | 2396 | 4
ADIDAS | 0903254980-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 619 | 15/10/2026 | 619 | SI | SI10/07/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254980 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 619 |  | 619 |  |  | 13/10/2026 | 15/10/2026 |  |  | 619 |  | 619
ADIDAS | 0903255009-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 389 | 15/10/2026 | 389 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255009 LG8051 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 389 |  | 389 |  |  | 22/09/2026 | 22/09/2026 |  |  | 389 |  | 389
ADIDAS | 0903255022-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 135 | 15/10/2026 | 135 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903255022 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 135 |  | 135 |  |  | 2026-07-10 | 2026-09-10 |  |  | 135 |  | 135
ADIDAS | 0903255023-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1203 | 2026-09-09 | 1203 | SA | SA10/07/2026 | G3G | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255023 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 29/08/2026 | 2026-05-09 | 1203 | 1203 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-04-09 | 1203 | 1203
ADIDAS | 0903255038-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255038 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 169 |  | 169 |  |  | 2026-01-10 | 2026-02-10 |  |  | 169 |  | 169
ADIDAS | 0903255050-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255050 IZ0443 | 2026-11-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-02-09 | 2026-09-09 | 276 | 276
ADIDAS | 0903255078-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 161 | 15/10/2026 | 161 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903255078 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 161 |  | 161 |  |  | 2026-12-10 | 13/10/2026 |  |  | 161 |  | 161 |  |  | 2026-10-10 | 2026-12-10 |  |  | 161 |  | 161
ADIDAS | 0903255103-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 276 | 2026-12-09 | 276 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255103 KA0546 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 276 | 276 |  |  |  | 28/08/2026 | 2026-09-09 | 13/08/2026 | 2026-03-09 | 276 | 276
ADIDAS | 0903255118-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 344 | 15/10/2026 | 344 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255118 LG8052 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 344 |  | 344 |  |  | 2026-10-10 | 2026-12-10 |  |  | 344 |  | 344
ADIDAS | 0903255151-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903255151 LI7657 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903255192-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 492 | 15/10/2026 | 492 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | T2 Formosa, PI Date 08-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255192 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-05-11 | 2026-05-11 |  |  | 492 |  | 492 |  |  | 2026-02-11 | 2026-02-11 |  |  | 492 |  | 492
ADIDAS | 0903255212-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1894 | 15/10/2026 | 1894 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Formosa, PI Date 08-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255212 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 1894 |  | 1894 |  |  | 2026-02-11 | 2026-05-11 |  |  | 1894 |  | 1894
ADIDAS | 0903255230-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 287 | 15/10/2026 | 287 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255230 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 287 |  | 287 |  |  | 2026-02-10 | 2026-02-10 |  |  | 287 |  | 287
ADIDAS | 0903255277-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 234 | 15/10/2026 | 234 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255277 LI7658 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 234 |  | 234 |  |  | 29/09/2026 | 2026-01-10 |  |  | 234 |  | 234
ADIDAS | 0903255316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 365 | 15/10/2026 | 365 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 365 |  | 365 |  |  | 29/09/2026 | 2026-01-10 |  |  | 365 |  | 365
ADIDAS | 0903255344-1 IN1173 | WHITE | 90D | S2408WR1600 | 2980 | 15/10/2026 | 2980 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 960006 | HT SUB PROCESS_V1 | 0903255344 IN1173 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-07-10 |  |  | 2980 |  | 2980 |  |  | 30/09/2026 | 2026-05-10 |  |  | 2980 |  | 2980 |  |  | 29/09/2026 | 2026-03-10 |  |  | 2980 |  | 2980
ADIDAS | 0903255352-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 180 | 15/10/2026 | 180 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255352 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 180 |  | 180 |  |  | 2026-01-10 | 2026-02-10 |  |  | 180 |  | 180
ADIDAS | 0903255377-1 IN1157 | WHITE | 90D | S2408MR1600 | 3100 | 15/10/2026 | 3100 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903255377 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-12-10 |  |  | 3100 |  | 3100 |  |  | 2026-06-10 | 2026-09-10 | 2026-09-09 | 14/09/2026 | 3100 | 565 | 2535 |  | 9 | 2026-05-10 | 2026-08-10 | 2026-04-09 | 2026-12-09 | 3100 | 565 | 2535 |  | 59
ADIDAS | 0903255384-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 204 | 15/10/2026 | 204 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903255384 LI7658 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 204 |  | 204 |  |  | 28/09/2026 | 29/09/2026 |  |  | 204 |  | 204
ADIDAS | 0903255415-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255415 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0903255423-1 IN1159 | BLACK | 90D | S2408MR1601 | 3310 | 15/10/2026 | 3310 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-12-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-12-10 | 17/10/2026 |  |  | 3310 |  | 3310 |  |  | 2026-09-10 | 15/10/2026 |  |  | 3310 |  | 3310 |  |  | 2026-08-10 | 14/10/2026 |  |  | 3310 |  | 3310
ADIDAS | 0903255441-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 960 | 15/10/2026 | 960 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L3 SUB PROCESS_V3 | 0903255441 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 960 |  | 960 |  |  | 24/09/2026 | 25/09/2026 |  |  | 960 |  | 960
ADIDAS | 0903255467-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 1080 | 15/10/2026 | 1080 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L1 SUB PROCESS_V3 | 0903255467 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 30/09/2026 | 30/09/2026 |  |  | 1080 |  | 1080 |  |  | 26/09/2026 | 26/09/2026 |  |  | 1080 |  | 1080
ADIDAS | 0903255589-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903255589 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903255616-1 IN1172 | BLACK | 90D | S2408WR1600 | 4574 | 15/10/2026 | 4574 | SI | SI10/07/2026 | G1I | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255616 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 20/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-10-10 | 17/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-09-10 | 16/10/2026 |  |  | 4574 |  | 4574
ADIDAS | 0903255630-1 KA4331 | BLACK | 90D | S2608MR0902 | 1734 | 15/10/2026 | 1734 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255630 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-02-10 | 2026-06-10 |  |  | 1734 |  | 1734 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1734 |  | 1734 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1734 |  | 1734
ADIDAS | 0903255643-1 IN1173 | WHITE | 90D | S2408WR1600 | 4544 | 15/10/2026 | 4544 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255643 IN1173 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 13/10/2026 |  |  | 4544 |  | 4544 |  |  | 2026-05-10 | 2026-10-10 |  |  | 4544 |  | 4544 |  |  | 2026-03-10 | 2026-09-10 |  |  | 4544 |  | 4544
ADIDAS | 0903255659-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1202 | 28/08/2026 | 1202 | SA | SA10/07/2026 | G3D | SWEATSHIRT | G3 | ok | ok | 27/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255659 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | ESS HDY |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1202 | 1202 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 1202 | 1202
ADIDAS | 0903255693-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1026 | 15/10/2026 | 1026 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516204 | PAD+HT SUB PROCESS_V3 | 0903255693 KF5295 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 1026 |  | 1026 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903255699-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 509 | 15/10/2026 | 509 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255699 KV7863 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 509 |  | 509 |  |  | 2026-07-11 | 2026-09-11 |  |  | 509 |  | 509
ADIDAS | 0903255776-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1452 | 15/10/2026 | 1452 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255776 JE6414 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 13/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1452 |  | 1452 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1452 |  | 1452
ADIDAS | 0903255800-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 149 | 15/10/2026 | 149 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512102 | PRINT L2+HT SUB PROCESS_V3 | 0903255800 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 149 |  | 149 |  |  | 2026-12-10 | 13/10/2026 |  |  | 149 |  | 149 |  |  | 2026-10-10 | 2026-12-10 |  |  | 149 |  | 149
ADIDAS | 0903255801-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1140 | 15/10/2026 | 1140 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255801 JE6338 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 13/10/2026 | M 3S FT FZ HD |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1140 |  | 1140 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1140 |  | 1140
ADIDAS | 0903255819-1 HK7309 | BLACK | 45D | F2225M402 | 4302 | 31/08/2026 | 4302 | SA | SA10/07/2026 | G1F,G1N,G1P | SWEATSHIRT | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255819 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 4302 | 4302 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 2026-02-09 | 4302 | 4302
ADIDAS | 0903255833-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 918 | 15/10/2026 | 918 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255833 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 918 |  | 918 |  |  | 13/10/2026 | 15/10/2026 |  |  | 918 |  | 918
ADIDAS | 0903255882-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1546 | 15/10/2026 | 1546 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255882 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1546 |  | 1546 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1546 |  | 1546
ADIDAS | 0903255885-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4737 | 31/08/2026 | 4737 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255885 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | ESS HDY |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 31/08/2026 | 4737 | 4737 |  |  |  | 20/08/2026 | 27/08/2026 | 21/08/2026 | 31/08/2026 | 4737 | 4737
ADIDAS | 0903255908-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255908 JE6419 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1278 |  | 1278
ADIDAS | 0903255912-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903255912 KF5295 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 29/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 29/10/2026 | 2026-02-11 |  |  | 1967 |  | 1967 |  |  | 26/10/2026 | 29/10/2026 |  |  | 1967 |  | 1967 |  |  | 24/10/2026 | 28/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903255968-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516442 | PAD+HT SUB PROCESS_V3 | 0903255968 KF5295 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 27/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 1967 |  | 1967 |  |  | 23/10/2026 | 26/10/2026 |  |  | 1967 |  | 1967 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903256022-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256022 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | M SL WV PT 2 |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 896 |  | 896 |  |  | 30/10/2026 | 2026-02-11 |  |  | 896 |  | 896
ADIDAS | 0903256045-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 181 | 15/10/2026 | 181 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848024 | PRINT L2+HT SUB PROCESS_V3 | 0903256045 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 181 |  | 181 |  |  | 2026-12-10 | 13/10/2026 |  |  | 181 |  | 181 |  |  | 2026-10-10 | 2026-12-10 |  |  | 181 |  | 181
ADIDAS | 0903256347-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256347 JD5302 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 23/10/2026 | W 3S FT CF PT |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 896 |  | 896 |  |  | 20/10/2026 | 21/10/2026 |  |  | 896 |  | 896
ADIDAS | 0903256411-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | (20/08/2026) | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903256411 JE6417 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278
ADIDAS | 0903256435-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1230 | 15/10/2026 | 1230 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903256435 JE6341 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 1230 |  | 1230 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1230 |  | 1230
ADIDAS | 0903256461-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 792 | 15/10/2026 | 792 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256461 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-11 | M SL WV PT 2 |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 792 |  | 792 |  |  | 29/10/2026 | 30/10/2026 |  |  | 792 |  | 792
ADIDAS | 0903256486-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 113 | 15/10/2026 | 113 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903256486 LC8882 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-10 | M ADI RETRO T BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 113 |  | 113 |  |  | 2026-06-10 | 2026-07-10 |  |  | 113 |  | 113
ADIDAS | 0903256510-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1210 | 15/10/2026 | 1210 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256510 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 1210 |  | 1210 |  |  | 17/10/2026 | 20/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903256620-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 14/10/2026 | 610 | AN | AN10/07/2026 | G3D | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256620 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 26/10/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 610 |  | 610 |  |  | 22/10/2026 | 23/10/2026 |  |  | 610 |  | 610
ADIDAS | 0903256755-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 209 | 15/10/2026 | 209 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256755 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 24/09/2026 | 25/09/2026 |  |  | 209 |  | 209 |  |  | 21/09/2026 | 22/09/2026 |  |  | 209 |  | 209
ADIDAS | 0903256779-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 119 | 15/10/2026 | 119 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903256779 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 24/09/2026 | 25/09/2026 |  |  | 119 |  | 119 |  |  | 21/09/2026 | 22/09/2026 |  |  | 119 |  | 119
ADIDAS | 0903256801-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 121 | 15/10/2026 | 121 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256801 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 24/09/2026 | 25/09/2026 |  |  | 121 |  | 121 |  |  | 21/09/2026 | 22/09/2026 |  |  | 121 |  | 121
ADIDAS | 0903256821-1 KE3743 | BLACK | 30D | F25ORIGFXBLANKW | 2387 | 28/08/2026 | 2387 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/08: ex-fty 1st Art (TC 10 pcs) 960026 | EMBRO SUB PROCESS_V1 | 0903256821 KE3743 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | W BLANK TEE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 2387 | 2387 |  |  |  | 2026-12-08 | 24/08/2026 | 14/08/2026 | 21/08/2026 | 2387 | 2387
ADIDAS | 0903256825-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 132 | 15/10/2026 | 132 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903256825 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 132 |  | 132 |  |  | 2026-05-10 | 2026-06-10 |  |  | 132 |  | 132
ADIDAS | 0903256846-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 216 | 15/10/2026 | 216 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256846 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 216 |  | 216 |  |  | 2026-03-10 | 2026-05-10 |  |  | 216 |  | 216
ADIDAS | 0903256847-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 210 | 15/10/2026 | 210 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256847 JE6346 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | M 3S FT TC PT |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 210 |  | 210 |  |  | 2026-03-10 | 2026-03-10 |  |  | 210 |  | 210
ADIDAS | 0903256851-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256851 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 288 |  | 288 |  |  | 2026-02-10 | 2026-05-10 |  |  | 288 |  | 288
ADIDAS | 0903256871-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 124 | 15/10/2026 | 124 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256871 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 124 |  | 124 |  |  | 2026-03-10 | 2026-05-10 |  |  | 124 |  | 124
ADIDAS | 0903256878-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 299 | 15/10/2026 | 299 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256878 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-10 | M 3S FT TC PT |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 299 |  | 299 |  |  | 2026-07-10 | 2026-08-10 |  |  | 299 |  | 299
ADIDAS | 0903256884-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256884 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 342 |  | 342 |  |  | 2026-05-11 | 2026-06-11 |  |  | 342 |  | 342
ADIDAS | 0903256891-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 269 | 15/10/2026 | 269 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903256891 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 269 |  | 269 |  |  | 28/09/2026 | 29/09/2026 |  |  | 269 |  | 269
ADIDAS | 0903256901-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256901 LF1392 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-08-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 107 |  | 107 |  |  | 2026-05-10 | 2026-09-10 |  |  | 107 |  | 107
ADIDAS | 0903256955-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 219 | 15/10/2026 | 219 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256955 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 28/10/2026 | 28/10/2026 |  |  | 219 |  | 219 |  |  | 24/10/2026 | 24/10/2026 |  |  | 219 |  | 219
ADIDAS | 0903256972-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 123 | 15/10/2026 | 123 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512102 | PRINT L2+PAD SUB PROCESS_V3 | 0903256972 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 123 |  | 123 |  |  | 2026-12-10 | 13/10/2026 |  |  | 123 |  | 123
ADIDAS | 0903257022-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257022 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-08-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 120 |  | 120 |  |  | 2026-05-10 | 2026-09-10 |  |  | 120 |  | 120
ADIDAS | 0903257161-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 176 | 15/10/2026 | 176 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257161 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 176 |  | 176 |  |  | 23/09/2026 | 25/09/2026 |  |  | 176 |  | 176
ADIDAS | 0903257172-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 119 | 15/10/2026 | 119 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257172 LG8055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 119 |  | 119 |  |  | 2026-02-10 | 2026-02-10 |  |  | 119 |  | 119
ADIDAS | 0903257177-1 IS1413 | BLACK | 60D | S2425M405 | 1203 | 2026-12-09 | 1203 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903257177 IS1413 | 26/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | IN RANGE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 1203 | 1203 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-03-09 | 2026-11-09 | 1203 | 1203
ADIDAS | 0903257182-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 336 | 15/10/2026 | 336 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257182 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 336 |  | 336 |  |  | 2026-06-10 | 2026-07-10 |  |  | 336 |  | 336
ADIDAS | 0903257198-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 404 | 15/10/2026 | 404 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257198 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 404 |  | 404 |  |  | 2026-02-10 | 2026-03-10 |  |  | 404 |  | 404
ADIDAS | 0903257203-1 HK7309 | BLACK | 45D | F2225M402 | 1653 | 2026-09-09 | 1653 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257203 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 31/08/2026 | 2026-07-09 | 1653 | 1653 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-10-09 | 1653 | 1653
ADIDAS | 0903257227-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 101 | 15/10/2026 | 101 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257227 LG8056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-02-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903257252-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 848 | 15/10/2026 | 848 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257252 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 848 |  | 848 |  |  | 28/09/2026 | 29/09/2026 |  |  | 848 |  | 848
ADIDAS | 0903257280-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1098 | 15/10/2026 | 1098 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903257280 IB8686 |  | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1098 |  | 1098 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1098 |  | 1098
ADIDAS | 0903257284-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257284 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 169 |  | 169 |  |  | 23/09/2026 | 24/09/2026 |  |  | 169 |  | 169
ADIDAS | 0903257292-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903257292 JC8238 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 195 |  | 195 |  |  | 25/09/2026 | 26/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903257307-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 177 | 15/10/2026 | 177 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257307 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 177 |  | 177 |  |  | 22/09/2026 | 22/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903257317-1 KD4067 | WHITE | 30D | F25ORIGFXBLANKW | 2398 | 28/08/2026 | 2398 | SA | SA10/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok | ok | 28/08: ex-fty 1st Art (TC 10 pcs) 960026 | EMBRO SUB PROCESS_V1 | 0903257317 KD4067 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | W BLANK TEE |  | SS27 | 18/08/2026 | 28/08/2026 | 18/08/2026 | 28/08/2026 | 2398 | 2398 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-12-08 | 31/08/2026 | 2398 | 2398
ADIDAS | 0903257329-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903257329 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-03-10 |  |  | 100 |  | 100
ADIDAS | 0903257350-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 140 | 15/10/2026 | 140 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257350 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 23/09/2026 | 23/09/2026 |  |  | 140 |  | 140 |  |  | 19/09/2026 | 19/09/2026 |  |  | 140 |  | 140 |  |  | 18/09/2026 | 18/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903257370-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 302 | 15/10/2026 | 302 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257370 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | W 3S WV SHO |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 302 |  | 302 |  |  | 2026-05-10 | 2026-06-10 |  |  | 302 |  | 302
ADIDAS | 0903257378-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 178 | 15/10/2026 | 178 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257378 LF1392 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 178 |  | 178 |  |  | 2026-05-10 | 2026-09-10 |  |  | 178 |  | 178
ADIDAS | 0903257558-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 296 | 2026-12-09 | 296 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903257558 KA0544 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 296 | 296 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-01-09 | 296 | 296
ADIDAS | 0903257658-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 272 | 15/10/2026 | 272 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257658 KY3737 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 30/09/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 272 |  | 272 |  |  | 26/09/2026 | 26/09/2026 |  |  | 272 |  | 272
ADIDAS | 0903257671-1 IN1159 | BLACK | 90D | S2408MR1601 | 2727 | 15/10/2026 | 2727 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903257671 IN1159 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-10 | 2026-12-10 |  |  | 2727 |  | 2727 |  |  | 2026-03-10 | 2026-09-10 |  |  | 2727 |  | 2727 |  |  | 2026-02-10 | 2026-08-10 |  |  | 2727 |  | 2727
ADIDAS | 0903257687-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257687 KV0458 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 30/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 224 |  | 224 |  |  | 26/09/2026 | 28/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903257700-1 IN8707 | BLACK | 105D | S2408WR1601A | 2203 | 15/10/2026 | 2203 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903257700 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 21/10/2026 |  |  | 2203 |  | 2203 |  |  | 14/10/2026 | 19/10/2026 |  |  | 2203 |  | 2203 |  |  | 13/10/2026 | 17/10/2026 |  |  | 2203 |  | 2203
ADIDAS | 0903257706-1 IS1413 | BLACK | 60D | S2425M405 | 396 | 2026-07-10 | 396 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903257706 IS1413 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 23/09/2026 | IN RANGE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 396 |  | 396 |  |  | 19/09/2026 | 21/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903257728-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903257728 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903257736-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 636 | 15/10/2026 | 636 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257736 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 28/09/2026 | 28/09/2026 |  |  | 636 |  | 636 |  |  | 24/09/2026 | 24/09/2026 |  |  | 636 |  | 636
ADIDAS | 0903257740-1 KA4331 | BLACK | 90D | S2608MR0902 | 483 | 15/10/2026 | 483 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257740 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 483 |  | 483 |  |  | 2026-06-10 | 2026-07-10 |  |  | 483 |  | 483 |  |  | 2026-05-10 | 2026-06-10 |  |  | 483 |  | 483
ADIDAS | 0903257744-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903257744 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 25/09/2026 | MINI EMB T |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 23/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 21/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903257771-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 534 | 15/10/2026 | 534 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257771 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 29/09/2026 | 30/09/2026 |  |  | 534 |  | 534 |  |  | 25/09/2026 | 26/09/2026 |  |  | 534 |  | 534
ADIDAS | 0903257785-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 218 | 15/10/2026 | 218 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848024 | PRINT L2+PAD SUB PROCESS_V3 | 0903257785 LC8884 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 218 |  | 218 |  |  | 2026-12-10 | 13/10/2026 | 26/08/2026 | 29/08/2026 | 218 | 199 | 19
ADIDAS | 0903257807-1 KA4331 | BLACK | 90D | S2608MR0902 | 334 | 15/10/2026 | 334 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903257807 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 334 |  | 334 |  |  | 2026-03-10 | 2026-05-10 |  |  | 334 |  | 334 |  |  | 2026-02-10 | 2026-03-10 |  |  | 334 |  | 334
ADIDAS | 0903257817-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 113 | 15/10/2026 | 113 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257817 LE4307 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-06-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 113 |  | 113 |  |  | 2026-02-10 | 2026-05-10 |  |  | 113 |  | 113
ADIDAS | 0903257833-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 128 | 15/10/2026 | 128 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 848012 | EMBRO SUB PROCESS_V1 | 0903257833 HK7303 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 128 |  | 128 |  |  | 26/09/2026 | 26/09/2026 |  |  | 128 |  | 128
ADIDAS | 0903257863-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 111 | 15/10/2026 | 111 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903257863 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 111 |  | 111 |  |  | 26/09/2026 | 26/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903257897-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257897 JD1877 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1278 |  | 1278 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1278 |  | 1278
ADIDAS | 0903257898-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3008 | 15/10/2026 | 3008 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257898 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 29/09/2026 | 2026-03-10 |  |  | 3008 |  | 3008 |  |  | 25/09/2026 | 30/09/2026 |  |  | 3008 |  | 3008
ADIDAS | 0903257913-1 KA4331 | BLACK | 90D | S2608MR0902 | 306 | 15/10/2026 | 306 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257913 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 306 |  | 306 |  |  | 2026-03-10 | 2026-05-10 |  |  | 306 |  | 306 |  |  | 2026-02-10 | 2026-03-10 |  |  | 306 |  | 306
ADIDAS | 0903258010-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1100 | 15/10/2026 | 1100 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903258010 JG8642 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1100 |  | 1100 |  |  | 29/09/2026 | 2026-01-10 | 2026-09-09 | 2026-11-09 | 1100 | 1056 | 44
ADIDAS | 0903258064-1 KA0527 | PURE RUBY S25 | 60D | S26KJUGFX003 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 1st Art (TC 10 pcs) 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258064 KA0527 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | J SUMMER T |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903258118-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903258118 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 368 |  | 368 |  |  | 2026-05-10 | 2026-06-10 | 2026-09-09 | 2026-09-09 | 368 | 349 | 19
ADIDAS | 0903258121-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 117 | 15/10/2026 | 117 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258121 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 117 |  | 117 |  |  | 2026-05-10 | 2026-09-10 |  |  | 117 |  | 117
ADIDAS | 0903258209-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 272 | 15/10/2026 | 272 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903258209 LI7655 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 29/09/2026 | 30/09/2026 |  |  | 272 |  | 272 |  |  | 25/09/2026 | 26/09/2026 |  |  | 272 |  | 272
ADIDAS | 0903258233-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1002 | 15/10/2026 | 1002 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903258233 JE6419 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1002 |  | 1002 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1002 |  | 1002
ADIDAS | 0903258257-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1403 | 2026-09-09 | 1403 | SA | SA10/07/2026 | G3H | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258257 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403
ADIDAS | 0903258325-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 111 | 15/10/2026 | 111 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903258325 LI7660 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 111 |  | 111 |  |  | 23/09/2026 | 24/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903258342-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 1448 | 15/10/2026 | 1448 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258342 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 1448 |  | 1448 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1448 |  | 1448
ADIDAS | 0903258375-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258375 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903258592-1 KH3706 | WHITE | 60D | S26FBWCGFX410 | 1 | 26/08/2026 | 1 | SI | SI10/07/2026 | G1P | T-SHIRT | G1 |  |  | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903258592 KH3706 | 26/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | WC HC T PHILI |  | SS27-WC | 29/07/2026 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 1 | 1 |  |  |  | 24/07/2026 | 31/07/2026 | 2026-05-08 | 2026-05-08 | 1 | 1
ADIDAS | 0903258612-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 2 | 15/10/2026 | 2 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903258612 IT1469 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 2 |  | 2 |  |  | 2026-06-10 | 2026-07-10 |  |  | 2 |  | 2 |  |  | 2026-05-10 | 2026-06-10 |  |  | 2 |  | 2
ADIDAS | 0903258647-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 4605 | 15/10/2026 | 4605 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903258647 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-12-10 |  |  | 4605 |  | 4605 |  |  | 2026-03-10 | 2026-09-10 |  |  | 4605 |  | 4605 |  |  | 2026-02-10 | 2026-08-10 |  |  | 4605 |  | 4605
ADIDAS | 0903258675-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 2130 | 15/10/2026 | 2130 | SI | SI10/07/2026 | G1D | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258675 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 19/10/2026 | 23/10/2026 |  |  | 2130 |  | 2130 |  |  | 16/10/2026 | 21/10/2026 |  |  | 2130 |  | 2130 |  |  | 15/10/2026 | 20/10/2026 |  |  | 2130 |  | 2130
ADIDAS | 0903258696-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 510 | 14/10/2026 | 510 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258696 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 510 |  | 510 |  |  | 2026-03-10 | 2026-05-10 |  |  | 510 |  | 510
ADIDAS | 0903258702-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258702 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 120 |  | 120 |  |  | 2026-05-10 | 2026-06-10 | 2026-11-09 | 2026-11-09 | 120 | 19 | 101
ADIDAS | 0903258720-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1066 | 15/10/2026 | 1066 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903258720 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 28/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 28/10/2026 | 30/10/2026 |  |  | 1066 |  | 1066 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1066 |  | 1066
ADIDAS | 0903258750-1 IN1157 | WHITE | 90D | S2408MR1600 | 6183 | 15/10/2026 | 6183 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903258750 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 20/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-09-10 | 17/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-08-10 | 16/10/2026 |  |  | 6183 |  | 6183
ADIDAS | 0903258776-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 488 | 15/10/2026 | 488 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258776 LF1392 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 488 |  | 488 |  |  | 2026-05-10 | 2026-09-10 |  |  | 488 |  | 488
ADIDAS | 0903258807-1 IN8707 | BLACK | 105D | S2408WR1601A | 65 | 15/10/2026 | 65 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258807 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 21/10/2026 |  |  | 65 |  | 65 |  |  | 14/10/2026 | 19/10/2026 |  |  | 65 |  | 65 |  |  | 13/10/2026 | 17/10/2026 |  |  | 65 |  | 65
ADIDAS | 0903258822-1 IN1156 | BLACK | 90D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258822 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 1 |  | 1 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1 |  | 1 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903258858-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 672027 | HT SUB PROCESS_V1 | 0903258858 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 250 |  | 250 |  |  | 13/10/2026 | 14/10/2026 |  |  | 250 |  | 250 |  |  | 2026-12-10 | 13/10/2026 | 2026-04-09 | 2026-12-09 | 250 | 81 | 169 |  | 14
ADIDAS | 0903258889-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903258889 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903258929-1 IN1157 | WHITE | 90D | S2408MR1600 | 145 | 15/10/2026 | 145 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258929 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 145 |  | 145 |  |  | 29/09/2026 | 30/09/2026 |  |  | 145 |  | 145 |  |  | 28/09/2026 | 29/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903258964-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 05-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258964 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 | 20/08/2026 | 29/08/2026 | 100 | 99 | 1 |  |  | 2026-09-10 | 2026-10-10 | 19/08/2026 | 28/08/2026 | 100 | 99 | 1
ADIDAS | 0903258997-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903258997 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 60 |  | 60 |  |  | 2026-05-10 | 2026-06-10 |  |  | 60 |  | 60 |  |  | 2026-03-10 | 2026-05-10 |  |  | 60 |  | 60
ADIDAS | 0903259051-1 KA4331 | BLACK | 90D | S2608MR0902 | 62 | 15/10/2026 | 62 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903259051 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 62 |  | 62 |  |  | 2026-06-10 | 2026-07-10 |  |  | 62 |  | 62 |  |  | 2026-05-10 | 2026-06-10 |  |  | 62 |  | 62
ADIDAS | 0903259083-1 KT4839 | ONIX | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903259083 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 30/09/2026 | 2026-03-10 |  |  | 60 |  | 60 |  |  | 28/09/2026 | 2026-01-10 |  |  | 60 |  | 60 |  |  | 26/09/2026 | 30/09/2026 |  |  | 60 |  | 60
ADIDAS | 0903259087-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259087 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 200 |  | 200 |  |  | 2026-03-10 | 2026-05-10 |  |  | 200 |  | 200
ADIDAS | 0903259113-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 228 | 15/10/2026 | 228 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259113 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 228 |  | 228 |  |  | 28/09/2026 | 29/09/2026 |  |  | 228 |  | 228
ADIDAS | 0903259117-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 135 | 15/10/2026 | 135 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903259117 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 135 |  | 135 |  |  | 2026-10-10 | 2026-12-10 |  |  | 135 |  | 135 |  |  | 2026-09-10 | 2026-10-10 |  |  | 135 |  | 135
ADIDAS | 0903259145-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I., PI Date 14-Aug, material quality issues body: stain), body&mesh actual receives 18-Aug. 672027 | HT SUB PROCESS_V1 | 0903259145 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-02-10 | 2026-04-09 | 2026-07-09 | 100 | 98 | 2 |  |  | 29/09/2026 | 2026-01-10 | 29/08/2026 | 2026-07-09 | 100 | 98 | 2
ADIDAS | 0903259225-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 101 | 15/10/2026 | 101 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903259225 JE6419 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 26/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 101 |  | 101 |  |  | 23/09/2026 | 25/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903259421-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 35000 | 30/09/2026 | 35000 | SA | SA10/07/2026 | G2I,G2J,G2L | T-SHIRT | G2 | ok | ok | 29/09: ex-fty (1x20). DRC 0090-early shipment customer (GTS89140-1 Early Shipment Order 0903259421). 834012 | HT+PAD SUB PROCESS_V3 | 0903259421 KB5966 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 18/09/2026 | Run Ess Tee M |  | SS27-TI | 18/09/2026 | 2026-01-10 |  |  | 35000 |  | 35000 |  |  | 15/09/2026 | 28/09/2026 | 2026-10-09 | 14/09/2026 | 35000 | 7129 | 27871 |  | 2002 | 2026-12-09 | 25/09/2026 | 2026-10-09 | 14/09/2026 | 35000 | 9824 | 25176 |  | 3717
ADIDAS | 0903259496-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1820 | 15/10/2026 | 1820 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903259496 JE6346 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | M 3S FT TC PT |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 1820 |  | 1820 |  |  | 2026-03-10 | 2026-07-10 |  |  | 1820 |  | 1820
ADIDAS | 0903259552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 440 | 15/10/2026 | 440 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259552 KV7963 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 19/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 440 |  | 440 |  |  | 15/10/2026 | 15/10/2026 |  |  | 440 |  | 440
ADIDAS | 0903259631-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 425 | 15/10/2026 | 425 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259631 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 425 |  | 425 |  |  | 15/10/2026 | 15/10/2026 |  |  | 425 |  | 425
ADIDAS | 0903259656-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259656 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 396 |  | 396 |  |  | 24/09/2026 | 26/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903259689-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 270 | 15/10/2026 | 270 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259689 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | W 3S FT CF PT |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 270 |  | 270 |  |  | 20/10/2026 | 21/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903259717-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903259717 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 432 |  | 432 |  |  | 2026-06-10 | 2026-07-10 |  |  | 432 |  | 432
ADIDAS | 0903259814-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 371 | 15/10/2026 | 371 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259814 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 371 |  | 371 |  |  | 2026-07-11 | 2026-09-11 |  |  | 371 |  | 371
ADIDAS | 0903259865-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259865 JC8239 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 195 |  | 195 |  |  | 24/09/2026 | 25/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903259938-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 200 | 15/10/2026 | 200 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259938 JG8642 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 29/09/2026 | 29/09/2026 | 2026-11-09 | 2026-11-09 | 200 | 60 | 140
ADIDAS | 0903260199-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903260199 JD1877 |  | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | M 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1203 |  | 1203 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903260217-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 703 | 15/10/2026 | 703 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260217 JE0052 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 30/10/2026 | W 3S FT FZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 703 |  | 703 |  |  | 27/10/2026 | 28/10/2026 |  |  | 703 |  | 703
ADIDAS | 0903260239-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2400 | 31/08/2026 | 2400 | SI | SI10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 31/08: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903260239 KE3742 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | M BLANK TEE WHITE |  | SS27 | 21/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 2400 | 2400 |  |  |  | 18/08/2026 | 27/08/2026 | 2026-10-08 | 29/08/2026 | 2400 | 2400
ADIDAS | 0903260282-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 302 | 15/10/2026 | 302 | SA | SA10/07/2026 | G3K | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260282 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/10/2026 | W 3S FT OH PT |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 302 |  | 302 |  |  | 15/10/2026 | 16/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903260434-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260434 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | ADIZERO E TEE |  | SS27-YTI | 19/09/2026 | 21/09/2026 |  |  | 327 |  | 327 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 311 | 16 |  |  | 16/09/2026 | 17/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 313 | 14
ADIDAS | 0903260741-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 212 | 15/10/2026 | 212 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903260741 KV0458 |  | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 212 |  | 212 |  |  | 26/09/2026 | 28/09/2026 |  |  | 212 |  | 212
ADIDAS | 0903261098-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903261098 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 19/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261108-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261108 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 19/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261122-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261122 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 15/09/2026 | MER KA GFSWT M BLACK |  | SS27-MS | 15/09/2026 | 15/09/2026 |  |  | 2 |  | 2 |  |  | 2026-11-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903261168-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 35 | 15/10/2026 | 35 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903261168 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 35 |  | 35 |  |  | 19/10/2026 | 20/10/2026 |  |  | 35 |  | 35 |  |  | 17/10/2026 | 19/10/2026 |  |  | 35 |  | 35
ADIDAS | 0903261626-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 349 | 15/10/2026 | 349 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903261626 KG8553 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 349 |  | 349 |  |  | 2026-05-10 | 2026-06-10 |  |  | 349 |  | 349 |  |  | 2026-03-10 | 2026-05-10 |  |  | 349 |  | 349
ADIDAS | 0903262069-1 IS1413 | BLACK | 60D | S2425M405 | 944 | 2026-09-09 | 944 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903262069 IS1413 | 26/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 944 | 944 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 944 | 944
ADIDAS | 0903262266-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 395 | 15/10/2026 | 395 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903262266 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 395 |  | 395 |  |  | 23/09/2026 | 23/09/2026 |  |  | 395 |  | 395
ADIDAS | 0903262302-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 285 | 15/10/2026 | 285 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903262302 LI7656 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 25/09/2026 | 26/09/2026 |  |  | 285 |  | 285 |  |  | 22/09/2026 | 23/09/2026 |  |  | 285 |  | 285
ADIDAS | 0903262703-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 126 | 15/10/2026 | 126 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262703 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 126 |  | 126 |  |  | 2026-07-11 | 2026-09-11 |  |  | 126 |  | 126
ADIDAS | 0903262820-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 190 | 15/10/2026 | 190 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903262820 JE6346 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-07-10 | M 3S FT TC PT |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 190 |  | 190 |  |  | 2026-03-10 | 2026-03-10 |  |  | 190 |  | 190
ADIDAS | 0903262992-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 572 | 30/09/2026 | 572 | SI | SI10/07/2026 | G1E | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). IMPROVE. DRC 0010-T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 652001 | HT SUB PROCESS_V1 | 0903262992 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | ADIZERO E TEE |  | SS27-YTI | 19/09/2026 | 21/09/2026 |  |  | 572 |  | 572 |  |  | 17/09/2026 | 18/09/2026 | 29/08/2026 | 2026-04-09 | 572 | 569 | 3 |  |  | 16/09/2026 | 17/09/2026 | 24/08/2026 | 2026-04-09 | 572 | 569 | 3
ADIDAS | 0903263117-1 JZ7711 | BLACK | 120D | S2608MR0202 | 2362 | 15/10/2026 | 2362 | SA | SA10/07/2026 | G3E | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263117 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 2026-03-10 | 2026-08-10 |  |  | 2362 |  | 2362 |  |  | 30/09/2026 | 2026-05-10 |  |  | 2362 |  | 2362 |  |  | 26/09/2026 | 2026-01-10 |  |  | 2362 |  | 2362
ADIDAS | 0903263138-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 529 | 15/10/2026 | 529 | SA | SA10/07/2026 | G3E | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263138 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-10 | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 529 |  | 529 |  |  | 29/09/2026 | 30/09/2026 |  |  | 529 |  | 529 |  |  | 25/09/2026 | 26/09/2026 |  |  | 529 |  | 529
ADIDAS | 0903263275-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 160 | 15/10/2026 | 160 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903263275 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 15/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 160 |  | 160 |  |  | 2026-12-10 | 13/10/2026 |  |  | 160 |  | 160 |  |  | 2026-10-10 | 2026-12-10 |  |  | 160 |  | 160
ADIDAS | 0903263698-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2330 | 15/10/2026 | 2330 | AN | AN10/07/2026 | G3B | PANTS | G3 | ok | ok | (Mexico). T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 03-Jul, actual receives 28-Jul. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263698 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/11/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 14/11/2026 | 18/11/2026 |  |  | 2330 |  | 2330 |  |  | 2026-11-11 | 14/11/2026 |  |  | 2330 |  | 2330
ADIDAS | 0903263747-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G2M | SHORTS | G2 | (20/08/2026) | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903263747 JG8639 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-05-10 | W LIN FT SHO |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 250 |  | 250 |  |  | 2026-01-10 | 2026-03-10 |  |  | 250 |  | 250
ADIDAS | 0903263877-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263877 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 17/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 340 |  | 340 |  |  | 14/10/2026 | 15/10/2026 |  |  | 340 |  | 340
ADIDAS | 0903264038-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264038 JC8239 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 1500 |  | 1500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903264065-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 301 | 15/10/2026 | 301 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903264065 JE6414 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301 |  |  | 2026-06-10 | 2026-07-10 |  |  | 301 |  | 301
ADIDAS | 0903264129-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903264129 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903264137-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G2M | SHORTS | G2 | (20/08/2026) | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264137 JG8639 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-05-10 | W LIN FT SHO |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1000 |  | 1000 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1000 |  | 1000
ADIDAS | 0903265194-1 KA4331 | BLACK | 90D | S2608MR0902 | 5581 | 15/10/2026 | 5581 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903265194 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-02-10 | 2026-09-10 |  |  | 5581 |  | 5581 |  |  | 29/09/2026 | 2026-06-10 |  |  | 5581 |  | 5581 |  |  | 28/09/2026 | 2026-05-10 |  |  | 5581 |  | 5581
ADIDAS | 0903265258-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 831 | 15/10/2026 | 831 | SI | SI10/07/2026 | G3K | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265258 KD3854 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 22/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 831 |  | 831 |  |  | 19/10/2026 | 21/10/2026 |  |  | 831 |  | 831 |  |  | 15/10/2026 | 17/10/2026 |  |  | 831 |  | 831
ADIDAS | 0903265296-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265296 KF5311 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 13/10/2026 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-07-10 |  |  | 300 |  | 300
ADIDAS | 0903265322-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 572 | 15/10/2026 | 572 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265322 KE8424 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 572 |  | 572 |  |  | 2026-03-10 | 2026-05-10 |  |  | 572 |  | 572 |  |  | 2026-01-10 | 2026-02-10 |  |  | 572 |  | 572
ADIDAS | 0903265342-1 KG8547 | ONIX | 90D | S2408WR1600 | 3535 | 15/10/2026 | 3535 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903265342 KG8547 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 15/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-09-10 | 13/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-08-10 | 2026-12-10 |  |  | 3535 |  | 3535
ADIDAS | 0903265374-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 5948 | 15/10/2026 | 5948 | SA | SA10/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903265374 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 24/10/2026 |  |  | 5948 |  | 5948 |  |  | 14/10/2026 | 22/10/2026 | 2026-12-08 | 2026-10-09 | 5948 | 5859 | 89 |  |  | 13/10/2026 | 21/10/2026 | 2026-12-08 | 2026-10-09 | 5948 | 5864 | 84
ADIDAS | 0903265404-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 1408 | 15/10/2026 | 1408 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265404 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 1408 |  | 1408 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1408 |  | 1408 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1408 |  | 1408
ADIDAS | 0903265435-1 KT4840 | ONIX | 90D | S2408MR1600 | 5404 | 15/10/2026 | 5404 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903265435 KT4840 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 21/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-12-10 | 19/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-10-10 | 17/10/2026 |  |  | 5404 |  | 5404
ADIDAS | 0903265463-1 KT4839 | ONIX | 90D | S2408MR1601 | 1613 | 15/10/2026 | 1613 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265463 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 30/09/2026 | 2026-03-10 |  |  | 1613 |  | 1613 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1613 |  | 1613 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903266153-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 309 | 15/10/2026 | 309 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266153 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 309 |  | 309 |  |  | 28/09/2026 | 28/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903266170-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 285 | 15/10/2026 | 285 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266170 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 285 |  | 285 |  |  | 28/09/2026 | 28/09/2026 |  |  | 285 |  | 285
ADIDAS | 0903266198-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 177 | 15/10/2026 | 177 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (06/08/2026) | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266198 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 177 |  | 177 |  |  | 19/09/2026 | 21/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903266331-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266331 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903266349-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266349 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 |  |  | 143 |  | 143
ADIDAS | 0903266525-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 310 | 15/10/2026 | 310 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266525 LH4535 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 17/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 310 |  | 310 |  |  | 14/10/2026 | 15/10/2026 |  |  | 310 |  | 310
ADIDAS | 0903266526-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 273 | 15/10/2026 | 273 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266526 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 273 |  | 273 |  |  | 28/09/2026 | 29/09/2026 |  |  | 273 |  | 273
ADIDAS | 0903266548-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266548 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 30/09/2026 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 26/09/2026 | 28/09/2026 |  |  | 120 |  | 120
ADIDAS | 0903266578-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266578 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 30/09/2026 | 2026-01-10 |  |  | 143 |  | 143 |  |  | 26/09/2026 | 28/09/2026 |  |  | 143 |  | 143
ADIDAS | 0903266599-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266599 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903269490-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269490 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 120 |  | 120 |  |  | 22/09/2026 | 22/09/2026 |  |  | 120 |  | 120
ADIDAS | 0903269545-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903269545 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 100 |  | 100 |  |  | 23/09/2026 | 23/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903269592-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 337 | 15/10/2026 | 337 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269592 LI7656 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 25/09/2026 | 26/09/2026 |  |  | 337 |  | 337 |  |  | 22/09/2026 | 23/09/2026 |  |  | 337 |  | 337
ADIDAS | 0903269617-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 103 | 15/10/2026 | 103 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903269617 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 103 |  | 103 |  |  | 22/09/2026 | 22/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903271653-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903271653 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 107 |  | 107 |  |  | 22/09/2026 | 22/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903271675-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 150 | 15/10/2026 | 150 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903271675 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 150 |  | 150 |  |  | 23/09/2026 | 23/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903273743-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 309 | 15/10/2026 | 309 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273743 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 28/10/2026 | 28/10/2026 |  |  | 309 |  | 309 |  |  | 24/10/2026 | 24/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903274607-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903274607 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903274622-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2L | T-SHIRT | G2 | (09/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274622 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-05-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 2 |  | 2 |  |  | 2026-01-10 | 2026-01-10 | 26/08/2026 | 26/08/2026 | 2 | 1 | 1
ADIDAS | 0903274637-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 2 | 2026-07-10 | 2 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274637 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 25/09/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 25/09/2026 | 25/09/2026 |  |  | 2 |  | 2 |  |  | 22/09/2026 | 22/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903276235-1 KY5870 | GREY | 90D | S2750MTR052 | 114 | 15/10/2026 | 114 | SI | SI10/07/2026 | G2C | SHORTS | G2 | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 830009 | HT SUB PROCESS_V1 | 0903276235 KY5870 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | D74T ESS SHORTS GREY |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 114 |  | 114 |  |  | 28/09/2026 | 29/09/2026 |  |  | 114 |  | 114 |  |  | 26/09/2026 | 28/09/2026 |  |  | 114 |  | 114
ADIDAS | 0903305162-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 158 | 15/10/2026 | 158 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848016 | PRINT L2+PAD SUB PROCESS_V3 | 0903305162 LC8884 |  | KAHATEX CIJERAH | MOROCCO | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 158 |  | 158 |  |  | 2026-12-10 | 13/10/2026 |  |  | 158 |  | 158
ADIDAS | 0903305163-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 198 | 15/10/2026 | 198 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848012 | PRINT L2+PAD SUB PROCESS_V3 | 0903305163 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 198 |  | 198 |  |  | 2026-12-10 | 13/10/2026 | 26/08/2026 | 26/08/2026 | 198 | 8 | 190
ADIDAS | 0903306652-1 KA6229 | BLACK | 120D | S2608WR0202 | 255 | 15/10/2026 | 255 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306652 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 17/10/2026 | 20/10/2026 |  |  | 255 |  | 255 |  |  | 14/10/2026 | 16/10/2026 |  |  | 255 |  | 255 |  |  | 2026-10-10 | 13/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903306653-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 15/10/2026 | 1009 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306653 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 20/10/2026 | 23/10/2026 |  |  | 1009 |  | 1009 |  |  | 16/10/2026 | 20/10/2026 |  |  | 1009 |  | 1009 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903309141-1 KA4331 | BLACK | 90D | S2608MR0902 | 6720 | 15/10/2026 | 6720 | SA | SA20/07/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. DRC 0064-T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand tex, PI Date 16-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903309141 KA4331 | 2026-02-10 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27 | 25/09/2026 | 2026-06-10 |  |  | 6720 |  | 6720 |  |  | 22/09/2026 | 2026-02-10 |  |  | 6720 |  | 6720 |  |  | 21/09/2026 | 2026-01-10 |  |  | 6720 |  | 6720
ADIDAS | 0903309142-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 3 | 15/10/2026 | 3 | AN | AN20/07/2026 | G2R | SHORTS | G2 |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? Waiting fabroc. T2 Formosa, PI Date ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309142 KZ3231 | 2026-02-10 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 3 |  | 3 |  |  | 2026-09-10 | 2026-09-10 |  |  | 3 |  | 3
ADIDAS | 0903309143-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 28 | 15/10/2026 | 28 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309143 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 28 |  | 28 |  |  | 2026-06-10 | 2026-07-10 |  |  | 28 |  | 28 |  |  | 2026-05-10 | 2026-06-10 |  |  | 28 |  | 28
ADIDAS | 0903309144-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309144 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 1 |  | 1 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1 |  | 1 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1 |  | 1
ADIDAS | 0903309880-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309880 JE6414 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 23/09/2026 | 28/09/2026 |  |  | 2637 |  | 2637 |  |  | 19/09/2026 | 24/09/2026 | 31/08/2026 | 2026-01-09 | 2637 | 2637
ADIDAS | 0903309881-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 6599 | 30/09/2026 | 6599 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309881 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S FT FZ HD |  | SS27 | 23/09/2026 | 2026-01-10 |  |  | 6599 |  | 6599 |  |  | 19/09/2026 | 28/09/2026 |  |  | 6599 |  | 6599
ADIDAS | 0903309882-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 4400 | 30/09/2026 | 4400 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309882 IB8686 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | ESS TEE |  | SS27 | 19/09/2026 | 24/09/2026 |  |  | 4400 |  | 4400 |  |  | 16/09/2026 | 21/09/2026 | 2026-02-09 | 2026-10-09 | 4400 | 4395 | 5
ADIDAS | 0903309883-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3522 | 30/09/2026 | 3522 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309883 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 3522 |  | 3522 |  |  | 21/09/2026 | 26/09/2026 |  |  | 3522 |  | 3522
ADIDAS | 0903309884-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1321 | 30/09/2026 | 1321 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309884 JE6340 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M 3S FT FZ HD |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 1321 |  | 1321 |  |  | 2026-11-09 | 14/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903309886-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 7920 | 30/09/2026 | 7920 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309886 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W 3S FT CF PT |  | SS27 | 15/09/2026 | 24/09/2026 |  |  | 7920 |  | 7920 |  |  | 2026-11-09 | 21/09/2026 |  |  | 7920 |  | 7920
ADIDAS | 0903309887-1 HZ0747 | BLACK | 90D | F2325M414 | 9088 | 30/09/2026 | 9088 | SA | SA26/06/2026 | G2R | T-SHIRT | G2 | (29/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309887 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 25/09/2026 |  |  | 9088 |  | 9088 |  |  | 2026-12-09 | 22/09/2026 |  |  | 9088 |  | 9088
ADIDAS | 0903309888-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 3520 | 30/09/2026 | 3520 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309888 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-08-10 |  |  | 3520 |  | 3520 |  |  | 29/09/2026 | 2026-05-10 |  |  | 3520 |  | 3520
ADIDAS | 0903309889-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 6600 | 30/09/2026 | 6600 | SI | SI26/06/2026 | G3G,G3H | JACKET | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309889 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | W 3S FT FZ HD |  | SS27 | 2026-05-10 | 14/10/2026 |  |  | 6600 |  | 6600 |  |  | 2026-01-10 | 2026-10-10 | 13/08/2026 | 2026-11-09 | 6600 | 5277 | 1323
ADIDAS | 0903309890-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1050 | 15/10/2026 | 1050 | SI | SI10/07/2026 | G3A | PANTS | G3 | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309890 JM1776 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-11 | M SL WV PT 2 |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 1050 |  | 1050 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1050 |  | 1050
ADIDAS | 0903309891-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1760 | 30/09/2026 | 1760 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309891 KD3911 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | RELEASED |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 1760 |  | 1760 |  |  | 14/09/2026 | 16/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903309892-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1761 | 30/09/2026 | 1761 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309892 JE6341 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 21/09/2026 |  |  | 1761 |  | 1761 |  |  | 2026-12-09 | 17/09/2026 |  |  | 1761 |  | 1761
ADIDAS | 0903309893-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 6602 | 30/09/2026 | 6602 | SI | SI26/06/2026 | G3E,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309893 HR8583 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | ESS SWTP |  | SS27 | 14/09/2026 | 2026-03-10 |  |  | 6602 |  | 6602 |  |  | 2026-10-09 | 30/09/2026 |  |  | 6602 |  | 6602
ADIDAS | 0903309894-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309894 JE6417 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 30/09/2026 | 2026-05-10 |  |  | 2637 |  | 2637 |  |  | 26/09/2026 | 2026-01-10 |  |  | 2637 |  | 2637
ADIDAS | 0903309895-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2638 | 30/09/2026 | 2638 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309895 JE6419 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 2638 |  | 2638 |  |  | 19/09/2026 | 23/09/2026 | 29/08/2026 | 2026-08-09 | 2638 | 2484 | 154
ADIDAS | 0903309897-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 5722 | 30/09/2026 | 5722 | SI | SI26/06/2026 | G3D,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309897 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | ESS SWTP |  | SS27 | 30/09/2026 | 2026-08-10 |  |  | 5722 |  | 5722 |  |  | 26/09/2026 | 2026-05-10 |  |  | 5722 |  | 5722
ADIDAS | 0903309899-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 24312 | 15/09/2026 | 24312 | SA | SA10/07/2026 | G1E,G1F,G1K,G1N,G1P,G2A,G2R,G3D,G3G,G3H,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309899 IB8688 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 22/09/2026 | 31/08/2026 | 14/09/2026 | 24312 | 14855 | 9457 |  | 184 | 27/08/2026 | 18/09/2026 | 24/08/2026 | 14/09/2026 | 24312 | 18228 | 6084 |  | 251
ADIDAS | 0903309900-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2100 | 15/10/2026 | 2100 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309900 JE6338 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 3S FT FZ HD |  | SS27 | 20/10/2026 | 24/10/2026 |  |  | 2100 |  | 2100 |  |  | 16/10/2026 | 21/10/2026 |  |  | 2100 |  | 2100
ADIDAS | 0903309901-1 HK7319 | BLACK | 90D | F2225M403 | 5282 | 30/09/2026 | 5282 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309901 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-08-10 |  |  | 5282 |  | 5282 |  |  | 24/09/2026 | 2026-05-10 |  |  | 5282 |  | 5282
ADIDAS | 0903309902-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2940 | 15/10/2026 | 2940 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309902 JD1877 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 2940 |  | 2940 |  |  | 2026-01-10 | 2026-06-10 |  |  | 2940 |  | 2940
ADIDAS | 0903309903-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1051 | 15/10/2026 | 1051 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309903 JM1775 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1051 |  | 1051 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1051 |  | 1051
ADIDAS | 0903309904-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 24142 | 15/09/2026 | 24142 | SA | SA10/07/2026 | G1E,G1F,G1K,G1N,G1P,G2A,G2R,G2T,G3G,G3H,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309904 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 22/09/2026 | 2026-01-09 | 14/09/2026 | 24142 | 17155 | 6987 |  | 1991 | 27/08/2026 | 18/09/2026 | 2026-01-09 | 14/09/2026 | 24142 | 19248 | 4894 |  | 1240
ADIDAS | 0903309905-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2642 | 30/09/2026 | 2642 | SI | SI26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Gistex, (3S) PI Date 10-Aug, actual receives 06-Aug (using fabric stock from libolon). T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309905 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV SHO |  | SS27 | 24/09/2026 | 29/09/2026 |  |  | 2642 |  | 2642 |  |  | 21/09/2026 | 25/09/2026 |  |  | 2642 |  | 2642
ADIDAS | 0903309907-1 HK7309 | BLACK | 45D | F2225M402 | 24310 | 15/09/2026 | 24310 | SA | SA10/07/2026 | G1F,G1K,G1N,G1P,G2T,G3G,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309907 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 22/09/2026 | 28/08/2026 | 14/09/2026 | 24310 | 19159 | 5151 |  | 1024 | 27/08/2026 | 18/09/2026 | 27/08/2026 | 14/09/2026 | 24310 | 21123 | 3187 |  | 392
ADIDAS | 0903309910-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1512 | 15/10/2026 | 1512 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309910 JE6341 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 1512 |  | 1512 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1512 |  | 1512
ADIDAS | 0903316928-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) |  | 29/09: ex-fty (NYK warehouse). T2 Y.T.I, Body & mesh actual receives 05-Aug. 800005 | HT SUB PROCESS_V1 | 0903316928 KG8548 | 17/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-05-09 | 2026-07-09 | 327 | 304 | 23 |  |  | 29/08/2026 | 2026-12-09 | 2026-11-08 | 22/08/2026 | 327 | 327 |  |  |  | 28/08/2026 | 2026-11-09 | 2026-11-08 | 21/08/2026 | 327 | 327
ADIDAS | 0903316929-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 585 | 30/09/2026 | 585 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) |  | Waiting fabric (NYK warehouse). DRC 0064-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800005 | PRINT L2+HT SUB PROCESS_V3 | 0903316929 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | INDONESIA | SEA | 15/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 585 |  | 585 |  |  | 2026-11-09 | 2026-12-09 |  |  | 585 |  | 585 |  |  | 2026-10-09 | 2026-11-09 |  |  | 585 |  | 585
ADIDAS | 0903316930-1 KG8547 | ONIX | 90D | S2408WR1600 | 107 | 15/10/2026 | 107 | SI | SI30/06/2026 | G1I | T-SHIRT | G1 | ok |  | (NYK warehouse). T2 Y.T.I, body & mesh actual receives 08-Aug. 800005 | HT SUB PROCESS_V1 | 0903316930 KG8547 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 13/10/2026 |  |  | 107 |  | 107 |  |  | 2026-10-10 | 2026-10-10 |  |  | 107 |  | 107 |  |  | 2026-09-10 | 2026-09-10 |  |  | 107 |  | 107
ADIDAS | 0903322460-1 IN1159 | BLACK | 90D | S2408MR1601 | 331 | 2026-07-10 | 331 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT SUB PROCESS_V1 | 0903322460 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 331 |  | 331 |  |  | 21/09/2026 | 22/09/2026 |  |  | 331 |  | 331 |  |  | 19/09/2026 | 21/09/2026 |  |  | 331 |  | 331
ADIDAS | 0903322461-1 IN1157 | WHITE | 90D | S2408MR1600 | 335 | 15/10/2026 | 335 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 06-Aug. 516471 | HT SUB PROCESS_V1 | 0903322461 IN1157 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 335 |  | 335 |  |  | 28/09/2026 | 29/09/2026 | 2026-09-09 | 2026-12-09 | 335 | 308 | 27 |  | 16 | 26/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 335 | 308 | 27
ADIDAS | 0903322476-1 IN1157 | WHITE | 90D | S2408MR1600 | 845 | 2026-07-10 | 845 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, actual receives 06-Aug. T2 Fu Hsun, Mesh PI Date 03-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322476 IN1157 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 845 |  | 845 |  |  | 24/09/2026 | 25/09/2026 | 2026-10-09 | 2026-12-09 | 845 | 782 | 63 |  | 30 | 23/09/2026 | 24/09/2026 | 2026-03-09 | 14/09/2026 | 845 | 831 | 14 |  | 30
ADIDAS | 0903322477-1 IN1156 | BLACK | 90D | S2408MR1600 | 553 | 18/09/2026 | 553 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322477 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-02-09 | 2026-05-09 | 553 | 553 |  |  |  | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553
ADIDAS | 0903322478-1 IN1173 | WHITE | 90D | S2408WR1600 | 304 | 15/09/2026 | 304 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516471 | HT SUB PROCESS_V1 | 0903322478 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-04-09 | 2026-07-09 | 304 | 297 | 7 |  |  | 29/08/2026 | 2026-12-09 | 15/08/2026 | 15/08/2026 | 304 | 304 |  |  |  | 28/08/2026 | 2026-11-09 | 2026-11-08 | 2026-11-08 | 304 | 304
ADIDAS | 0903322479-1 IN1172 | BLACK | 90D | S2408WR1600 | 807 | 15/09/2026 | 807 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322479 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-03-09 | 2026-07-09 | 807 | 802 | 5 |  |  | 29/08/2026 | 2026-12-09 | 26/08/2026 | 2026-07-09 | 807 | 805 | 2 |  |  | 28/08/2026 | 2026-11-09 | 26/08/2026 | 2026-12-09 | 807 | 807 |  |  | 1
ADIDAS | 0903322480-1 IN1156 | BLACK | 90D | S2408MR1600 | 924 | 15/09/2026 | 924 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) 516471 | HT SUB PROCESS_V1 | 0903322480 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 15/09/2026 | 2026-01-09 | 2026-07-09 | 924 | 922 | 2 |  |  | 27/08/2026 | 2026-12-09 | 22/08/2026 | 2026-09-09 | 924 | 924 |  |  |  | 26/08/2026 | 2026-11-09 | 22/08/2026 | 2026-08-09 | 924 | 924
ADIDAS | 0903322484-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 2026-07-10 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322484 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 23/09/2026 | 26/08/2026 | 2026-02-09 | 300 | 297 | 3 |  |  | 21/09/2026 | 22/09/2026 | 24/08/2026 | 2026-05-09 | 300 | 300
ADIDAS | 0903322486-1 IN1172 | BLACK | 90D | S2408WR1600 | 265 | 15/10/2026 | 265 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322486 IN1172 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 265 |  | 265 |  |  | 14/10/2026 | 15/10/2026 |  |  | 265 |  | 265 |  |  | 13/10/2026 | 14/10/2026 | 2026-05-09 | 2026-05-09 | 265 | 188 | 77
ADIDAS | 0903322488-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 352 | 2026-07-10 | 352 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516471 | HT SUB PROCESS_V1 | 0903322488 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 352 |  | 352 |  |  | 24/09/2026 | 25/09/2026 | 2026-07-09 | 14/09/2026 | 352 | 175 | 177 |  | 4 | 23/09/2026 | 24/09/2026 | 2026-07-09 | 2026-12-09 | 352 | 177 | 175 |  | 39
ADIDAS | 0903322491-1 IN1172 | BLACK | 90D | S2408WR1600 | 324 | 30/09/2026 | 324 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322491 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 324 |  | 324 |  |  | 24/09/2026 | 25/09/2026 | 26/08/2026 | 2026-07-09 | 324 | 324 |  |  |  | 23/09/2026 | 24/09/2026 | 26/08/2026 | 2026-04-09 | 324 | 324
ADIDAS | 0903322492-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 254 | 2026-07-10 | 254 | NT | NT24/04/2026 | G1M | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516471 | HT SUB PROCESS_V1 | 0903322492 IT1824 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | ADIZERO E TEE |  | FW26 | 2026-08-10 | 2026-08-10 |  |  | 254 |  | 254 |  |  | 2026-06-10 | 2026-06-10 | 2026-05-08 | 2026-10-08 | 254 | 254 |  |  |  | 2026-05-10 | 2026-05-10 | 2026-05-08 | 2026-10-08 | 254 | 254
ADIDAS | 0903353862-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353862 KC6387 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | K BLANK TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 400 |  | 400 |  |  | 29/09/2026 | 29/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903361428-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 369 | 30/09/2026 | 369 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361428 KT7554 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | M CLUB AM TAT |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 369 |  | 369 |  |  | 23/09/2026 | 24/09/2026 | 2026-11-09 | 2026-12-09 | 369 | 341 | 28 |  | 168
ADIDAS | 0903361937-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361937 KD9090 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | K BLANK TEE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 400 |  | 400 |  |  | 28/09/2026 | 29/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903362075-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 531 | 15/09/2026 | 531 | ID | ID31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 14/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903362075 KB5965 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee M |  | SS27-TI-SLT | 2026-05-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 531 | 531 |  |  |  | 2026-02-09 | 2026-04-09 | 29/08/2026 | 2026-08-09 | 531 | 531 |  |  |  | 31/08/2026 | 2026-02-09 | 29/08/2026 | 2026-07-09 | 531 | 531
ADIDAS | 0903365289-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 650 | 2026-07-10 | 650 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365289 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-07-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-07-10 | 2026-08-10 |  |  | 650 |  | 650 |  |  | 2026-03-10 | 2026-05-10 |  |  | 650 |  | 650 |  |  | 2026-01-10 | 2026-02-10 |  |  | 650 |  | 650
ADIDAS | 0903365322-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 500 | 2026-07-10 | 500 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365322 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-06-10 | 2026-07-10 |  |  | 500 |  | 500 |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 31/08/2026 | 500 | 340 | 160 |  |  | 30/09/2026 | 2026-01-10 | 27/08/2026 | 29/08/2026 | 500 | 500
ADIDAS | 0903365354-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 850 | 31/08/2026 | 850 | ID | ID31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 31/08: ex-fty 823016 | HT+PAD SUB PROCESS_V3 | 0903365354 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 29/08/2026 | Run Ess Tee M |  | SS27-TI-SLT | 29/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 850 | 850 |  |  |  | 26/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 850 | 850 |  |  |  | 21/08/2026 | 24/08/2026 | 22/08/2026 | 28/08/2026 | 850 | 850
ADIDAS | 0903365391-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 2350 | 31/08/2026 | 2350 | ID | ID31/07/2026 | G2G,G2H,G2J,G2K | T-SHIRT | G2 | ok |  | 31/08: ex-fty 823016 | HT+PAD SUB PROCESS_V3 | 0903365391 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 28/08/2026 | Run Ess Tee M |  | SS27-TI-SLT | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 2350 | 2350 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 2026-03-09 | 2350 | 2318 | 32 |  |  | 20/08/2026 | 24/08/2026 | 29/08/2026 | 31/08/2026 | 2350 | 2350
ADIDAS | 0903366562-1 IS1413 | BLACK | 60D | S2425M405 | 7 | 30/09/2026 | 7 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903366562 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 7 |  | 7 |  |  | 2026-11-09 | 2026-12-09 |  |  | 7 |  | 7
ADIDAS | 0903368552-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2520 | 15/09/2026 | 2520 | SA | SA31/07/2026 | G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368552 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 2520 | 2198 | 322 |  | 296 | 2026-03-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 2520 | 2392 | 128 |  | 205
ADIDAS | 0903368635-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 401 | 15/09/2026 | 401 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368635 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | ESS HDY |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-10-09 | 2026-11-09 | 401 | 401 |  |  |  | 2026-05-09 | 2026-12-09 | 2026-10-09 | 13/09/2026 | 401 | 315 | 86 |  | 7
ADIDAS | 0903369017-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 535 | 30/09/2026 | 535 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 25/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369017 IU0217 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 535 |  | 535 |  |  | 2026-12-09 | 2026-12-09 |  |  | 535 |  | 535
ADIDAS | 0903369058-1 IS1413 | BLACK | 60D | S2425M405 | 374 | 30/09/2026 | 374 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369058 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 374 |  | 374 |  |  | 2026-11-09 | 2026-12-09 |  |  | 374 |  | 374
ADIDAS | 0903369096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 514 | 30/09/2026 | 514 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 24/09: ex-fty 672027 | PRINT L3+PAD SUB PROCESS_V3 | 0903369096 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | BRAZIL | SEA | 22/09/2026 | POS TABLE LK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 514 |  | 514 |  |  | 18/09/2026 | 18/09/2026 | 2026-08-09 | 2026-09-09 | 514 | 506 | 8
ADIDAS | 0903370885-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G3G | SWEATSHIRT | G3 | (02/09/2026) |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370885 IB8688 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-09 | ESS HDY |  | SS27 | 2026-12-09 | 22/09/2026 | 2026-12-09 | 14/09/2026 | 1840 | 391 | 1449 |  | 329 | 2026-09-09 | 18/09/2026 | 2026-12-09 | 14/09/2026 | 1840 | 1100 | 740 |  | 947
ADIDAS | 0903370934-1 HK7309 | BLACK | 45D | F2225M402 | 399 | 15/09/2026 | 399 | SA | SA31/07/2026 | G1K | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370934 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-10-09 | 2026-11-09 | 399 | 354 | 45 |  |  | 2026-04-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 399 | 396 | 3 |  | 20
ADIDAS | 0903370987-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 600 | 15/09/2026 | 600 | SA | SA31/07/2026 | G2A | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370987 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-10-09 | 2026-12-09 | 600 | 519 | 81 |  | 66 | 2026-04-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 600 | 563 | 37 |  | 8
ADIDAS | 0903371106-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1800 | 15/10/2026 | 1800 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903371106 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | RELEASED |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 1800 |  | 1800 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1800 |  | 1800
ADIDAS | 0903371472-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 400 | 2026-02-10 | 400 | SI | SI31/07/2026 | G2T | SWEATSHIRT | G2 | (16/09/2026) |  | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371472 JE6374 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-08-10 | M 3S FT SWT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 400 |  | 400 |  |  | 2026-05-10 | 2026-06-10 |  |  | 400 |  | 400
ADIDAS | 0903371511-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903371511 IW2479 | 2026-03-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903372828-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT-SLT | 149 | 2026-09-09 | 149 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 09/09: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903372828 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27-SLT | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 149 | 149 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 149 | 149
ADIDAS | 0903372885-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1E,G1F | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372885 HK7309 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-04-09 | ESS HDY |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-09-09 | 14/09/2026 | 1495 | 723 | 772 |  | 76 | 2026-01-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1495 | 1142 | 353 |  | 170
ADIDAS | 0903372967-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 296 | 30/09/2026 | 296 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903372967 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 296 |  | 296 |  |  | 2026-12-09 | 15/09/2026 | 2026-11-09 | 2026-11-09 | 296 | 247 | 49
ADIDAS | 0903373006-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373006 HK7311 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-03-09 | ESS HDY |  | SS27 | 2026-03-09 | 22/09/2026 | 2026-09-09 | 2026-12-09 | 1379 | 1333 | 46 |  | 29 | 31/08/2026 | 18/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1296 | 83 |  | 13
ADIDAS | 0903373118-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug.. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373118 IB8688 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 18/09/2026 | 2026-10-09 | 14/09/2026 | 1840 | 1697 | 143 |  | 217 | 2026-03-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1840 | 1712 | 128 |  | 13
ADIDAS | 0903373810-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373810 LI2671 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 18/09/2026 | 19/09/2026 | 2026-09-09 | 2026-09-09 | 10 | 6 | 4
ADIDAS | 0903373816-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1K,G1P | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373816 HK7309 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 18/09/2026 | 2026-10-09 | 14/09/2026 | 1495 | 1284 | 211 |  | 28 | 2026-04-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1495 | 1481 | 14 |  | 87
ADIDAS | 0903373846-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373846 LI2645 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 15/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 10 |  | 10 |  |  | 2026-11-09 | 2026-12-09 |  |  | 10 |  | 10
ADIDAS | 0903373872-1 HK7309 | BLACK | 45D | F2225M402 | 2730 | 15/09/2026 | 2730 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373872 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 2730 | 1960 | 770 |  | 772 | 2026-03-09 | 14/09/2026 | 2026-10-09 | 13/09/2026 | 2730 | 2418 | 312 |  | 455
ADIDAS | 0903373878-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373878 LI2672 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 10 |  | 10 |  |  | 17/09/2026 | 18/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373912-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373912 LI2647 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 10 |  | 10 |  |  | 28/09/2026 | 29/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373945 LI2646 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 10 |  | 10 |  |  | 16/09/2026 | 16/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903374039-1 HK7309 | BLACK | 45D | F2225M402 | 3000 | 15/09/2026 | 3000 | SA | SA31/07/2026 | G1N | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903374039 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | ESS HDY |  | SS27 | 14/09/2026 | 19/09/2026 | 14/09/2026 | 14/09/2026 | 3000 | 75 | 2925 |  |  | 2026-10-09 | 16/09/2026 | 13/09/2026 | 14/09/2026 | 3000 | 804 | 2196
ADIDAS | 0903374608-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374608 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 460 |  | 460 |  |  | 2026-12-09 | 14/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903374883-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 103 | 30/09/2026 | 103 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374883 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 103 |  | 103 |  |  | 16/09/2026 | 16/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903374908-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374908 LI2668 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 107 |  | 107 |  |  | 15/09/2026 | 15/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903374971-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 111 | 30/09/2026 | 111 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374971 LI2669 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 111 |  | 111 |  |  | 15/09/2026 | 15/09/2026 | 2026-12-09 | 2026-12-09 | 111 | 29 | 82 |  | 29
ADIDAS | 0903375054-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 519 | 30/09/2026 | 519 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903375054 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-03-10 | M L SLIDE PKT T |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 519 |  | 519 |  |  | 30/09/2026 | 2026-01-10 |  |  | 519 |  | 519 |  |  | 28/09/2026 | 29/09/2026 |  |  | 519 |  | 519
ADIDAS | 0903375519-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 413 | 29/08/2026 | 413 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903375519 KC6387 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 413 | 413 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 29/08/2026 | 413 | 413
ADIDAS | 0903375565-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 968 | 29/08/2026 | 968 | SA | SA31/07/2026 | G2G,G2H | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903375565 KC6387 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 968 | 968 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 29/08/2026 | 968 | 968
ADIDAS | 0903375868-1 HK7309 | BLACK | 45D | F2225M402 | 780 | 15/09/2026 | 780 | SA | SA31/07/2026 | G1P | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375868 HK7309 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | ESS HDY |  | SS27 | 2026-10-09 | 18/09/2026 | 2026-11-09 | 14/09/2026 | 780 | 554 | 226 |  | 169 | 2026-07-09 | 15/09/2026 | 2026-11-09 | 13/09/2026 | 780 | 711 | 69 |  | 343
ADIDAS | 0903376260-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 246 | 30/09/2026 | 246 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903376260 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 246 |  | 246 |  |  | 26/09/2026 | 28/09/2026 |  |  | 246 |  | 246
ADIDAS | 0903377653-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 167 | 30/09/2026 | 167 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377653 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 167 |  | 167 |  |  | 17/09/2026 | 18/09/2026 |  |  | 167 |  | 167
ADIDAS | 0903377680-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 175 | 30/09/2026 | 175 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377680 LI2671 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 175 |  | 175 |  |  | 18/09/2026 | 19/09/2026 | 2026-09-09 | 2026-11-09 | 175 | 168 | 7
ADIDAS | 0903378323-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 923 | 23/09/2026 | 923 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378323 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 923 |  | 923 |  |  | 2026-11-09 | 2026-12-09 |  |  | 923 |  | 923
ADIDAS | 0903378381-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 657 | 23/09/2026 | 657 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378381 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 657 |  | 657 |  |  | 2026-12-09 | 2026-12-09 |  |  | 657 |  | 657
ADIDAS | 0903378401-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 140 | 30/09/2026 | 140 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378401 LI2646 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 140 |  | 140 |  |  | 16/09/2026 | 16/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903378433-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI31/07/2026 | G1M | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378433 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 230 |  | 230 |  |  | 29/09/2026 | 30/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903378476-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378476 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 113 |  | 113 |  |  | 17/09/2026 | 18/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903378501-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 114 | 30/09/2026 | 114 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378501 LI2667 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 114 |  | 114 |  |  | 2026-12-09 | 15/09/2026 |  |  | 114 |  | 114
ADIDAS | 0903378523-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 121 | 30/09/2026 | 121 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378523 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 121 |  | 121 |  |  | 15/09/2026 | 15/09/2026 | 2026-12-09 | 2026-12-09 | 121 | 109 | 12 |  | 109
ADIDAS | 0903378603-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 351 | 23/09/2026 | 351 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378603 LI2646 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 351 |  | 351 |  |  | 14/09/2026 | 16/09/2026 |  |  | 351 |  | 351
ADIDAS | 0903378692-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 132 | 23/09/2026 | 132 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026(2)) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378692 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-12-09 | 14/09/2026 |  |  | 132 |  | 132 |  |  | 2026-09-09 | 2026-10-09 |  |  | 132 |  | 132
ADIDAS | 0903378741-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 721 | 15/09/2026 | 721 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378741 HK7311 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | ESS HDY |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-10-09 | 14/09/2026 | 721 | 573 | 148 |  | 27 | 2026-05-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 721 | 508 | 213 |  | 34
ADIDAS | 0903378980-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 153 | 2026-07-10 | 153 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | (12/09/2026) |  | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378980 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 153 |  | 153 |  |  | 29/09/2026 | 30/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903379027-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 960 | 15/09/2026 | 960 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379027 IB8688 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | ESS HDY |  | SS27 | 2026-03-09 | 22/09/2026 | 2026-09-09 | 2026-12-09 | 960 | 952 | 8 |  | 209 | 31/08/2026 | 18/09/2026 | 2026-08-09 | 2026-12-09 | 960 | 909 | 51 |  | 1
ADIDAS | 0903379083-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/09/2026 | 2000 | SA | SA31/07/2026 | G2A,G2R,G2T | SWEATSHIRT | G2 | (02/09/2026) |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379083 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 18/09/2026 | 2026-12-09 | 14/09/2026 | 2000 | 1153 | 847 |  | 819 | 2026-03-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 2000 | 1663 | 337 |  | 553
ADIDAS | 0903379104-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 3360 | 15/09/2026 | 3360 | SA | SA31/07/2026 | G2T,G3A,G3H,G3I | SWEATSHIRT | G2,G3 | (02/09/2026) |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379104 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | ESS HDY |  | SS27 | 2026-09-09 | 18/09/2026 | 2026-12-09 | 14/09/2026 | 3360 | 908 | 2452 |  | 501 | 2026-05-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 3360 | 2576 | 784 |  | 945
ADIDAS | 0903380322-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380322 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 109 |  | 109 |  |  | 28/09/2026 | 29/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380373-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 109 | 30/09/2026 | 109 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380373 LI2672 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 109 |  | 109 |  |  | 17/09/2026 | 18/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380504-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380504 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 460 |  | 460 |  |  | 14/09/2026 | 16/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903380521-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380521 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 32 |  | 32 |  |  | 16/09/2026 | 16/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380549-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 32 | 30/09/2026 | 32 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380549 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 32 |  | 32 |  |  | 17/09/2026 | 18/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380551-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 1254 | 2026-09-09 | 1254 | NT | NT31/07/2026 | G2Q | PANTS | G2 | ok |  | 09/09: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903380551 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-09 | M FEELCOZY PANT |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 1254 | 1254 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 1254 | 1254
ADIDAS | 0903380577-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380577 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 32 |  | 32 |  |  | 26/09/2026 | 28/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380602-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 65 | 30/09/2026 | 65 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380602 LI2645 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 65 |  | 65 |  |  | 2026-11-09 | 2026-12-09 |  |  | 65 |  | 65
ADIDAS | 0903380624-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 442 | 23/09/2026 | 442 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380624 LI2668 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 442 |  | 442 |  |  | 2026-10-09 | 2026-11-09 |  |  | 442 |  | 442
ADIDAS | 0903380631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 50 | 30/09/2026 | 50 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380631 LI2667 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 16/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 50 |  | 50 |  |  | 2026-12-09 | 15/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903380648-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380648 HK7311 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 22/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1136 | 243 |  | 8 | 2026-03-09 | 18/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1327 | 52 |  | 15
ADIDAS | 0903380684-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 393 | 30/09/2026 | 393 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380684 LI2647 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 393 |  | 393 |  |  | 28/09/2026 | 29/09/2026 |  |  | 393 |  | 393
ADIDAS | 0903380949-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 130 | 30/09/2026 | 130 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380949 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 130 |  | 130 |  |  | 28/09/2026 | 29/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903380973-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 327 | 30/09/2026 | 327 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380973 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 327 |  | 327 |  |  | 26/09/2026 | 28/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903381000-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381000 LI2671 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 113 |  | 113 |  |  | 18/09/2026 | 19/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903381024-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 379 | 30/09/2026 | 379 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381024 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 379 |  | 379 |  |  | 26/09/2026 | 28/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903381048-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 265 | 30/09/2026 | 265 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381048 LI2672 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 265 |  | 265 |  |  | 17/09/2026 | 18/09/2026 |  |  | 265 |  | 265
ADIDAS | 0903381067-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 271 | 15/10/2026 | 271 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381067 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 29/09/2026 | M BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 271 |  | 271 |  |  | 25/09/2026 | 26/09/2026 |  |  | 271 |  | 271
ADIDAS | 0903381072-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 241 | 2026-07-10 | 241 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381072 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 241 |  | 241 |  |  | 2026-11-09 | 2026-12-09 |  |  | 241 |  | 241
ADIDAS | 0903381723-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 130 | 30/09/2026 | 130 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381723 LI2668 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 130 |  | 130 |  |  | 15/09/2026 | 15/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903381763-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 23/09/2026 | 150 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381763 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 150 |  | 150 |  |  | 2026-10-09 | 2026-11-09 | 2026-09-09 | 2026-12-09 | 150 | 150 |  |  | 2
ADIDAS | 0903381803-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 498 | 23/09/2026 | 498 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381803 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 498 |  | 498 |  |  | 2026-10-09 | 2026-11-09 |  |  | 498 |  | 498
ADIDAS | 0903381828-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 568 | 23/09/2026 | 568 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381828 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 568 |  | 568 |  |  | 2026-12-09 | 15/09/2026 | 2026-11-09 | 2026-11-09 | 568 | 544 | 24
ADIDAS | 0903381881-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 732 | 30/09/2026 | 732 | SA | SA31/07/2026 | G1F | SWEATSHIRT | G1 | (02/09/2026) |  | 21/09: ex-fty 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381881 HK7311 | 2026-03-09 | KAHATEX CIJERAH | CANADA | SEA | 17/09/2026 | ESS HDY |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 732 |  | 732 |  |  | 14/09/2026 | 15/09/2026 |  |  | 732 |  | 732
ADIDAS | 0903382128-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 511 | 31/08/2026 | 511 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L1 SUB PROCESS_V3 | 0903382128 JC8238 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | W LIN SJ T |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 511 | 511 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 511 | 511
ADIDAS | 0903382140-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 420 | 2026-09-09 | 420 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903382140 IW2479 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 420 | 420 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 420 | 420
ADIDAS | 0903382660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 40 | 30/09/2026 | 40 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382660 LI2671 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 40 |  | 40 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 40 | 23 | 17
ADIDAS | 0903382688-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 50 | 30/09/2026 | 50 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382688 LI2646 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 50 |  | 50 |  |  | 16/09/2026 | 16/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903382689-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 149 | 30/09/2026 | 149 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382689 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 149 |  | 149 |  |  | 17/09/2026 | 18/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903382714-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 40 | 30/09/2026 | 40 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382714 LI2668 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 40 |  | 40 |  |  | 15/09/2026 | 15/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903382830-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2D,G2P | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382830 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M FEELCOZY HD |  | SS27 | 2026-08-09 | 19/09/2026 | 2026-08-09 | 14/09/2026 | 15000 | 8971 | 6029 |  | 2090 | 2026-04-09 | 16/09/2026 | 2026-08-09 | 14/09/2026 | 15000 | 12756 | 2244 |  | 1890
ADIDAS | 0903383240-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 23/09/2026 | 234 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903383240 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 234 |  | 234 |  |  | 2026-10-09 | 2026-11-09 |  |  | 234 |  | 234
ADIDAS | 0903383252-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 292 | 15/10/2026 | 292 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383252 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/09/2026 | M BLANK TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 292 |  | 292 |  |  | 26/09/2026 | 28/09/2026 |  |  | 292 |  | 292
ADIDAS | 0903384022-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 3923 | 29/08/2026 | 3923 | SA | SA31/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok |  | 29/08: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903384022 KD9094 | 20/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 29/08/2026 | 27/08/2026 | 29/08/2026 | 3923 | 3923 |  |  |  | 20/08/2026 | 26/08/2026 | 24/08/2026 | 29/08/2026 | 3923 | 3923
ADIDAS | 0903384056-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 5972 | 28/08/2026 | 5972 | SA | SA31/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok |  | 28/08: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903384056 KC6386 | 20/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 5972 | 5972 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 31/08/2026 | 5972 | 5963 | 9
ADIDAS | 0903384138-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 104 | 30/09/2026 | 104 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 29/09: ex-fty 839055 | PRINT L2 SUB PROCESS_V3 | 0903384138 KB7172 | 16/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-05-10 | HOT COMMUNITY |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 104 |  | 104 |  |  | 2026-01-10 | 2026-01-10 |  |  | 104 |  | 104
ADIDAS | 0903384150-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT-SLT | 1272 | 28/08/2026 | 1272 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 27/08: ex-fty 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384150 JD5302 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W 3S FT CF PT |  | SS27-SLT | 26/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 1272 | 1272 |  |  |  | 20/08/2026 | 24/08/2026 | 22/08/2026 | 31/08/2026 | 1272 | 1272
ADIDAS | 0903384172-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 498 | 28/08/2026 | 498 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 28/08: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903384172 JC8238 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W LIN SJ T |  | SS27-SLT | 26/08/2026 | 28/08/2026 | 28/08/2026 | 28/08/2026 | 498 | 498 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 31/08/2026 | 498 | 498
ADIDAS | 0903384176-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 480 | 2026-09-09 | 480 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903384176 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 480 | 480 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-04-09 | 2026-08-09 | 480 | 480
ADIDAS | 0903384200-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT-SLT | 765 | 31/08/2026 | 765 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 29/08: ex-fty 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384200 JD5302 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 765 | 765 |  |  |  | 24/08/2026 | 27/08/2026 | 26/08/2026 | 29/08/2026 | 765 | 765
ADIDAS | 0903384236-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 514 | 31/08/2026 | 514 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 31/08: ex-fty 516342 | PRINT L1 SUB PROCESS_V3 | 0903384236 JC8238 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W LIN SJ T |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 514 | 514 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 31/08/2026 | 514 | 514
ADIDAS | 0903384949-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 1138 | 2026-07-10 | 1138 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903384949 JC5283 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-06-10 | M L SLIDE PKT T |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1138 |  | 1138 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1138 |  | 1138 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1138 |  | 1138
ADIDAS | 0903385022-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 1278 | 2026-07-10 | 1278 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385022 JC5282 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-10 | M L SLIDE PKT T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1278 |  | 1278 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1278 |  | 1278
ADIDAS | 0903385097-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 1076 | 2026-07-10 | 1076 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 1st Art (TC 10 pcs) 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385097 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 1076 |  | 1076 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1076 |  | 1076 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1076 |  | 1076
ADIDAS | 0903385968-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 100 | 15/10/2026 | 100 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903385968 KD3936 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | RELEASED |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903386031-1 KY7166 | BLACK | 75D | S2706CHCC008 | 1328 | 15/10/2026 | 1328 | ID | ID31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386031 KY7166 |  | KAHATEX CIJERAH | CHILE | SEA | 15/10/2026 | CC DNA SHO BLACK |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 1328 |  | 1328 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1328 |  | 1328
ADIDAS | 0903386171-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2E,G2F,G2Q,G2S | PANTS | G2 | ok |  | 14/09: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903386171 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M FEELCOZY PANT |  | SS27 | 2026-09-09 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 15000 | 10980 | 4020 |  | 2493 | 2026-05-09 | 14/09/2026 | 2026-07-09 | 14/09/2026 | 15000 | 14652 | 348 |  | 2117
ADIDAS | 0903386207-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 248 | 29/08/2026 | 248 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | ok |  | 29/08: ex-fty 839055 | EMBRO SUB PROCESS_V1 | 0903386207 KD9090 | 20/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 248 | 248 |  |  |  | 24/08/2026 | 26/08/2026 | 24/08/2026 | 29/08/2026 | 248 | 248
ADIDAS | 0903386305-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 230 | 30/09/2026 | 230 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 22/09: ex-fty 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903386305 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | MINI EMB T |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 230 |  | 230 |  |  | 18/09/2026 | 19/09/2026 |  |  | 230 |  | 230 |  |  | 16/09/2026 | 17/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903387168-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903387168 LI2667 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 107 |  | 107 |  |  | 2026-12-09 | 15/09/2026 | 2026-11-09 | 2026-11-09 | 107 | 81 | 26
ADIDAS | 0903387206-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 463 | 23/09/2026 | 463 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903387206 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 463 |  | 463 |  |  | 2026-10-09 | 2026-11-09 |  |  | 463 |  | 463
ADIDAS | 0903388753-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 450 | 31/08/2026 | 450 | SA | SA31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 31/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903388753 KD9090 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | K BLANK TEE |  | SS27 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 450 | 450 |  |  |  | 26/08/2026 | 27/08/2026 | 26/08/2026 | 31/08/2026 | 450 | 450
ADIDAS | 0903388790-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 1096 | 28/08/2026 | 1096 | SA | SA31/07/2026 | G2C,G2G | T-SHIRT | G2 | ok |  | 28/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903388790 KD9090 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | K BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1096 | 1096 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1096 | 1096
ADIDAS | 0903389129-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903389129 KW1544 |  | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | M BLANK TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 800 |  | 800 |  |  | 26/09/2026 | 28/09/2026 |  |  | 800 |  | 800
ADIDAS | 0903389678-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 207 | 30/09/2026 | 207 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 29/09: ex-fty (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903389678 KD3911 | 16/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/09/2026 | RELEASED |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 207 |  | 207 |  |  | 2026-10-09 | 2026-11-09 |  |  | 207 |  | 207
ADIDAS | 0903389758-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 25/09: ex-fty 814006 | EMBRO SUB PROCESS_V1 | 0903389758 KD3911 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/09/2026 | RELEASED |  | SS27 | 14/09/2026 | 15/09/2026 |  |  | 109 |  | 109 |  |  | 2026-10-09 | 2026-11-09 |  |  | 109 |  | 109
ADIDAS | 0903389769-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 232 | 30/09/2026 | 232 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903389769 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 232 |  | 232 |  |  | 18/09/2026 | 19/09/2026 |  |  | 232 |  | 232
ADIDAS | 0903389808-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 415 | 23/09/2026 | 415 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903389808 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 14/09/2026 | 14/09/2026 |  |  | 415 |  | 415 |  |  | 2026-10-09 | 2026-10-09 | 2026-11-09 | 2026-11-09 | 415 | 354 | 61
ADIDAS | 0903390259-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390259 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 25/09/2026 | MINI EMB T |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 22/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 19/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903390291-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903390291 IW2479 | 2026-03-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-08-09 | 276 | 276
ADIDAS | 0903390301-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 2062 | 15/10/2026 | 2062 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903390301 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-08-10 | M L SLIDE PKT T |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 2062 |  | 2062 |  |  | 2026-05-10 | 2026-06-10 |  |  | 2062 |  | 2062 |  |  | 2026-02-10 | 2026-03-10 |  |  | 2062 |  | 2062
ADIDAS | 0903391446-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 1098 | 28/08/2026 | 1098 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | ok |  | 28/08: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903391446 KC6386 | 20/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1098 | 1098 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 29/08/2026 | 1098 | 1098
ADIDAS | 0903391655-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903391655 KW1543 |  | KAHATEX CIJERAH | VIETNAM | SEA | 29/09/2026 | M BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 800 |  | 800 |  |  | 25/09/2026 | 26/09/2026 |  |  | 800 |  | 800
ADIDAS | 0903393703-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 1833 | 2026-12-09 | 1833 | NT | NT31/07/2026 | G2P | SWEATSHIRT | G2 | ok |  | 10/09: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393703 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M FEELCOZY HD |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-10-09 | 1833 | 1833 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-04-09 | 2026-11-09 | 1833 | 1833
ADIDAS | 0903394768-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 891 | 30/09/2026 | 891 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394768 KA5090 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | MINI EMB T |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 891 |  | 891 |  |  | 18/09/2026 | 19/09/2026 |  |  | 891 |  | 891 |  |  | 16/09/2026 | 17/09/2026 | 2026-09-09 | 2026-09-09 | 891 |  | 891
ADIDAS | 0903394796-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 940 | 30/09/2026 | 940 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394796 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | MINI EMB T |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 940 |  | 940 |  |  | 19/09/2026 | 21/09/2026 |  |  | 940 |  | 940 |  |  | 17/09/2026 | 18/09/2026 |  |  | 940 |  | 940
ADIDAS | 0903396292-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 316 | 15/10/2026 | 316 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396292 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-10 | K BLANK TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 316 |  | 316 |  |  | 29/09/2026 | 29/09/2026 |  |  | 316 |  | 316
ADIDAS | 0903396384-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 435 | 15/10/2026 | 435 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396384 KD9090 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-10 | K BLANK TEE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 435 |  | 435 |  |  | 28/09/2026 | 29/09/2026 |  |  | 435 |  | 435
ADIDAS | 0903396585-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT-SLT | 3823 | 28/08/2026 | 3823 | ID | ID31/07/2026 | G3F | PANTS | G3 | ok |  | 27/08: ex-fty 516471 | EMBRO SUB PROCESS_V1 | 0903396585 JE3854 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | M FEELCOZY PANT |  | SS27-SLT | 19/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 3823 | 3823 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 3823 | 3823
ADIDAS | 0903397832-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 356 | 30/09/2026 | 356 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397832 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-10 | M L SLIDE PKT T |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 356 |  | 356 |  |  | 30/09/2026 | 2026-01-10 |  |  | 356 |  | 356 |  |  | 28/09/2026 | 29/09/2026 | 2026-01-09 | 2026-01-09 | 356 | 1 | 355
ADIDAS | 0903397883-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 258 | 30/09/2026 | 258 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 28/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397883 JC5282 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-10 | M L SLIDE PKT T |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 258 |  | 258 |  |  | 30/09/2026 | 2026-01-10 |  |  | 258 |  | 258 |  |  | 28/09/2026 | 29/09/2026 | 2026-04-09 | 2026-04-09 | 258 | 1 | 257
ADIDAS | 0903402737-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 268 | 29/08/2026 | 268 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 839055 | EMBRO SUB PROCESS_V1 | 0903402737 KC6387 | 20/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 268 | 268 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 28/08/2026 | 268 | 268
ADIDAS | 0903445381-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 2861 | 30/09/2026 | 2861 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445381 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 2861 |  | 2861 |  |  | 15/09/2026 | 18/09/2026 | 2026-02-09 | 13/09/2026 | 2861 | 2498 | 363 |  | 1108
ADIDAS | 0903445382-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 24/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445382 LC6339 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 100 |  | 100 |  |  | 17/09/2026 | 18/09/2026 | 2026-09-09 | 2026-09-09 | 100 | 100
ADIDAS | 0903445383-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | (11/07/2026) | (04/07/2026) | 25/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445383 KX8877 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | M CHIP T WHITE |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 100 |  | 100 |  |  | 17/09/2026 | 17/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903445384-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 3083 | 30/09/2026 | 3083 | SA | SA26/06/2026 | G3B | PANTS | G3 | (08/08/2026) | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445384 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | W 3S FT OH PT |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 3083 |  | 3083 |  |  | 30/09/2026 | 2026-03-10 |  |  | 3083 |  | 3083
ADIDAS | 0903445385-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 3082 | 30/09/2026 | 3082 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903445385 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S FT QZ HD |  | SS27 | 21/09/2026 | 25/09/2026 |  |  | 3082 |  | 3082 |  |  | 17/09/2026 | 22/09/2026 |  |  | 3082 |  | 3082
ADIDAS | 0903450148-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1114 | 2026-05-09 | 1114 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450148 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-04-09 | 1114 | 1114 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-03-09 | 1114 | 1114 |  |  |  | 24/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 1114 | 1114
ADIDAS | 0903450149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 3791 | 2026-05-09 | 3791 | SA | SA15/05/2026 | G2J,G2K | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450149 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-04-09 | 3791 | 3791 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-02-09 | 3791 | 3791 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-02-09 | 3791 | 3791
ADIDAS | 0903450150-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 129 | 23/09/2026 | 129 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 21/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450150 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 129 | 129 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 29/08/2026 | 129 | 129
ADIDAS | 0903450152-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 172 | 23/09/2026 | 172 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 18/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450152 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 2026-12-08 | 2026-06-08 | 2026-07-08 | 172 | 172 |  |  |  | 2026-04-08 | 2026-07-08 | 31/07/2026 | 29/08/2026 | 172 | 168 | 4
ADIDAS | 0903450153-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 942 | 15/10/2026 | 942 | SA | SA24/01/2026 | G1M | T-SHIRT | G1 | ok |  | DRC 0010-hold shipment customer (BTP_24_06_2026 -> Req. PO Cancel & Quantity Change). T2 Far Eastern, PI Date 21-Sep (switch with fabric from Libolon for 500pcs). T2 Fu Hsun, PI Date 18-Aug. 814006 | HT SUB PROCESS_V1 | 0903450153 KG8548 | 2026-08-04 | KAHATEX CIJERAH | THAILAND | SEA | 30/06/2026 | ADIZERO E TEE |  | FW26 | 30/06/2026 | 15/09/2026 | 30/06/2026 | 2026-07-07 | 942 | 273 | 669 |  |  | 26/06/2026 | 2026-12-09 | 20/06/2026 | 20/06/2026 | 942 | 273 | 669 |  |  | 25/06/2026 | 2026-11-09 | 2026-12-08 | 2026-12-08 | 942 | 273 | 669
ADIDAS | 0903467951-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903467951 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 920 |  | 920 |  |  | 2026-08-10 | 2026-10-10 |  |  | 920 |  | 920
ADIDAS | 0903472791-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1P | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472791 IB8688 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | ESS HDY |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 2000 |  | 2000 |  |  | 21/09/2026 | 23/09/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903472864-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472864 IB8688 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 480 |  | 480 |  |  | 2026-08-10 | 2026-10-10 |  |  | 480 |  | 480
ADIDAS | 0903476466-1 JZ7711 | BLACK | 120D | S2608MR0202 | 249 | 23/09/2026 | 249 | SA | SA14/08/2026 | G3G | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903476466 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 22/09/2026 | 22/09/2026 |  |  | 249 |  | 249 |  |  | 18/09/2026 | 18/09/2026 |  |  | 249 |  | 249 |  |  | 15/09/2026 | 15/09/2026 |  |  | 249 |  | 249
ADIDAS | 0903478300-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 24/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478300 HK7311 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | ESS HDY |  | SS27 | 2026-08-10 | 2026-12-10 |  |  | 2001 |  | 2001 |  |  | 2026-05-10 | 2026-08-10 |  |  | 2001 |  | 2001
ADIDAS | 0903478487-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 202 | 15/09/2026 | 202 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478487 IN1172 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 |  |  | 202 |  | 202 |  |  | 2026-08-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 202 | 183 | 19 |  | 11 | 2026-07-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 202 | 199 | 3 |  | 38
ADIDAS | 0903478570-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478570 HK7311 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | ESS HDY |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 2001 |  | 2001 |  |  | 22/09/2026 | 26/09/2026 |  |  | 2001 |  | 2001
ADIDAS | 0903478582-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 139 | 15/09/2026 | 139 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478582 IN1156 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 139 | 89 | 50 |  | 18 | 2026-08-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 139 | 139 |  |  |  | 2026-07-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 139 | 139
ADIDAS | 0903478609-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 164 | 15/09/2026 | 164 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478609 IN1157 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 |  |  | 164 |  | 164 |  |  | 2026-08-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 164 | 127 | 37 |  | 110 | 2026-07-09 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 164 | 161 | 3 |  | 157
ADIDAS | 0903478627-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478627 HK7311 |  | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ESS HDY |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 920 |  | 920 |  |  | 13/10/2026 | 16/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903480271-1 IS1413 | BLACK | 60D | S2425M405 | 900 | 15/10/2026 | 900 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848024 | PRINT L3 SUB PROCESS_V3 | 0903480271 IS1413 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 21/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903480314-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903480314 KA5090 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 25/09/2026 | MINI EMB T |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 602 |  | 602 |  |  | 22/09/2026 | 22/09/2026 |  |  | 602 |  | 602 |  |  | 19/09/2026 | 19/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903480831-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 335 | 15/10/2026 | 335 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480831 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-10 | W BLANK TEE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 335 |  | 335 |  |  | 2026-06-10 | 2026-06-10 |  |  | 335 |  | 335
ADIDAS | 0903480958-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1F | SWEATSHIRT | G1 | (15/09/2026) |  | 26/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480958 HK7309 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | ESS HDY |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 2250 |  | 2250 |  |  | 15/09/2026 | 19/09/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903480993-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1679 | 15/10/2026 | 1679 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480993 HK7311 |  | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | ESS HDY |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1679 |  | 1679 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1679 |  | 1679
ADIDAS | 0903481767-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 5210 | 15/10/2026 | 5210 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903481767 KD9097 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-10 | W BLANK TEE |  | SS27 | 2026-09-10 | 14/10/2026 |  |  | 5210 |  | 5210 |  |  | 2026-06-10 | 2026-10-10 |  |  | 5210 |  | 5210
ADIDAS | 0903482244-1 HK7309 | BLACK | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482244 HK7309 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | ESS HDY |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 480 |  | 480 |  |  | 29/09/2026 | 2026-02-10 |  |  | 480 |  | 480
ADIDAS | 0903482398-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482398 HK7311 |  | KAHATEX CIJERAH | SPAIN | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 920 |  | 920 |  |  | 2026-12-10 | 13/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903482505-1 HK7309 | BLACK | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482505 HK7309 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | ESS HDY |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1680 |  | 1680 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1680 |  | 1680
ADIDAS | 0903483394-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483394 HK7309 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-10 | ESS HDY |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 920 |  | 920 |  |  | 29/09/2026 | 2026-02-10 |  |  | 920 |  | 920
ADIDAS | 0903483669-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483669 IB8688 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 2000 |  | 2000 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2000 |  | 2000
ADIDAS | 0903483726-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483726 IB8688 |  | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1680 |  | 1680 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903484758-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484758 HK7309 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | ESS HDY |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 2250 |  | 2250 |  |  | 28/09/2026 | 2026-01-10 |  |  | 2250 |  | 2250
ADIDAS | 0903484802-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 481 | 15/10/2026 | 481 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484802 HK7311 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ESS HDY |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 481 |  | 481 |  |  | 13/10/2026 | 16/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903484985-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484985 IB8688 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | ESS HDY |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920 |  |  | 2026-07-10 | 2026-08-10 |  |  | 920 |  | 920
ADIDAS | 0903485610-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 23/09/2026 | 100 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485610 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA | 16/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 16/09/2026 | 17/09/2026 |  |  | 100 |  | 100 |  |  | 2026-12-09 | 14/09/2026 |  |  | 100 |  | 100 |  |  | 2026-09-09 | 2026-10-09 |  |  | 100 |  | 100
ADIDAS | 0903486465-1 IS1413 | BLACK | 60D | S2425M405 | 1322 | 15/10/2026 | 1322 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903486465 IS1413 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | IN RANGE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 1322 |  | 1322 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1322 |  | 1322
ADIDAS | 0903486554-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 207 | 15/09/2026 | 207 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486554 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 |  |  | 207 |  | 207 |  |  | 2026-08-09 | 2026-12-09 | 2026-08-09 | 2026-12-09 | 207 | 198 | 9 |  | 14 | 2026-07-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 207 | 203 | 4 |  | 5
ADIDAS | 0903486586-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 23/09/2026 | 106 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486586 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 16/09/2026 | 18/09/2026 |  |  | 106 |  | 106 |  |  | 2026-12-09 | 15/09/2026 |  |  | 106 |  | 106 |  |  | 2026-09-09 | 2026-11-09 |  |  | 106 |  | 106
ADIDAS | 0903486633-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 103 | 15/09/2026 | 103 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, PI Date 23-Oct, switch from order 0903443493). T2 Fu Hsun, PI Date 11-Sep, switch from order 903443493). 830009 | HT SUB PROCESS_V1 | 0903486633 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 103 | 94 | 9 |  | 93 | 2026-08-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 103 | 103 |  |  |  | 2026-07-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 103 | 103
ADIDAS | 0903486870-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1164 | 15/10/2026 | 1164 | SI | SI14/08/2026 | G3J | SHORTS | G3 | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486870 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/10/2026 | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX | 24/10/2026 | 28/10/2026 |  |  | 1164 |  | 1164 |  |  | 21/10/2026 | 24/10/2026 |  |  | 1164 |  | 1164 |  |  | 17/10/2026 | 21/10/2026 |  |  | 1164 |  | 1164
ADIDAS | 0903487218-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487218 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | ESS HDY |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 920 |  | 920 |  |  | 28/09/2026 | 29/09/2026 |  |  | 920 |  | 920
ADIDAS | 0903487925-1 JZ7709 | BLACK | 120D | S2608MR0201 | 249 | 23/09/2026 | 249 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487925 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 16/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 16/09/2026 | 17/09/2026 |  |  | 249 |  | 249 |  |  | 2026-12-09 | 14/09/2026 |  |  | 249 |  | 249 |  |  | 2026-09-09 | 2026-10-09 |  |  | 249 |  | 249
ADIDAS | 0903488008-1 JZ7709 | BLACK | 120D | S2608MR0201 | 706 | 23/09/2026 | 706 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488008 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 16/09/2026 | 17/09/2026 |  |  | 706 |  | 706 |  |  | 2026-12-09 | 14/09/2026 |  |  | 706 |  | 706 |  |  | 2026-09-09 | 2026-10-09 |  |  | 706 |  | 706
ADIDAS | 0903488538-1 JZ7711 | BLACK | 120D | S2608MR0202 | 690 | 23/09/2026 | 690 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488538 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 16/09/2026 | 18/09/2026 |  |  | 690 |  | 690 |  |  | 2026-12-09 | 15/09/2026 |  |  | 690 |  | 690 |  |  | 2026-09-09 | 2026-11-09 |  |  | 690 |  | 690
ADIDAS | 0903488735-1 JZ7709 | BLACK | 120D | S2608MR0201 | 101 | 23/09/2026 | 101 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488735 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 16/09/2026 | 17/09/2026 |  |  | 101 |  | 101 |  |  | 2026-12-09 | 14/09/2026 |  |  | 101 |  | 101 |  |  | 2026-09-09 | 2026-10-09 |  |  | 101 |  | 101
ADIDAS | 0903489269-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 714 | 15/10/2026 | 714 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903489269 KA5090 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | MINI EMB T |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 714 |  | 714 |  |  | 2026-05-10 | 2026-05-10 |  |  | 714 |  | 714 |  |  | 2026-02-10 | 2026-02-10 |  |  | 714 |  | 714
ADIDAS | 0903490564-1 JZ7711 | BLACK | 120D | S2608MR0202 | 241 | 23/09/2026 | 241 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490564 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 16/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 16/09/2026 | 18/09/2026 |  |  | 241 |  | 241 |  |  | 2026-12-09 | 15/09/2026 |  |  | 241 |  | 241 |  |  | 2026-09-09 | 2026-11-09 |  |  | 241 |  | 241
ADIDAS | 0903492168-1 JM6500 | COLLEGIATE GREEN | 60D | F25SPRMGFX040 | 70 | 15/10/2026 | 70 | NT | NT14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 848012 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903492168 JM6500 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | M DDL SKATE T |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 70 |  | 70 |  |  | 28/09/2026 | 28/09/2026 |  |  | 70 |  | 70
ADIDAS | 0903492638-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 120 | 15/10/2026 | 120 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3+HT SUB PROCESS_V3 | 0903492638 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903492648-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1200 | 2026-12-09 | 1200 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 11/09: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903492648 KX7410 | 2026-04-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903492683-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1352 | 15/09/2026 | 1352 | SI | SI14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 14/09: ex-fty 834012 | EMBRO SUB PROCESS_V1 | 0903492683 KX7410 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-12-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1352 | 1328 | 24 |  | 702 | 2026-09-09 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 1352 | 1352
ADIDAS | 0903493699-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1299 | 15/10/2026 | 1299 | ID | ID14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493699 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | SPORT GOODS T |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1299 |  | 1299 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1299 |  | 1299
ADIDAS | 0903493969-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 2 | 2026-07-10 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903493969 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 19/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494061-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 2 | 2026-07-10 | 2 | AN | AN14/08/2026 | G2C | T-SHIRT | G2 | (14/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903494061 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 25/09/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 25/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 22/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494405-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 116 | 15/09/2026 | 116 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 814006 | HT SUB PROCESS_V1 | 0903494405 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 116 | 58 | 58 |  |  | 2026-08-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 116 | 116 |  |  |  | 2026-07-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 116 | 116
ADIDAS | 0903494445-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 126 | 15/09/2026 | 126 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 814006 | HT SUB PROCESS_V1 | 0903494445 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-10-09 | 15/09/2026 |  |  | 126 |  | 126 |  |  | 2026-08-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 126 | 112 | 14 |  | 92 | 2026-07-09 | 2026-11-09 | 2026-11-09 | 14/09/2026 | 126 | 126 |  |  | 123
ADIDAS | 0903494678-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 100 | 15/10/2026 | 100 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3 SUB PROCESS_V3 | 0903494678 LE1858 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 24/10/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 24/10/2026 | 24/10/2026 |  |  | 100 |  | 100 |  |  | 21/10/2026 | 21/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903495174-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 2 | 29/09/2026 | 2 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(35)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495174 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-12-09 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 2026-12-09 | 14/09/2026 |  |  | 2 |  | 2 |  |  | 2026-09-09 | 2026-10-09 |  |  | 2 |  | 2 |  |  | 2026-08-09 | 2026-09-09 |  |  | 2 |  | 2
ADIDAS | 0903495387-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 2 | 29/09/2026 | 2 | SI | SI14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(35)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495387 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-12-09 | MER DNA PT JSY BLACK |  | SS27-MS | 2026-12-09 | 14/09/2026 |  |  | 2 |  | 2 |  |  | 2026-09-09 | 2026-10-09 |  |  | 2 |  | 2 |  |  | 2026-08-09 | 2026-09-09 |  |  | 2 |  | 2
ADIDAS | 0903495400-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 2 | 29/09/2026 | 2 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(35)) |  | 825054 | PRINT L3 SUB PROCESS_V3 | 0903495400 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-12-09 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 2026-12-09 | 14/09/2026 |  |  | 2 |  | 2 |  |  | 2026-09-09 | 2026-10-09 |  |  | 2 |  | 2
ADIDAS | 0903496564-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 29 | 15/10/2026 | 29 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496564 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 29 |  | 29 |  |  | 16/10/2026 | 17/10/2026 |  |  | 29 |  | 29 |  |  | 15/10/2026 | 16/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496599-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 29 | 15/10/2026 | 29 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496599 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 29 |  | 29 |  |  | 20/10/2026 | 21/10/2026 |  |  | 29 |  | 29 |  |  | 19/10/2026 | 20/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496637-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 517 | 15/10/2026 | 517 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903496637 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 517 |  | 517 |  |  | 16/10/2026 | 17/10/2026 |  |  | 517 |  | 517 |  |  | 15/10/2026 | 16/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903497305-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 161 | 15/10/2026 | 161 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903497305 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 161 |  | 161 |  |  | 20/10/2026 | 21/10/2026 |  |  | 161 |  | 161 |  |  | 19/10/2026 | 20/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903497830-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 9287 | 15/10/2026 | 9287 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903497830 KA5089 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 2026-06-10 |  |  | 9287 |  | 9287 |  |  | 24/09/2026 | 2026-02-10 |  |  | 9287 |  | 9287 |  |  | 22/09/2026 | 30/09/2026 |  |  | 9287 |  | 9287
ADIDAS | 0903500463-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 889 | 15/10/2026 | 889 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903500463 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 889 |  | 889 |  |  | 17/10/2026 | 19/10/2026 |  |  | 889 |  | 889 |  |  | 16/10/2026 | 17/10/2026 |  |  | 889 |  | 889
ADIDAS | 0903501618-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 122 | 15/10/2026 | 122 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903501618 LE4570 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 122 |  | 122 |  |  | 20/10/2026 | 21/10/2026 |  |  | 122 |  | 122 |  |  | 19/10/2026 | 20/10/2026 |  |  | 122 |  | 122
ADIDAS | 0903502054-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 823 | 15/10/2026 | 823 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903502054 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 22/10/2026 | 23/10/2026 |  |  | 823 |  | 823 |  |  | 19/10/2026 | 20/10/2026 |  |  | 823 |  | 823 |  |  | 17/10/2026 | 19/10/2026 |  |  | 823 |  | 823
ADIDAS | 0903502085-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 166 | 15/10/2026 | 166 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 848012 | PRINT L3+HT SUB PROCESS_V3 | 0903502085 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 166 |  | 166 |  |  | 20/10/2026 | 21/10/2026 |  |  | 166 |  | 166 |  |  | 19/10/2026 | 20/10/2026 |  |  | 166 |  | 166
ADIDAS | 0903502271-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 842 | 2026-12-09 | 842 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903502271 KC6386 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-09 | M BLANK TEE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 842 | 842 |  |  |  | 2026-05-09 | 2026-09-09 | 31/08/2026 | 2026-09-09 | 842 | 839 | 3
ADIDAS | 0903502599-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 324 | 15/10/2026 | 324 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903502599 KD9094 |  | KAHATEX CIJERAH | THAILAND | SEA | 29/09/2026 | M BLANK TEE |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 324 |  | 324 |  |  | 25/09/2026 | 25/09/2026 |  |  | 324 |  | 324
ADIDAS | 0903503153-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 124 | 15/10/2026 | 124 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 1st Art (TC 10 pcs) 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503153 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 124 |  | 124 |  |  | 20/10/2026 | 21/10/2026 |  |  | 124 |  | 124 |  |  | 19/10/2026 | 20/10/2026 |  |  | 124 |  | 124
ADIDAS | 0903503177-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 204 | 15/10/2026 | 204 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503177 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 204 |  | 204 |  |  | 20/10/2026 | 21/10/2026 |  |  | 204 |  | 204 |  |  | 19/10/2026 | 20/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903503204-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 244 | 15/10/2026 | 244 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503204 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 244 |  | 244 |  |  | 16/10/2026 | 17/10/2026 |  |  | 244 |  | 244 |  |  | 15/10/2026 | 16/10/2026 |  |  | 244 |  | 244
ADIDAS | 0903503236-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 226 | 15/10/2026 | 226 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503236 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 226 |  | 226 |  |  | 17/10/2026 | 19/10/2026 |  |  | 226 |  | 226 |  |  | 16/10/2026 | 17/10/2026 |  |  | 226 |  | 226
ADIDAS | 0903503267-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 127 | 15/10/2026 | 127 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903503267 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 127 |  | 127 |  |  | 16/10/2026 | 17/10/2026 |  |  | 127 |  | 127 |  |  | 15/10/2026 | 16/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903503360-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2004 | 2026-12-09 | 2004 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 834012 | EMBRO SUB PROCESS_V1 | 0903503360 KD4066 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | M BLANK TEE BLACK |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2004 | 2004 |  |  | 6 | 2026-05-09 | 2026-09-09 | 2026-01-09 | 2026-08-09 | 2004 | 2004
ADIDAS | 0903503397-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2503 | 15/09/2026 | 2503 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 14/09: ex-fty 834012 | EMBRO SUB PROCESS_V1 | 0903503397 KE3742 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-12-09 | M BLANK TEE WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2503 | 1774 | 729 |  | 1029 | 2026-09-09 | 2026-11-09 | 2026-07-09 | 13/09/2026 | 2503 | 2500 | 3 |  | 15
ADIDAS | 0903503800-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 300 | 15/10/2026 | 300 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903503800 KC6386 |  | KAHATEX CIJERAH | THAILAND | SEA | 29/09/2026 | M BLANK TEE |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903504690-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 1006 | 2026-12-09 | 1006 | SA | SA14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504690 KD9094 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | M BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 1006 | 1006 |  |  | 508 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-12-09 | 1006 | 1006 |  |  | 10
ADIDAS | 0903504729-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 2022 | 2026-12-09 | 2022 | SI | SI14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504729 KD9097 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | W BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2022 | 2022 |  |  | 79 | 2026-07-09 | 2026-09-09 | 31/08/2026 | 2026-08-09 | 2022 | 2022
ADIDAS | 0903535974-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 15/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | 804028 | PRINT L3 SUB PROCESS_V3 | 0903535974 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 14/09/2026 | 16/09/2026 |  |  | 500 |  | 500 |  |  | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 500 | 290 | 210
ADIDAS | 0903535975-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 15/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | 960026 | PRINT L3 SUB PROCESS_V3 | 0903535975 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 14/09/2026 | 16/09/2026 |  |  | 500 |  | 500 |  |  | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 500 | 500
ADIDAS | 0903548414-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 141 | 30/09/2026 | 141 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 29/09: ex-fty 800005 | HT+PAD SUB PROCESS_V3 | 0903548414 KB5961 | 24/11/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 23/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 23/09/2026 | 23/09/2026 |  |  | 141 |  | 141 |  |  | 19/09/2026 | 19/09/2026 |  |  | 141 |  | 141 |  |  | 17/09/2026 | 17/09/2026 |  |  | 141 |  | 141
ADIDAS | 0903550837-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ-SLT | 898 | 30/09/2026 | 898 | ID | ID28/08/2026 | G2J | T-SHIRT | G2 | (26/09/2026) |  | 23/09: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903550837 JC8239 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W LIN SJ T |  | SS27-SLT | 28/09/2026 | 28/09/2026 |  |  | 898 |  | 898 |  |  | 24/09/2026 | 24/09/2026 |  |  | 898 |  | 898
ADIDAS | 0903553857-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 123 | 30/09/2026 | 123 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (26/10/2026(37)) |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553857 KB5965 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 23/09/2026 |  |  | 123 |  | 123 |  |  | 17/09/2026 | 19/09/2026 |  |  | 123 |  | 123 |  |  | 15/09/2026 | 17/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903553911-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 134 | 30/09/2026 | 134 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553911 KB5961 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 23/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 23/09/2026 | 23/09/2026 |  |  | 134 |  | 134 |  |  | 19/09/2026 | 19/09/2026 |  |  | 134 |  | 134 |  |  | 17/09/2026 | 17/09/2026 |  |  | 134 |  | 134
ADIDAS | 0903554010-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 108 | 30/09/2026 | 108 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (26/10/2026(37)) |  | 25/09: ex-fty 814006 | HT+PAD SUB PROCESS_V3 | 0903554010 KB5965 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 23/09/2026 |  |  | 108 |  | 108 |  |  | 17/09/2026 | 19/09/2026 |  |  | 108 |  | 108 |  |  | 15/09/2026 | 17/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903556417-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 107 | 30/09/2026 | 107 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0903556417 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 23/09/2026 | 23/09/2026 |  |  | 107 |  | 107 |  |  | 19/09/2026 | 19/09/2026 |  |  | 107 |  | 107 |  |  | 17/09/2026 | 17/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903557215-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 2026-12-09 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty (By Air-Collect). 859013 | PRINT L3 SUB PROCESS_V3 | 0903557215 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | TAIWAN | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 300 | 300
ADIDAS | 0903557229-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2 | 30/09/2026 | 2 | SI | SI28/08/2026 | G2K | T-SHIRT | G2 | (25/09/2026(11)) |  | 18/09: ex-fty (CMA test) (By Air-Express). DRC 0064-other customer related delay reason. 825054 | PRINT L3 SUB PROCESS_V3 | 0903557229 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | AIR-EXPRESS | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 16/09/2026 | 18/09/2026 |  |  | 2 |  | 2 |  |  | 2026-12-09 | 15/09/2026 | 2026-03-09 | 2026-03-09 | 2 | 2
ADIDAS | 0903557263-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2600 | 30/09/2026 | 2600 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(15)) |  | 18/09: ex-fty (China) (By Air-Collect). DRC 0064-other customer related delay reason. 825066 | PRINT L3 SUB PROCESS_V3 | 0903557263 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | SEA | 2026-12-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2600 | 676 | 1924 |  | 588 | 2026-09-09 | 2026-11-09 | 2026-02-09 | 2026-11-09 | 2600 | 2597 | 3
ADIDAS | 0903565505-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 1473 | 30/09/2026 | 1473 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (26/10/2026(37)) |  | 25/09: ex-fty 960026 | HT+PAD SUB PROCESS_V3 | 0903565505 KB5965 | 24/11/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 23/09/2026 |  |  | 1473 |  | 1473 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1473 |  | 1473 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1473 |  | 1473
ADIDAS | 0903566115-1 HL2231 | LEGEND INK F17/WHITE | 45D | F224CSIM430 | 71 | 15/10/2026 | 71 | NT | NT28/08/2026 | G2M | PANTS | G2 | (02/10/2026) |  | 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903566115 HL2231 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 71 |  | 71 |  |  | 2026-06-10 | 2026-06-10 |  |  | 71 |  | 71
ADIDAS | 0903595003-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 4024 | 2026-12-09 | 4024 | SI | SI28/08/2026 | G2I | T-SHIRT | G2 | (25/09/2026(15)) |  | 11/09: ex-fty 516343 | PRINT L3 SUB PROCESS_V3 | 0903595003 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-12-09 | 16/09/2026 | 14/09/2026 | 14/09/2026 | 4024 | 338 | 3686 |  |  | 2026-09-09 | 2026-12-09 | 2026-03-09 | 2026-03-09 | 4024 | 4024
ADIDAS | 0903595010-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 5004 | 2026-12-09 | 5004 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty (By Air-Collect). 516333 | PRINT L3 SUB PROCESS_V3 | 0903595010 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | AIR COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 5004 | 4276 | 728 |  | 1570 | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-02-09 | 5004 | 5004
ADIDAS | 0903595012-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 890 | 2026-12-09 | 890 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903595012 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 890 | 497 | 393 |  | 98 | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 890 | 890
ADIDAS | 0903595017-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 310 | 2026-12-09 | 310 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty 516343 | PRINT L3 SUB PROCESS_V3 | 0903595017 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 310 | 282 | 28 |  | 272 | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-04-09 | 310 | 310
ADIDAS | 0903595019-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 2026-12-09 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 12/09: ex-fty (By Air-Collect). 806020 | PRINT L3 SUB PROCESS_V3 | 0903595019 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | HONGKONG | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 300 | 300 |  |  | 233 | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-12-09 | 300 | 300 |  |  | 2
ADIDAS | 0903602357-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 700 | 30/09/2026 | 700 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | 800005 | PRINT L3 SUB PROCESS_V3 | 0903602357 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | INDONESIA | SEA | 21/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 21/09/2026 | 22/09/2026 |  |  | 700 |  | 700 |  |  | 17/09/2026 | 18/09/2026 | 2026-10-09 | 2026-10-09 | 700 | 590 | 110
ADIDAS | 0903602358-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1400 | 30/09/2026 | 1400 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903602358 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 22/09/2026 | 23/09/2026 |  |  | 1400 |  | 1400 |  |  | 18/09/2026 | 19/09/2026 | 2026-10-09 | 2026-10-09 | 1400 | 1119 | 281
ADIDAS | 0903602359-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1880 | 30/09/2026 | 1880 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903602359 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | THAILAND | SEA | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 16/09/2026 | 18/09/2026 |  |  | 1880 |  | 1880 |  |  | 2026-12-09 | 15/09/2026 | 2026-10-09 | 2026-10-09 | 1880 | 1647 | 233
ADIDAS | 0903602360-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2100 | 30/09/2026 | 2100 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903602360 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 18/09/2026 | 19/09/2026 |  |  | 2100 |  | 2100 |  |  | 15/09/2026 | 16/09/2026 | 2026-10-09 | 2026-10-09 | 2100 | 1800 | 300
ADIDAS | 0903602828-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1200 | 15/09/2026 | 1200 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | 600000 | PRINT L3 SUB PROCESS_V3 | 0903602828 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 16/09/2026 | 16/09/2026 |  |  | 1200 |  | 1200 |  |  | 2026-12-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903603199-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 221 | 2026-12-09 | 221 | SI | SI28/08/2026 | G2I | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903603199 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 221 | 97 | 124 |  | 94 | 2026-07-09 | 2026-09-09 | 2026-02-09 | 2026-05-09 | 221 | 221
ADIDAS | 0903603200-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 484 | 2026-12-09 | 484 | SI | SI28/08/2026 | G2I | T-SHIRT | G2 | (25/09/2026(17)) |  | 11/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903603200 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 484 | 140 | 344 |  | 139 | 2026-07-09 | 2026-09-09 | 2026-03-09 | 2026-03-09 | 484 | 484
ADIDAS | 0903613329-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 301 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903613329 KA6229 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903613711-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 345 | 15/10/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903613711 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903613739-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 116 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 838103 | PAD+HT SUB PROCESS_V3 | 0903613739 KA0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903614275-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 241 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614275 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903614393-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 100 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614393 KA6229 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903614427-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 111 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614427 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903615793-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 117 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 839055 | PAD+HT SUB PROCESS_V3 | 0903615793 KD3875 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 4501440021-2 KA3521 | BLACK/WHITE | 60D | S2650MTR434 | 46 | 26/08/2026 | 46 | SI | SI19/12/2025 | G3E | SHORTS | G3 | ok |  | 24/08: ex-fty (By Air-Collect). T2 Libolon, PI Date 12-Jan, actual receives 12-Jan. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501440021 KA3521 | 2026-05-02 | KAHATEX CIJERAH | SOUTH AFRICA | AIR-COLLECT | 17/07/2026 | WE BAS 3SWV SH |  | FW26 | 17/07/2026 | 24/07/2026 | 20/07/2026 | 22/07/2026 | 46 | 46 |  |  |  | 14/07/2026 | 21/07/2026 | 15/07/2026 | 16/07/2026 | 46 | 46 |  |  |  | 2026-07-07 | 14/07/2026 | 14/07/2026 | 14/07/2026 | 46 | 46
ADIDAS | 4501769841-5 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 2026-10-07 | 2026-09-07 | 2026-10-07 | 400 | 400 |  |  |  | 2026-03-07 | 2026-07-07 | 26/06/2026 | 14/07/2026 | 400 | 400
ADIDAS | 4501769841-6 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 383 | 2026-05-09 | 383 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 04/09: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 27/07/2026 | IN RANGE |  | FW26 | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 383 | 383 |  |  |  | 22/07/2026 | 29/07/2026 | 2026-08-07 | 27/07/2026 | 383 | 383
ADIDAS | 4501904766-1 IX3617 | TENT GREEN F16 | 60D | S2315KSWU253 | 400 | 28/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3 SUB PROCESS_V3 | 4501904766 IX3617 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 400 | 400 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-08-07 | 17/07/2026 | 400 | 400
ADIDAS | 4501906112-1 HR6306 | BLACK/BLACK | 60D | S2315KSWU253 | 461 | 28/08/2026 | 461 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906112 HR6306 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 461 | 461 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-08-07 | 20/07/2026 | 461 | 461
ADIDAS | 4501906120-2 HR6306 | BLACK/BLACK | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906120 HR6306 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 17/07/2026 | 400 | 400 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-07-07 | 20/07/2026 | 400 | 400
ADIDAS | 4501906793-2 IX3617 | TENT GREEN F16 | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906793 IX3617 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 16/07/2026 | U FI LOGO SH |  | FW26 | 16/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 400 | 400 |  |  |  | 13/07/2026 | 16/07/2026 | 2026-07-07 | 17/07/2026 | 400 | 400
ADIDAS | 4501928501-1 LG9669 | BLACK | 120D | S2754WAS514C | 189 | 14/10/2026 | 189 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928501 LG9669 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-09-10 | W SL WV SK BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 189 |  | 189 |  |  | 2026-06-10 | 2026-07-10 |  |  | 189 |  | 189
ADIDAS | 4501929295-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 160 | 14/10/2026 | 160 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929295 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 160 |  | 160 |  |  | 19/09/2026 | 21/09/2026 |  |  | 160 |  | 160 |  |  | 17/09/2026 | 18/09/2026 |  |  | 160 |  | 160
ADIDAS | 4501929321-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 582 | 14/10/2026 | 582 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929321 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 582 |  | 582 |  |  | 2026-05-10 | 2026-06-10 |  |  | 582 |  | 582 |  |  | 2026-02-10 | 2026-03-10 |  |  | 582 |  | 582
ADIDAS | 4501933525-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 113 | 21/08/2026 | 113 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, using fabric stock. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933525 KA3521 | 22/07/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 113 | 113 |  |  |  | 2026-10-07 | 16/07/2026 | 13/07/2026 | 15/07/2026 | 113 | 113 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-10-07 | 15/07/2026 | 113 | 113
ADIDAS | 4501933526-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 647 | 21/08/2026 | 647 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, PI Date 28-May, actual receives 20-May. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933526 KD0677 | 22/07/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 17/07/2026 | WE BAS 3SWV SH |  | FW26 | 17/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 647 | 647 |  |  |  | 14/07/2026 | 21/07/2026 | 14/07/2026 | 17/07/2026 | 647 | 647 |  |  |  | 2026-07-07 | 14/07/2026 | 13/07/2026 | 17/07/2026 | 647 | 647
ADIDAS | 4501933527-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 347 | 21/08/2026 | 347 | SI | SI21/05/2026 | G3E | SHORTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Libolon, using fabric stock. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933527 KA3521 | 2026-06-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 347 | 347 |  |  |  | 2026-10-07 | 16/07/2026 | 2026-09-07 | 13/07/2026 | 347 | 347 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-09-07 | 14/07/2026 | 347 | 347
ADIDAS | 4502065732-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 671 | 14/10/2026 | 671 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 18/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 18/09/2026 | 22/09/2026 |  |  | 671 |  | 671 |  |  | 15/09/2026 | 18/09/2026 |  |  | 671 |  | 671
ADIDAS | 4502070409-1 LF0718 | BLACK | 105D | S2754MAS512B | 140 | 14/10/2026 | 140 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 140 |  | 140 |  |  | 2026-10-10 | 2026-12-10 |  |  | 140 |  | 140
ADIDAS | 4502075077-1 IN1173 | WHITE | 90D | S2408WR1600 | 190 | 2026-07-10 | 190 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075077 IN1173 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 190 |  | 190 |  |  | 2026-06-10 | 2026-07-10 | 2026-11-08 | 26/08/2026 | 190 | 190 |  |  |  | 2026-05-10 | 2026-06-10 | 2026-08-08 | 22/08/2026 | 190 | 190
ADIDAS | 4502075081-1 KA0246 | BLACK | 90D | S2608WR0902 | 961 | 14/10/2026 | 961 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075081 KA0246 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-02-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 961 |  | 961 |  |  | 29/09/2026 | 30/09/2026 |  |  | 961 |  | 961 |  |  | 28/09/2026 | 29/09/2026 |  |  | 961 |  | 961
ADIDAS | 4502075922-1 KT4840 | ONIX | 90D | S2408MR1600 | 100 | 14/10/2026 | 100 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075922 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 4502075923-1 IN1156 | BLACK | 90D | S2408MR1600 | 413 | 2026-07-10 | 413 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/09/2026 | ADIZERO E TEE |  | SS27-YTI | 23/09/2026 | 24/09/2026 |  |  | 413 |  | 413 |  |  | 21/09/2026 | 22/09/2026 | 26/08/2026 | 2026-12-09 | 413 | 413 |  |  | 39 | 19/09/2026 | 21/09/2026 | 18/08/2026 | 2026-05-09 | 413 | 413
ADIDAS | 4502075924-1 IN1172 | BLACK | 90D | S2408WR1600 | 212 | 2026-07-10 | 212 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075924 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 212 |  | 212 |  |  | 28/09/2026 | 29/09/2026 | 27/08/2026 | 2026-04-09 | 212 | 212 |  |  |  | 26/09/2026 | 28/09/2026 | 27/08/2026 | 2026-04-09 | 212 | 212
ADIDAS | 4502075931-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 179 | 14/10/2026 | 179 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502075931 LD0292 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 179 |  | 179 |  |  | 2026-05-10 | 2026-08-10 |  |  | 179 |  | 179 |  |  | 2026-03-10 | 2026-07-10 |  |  | 179 |  | 179
ADIDAS | 4502075932-1 KA0235 | BLACK | 90D | S2608WR0901 | 971 | 14/10/2026 | 971 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075932 KA0235 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 22/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 22/10/2026 | 26/10/2026 |  |  | 971 |  | 971 |  |  | 19/10/2026 | 22/10/2026 |  |  | 971 |  | 971 |  |  | 17/10/2026 | 21/10/2026 |  |  | 971 |  | 971
ADIDAS | 4502076908-1 KA4331 | BLACK | 90D | S2608MR0902 | 1102 | 14/10/2026 | 1102 | SA | SA03/07/2026 | G1C | SHORTS | G1 | (26/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-05-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 1102 |  | 1102 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1102 |  | 1102 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1102 |  | 1102
ADIDAS | 4502077517-1 IN1172 | BLACK | 90D | S2408WR1600 | 292 | 30/09/2026 | 292 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077517 IN1172 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 292 |  | 292 |  |  | 24/09/2026 | 25/09/2026 | 27/08/2026 | 2026-10-09 | 292 | 292 |  |  |  | 23/09/2026 | 24/09/2026 | 24/08/2026 | 2026-09-09 | 292 | 292
ADIDAS | 4502077518-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 30/09/2026 | 167 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502077518 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 30/09/2026 |  |  | 167 |  | 167 |  |  | 25/09/2026 | 28/09/2026 | 24/08/2026 | 2026-07-09 | 167 | 167 |  |  |  | 24/09/2026 | 26/09/2026 | 22/08/2026 | 2026-05-09 | 167 | 167
ADIDAS | 4502077519-1 IN1157 | WHITE | 90D | S2408MR1600 | 706 | 30/09/2026 | 706 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 06-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077519 IN1157 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 30/09/2026 |  |  | 706 |  | 706 |  |  | 25/09/2026 | 28/09/2026 | 2026-09-09 | 2026-11-09 | 706 | 703 | 3 |  |  | 24/09/2026 | 26/09/2026 | 2026-02-09 | 2026-10-09 | 706 | 703 | 3
ADIDAS | 4502080370-1 IN1156 | BLACK | 90D | S2408MR1600 | 527 | 30/09/2026 | 527 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502080370 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 19/09/2026 |  |  | 527 |  | 527 |  |  | 16/09/2026 | 17/09/2026 | 26/08/2026 | 2026-10-09 | 527 | 527 |  |  |  | 15/09/2026 | 16/09/2026 | 24/08/2026 | 2026-09-09 | 527 | 527
ADIDAS | 4502080372-1 IN1173 | WHITE | 90D | S2408WR1600 | 109 | 30/09/2026 | 109 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. ZA30 | HT SUB PROCESS_V1 | 4502080372 IN1173 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 16/09/2026 | ADIZERO E TEE |  | SS27-YTI | 16/09/2026 | 17/09/2026 |  |  | 109 |  | 109 |  |  | 14/09/2026 | 15/09/2026 | 2026-12-08 | 21/08/2026 | 109 | 109 |  |  |  | 2026-12-09 | 14/09/2026 | 2026-11-08 | 20/08/2026 | 109 | 109
ADIDAS | 4502347774-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 800 | 15/09/2026 | 800 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3+PAD SUB PROCESS_V3 | 4502347774 KA0546 | 26/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 800 | 800 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-09-09 | 800 | 800
ADIDAS | 46075347-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1622 | 15/09/2026 |  | SI | SI22/08/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 46075347 LZ9161 | 2026-04-11 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27 | [11 empty] | 29/08/2026 | 2026-11-09 |  | 4200 |  | 4200
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902859677-1 JZ7808 | BLACK | 60D | S2608WR0900 | 364 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902859677 JZ7808 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862146-1 JZ7808 | BLACK | 60D | S2608WR0900 | 332 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902862146 JZ7808 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862481-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 309 | 31/10/2026 | 309 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (04/06/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, PI Date 07-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862481 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46364 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 46364 | 31/08/2026 | 46364 | 46031 | 309 | 309 |  |  |  | 46211 | 27/08/2026 | 46150 | 31/08/2026 | 309 | 309
ADIDAS | 0902882924-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 306 | 31/10/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902882924 KD0677 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887722-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 329 | 46214 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887722 KD0677 | 22/07/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887725-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 759 | 30/11/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887725 KA3521 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902900852-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 312 | 30/11/2026 |  | SI | SI15/05/2026 |  | T-SHIRT |  | (13/07/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0902900852 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902900942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 23/10/2026 | 306 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 306 |  | 306 |  |  | 25/09/2026 | 26/09/2026 | 46120 | 28/08/2026 | 306 | 305 | 1 |  |  | 23/09/2026 | 24/09/2026 | 46030 | 27/08/2026 | 306 | 306
ADIDAS | 0902901036-1 JZ7808 | BLACK | 120D | S2608WR0900 | 483 | 46214 |  | SA | SA15/05/2026 |  | T-SHIRT |  | (13/07/2026) | ok | 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902901036 JZ7808 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902902915-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 306 | 46214 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | (08/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902902915 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902903045-1 KE8425 | WHITE | 120D | S2608MR0906A | 318 | 23/10/2026 |  | SI | SI15/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902903045 KE8425 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0902904560-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902904560 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 46032 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 46032 | 46032 |  |  | 319 |  | 319 |  |  | 28/09/2026 | 28/09/2026 | 46303 | 46364 | 319 | 319 |  |  |  | 25/09/2026 | 25/09/2026 | 46242 | 46364 | 319 | 319
ADIDAS | 0902930249-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 563 | 46214 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930249 KX3713 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930252-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 342 | 23/11/2026 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902930252 KX3713 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930263-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 334 | 46214 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930263 LD0283 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902931102-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA21/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902931102 LD0285 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 46032 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46032 | 46063 |  |  | 319 |  | 319 |  |  | 28/09/2026 | 29/09/2026 | 46089 | 46211 | 319 | 319 |  |  |  | 25/09/2026 | 26/09/2026 | 46089 | 46150 | 319 | 319
ADIDAS | 0902931104-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 335 | 46214 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902931104 LD0285 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902945143-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945143 LE8186 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902951389-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 302 | 31/10/2026 | 302 | SA | SA29/05/2026 | G1H | JACKET | G1 | (15/07/2026) | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951389 LG9664 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | W SL WV TT LEGEND IVY S19 |  | SS27 | 46153 | 46214 |  |  | 302 |  | 302 |  |  | 46064 | 46123 |  |  | 302 |  | 302
ADIDAS | 0902951506-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 304 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951506 LG9673 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902952685-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 498 | 31/10/2026 | 498 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 31-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902952685 LG9666 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46064 | W SL WV TT BLACK |  | SS27 | 46064 | 46153 |  |  | 498 |  | 498 |  |  | 29/10/2026 | 46064 |  |  | 498 |  | 498
ADIDAS | 0902954134-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 322 | 46214 |  | SA | SA29/05/2026 |  | JACKET |  | (15/07/2026) | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954134 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0902954770-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 453 | 46214 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954770 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902954935-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 340 | 46214 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954935 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956034-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 355 | 46214 |  | SI | SI29/05/2026 |  | SHORTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956034 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0902956889-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 599 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902956889 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956935-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 370 | 46214 |  | AN | AN29/05/2026 |  | JACKET |  | (29/06/2026) | (19/06/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Jun, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jun, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956935 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0902960952-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 110 | 15/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902960952 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961002-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 120 | 46214 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961002 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961860-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 592 | 31/10/2026 | 592 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902961860 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46305 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 46305 | 46366 |  |  | 592 |  | 592 |  |  | 46213 | 46244 |  |  | 592 |  | 592 |  |  | 46152 | 46183 |  |  | 592 |  | 592
ADIDAS | 0902961947-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 136 | 23/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961947 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961984-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 427 | 23/10/2026 | 427 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902961984 LD0287 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 46063 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 46063 | 46091 |  |  | 427 |  | 427 |  |  | 29/09/2026 | 30/09/2026 |  |  | 427 |  | 427 |  |  | 26/09/2026 | 28/09/2026 |  |  | 427 |  | 427
ADIDAS | 0902962237-1 JZ7808 | BLACK | 120D | S2608WR0900 | 300 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902962237 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902969632-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 535 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 672027 | HT+PAD SUB PROCESS_V3 | 0902969632 KF5311 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0902973591-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 894 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973591 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902973641-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2142 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973641 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902975671-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1236 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902975671 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902975836-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 2400 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0902975836 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0902976602-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1120 | 31/10/2026 | 1120 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902976602 LD0287 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 46091 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 46091 | 46152 |  |  | 1120 |  | 1120 |  |  | 30/09/2026 | 46032 |  |  | 1120 |  | 1120 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902977881-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 504 | 31/10/2026 | 504 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 800187 | HT+PAD SUB PROCESS_V3 | 0902977881 LD0287 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 46091 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 46091 | 46091 |  |  | 504 |  | 504 |  |  | 30/09/2026 | 30/09/2026 |  |  | 504 |  | 504 |  |  | 28/09/2026 | 28/09/2026 |  |  | 504 |  | 504
ADIDAS | 0902980516-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2141 | 23/10/2026 | 2141 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980516 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 46334 | 31/08/2026 | 2141 | 2141 |  |  |  | 46303 | 27/08/2026 | 46242 | 21/08/2026 | 2141 | 2125 | 16
ADIDAS | 0902982427-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 363 | 31/10/2026 | 363 | ID | ID29/05/2026 | G2J | T-SHIRT | G2 | (28/07/2026) | (27/06/2026) | DRC 0090-early shipment customer (BTP_12_06_2026 EARLY HOLD SHIPMENT). 800187 | HT+PAD SUB PROCESS_V3 | 0902982427 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 46305 | Run Ess Tee W BLACK |  | SS27-SLT-TI | 46305 | 46305 |  |  | 363 |  | 363 |  |  | 46213 | 46213 |  |  | 363 |  | 363 |  |  | 46152 | 46152 |  |  | 363 |  | 363
ADIDAS | 0902982687-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902982687 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0902982774-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 321 | 31/10/2026 | 321 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902982774 LD0285 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 46183 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46183 | 46213 |  |  | 321 |  | 321 |  |  | 46063 | 46091 | 46120 | 46211 | 321 | 321 |  |  |  | 30/09/2026 | 46032 | 46030 | 46181 | 321 | 321
ADIDAS | 0902982827-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 524 | 31/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902982827 LD0285 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 46183 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46183 | 46213 |  |  | 524 |  | 524 |  |  | 46063 | 46091 | 46120 | 46303 | 524 | 524 |  |  |  | 30/09/2026 | 46032 | 46030 | 46303 | 524 | 524
ADIDAS | 0902982993-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 810 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902982993 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0902983024-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1000 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902983024 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0902983061-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902983061 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902987712-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 319 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987712 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987796-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 451 | 23/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987796 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987830-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987830 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902988826-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 229 | 46214 |  | SA | SA29/05/2026 |  | PANTS |  | (27/07/2026) | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988826 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0902990760-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 144 | 23/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990760 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902990823-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 128 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990823 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902990853-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990853 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902997893-1 KB5960 | WHITE | 120D | S2608MR0900A | 500 | 31/10/2026 | 500 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902997893 KB5960 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46244 | Run Ess Tee M |  | SS27-TI | 46244 | 46244 |  |  | 500 |  | 500 |  |  | 46152 | 46152 | 46062 | 46212 | 500 | 447 | 53 |  |  | 46063 | 46063 | 46062 | 46365 | 500 | 500 |  |  | 53
ADIDAS | 0903037254-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037254 LH3761 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903037304-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037304 LH3759 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903043064-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903043064 LF0729 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 46064 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903043395-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4200 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043395 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903043496-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043496 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903043590-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 4800 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043590 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903045667-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4800 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045667 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903045765-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 4800 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045765 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903045811-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1200 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045811 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903045956-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4800 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045956 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27
ADIDAS | 0903046008-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 948 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903046008 KX3650 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903046882-1 KB5965 | BLACK | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046882 KB5965 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903046898-1 KB5960 | WHITE | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046898 KB5960 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903046980-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 286 | 31/10/2026 | 286 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512110 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046980 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46121 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 46121 | 22/09/2026 | 46151 | 46304 | 286 | 286 |  |  |  | 46031 | 18/09/2026 | 46303 | 24/08/2026 | 286 | 286
ADIDAS | 0903047008-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 282 | 46214 |  | AN | AN12/06/2026 |  | JACKET |  | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047008 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903047031-1 LG9675 | BLACK | 120D | S2754WAS513C | 208 | 30/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047031 LG9675 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047055-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 369 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903047055 KX3654 | 46335 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903047059-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 120 | 30/11/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047059 LG9669 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903047167-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 468 | 23/10/2026 | 468 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047167 KY6616 | 46335 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 468 |  | 468 |  |  | 22/10/2026 | 24/10/2026 |  |  | 468 |  | 468
ADIDAS | 0903047297-1 LG9675 | BLACK | 120D | S2754WAS513C | 348 | 23/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047297 LG9675 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047322-1 LG9675 | BLACK | 120D | S2754WAS513C | 383 | 46214 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047322 LG9675 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047344-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047344 KX0123 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/10/2026 | M ADI RETRO T WHITE |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 22/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903047367-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047367 LC8882 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/10/2026 | M ADI RETRO T BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 22/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903047397-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903047397 LH3759 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903048496-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1018 | 23/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok |  | 804028 | HT+PAD SUB PROCESS_V3 | 0903048496 KX3650 | 46335 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903048525-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 395 | 31/10/2026 | 395 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048525 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 46275 | W 3S WV WB BLACK/WHITE |  | SS27 | 46275 | 46305 |  |  | 395 |  | 395 |  |  | 46183 | 46213 | 20/08/2026 | 20/08/2026 | 395 | 26 | 369
ADIDAS | 0903048540-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 409 | 23/10/2026 | 409 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048540 LD0287 | 46335 | KAHATEX CIJERAH | JAPAN | SEA | 46063 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 46063 | 46091 |  |  | 409 |  | 409 |  |  | 29/09/2026 | 30/09/2026 | 46242 | 29/08/2026 | 409 | 409 |  |  |  | 26/09/2026 | 28/09/2026 | 46211 | 28/08/2026 | 409 | 409
ADIDAS | 0903048584-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 459 | 30/11/2026 | 459 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048584 LD0287 | 46335 | KAHATEX CIJERAH | JAPAN | SEA | 13/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 13/10/2026 | 13/10/2026 |  |  | 459 |  | 459 |  |  | 46275 | 46275 | 27/08/2026 | 46304 | 459 | 458 | 1 |  |  | 46213 | 46213 | 26/08/2026 | 46304 | 459 | 458 | 1
ADIDAS | 0903048634-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 151 | 23/10/2026 | 151 | AN | AN12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048634 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 30/10/2026 | 46153 |  |  | 151 |  | 151 |  |  | 27/10/2026 | 46064 |  |  | 151 |  | 151
ADIDAS | 0903049164-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903049164 KB5965 | 46335 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903049235-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 508 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049235 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903049482-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 450 | 31/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049482 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903053818-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 450 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903053818 KX3650 | 46335 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903054588-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054588 LH3759 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903054623-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054623 LH3761 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903054797-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 217 | 23/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (03/07/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0903054797 KX3655 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903054844-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1405 | 31/10/2026 |  | AN | AN12/06/2026 |  | PANTS |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903054844 LG9675 | 46335 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903055956-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 629 | 31/10/2026 |  | SA | SA12/06/2026 |  | JACKET |  | ok | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903055956 JE6338 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903055994-1 LG9675 | BLACK | 120D | S2754WAS513C | 498 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903055994 LG9675 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903056025-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056025 KB5965 | 46335 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903056060-1 LF0723 | BLACK | 105D | S2754MAS511B | 325 | 31/10/2026 |  | SI | SI12/06/2026 |  | SHORTS |  | ok | (04/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 04-Sep. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903056060 LF0723 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903056140-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1431 | 31/10/2026 |  | SA | SA12/06/2026 |  | JACKET |  | (22/07/2026) | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056140 JD1877 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903056557-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 141 | 15/11/2026 |  | AN | AN12/06/2026 |  | SWEATSHIRT |  | ok | (17/07/2026) | 516205 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903056557 KY1361 | 29/07/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | REAL HER CR BLACK/BLACK |  | SS27
ADIDAS | 0903057195-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 499 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | (20/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903057195 LG9669 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903058189-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 541 | 31/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | (11/07/2026) | (03/07/2026) | 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903058189 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA |  | M RESORT T OLIVE FOUR S27 |  | SS27
ADIDAS | 0903058216-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 610 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058216 KX3654 | 46335 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903059465-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 865 | 46214 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059465 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059485-1 LF0718 | BLACK | 105D | S2754MAS512B | 170 | 31/10/2026 |  | SA | SA12/06/2026 |  | PANTS |  | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 31-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059485 LF0718 | 46335 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903059517-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 365 | 23/10/2026 | 365 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059517 LF0727 | 46335 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M SL WV TT BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 365 |  | 365 |  |  | 21/10/2026 | 22/10/2026 |  |  | 365 |  | 365
ADIDAS | 0903059595-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 161 | 23/10/2026 | 161 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059595 LF0727 | 46335 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | M SL WV TT BLACK |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 161 |  | 161 |  |  | 21/10/2026 | 22/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903059867-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 750 | 31/10/2026 | 750 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903059867 LD0285 | 46335 | KAHATEX CIJERAH | SPAIN | SEA | 46213 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46213 | 46244 |  |  | 750 |  | 750 |  |  | 46091 | 46152 | 24/08/2026 | 46090 | 750 | 744 | 6 |  |  | 46032 | 46063 | 24/08/2026 | 46365 | 750 | 750 |  |  | 6
ADIDAS | 0903060279-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 152 | 31/10/2026 | 152 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060279 LF0729 | 46335 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 46064 |  |  | 152 |  | 152 |  |  | 27/10/2026 | 29/10/2026 |  |  | 152 |  | 152
ADIDAS | 0903060359-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 315 | 23/10/2026 | 315 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (30/06/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060359 LF0729 | 46335 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 46064 |  |  | 315 |  | 315 |  |  | 27/10/2026 | 29/10/2026 |  |  | 315 |  | 315
ADIDAS | 0903060814-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 325 | 23/10/2026 | 325 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903060814 LD0285 | 46335 | KAHATEX CIJERAH | ITALY | SEA | 46063 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46063 | 46063 |  |  | 325 |  | 325 |  |  | 29/09/2026 | 29/09/2026 | 20/08/2026 | 31/08/2026 | 325 | 324 | 1 |  |  | 26/09/2026 | 26/09/2026 | 19/08/2026 | 31/08/2026 | 325 | 324 | 1
ADIDAS | 0903061680-1 LE5038 | BLACK | 105D | S2750MTR104A | 180 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903061680 LE5038 | 46335 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061955-1 LE5038 | BLACK | 105D | S2750MTR104A | 241 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061955 LE5038 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061985-1 LE5038 | BLACK | 105D | S2750MTR104A | 221 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061985 LE5038 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903062015-1 LE5038 | BLACK | 105D | S2750MTR104A | 141 | 23/10/2026 | 141 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903062015 LE5038 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | D4T AOP GFX T BLACK |  | SS27-TI | 24/10/2026 | 24/10/2026 |  |  | 141 |  | 141 |  |  | 21/10/2026 | 21/10/2026 |  |  | 141 |  | 141 |  |  | 20/10/2026 | 20/10/2026 |  |  | 141 |  | 141
ADIDAS | 0903062051-1 LE5038 | BLACK | 105D | S2750MTR104A | 252 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903062051 LE5038 | 46335 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903063396-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 394 | 46214 |  | AN | AN12/06/2026 |  | SKIRT |  | (20/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063396 LG9669 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903063462-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 347 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | (20/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063462 LG9669 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903093131-1 KF5803 | BLACK | 105D | S2608MR0602A | 727 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903093131 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093134-1 KF5803 | BLACK | 105D | S2608MR0602A | 302 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093134 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093139-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 376 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (25/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093139 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903093140-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 303 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (04/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093140 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903093432-1 KZ4392 | WHITE | 120D | F2608WR1500 | 50 | 30/11/2026 | 50 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. DRC 0064-T2 Men Chuen, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093432 KZ4392 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | ADIZERO A TEE W WHITE |  | SS27-TRAX | 46153 | 46153 |  |  | 50 |  | 50 |  |  | 46064 | 46064 |  |  | 50 |  | 50 |  |  | 31/10/2026 | 31/10/2026 |  |  | 50 |  | 50
ADIDAS | 0903093481-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1637 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093481 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903093484-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 350 | 46214 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093484 KY9384 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903093894-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 202 | 31/10/2026 | 202 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 516333 | PRINT L2+HT SUB PROCESS_V3 | 0903093894 KZ0028 | 46212 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 202 |  | 202 |  |  | 46366 | 13/10/2026 |  |  | 202 |  | 202 |  |  | 46305 | 46366 |  |  | 202 |  | 202
ADIDAS | 0903093896-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 6 | 23/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 960026 | PRINT L2+HT SUB PROCESS_V3 | 0903093896 KZ0028 | 46212 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093897-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 478 | 15/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 830009 | PRINT L2+HT SUB PROCESS_V3 | 0903093897 KZ0028 | 46212 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093898-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 731 | 31/10/2026 | 731 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093898 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46092 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 46092 | 46123 |  |  | 731 |  | 731 |  |  | 30/10/2026 | 31/10/2026 |  |  | 731 |  | 731 |  |  | 29/10/2026 | 30/10/2026 |  |  | 731 |  | 731
ADIDAS | 0903093899-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 208 | 31/10/2026 | 208 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903093899 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 46092 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 46092 | 46123 |  |  | 208 |  | 208 |  |  | 30/10/2026 | 31/10/2026 |  |  | 208 |  | 208 |  |  | 29/10/2026 | 30/10/2026 |  |  | 208 |  | 208
ADIDAS | 0903093900-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 300 | 31/10/2026 | 300 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093900 LG1784 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300 |  |  | 21/10/2026 | 22/10/2026 |  |  | 300 |  | 300 |  |  | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903093901-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 162 | 23/10/2026 | 162 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093901 LG1784 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 162 |  | 162 |  |  | 21/10/2026 | 22/10/2026 |  |  | 162 |  | 162 |  |  | 20/10/2026 | 21/10/2026 |  |  | 162 |  | 162
ADIDAS | 0903093913-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 749 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093913 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093914-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 323 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093914 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093915-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 179 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903093915 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093916-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 320 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516254 | PAD+HT SUB PROCESS_V3 | 0903093916 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903095148-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 366 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903095148 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903095159-1 KZ1333 | HAZE CORAL S17 | 105D | S2608WR0201A | 60 | 15/11/2026 | 60 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903095159 KZ1333 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46184 | ADI365 SHO W HAZE CORAL S17 |  | SS27-TRAX | 46184 | 46184 |  |  | 60 |  | 60 |  |  | 46092 | 46092 |  |  | 60 |  | 60 |  |  | 46064 | 46064 |  |  | 60 |  | 60
ADIDAS | 0903095166-1 LF4208 | TEAM ROYAL BLUE | 105D | S2608WR0201A | 50 | 15/11/2026 | 50 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903095166 LF4208 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46184 | ADI365 SHO W TEAM ROYAL BLUE |  | SS27-TRAX | 46184 | 46184 |  |  | 50 |  | 50 |  |  | 46092 | 46092 |  |  | 50 |  | 50 |  |  | 46064 | 46064 |  |  | 50 |  | 50
ADIDAS | 0903095181-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 235 | 46214 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095181 LC6791 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903095207-1 KC4947 | BLACK | 105D | S2608WR0216 | 304 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903095207 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095212-1 KC4947 | BLACK | 105D | S2608WR0216 | 100 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 512110 | PAD+HT SUB PROCESS_V3 | 0903095212 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095214-1 KC4947 | BLACK | 105D | S2608WR0216 | 109 | 15/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | PAD+HT SUB PROCESS_V3 | 0903095214 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903110773-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 580 | 31/10/2026 | 580 | SI | SI26/06/2026 | G1L | JACKET | G1 | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110773 LE4307 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA | 46276 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 46276 | 46337 |  |  | 580 |  | 580 |  |  | 46153 | 46214 |  |  | 580 |  | 580
ADIDAS | 0903110808-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1204 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (29/07/2026) | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110808 LE4307 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903128980-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 367 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903128980 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903129024-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 400 | 31/10/2026 | 400 | SA | SA26/06/2026 | G1H | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903129024 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | W SL WV TT LEGEND IVY S19 |  | SS27 | 46153 | 46214 |  |  | 400 |  | 400 |  |  | 46064 | 46123 |  |  | 400 |  | 400
ADIDAS | 0903129074-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 152 | 23/10/2026 | 152 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129074 LI2671 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 46184 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 46184 | 46214 |  |  | 152 |  | 152 |  |  | 46092 | 46123 |  |  | 152 |  | 152
ADIDAS | 0903129078-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 399 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903129078 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903129444-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 750 | 23/10/2026 | 750 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129444 LI2645 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 750 |  | 750 |  |  | 13/10/2026 | 15/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903130651-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 698 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903130651 LG9672 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903130696-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 387 | 31/10/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130696 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903130792-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1497 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? T2 Libolon, PI Date 06-Aug, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903130792 LC5741 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 72S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27
ADIDAS | 0903130818-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130818 LI2646 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903130839-1 LF0723 | BLACK | 105D | S2754MAS511B | 358 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130839 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130858-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130858 LI2645 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903130900-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 2415 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | (04/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130900 LI2668 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903130905-1 LF0723 | BLACK | 105D | S2754MAS511B | 427 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130905 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130944-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 300 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130944 LF0725 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903130954-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 144 | 23/10/2026 | 144 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130954 LI2670 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 144 |  | 144 |  |  | 26/10/2026 | 28/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903131080-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 120 | 23/10/2026 | 120 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131080 LI2672 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 120 |  | 120 |  |  | 21/10/2026 | 23/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903131188-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131188 LI2647 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903131943-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 580 | 23/10/2026 | 580 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131943 LI2671 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 46214 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 46214 | 46276 |  |  | 580 |  | 580 |  |  | 46123 | 46153 |  |  | 580 |  | 580
ADIDAS | 0903132003-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 586 | 23/10/2026 | 586 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132003 LI2647 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 586 |  | 586 |  |  | 16/10/2026 | 17/10/2026 |  |  | 586 |  | 586
ADIDAS | 0903132130-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 450 | 23/10/2026 | 450 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132130 LI2672 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 450 |  | 450 |  |  | 21/10/2026 | 23/10/2026 |  |  | 450 |  | 450
ADIDAS | 0903132522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 634 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903132522 KX3654 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903132607-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 339 | 31/10/2026 |  | SI | SI26/06/2026 |  | JACKET |  | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132607 JE0055 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903132921-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 615 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903132921 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903132951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 830 | 31/10/2026 | 830 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903132951 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 830 |  | 830 |  |  | 46306 | 46367 |  |  | 830 |  | 830
ADIDAS | 0903133068-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 312 | 31/10/2026 | 312 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903133068 LG9661 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46276 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 46276 | 46337 |  |  | 312 |  | 312 |  |  | 46153 | 46214 |  |  | 312 |  | 312
ADIDAS | 0903133687-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1580 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133687 LI2667 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903133715-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 545 | 23/10/2026 | 545 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133715 LI2667 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 27/10/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 27/10/2026 | 27/10/2026 |  |  | 545 |  | 545 |  |  | 23/10/2026 | 23/10/2026 | 46090 | 46090 | 545 | 545
ADIDAS | 0903133886-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 888 | 23/10/2026 | 888 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133886 LI2668 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 888 |  | 888 |  |  | 20/10/2026 | 21/10/2026 | 31/08/2026 | 46212 | 888 | 687 | 201
ADIDAS | 0903133962-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1891 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133962 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903134663-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 582 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. T2 Libolon, PI Date 23-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134663 KW2909 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV WB BLACK/WHITE |  | SS27
ADIDAS | 0903134760-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134760 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903134876-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 31/10/2026 | 803 | SI | SI26/06/2026 | G2H | T-SHIRT | G2 | ok | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134876 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 46213 | BIG APPLE TEE |  | SS27 | 46213 | 46244 |  |  | 803 |  | 803 |  |  | 46091 | 46152 |  |  | 803 |  | 803
ADIDAS | 0903134935-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 31/10/2026 | 804 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134935 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | ARCH SEAL TEE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 804 |  | 804 |  |  | 15/10/2026 | 16/10/2026 |  |  | 804 |  | 804
ADIDAS | 0903135025-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (29/07/2026) | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135025 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARCH SEAL TEE |  | SS27
ADIDAS | 0903135182-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 171 | 23/10/2026 | 171 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | (04/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135182 LI2669 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 171 |  | 171 |  |  | 15/10/2026 | 16/10/2026 |  |  | 171 |  | 171
ADIDAS | 0903135229-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 184 | 23/10/2026 | 184 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135229 LI2645 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 184 |  | 184 |  |  | 13/10/2026 | 15/10/2026 |  |  | 184 |  | 184
ADIDAS | 0903135264-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 596 | 31/10/2026 | 596 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135264 LG9664 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46214 | W SL WV TT LEGEND IVY S19 |  | SS27 | 46214 | 46337 |  |  | 596 |  | 596 |  |  | 46123 | 46214 |  |  | 596 |  | 596
ADIDAS | 0903135275-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 119 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135275 LI2669 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135338-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 182 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135338 LI2645 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903135342-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 568 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | (04/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135342 LI2669 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135358-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 750 | 23/10/2026 | 750 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135358 LI2670 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 750 |  | 750 |  |  | 26/10/2026 | 28/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903135375-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 498 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903135375 LG9673 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135402-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 377 | 31/10/2026 | 377 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135402 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46276 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 46276 | 46337 |  |  | 377 |  | 377 |  |  | 46153 | 46214 |  |  | 377 |  | 377
ADIDAS | 0903135865-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 247 | 23/10/2026 | 247 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135865 LI2671 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 46184 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 46184 | 46214 |  |  | 247 |  | 247 |  |  | 46092 | 46123 |  |  | 247 |  | 247
ADIDAS | 0903135996-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1281 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135996 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136653-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 136 | 23/10/2026 | 136 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136653 LI2646 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 136 |  | 136 |  |  | 13/10/2026 | 13/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903136713-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 580 | 23/10/2026 | 580 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136713 LI2646 | 46303 | KAHATEX CIJERAH | MALAYSIA | SEA | 15/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 580 |  | 580 |  |  | 46366 | 13/10/2026 | 22/08/2026 | 46274 | 580 | 534 | 46
ADIDAS | 0903136768-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 529 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136768 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136798-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1276 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136798 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903136848-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 249 | 23/10/2026 | 249 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136848 LI2670 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 249 |  | 249 |  |  | 26/10/2026 | 28/10/2026 |  |  | 249 |  | 249
ADIDAS | 0903136900-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 254 | 23/10/2026 | 254 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136900 LI2646 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 254 |  | 254 |  |  | 46366 | 13/10/2026 | 27/08/2026 | 46031 | 254 | 254
ADIDAS | 0903136945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 127 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136945 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903136981-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 417 | 23/10/2026 | 417 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136981 LI2672 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 417 |  | 417 |  |  | 21/10/2026 | 23/10/2026 |  |  | 417 |  | 417
ADIDAS | 0903137343-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 826 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (03/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137343 KZ3227 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903137463-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 465 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (29/07/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137463 KV8005 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903138115-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 719 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138115 LI2647 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903138412-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 525 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138412 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903139177-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 107 | 23/10/2026 | 107 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139177 LI2647 | 46303 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 107 |  | 107 |  |  | 16/10/2026 | 17/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903139689-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 993 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139689 LI2672 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903140620-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 500 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903140620 KG3190 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903140969-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 5996 | 23/10/2026 | 5996 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140969 LI2645 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 19/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/10/2026 | 24/10/2026 |  |  | 5996 |  | 5996 |  |  | 15/10/2026 | 21/10/2026 |  |  | 5996 |  | 5996
ADIDAS | 0903140992-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 2091 | 23/10/2026 | 2091 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140992 LI2672 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 27/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 27/10/2026 | 30/10/2026 |  |  | 2091 |  | 2091 |  |  | 23/10/2026 | 27/10/2026 |  |  | 2091 |  | 2091
ADIDAS | 0903141018-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141018 LI2646 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 16/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 3656 |  | 3656 |  |  | 13/10/2026 | 16/10/2026 |  |  | 3656 |  | 3656
ADIDAS | 0903141059-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2521 | 23/10/2026 | 2521 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141059 LI2671 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 46276 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 46276 | 13/11/2026 |  |  | 2521 |  | 2521 |  |  | 46153 | 46306 |  |  | 2521 |  | 2521
ADIDAS | 0903141111-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3286 | 23/10/2026 | 3286 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141111 LI2670 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 31/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/10/2026 | 46184 |  |  | 3286 |  | 3286 |  |  | 28/10/2026 | 46092 |  |  | 3286 |  | 3286
ADIDAS | 0903142255-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142255 LI2647 | 46303 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 21/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/10/2026 | 24/10/2026 |  |  | 3656 |  | 3656 |  |  | 17/10/2026 | 21/10/2026 |  |  | 3656 |  | 3656
ADIDAS | 0903142659-1 KB5965 | BLACK | 120D | S2608MR0900A | 1804 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142659 KB5965 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142728-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 680 | 31/10/2026 | 680 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | (07/08/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903142728 LD0288 | 25/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 46366 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 46366 | 13/10/2026 |  |  | 680 |  | 680 |  |  | 46244 | 46275 |  |  | 680 |  | 680 |  |  | 46183 | 46213 |  |  | 680 |  | 680
ADIDAS | 0903142768-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 1350 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142768 KB5959 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142831-1 KB5962 | WONDER CARGO S26 | 120D | S2608MR0900A | 1250 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142831 KB5962 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142864-1 KB5960 | WHITE | 120D | S2608MR0900A | 677 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142864 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903143517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143517 LI2645 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903143540-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143540 LI2671 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903143571-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 450 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143571 LI2647 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903143577-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 100 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143577 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903143597-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143597 LI2646 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903143634-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143634 LI2670 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903144865-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 173 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903144865 JG5832 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903144953-1 LG9669 | BLACK | 120D | S2754WAS514C | 756 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903144953 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903144982-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1140 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903144982 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145068-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 366 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145068 LF0726 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145092-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 144 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903145092 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903145124-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 258 | 31/10/2026 | 258 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145124 LF0726 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 13/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 258 |  | 258 |  |  | 46306 | 46367 |  |  | 258 |  | 258
ADIDAS | 0903145411-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 1000 | 46214 |  | AN | AN26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145411 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903145447-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 199 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903145447 KR3066 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903145474-1 LG9669 | BLACK | 120D | S2754WAS514C | 106 | 46214 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903145474 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903145521-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903145521 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903145548-1 LG9675 | BLACK | 120D | S2754WAS513C | 1000 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903145548 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903145603-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 1400 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145603 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903145609-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 23/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145609 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | M 3S CHELSEA B7 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 330 |  | 330 |  |  | 23/10/2026 | 24/10/2026 |  |  | 330 |  | 330
ADIDAS | 0903145625-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 23/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145625 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | M 3S CHELSEA B7 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 24/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903145643-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 235 | 31/10/2026 | 235 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145643 LF0729 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 46064 | M SL WV TT OLIVE ONE S27 |  | SS27 | 46064 | 46123 |  |  | 235 |  | 235 |  |  | 29/10/2026 | 31/10/2026 |  |  | 235 |  | 235
ADIDAS | 0903145666-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 204 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145666 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903145710-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 562 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800187 | PRINT L1+HT SUB PROCESS_V3 | 0903145710 KU8361 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146070-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 798 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903146070 KU8361 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146231-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 581 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146231 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146256-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146256 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146268-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 132 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146268 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903146275-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 527 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903146275 KU8361 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146335-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 402 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146335 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903146356-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 414 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146356 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903146377-1 KB5965 | BLACK | 120D | S2608MR0900A | 930 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146377 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146405-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 1844 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146405 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903146415-1 KB5960 | WHITE | 120D | S2608MR0900A | 360 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146415 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146436-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 120 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Cargoport). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650036 | HT+PAD SUB PROCESS_V3 | 0903146436 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146460-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 192 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146460 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903146478-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Cargoport). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 650036 | HT+PAD SUB PROCESS_V3 | 0903146478 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903146497-1 KE8424 | BLACK | 120D | S2608MR0906A | 438 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146497 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903146508-1 JZ7711 | BLACK | 120D | S2608MR0202 | 144 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (Cargoport). T2 Trax, PI Date 24-Jul, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146508 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146621-1 LC6583 | GREY | 105D | S2750MTR051 | 680 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 814006 | HT SUB PROCESS_V1 | 0903146621 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903146631-1 KB5960 | WHITE | 120D | S2608MR0900A | 1601 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903146631 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146633-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 226 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903146633 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903146650-1 LE8187 | BLACK | 105D | S2754MAS513 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146650 LE8187 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903146681-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146681 KA3549 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903146708-1 LG9669 | BLACK | 120D | S2754WAS514C | 235 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903146708 LG9669 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146764-1 LG9669 | BLACK | 120D | S2754WAS514C | 333 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903146764 LG9669 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146867-1 JZ7711 | BLACK | 120D | S2608MR0202 | 274 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146867 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146909-1 KB5960 | WHITE | 120D | S2608MR0900A | 796 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903146909 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146928-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 956 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903146928 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146963-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 220 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146963 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903147001-1 KB5965 | BLACK | 120D | S2608MR0900A | 922 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147001 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903147074-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 304 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903147074 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903147100-1 KE8424 | BLACK | 120D | S2608MR0906A | 306 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147100 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903147122-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 820 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147122 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903147964-1 LC6583 | GREY | 105D | S2750MTR051 | 210 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800187 | HT SUB PROCESS_V1 | 0903147964 LC6583 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148024-1 KU8357 | BLACK | 105D | S2750MTR051 | 331 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800187 | HT SUB PROCESS_V1 | 0903148024 KU8357 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148048-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 221 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148048 KY5901 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148050-1 KE8424 | BLACK | 120D | S2608MR0906A | 1085 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903148050 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903148127-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 213 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148127 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148659-1 LF0727 | BLACK | 120D | S2754MAS510B | 143 | 31/10/2026 | 143 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148659 LF0727 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 46092 | M SL WV TT BLACK |  | SS27 | 46092 | 46153 |  |  | 143 |  | 143 |  |  | 30/10/2026 | 46064 |  |  | 143 |  | 143
ADIDAS | 0903148668-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148668 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148669-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 150 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 826010 | HT+PAD SUB PROCESS_V3 | 0903148669 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148676-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 2259 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903148676 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903148695-1 KE8424 | BLACK | 120D | S2608MR0906A | 146 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148695 KE8424 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903148707-1 LG9675 | BLACK | 120D | S2754WAS513C | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903148707 LG9675 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903148723-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 120 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148723 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148742-1 KU8357 | BLACK | 105D | S2750MTR051 | 221 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148742 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148757-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 128 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148757 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148758-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 393 | 30/10/2026 | 393 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148758 LG9666 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 46064 | W SL WV TT BLACK |  | SS27 | 46064 | 46153 |  |  | 393 |  | 393 |  |  | 29/10/2026 | 46064 |  |  | 393 |  | 393
ADIDAS | 0903148833-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1032 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148833 KC8152 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903148870-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 308 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903148870 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148894-1 KB5965 | BLACK | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148894 KB5965 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148901-1 KU8357 | BLACK | 105D | S2750MTR051 | 450 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148901 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148919-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 383 | 31/10/2026 | 383 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148919 LG9661 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 46337 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 46337 | 13/11/2026 |  |  | 383 |  | 383 |  |  | 46214 | 46306 |  |  | 383 |  | 383
ADIDAS | 0903148944-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 732 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903148944 LD0283 | 25/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903149035-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1 | 30/10/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. Waiting fabric. DRC 0064-T2 Libolon, PI Date 08-Sep, ETD ?? T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149035 KZ3231 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 1 |  | 1 |  |  | 46275 | 46275 |  |  | 1 |  | 1
ADIDAS | 0903149084-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 712 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 659018 | HT+PAD SUB PROCESS_V3 | 0903149084 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903149176-1 JZ7711 | BLACK | 120D | S2608MR0202 | 540 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (KN GLT). T2 Trax, PI Date 24-Jul, ETD ?? 650031 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149176 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903149255-1 KT4840 | ONIX | 90D | S2408MR1600 | 352 | 31/10/2026 | 352 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903149255 KT4840 | 46304 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 352 |  | 352 |  |  | 26/10/2026 | 27/10/2026 |  |  | 352 |  | 352 |  |  | 24/10/2026 | 26/10/2026 |  |  | 352 |  | 352
ADIDAS | 0903149303-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149303 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149363-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 158 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149363 KR3066 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149522-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 108 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149522 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149602-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 100 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903149602 JJ0052 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903149641-1 KA3530 | BLACK | 105D | S2650MTR402 | 128 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903149641 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903149843-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 396 | 30/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149843 JW7182 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903149931-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903149931 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903149955-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149955 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903150045-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1980 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516415 | HT+PAD SUB PROCESS_V3 | 0903150045 KX3651 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0903150153-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 125 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150153 LF0725 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903150285-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 31/10/2026 |  | AN | AN26/06/2026 |  | SKIRT |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPA SUB PROCESS_V3 | 0903150285 LG9669 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903150319-1 LF0727 | BLACK | 120D | S2754MAS510B | 1245 | 31/10/2026 | 1245 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150319 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 46306 | M SL WV TT BLACK |  | SS27 | 46306 | 14/11/2026 |  |  | 1245 |  | 1245 |  |  | 46184 | 46337 |  |  | 1245 |  | 1245
ADIDAS | 0903150418-1 KB5960 | WHITE | 120D | S2608MR0900A | 1040 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150418 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903150446-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 340 | 30/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150446 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903150468-1 KE8424 | BLACK | 120D | S2608MR0906A | 487 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150468 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903150575-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1906 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903150575 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903150606-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 850 | 30/10/2026 | 850 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150606 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 46213 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46213 | 46213 |  |  | 850 |  | 850 |  |  | 46091 | 46091 |  |  | 850 |  | 850 |  |  | 46032 | 46032 |  |  | 850 |  | 850
ADIDAS | 0903150974-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 534 | 31/10/2026 | 534 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150974 LC6339 | 46304 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 534 |  | 534 |  |  | 46305 | 46305 | 46243 | 46274 | 534 | 467 | 67
ADIDAS | 0903150999-1 LG9669 | BLACK | 120D | S2754WAS514C | 143 | 15/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512102 | PRINT L3+PPA SUB PROCESS_V3 | 0903150999 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151026-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 739 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 659018 | HT+PAD SUB PROCESS_V3 | 0903151026 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903151067-1 HK7319 | BLACK | 90D | F2225M403 | 378 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | 848016 | EMBRO+PPA SUB PROCESS_V3 | 0903151067 HK7319 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903151173-1 KA3530 | BLACK | 105D | S2650MTR402 | 376 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151173 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151195-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1684 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903151195 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903151218-1 JZ7766 | MEDIUM GREY HEATHER | 90D | S2608MR0901 | 112 | 31/10/2026 | 112 | AN | AN26/06/2026 | G1E | SHORTS | G1 |  |  | (NYK warehouse). Waiting fabric. T2 Formosa, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 07-Sep. 800005 | PAD+HT SUB PROCESS_V3 | 0903151218 JZ7766 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA | 46184 | Run Ess Shor M MEDIUM GREY HEATHER |  | SS27-TRAX | 46184 | 46184 |  |  | 112 |  | 112 |  |  | 46092 | 46092 |  |  | 112 |  | 112 |  |  | 46064 | 46064 |  |  | 112 |  | 112
ADIDAS | 0903151246-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 222 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151246 KD5507 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903151271-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151271 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151275-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 991 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903151275 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903151312-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 434 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903151312 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903151379-1 LG9669 | BLACK | 120D | S2754WAS514C | 600 | 46214 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903151379 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151446-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1400 | 30/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903151446 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903151598-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 539 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903151598 KU8361 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903152248-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 870 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152248 KY9384 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903152349-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 533 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152349 HK7317 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152378-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 731 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152378 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152402-1 KB5965 | BLACK | 120D | S2608MR0900A | 551 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152402 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152441-1 LF0727 | BLACK | 120D | S2754MAS510B | 813 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152441 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903152456-1 KB5965 | BLACK | 120D | S2608MR0900A | 926 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152456 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152475-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 568 | 31/10/2026 | 568 | AN | AN26/06/2026 | G1J | JACKET | G1 | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jul, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152475 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 13/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 568 |  | 568 |  |  | 46306 | 46367 |  |  | 568 |  | 568
ADIDAS | 0903152478-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 533 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152478 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152519-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 897 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152519 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152536-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1831 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152536 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903152621-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 285 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152621 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903152760-1 KB5960 | WHITE | 120D | S2608MR0900A | 430 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903152760 KB5960 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152806-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 1128 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152806 KD3854 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152841-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152841 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152887-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 435 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903152887 KY9391 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152912-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 100 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903152912 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152941-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152941 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903153139-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 447 | 31/10/2026 | 447 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903153139 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46367 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 46367 | 14/11/2026 |  |  | 447 |  | 447 |  |  | 46276 | 46337 |  |  | 447 |  | 447 |  |  | 46153 | 46214 |  |  | 447 |  | 447
ADIDAS | 0903153406-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 477 | 46214 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 823016 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153406 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903153476-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 102 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 680014 | PRINT L2+HT SUB PROCESS_V3 | 0903153476 KZ0028 | 46304 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903153519-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 17 | 31/10/2026 | 17 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153519 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27-SPOMA | 13/11/2026 | 16/11/2026 |  |  | 17 |  | 17 |  |  | 46306 | 46367 |  |  | 17 |  | 17
ADIDAS | 0903153531-1 KT4840 | ONIX | 90D | S2408MR1600 | 348 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903153531 KT4840 | 46304 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903153585-1 LG9675 | BLACK | 120D | S2754WAS513C | 17 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903153585 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27-SPOMA
ADIDAS | 0903153589-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1010 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903153589 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903153623-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 17 | 31/10/2026 | 17 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153623 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46064 | W SL WV TT KHAKI THREE F26 |  | SS27-SPOMA | 46064 | 46153 |  |  | 17 |  | 17 |  |  | 29/10/2026 | 46064 |  |  | 17 |  | 17
ADIDAS | 0903153628-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 774 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (Damco offline). 688010 | PRINT L2+PAD SUB PROCESS_V3 | 0903153628 KU2430 | 46303 | KAHATEX CIJERAH | PANAMA | SEA |  | M FB NOVELTY T WHITE |  | SS27
ADIDAS | 0903153664-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 228 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | HT+PAD SUB PROCESS_V3 | 0903153664 KX3655 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903153698-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 409 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903153698 KB5961 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903153721-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 348 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903153721 KE6716 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903153738-1 JZ5129 | CRYSTAL LINEN S26 | 120D | S2608WR0201 | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Best Pacific, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD 30-Jul, ETA-Kaha 14-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903153738 JZ5129 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W CRYSTAL LINEN S26 |  | SS27-TRAX
ADIDAS | 0903153739-1 KE8424 | BLACK | 120D | S2608MR0906A | 463 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153739 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903153765-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 360 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153765 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903153773-1 KB5965 | BLACK | 120D | S2608MR0900A | 1585 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153773 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903153793-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1153 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153793 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903153803-1 KE8424 | BLACK | 120D | S2608MR0906A | 580 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153803 KE8424 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903153815-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1477 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153815 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903153840-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 540 | 30/10/2026 | 540 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903153840 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 46275 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 46275 | 46305 |  |  | 540 |  | 540 |  |  | 46183 | 46213 |  |  | 540 |  | 540 |  |  | 46091 | 46152 |  |  | 540 |  | 540
ADIDAS | 0903153959-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 609 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153959 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903153964-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 242 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153964 LD5446 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903153995-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 401 | 31/10/2026 | 401 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153995 LD0285 | 25/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 46213 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46213 | 46244 |  |  | 401 |  | 401 |  |  | 46091 | 46152 |  |  | 401 |  | 401 |  |  | 46032 | 46063 |  |  | 401 |  | 401
ADIDAS | 0903154696-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 68 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903154696 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903154728-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 58 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903154728 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903154754-1 KB5965 | BLACK | 120D | S2608MR0900A | 270 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903154754 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903154776-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 1663 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154776 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154799-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 13 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154799 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154868-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 393 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154868 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903154889-1 KA3549 | BLACK | 135D | S2650MTR412 | 126 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154889 KA3549 | 46334 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903154942-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 313 | 30/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903154942 KX3654 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155043-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 210 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903155043 LC8943 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903155169-1 KB5960 | WHITE | 120D | S2608MR0900A | 2500 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903155169 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155209-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 834012 | HT+PAD SUB PROCESS_V3 | 0903155209 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155422-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1482 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903155422 KX3654 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155535-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 180 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155535 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155567-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155567 KF5311 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903155586-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903155586 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903155594-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155594 KX3654 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155612-1 KT4840 | ONIX | 90D | S2408MR1600 | 186 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 680014 | HT SUB PROCESS_V1 | 0903155612 KT4840 | 46304 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903155635-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 467 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Airowes). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650034 | HT+PAD SUB PROCESS_V3 | 0903155635 KB5961 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155678-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 224 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155678 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 558 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903155800-1 LC7300 | WHITE | 90D | S2725M926A | 262 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903155800 LC7300 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903155810-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1129 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155810 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903155831-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 112 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903155831 LC7301 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903155848-1 KB5965 | BLACK | 120D | S2608MR0900A | 985 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155848 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155878-1 KB5960 | WHITE | 120D | S2608MR0900A | 591 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155878 KB5960 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155908-1 KB5960 | WHITE | 120D | S2608MR0900A | 460 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155908 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155939-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 908 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 684009 | HT+PAD SUB PROCESS_V3 | 0903155939 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155947-1 KA3549 | BLACK | 135D | S2650MTR412 | 110 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903155947 KA3549 | 46334 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156012-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903156012 KA3549 | 46334 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156032-1 KE8424 | BLACK | 120D | S2608MR0906A | 522 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903156032 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903156091-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 126 | 31/10/2026 | 126 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156091 LG9666 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 46064 | W SL WV TT BLACK |  | SS27 | 46064 | 46153 |  |  | 126 |  | 126 |  |  | 29/10/2026 | 46064 |  |  | 126 |  | 126
ADIDAS | 0903156098-1 LC6583 | GREY | 105D | S2750MTR051 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 839055 | HT SUB PROCESS_V1 | 0903156098 LC6583 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156120-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 131 | 31/10/2026 | 131 | SA | SA26/06/2026 | G1H | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156120 LG9664 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 46214 | W SL WV TT LEGEND IVY S19 |  | SS27 | 46214 | 46337 |  |  | 131 |  | 131 |  |  | 46123 | 46214 |  |  | 131 |  | 131
ADIDAS | 0903156126-1 KU8357 | BLACK | 105D | S2750MTR051 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 839055 | HT SUB PROCESS_V1 | 0903156126 KU8357 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156155-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 684 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903156155 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903156456-1 LC7300 | WHITE | 90D | S2725M926A | 207 | 23/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903156456 LC7300 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903156549-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 198 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156549 KW8934 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX
ADIDAS | 0903156599-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 300 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156599 KW8935 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX
ADIDAS | 0903156637-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 320 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903156637 KB0246 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903156704-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 101 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903156704 LD0908 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903156821-1 LC6583 | GREY | 105D | S2750MTR051 | 196 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903156821 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156923-1 KU8357 | BLACK | 105D | S2750MTR051 | 232 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903156923 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156956-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 114 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903156956 LC8884 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903157033-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903157033 LC7300 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903157056-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903157056 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903157138-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 106 | 23/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903157138 LC8943 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903157615-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 102 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157615 LG9664 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903157637-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 149 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157637 LD5446 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903157666-1 KB5965 | BLACK | 120D | S2608MR0900A | 1085 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157666 KB5965 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157694-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 909 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903157694 KE8420 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903157699-1 KB5960 | WHITE | 120D | S2608MR0900A | 191 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157699 KB5960 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157718-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 850 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903157718 KF5311 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157739-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1210 | 23/10/2026 | 1210 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157739 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 1210 |  | 1210 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903157760-1 KB5965 | BLACK | 120D | S2608MR0900A | 410 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903157760 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157766-1 KE6899 | BLACK | 105D | S2608WR0601B | 120 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Airowes). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903157766 KE6899 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903157787-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 546 | 30/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT+PAD SUB PROCESS_V3 | 0903157787 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903157799-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157799 KF5311 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157832-1 KB5960 | WHITE | 120D | S2608MR0900A | 1492 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157832 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157859-1 KB5965 | BLACK | 120D | S2608MR0900A | 3535 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157859 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157884-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 502 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 678002 | HT+PAD SUB PROCESS_V3 | 0903157884 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157900-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 961 | 31/10/2026 | 961 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157900 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 961 |  | 961 |  |  | 46367 | 14/11/2026 |  |  | 961 |  | 961
ADIDAS | 0903157922-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 3009 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903157922 KR3066 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903157925-1 LG9669 | BLACK | 120D | S2754WAS514C | 100 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric (Airowes). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903157925 LG9669 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903157926-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 1091 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 60000 | PRINT L3+PPA SUB PROCESS_V3 | 0903157926 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158029-1 KE6712 | BLACK | 105D | S2608MR0601A | 102 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric (Airowes). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903158029 KE6712 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 SHORT M BLACK |  | SS27-TRAX
ADIDAS | 0903158101-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 266 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158101 KX3655 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 379 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158133 KX3654 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903158148-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 162 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158148 LG9673 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158151-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 436 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158151 KU8797 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B SJ LF T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903158174-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 142 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903158174 KE8420 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903158194-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 838103 | HT SUB PROCESS_V1 | 0903158194 KY5866 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903158195-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 160 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903158195 KF5311 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903158219-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 168 | 23/10/2026 | 168 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158219 KW9039 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 28/10/2026 | 28/10/2026 |  |  | 168 |  | 168 |  |  | 24/10/2026 | 24/10/2026 |  |  | 168 |  | 168
ADIDAS | 0903158242-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 550 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903158242 JZ1089 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903158287-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 624 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158287 LG9672 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903158307-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 310 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903158307 KX3651 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0903158314-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 492 | 31/10/2026 | 492 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158314 LC6790 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46367 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 46367 | 14/11/2026 |  |  | 492 |  | 492 |  |  | 46276 | 46337 |  |  | 492 |  | 492 |  |  | 46153 | 46214 |  |  | 492 |  | 492
ADIDAS | 0903158332-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158332 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158354-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158354 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158375-1 LG9666 | BLACK | 120D | S2754WAS512C | 201 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158375 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903158394-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 571 | 31/10/2026 | 571 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903158394 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46275 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 46275 | 46305 |  |  | 571 |  | 571 |  |  | 46183 | 46213 |  |  | 571 |  | 571 |  |  | 46091 | 46152 |  |  | 571 |  | 571
ADIDAS | 0903158398-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 188 | 23/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158398 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158417-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 738 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158417 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903158426-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903158426 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158432-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 2411 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158432 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903158445-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 900 | 31/10/2026 | 900 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158445 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/11/2026 | 23/11/2026 |  |  | 900 |  | 900 |  |  | 16/11/2026 | 19/11/2026 |  |  | 900 |  | 900
ADIDAS | 0903158447-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 152 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158447 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158467-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 347 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903158467 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903158468-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158468 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158523-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158523 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158528-1 KB5960 | WHITE | 120D | S2608MR0900A | 450 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903158528 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903158543-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158543 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158556-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1004 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158556 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903158570-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158570 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158596-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158596 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158627-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158627 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158646-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 507 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903158646 LD0930 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158671-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 319 | 31/10/2026 | 319 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158671 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 18/11/2026 |  |  | 319 |  | 319 |  |  | 46337 | 14/11/2026 |  |  | 319 |  | 319 |  |  | 46214 | 46337 |  |  | 319 |  | 319
ADIDAS | 0903158788-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158788 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | PDX HBR TEE |  | SS27
ADIDAS | 0903158813-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158813 KR1994 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | DICE TEE |  | SS27
ADIDAS | 0903158854-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 107 | 31/10/2026 | 107 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158854 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | PDX HBR TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 107 |  | 107 |  |  | 15/09/2026 | 16/09/2026 | 15/08/2026 | 26/08/2026 | 107 | 107
ADIDAS | 0903158880-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158880 KR1994 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | DICE TEE |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 311 |  | 311 |  |  | 17/10/2026 | 17/10/2026 |  |  | 311 |  | 311 |  |  | 15/10/2026 | 15/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903159008-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159008 KS2145 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | PIZZA TEE |  | SS27
ADIDAS | 0903159048-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 340 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903159048 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903159067-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159067 KS2145 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | PIZZA TEE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 311 |  | 311 |  |  | 13/10/2026 | 14/10/2026 | 21/08/2026 | 22/08/2026 | 311 | 308 | 3
ADIDAS | 0903159089-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | ok | ok | T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159089 KV7963 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903159152-1 JZ7711 | BLACK | 120D | S2608MR0202 | 187 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159152 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903159185-1 KU8357 | BLACK | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903159185 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903159233-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 114 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159233 KX0126 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T OLIVE FOUR S27 |  | SS27
ADIDAS | 0903159261-1 KT4840 | ONIX | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903159261 KT4840 | 46304 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 324 |  | 324 |  |  | 26/10/2026 | 27/10/2026 |  |  | 324 |  | 324 |  |  | 24/10/2026 | 26/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903159272-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 228 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159272 LC7301 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903159289-1 KA0235 | BLACK | 90D | S2608WR0901 | 1180 | 23/10/2026 | 1180 | SI | SI26/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 516415 | PAD+HT SUB PROCESS_V3 | 0903159289 KA0235 | 46304 | KAHATEX CIJERAH | GERMANY | SEA | 46184 | Run Ess Shor W BLACK |  | SS27-TRAX | 46184 | 46306 |  |  | 1180 |  | 1180 |  |  | 46092 | 46184 |  |  | 1180 |  | 1180 |  |  | 46064 | 46153 |  |  | 1180 |  | 1180
ADIDAS | 0903159311-1 LC7300 | WHITE | 90D | S2725M926A | 228 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159311 LC7300 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903159349-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 156 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903159349 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903159424-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric (Cargoport). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650036 | PRINT L3+PPA SUB PROCESS_V3 | 0903159424 LG9669 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903159447-1 KE6899 | BLACK | 105D | S2608WR0601B | 102 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Cargoport). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903159447 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903159678-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 159 | 23/10/2026 | 159 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903159678 KZ0028 | 46304 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 159 |  | 159 |  |  | 46366 | 13/10/2026 |  |  | 159 |  | 159 |  |  | 46305 | 46366 |  |  | 159 |  | 159
ADIDAS | 0903159703-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 23/10/2026 | 101 | AN | AN26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159703 KZ3205 | 46304 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 30/10/2026 | 46153 |  |  | 101 |  | 101 |  |  | 27/10/2026 | 46064 |  |  | 101 |  | 101
ADIDAS | 0903159732-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 155 | 23/10/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 512106 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159732 KU8975 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903159754-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 584 | 23/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159754 LF0726 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159774-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159774 KR3066 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903159800-1 LG9669 | BLACK | 120D | S2754WAS514C | 396 | 23/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903159800 LG9669 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903159879-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 300 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903159879 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903159916-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 305 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159916 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903159937-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 920 | 31/10/2026 | 920 | SA | SA26/06/2026 | G1I | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903159937 JZ7775 | 46304 | KAHATEX CIJERAH | CANADA | SEA | 13/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 920 |  | 920 |  |  | 46306 | 46367 |  |  | 920 |  | 920 |  |  | 46276 | 46337 |  |  | 920 |  | 920
ADIDAS | 0903160049-1 KA3530 | BLACK | 105D | S2650MTR402 | 244 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903160049 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160079-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 130 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903160079 KB0237 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903160116-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 364 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903160116 KV7863 | 46304 | KAHATEX CIJERAH | CANADA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903160125-1 KA3530 | BLACK | 105D | S2650MTR402 | 257 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903160125 KA3530 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160143-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 382 | 31/10/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160143 KW2924 | 46304 | KAHATEX CIJERAH | CANADA | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903160245-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160245 KY5866 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160344-1 KY5866 | BLACK | 90D | S2750MTR052 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160344 KY5866 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160502-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 852 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516267 | PAD+HT SUB PROCESS_V3 | 0903160502 LD0908 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903160662-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 1461 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160662 LD6542 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903160682-1 KB5960 | WHITE | 120D | S2608MR0900A | 250 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903160682 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903160693-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 359 | 31/10/2026 | 359 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160693 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | W SL WV TT BLACK |  | SS27 | 46153 | 46184 |  |  | 359 |  | 359 |  |  | 46064 | 46092 |  |  | 359 |  | 359
ADIDAS | 0903160711-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 758 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903160711 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903160743-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 594 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903160743 KX3655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903160769-1 LG9675 | BLACK | 120D | S2754WAS513C | 392 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903160769 LG9675 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903160891-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 317 | 31/10/2026 | 317 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160891 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 16/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/11/2026 | 19/11/2026 |  |  | 317 |  | 317 |  |  | 46367 | 16/11/2026 |  |  | 317 |  | 317
ADIDAS | 0903161179-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2545 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161179 KZ3202 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903161241-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2662 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | (07/08/2026) | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161241 KZ3200 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903162158-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162158 KB0234 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903162234-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 324 | 46214 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162234 JZ1077 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T BLACK |  | SS27-STX
ADIDAS | 0903162276-1 KA3530 | BLACK | 105D | S2650MTR402 | 1263 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903162276 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903162278-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1526 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162278 LD0283 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903162384-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162384 JZ1089 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA | 46306 | M SERENO SHO WHITE |  | SS27-STX | 46306 | 46337 |  |  | 327 |  | 327 |  |  | 46184 | 46214 |  |  | 327 |  | 327 |  |  | 46153 | 46184 |  |  | 327 |  | 327
ADIDAS | 0903162397-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 1526 | 31/10/2026 | 1526 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162397 LD0285 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 46244 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 46244 | 46305 |  |  | 1526 |  | 1526 |  |  | 46152 | 46213 |  |  | 1526 |  | 1526 |  |  | 46063 | 46152 |  |  | 1526 |  | 1526
ADIDAS | 0903162423-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 1500 | 31/10/2026 | 1500 | AN | AN29/06/2026 | G2H | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162423 LD0287 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 46152 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 46152 | 46183 |  |  | 1500 |  | 1500 |  |  | 46032 | 46063 |  |  | 1500 |  | 1500 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903162450-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 31/10/2026 | 300 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162450 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 46305 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 46305 | 46366 |  |  | 300 |  | 300 |  |  | 46213 | 46244 |  |  | 300 |  | 300 |  |  | 46152 | 46183 |  |  | 300 |  | 300
ADIDAS | 0903162460-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162460 JZ1090 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA | 46306 | M SERENO SHO BLACK |  | SS27-STX | 46306 | 46337 |  |  | 327 |  | 327 |  |  | 46184 | 46214 |  |  | 327 |  | 327 |  |  | 46153 | 46184 |  |  | 327 |  | 327
ADIDAS | 0903162479-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 20-Jul, actual receives 31-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162479 LF0727 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 46092 | M SL WV TT BLACK |  | SS27 | 46092 | 46153 |  |  | 300 |  | 300 |  |  | 30/10/2026 | 46064 |  |  | 300 |  | 300
ADIDAS | 0903162492-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 348 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162492 KB0247 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903162518-1 KA3549 | BLACK | 135D | S2650MTR412 | 208 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162518 KA3549 | 46334 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903162545-1 KA3549 | BLACK | 135D | S2650MTR412 | 921 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162545 KA3549 | 46334 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903163092-1 KU8357 | BLACK | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 838103 | HT SUB PROCESS_V1 | 0903163092 KU8357 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903163124-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 372 | 31/10/2026 | 372 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903163124 LG9661 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA | 46337 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 46337 | 13/11/2026 |  |  | 372 |  | 372 |  |  | 46214 | 46306 |  |  | 372 |  | 372
ADIDAS | 0903163238-1 KB5960 | WHITE | 120D | S2608MR0900A | 887 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163238 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903163335-1 KB5965 | BLACK | 120D | S2608MR0900A | 1228 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163335 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903163398-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903163398 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903163452-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 411 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163452 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903163561-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 610 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163561 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903164375-1 KW5050 | MAROON | 90D | F2625M101 | 1414 | 23/10/2026 | 1414 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | (29/07/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164375 KW5050 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA | 46366 | ESS REG |  | SS27-STX | 46366 | 13/10/2026 |  |  | 1414 |  | 1414 |  |  | 46244 | 46275 |  |  | 1414 |  | 1414
ADIDAS | 0903164394-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 940 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164394 KB0237 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903164435-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 280 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164435 KB0234 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164449-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 892 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164449 KS3009 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903164473-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 776 | 23/10/2026 | 776 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164473 KT7396 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 13/10/2026 | 14/10/2026 |  |  | 776 |  | 776 |  |  | 46275 | 46305 |  |  | 776 |  | 776
ADIDAS | 0903164515-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903164515 KA3530 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903164654-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 651 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903164654 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903164675-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 141 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164675 JZ1090 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164712-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 100 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164712 JZ1090 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164747-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 205 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164747 KB0246 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164777-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 102 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164777 JZ1089 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164808-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 278 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164808 JZ1089 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164853-1 KT4840 | ONIX | 90D | S2408MR1600 | 206 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903164853 KT4840 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903164866-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 522 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903164866 KU8361 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903164923-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 182 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164923 KV8149 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164958-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 150 | 46214 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164958 KV8142 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164977-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 845 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903164977 KW8933 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903165011-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 112 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903165011 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI
ADIDAS | 0903165037-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 273 | 31/10/2026 | 273 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165037 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/11/2026 | 19/11/2026 |  |  | 273 |  | 273 |  |  | 46367 | 16/11/2026 |  |  | 273 |  | 273
ADIDAS | 0903165062-1 LF0727 | BLACK | 120D | S2754MAS510B | 562 | 31/10/2026 | 562 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165062 LF0727 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46153 | M SL WV TT BLACK |  | SS27 | 46153 | 46306 |  |  | 562 |  | 562 |  |  | 46064 | 46184 |  |  | 562 |  | 562
ADIDAS | 0903165085-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 303 | 31/10/2026 | 303 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165085 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/11/2026 | 19/11/2026 |  |  | 303 |  | 303 |  |  | 46367 | 16/11/2026 |  |  | 303 |  | 303
ADIDAS | 0903165093-1 KY5866 | BLACK | 90D | S2750MTR052 | 294 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903165093 KY5866 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903165114-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 152 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903165114 KS3009 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903165143-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903165143 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165365-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 400 | 46214 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165365 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903165408-1 LG9675 | BLACK | 120D | S2754WAS513C | 384 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903165408 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903165453-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 924 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903165453 KV8149 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903165496-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 300 | 31/10/2026 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165496 LF0729 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46064 | M SL WV TT OLIVE ONE S27 |  | SS27 | 46064 | 46123 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903165549-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903165549 KD5507 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165577-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 178 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PAD+HT SUB PROCESS_V3 | 0903165577 JG5832 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903165613-1 LC7300 | WHITE | 90D | S2725M926A | 240 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903165613 LC7300 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903165645-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 428 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903165645 KG3190 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903166410-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 217 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PAD+HT SUB PROCESS_V3 | 0903166410 JJ0052 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903166569-1 JJ2417 | BLACK/WHITE | 90D | S2506GHTM401Y | 174 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | 1st Art (TC 10 pcs) 838103 | PAD+HT SUB PROCESS_V3 | 0903166569 JJ2417 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 SHO Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903166626-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 123 | 16/10/2026 | 123 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903166626 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/10/2026 | W SL WV TT BLACK |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 123 |  | 123 |  |  | 22/10/2026 | 23/10/2026 |  |  | 123 |  | 123
ADIDAS | 0903167173-1 LF0727 | BLACK | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167173 LF0727 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46092 | M SL WV TT BLACK |  | SS27 | 46092 | 46153 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 46064 |  |  | 127 |  | 127
ADIDAS | 0903167251-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 31/10/2026 | 311 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167251 KR6693 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | LV COLLEGIATE T |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 311 |  | 311 |  |  | 15/10/2026 | 15/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903167257-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 852 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903167257 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167292-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167292 KR6693 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | LV COLLEGIATE T |  | SS27
ADIDAS | 0903167354-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 180 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903167354 KU8361 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903167397-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 615 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903167397 LC7301 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903167406-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 160 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903167406 KB0247 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903167413-1 LC7300 | WHITE | 90D | S2725M926A | 354 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903167413 LC7300 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167435-1 LF0727 | BLACK | 120D | S2754MAS510B | 884 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167435 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903167439-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1157 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903167439 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167515-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 800187 | PRINT L1 SUB PROCESS_V3 | 0903167515 LC7300 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167519-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 733 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167519 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167539-1 KY5866 | BLACK | 90D | S2750MTR052 | 100 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903167539 KY5866 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167551-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 700 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167551 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903167578-1 KY5866 | BLACK | 90D | S2750MTR052 | 1639 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903167578 KY5866 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167609-1 LF0727 | BLACK | 120D | S2754MAS510B | 718 | 31/10/2026 | 718 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167609 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | M SL WV TT BLACK |  | SS27 | 46153 | 46306 |  |  | 718 |  | 718 |  |  | 46064 | 46184 |  |  | 718 |  | 718
ADIDAS | 0903167625-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 494 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167625 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167656-1 LC6583 | GREY | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 838103 | HT SUB PROCESS_V1 | 0903167656 LC6583 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903167699-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903167699 KD5507 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167760-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167760 LF0729 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46064 | M SL WV TT OLIVE ONE S27 |  | SS27 | 46064 | 46123 |  |  | 127 |  | 127 |  |  | 29/10/2026 | 31/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903167765-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 536 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 04-Sep. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516267 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167765 KV7863 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903167819-1 KA4331 | BLACK | 90D | S2608MR0902 | 418 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903167819 KA4331 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903167827-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 504 | 31/10/2026 | 504 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167827 LG9665 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46064 | W SL WV TT KHAKI THREE F26 |  | SS27 | 46064 | 46153 |  |  | 504 |  | 504 |  |  | 29/10/2026 | 46064 |  |  | 504 |  | 504
ADIDAS | 0903167866-1 LG9675 | BLACK | 120D | S2754WAS513C | 530 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167866 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903167963-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 332 | 31/10/2026 | 332 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167963 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46064 | W SL WV TT KHAKI THREE F26 |  | SS27 | 46064 | 46153 |  |  | 332 |  | 332 |  |  | 29/10/2026 | 46064 |  |  | 332 |  | 332
ADIDAS | 0903167978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 344 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167978 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903168036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 707 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903168036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903168065-1 KB5960 | WHITE | 120D | S2608MR0900A | 304 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0903168065 KB5960 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903168155-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 209 | 23/10/2026 | 209 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168155 KT7396 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 13/10/2026 | 14/10/2026 |  |  | 209 |  | 209 |  |  | 46275 | 46305 |  |  | 209 |  | 209
ADIDAS | 0903168201-1 KW5050 | MAROON | 90D | F2625M101 | 339 | 23/10/2026 | 339 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168201 KW5050 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA | 46305 | ESS REG |  | SS27-STX | 46305 | 46366 |  |  | 339 |  | 339 |  |  | 46213 | 46244 |  |  | 339 |  | 339
ADIDAS | 0903168237-1 KA3530 | BLACK | 105D | S2650MTR402 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903168237 KA3530 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903168653-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 190 | 31/10/2026 | 190 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903168653 LG9666 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46153 | W SL WV TT BLACK |  | SS27 | 46153 | 46184 |  |  | 190 |  | 190 |  |  | 46064 | 46092 |  |  | 190 |  | 190
ADIDAS | 0903169208-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 320 | 23/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169208 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903169300-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 150 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903169300 KD5507 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903169653-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 438 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903169653 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903169676-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 310 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903169676 LC7301 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903169815-1 KY5866 | BLACK | 90D | S2750MTR052 | 259 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903169815 KY5866 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903170004-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903170004 LC7301 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903170187-1 KB5965 | BLACK | 120D | S2608MR0900A | 509 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170187 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI | [20 empty] | 46335 | 46335
ADIDAS | 0903170312-1 KB5960 | WHITE | 120D | S2608MR0900A | 164 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170312 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903170968-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 160 | 23/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903170968 LC7301 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903171050-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 600 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903171050 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903171083-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 689 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903171083 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI
ADIDAS | 0903171134-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 222 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903171134 KS3009 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903173165-1 KE9633 | BLACK | 105D | S2650MTR810B | 243 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (02/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 02-Aug, ETD ?? Waiting fabric. T2 Sue's, PI Date 28-Jul, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903173165 KE9633 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHES 2in1 SHO BLACK |  | SS27-TI
ADIDAS | 0903173400-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903173400 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903173426-1 LG9669 | BLACK | 120D | S2754WAS514C | 276 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903173426 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903173490-1 LG9669 | BLACK | 120D | S2754WAS514C | 161 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903173490 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903174404-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 400 | 31/10/2026 |  | AN | AN26/06/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 21-Jul, ETD ?? T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903174404 LG9660 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903176816-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 314 | 23/10/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176816 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903194096-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 249 | 31/10/2026 | 249 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194096 LC6790 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 18/11/2026 |  |  | 249 |  | 249 |  |  | 46337 | 14/11/2026 |  |  | 249 |  | 249 |  |  | 46214 | 46337 |  |  | 249 |  | 249
ADIDAS | 0903194098-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 317 | 31/10/2026 | 317 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194098 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 18/11/2026 |  |  | 317 |  | 317 |  |  | 46337 | 14/11/2026 |  |  | 317 |  | 317 |  |  | 46214 | 46337 |  |  | 317 |  | 317
ADIDAS | 0903194100-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194100 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194102-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194102 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194104-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 314 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194104 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194106-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 415 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194106 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194107-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1210 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194107 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194109-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194109 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194111-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 320 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194111 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194112-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 329 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194112 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194115-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 900 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903194115 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194119-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1516 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194119 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903194120-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 399 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516277 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194120 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194122-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 660 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194122 LF9775 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX
ADIDAS | 0903194123-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1198 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903194123 KY9391 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194125-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 100 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194125 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194126-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 289 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194126 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194127-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 221 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194127 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194129-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1331 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903194129 KY9391 | 28/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194130-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 107 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194130 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194131-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 616 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516439 | PAD+HT SUB PROCESS_V3 | 0903194131 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194134-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1011 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194134 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903194137-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1214 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194137 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194139-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1080 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194139 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194143-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 262 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194143 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194145-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 133 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194145 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194293-1 IN1156 | BLACK | 90D | S2408MR1600 | 532 | 31/10/2026 | 532 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194293 IN1156 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 532 |  | 532 |  |  | 23/10/2026 | 24/10/2026 |  |  | 532 |  | 532 |  |  | 22/10/2026 | 23/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903194295-1 IN1157 | WHITE | 90D | S2408MR1600 | 328 | 31/10/2026 | 328 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194295 IN1157 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 328 |  | 328 |  |  | 24/10/2026 | 26/10/2026 |  |  | 328 |  | 328 |  |  | 23/10/2026 | 24/10/2026 |  |  | 328 |  | 328
ADIDAS | 0903194296-1 IN1172 | BLACK | 90D | S2408WR1600 | 645 | 31/10/2026 | 645 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194296 IN1172 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 645 |  | 645 |  |  | 21/10/2026 | 22/10/2026 |  |  | 645 |  | 645 |  |  | 20/10/2026 | 21/10/2026 |  |  | 645 |  | 645
ADIDAS | 0903194298-1 IN1173 | WHITE | 90D | S2408WR1600 | 356 | 31/10/2026 | 356 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194298 IN1173 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46366 | ADIZERO E TEE |  | SS27-YTI | 46366 | 46366 |  |  | 356 |  | 356 |  |  | 46275 | 46275 |  |  | 356 |  | 356 |  |  | 46244 | 46244 |  |  | 356 |  | 356
ADIDAS | 0903194299-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 116 | 31/10/2026 | 116 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194299 IT1828 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46092 | ADIZERO E TEE |  | SS27-YTI | 46092 | 46092 |  |  | 116 |  | 116 |  |  | 31/10/2026 | 31/10/2026 |  |  | 116 |  | 116 |  |  | 30/10/2026 | 30/10/2026 |  |  | 116 |  | 116
ADIDAS | 0903194300-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 31/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194300 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 120 |  | 120 |  |  | 24/10/2026 | 26/10/2026 |  |  | 120 |  | 120 |  |  | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194302-1 IN1173 | WHITE | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194302 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 46305 | ADIZERO E TEE |  | SS27-YTI | 46305 | 46366 |  |  | 120 |  | 120 |  |  | 46244 | 46275 |  |  | 120 |  | 120 |  |  | 46213 | 46244 |  |  | 120 |  | 120
ADIDAS | 0903194303-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194303 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 324 |  | 324 |  |  | 23/10/2026 | 24/10/2026 |  |  | 324 |  | 324 |  |  | 22/10/2026 | 23/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903194320-1 KG8547 | ONIX | 90D | S2408WR1600 | 224 | 30/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194320 KG8547 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194322-1 KT4840 | ONIX | 90D | S2408MR1600 | 212 | 30/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194322 KT4840 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194332-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903194332 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194334-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/10/2026 | 200 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903194334 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 22/10/2026 |  |  | 200 |  | 200 |  |  | 20/10/2026 | 21/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903194337-1 IN8707 | BLACK | 90D | S2408WR1601A | 1643 | 23/10/2026 | 1643 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 823016 | HT SUB PROCESS_V1 | 0903194337 IN8707 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 26/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 26/10/2026 | 29/10/2026 |  |  | 1643 |  | 1643 |  |  | 23/10/2026 | 27/10/2026 |  |  | 1643 |  | 1643 |  |  | 22/10/2026 | 26/10/2026 |  |  | 1643 |  | 1643
ADIDAS | 0903194338-1 IN1156 | BLACK | 90D | S2408MR1600 | 697 | 23/10/2026 | 697 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194338 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 697 |  | 697 |  |  | 13/10/2026 | 14/10/2026 |  |  | 697 |  | 697 |  |  | 46366 | 13/10/2026 |  |  | 697 |  | 697
ADIDAS | 0903194339-1 KA0235 | BLACK | 90D | S2608WR0901 | 229 | 23/10/2026 | 229 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194339 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 46153 | Run Ess Shor W BLACK |  | SS27-TRAX | 46153 | 46184 |  |  | 229 |  | 229 |  |  | 46064 | 46092 |  |  | 229 |  | 229 |  |  | 31/10/2026 | 46064 |  |  | 229 |  | 229
ADIDAS | 0903194342-1 KA0246 | BLACK | 90D | S2608WR0902 | 106 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | PAD+HT SUB PROCESS_V3 | 0903194342 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194343-1 IN1173 | WHITE | 90D | S2408WR1600 | 613 | 23/10/2026 | 613 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194343 IN1173 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 46305 | ADIZERO E TEE |  | SS27-YTI | 46305 | 46366 |  |  | 613 |  | 613 |  |  | 46244 | 46275 |  |  | 613 |  | 613 |  |  | 46213 | 46244 |  |  | 613 |  | 613
ADIDAS | 0903194344-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 568 | 23/10/2026 | 568 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 804028 | PAD+HT SUB PROCESS_V3 | 0903194344 KA0238 | 14/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 46123 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 46123 | 46153 |  |  | 568 |  | 568 |  |  | 31/10/2026 | 46064 |  |  | 568 |  | 568 |  |  | 30/10/2026 | 31/10/2026 |  |  | 568 |  | 568
ADIDAS | 0903194347-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 112 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 838103 | PAD+HT SUB PROCESS_V3 | 0903194347 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194348-1 KT4840 | ONIX | 90D | S2408MR1600 | 243 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194348 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194349-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194349 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 500 |  | 500 |  |  | 22/10/2026 | 24/10/2026 |  |  | 500 |  | 500 |  |  | 21/10/2026 | 23/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903194350-1 KG8547 | ONIX | 90D | S2408WR1600 | 365 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194350 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194351-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194351 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 500 |  | 500 |  |  | 22/10/2026 | 24/10/2026 |  |  | 500 |  | 500 |  |  | 21/10/2026 | 23/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903194353-1 KG8547 | ONIX | 90D | S2408WR1600 | 308 | 46214 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194353 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194354-1 KA0235 | BLACK | 90D | S2608WR0901 | 518 | 23/10/2026 | 518 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194354 KA0235 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 46153 | Run Ess Shor W BLACK |  | SS27-TRAX | 46153 | 46184 |  |  | 518 |  | 518 |  |  | 46064 | 46092 |  |  | 518 |  | 518 |  |  | 31/10/2026 | 46064 |  |  | 518 |  | 518
ADIDAS | 0903194355-1 KG8547 | ONIX | 90D | S2408WR1600 | 235 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194355 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194356-1 KG8549 | ONIX | 90D | S2408WR1601A | 264 | 31/10/2026 | 264 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903194356 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 46064 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 46064 | 46092 |  |  | 264 |  | 264 |  |  | 30/10/2026 | 31/10/2026 |  |  | 264 |  | 264 |  |  | 29/10/2026 | 30/10/2026 |  |  | 264 |  | 264
ADIDAS | 0903194358-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194358 KX9851 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46064 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46064 | 46092 |  |  | 102 |  | 102 |  |  | 30/10/2026 | 31/10/2026 |  |  | 102 |  | 102 |  |  | 29/10/2026 | 30/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903194359-1 KT4840 | ONIX | 90D | S2408MR1600 | 414 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194359 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194360-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 104 | 31/10/2026 | 104 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194360 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46123 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 46123 | 46214 |  |  | 104 |  | 104 |  |  | 46064 | 46153 |  |  | 104 |  | 104 |  |  | 31/10/2026 | 46123 |  |  | 104 |  | 104
ADIDAS | 0903194363-1 KA0246 | BLACK | 90D | S2608WR0902 | 228 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650034 | PAD+HT SUB PROCESS_V3 | 0903194363 KA0246 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194365-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 394 | 31/10/2026 | 394 | SA | SA30/06/2026 | G1I | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903194365 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 394 |  | 394 |  |  | 46306 | 46367 |  |  | 394 |  | 394 |  |  | 46276 | 46337 |  |  | 394 |  | 394
ADIDAS | 0903194367-1 KA0235 | BLACK | 90D | S2608WR0901 | 459 | 31/10/2026 | 459 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194367 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46337 | Run Ess Shor W BLACK |  | SS27-TRAX | 46337 | 46367 |  |  | 459 |  | 459 |  |  | 46214 | 46276 |  |  | 459 |  | 459 |  |  | 46184 | 46214 |  |  | 459 |  | 459
ADIDAS | 0903194370-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 543 | 31/10/2026 | 543 | SA | SA30/06/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194370 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46184 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 46184 | 46214 |  |  | 543 |  | 543 |  |  | 46092 | 46123 |  |  | 543 |  | 543 |  |  | 46064 | 46092 |  |  | 543 |  | 543
ADIDAS | 0903194372-1 KA0235 | BLACK | 90D | S2608WR0901 | 434 | 31/10/2026 | 434 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194372 KA0235 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46337 | Run Ess Shor W BLACK |  | SS27-TRAX | 46337 | 46367 |  |  | 434 |  | 434 |  |  | 46214 | 46276 |  |  | 434 |  | 434 |  |  | 46184 | 46214 |  |  | 434 |  | 434
ADIDAS | 0903194375-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 348 | 31/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903194375 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 46184 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 46184 | 46306 |  |  | 348 |  | 348 |  |  | 46092 | 46184 |  |  | 348 |  | 348 |  |  | 46064 | 46153 |  |  | 348 |  | 348
ADIDAS | 0903194378-1 KG8549 | ONIX | 90D | S2408WR1601A | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903194378 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 46064 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 46064 | 46092 |  |  | 120 |  | 120 |  |  | 30/10/2026 | 31/10/2026 |  |  | 120 |  | 120 |  |  | 29/10/2026 | 30/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194380-1 KA0246 | BLACK | 90D | S2608WR0902 | 564 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650036 | PAD+HT SUB PROCESS_V3 | 0903194380 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194383-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 452 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903194383 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194384-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 450 | 31/10/2026 | 450 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194384 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46184 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 46184 | 46306 |  |  | 450 |  | 450 |  |  | 46092 | 46184 |  |  | 450 |  | 450 |  |  | 46064 | 46153 |  |  | 450 |  | 450
ADIDAS | 0903194387-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 330 | 31/10/2026 | 330 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903194387 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 46064 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46064 | 46092 |  |  | 330 |  | 330 |  |  | 30/10/2026 | 31/10/2026 |  |  | 330 |  | 330 |  |  | 29/10/2026 | 30/10/2026 |  |  | 330 |  | 330
ADIDAS | 0903194391-1 IN8707 | BLACK | 90D | S2408WR1601A | 201 | 31/10/2026 | 201 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194391 IN8707 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 29/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 201 |  | 201 |  |  | 27/10/2026 | 28/10/2026 |  |  | 201 |  | 201 |  |  | 26/10/2026 | 27/10/2026 |  |  | 201 |  | 201
ADIDAS | 0903194394-1 KG8549 | ONIX | 90D | S2408WR1601A | 144 | 31/10/2026 | 144 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194394 KG8549 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46064 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 46064 | 46092 |  |  | 144 |  | 144 |  |  | 30/10/2026 | 31/10/2026 |  |  | 144 |  | 144 |  |  | 29/10/2026 | 30/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903194397-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 319 | 31/10/2026 | 319 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194397 LD0292 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46184 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 46184 | 46306 |  |  | 319 |  | 319 |  |  | 46092 | 46184 |  |  | 319 |  | 319 |  |  | 46064 | 46153 |  |  | 319 |  | 319
ADIDAS | 0903194400-1 KA0246 | BLACK | 90D | S2608WR0902 | 591 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903194400 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194402-1 KA0235 | BLACK | 90D | S2608WR0901 | 807 | 31/10/2026 | 807 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194402 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 46367 | Run Ess Shor W BLACK |  | SS27-TRAX | 46367 | 14/11/2026 |  |  | 807 |  | 807 |  |  | 46276 | 46337 |  |  | 807 |  | 807 |  |  | 46214 | 46306 |  |  | 807 |  | 807
ADIDAS | 0903194405-1 KA4331 | BLACK | 90D | S2608MR0902 | 628 | 31/10/2026 | 628 | SA | SA30/06/2026 | G1G | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194405 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 628 |  | 628 |  |  | 26/10/2026 | 28/10/2026 |  |  | 628 |  | 628 |  |  | 24/10/2026 | 27/10/2026 |  |  | 628 |  | 628
ADIDAS | 0903194447-1 KA6229 | BLACK | 120D | S2608WR0202 | 1079 | 31/10/2026 | 1079 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194447 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 46214 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 46214 | 46367 |  |  | 1079 |  | 1079 |  |  | 46123 | 46276 |  |  | 1079 |  | 1079 |  |  | 31/10/2026 | 46153 |  |  | 1079 |  | 1079
ADIDAS | 0903194450-1 KA6229 | BLACK | 120D | S2608WR0202 | 354 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194450 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903194453-1 KA6229 | BLACK | 120D | S2608WR0202 | 516 | 23/10/2026 | 516 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194453 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 516 |  | 516 |  |  | 23/10/2026 | 26/10/2026 |  |  | 516 |  | 516 |  |  | 20/10/2026 | 22/10/2026 |  |  | 516 |  | 516
ADIDAS | 0903194462-1 KA6229 | BLACK | 120D | S2608WR0202 | 150 | 23/10/2026 | 150 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194462 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 150 |  | 150 |  |  | 23/10/2026 | 26/10/2026 |  |  | 150 |  | 150 |  |  | 20/10/2026 | 22/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903194468-1 KA6229 | BLACK | 120D | S2608WR0202 | 880 | 31/10/2026 | 880 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194468 KA6229 | 28/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 46092 |  |  | 880 |  | 880 |  |  | 26/10/2026 | 30/10/2026 |  |  | 880 |  | 880 |  |  | 22/10/2026 | 27/10/2026 |  |  | 880 |  | 880
ADIDAS | 0903194501-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194501 KA6229 | 28/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 46092 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 27/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903195079-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 177 | 46214 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195079 LF0718 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903195509-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 221 | 46214 |  | SA | SA30/06/2026 |  | JACKET |  | (23/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 23-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195509 LG9664 | 28/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903196029-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 46214 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903196029 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903196038-1 IN1172 | BLACK | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196038 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 138 |  | 138 |  |  | 19/10/2026 | 20/10/2026 |  |  | 138 |  | 138 |  |  | 17/10/2026 | 19/10/2026 |  |  | 138 |  | 138
ADIDAS | 0903196039-1 IN1173 | WHITE | 90D | S2408WR1600 | 142 | 31/10/2026 | 142 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196039 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 46366 | ADIZERO E TEE |  | SS27-YTI | 46366 | 46366 |  |  | 142 |  | 142 |  |  | 46275 | 46275 |  |  | 142 |  | 142 |  |  | 46244 | 46244 |  |  | 142 |  | 142
ADIDAS | 0903196040-1 IN1156 | BLACK | 90D | S2408MR1600 | 496 | 31/10/2026 | 496 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196040 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 496 |  | 496 |  |  | 24/10/2026 | 26/10/2026 |  |  | 496 |  | 496 |  |  | 23/10/2026 | 24/10/2026 |  |  | 496 |  | 496
ADIDAS | 0903197147-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 652 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903197147 KY9391 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197391-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197391 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197393-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 148 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 839055 | PAD+HT SUB PROCESS_V3 | 0903197393 LD0908 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197395-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197395 LD0278 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903197397-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197397 LD0293 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197399-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 190 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197399 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197401-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 305 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197401 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197403-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 380 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 838103 | PAD+HT SUB PROCESS_V3 | 0903197403 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197405-1 KG8549 | ONIX | 90D | S2408WR1601A | 181 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197405 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197406-1 KT4839 | ONIX | 90D | S2408MR1601 | 188 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 830009 | HT SUB PROCESS_V1 | 0903197406 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197408-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 8 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 1st Art (TC 10 pcs) 650010 | HT SUB PROCESS_V1 | 0903197408 IT1467 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903197410-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903197410 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903197411-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 102 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903197411 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197413-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 182 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197413 KX9851 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197415-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 116 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197415 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197416-1 KG8549 | ONIX | 90D | S2408WR1601A | 282 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197416 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197418-1 KG8549 | ONIX | 90D | S2408WR1601A | 254 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197418 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197420-1 KT4839 | ONIX | 90D | S2408MR1601 | 233 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197420 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197422-1 KT4839 | ONIX | 90D | S2408MR1601 | 134 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197422 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197423-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 514 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197423 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903197470-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 708 | 30/11/2026 | 708 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903197470 LD0293 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 19/11/2026 | 23/11/2026 |  |  | 708 |  | 708 |  |  | 16/11/2026 | 19/11/2026 |  |  | 708 |  | 708 |  |  | 14/11/2026 | 18/11/2026 |  |  | 708 |  | 708
ADIDAS | 0903197493-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 676 | 30/11/2026 | 676 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197493 LD0293 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 19/11/2026 | 23/11/2026 |  |  | 676 |  | 676 |  |  | 16/11/2026 | 19/11/2026 |  |  | 676 |  | 676 |  |  | 14/11/2026 | 18/11/2026 |  |  | 676 |  | 676
ADIDAS | 0903197745-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 1860 | 31/10/2026 | 1860 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197745 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46123 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 46123 | 46306 |  |  | 1860 |  | 1860 |  |  | 31/10/2026 | 46184 |  |  | 1860 |  | 1860 |  |  | 28/10/2026 | 46092 |  |  | 1860 |  | 1860
ADIDAS | 0903197746-1 JZ7711 | BLACK | 120D | S2608MR0202 | 3000 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197746 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197755-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 749 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197755 KY9391 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197773-1 KE9656 | BLACK | 105D | S2608WR0201A | 7617 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903197773 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903197777-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 2329 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197777 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197780-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 964 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197780 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197782-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1337 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197782 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197785-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1015 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197785 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197791-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 303 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197791 LF9775 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX
ADIDAS | 0903197795-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 197 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903197795 KY9393 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197798-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 527 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197798 KY9391 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197802-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 321 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197802 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197807-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 341 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197807 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197811-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 249 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197811 KY9391 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197815-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 390 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197815 KY9393 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197818-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1039 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516267 | PAD+HT SUB PROCESS_V3 | 0903197818 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197829-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 445 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197829 KY9385 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903197832-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 367 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197832 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903197837-1 JZ7711 | BLACK | 120D | S2608MR0202 | 379 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197837 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197840-1 JZ7711 | BLACK | 120D | S2608MR0202 | 615 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197840 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197843-1 JZ7711 | BLACK | 120D | S2608MR0202 | 622 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197843 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197845-1 JZ7711 | BLACK | 120D | S2608MR0202 | 322 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197845 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197849-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197849 KY9384 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903197853-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1291 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197853 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197856-1 JZ7711 | BLACK | 120D | S2608MR0202 | 330 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197856 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197859-1 JZ7711 | BLACK | 120D | S2608MR0202 | 601 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197859 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197863-1 JZ7711 | BLACK | 120D | S2608MR0202 | 366 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197863 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197870-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197870 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903197872-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 695 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197872 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903197875-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516403 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197875 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46092 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 46092 | 46123 |  |  | 300 |  | 300 |  |  | 30/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197879-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 408 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197879 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197882-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 304 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 10-Aug. Waiting fabric. T2 Best Pacific, PI Date 09-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903197882 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197886-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1556 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197886 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197889-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 816 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197889 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903201074-1 JZ7711 | BLACK | 120D | S2608MR0202 | 211 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201074 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903201075-1 JZ7711 | BLACK | 120D | S2608MR0202 | 102 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201075 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903203165-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 251 | 31/10/2026 |  | SI | SI29/05/2026 |  | SHORTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903203165 LF0725 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903203174-1 KB5960 | WHITE | 120D | S2608MR0900A | 108 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903203174 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903208399-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 80 | 31/10/2026 | 80 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208399 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 29/10/2026 |  |  | 80 |  | 80 |  |  | 27/10/2026 | 27/10/2026 |  |  | 80 |  | 80 |  |  | 26/10/2026 | 26/10/2026 |  |  | 80 |  | 80
ADIDAS | 0903208400-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1268 | 31/10/2026 | 1268 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208400 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 1268 |  | 1268 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1268 |  | 1268 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903208401-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 100 | 23/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903208401 KX9855 | 17/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208402-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 168 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903208402 KX9855 | 17/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208403-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 182 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903208403 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208404-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 102 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208404 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208405-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 170 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208405 KX9855 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208415-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 138 | 31/10/2026 | 138 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650031 | HT SUB PROCESS_V1 | 0903208415 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 138 |  | 138 |  |  | 46064 | 46092 |  |  | 138 |  | 138 |  |  | 31/10/2026 | 46064 |  |  | 138 |  | 138
ADIDAS | 0903208416-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 143 | 31/10/2026 | 143 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Airowes). T2 Y.T.I, body & mesh actual receives 12-Aug. 650034 | HT SUB PROCESS_V1 | 0903208416 IT1469 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 143 |  | 143 |  |  | 46064 | 46092 |  |  | 143 |  | 143 |  |  | 31/10/2026 | 46064 |  |  | 143 |  | 143
ADIDAS | 0903208436-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 102 | 31/10/2026 | 102 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208436 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 102 |  | 102 |  |  | 46064 | 46092 |  |  | 102 |  | 102 |  |  | 31/10/2026 | 46064 |  |  | 102 |  | 102
ADIDAS | 0903208437-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 163 | 31/10/2026 | 163 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208437 KG8548 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 163 |  | 163 |  |  | 46064 | 46092 |  |  | 163 |  | 163 |  |  | 31/10/2026 | 46064 |  |  | 163 |  | 163
ADIDAS | 0903208438-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 252 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903208438 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903208439-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 474 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903208439 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903208444-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 102 | 31/10/2026 | 102 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208444 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 31/10/2026 |  |  | 102 |  | 102 |  |  | 29/10/2026 | 29/10/2026 |  |  | 102 |  | 102 |  |  | 28/10/2026 | 28/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903208445-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 136 | 31/10/2026 | 136 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208445 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 31/10/2026 |  |  | 136 |  | 136 |  |  | 29/10/2026 | 29/10/2026 |  |  | 136 |  | 136 |  |  | 28/10/2026 | 28/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903209752-1 IN1156 | BLACK | 90D | S2408MR1600 | 1969 | 31/10/2026 | 1969 | SA | SA07/07/2026 | G1O | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209752 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 13/11/2026 | ADIZERO E TEE |  | SS27-YTI | 13/11/2026 | 17/11/2026 |  |  | 1969 |  | 1969 |  |  | 46337 | 14/11/2026 |  |  | 1969 |  | 1969 |  |  | 46306 | 13/11/2026 |  |  | 1969 |  | 1969
ADIDAS | 0903209753-1 IN1156 | BLACK | 90D | S2408MR1600 | 640 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 512107 | HT SUB PROCESS_V1 | 0903209753 IN1156 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209759-1 IN1157 | WHITE | 90D | S2408MR1600 | 253 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Y.T.I, Mesh: ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209759 IN1157 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209770-1 IN1172 | BLACK | 90D | S2408WR1600 | 400 | 23/10/2026 | 400 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | 516205 | HT SUB PROCESS_V1 | 0903209770 IN1172 |  | KAHATEX CIJERAH | SPAIN | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 20/10/2026 |  |  | 400 |  | 400 |  |  | 17/10/2026 | 17/10/2026 |  |  | 400 |  | 400 |  |  | 16/10/2026 | 16/10/2026 |  |  | 400 |  | 400
ADIDAS | 0903209771-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209771 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209776-1 KG8547 | ONIX | 90D | S2408WR1600 | 234 | 30/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 680014 | HT SUB PROCESS_V1 | 0903209776 KG8547 |  | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209777-1 KG8547 | ONIX | 90D | S2408WR1600 | 319 | 31/10/2026 | 319 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Airowes). 650034 | HT SUB PROCESS_V1 | 0903209777 KG8547 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 319 |  | 319 |  |  | 24/10/2026 | 26/10/2026 |  |  | 319 |  | 319 |  |  | 23/10/2026 | 24/10/2026 |  |  | 319 |  | 319
ADIDAS | 0903209778-1 KG8547 | ONIX | 90D | S2408WR1600 | 150 | 31/10/2026 | 150 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650031 | HT SUB PROCESS_V1 | 0903209778 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 150 |  | 150 |  |  | 24/10/2026 | 26/10/2026 |  |  | 150 |  | 150 |  |  | 23/10/2026 | 24/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903209779-1 KG8547 | ONIX | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Cargoport). 650036 | HT SUB PROCESS_V1 | 0903209779 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 120 |  | 120 |  |  | 24/10/2026 | 26/10/2026 |  |  | 120 |  | 120 |  |  | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903209790-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 397 | 31/10/2026 | 397 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209790 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 46092 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46092 | 46092 |  |  | 397 |  | 397 |  |  | 31/10/2026 | 31/10/2026 |  |  | 397 |  | 397 |  |  | 30/10/2026 | 30/10/2026 |  |  | 397 |  | 397
ADIDAS | 0903209791-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 840 | 31/10/2026 | 840 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903209791 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 46123 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46123 | 46153 |  |  | 840 |  | 840 |  |  | 46064 | 46092 |  |  | 840 |  | 840 |  |  | 31/10/2026 | 46064 |  |  | 840 |  | 840
ADIDAS | 0903209792-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 114 | 31/10/2026 | 114 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903209792 KX9838 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 46092 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46092 | 46092 |  |  | 114 |  | 114 |  |  | 31/10/2026 | 31/10/2026 |  |  | 114 |  | 114 |  |  | 30/10/2026 | 30/10/2026 |  |  | 114 |  | 114
ADIDAS | 0903209793-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 120 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209793 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209794-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 418 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209794 KX9838 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209795-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903209795 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209796-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 234 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903209796 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209797-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 342 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903209797 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209807-1 IN1173 | WHITE | 90D | S2408WR1600 | 427 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209807 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209906-1 IN1172 | BLACK | 90D | S2408WR1600 | 321 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903209906 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209908-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 511 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903209908 KZ2984 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209909-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 341 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209909 KG8548 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903245372-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903245372 IN8707 | 46244 | KAHATEX CIJERAH | CHILE | SEA | 29/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 28/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903245450-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 300 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 680015 | HT+PAD SUB PROCESS_V3 | 0903245450 KB5961 | 46244 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245476-1 KB5965 | BLACK | 120D | S2608MR0900A | 800 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245476 KB5965 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245499-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903245499 KA4331 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903245532-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 600 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245532 KB5959 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903248036-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 12 | 31/10/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903248036 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903248063-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 36 | 30/10/2026 | 36 | AN | AN10/07/2026 | G2R | SHORTS | G2 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Kahatex, PI Date 22-Sep. Waiting fabrIc. T2 Formosa, PI Date 12-Sep. T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248063 LG9660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 36 |  | 36 |  |  | 46275 | 46275 |  |  | 36 |  | 36
ADIDAS | 0903248603-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1020 | 23/10/2026 | 1020 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248603 JN1948 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/10/2026 | W 3S FT QZ HD |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 1020 |  | 1020 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1020 |  | 1020
ADIDAS | 0903248633-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 256 | 23/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903248633 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903248693-1 LG9666 | BLACK | 120D | S2754WAS512C | 560 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? s516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903248693 LG9666 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903248718-1 LG9675 | BLACK | 120D | S2754WAS513C | 371 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903248718 LG9675 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903248892-1 KG3189 | MAROON | 120D | S2608MR0900A | 699 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248892 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903248948-1 KG3189 | MAROON | 120D | S2608MR0900A | 453 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248948 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903249024-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 383 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249024 KC9082 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249045-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 337 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249045 KC9082 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249143-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903249143 KX3655 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903249918-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 600 | 31/10/2026 | 600 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249918 KA0237 | 46244 | KAHATEX CIJERAH | CHILE | SEA | 13/11/2026 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 600 |  | 600 |  |  | 46306 | 46367 |  |  | 600 |  | 600 |  |  | 46276 | 46337 |  |  | 600 |  | 600
ADIDAS | 0903249936-1 IN2961 | BLACK | 105D | S2408WR2400 | 460 | 31/10/2026 | 460 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249936 IN2961 | 46244 | KAHATEX CIJERAH | COLOMBIA | SEA | 46306 | OTR B TEE BLACK |  | SS27 | 46306 | 46337 |  |  | 460 |  | 460 |  |  | 46214 | 46276 |  |  | 460 |  | 460 |  |  | 46184 | 46214 |  |  | 460 |  | 460
ADIDAS | 0903249960-1 IK7442 | WHITE | 105D | S2408WR2400 | 476 | 31/10/2026 | 476 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249960 IK7442 | 46244 | KAHATEX CIJERAH | COLOMBIA | SEA | 46092 | OTR B TEE WHITE |  | SS27 | 46092 | 46092 |  |  | 476 |  | 476 |  |  | 31/10/2026 | 31/10/2026 |  |  | 476 |  | 476 |  |  | 30/10/2026 | 30/10/2026 |  |  | 476 |  | 476
ADIDAS | 0903249983-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 679 | 31/10/2026 | 679 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249983 LD0277 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 46306 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46306 | 46337 |  |  | 679 |  | 679 |  |  | 46184 | 46214 |  |  | 679 |  | 679 |  |  | 46153 | 46184 |  |  | 679 |  | 679
ADIDAS | 0903250431-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 157 | 31/10/2026 | 157 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903250431 KU7520 | 46244 | KAHATEX CIJERAH | ITALY | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 157 |  | 157 |  |  | 31/10/2026 | 46064 |  |  | 157 |  | 157 |  |  | 30/10/2026 | 31/10/2026 |  |  | 157 |  | 157
ADIDAS | 0903250451-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 503 | 31/10/2026 | 503 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516342 | HT SUB PROCESS_V1 | 0903250451 KU7520 | 46244 | KAHATEX CIJERAH | GERMANY | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 503 |  | 503 |  |  | 31/10/2026 | 46064 |  |  | 503 |  | 503 |  |  | 30/10/2026 | 31/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903250476-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 264 | 16/10/2026 | 264 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L1 SUB PROCESS_V3 | 0903250476 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46152 | MER KA NNTEE M BLACK |  | SS27-MS | 46152 | 46183 |  |  | 264 |  | 264 |  |  | 46032 | 46063 |  |  | 264 |  | 264
ADIDAS | 0903250899-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903250899 LG9665 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903250925-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 322 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903250925 LG9668 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903250948-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 127 | 31/10/2026 | 127 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903250948 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46092 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46092 | 46092 |  |  | 127 |  | 127 |  |  | 31/10/2026 | 31/10/2026 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 30/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903250999-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903250999 LE4307 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 46276 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 46276 | 46337 |  |  | 100 |  | 100 |  |  | 46153 | 46214 |  |  | 100 |  | 100
ADIDAS | 0903251000-1 KG3189 | MAROON | 120D | S2608MR0900A | 123 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251000 KG3189 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251073-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 1204 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848012 | HT+PAD SUB PROCESS_V3 | 0903251073 KB5961 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903251098-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 277 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877).. 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251098 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903251123-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 311 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251123 LE8188 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903251133-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1072 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251133 KX3655 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903251145-1 KA0246 | BLACK | 105D | S2608WR0902 | 132 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 848016 | PAD+HT SUB PROCESS_V3 | 0903251145 KA0246 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251161-1 KA0246 | BLACK | 105D | S2608WR0902 | 600 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 684009 | PAD+HT SUB PROCESS_V3 | 0903251161 KA0246 | 46244 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251312-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 230 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903251312 KD0738 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903251430-1 KA0246 | BLACK | 105D | S2608WR0902 | 309 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903251430 KA0246 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251454-1 KA0246 | BLACK | 105D | S2608WR0902 | 322 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903251454 KA0246 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251481-1 KA0246 | BLACK | 105D | S2608WR0902 | 636 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251481 KA0246 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251511-1 KA0246 | BLACK | 105D | S2608WR0902 | 1186 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251511 KA0246 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251540-1 KA0246 | BLACK | 105D | S2608WR0902 | 491 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251540 KA0246 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251558-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 321 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903251558 LD0908 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251577-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 298 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903251577 LD0908 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251605-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 200 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251605 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251656-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 148 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903251656 KX0123 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903251702-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251702 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251716-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 848 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 960006 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903251716 KA4914 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903251816-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 800 | 23/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251816 KC5231 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903251866-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1760 | 23/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903251866 KD4872 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903251870-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 118 | 31/10/2026 | 118 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251870 KV8005 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 46153 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 46153 | 46214 |  |  | 118 |  | 118 |  |  | 46064 | 46123 |  |  | 118 |  | 118
ADIDAS | 0903251884-1 LF0723 | BLACK | 105D | S2754MAS511B | 297 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251884 LF0723 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903251890-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 144 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251890 LG9665 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903251904-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251904 LG9666 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903251930-1 KG3189 | MAROON | 120D | S2608MR0900A | 1103 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903251930 KG3189 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251931-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 124 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251931 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251936-1 KT4839 | ONIX | 90D | S2408MR1601 | 566 | 31/10/2026 | 566 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903251936 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 566 |  | 566 |  |  | 27/10/2026 | 29/10/2026 |  |  | 566 |  | 566 |  |  | 26/10/2026 | 28/10/2026 |  |  | 566 |  | 566
ADIDAS | 0903251993-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 187 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251993 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903252016-1 IS1413 | BLACK | 60D | S2425M405 | 1810 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252016 IS1413 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252017-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 265 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848024 | HT+PAD SUB PROCESS_V3 | 0903252017 KB5961 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252038-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1900 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252038 IU0217 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252040-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 324 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903252040 IN0088 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903252045-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 229 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 547012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903252045 KY5988 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903252073-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 928 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252073 JE0052 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252080-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252080 LG9661 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903252095-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1760 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252095 JD5302 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903252110-1 LF0727 | BLACK | 120D | S2754MAS510B | 116 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252110 LF0727 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903252125-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1028 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903252125 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903252133-1 LG9666 | BLACK | 120D | S2754WAS512C | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252133 LG9666 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903252138-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 141 | 31/10/2026 | 141 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252138 KA0237 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA | 13/11/2026 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 141 |  | 141 |  |  | 46306 | 46367 |  |  | 141 |  | 141 |  |  | 46276 | 46337 |  |  | 141 |  | 141
ADIDAS | 0903252145-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1020 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252145 JE0055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252154-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 468 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252154 IN0088 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903252275-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 126 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252275 KY9383 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903252505-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848012 | HT+PAD SUB PROCESS_V3 | 0903252505 KB5961 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252541-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252541 KD3854 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903252572-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 272 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903252572 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903252595-1 IN1172 | BLACK | 90D | S2408WR1600 | 264 | 31/10/2026 | 264 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903252595 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 264 |  | 264 |  |  | 19/10/2026 | 20/10/2026 |  |  | 264 |  | 264 |  |  | 17/10/2026 | 19/10/2026 |  |  | 264 |  | 264
ADIDAS | 0903252598-1 KG8547 | ONIX | 90D | S2408WR1600 | 118 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903252598 KG8547 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903252620-1 IN1157 | WHITE | 90D | S2408MR1600 | 1027 | 31/10/2026 | 1027 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903252620 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 1027 |  | 1027 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1027 |  | 1027 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1027 |  | 1027
ADIDAS | 0903252991-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 120 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903252991 KY5900 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253066-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 542 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 814006 | PAD+HT SUB PROCESS_V3 | 0903253066 LD0908 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903253138-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 381 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903253138 KY5900 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253152-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 130 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903253152 LH3760 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253168-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 129 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903253168 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253200-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 267 | 31/10/2026 | 267 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903253200 LD0278 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 46184 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 46184 | 46214 |  |  | 267 |  | 267 |  |  | 46092 | 46123 |  |  | 267 |  | 267 |  |  | 46064 | 46092 |  |  | 267 |  | 267
ADIDAS | 0903253208-1 KD3875 | BLACK | 120D | S2608WR0201 | 108 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903253208 KD3875 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903253221-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253221 LE8188 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253302-1 KT4840 | ONIX | 90D | S2408MR1600 | 181 | 31/10/2026 | 181 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253302 KT4840 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 181 |  | 181 |  |  | 26/10/2026 | 27/10/2026 |  |  | 181 |  | 181 |  |  | 24/10/2026 | 26/10/2026 |  |  | 181 |  | 181
ADIDAS | 0903253313-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 406 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253313 KC5231 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903253357-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 160 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253357 LF0729 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903253378-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 140 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903253378 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903253434-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 600 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903253434 IN0088 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903253436-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 490 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253436 JE6338 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903253467-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253467 LG9663 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903253468-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 331 | 23/10/2026 | 331 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512106 | PRINT L2+PAD SUB PROCESS_V3 | 0903253468 LC8884 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 16/10/2026 | M RESORT T BLACK |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 331 |  | 331 |  |  | 13/10/2026 | 13/10/2026 | 26/08/2026 | 27/08/2026 | 331 | 160 | 171
ADIDAS | 0903253478-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 266 | 31/10/2026 | 266 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 516342 | HT SUB PROCESS_V1 | 0903253478 KX9838 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46092 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46092 | 46123 |  |  | 266 |  | 266 |  |  | 31/10/2026 | 46064 |  |  | 266 |  | 266 |  |  | 30/10/2026 | 31/10/2026 |  |  | 266 |  | 266
ADIDAS | 0903253486-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 186 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903253486 KX3655 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253492-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253492 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253500-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 378 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253500 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253511-1 LH3758 | BLACK | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253511 LH3758 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903253522-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 462 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253522 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253530-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 216 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903253530 LI7658 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903253536-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 542 | 31/10/2026 | 542 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903253536 IT1467 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 542 |  | 542 |  |  | 27/10/2026 | 29/10/2026 |  |  | 542 |  | 542 |  |  | 26/10/2026 | 28/10/2026 |  |  | 542 |  | 542
ADIDAS | 0903253561-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 506 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | TRAX (MOQ Issue)-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903253561 LD0909 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903253578-1 IN1157 | WHITE | 90D | S2408MR1600 | 1664 | 31/10/2026 | 1664 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253578 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 46092 |  |  | 1664 |  | 1664 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1664 |  | 1664 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1664 |  | 1664
ADIDAS | 0903253594-1 KG8547 | ONIX | 90D | S2408WR1600 | 194 | 31/10/2026 | 194 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903253594 KG8547 |  | KAHATEX CIJERAH | MOROCCO | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 194 |  | 194 |  |  | 24/10/2026 | 26/10/2026 |  |  | 194 |  | 194 |  |  | 23/10/2026 | 24/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903253608-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT SUB PROCESS_V1 | 0903253608 IT1467 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 102 |  | 102 |  |  | 27/10/2026 | 29/10/2026 |  |  | 102 |  | 102 |  |  | 26/10/2026 | 28/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903253631-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 226 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Easten, PI Date 25-Aug. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253631 JZ7715 | 46244 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903253635-1 IN8707 | BLACK | 105D | S2408WR1601A | 781 | 31/10/2026 | 781 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253635 IN8707 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA | 30/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 30/10/2026 | 46064 |  |  | 781 |  | 781 |  |  | 28/10/2026 | 30/10/2026 |  |  | 781 |  | 781 |  |  | 27/10/2026 | 29/10/2026 |  |  | 781 |  | 781
ADIDAS | 0903253647-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 1 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253647 LK8779 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903253654-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 382 | 23/10/2026 | 382 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253654 LF1392 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 30/10/2026 | 46153 |  |  | 382 |  | 382 |  |  | 27/10/2026 | 46064 |  |  | 382 |  | 382
ADIDAS | 0903253720-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. DRC 0064-T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253720 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253727-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 220 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253727 LE8181 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253750-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 322 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903253750 KX3655 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253760-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 268 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903253760 KX3650 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253780-1 IN1173 | WHITE | 90D | S2408WR1600 | 152 | 31/10/2026 | 152 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903253780 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46366 | ADIZERO E TEE |  | SS27-YTI | 46366 | 46366 |  |  | 152 |  | 152 |  |  | 46275 | 46275 |  |  | 152 |  | 152 |  |  | 46244 | 46244 |  |  | 152 |  | 152
ADIDAS | 0903253801-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903253801 KG8547 |  | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 26/10/2026 | 27/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903253837-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 131 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253837 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253860-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 163 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253860 KY5988 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253892-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 1513 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903253892 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903253913-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 361 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253913 KD3854 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903253915-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 118 | 31/10/2026 | 118 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903253915 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 118 |  | 118 |  |  | 46064 | 46092 |  |  | 118 |  | 118 |  |  | 31/10/2026 | 46064 |  |  | 118 |  | 118
ADIDAS | 0903253948-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253948 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253950-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 190 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903253950 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253973-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 321 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253973 LG9661 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254003-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 425 | 23/10/2026 | 425 | SI | SI10/07/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254003 KV8005 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 30/10/2026 | 46153 |  |  | 425 |  | 425 |  |  | 27/10/2026 | 46064 |  |  | 425 |  | 425
ADIDAS | 0903254007-1 LF0727 | BLACK | 120D | S2754MAS510B | 1051 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254007 LF0727 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254012-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254012 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903254029-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1232 | 23/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254029 JW7178 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903254059-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 109 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903254059 KX3655 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903254074-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254074 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254093-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 290 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254093 KY9385 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254114-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 990 | 23/10/2026 |  | SI | SI10/07/2026 |  | SWEATSHIRT |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254114 KD4874 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903254125-1 IN1156 | BLACK | 90D | S2408MR1600 | 335 | 31/10/2026 | 335 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903254125 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 335 |  | 335 |  |  | 24/10/2026 | 26/10/2026 |  |  | 335 |  | 335 |  |  | 23/10/2026 | 24/10/2026 |  |  | 335 |  | 335
ADIDAS | 0903254135-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254135 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903254152-1 LF0727 | BLACK | 120D | S2754MAS510B | 227 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254152 LF0727 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254162-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 220 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254162 JW7182 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903254182-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903254182 KG3234 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA | 46306 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 46306 | 13/11/2026 |  |  | 100 |  | 100 |  |  | 46184 | 46306 |  |  | 100 |  | 100 |  |  | 46153 | 46276 |  |  | 100 |  | 100
ADIDAS | 0903254188-1 IN1157 | WHITE | 90D | S2408MR1600 | 621 | 31/10/2026 | 621 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254188 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 28/10/2026 |  |  | 621 |  | 621 |  |  | 26/10/2026 | 26/10/2026 |  |  | 621 |  | 621 |  |  | 24/10/2026 | 24/10/2026 |  |  | 621 |  | 621
ADIDAS | 0903254192-1 KT4839 | ONIX | 90D | S2408MR1601 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848024 | HT SUB PROCESS_V1 | 0903254192 KT4839 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 275 |  | 275 |  |  | 26/10/2026 | 27/10/2026 |  |  | 275 |  | 275 |  |  | 24/10/2026 | 26/10/2026 |  |  | 275 |  | 275
ADIDAS | 0903254208-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512108 | HT+PAD SUB PROCESS_V3 | 0903254208 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254210-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 200 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903254210 KD3911 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | RELEASED |  | SS27
ADIDAS | 0903254214-1 IN1156 | BLACK | 90D | S2408MR1600 | 572 | 31/10/2026 | 572 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254214 IN1156 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 572 |  | 572 |  |  | 26/10/2026 | 27/10/2026 |  |  | 572 |  | 572 |  |  | 24/10/2026 | 26/10/2026 |  |  | 572 |  | 572
ADIDAS | 0903254234-1 KG3189 | MAROON | 120D | S2608MR0900A | 130 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | Request Cancel (BTP_19_07_2026 -> Req. PO Cancel & Quantity Change). 512109 | HT+PAD SUB PROCESS_V3 | 0903254234 KG3189 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254241-1 IN1173 | WHITE | 90D | S2408WR1600 | 217 | 31/10/2026 | 217 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848024 | HT SUB PROCESS_V1 | 0903254241 IN1173 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 217 |  | 217 |  |  | 46305 | 46366 |  |  | 217 |  | 217 |  |  | 46275 | 46305 |  |  | 217 |  | 217
ADIDAS | 0903254247-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 31/10/2026 | 512 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254247 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46214 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 46214 | 46276 |  |  | 512 |  | 512 |  |  | 46123 | 46153 |  |  | 512 |  | 512 |  |  | 46092 | 46123 |  |  | 512 |  | 512
ADIDAS | 0903254259-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903254259 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254263-1 IN1156 | BLACK | 90D | S2408MR1600 | 118 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254263 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254266-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512102 | HT SUB PROCESS_V1 | 0903254266 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46064 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46064 | 46092 |  |  | 100 |  | 100 |  |  | 30/10/2026 | 31/10/2026 |  |  | 100 |  | 100 |  |  | 29/10/2026 | 30/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903254271-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254271 IS1413 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254284-1 LH3758 | BLACK | 120D | S2754WAS518B | 125 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903254284 LH3758 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903254294-1 IN1173 | WHITE | 90D | S2408WR1600 | 122 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254294 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254297-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254297 IU0217 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254305-1 KD3875 | BLACK | 120D | S2608WR0201 | 745 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903254305 KD3875 | 46244 | KAHATEX CIJERAH | HONGKONG | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903254314-1 IN1172 | BLACK | 90D | S2408WR1600 | 147 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254314 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254326-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1080 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254326 JZ7709 | 46244 | KAHATEX CIJERAH | HONGKONG | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 0903254327-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 123 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254327 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903254352-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254352 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254359-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 175 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254359 JE0052 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254392-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254392 JD5302 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903254416-1 IN1173 | WHITE | 90D | S2408WR1600 | 270 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254416 IN1173 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254417-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254417 JE0055 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254462-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254462 LG9661 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254473-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254473 KX8875 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903254483-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 78 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254483 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254500-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 68 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254500 LC6339 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903254520-1 IN1156 | BLACK | 90D | S2408MR1600 | 422 | 31/10/2026 | 422 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903254520 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 422 |  | 422 |  |  | 26/10/2026 | 27/10/2026 |  |  | 422 |  | 422 |  |  | 24/10/2026 | 26/10/2026 |  |  | 422 |  | 422
ADIDAS | 0903254528-1 LC6341 | BLACK | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254528 LC6341 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903254540-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 1120 | 30/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903254540 LF5052 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903254634-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 355 | 31/10/2026 | 355 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254634 KY4155 | 46244 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 355 |  | 355 |  |  | 20/10/2026 | 22/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903254654-1 LF0718 | BLACK | 105D | S2754MAS512B | 367 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254654 LF0718 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903254679-1 LF0727 | BLACK | 120D | S2754MAS510B | 557 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254679 LF0727 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254704-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 100 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903254704 LD0908 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903254722-1 LF0723 | BLACK | 105D | S2754MAS511B | 505 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254722 LF0723 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903254734-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254734 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903254737-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 159 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254737 KY9385 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254769-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 271 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | PAD+HT SUB PROCESS_V3 | 0903254769 LD0908 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903254782-1 IN1172 | BLACK | 90D | S2408WR1600 | 915 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254782 IN1172 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254783-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 359 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254783 LG9663 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254804-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 353 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254804 LE8181 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903254813-1 JZ7711 | BLACK | 120D | S2608MR0202 | 169 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254813 JZ7711 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903254815-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 643 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254815 LG9663 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254837-1 LG9666 | BLACK | 120D | S2754WAS512C | 941 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254837 LG9666 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254839-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 116 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903254839 LD0293 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903254841-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 421 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254841 LG9661 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254883-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903254883 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903254895-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 263 | 31/10/2026 | 263 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254895 LD0292 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46306 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 46306 | 46367 |  |  | 263 |  | 263 |  |  | 46184 | 46276 |  |  | 263 |  | 263 |  |  | 46153 | 46214 |  |  | 263 |  | 263
ADIDAS | 0903254897-1 KB5960 | WHITE | 120D | S2608MR0900A | 361 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903254897 KB5960 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903254912-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254912 LF0721 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903254929-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 233 | 31/10/2026 | 233 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903254929 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 233 |  | 233 |  |  | 31/10/2026 | 46064 |  |  | 233 |  | 233 |  |  | 30/10/2026 | 31/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903254954-1 LG9675 | BLACK | 120D | S2754WAS513C | 137 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254954 LG9675 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903254957-1 LG9666 | BLACK | 120D | S2754WAS512C | 428 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254957 LG9666 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254967-1 KT4839 | ONIX | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512108 | HT SUB PROCESS_V1 | 0903254967 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 26/10/2026 | 27/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903254971-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254971 LG9668 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255002-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 18 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903255002 LG9670 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27-SPOMA
ADIDAS | 0903255005-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 494 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255005 LF0721 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255036-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 123 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903255036 KX3650 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255046-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255046 LG9665 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255047-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 1203 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903255047 KG3190 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903255082-1 LG9666 | BLACK | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255082 LG9666 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255083-1 IL7232 | BLACK | 105D | S2408MR3202 | 468 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 512102 | PAD+HT SUB PROCESS_V3 | 0903255083 IL7232 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903255105-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255105 LH3760 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255107-1 KT4840 | ONIX | 90D | S2408MR1600 | 770 | 31/10/2026 | 770 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903255107 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 770 |  | 770 |  |  | 27/10/2026 | 28/10/2026 |  |  | 770 |  | 770 |  |  | 26/10/2026 | 27/10/2026 |  |  | 770 |  | 770
ADIDAS | 0903255126-1 LH3758 | BLACK | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255126 LH3758 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903255128-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 220 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255128 LG9668 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255132-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255132 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903255138-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255138 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903255194-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 716 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903255194 LD0908 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255239-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 16/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L1 SUB PROCESS_V3 | 0903255239 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46032 | MER KA NNHD M BLACK |  | SS27-MS | 46032 | 46063 |  |  | 120 |  | 120 |  |  | 28/09/2026 | 29/09/2026 |  |  | 120 |  | 120
ADIDAS | 0903255241-1 KA0246 | BLACK | 105D | S2608WR0902 | 160 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 512106 | PAD+HT SUB PROCESS_V3 | 0903255241 KA0246 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903255271-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 219 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903255271 KA0544 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903255297-1 JZ7711 | BLACK | 120D | S2608MR0202 | 101 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255297 JZ7711 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255324-1 IN1157 | WHITE | 90D | S2408MR1600 | 493 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255324 IN1157 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255351-1 KA4331 | BLACK | 90D | S2608MR0902 | 158 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903255351 KA4331 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255416-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 330 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255416 JE6419 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903255444-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 850 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 29-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255444 JM1775 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903255455-1 IN1157 | WHITE | 90D | S2408MR1600 | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903255455 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255459-1 JZ7774 | TECH INDIGO S20 | 90D | S2608MR0902 | 1200 | 31/10/2026 | 1200 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903255459 JZ7774 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 46276 | Run Ess 21 S M TECH INDIGO S20 |  | SS27-TRAX | 46276 | 46337 |  |  | 1200 |  | 1200 |  |  | 46153 | 46214 |  |  | 1200 |  | 1200 |  |  | 46123 | 46184 |  |  | 1200 |  | 1200
ADIDAS | 0903255472-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 116 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255472 LG9663 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903255493-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 301 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255493 LG9665 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255505-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 2661 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255505 KX3650 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255507-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 23/10/2026 | 200 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255507 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 26/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 24/10/2026 | 24/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903255515-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255515 LF0718 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255516-1 KA4331 | BLACK | 90D | S2608MR0902 | 763 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903255516 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255537-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 943 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255537 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903255538-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255538 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903255541-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 766 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903255541 KY5935 | 27/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255547-1 KA4331 | BLACK | 90D | S2608MR0902 | 4004 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255547 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255551-1 KD3875 | BLACK | 120D | S2608WR0201 | 131 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903255551 KD3875 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903255562-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 4122 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255562 KX3655 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255565-1 IN1173 | WHITE | 90D | S2408WR1600 | 219 | 31/10/2026 | 219 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903255565 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 219 |  | 219 |  |  | 46305 | 46366 |  |  | 219 |  | 219 |  |  | 46275 | 46305 |  |  | 219 |  | 219
ADIDAS | 0903255580-1 KT4839 | ONIX | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT SUB PROCESS_V1 | 0903255580 KT4839 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 26/10/2026 | 26/10/2026 |  |  | 125 |  | 125 |  |  | 24/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903255584-1 IN1156 | BLACK | 90D | S2408MR1600 | 543 | 31/10/2026 | 543 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903255584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 543 |  | 543 |  |  | 27/10/2026 | 29/10/2026 |  |  | 543 |  | 543 |  |  | 26/10/2026 | 28/10/2026 |  |  | 543 |  | 543
ADIDAS | 0903255600-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 252 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 839062 | PAD+HT SUB PROCESS_V3 | 0903255600 KY5935 | 27/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255606-1 KT4840 | ONIX | 90D | S2408MR1600 | 105 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255606 KT4840 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255609-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 472 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255609 JE6341 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903255612-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 137 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255612 LG9665 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255624-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 800 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 839055 | HT+PAD SUB PROCESS_V3 | 0903255624 KX3655 | 46244 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255629-1 JZ7711 | BLACK | 120D | S2608MR0202 | 139 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255629 JZ7711 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255640-1 LF0727 | BLACK | 120D | S2754MAS510B | 260 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255640 LF0727 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255641-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255641 JW9678 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255648-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 251 | 31/10/2026 | 251 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255648 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46306 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 46306 | 46367 |  |  | 251 |  | 251 |  |  | 46184 | 46276 |  |  | 251 |  | 251
ADIDAS | 0903255672-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 194 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255672 LG9665 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255675-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255675 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903255687-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 848 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903255687 JW9678 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255711-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255711 LF0726 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903255746-1 IN1157 | WHITE | 90D | S2408MR1600 | 414 | 31/10/2026 | 414 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903255746 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 414 |  | 414 |  |  | 26/10/2026 | 27/10/2026 |  |  | 414 |  | 414 |  |  | 24/10/2026 | 26/10/2026 |  |  | 414 |  | 414
ADIDAS | 0903255755-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 687 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255755 LG9674 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255780-1 LG9666 | BLACK | 120D | S2754WAS512C | 285 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255780 LG9666 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255794-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 367 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903255794 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903255825-1 LG9669 | BLACK | 120D | S2754WAS514C | 270 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255825 LG9669 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903255856-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 152 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848016 | HT+PAD SUB PROCESS_V3 | 0903255856 KB5961 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903255884-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255884 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T BLACK |  | SS27
ADIDAS | 0903255888-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1370 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255888 JZ7711 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255911-1 IN2961 | BLACK | 105D | S2408WR2400 | 1200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255911 IN2961 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903255932-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 212 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903255932 KY5900 | 46244 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255936-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255936 LF0729 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255945-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 568 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903255945 LD0292 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255947-1 LF0727 | BLACK | 120D | S2754MAS510B | 410 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255947 LF0727 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255969-1 IN1156 | BLACK | 90D | S2408MR1600 | 1798 | 31/10/2026 | 1798 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903255969 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 46064 | ADIZERO E TEE |  | SS27-YTI | 46064 | 46123 |  |  | 1798 |  | 1798 |  |  | 30/10/2026 | 46064 |  |  | 1798 |  | 1798 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1798 |  | 1798
ADIDAS | 0903255971-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 803 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903255971 KA0247 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903255977-1 LF0718 | BLACK | 105D | S2754MAS512B | 453 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255977 LF0718 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255991-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 100 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (NYK warehouse). 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903255991 LF5052 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903255999-1 IN1173 | WHITE | 90D | S2408WR1600 | 1056 | 31/10/2026 | 1056 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903255999 IN1173 |  | KAHATEX CIJERAH | ISRAEL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 1056 |  | 1056 |  |  | 46366 | 13/10/2026 |  |  | 1056 |  | 1056 |  |  | 46305 | 46366 |  |  | 1056 |  | 1056
ADIDAS | 0903256003-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256003 LG9665 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903256009-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903256009 KA0237 | 46244 | KAHATEX CIJERAH | JAPAN | SEA | 16/11/2026 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 16/11/2026 | 19/11/2026 |  |  | 1250 |  | 1250 |  |  | 46367 | 16/11/2026 |  |  | 1250 |  | 1250 |  |  | 46337 | 14/11/2026 |  |  | 1250 |  | 1250
ADIDAS | 0903256019-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 136 | 46214 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256019 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256028-1 LG9669 | BLACK | 120D | S2754WAS514C | 291 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903256028 LG9669 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903256042-1 IK7442 | WHITE | 105D | S2408WR2400 | 2500 | 31/10/2026 | 2500 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903256042 IK7442 | 46244 | KAHATEX CIJERAH | JAPAN | SEA | 46123 | OTR B TEE WHITE |  | SS27 | 46123 | 46184 |  |  | 2500 |  | 2500 |  |  | 46064 | 46123 |  |  | 2500 |  | 2500 |  |  | 31/10/2026 | 46092 |  |  | 2500 |  | 2500
ADIDAS | 0903256052-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 107 | 23/10/2026 | 107 | AN | AN10/07/2026 | G2E | T-SHIRT | G2 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256052 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L | 13/10/2026 | 14/10/2026 |  |  | 107 |  | 107 |  |  | 46275 | 46305 |  |  | 107 |  | 107
ADIDAS | 0903256056-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 455 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256056 KQ8640 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256058-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 564 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256058 KQ8640 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256065-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1251 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256065 KQ8640 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256109-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1043 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256109 KX3654 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903256111-1 IN8707 | BLACK | 105D | S2408WR1601A | 104 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903256111 IN8707 | 46244 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903256137-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256137 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903256140-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 2846 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256140 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256160-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 154 | 31/10/2026 | 154 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT SUB PROCESS_V1 | 0903256160 KG8553 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 154 |  | 154 |  |  | 26/10/2026 | 27/10/2026 |  |  | 154 |  | 154 |  |  | 24/10/2026 | 26/10/2026 |  |  | 154 |  | 154
ADIDAS | 0903256178-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 168 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256178 JZ7715 | 46244 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903256216-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 160 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903256216 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903256236-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256236 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903256262-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 803 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256262 KB5959 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256378-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 343 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903256378 KB5960 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256533-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 132 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903256533 KB5959 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256569-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 120 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903256569 LD0292 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903256659-1 KT4840 | ONIX | 90D | S2408MR1600 | 200 | 31/10/2026 | 200 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256659 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 200 |  | 200 |  |  | 27/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 26/10/2026 | 27/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903256662-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 557 | 31/10/2026 | 557 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 12-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256662 KY4155 | 46244 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 557 |  | 557 |  |  | 20/10/2026 | 22/10/2026 |  |  | 557 |  | 557
ADIDAS | 0903256695-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 384 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256695 KY4155 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903256720-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 302 | 31/10/2026 | 302 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256720 KY6510 | 46244 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | M 3S CHELSEA B7 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 302 |  | 302 |  |  | 24/10/2026 | 26/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903256734-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256734 KA6229 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903256760-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1957 | 31/10/2026 | 1957 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256760 KY6510 | 46244 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | M 3S CHELSEA B7 |  | SS27 | 29/10/2026 | 46064 |  |  | 1957 |  | 1957 |  |  | 26/10/2026 | 29/10/2026 |  |  | 1957 |  | 1957
ADIDAS | 0903256777-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 280 | 23/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903256777 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903256808-1 KD3875 | BLACK | 120D | S2608WR0201 | 203 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903256808 KD3875 | 46244 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256829-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 364 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256829 LE8188 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903256830-1 KD3875 | BLACK | 120D | S2608WR0201 | 454 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903256830 KD3875 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256862-1 KD3875 | BLACK | 120D | S2608WR0201 | 603 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903256862 KD3875 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256866-1 KA0246 | BLACK | 105D | S2608WR0902 | 230 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | PAD+HT SUB PROCESS_V3 | 0903256866 KA0246 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903256873-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 113 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256873 KD3854 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256876-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 266 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848024 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256876 KY5988 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903256903-1 LE8187 | BLACK | 105D | S2754MAS513 | 212 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256903 LE8187 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903256918-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 31/10/2026 | 148 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256918 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 148 |  | 148 |  |  | 46064 | 46092 |  |  | 148 |  | 148 |  |  | 31/10/2026 | 46064 |  |  | 148 |  | 148
ADIDAS | 0903256925-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 226 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903256925 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903256933-1 JZ7711 | BLACK | 120D | S2608MR0202 | 686 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256933 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256939-1 JZ7711 | BLACK | 120D | S2608MR0202 | 319 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256939 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256944-1 KT4840 | ONIX | 90D | S2408MR1600 | 149 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903256944 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903256969-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 105 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903256969 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903256981-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 120 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256981 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903256982-1 JZ7711 | BLACK | 120D | S2608MR0202 | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256982 JZ7711 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256991-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 250 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903256991 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903257000-1 JZ7711 | BLACK | 120D | S2608MR0202 | 556 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257000 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257035-1 JZ7711 | BLACK | 120D | S2608MR0202 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257035 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257051-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 144 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257051 KC5231 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903257067-1 JZ7711 | BLACK | 120D | S2608MR0202 | 378 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257067 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257069-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 102 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257069 KX3655 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257106-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1785 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257106 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257118-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257118 KY9385 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257136-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257136 LF0729 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903257138-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 318 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257138 KY9384 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903257149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903257149 KX3654 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257153-1 LG9675 | BLACK | 120D | S2754WAS513C | 727 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257153 LG9675 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903257175-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 182 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257175 KY9385 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257188-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 246 | 23/10/2026 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903257188 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903257201-1 LF0727 | BLACK | 120D | S2754MAS510B | 100 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257201 LF0727 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903257220-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257220 KU7520 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 180 |  | 180 |  |  | 31/10/2026 | 46064 |  |  | 180 |  | 180 |  |  | 30/10/2026 | 31/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257245-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 848016 | HT SUB PROCESS_V1 | 0903257245 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 29/10/2026 |  |  | 180 |  | 180 |  |  | 27/10/2026 | 27/10/2026 |  |  | 180 |  | 180 |  |  | 26/10/2026 | 26/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257251-1 IN1159 | BLACK | 90D | S2408MR1601 | 162 | 31/10/2026 | 162 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903257251 IN1159 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 46184 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 46184 | 46184 |  |  | 162 |  | 162 |  |  | 46123 | 46123 |  |  | 162 |  | 162 |  |  | 46092 | 46092 |  |  | 162 |  | 162
ADIDAS | 0903257256-1 IK7442 | WHITE | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903257256 IK7442 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903257264-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257264 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 46123 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46123 | 46153 |  |  | 100 |  | 100 |  |  | 46064 | 46092 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 46064 |  |  | 100 |  | 100
ADIDAS | 0903257282-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 267 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512102 | HT+PAD SUB PROCESS_V3 | 0903257282 KX3654 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257289-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 139 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903257289 KY5988 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903257305-1 KA4331 | BLACK | 90D | S2608MR0902 | 317 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903257305 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257308-1 LF0718 | BLACK | 105D | S2754MAS512B | 111 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257308 LF0718 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903257351-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 145 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257351 LK8779 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903257417-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 452 | 46214 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L1 SUB PROCESS_V3 | 0903257417 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903257458-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 239 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 512106 | HT+PAD SUB PROCESS_V3 | 0903257458 KB5961 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257584-1 LG9666 | BLACK | 120D | S2754WAS512C | 524 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257584 LG9666 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903257609-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 171 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903257609 LH3760 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257661-1 KA4331 | BLACK | 90D | S2608MR0902 | 1151 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257661 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257667-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 219 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257667 LG9674 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257668-1 IN1173 | WHITE | 90D | S2408WR1600 | 269 | 31/10/2026 | 269 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257668 IN1173 |  | KAHATEX CIJERAH | MOROCCO | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 269 |  | 269 |  |  | 46305 | 46366 |  |  | 269 |  | 269 |  |  | 46275 | 46305 |  |  | 269 |  | 269
ADIDAS | 0903257681-1 IN1156 | BLACK | 90D | S2408MR1600 | 581 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903257681 IN1156 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257689-1 KA4331 | BLACK | 90D | S2608MR0902 | 1781 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257689 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257710-1 IN1159 | BLACK | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT SUB PROCESS_V1 | 0903257710 IN1159 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 26/10/2026 | 26/10/2026 |  |  | 125 |  | 125 |  |  | 24/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903257712-1 IN1173 | WHITE | 90D | S2408WR1600 | 540 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903257712 IN1173 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257721-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 230 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 547012 | HT+PAD SUB PROCESS_V3 | 0903257721 KX3650 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257739-1 LF0723 | BLACK | 105D | S2754MAS511B | 207 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257739 LF0723 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257757-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 244 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903257757 KU7520 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903257763-1 IN1157 | WHITE | 90D | S2408MR1600 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903257763 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 275 |  | 275 |  |  | 24/10/2026 | 26/10/2026 |  |  | 275 |  | 275 |  |  | 23/10/2026 | 24/10/2026 |  |  | 275 |  | 275
ADIDAS | 0903257766-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 727 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257766 KV7863 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903257770-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 322 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257770 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903257777-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 441 | 31/10/2026 | 441 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903257777 KX9855 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 29/10/2026 |  |  | 441 |  | 441 |  |  | 27/10/2026 | 27/10/2026 |  |  | 441 |  | 441 |  |  | 26/10/2026 | 26/10/2026 |  |  | 441 |  | 441
ADIDAS | 0903257790-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 410 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257790 JE6417 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903257793-1 LE8187 | BLACK | 105D | S2754MAS513 | 397 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257793 LE8187 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257797-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 547012 | HT+PAD SUB PROCESS_V3 | 0903257797 KB5961 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257799-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 406 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257799 JE1309 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903257805-1 KZ1322 | KHAKI SIX F26/KHAKI THREE F26 | 120D | S2608MR0202 | 2388 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257805 KZ1322 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M KHAKI SIX F26/KHAKI THREE F26 |  | SS27-TRAX
ADIDAS | 0903257826-1 KA4331 | BLACK | 90D | S2608MR0902 | 395 | 23/10/2026 | 395 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257826 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 395 |  | 395 |  |  | 21/10/2026 | 22/10/2026 |  |  | 395 |  | 395 |  |  | 20/10/2026 | 21/10/2026 |  |  | 395 |  | 395
ADIDAS | 0903257828-1 IN2961 | BLACK | 105D | S2408WR2400 | 3750 | 31/10/2026 | 3750 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903257828 IN2961 | 46244 | KAHATEX CIJERAH | JAPAN | SEA | 46367 | OTR B TEE BLACK |  | SS27 | 46367 | 16/11/2026 |  |  | 3750 |  | 3750 |  |  | 46306 | 13/11/2026 |  |  | 3750 |  | 3750 |  |  | 46276 | 46367 |  |  | 3750 |  | 3750
ADIDAS | 0903257836-1 IN1159 | BLACK | 90D | S2408MR1601 | 130 | 31/10/2026 | 130 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903257836 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46184 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 46184 | 46184 |  |  | 130 |  | 130 |  |  | 46123 | 46123 |  |  | 130 |  | 130 |  |  | 46092 | 46092 |  |  | 130 |  | 130
ADIDAS | 0903257842-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 500 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903257842 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257844-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 460 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (14/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257844 JM1776 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903257857-1 LF0723 | BLACK | 105D | S2754MAS511B | 1205 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257857 LF0723 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257864-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 329 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257864 LG9661 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903257865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 578 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257865 KX3650 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257872-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 296 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903257872 LC6339 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903257890-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 126 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903257890 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903257892-1 LE8187 | BLACK | 105D | S2754MAS513 | 180 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257892 LE8187 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257900-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903257900 KG3234 | 46244 | KAHATEX CIJERAH | JAPAN | SEA | 46306 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 46306 | 13/11/2026 |  |  | 1250 |  | 1250 |  |  | 46184 | 46306 |  |  | 1250 |  | 1250 |  |  | 46153 | 46276 |  |  | 1250 |  | 1250
ADIDAS | 0903257925-1 KA4331 | BLACK | 90D | S2608MR0902 | 253 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257925 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257930-1 KA4331 | BLACK | 90D | S2608MR0902 | 460 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257930 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257952-1 IN1172 | BLACK | 90D | S2408WR1600 | 380 | 31/10/2026 | 380 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257952 IN1172 |  | KAHATEX CIJERAH | MOROCCO | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 380 |  | 380 |  |  | 19/10/2026 | 20/10/2026 |  |  | 380 |  | 380 |  |  | 17/10/2026 | 19/10/2026 |  |  | 380 |  | 380
ADIDAS | 0903257955-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 155 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903257955 KZ1286 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903257978-1 IN1159 | BLACK | 90D | S2408MR1601 | 163 | 31/10/2026 | 163 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903257978 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 46153 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 46153 | 46184 |  |  | 163 |  | 163 |  |  | 46092 | 46123 |  |  | 163 |  | 163 |  |  | 46064 | 46092 |  |  | 163 |  | 163
ADIDAS | 0903257981-1 IN1156 | BLACK | 90D | S2408MR1600 | 2281 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903257981 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257984-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 473 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903257984 LD0293 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903257985-1 IK7442 | WHITE | 105D | S2408WR2400 | 1056 | 31/10/2026 | 1056 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903257985 IK7442 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA | 46092 | OTR B TEE WHITE |  | SS27 | 46092 | 46123 |  |  | 1056 |  | 1056 |  |  | 31/10/2026 | 46064 |  |  | 1056 |  | 1056 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1056 |  | 1056
ADIDAS | 0903258004-1 IN1173 | WHITE | 90D | S2408WR1600 | 314 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903258004 IN1173 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258033-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 142 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903258033 LG9668 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903258038-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 183 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258038 LF0726 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258044-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 304 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258044 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258059-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 1550 | 31/10/2026 | 1550 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903258059 JW9678 | 46244 | KAHATEX CIJERAH | JAPAN | SEA | 46184 | OTR B TEE POWDER PLUM F25 |  | SS27 | 46184 | 46276 |  |  | 1550 |  | 1550 |  |  | 46123 | 46184 |  |  | 1550 |  | 1550 |  |  | 46092 | 46153 |  |  | 1550 |  | 1550
ADIDAS | 0903258065-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 242 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258065 LG9674 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903258089-1 LE8187 | BLACK | 105D | S2754MAS513 | 1030 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258089 LE8187 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903258094-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 100 | 31/10/2026 | 100 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 10-Aug, ETD 10-Aug, ETA KH 21-Aug. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258094 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46153 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 46153 | 46214 |  |  | 100 |  | 100 |  |  | 46064 | 46123 |  |  | 100 |  | 100
ADIDAS | 0903258102-1 LH3758 | BLACK | 120D | S2754WAS518B | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPA SUB PROCESS_V3 | 0903258102 LH3758 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258123-1 LG9666 | BLACK | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258123 LG9666 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903258126-1 IN1157 | WHITE | 90D | S2408MR1600 | 319 | 23/10/2026 | 319 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903258126 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 319 |  | 319 |  |  | 23/10/2026 | 24/10/2026 |  |  | 319 |  | 319 |  |  | 22/10/2026 | 23/10/2026 |  |  | 319 |  | 319
ADIDAS | 0903258129-1 LF0727 | BLACK | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258129 LF0727 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903258151-1 IN1160 | WHITE | 90D | S2408MR1601 | 585 | 31/10/2026 | 585 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903258151 IN1160 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 31/10/2026 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 31/10/2026 | 46064 |  |  | 585 |  | 585 |  |  | 29/10/2026 | 30/10/2026 |  |  | 585 |  | 585 |  |  | 28/10/2026 | 29/10/2026 |  |  | 585 |  | 585
ADIDAS | 0903258170-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258170 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 28/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 28/10/2026 | 28/10/2026 |  |  | 107 |  | 107 |  |  | 24/10/2026 | 24/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903258174-1 IL7232 | BLACK | 105D | S2408MR3202 | 684 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 547012 | PAD+HT SUB PROCESS_V3 | 0903258174 IL7232 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903258181-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 290 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258181 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903258192-1 LF0723 | BLACK | 105D | S2754MAS511B | 144 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258192 LF0723 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903258203-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 845 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258203 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258204-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 360 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 547012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258204 KA0544 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903258217-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 584 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516343 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258217 KC8152 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258219-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 5500 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258219 JD1877 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258228-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 115 | 46214 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258228 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258241-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 340 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258241 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258249-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 319 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258249 KR3066 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258259-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 326 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258259 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258260-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258260 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 28/10/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 28/10/2026 | 28/10/2026 |  |  | 107 |  | 107 |  |  | 24/10/2026 | 24/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903258280-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 5000 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258280 JE6338 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258290-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 305 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258290 KR3066 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258291-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 711 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258291 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258292-1 KT4839 | ONIX | 90D | S2408MR1601 | 161 | 31/10/2026 | 161 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903258292 KT4839 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 161 |  | 161 |  |  | 26/10/2026 | 27/10/2026 |  |  | 161 |  | 161 |  |  | 24/10/2026 | 26/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903258294-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258294 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903258321-1 IN1172 | BLACK | 90D | S2408WR1600 | 1722 | 31/10/2026 | 1722 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903258321 IN1172 |  | KAHATEX CIJERAH | ISRAEL | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 1722 |  | 1722 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1722 |  | 1722 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1722 |  | 1722
ADIDAS | 0903258324-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 115 | 46214 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258324 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258343-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 283 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903258343 KZ1286 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903258404-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 461 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903258404 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258496-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 445 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258496 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258628-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 350 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258628 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903258660-1 KT4839 | ONIX | 90D | S2408MR1601 | 112 | 31/10/2026 | 112 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903258660 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 112 |  | 112 |  |  | 26/10/2026 | 27/10/2026 |  |  | 112 |  | 112 |  |  | 24/10/2026 | 26/10/2026 |  |  | 112 |  | 112
ADIDAS | 0903258682-1 LH3758 | BLACK | 120D | S2754WAS518B | 162 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258682 LH3758 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258718-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258718 LE8188 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258746-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258746 LF0729 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903258772-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 102 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258772 LE8181 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258820-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 147 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903258820 KX3655 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903258846-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 334 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258846 LG9675 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903258880-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903258880 KZ2984 |  | KAHATEX CIJERAH | MOROCCO | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 31/10/2026 |  |  | 138 |  | 138 |  |  | 29/10/2026 | 29/10/2026 |  |  | 138 |  | 138 |  |  | 28/10/2026 | 28/10/2026 |  |  | 138 |  | 138
ADIDAS | 0903258904-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 261 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903258904 LD0293 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258907-1 KB5965 | BLACK | 120D | S2608MR0900A | 789 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258907 KB5965 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903258933-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 556 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258933 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903258954-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 420 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258954 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903259111-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259111 JE1309 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903259160-1 IN1157 | WHITE | 90D | S2408MR1600 | 483 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259160 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259172-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 164 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259172 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903259177-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 437 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259177 KY9383 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259204-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 730 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259204 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259211-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259211 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259212-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 316 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259212 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259232-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 380 | 46214 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259232 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903259252-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 529 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259252 KY9383 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259268-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 405 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259268 KR3066 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903259305-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259305 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259338-1 LG9666 | BLACK | 120D | S2754WAS512C | 320 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259338 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903259343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 313 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259343 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259378-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259378 KY9385 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903259404-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 315 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259404 LF0726 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903259471-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903259471 KX9851 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903259524-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 125 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259524 KY9384 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259561-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903259561 KC8152 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903259595-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 510 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903259595 LG9675 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903259603-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 900 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903259603 KF5295 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903259633-1 KA0246 | BLACK | 105D | S2608WR0902 | 300 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | PAD+HT SUB PROCESS_V3 | 0903259633 KA0246 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903259751-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 204 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903259751 KA0546 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903259789-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903259789 IN1172 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259835-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 249 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903259835 LC6339 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903259841-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 225 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259841 JW7178 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903259864-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 822 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 806020 | HT+PAD SUB PROCESS_V3 | 0903259864 KX3655 | 46244 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259916-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 346 | 23/10/2026 | 346 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259916 LE4307 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 46153 |  |  | 346 |  | 346 |  |  | 27/10/2026 | 46064 |  |  | 346 |  | 346
ADIDAS | 0903260147-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260147 LG9665 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903260151-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 84 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 02-Sep. T2 Teijin Nantong, PI Date 30-Aug, actual receives 31-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260151 LD5446 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903260153-1 IN8707 | BLACK | 105D | S2408WR1601A | 135 | 31/10/2026 | 135 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903260153 IN8707 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 135 |  | 135 |  |  | 27/10/2026 | 28/10/2026 |  |  | 135 |  | 135 |  |  | 26/10/2026 | 27/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903260154-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 208 | 23/10/2026 | 208 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 03-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260154 KZ3204 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 30/10/2026 | 46153 |  |  | 208 |  | 208 |  |  | 27/10/2026 | 46064 |  |  | 208 |  | 208
ADIDAS | 0903260162-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 160 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 980004 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903260162 KA4914 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903260166-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260166 LF0729 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260176-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 647 | 31/10/2026 | 647 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903260176 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46092 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46092 | 46123 |  |  | 647 |  | 647 |  |  | 31/10/2026 | 46064 |  |  | 647 |  | 647 |  |  | 30/10/2026 | 31/10/2026 |  |  | 647 |  | 647
ADIDAS | 0903260179-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 252 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260179 LG9675 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903260189-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 180 | 31/10/2026 | 180 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260189 JN1948 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/10/2026 | W 3S FT QZ HD |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 180 |  | 180 |  |  | 26/10/2026 | 27/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903260204-1 IN1156 | BLACK | 90D | S2408MR1600 | 445 | 31/10/2026 | 445 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903260204 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 445 |  | 445 |  |  | 27/10/2026 | 29/10/2026 |  |  | 445 |  | 445 |  |  | 26/10/2026 | 28/10/2026 |  |  | 445 |  | 445
ADIDAS | 0903260210-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 100 | 31/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903260210 KD4872 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903260237-1 IN1173 | WHITE | 90D | S2408WR1600 | 663 | 31/10/2026 | 663 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260237 IN1173 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46366 | ADIZERO E TEE |  | SS27-YTI | 46366 | 13/10/2026 |  |  | 663 |  | 663 |  |  | 46275 | 46305 |  |  | 663 |  | 663 |  |  | 46244 | 46275 |  |  | 663 |  | 663
ADIDAS | 0903260251-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903260251 LD0277 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 46306 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46306 | 46337 |  |  | 102 |  | 102 |  |  | 46184 | 46214 |  |  | 102 |  | 102 |  |  | 46153 | 46184 |  |  | 102 |  | 102
ADIDAS | 0903260280-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903260280 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46153 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 46153 | 46184 |  |  | 300 |  | 300 |  |  | 46092 | 46123 |  |  | 300 |  | 300 |  |  | 46064 | 46092 |  |  | 300 |  | 300
ADIDAS | 0903260281-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 285 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260281 LF0721 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260320-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260320 LG9661 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903260341-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 452 | 46214 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903260341 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260342-1 KG8547 | ONIX | 90D | S2408WR1600 | 209 | 31/10/2026 | 209 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903260342 KG8547 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 209 |  | 209 |  |  | 26/10/2026 | 27/10/2026 |  |  | 209 |  | 209 |  |  | 24/10/2026 | 26/10/2026 |  |  | 209 |  | 209
ADIDAS | 0903260350-1 LF0723 | BLACK | 105D | S2754MAS511B | 252 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260350 LF0723 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903260366-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 400 | 31/10/2026 | 400 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260366 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 46153 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 46153 | 46214 |  |  | 400 |  | 400 |  |  | 46064 | 46123 |  |  | 400 |  | 400
ADIDAS | 0903260374-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 139 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903260374 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903260383-1 LG9669 | BLACK | 120D | S2754WAS514C | 252 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260383 LG9669 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260410-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 252 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260410 LE8181 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903260461-1 LF0727 | BLACK | 120D | S2754MAS510B | 114 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260461 LF0727 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260463-1 IN1172 | BLACK | 90D | S2408WR1600 | 676 | 31/10/2026 | 676 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260463 IN1172 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 676 |  | 676 |  |  | 20/10/2026 | 21/10/2026 |  |  | 676 |  | 676 |  |  | 19/10/2026 | 20/10/2026 |  |  | 676 |  | 676
ADIDAS | 0903260486-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 473 | 31/10/2026 | 473 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260486 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 473 |  | 473 |  |  | 46064 | 46092 |  |  | 473 |  | 473 |  |  | 31/10/2026 | 46064 |  |  | 473 |  | 473
ADIDAS | 0903260513-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 1062 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903260513 JZ7715 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903260517-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 331 | 23/10/2026 |  | AN | AN10/07/2026 |  | SHORTS |  | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260517 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903260543-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 252 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260543 LF0718 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903260544-1 LF0727 | BLACK | 120D | S2754MAS510B | 380 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260544 LF0727 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260564-1 LG9669 | BLACK | 120D | S2754WAS514C | 231 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903260564 LG9669 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260662-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 510 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825057 | PRINT L3 SUB PROCESS_V3 | 0903260662 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260775-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 631 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825056 | PRINT L3 SUB PROCESS_V3 | 0903260775 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260885-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 113 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903260885 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903260989-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 600 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903260989 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903261075-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 355 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). (China). (China). 825057 | PRINT L1 SUB PROCESS_V3 | 0903261075 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903261204-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1609 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261204 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903261255-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1232 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261255 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903261283-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1152 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903261283 KD3911 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | RELEASED |  | SS27
ADIDAS | 0903261379-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 434 | 31/10/2026 | 434 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903261379 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 434 |  | 434 |  |  | 31/10/2026 | 46064 |  |  | 434 |  | 434 |  |  | 30/10/2026 | 31/10/2026 |  |  | 434 |  | 434
ADIDAS | 0903261414-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261414 LD0293 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903261439-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 700 | 31/10/2026 | 700 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261439 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46064 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46064 | 46123 |  |  | 700 |  | 700 |  |  | 29/10/2026 | 31/10/2026 |  |  | 700 |  | 700 |  |  | 28/10/2026 | 30/10/2026 |  |  | 700 |  | 700
ADIDAS | 0903261449-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 298 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261449 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903261459-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 531 | 31/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903261459 KX3654 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903261492-1 IN1157 | WHITE | 90D | S2408MR1600 | 507 | 31/10/2026 | 507 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261492 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 507 |  | 507 |  |  | 26/10/2026 | 27/10/2026 |  |  | 507 |  | 507 |  |  | 24/10/2026 | 26/10/2026 |  |  | 507 |  | 507
ADIDAS | 0903261505-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 268 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261505 JE0055 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903261529-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261529 LD0292 | 46244 | KAHATEX CIJERAH | MEXICO | SEA | 46306 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 46306 | 46367 |  |  | 300 |  | 300 |  |  | 46184 | 46276 |  |  | 300 |  | 300 |  |  | 46153 | 46214 |  |  | 300 |  | 300
ADIDAS | 0903261530-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 800 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | T2 Gistex, material quality issues (creasemark), PI Date 09-Aug, actual receives 14-Aug (100% QC panel). 826010 | HT SUB PROCESS_V1 | 0903261530 IL4127 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903261558-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 1889 | 31/10/2026 | 1889 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (Mexico). T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 652001 | HT SUB PROCESS_V1 | 0903261558 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46153 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 46153 | 46214 |  |  | 1889 |  | 1889 |  |  | 46092 | 46153 |  |  | 1889 |  | 1889 |  |  | 46064 | 46123 |  |  | 1889 |  | 1889
ADIDAS | 0903261559-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1040 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261559 JD5302 |  | KAHATEX CIJERAH | TURKEY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903261581-1 LF0723 | BLACK | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903261581 LF0723 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903261586-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 360 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903261586 KY5988 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903261602-1 KA0246 | BLACK | 105D | S2608WR0902 | 12 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | PAD+HT SUB PROCESS_V3 | 0903261602 KA0246 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903261610-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 550 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903261610 JD1877 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903261645-1 KT4840 | ONIX | 90D | S2408MR1600 | 2134 | 31/10/2026 | 2134 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261645 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/10/2026 | ADIZERO E TEE |  | SS27-YTI | 30/10/2026 | 46092 |  |  | 2134 |  | 2134 |  |  | 28/10/2026 | 31/10/2026 |  |  | 2134 |  | 2134 |  |  | 27/10/2026 | 30/10/2026 |  |  | 2134 |  | 2134
ADIDAS | 0903262104-1 IL7232 | BLACK | 105D | S2408MR3202 | 367 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 804028 | PAD+HT SUB PROCESS_V3 | 0903262104 IL7232 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903262124-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 1676 | 46214 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262124 LF0718 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903262654-1 KA4331 | BLACK | 90D | S2608MR0902 | 1174 | 30/10/2026 | 1174 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  | ok | (Mexico). DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262654 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 27/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 1174 |  | 1174 |  |  | 23/10/2026 | 26/10/2026 |  |  | 1174 |  | 1174 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1174 |  | 1174
ADIDAS | 0903262659-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 100 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903262659 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903262676-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 878 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262676 KD3854 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903262680-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 550 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903262680 KX3655 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262708-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1006 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug. Waiting fabric. T2 Far Easten, PI Date 25-Aug. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262708 JZ7711 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903262735-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 309 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | (05/08/2026) | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903262735 KZ1286 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903262736-1 KG8547 | ONIX | 90D | S2408WR1600 | 343 | 31/10/2026 | 343 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262736 KG8547 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 343 |  | 343 |  |  | 26/10/2026 | 27/10/2026 |  |  | 343 |  | 343 |  |  | 24/10/2026 | 26/10/2026 |  |  | 343 |  | 343
ADIDAS | 0903262752-1 IK7442 | WHITE | 105D | S2408WR2400 | 190 | 31/10/2026 | 190 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903262752 IK7442 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 46092 | OTR B TEE WHITE |  | SS27 | 46092 | 46092 |  |  | 190 |  | 190 |  |  | 31/10/2026 | 31/10/2026 |  |  | 190 |  | 190 |  |  | 30/10/2026 | 30/10/2026 |  |  | 190 |  | 190
ADIDAS | 0903262767-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 1656 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903262767 KY5988 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903262778-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 125 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903262778 KF5295 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903262788-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1466 | 31/10/2026 | 1466 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262788 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46153 | ADIZERO E TEE |  | SS27-YTI | 46153 | 46214 |  |  | 1466 |  | 1466 |  |  | 46092 | 46153 |  |  | 1466 |  | 1466 |  |  | 46064 | 46123 |  |  | 1466 |  | 1466
ADIDAS | 0903262802-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 120 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903262802 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262839-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 31/10/2026 | 300 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262839 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46214 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 46214 | 46276 |  |  | 300 |  | 300 |  |  | 46123 | 46153 |  |  | 300 |  | 300 |  |  | 46092 | 46123 |  |  | 300 |  | 300
ADIDAS | 0903262846-1 LE8187 | BLACK | 105D | S2754MAS513 | 329 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262846 LE8187 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903262866-1 KT4839 | ONIX | 90D | S2408MR1601 | 2542 | 30/10/2026 | 2542 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903262866 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 46153 |  |  | 2542 |  | 2542 |  |  | 29/10/2026 | 46092 |  |  | 2542 |  | 2542 |  |  | 28/10/2026 | 46064 |  |  | 2542 |  | 2542
ADIDAS | 0903262869-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262869 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903262892-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262892 IN8707 | 46244 | KAHATEX CIJERAH | MEXICO | SEA | 30/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 30/10/2026 | 46064 |  |  | 300 |  | 300 |  |  | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903262893-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 407 | 23/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903262893 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903262897-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262897 LE8181 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262920-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 1163 | 31/10/2026 | 1163 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262920 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 46092 |  |  | 1163 |  | 1163 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1163 |  | 1163 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1163 |  | 1163
ADIDAS | 0903262938-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 369 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262938 LF0726 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262943-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 406 | 31/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903262943 KX3655 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262965-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 1142 | 31/10/2026 | 1142 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262965 KZ2988 | 46244 | KAHATEX CIJERAH | MEXICO | SEA | 46123 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 46123 | 46214 |  |  | 1142 |  | 1142 |  |  | 46064 | 46153 |  |  | 1142 |  | 1142 |  |  | 31/10/2026 | 46123 |  |  | 1142 |  | 1142
ADIDAS | 0903262975-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 1568 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262975 LG9665 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263005-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 410 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263005 LG9661 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903263040-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C-MTF | 1621 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263040 LG9674 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263070-1 LG9669 | BLACK | 120D | S2754WAS514C | 441 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263070 LG9669 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903263086-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1346 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263086 LG9675 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903263306-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 430 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 512106 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903263306 KY5988 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903263330-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 160 | 31/10/2026 | 160 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263330 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46123 | ADIZERO E TEE |  | SS27-YTI | 46123 | 46153 |  |  | 160 |  | 160 |  |  | 46064 | 46092 |  |  | 160 |  | 160 |  |  | 31/10/2026 | 46064 |  |  | 160 |  | 160
ADIDAS | 0903263390-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263390 LF0729 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263420-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 198 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263420 LF0721 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263452-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 130 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903263452 KX9838 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903263473-1 KB5960 | WHITE | 120D | S2608MR0900A | 260 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903263473 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903263497-1 IN1157 | WHITE | 90D | S2408MR1600 | 193 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263497 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903263545-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 31/10/2026 | 250 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903263545 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 250 |  | 250 |  |  | 21/10/2026 | 22/10/2026 |  |  | 250 |  | 250 |  |  | 20/10/2026 | 21/10/2026 |  |  | 250 |  | 250
ADIDAS | 0903263584-1 IN1156 | BLACK | 90D | S2408MR1600 | 1058 | 31/10/2026 | 1058 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 46064 |  |  | 1058 |  | 1058 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1058 |  | 1058 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1058 |  | 1058
ADIDAS | 0903263651-1 IS1413 | BLACK | 60D | S2425M405 | 376 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3 SUB PROCESS_V3 | 0903263651 IS1413 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903263669-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 568 | 30/10/2026 | 568 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903263669 IT1467 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 568 |  | 568 |  |  | 27/10/2026 | 29/10/2026 |  |  | 568 |  | 568 |  |  | 26/10/2026 | 28/10/2026 |  |  | 568 |  | 568
ADIDAS | 0903263677-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 574 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263677 JE6414 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903263715-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 500 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263715 JE0052 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903263748-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 530 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263748 JD5302 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903263778-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 204 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903263778 KA5089 | 26/08/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903263840-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1055 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263840 KY9384 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903263913-1 LH3758 | BLACK | 120D | S2754WAS518B | 246 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903263913 LH3758 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903263936-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 160 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903263936 JW9678 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903264012-1 LG9666 | BLACK | 120D | S2754WAS512C | 135 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264012 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903264103-1 IN2961 | BLACK | 105D | S2408WR2400 | 1320 | 31/10/2026 | 1320 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903264103 IN2961 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA | 46337 | OTR B TEE BLACK |  | SS27 | 46337 | 46367 |  |  | 1320 |  | 1320 |  |  | 46276 | 46306 |  |  | 1320 |  | 1320 |  |  | 46214 | 46276 |  |  | 1320 |  | 1320
ADIDAS | 0903264121-1 LG9669 | BLACK | 120D | S2754WAS514C | 1 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903264121 LG9669 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903264660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 1032 | 46214 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264660 LE8181 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903264697-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 419 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264697 LF0721 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903264733-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 351 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264733 LE8188 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903266169-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 226 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L1 SUB PROCESS_V3 | 0903266169 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903266211-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 150 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903266211 KX9838 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903266275-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266275 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903266343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 172 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903266343 KY9384 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903266371-1 IN1157 | WHITE | 90D | S2408MR1600 | 350 | 23/10/2026 | 350 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516290 | HT SUB PROCESS_V1 | 0903266371 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 350 |  | 350 |  |  | 23/10/2026 | 24/10/2026 |  |  | 350 |  | 350 |  |  | 22/10/2026 | 23/10/2026 |  |  | 350 |  | 350
ADIDAS | 0903266377-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 355 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903266377 LI7659 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903266421-1 IN1172 | BLACK | 90D | S2408WR1600 | 1030 | 23/10/2026 | 1030 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 516438 | HT SUB PROCESS_V1 | 0903266421 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 1030 |  | 1030 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1030 |  | 1030 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1030 |  | 1030
ADIDAS | 0903266452-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 23/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903266452 LC6339 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903266484-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 28 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903266484 KZ1286 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903266504-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903266504 KX3650 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903266546-1 IN2961 | BLACK | 105D | S2408WR2400 | 240 | 31/10/2026 | 240 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903266546 IN2961 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 46306 | OTR B TEE BLACK |  | SS27 | 46306 | 46337 |  |  | 240 |  | 240 |  |  | 46214 | 46276 |  |  | 240 |  | 240 |  |  | 46184 | 46214 |  |  | 240 |  | 240
ADIDAS | 0903266593-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 210 | 31/10/2026 |  | SI | SI10/07/2026 |  | SWEATSHIRT |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266593 KD4874 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903266636-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 164 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903266636 LD0292 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903269380-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 352 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903269380 KZ1286 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903269421-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903269421 KR3066 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903269653-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 748 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903269653 LG9668 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903269724-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 62 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903269724 LC6339 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903270238-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 29 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270238 LF0718 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27-SPOMA
ADIDAS | 0903270268-1 LF0728 | LIGHT CINNAMON S27 | 120D | S2754MAS510B | 128 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270268 LF0728 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903270294-1 LG9662 | LIGHT CINNAMON S27 | 120D | S2754WAS512C | 95 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270294 LG9662 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903271870-1 KY5870 | GREY | 90D | S2750MTR052 | 136 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271870 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271911-1 KY5870 | GREY | 90D | S2750MTR052 | 368 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271911 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271953-1 KY5870 | GREY | 90D | S2750MTR052 | 110 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 838103 | HT SUB PROCESS_V1 | 0903271953 KY5870 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271991-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1139 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903271991 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903272018-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 261 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272018 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903272051-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 179 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903272051 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903272076-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 464 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272076 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903272106-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1252 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272106 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903273766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 545 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903273766 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903273803-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 305 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273803 KV7863 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903274149-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 607 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903274149 KV7863 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903276188-1 KY5870 | GREY | 90D | S2750MTR052 | 135 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 800187 | HT SUB PROCESS_V1 | 0903276188 KY5870 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903305161-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903305161 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903305164-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 317 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903305164 KY5988 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903306650-1 KA6229 | BLACK | 120D | S2608WR0202 | 388 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306650 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903306651-1 KA6229 | BLACK | 120D | S2608WR0202 | 222 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306651 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903309885-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 3277 | 31/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 14-Aug. 516318 | PAD+HT SUB PROCESS_V3 | 0903309885 IT3474 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903309908-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 3591 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516318 | PAD+HT SUB PROCESS_V3 | 0903309908 KF5295 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903316927-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 201 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316927 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903316932-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 798 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903316932 KY9391 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903322462-1 IN8707 | BLACK | 105D | S2408WR1601A | 170 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug. 516471 | HT SUB PROCESS_V1 | 0903322462 IN8707 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322463-1 IN1173 | WHITE | 90D | S2408WR1600 | 215 | 15/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322463 IN1173 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322464-1 IN1173 | WHITE | 90D | S2408WR1600 | 303 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322464 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322466-1 IN1173 | WHITE | 90D | S2408WR1600 | 318 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322466 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322471-1 IN1172 | BLACK | 90D | S2408WR1600 | 336 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322471 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322473-1 IN8707 | BLACK | 105D | S2408WR1601A | 339 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516471 | HT SUB PROCESS_V1 | 0903322473 IN8707 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322475-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 154 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516471 | HT SUB PROCESS_V1 | 0903322475 IN1159 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322481-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 339 | 23/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322481 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322483-1 IN1172 | BLACK | 90D | S2408WR1600 | 335 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322483 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322485-1 IN1172 | BLACK | 90D | S2408WR1600 | 299 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322485 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322493-1 IN1156 | BLACK | 90D | S2408MR1600 | 372 | 23/10/2026 | 372 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322493 IN1156 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 372 |  | 372 |  |  | 13/10/2026 | 14/10/2026 |  |  | 372 |  | 372 |  |  | 46366 | 13/10/2026 |  |  | 372 |  | 372
ADIDAS | 0903322494-1 IN1156 | BLACK | 105D | S2408MR1600 | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516471 | HT SUB PROCESS_V1 | 0903322494 IN1156 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903324319-1 KT4839 | ONIX | 90D | S2408MR1601 | 320 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 960026 | HT SUB PROCESS_V1 | 0903324319 KT4839 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903348712-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 634 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348712 KU0073 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903348833-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 1013 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348833 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903348882-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 858 | 31/10/2026 | 858 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903348882 KY1335 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 46276 | M PANCAKE T OFF WHITE |  | SS27-STX | 46276 | 46306 |  |  | 858 |  | 858 |  |  | 46153 | 46184 |  |  | 858 |  | 858
ADIDAS | 0903349016-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 517 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903349016 KA0237 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903349056-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349056 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903349066-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349066 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903350099-1 IN1172 | BLACK | 105D | S2408WR1600 | 481 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903350099 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903351210-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 285 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903351210 KS4777 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903351318-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 530 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903351318 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903351554-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 172 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903351554 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903352148-1 IN1172 | BLACK | 105D | S2408WR1600 | 406 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352148 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352206-1 IN1173 | WHITE | 105D | S2408WR1600 | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352206 IN1173 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352294-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 405 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903352294 LD0292 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903353792-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 117 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353792 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903354015-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 100 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354015 KS4777 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903354120-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 244 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903354120 KU3269 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356221-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 594 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903356221 KU3274 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356305-1 IP2310 | BLACK | 105D | S2450MTR701 | 528 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903356305 IP2310 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903356398-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903356398 JW9678 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903356461-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903356461 KB5966 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903356572-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356572 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903356606-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 104 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903356606 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356614-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 126 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356614 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903357612-1 KZ4392 | WHITE | 120D | F2608WR1500 | 1209 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903357612 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903357761-1 KA4331 | BLACK | 90D | S2608MR0902 | 1089 | 31/10/2026 | 1089 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357761 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 46184 | Run Ess 21 S M BLACK |  | SS27-TRAX | 46184 | 46276 |  |  | 1089 |  | 1089 |  |  | 46092 | 46153 |  |  | 1089 |  | 1089 |  |  | 46064 | 46123 |  |  | 1089 |  | 1089
ADIDAS | 0903357814-1 KA4331 | BLACK | 90D | S2608MR0902 | 343 | 31/10/2026 | 343 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903357814 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 343 |  | 343 |  |  | 26/10/2026 | 28/10/2026 |  |  | 343 |  | 343 |  |  | 24/10/2026 | 27/10/2026 |  |  | 343 |  | 343
ADIDAS | 0903357841-1 KA4331 | BLACK | 90D | S2608MR0902 | 816 | 31/10/2026 | 816 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357841 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 31/10/2026 | 46064 |  |  | 816 |  | 816 |  |  | 28/10/2026 | 29/10/2026 |  |  | 816 |  | 816 |  |  | 27/10/2026 | 28/10/2026 |  |  | 816 |  | 816
ADIDAS | 0903357878-1 KA4331 | BLACK | 90D | S2608MR0902 | 824 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357878 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357917-1 KA4331 | BLACK | 90D | S2608MR0902 | 1177 | 23/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357917 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357951-1 KB5960 | WHITE | 120D | S2608MR0900A | 638 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357951 KB5960 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903357990-1 KB5965 | BLACK | 120D | S2608MR0900A | 451 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357990 KB5965 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358022-1 KB5965 | BLACK | 120D | S2608MR0900A | 347 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903358022 KB5965 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358074-1 KA0246 | BLACK | 105D | S2608WR0902 | 308 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903358074 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358100-1 KA0246 | BLACK | 105D | S2608WR0902 | 434 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903358100 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358700-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 121 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358700 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903358802-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903358802 KS1493 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903358865-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358865 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903359060-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903359060 HB7454 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903359114-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 207 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903359114 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903359674-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903359674-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903359721-1 KZ4389 | WHITE | 120D | F2608MR1500 | 1210 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903359721 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903360101-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 112 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 516342 | PRINT L2+HT SUB PROCESS_V3 | 0903360101 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903360696-1 KA0246 | BLACK | 105D | S2608WR0902 | 843 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360696 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360725-1 KA0246 | BLACK | 105D | S2608WR0902 | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360725 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360753-1 KA0246 | BLACK | 105D | S2608WR0902 | 360 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903360753 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360794-1 KA0246 | BLACK | 105D | S2608WR0902 | 388 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903360794 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360848-1 KA0246 | BLACK | 105D | S2608WR0902 | 1003 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360848 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360897-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 167 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903360897 LE8186 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903361050-1 LE8187 | BLACK | 105D | S2754MAS513 | 383 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361050 LE8187 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361129-1 LE8187 | BLACK | 105D | S2754MAS513 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361129 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361463-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 887 | 31/10/2026 | 887 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361463 KT7554 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | M CLUB AM TAT |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 887 |  | 887 |  |  | 19/10/2026 | 20/10/2026 | 46365 | 14/09/2026 | 887 | 862 | 25 |  | 850
ADIDAS | 0903361503-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 962 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361503 KF5311 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903361592-1 KB5960 | WHITE | 120D | S2608MR0900A | 1902 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361592 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903361661-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361661 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903361766-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 121 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361766 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903361907-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1504 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361907 KD7980 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903362010-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 237 | 31/10/2026 | 237 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903362010 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA | 46276 | M PANCAKE T OFF WHITE |  | SS27-STX | 46276 | 46276 |  |  | 237 |  | 237 |  |  | 46153 | 46153 |  |  | 237 |  | 237
ADIDAS | 0903362282-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 606 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903362282 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903363183-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363183 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363301-1 JZ7709 | BLACK | 120D | S2608MR0201 | 340 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363301 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363352-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5618 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363352 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363689-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 2740 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903363689 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903363740-1 KB5965 | BLACK | 120D | S2608MR0900A | 1741 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363740 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903363791-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 594 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363791 KX3655 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903363855-1 KA0235 | BLACK | 105D | S2608WR0901 | 320 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903363855 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903363897-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 641 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903363897 LG9670 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903363970-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 907 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903363970 KY6616 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903364196-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 150 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364196 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364257-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 190 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364257 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903364361-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 838103 | PRINT L1 SUB PROCESS_V3 | 0903364361 KC8559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903364417-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 367 | 31/10/2026 | 367 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903364417 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 367 |  | 367 |  |  | 14/10/2026 | 15/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903364462-1 IK7442 | WHITE | 105D | S2408WR2400 | 105 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903364462 IK7442 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903364491-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 127 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364491 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903364570-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903364570 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903364588-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364588 KU3270 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 702 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903364604 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903364991-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903364991 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903365054-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 112 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903365054 JW9678 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903365140-1 IS1413 | BLACK | 60D | S2425M405 | 241 | 31/10/2026 | 241 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903365140 IS1413 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 19/10/2026 | IN RANGE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 241 |  | 241 |  |  | 15/10/2026 | 16/10/2026 |  |  | 241 |  | 241
ADIDAS | 0903365207-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903365207 KA0237 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903365256-1 IP2310 | BLACK | 105D | S2450MTR701 | 500 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903365256 IP2310 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903365788-1 JZ7709 | BLACK | 120D | S2608MR0201 | 446 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365788 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903365824-1 JZ7709 | BLACK | 120D | S2608MR0201 | 308 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365824 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903366512-1 KX8877 | WHITE | 90D | S27GMGFX100 | 246 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903366512 KX8877 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903366592-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 5 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903366592 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903366641-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 110 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903366641 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903366658-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 678 | 46214 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903366658 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903366668-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 101 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366668 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366697-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 101 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366697 KU3272 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366738-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 115 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366738 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366756-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 140 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903366756 KB0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366796-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 106 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366796 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366871-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 408 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366871 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366982-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366982 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903367017-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 221 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903367017 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903367183-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1603 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367183 KD7980 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903367215-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 303 | 31/10/2026 | 303 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903367215 IU0217 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 303 |  | 303 |  |  | 14/10/2026 | 15/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903367252-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903367252 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903367284-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 339 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367284 KD7980 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903367328-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 277 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367328 KD3683 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903367372-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 417 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903367372 IT3474 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903367407-1 IK7442 | WHITE | 105D | S2408WR2400 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903367407 IK7442 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903367462-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903367462 IW8374 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903367498-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367498 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903367624-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 1464 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367624 KD3683 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903368244-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903368244 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903368309-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 460 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903368309 KG3234 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX
ADIDAS | 0903368357-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368357 JE6340 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903368397-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516205 | HT SUB PROCESS_V1 | 0903368397 JC9584 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903368443-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368443 JE6341 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903368477-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368477 JE6338 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903368508-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4599 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903368508 JE0052 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903368598-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903368598 JE6414 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903368689-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 150 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903368689 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903368737-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 2776 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368737 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368757-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903368757 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368774-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 367 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 672027 | HT SUB PROCESS_V1 | 0903368774 IN1159 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903368797-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 512108 | PAD+HT SUB PROCESS_V3 | 0903368797 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368816-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 1661 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368816 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368842-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 1006 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903368842 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903368857-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 2061 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368857 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368875-1 KZ4392 | WHITE | 120D | F2608WR1500 | 146 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903368875 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368890-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 838 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368890 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368903-1 KZ4392 | WHITE | 120D | F2608WR1500 | 126 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903368903 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368937-1 KZ4392 | WHITE | 120D | F2608WR1500 | 125 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 512106 | PAD+HT SUB PROCESS_V3 | 0903368937 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368963-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 323 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368963 IT1469 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903369687-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 123 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903369687 JW7182 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903369734-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903369734 IU0217 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903369828-1 IN2961 | BLACK | 105D | S2408WR2400 | 109 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369828 IN2961 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903369857-1 IK7442 | WHITE | 105D | S2408WR2400 | 132 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369857 IK7442 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903369980-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 279 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903369980 KD3676 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903370112-1 IS1413 | BLACK | 60D | S2425M405 | 109 | 31/10/2026 | 109 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903370112 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA | 19/10/2026 | IN RANGE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 109 |  | 109 |  |  | 15/10/2026 | 16/10/2026 |  |  | 109 |  | 109
ADIDAS | 0903370681-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 1380 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903370681 KA0247 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903370711-1 KA0235 | BLACK | 105D | S2608WR0901 | 327 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903370711 KA0235 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370723-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370723 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903370756-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903370756 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370771-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903370771 JW7178 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903370821-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 2100 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370821 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903370854-1 LF0718 | BLACK | 105D | S2754MAS512B | 547 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370854 LF0718 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903370911-1 LF0727 | BLACK | 120D | S2754MAS510B | 440 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370911 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903371005-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 124 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371005 JD5308 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903371033-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 4200 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903371033 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903371108-1 LF0727 | BLACK | 120D | S2754MAS510B | 126 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903371108 LF0727 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903371252-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371252 JE6377 |  | KAHATEX CIJERAH | PERU | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903371280-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (16/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371280 JE6374 |  | KAHATEX CIJERAH | PERU | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903371315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 310 | 31/10/2026 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371315 JE6372 |  | KAHATEX CIJERAH | PERU | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903371346-1 IC5188 | BLACK | 90D | S23080640 | 802 | 31/10/2026 | 802 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371346 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | OWN THE RUN TEE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 802 |  | 802 |  |  | 27/10/2026 | 28/10/2026 |  |  | 802 |  | 802 |  |  | 26/10/2026 | 27/10/2026 |  |  | 802 |  | 802
ADIDAS | 0903371391-1 IC5189 | WHITE | 90D | S23080640 | 601 | 31/10/2026 | 601 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371391 IC5189 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 46064 |  |  | 601 |  | 601 |  |  | 28/10/2026 | 30/10/2026 |  |  | 601 |  | 601 |  |  | 27/10/2026 | 29/10/2026 |  |  | 601 |  | 601
ADIDAS | 0903371424-1 IC5188 | BLACK | 90D | S23080640 | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371424 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/10/2026 | OWN THE RUN TEE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 301 |  | 301 |  |  | 26/10/2026 | 27/10/2026 |  |  | 301 |  | 301 |  |  | 24/10/2026 | 26/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903371738-1 IN1172 | BLACK | 105D | S2408WR1600 | 2072 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903371738 IN1172 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371825-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 42 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903371825 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903371852-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric (Mexico). T2 Y.T.I, PI Date 10-Jul, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903371852 IT1469 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371889-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 523 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT SUB PROCESS_V1 | 0903371889 KG8553 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903371934-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1088 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903371934 IN1156 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371971-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903371971 KC8152 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903372005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 389 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903372035-1 JC5948 | BLACK/WHITE | 90D | S2554WES428FT | 2021 | 31/10/2026 | 2021 | SA | SA31/07/2026 | G1A | PANTS | G1 | (12/09/2026) |  | (Mexico). 1st Art (TC 10 pcs) 652001 | PRINT L1 SUB PROCESS_V3 | 0903372035 JC5948 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 46214 | W LIN FT CF PT |  | SS27 | 46214 | 46306 |  |  | 2021 |  | 2021 |  |  | 46123 | 46184 |  |  | 2021 |  | 2021
ADIDAS | 0903372069-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 546 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep.ity LLT from FAR EASTERN (VNM), ETD: 12-Oct (DOL 30D). 652001 | HT SUB PROCESS_V1 | 0903372069 IN1157 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903372107-1 KA0246 | BLACK | 105D | S2608WR0902 | 460 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (Mexico). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903372107 KA0246 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903372134-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2083 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | (Mexico). 652001 | EMBRO SUB PROCESS_V1 | 0903372134 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372170-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 239 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903372170 IW8374 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903372668-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO SUB PROCESS_V1 | 0903372668 JD1881 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372707-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3168 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372707 JE6414 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372751-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2064 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO SUB PROCESS_V1 | 0903372751 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372792-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 1300 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372792 JD5308 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372825-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1328 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903372825 JF3604 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372860-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372860 JD5308 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372905-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 240 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | PRINT L1 SUB PROCESS_V3 | 0903372905 JF3604 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372932-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 959 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372932 JW7178 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903372940-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 3000 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372940 LE7510 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903372958-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 101 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372958 JE6414 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372970-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372970 JD5302 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372979-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 128 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903372979 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373000-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 3600 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903373000 LE5391 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27
ADIDAS | 0903373023-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 228 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373023 IN1156 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373044-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1200 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373044 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903373054-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 2400 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373054 LE7508 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903373065-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 193 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903373065 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373080-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 600 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373080 JE6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903373102-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373102 IN1157 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373109-1 KS7769 | WHITE/BLACK | 90D | S26AAWVL320 | 6000 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903373109 KS7769 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WHITE/BLACK |  | SS27
ADIDAS | 0903373141-1 HK7319 | BLACK | 90D | F2225M403 | 276 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 512102 | EMBRO+PPA SUB PROCESS_V3 | 0903373141 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903373455-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903373455 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903373496-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 115 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903373496 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903373659-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1680 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903373659 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903373718-1 LF0727 | BLACK | 120D | S2754MAS510B | 377 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373718 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903373722-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 1080 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 516318 | PAD+HT SUB PROCESS_V3 | 0903373722 KG3234 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX
ADIDAS | 0903373765-1 LF0718 | BLACK | 105D | S2754MAS512B | 326 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373765 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903373776-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 199 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903373776 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903373917-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1080 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516318 | HT SUB PROCESS_V1 | 0903373917 JC9584 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903373958-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2520 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903373958 HK7317 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903374005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4199 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903374005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903374083-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903374083 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 46305 | ESS TEE |  | SS27 | 46305 | 46366 |  |  | 600 |  | 600 |  |  | 46213 | 46244 |  |  | 600 |  | 600
ADIDAS | 0903374122-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3779 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903374122 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903374636-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 140 | 23/10/2026 | 140 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374636 LI2647 |  | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 140 |  | 140 |  |  | 16/10/2026 | 17/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903374698-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374698 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903374782-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374782 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903374792-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903374792 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903374832-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 684009 | HT+PAD SUB PROCESS_V3 | 0903374832 KB5965 |  | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903374867-1 KA0246 | BLACK | 105D | S2608WR0902 | 346 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516199 | PAD+HT SUB PROCESS_V3 | 0903374867 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374887-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 604 | 31/10/2026 | 604 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903374887 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46064 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46064 | 46123 |  |  | 604 |  | 604 |  |  | 29/10/2026 | 31/10/2026 |  |  | 604 |  | 604 |  |  | 28/10/2026 | 30/10/2026 |  |  | 604 |  | 604
ADIDAS | 0903374899-1 KA0246 | BLACK | 105D | S2608WR0902 | 451 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516400 | PAD+HT SUB PROCESS_V3 | 0903374899 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374900-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1505 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903374900 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374933-1 KG8547 | ONIX | 105D | S2408WR1600 | 442 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903374933 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374934-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 197 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 848012 | HT SUB PROCESS_V1 | 0903374934 IN1159 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374938-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 202 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374938 LI2667 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903374939-1 JZ7709 | BLACK | 120D | S2608MR0201 | 519 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374939 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903374951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 637 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903374951 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903374969-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1297 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903374969 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903374996-1 KA4331 | BLACK | 90D | S2608MR0902 | 321 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903374996 KA4331 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903375019-1 IL7232 | BLACK | 105D | S2408MR3202 | 1837 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903375019 IL7232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903375027-1 KT4839 | ONIX | 90D | S2408MR1601 | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 684009 | HT SUB PROCESS_V1 | 0903375027 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903375052-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 200 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903375052 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903375053-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 687 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903375053 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903375063-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516299 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375063 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375096-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 556 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903375096 KA2571 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903375109-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375109 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375126-1 KA0246 | BLACK | 105D | S2608WR0902 | 376 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903375126 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903375259-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 599 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375259 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | AFA DNA SHO |  | SS27-WC
ADIDAS | 0903375499-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 146 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375499 LG9661 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375527-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 128 | 31/10/2026 | 128 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | (12/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375527 JN1958 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46123 | W 3S FT QZ HD |  | SS27 | 46123 | 46153 |  |  | 128 |  | 128 |  |  | 31/10/2026 | 46064 |  |  | 128 |  | 128
ADIDAS | 0903375564-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 198 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375564 LI2647 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903375575-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 181 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848024 | HT SUB PROCESS_V1 | 0903375575 IN1157 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903375623-1 LF0723 | BLACK | 105D | S2754MAS511B | 126 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375623 LF0723 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903375654-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 720 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375654 HR8583 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375688-1 KA0235 | BLACK | 105D | S2608WR0901 | 140 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep.848012 | PAD+HT SUB PROCESS_V3 | 0903375688 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903375690-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1800 | 31/10/2026 | 1800 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375690 IB8686 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 46366 | ESS TEE |  | SS27 | 46366 | 14/10/2026 |  |  | 1800 |  | 1800 |  |  | 46244 | 46305 |  |  | 1800 |  | 1800
ADIDAS | 0903375714-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1800 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903375714 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903375724-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 111 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903375724 LE0357 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903375727-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1079 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375727 JE6338 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903375762-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 481 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375762 JE6417 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903375797-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375797 JE6340 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903375840-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375840 JN1948 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | W 3S FT QZ HD |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 600 |  | 600 |  |  | 26/10/2026 | 27/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903375907-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 719 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375907 HK7317 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375937-1 HK7319 | BLACK | 90D | F2225M403 | 720 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375937 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375980-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903375980 HK7317 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903376012-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 960 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376012 JE0055 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903376053-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376053 JN1948 |  | KAHATEX CIJERAH | SPAIN | SEA | 30/10/2026 | W 3S FT QZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 1151 |  | 1151 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903376092-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376092 JE1309 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903376133-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903376133 JV5068 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 919 |  | 919 |  |  | 46305 | 46366 |  |  | 919 |  | 919
ADIDAS | 0903376163-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 3358 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376163 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903376197-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 6300 | 31/10/2026 | 6300 | SA | SA31/07/2026 | G2O | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376197 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | ESS TEE |  | SS27 | 13/10/2026 | 21/10/2026 |  |  | 6300 |  | 6300 |  |  | 46275 | 17/10/2026 |  |  | 6300 |  | 6300
ADIDAS | 0903376238-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 200 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376238 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903376273-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 300 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376273 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903376325-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903376325 JV5069 |  | KAHATEX CIJERAH | GERMANY | SEA | 46366 | I ADIRAPTOR T |  | SS27 | 46366 | 14/10/2026 |  |  | 1680 |  | 1680 |  |  | 46244 | 46305 |  |  | 1680 |  | 1680
ADIDAS | 0903376368-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3359 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376368 JE0055 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903376414-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 361 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376414 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903376447-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 6033 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376447 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903376448-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1080 | 31/10/2026 | 1080 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376448 JN1958 |  | KAHATEX CIJERAH | GERMANY | SEA | 46153 | W 3S FT QZ HD |  | SS27 | 46153 | 46214 |  |  | 1080 |  | 1080 |  |  | 46064 | 46123 |  |  | 1080 |  | 1080
ADIDAS | 0903376486-1 LE8187 | BLACK | 105D | S2754MAS513 | 358 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903376486 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903376489-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2521 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376489 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903376520-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 400 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376520 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903376565-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 2099 | 31/10/2026 | 2099 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376565 JN1948 |  | KAHATEX CIJERAH | GERMANY | SEA | 46092 | W 3S FT QZ HD |  | SS27 | 46092 | 46153 |  |  | 2099 |  | 2099 |  |  | 30/10/2026 | 46064 |  |  | 2099 |  | 2099
ADIDAS | 0903376600-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 401 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376600 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903376639-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 2520 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516318 | PAD+HT SUB PROCESS_V3 | 0903376639 KA0247 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903377133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 412 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377133 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377184-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377184 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377216-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 552 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377216 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377256-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 555 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377256 KD0738 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377291-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 301 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377291 KV7863 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903377300-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 401 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377300 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377314-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377314 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903377338-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377338 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377349-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 645 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903377349 KX9855 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903377350-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 488 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric (Mexico). T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903377350 IN1173 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377363-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 155 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377363 JW7182 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903377379-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 330 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 684009 | PAD+HT SUB PROCESS_V3 | 0903377379 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903377398-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 756 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377398 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377403-1 KA4331 | BLACK | 90D | S2608MR0902 | 740 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903377403 KA4331 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903377412-1 IN1157 | WHITE | 105D | S2408MR1600 | 1894 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377412 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377437-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 729 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377437 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377443-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 975 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903377443 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377446-1 KG8547 | ONIX | 105D | S2408WR1600 | 569 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903377446 KG8547 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377470-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1907 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903377470 KX3654 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903377476-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377476 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377486-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 2013 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377486 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377510-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377510 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377530-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 463 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377530 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377539-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1560 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903377539 JG8642 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W LIN FT SHO |  | SS27
ADIDAS | 0903377545-1 IN1173 | WHITE | 105D | S2408WR1600 | 5142 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377545 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377583-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 381 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 650010 | HT SUB PROCESS_V1 | 0903377583 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903377598-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 540 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377598 KD0738 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 773 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377600 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377618-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377618 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377633-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1048 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377633 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377643-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903377643 LE0357 | 29/10/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903377670-1 LF0723 | BLACK | 105D | S2754MAS511B | 192 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377670 LF0723 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903377679-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377679 LG9661 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377733-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 1230 | 31/10/2026 | 1230 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903377733 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46184 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 46184 | 46306 |  |  | 1230 |  | 1230 |  |  | 46092 | 46184 |  |  | 1230 |  | 1230 |  |  | 46064 | 46153 |  |  | 1230 |  | 1230
ADIDAS | 0903377770-1 KA4331 | BLACK | 90D | S2608MR0902 | 1737 | 31/10/2026 | 1737 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903377770 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46306 | Run Ess 21 S M BLACK |  | SS27-TRAX | 46306 | 13/11/2026 |  |  | 1737 |  | 1737 |  |  | 46184 | 46306 |  |  | 1737 |  | 1737 |  |  | 46153 | 46276 |  |  | 1737 |  | 1737
ADIDAS | 0903377805-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 103 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903377805 KG8548 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377842-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 194 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903377842 KT4840 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377883-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 148 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377883 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377912-1 KG2951 | NIGHT NAVY | 90D | F2606CHRM009 | 70 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377912 KG2951 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | REAL DNA PNT |  | SS27
ADIDAS | 0903377939-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 120 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903377939 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903377983-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377983 LD6542 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903378020-1 LG9666 | BLACK | 120D | S2754WAS512C | 299 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903378020 LG9666 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903378068-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 680 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378068 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903378096-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 209 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903378096 KB5961 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903378136-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 214 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378136 KA6260 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903378176-1 IP2310 | BLACK | 105D | S2450MTR701 | 4001 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 New Wide, PI Date ?? 516318 | HT SUB PROCESS_V1 | 0903378176 IP2310 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903378225-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378225 JV5068 |  | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | I ADIRAPTOR T |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1680 |  | 1680 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903378242-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 506 | 31/10/2026 | 506 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903378242 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA | 46276 | M PANCAKE T OFF WHITE |  | SS27-STX | 46276 | 46276 |  |  | 506 |  | 506 |  |  | 46153 | 46153 |  |  | 506 |  | 506
ADIDAS | 0903378264-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 201 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378264 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903378295-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903378295 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903378350-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2940 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378350 JE1309 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903378390-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2519 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378390 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903378425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 200 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378425 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903378460-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 151 | 23/10/2026 | 151 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | (12/09/2026) |  | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378460 LI2671 |  | KAHATEX CIJERAH | ITALY | SEA | 46184 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 46184 | 46214 |  |  | 151 |  | 151 |  |  | 46092 | 46123 |  |  | 151 |  | 151
ADIDAS | 0903378462-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 3780 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378462 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378502-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1260 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378502 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903378534-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2520 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903378534 HR8583 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903378548-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 145 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903378548 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903378553-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 131 | 23/10/2026 | 131 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378553 LI2669 |  | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 131 |  | 131 |  |  | 15/10/2026 | 16/10/2026 |  |  | 131 |  | 131
ADIDAS | 0903378584-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1890 | 31/10/2026 | 1890 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378584 JV5067 |  | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | I ADIRAPTOR T |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 1890 |  | 1890 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1890 |  | 1890
ADIDAS | 0903378612-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378612 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378670-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 1200 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378670 JE0052 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903378707-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903378707 JV5067 |  | KAHATEX CIJERAH | SPAIN | SEA | 15/10/2026 | I ADIRAPTOR T |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 1036 |  | 1036 |  |  | 46366 | 13/10/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903378787-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903378787 IB8686 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | ESS TEE |  | SS27 | 14/10/2026 | 17/10/2026 |  |  | 3452 |  | 3452 |  |  | 46305 | 14/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903378816-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903378816 HR8583 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903378844-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 4140 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378844 JD5302 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378881-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 539 | 31/10/2026 | 539 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903378881 JV5067 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 539 |  | 539 |  |  | 46305 | 46366 |  |  | 539 |  | 539
ADIDAS | 0903378923-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 840 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378923 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903378952-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 719 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516204 | PAD+HT SUB PROCESS_V3 | 0903378952 KA0247 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903379058-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 719 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379058 JE6419 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903379129-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379129 JE6414 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903379176-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 197 | 31/10/2026 | 197 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379176 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 46337 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 46337 | 13/11/2026 |  |  | 197 |  | 197 |  |  | 46214 | 46306 |  |  | 197 |  | 197
ADIDAS | 0903379258-1 JZ7711 | BLACK | 120D | S2608MR0202 | 7018 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379258 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379297-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 392 | 46214 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379297 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379338-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 471 | 31/10/2026 | 471 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379338 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46337 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 46337 | 13/11/2026 |  |  | 471 |  | 471 |  |  | 46214 | 46306 |  |  | 471 |  | 471
ADIDAS | 0903379368-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 280 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379368 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903379415-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 324 | 31/10/2026 | 324 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379415 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46214 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 46214 | 46306 |  |  | 324 |  | 324 |  |  | 46123 | 46184 |  |  | 324 |  | 324
ADIDAS | 0903379458-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379458 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379480-1 JZ7711 | BLACK | 120D | S2608MR0202 | 369 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379480 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379565-1 JZ7711 | BLACK | 120D | S2608MR0202 | 4347 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379565 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379576-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 152 | 31/10/2026 | 152 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379576 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 46214 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 46214 | 46306 |  |  | 152 |  | 152 |  |  | 46123 | 46184 |  |  | 152 |  | 152
ADIDAS | 0903379646-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 470 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379646 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379658-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 1801 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 652001 | HT SUB PROCESS_V1 | 0903379658 IN1159 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903379677-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 362 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379677 IT1469 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379694-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903379694 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903379699-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 7027 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379699 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379735-1 KT4840 | ONIX | 105D | S2408MR1600 | 674 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 10-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379735 KT4840 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379743-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 127 | 31/10/2026 | 127 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 839055 | HT SUB PROCESS_V1 | 0903379743 IL4127 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 46064 | OWN THE RUN TEE |  | SS27 | 46064 | 46092 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 31/10/2026 |  |  | 127 |  | 127 |  |  | 29/10/2026 | 30/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903379774-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 1960 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379774 KB5961 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379820-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 304 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379820 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379841-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 548 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379841 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379843-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379843 KB5965 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379876-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379876 KX9855 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903379894-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 398 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379894 LD6542 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903379909-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 401 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379909 KG8548 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379942-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT SUB PROCESS_V1 | 0903379942 KT4839 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903379978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 108 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903379978 LD5446 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903380015-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 1104 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903380015 LD0907 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380044-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903380044 LD0278 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903380052-1 IC5189 | WHITE | 90D | S23080640 | 297 | 31/10/2026 | 297 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380052 IC5189 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 46064 |  |  | 297 |  | 297 |  |  | 28/10/2026 | 30/10/2026 |  |  | 297 |  | 297 |  |  | 27/10/2026 | 29/10/2026 |  |  | 297 |  | 297
ADIDAS | 0903380079-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 198 | 31/10/2026 | 198 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380079 IL4127 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 46064 | OWN THE RUN TEE |  | SS27 | 46064 | 46092 |  |  | 198 |  | 198 |  |  | 30/10/2026 | 31/10/2026 |  |  | 198 |  | 198 |  |  | 29/10/2026 | 30/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903380117-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903380117 KX9838 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903380177-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 169 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903380177 KB5965 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380268-1 KE8425 | WHITE | 120D | S2608MR0906A | 873 | 31/10/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903380268 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0903380349-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 501 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903380349 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903380384-1 KB5960 | WHITE | 120D | S2608MR0900A | 952 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380384 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380418-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 187 | 23/10/2026 | 187 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | (12/09/2026) |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380418 LI2646 |  | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 187 |  | 187 |  |  | 13/10/2026 | 13/10/2026 |  |  | 187 |  | 187
ADIDAS | 0903380454-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 154 | 23/11/2026 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380454 LI2645 |  | KAHATEX CIJERAH | ITALY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380455-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 398 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380455 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903380474-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 421 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903380474 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380477-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 228 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380477 LI2646 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903380507-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 180 | 23/10/2026 | 180 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380507 LI2667 |  | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 180 |  | 180 |  |  | 15/10/2026 | 16/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903380516-1 KT7552 | BLACK | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903380516 KT7552 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 46213 | SOC CAT GFX T BLACK |  | SS27 | 46213 | 46244 |  |  | 2099 |  | 2099 |  |  | 46091 | 46152 |  |  | 2099 |  | 2099
ADIDAS | 0903380597-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 15544 | 31/10/2026 | 15544 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380597 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/10/2026 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 14/10/2026 | 24/10/2026 |  |  | 15544 |  | 15544 |  |  | 46305 | 21/10/2026 |  |  | 15544 |  | 15544
ADIDAS | 0903380644-1 LI7744 | WHITE | 90D | F2606LEMPM107MF | 8870 | 31/10/2026 | 8870 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380644 LI7744 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 46091 | PSMM A JSY FAN WHITE |  | SS27-L2L | 46091 | 13/10/2026 |  |  | 8870 |  | 8870 |  |  | 30/09/2026 | 46275 |  |  | 8870 |  | 8870
ADIDAS | 0903380647-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 211 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380647 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380663-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 665 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380663 LI2645 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380681-1 HK7319 | BLACK | 90D | F2225M403 | 2519 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903380681 HK7319 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903380713-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903380713 IB8686 |  | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | ESS TEE |  | SS27 | 17/10/2026 | 22/10/2026 |  |  | 3452 |  | 3452 |  |  | 14/10/2026 | 19/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903380739-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903380739-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903380751-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 204 | 31/10/2026 | 204 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903380751 IL4127 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 46064 | OWN THE RUN TEE |  | SS27 | 46064 | 46092 |  |  | 204 |  | 204 |  |  | 30/10/2026 | 31/10/2026 |  |  | 204 |  | 204 |  |  | 29/10/2026 | 30/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903380774-1 LH2842 | BLACK | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380774 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903380795-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 1477 | 31/10/2026 | 1477 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380795 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 13/10/2026 | 14/10/2026 |  |  | 1477 |  | 1477 |  |  | 46275 | 46305 |  |  | 1477 |  | 1477
ADIDAS | 0903380833-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 828 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903380833 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903380843-1 KG3189 | MAROON | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903380843 KG3189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903380864-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 950 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380864 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380881-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 485 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380881 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380896-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380896 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46153 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 46153 | 46276 |  |  | 301 |  | 301 |  |  | 46064 | 46153 |  |  | 301 |  | 301
ADIDAS | 0903380897-1 IC5188 | BLACK | 90D | S23080640 | 226 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380897 IC5188 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380911-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380911 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903380935-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 185 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903380935 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903380960-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 196 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380960 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380966-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 407 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380966 KG3190 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903380993-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 154 | 31/10/2026 | 154 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380993 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 46064 | OWN THE RUN TEE |  | SS27 | 46064 | 46092 |  |  | 154 |  | 154 |  |  | 30/10/2026 | 31/10/2026 |  |  | 154 |  | 154 |  |  | 29/10/2026 | 30/10/2026 |  |  | 154 |  | 154
ADIDAS | 0903381023-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1724 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381023 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381034-1 LH2841 | OFF WHITE | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381034 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903381059-1 KT7550 | BLACK | 90D | F26FBGFXP103 | 1228 | 31/10/2026 | 1228 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903381059 KT7550 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | M MX LIFESTL T |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 1228 |  | 1228 |  |  | 14/10/2026 | 15/10/2026 |  |  | 1228 |  | 1228 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1228 |  | 1228
ADIDAS | 0903381100-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 104 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381100 LI2645 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381106-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381106 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381112-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 307 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381112 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903381143-1 LH2842 | BLACK | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381143 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903381150-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3678 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381150 JE0055 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903381183-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 479 | 31/10/2026 | 479 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381183 JV5068 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 479 |  | 479 |  |  | 46305 | 46305 |  |  | 479 |  | 479
ADIDAS | 0903381211-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | (12/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381211 JN1958 |  | KAHATEX CIJERAH | SPAIN | SEA | 46123 | W 3S FT QZ HD |  | SS27 | 46123 | 46153 |  |  | 460 |  | 460 |  |  | 31/10/2026 | 46064 |  |  | 460 |  | 460
ADIDAS | 0903381242-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381242 JE6417 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903381274-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903381274 JV5069 |  | KAHATEX CIJERAH | SPAIN | SEA | 46275 | I ADIRAPTOR T |  | SS27 | 46275 | 46305 |  |  | 919 |  | 919 |  |  | 46183 | 46213 |  |  | 919 |  | 919
ADIDAS | 0903381304-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381304 JE6419 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903381342-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 480 | 31/10/2026 | 480 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381342 JV5069 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 46244 | I ADIRAPTOR T |  | SS27 | 46244 | 46275 |  |  | 480 |  | 480 |  |  | 46152 | 46183 |  |  | 480 |  | 480
ADIDAS | 0903381645-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 1400 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381645 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA |  | UCH DNA PNT |  | SS27
ADIDAS | 0903381653-1 KD3875 | BLACK | 120D | S2608WR0201 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903381653 KD3875 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381685-1 JE6353 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS605FT | 1200 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903381685 JE6353 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903381700-1 KD3875 | BLACK | 120D | S2608WR0201 | 982 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903381700 KD3875 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381705-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 173 | 23/10/2026 | 173 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381705 LI2668 |  | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 173 |  | 173 |  |  | 15/10/2026 | 16/10/2026 |  |  | 173 |  | 173
ADIDAS | 0903381732-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 2104 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 1st Art (TC 10 pcs) 804028 | PRINT L1 SUB PROCESS_V3 | 0903381732 JE8969 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M BL FT PT |  | SS27
ADIDAS | 0903381751-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 798 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381751 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA |  | UCH DNA PNT |  | SS27
ADIDAS | 0903381776-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 1200 | 31/10/2026 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381776 JE6377 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903381784-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1091 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 1st Art (TC 10 pcs) 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381784 KG5347 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | COLO DNA PNT |  | SS27
ADIDAS | 0903381802-1 KD3875 | BLACK | 120D | S2608WR0201 | 2262 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903381802 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381815-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 532 | 31/10/2026 | 532 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381815 HK7311 |  | KAHATEX CIJERAH | CANADA | SEA | 46184 | ESS HDY |  | SS27 | 46184 | 46214 |  |  | 532 |  | 532 |  |  | 46092 | 46123 |  |  | 532 |  | 532
ADIDAS | 0903381817-1 KX8877 | WHITE | 90D | S27GMGFX100 | 337 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903381817 KX8877 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381829-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381829 KV7963 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903381848-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 732 | 31/10/2026 | 732 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381848 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA | 46214 | ESS HDY |  | SS27 | 46214 | 46276 |  |  | 732 |  | 732 |  |  | 46123 | 46153 |  |  | 732 |  | 732
ADIDAS | 0903381859-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 318 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381859 KA6260 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381892-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903381892 KX8877 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381904-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 304 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381904 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381912-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381912 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903381949-1 IN1156 | BLACK | 105D | S2408MR1600 | 434 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381949 IN1156 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381982-1 IN1157 | WHITE | 105D | S2408MR1600 | 1157 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381982 IN1157 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381985-1 LF0718 | BLACK | 105D | S2754MAS512B | 328 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516438 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903381985 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903382018-1 IN1172 | BLACK | 105D | S2408WR1600 | 512 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382018 IN1172 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382039-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382039 LD5446 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903382050-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903382050 KX3655 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382074-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 314 | 31/10/2026 | 314 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382074 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 46214 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 46214 | 46306 |  |  | 314 |  | 314 |  |  | 46123 | 46184 |  |  | 314 |  | 314
ADIDAS | 0903382087-1 IN1173 | WHITE | 105D | S2408WR1600 | 1019 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382087 IN1173 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382119-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 359 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382119 KX9855 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903382147-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 1601 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382147 KX3653 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903382178-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382178 KX3655 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382246-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 652 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903382246 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903382454-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 111 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903382454 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903382503-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 462 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903382503 IN0088 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903382642-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 117 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903382642 JW9678 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903382648-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 294 | 46214 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382648 LI2670 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903382670-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 293 | 46214 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382670 LI2671 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903382686-1 KA0235 | BLACK | 105D | S2608WR0901 | 325 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903382686 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382719 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903382747-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 315 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382747 LI2668 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903382753-1 LH5251 | WHITE/BLACK | 105D | F2654MESS614WVB | 402 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382753 LH5251 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 141S WV WB LND WHITE/BLACK |  | SS27
ADIDAS | 0903382780-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903382780 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382781-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 1902 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382781 KB5965 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382810-1 LG9675 | BLACK | 120D | S2754WAS513C | 420 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903382810 LG9675 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903382812-1 KB5960 | WHITE | 120D | S2608MR0900A | 454 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382812 KB5960 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382838-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 704 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382838 KB5961 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382866-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 496 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382866 KF5311 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903382881-1 KA0235 | BLACK | 105D | S2608WR0901 | 4 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903382881 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382905-1 KA0246 | BLACK | 105D | S2608WR0902 | 8 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903382905 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903382942-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 12 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382942 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382966-1 KG8547 | ONIX | 105D | S2408WR1600 | 70 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382966 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382983-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 4 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT SUB PROCESS_V1 | 0903382983 KG8553 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903383005-1 KD3875 | BLACK | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903383005 KD3875 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903383011-1 KZ4389 | WHITE | 120D | F2608MR1500 | 160 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848016 | PAD+HT SUB PROCESS_V3 | 0903383011 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903383028-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 8 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383028 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903383050-1 LG9669 | BLACK | 120D | S2754WAS514C | 58 | 30/11/2026 |  | ID | ID31/07/2026 |  | SKIRT |  | (20/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 20-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903383050 LG9669 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903383053-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 100 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903383053 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903383079-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 7 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383079 KD3854 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903383116-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 4 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903383116 LD0292 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383141-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 391 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903383141 KC8152 |  | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903383154-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 559 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383154 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903383170-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 325 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383170 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903383175-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383175 LI2669 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903383211-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 770 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383211 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383295-1 KT7539 | CARBON S18 | 60D | F26FBGFXP101 | 1225 | 31/10/2026 | 1225 | AN | AN31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903383295 KT7539 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 46214 | IN RANGE |  | SS27 | 46214 | 46276 |  |  | 1225 |  | 1225 |  |  | 46123 | 46153 |  |  | 1225 |  | 1225
ADIDAS | 0903383301-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383301 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383333-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383333 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383370-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 662 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT SUB PROCESS_V1 | 0903383370 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383385-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903383385 KA0237 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903383400-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT SUB PROCESS_V1 | 0903383400 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383551-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383551 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383580-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 400 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903383580 IT3474 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903383585-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383585 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383600-1 KA0235 | BLACK | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 800005 | PAD+HT SUB PROCESS_V3 | 0903383600 KA0235 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383614-1 KA0235 | BLACK | 105D | S2608WR0901 | 135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903383614 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383625-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 468 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383625 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383934-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903383934 LE8186 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903383985-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 306 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903383985 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903383996-1 JZ6293 | CREW BLUE S21 | 90D | S2606CHAG011-MTF | 361 | 31/10/2026 | 361 | AN | AN31/07/2026 | G1B | PANTS | G1 | (12/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903383996 JZ6293 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 46123 | AFA DNA PNT |  | SS27-WC | 46123 | 46153 |  |  | 361 |  | 361 |  |  | 31/10/2026 | 46064 |  |  | 361 |  | 361
ADIDAS | 0903384024-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 915 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 1st Art (TC 10 pcs) 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384024 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | AFA DNA SHO |  | SS27-WC
ADIDAS | 0903384058-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 323 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384058 LH4746 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903384078-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1972 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903384078 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 269 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384085 LD5446 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903384087-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 144 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903384087 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903384116-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 678002 | HT SUB PROCESS_V1 | 0903384116 IN1159 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384123-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 82 | 31/10/2026 | 82 | SI | SI31/07/2026 | G1L | T-SHIRT | G1 | (07/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903384123 LE8210 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 46153 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 46153 | 46153 |  |  | 82 |  | 82 |  |  | 46064 | 46064 |  |  | 82 |  | 82
ADIDAS | 0903384142-1 IN1157 | WHITE | 105D | S2408MR1600 | 823 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903384142 IN1157 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384205-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 490 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903384205 LD0294 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903384218-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 497 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903384218 LG9670 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903384240-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903384240 JG8642 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | W LIN FT SHO |  | SS27
ADIDAS | 0903384263-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 370 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903384263 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903384268-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 414 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT SUB PROCESS_V1 | 0903384268 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384290-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 348 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384290 KA6260 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903384300-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 710 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384300 KV7863 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903384315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384315 JE6372 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903384325-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384325 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384351-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 551 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384351 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384354-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 384 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903384354 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903384380-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903384380 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903384406-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT SUB PROCESS_V1 | 0903384406 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384429-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 124 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903384429 KX3713 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903384435-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903384435 LD0278 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903384461-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903384461 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384496-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 142 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384496 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903384565-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903384565 KX8877 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903384912-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1200 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384912 JW7178 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903384989-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1550 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | PRINT L1 SUB PROCESS_V3 | 0903384989 JF3604 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903384992-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 510 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903384992 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903385024-1 IP2310 | BLACK | 105D | S2450MTR701 | 295 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903385024 IP2310 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903385058-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 2298 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (03/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 03-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385058 JM1772 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903385133-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2433 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903385133 JE6338 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903385161-1 KG8547 | ONIX | 105D | S2408WR1600 | 2190 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385161 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385187-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 661 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385187 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385236-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2986 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385236 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385265-1 KT4839 | ONIX | 90D | S2408MR1601 | 356 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT SUB PROCESS_V1 | 0903385265 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903385289-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 4617 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385289 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903385346-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 2915 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385346 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385373-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 418 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385373 LD5446 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903385404-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903385404 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385460-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 20 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385460 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903385671-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903385671 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903385684-1 LC9640 | BLACK/SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385684 LC9640 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365 SHO M BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385716-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 598 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903385716 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385727-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 1635 | 31/10/2026 | 1635 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 838103 | PRINT L1+PAD SUB PROCESS_V3 | 0903385727 KY1335 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 46306 | M PANCAKE T OFF WHITE |  | SS27-STX | 46306 | 46337 |  |  | 1635 |  | 1635 |  |  | 46184 | 46214 |  |  | 1635 |  | 1635
ADIDAS | 0903385741-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 570 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385741 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903385764-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 669 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385764 LD0278 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903385785-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 202 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903385785 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385792-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 311 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385792 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385813-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385813 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903385818-1 KA0235 | BLACK | 105D | S2608WR0901 | 477 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 806020 | PAD+HT SUB PROCESS_V3 | 0903385818 KA0235 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903385840-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 452 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385840 LF9808 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385844-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 254 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903385844 LD0292 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385935-1 KX8877 | WHITE | 90D | S27GMGFX100 | 110 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903385935 KX8877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903385942-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 328 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903385942 IW8374 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903385970-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1400 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385970 KG5347 |  | KAHATEX CIJERAH | CHILE | SEA |  | COLO DNA PNT |  | SS27
ADIDAS | 0903385989-1 IS1413 | BLACK | 60D | S2425M405 | 598 | 31/10/2026 | 598 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903385989 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | IN RANGE |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 598 |  | 598 |  |  | 16/10/2026 | 16/10/2026 |  |  | 598 |  | 598
ADIDAS | 0903386004-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 479 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386004 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903386008-1 KA0235 | BLACK | 105D | S2608WR0901 | 450 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 960006 | PAD+HT SUB PROCESS_V3 | 0903386008 KA0235 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386021-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386021 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386035-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 672 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903386035 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903386059-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 305 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 680015 | HT SUB PROCESS_V1 | 0903386059 KT4840 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386078-1 IN2961 | BLACK | 105D | S2408WR2400 | 201 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903386078 IN2961 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903386079-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 684009 | PAD+HT SUB PROCESS_V3 | 0903386079 LD0278 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903386106-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 300 | 31/10/2026 | 300 | AN | AN31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386106 LF1392 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 46306 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 46306 | 46367 |  |  | 300 |  | 300 |  |  | 46184 | 46276 |  |  | 300 |  | 300
ADIDAS | 0903386109-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 180 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386109 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903386123-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 304 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386123 KV7863 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386130-1 LH2842 | BLACK | 90D | S2725M993 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386130 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386150-1 LC6341 | BLACK | 90D | S27GMGFX130 | 368 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903386150 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903386183-1 IN1173 | WHITE | 105D | S2408WR1600 | 1024 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386183 IN1173 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386195-1 KT7553 | WHITE | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903386195 KT7553 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 46244 | SOC CAT GFX T WHITE |  | SS27 | 46244 | 46305 |  |  | 2099 |  | 2099 |  |  | 46152 | 46213 |  |  | 2099 |  | 2099
ADIDAS | 0903386198-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 149 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386198 LE8186 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903386216-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 1447 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386216 IN1172 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386221-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 518 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386221 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386246-1 IS1413 | BLACK | 60D | S2425M405 | 385 | 31/10/2026 | 385 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903386246 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 19/10/2026 | IN RANGE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 385 |  | 385 |  |  | 15/10/2026 | 16/10/2026 |  |  | 385 |  | 385
ADIDAS | 0903386253-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 171 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386253 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903386264-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386264 KD3683 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386278-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386278 IT1469 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386299-1 KA0235 | BLACK | 105D | S2608WR0901 | 510 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386299 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386301-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 659 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386301 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386304-1 KA0235 | BLACK | 105D | S2608WR0901 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903386304 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386327-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 666 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386327 KV7963 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386328-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386328 KB5961 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 680 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516462 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386331 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386337-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 170 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386337 LH4746 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903386348-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386348 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386352-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386352 KV7963 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386355-1 KB5960 | WHITE | 120D | S2608MR0900A | 371 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386355 KB5960 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386369-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903386369 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386372-1 IP2310 | BLACK | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903386372 IP2310 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903386387-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 435 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386387 KB5965 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386391-1 KG3189 | MAROON | 120D | S2608MR0900A | 400 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903386391 KG3189 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903386400-1 KE8425 | WHITE | 120D | S2608MR0906A | 718 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903386400 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0903386413-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386413 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903386435-1 KD3875 | BLACK | 120D | S2608WR0201 | 358 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386435 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903386485-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 104 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386485 JD9944 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903386490-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386490 KE8424 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903386521-1 KA0235 | BLACK | 105D | S2608WR0901 | 305 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386521 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386556-1 KA0246 | BLACK | 105D | S2608WR0902 | 393 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386556 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903386589-1 KT4840 | ONIX | 105D | S2408MR1600 | 405 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386589 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386620-1 KA4331 | BLACK | 90D | S2608MR0902 | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386620 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903386672-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 2749 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386672 JE6346 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386736-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386736 JW7182 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903386775-1 HK7319 | BLACK | 90D | F2225M403 | 2400 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | 804028 | EMBRO+PPA SUB PROCESS_V3 | 0903386775 HK7319 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903386782-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 988 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386782 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386825-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 3178 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386825 JD1881 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386860-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2230 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386860 JD1877 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903386863-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 434 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386863 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386894-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 103 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903386894 KS1493 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903386898-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 1250 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386898 JD7999 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903386936-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386936 JE6419 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903386983-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386983 JE6340 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903387009-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 889 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903387009 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903387028-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2037 | 46214 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387028 JE6374 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387071-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2557 | 46214 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387071 JE6372 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387109-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1289 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387109 JE6414 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903387118-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 498 | 46214 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387118 JE0052 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903387166-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 37 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387166 LG9663 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387197-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 39 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903387197 LG9672 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387223-1 LD0291 | HAZE CORAL S17 | 105D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903387223 LD0291 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903387244-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387244 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387271-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 71 | 31/10/2026 | 71 | SA | SA31/07/2026 | G1B | SHORTS | G1 |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Men Chuen, PI Date ?? 547012 | HT SUB PROCESS_V1 | 0903387271 KX9851 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 46092 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 46092 | 46123 |  |  | 71 |  | 71 |  |  | 31/10/2026 | 46064 |  |  | 71 |  | 71 |  |  | 30/10/2026 | 31/10/2026 |  |  | 71 |  | 71
ADIDAS | 0903387298-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 75 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387298 LF0725 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903387336-1 HK7319 | BLACK | 90D | F2225M403 | 500 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 547012 | EMBRO+PPA SUB PROCESS_V3 | 0903387336 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903387369-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387369 JE6340 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903387372-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 156 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387372 LH4744 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903387402-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387402 JE6414 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903387487-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516442 | HT SUB PROCESS_V1 | 0903387487 JC9584 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903387523-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903387523 HR8583 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903387560-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903387560 JV5067 |  | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | I ADIRAPTOR T |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 1036 |  | 1036 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903387602-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387602 JE6417 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903387607-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? Waiting fabric (NYK warehuose). T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387607 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903387638-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387638 JE6341 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903387643-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387643 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903387726-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 567 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387726 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903387764-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387764 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903387868-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 111 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903387868 LG9670 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387903-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387903 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903387928-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 204 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903387928 KA5090 | 16/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903387962-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387962 KY6616 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388016-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 410 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388016 LD6542 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388052-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 450 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388052 KY6616 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388124-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 162 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388124 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388131-1 IC5189 | WHITE | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903388131 IC5189 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 46064 |  |  | 217 |  | 217 |  |  | 28/10/2026 | 30/10/2026 |  |  | 217 |  | 217 |  |  | 27/10/2026 | 29/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903388178-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903388178 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388195-1 KA4331 | BLACK | 90D | S2608MR0902 | 397 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903388195 KA4331 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903388205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2641 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388205 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388219-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 571 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903388219 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903388238-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 1347 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903388238 KX9855 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388262-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 1134 | 15/11/2026 |  | AN | AN31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388262 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388290-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 1800 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388290 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388317-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1096 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388317 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903388347-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 511 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 678002 | PRINT L2+PAD SUB PROCESS_V3 | 0903388347 LC8884 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903388375-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 1000 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903388375 LD0292 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388403-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388403 KX8875 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903388415-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 823 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903388415 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388432-1 KX8877 | WHITE | 90D | S27GMGFX100 | 416 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388432 KX8877 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903388455-1 LC6341 | BLACK | 90D | S27GMGFX130 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388455 LC6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903388488-1 KX8877 | WHITE | 90D | S27GMGFX100 | 42 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903388488 KX8877 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903388544-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 773 | 31/10/2026 | 773 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388544 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 46337 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 46337 | 13/11/2026 |  |  | 773 |  | 773 |  |  | 46214 | 46306 |  |  | 773 |  | 773 |  |  | 46184 | 46276 |  |  | 773 |  | 773
ADIDAS | 0903388567-1 KA4331 | BLACK | 90D | S2608MR0902 | 1066 | 31/10/2026 | 1066 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903388567 KA4331 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 46153 | Run Ess 21 S M BLACK |  | SS27-TRAX | 46153 | 46184 |  |  | 1066 |  | 1066 |  |  | 46064 | 46092 |  |  | 1066 |  | 1066 |  |  | 31/10/2026 | 46064 |  |  | 1066 |  | 1066
ADIDAS | 0903388591-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 770 | 31/10/2026 | 770 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388591 LD0277 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 46123 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46123 | 46184 |  |  | 770 |  | 770 |  |  | 31/10/2026 | 46092 |  |  | 770 |  | 770 |  |  | 30/10/2026 | 46064 |  |  | 770 |  | 770
ADIDAS | 0903388611-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 158 | 31/10/2026 | 158 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903388611 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 46123 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 46123 | 46184 |  |  | 158 |  | 158 |  |  | 31/10/2026 | 46092 |  |  | 158 |  | 158 |  |  | 30/10/2026 | 46064 |  |  | 158 |  | 158
ADIDAS | 0903388629-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903388629 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388672-1 IC5188 | BLACK | 90D | S23080640 | 473 | 31/10/2026 | 473 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903388672 IC5188 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/10/2026 | OWN THE RUN TEE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 473 |  | 473 |  |  | 26/10/2026 | 27/10/2026 |  |  | 473 |  | 473 |  |  | 24/10/2026 | 26/10/2026 |  |  | 473 |  | 473
ADIDAS | 0903388692-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 104 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903388692 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903388696-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903388696 KX3654 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388713-1 KA0246 | BLACK | 105D | S2608WR0902 | 133 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 547012 | PAD+HT SUB PROCESS_V3 | 0903388713 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903388719-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 261 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903388719 KX3654 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388738-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 10 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 547012 | PAD+HT SUB PROCESS_V3 | 0903388738 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388755-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1160 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388755 KX3654 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388767-1 JZ7711 | BLACK | 120D | S2608MR0202 | 266 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388767 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903388782-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 482 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388782 KX3655 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903388797-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 183 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903388797 KE8424 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903388840-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 110 | 31/10/2026 | 110 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388840 KW2909 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 46276 | W 3S WV WB BLACK/WHITE |  | SS27 | 46276 | 46276 |  |  | 110 |  | 110 |  |  | 46153 | 46153 |  |  | 110 |  | 110
ADIDAS | 0903388850-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 130 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388850 KX9855 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388859-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 492 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903388859 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388861-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 116 | 31/10/2026 | 116 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388861 KW2909 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 46276 | W 3S WV WB BLACK/WHITE |  | SS27 | 46276 | 46276 |  |  | 116 |  | 116 |  |  | 46153 | 46153 |  |  | 116 |  | 116
ADIDAS | 0903388867-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 646 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903388867 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903388876-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 130 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388876 KX9838 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903388878-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 910 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388878 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903388888-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 166 | 31/10/2026 | 166 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388888 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 13/11/2026 | 14/11/2026 |  |  | 166 |  | 166 |  |  | 46306 | 46337 |  |  | 166 |  | 166
ADIDAS | 0903388890-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 430 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388890 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388903-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 150 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388903 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388910-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 380 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903388910 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903388929-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 125 | 31/10/2026 | 125 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388929 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 13/11/2026 | 14/11/2026 |  |  | 125 |  | 125 |  |  | 46306 | 46337 |  |  | 125 |  | 125
ADIDAS | 0903388942-1 KG3189 | MAROON | 120D | S2608MR0900A | 800 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903388942 KG3189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903388957-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 795 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388957 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903388990-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 10048 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388990 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 321 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389019 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903389062-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 477 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389062 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389159-1 IL7232 | BLACK | 105D | S2408MR3202 | 105 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389159 IL7232 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903389360-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 1000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903389360 KB5966 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903389399-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 419 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389399 KD3676 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903389461-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 599 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389461 IT3474 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903389493-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 737 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903389493 IW8374 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903389597-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 229 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389597 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903389635-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 447 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903389635 IN0089 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903389677-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | (12/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389677 JN1958 |  | KAHATEX CIJERAH | ITALY | SEA | 46123 | W 3S FT QZ HD |  | SS27 | 46123 | 46153 |  |  | 460 |  | 460 |  |  | 31/10/2026 | 46064 |  |  | 460 |  | 460
ADIDAS | 0903389747-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903389747 JE6338 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903389788-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903389788 JV5068 |  | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | I ADIRAPTOR T |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 919 |  | 919 |  |  | 46366 | 13/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903389845-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 460 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 516442 | PAD+HT SUB PROCESS_V3 | 0903389845 KG3234 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX
ADIDAS | 0903389891-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389891 JN1948 |  | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 46092 |  |  | 1151 |  | 1151 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903389932-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389932 HK7319 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903389964-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903389964 JE1309 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903389996-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389996 HK7317 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903390024-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903390024 JE6419 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903390063-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903390063 JV5069 |  | KAHATEX CIJERAH | ITALY | SEA | 46305 | I ADIRAPTOR T |  | SS27 | 46305 | 46366 |  |  | 919 |  | 919 |  |  | 46213 | 46244 |  |  | 919 |  | 919
ADIDAS | 0903390099-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390099 JW7178 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903390166-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903390166 KE8420 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903390198-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 377 | 31/10/2026 | 377 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903390198 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 46337 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 46337 | 13/11/2026 |  |  | 377 |  | 377 |  |  | 46214 | 46306 |  |  | 377 |  | 377 |  |  | 46184 | 46276 |  |  | 377 |  | 377
ADIDAS | 0903390226-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 104 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903390226 KA6260 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903390359-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903390359 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903390384-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 503 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390384 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903390534-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1795 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390534 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390588-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 642 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390588 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390685-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903390685 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903390730-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390730 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903390768-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 233 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390768 JD5302 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903390802-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390802 KA5090 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903390837-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 106 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390837 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903390896-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903390896 KB5966 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903390966-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390966 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903391007-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391007 KD3684 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903391036-1 KE9870 | BLACK | 105D | S2650MTR809B | 332 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903391036 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903391094-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 119 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391094 JD1881 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903391146-1 HK7319 | BLACK | 90D | F2225M403 | 1122 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903391146 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903391179-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 1026 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391179 KX8875 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391201-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 102 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391201 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391209-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 1170 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391209 LC6339 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391240-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1356 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903391240 IN0088 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391266-1 HK7319 | BLACK | 90D | F2225M403 | 900 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848024 | EMBRO+PPA SUB PROCESS_V3 | 0903391266 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903391298-1 IL7232 | BLACK | 105D | S2408MR3202 | 1512 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391298 IL7232 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903391321-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1080 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391321 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391350-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 972 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391350 LC6339 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391401-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 864 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391401 KX8875 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391415-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 604 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391415 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903391436-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1080 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391436 LC6341 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903391467-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 235 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391467 LH4744 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903391494-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 826 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391494 KY4221 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391497-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 565 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391497 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903391498-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 181 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391498 KY4221 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391515-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 102 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391515 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391521-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 190 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 512114 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391521 JW7182 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903391525-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 339 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391525 KY4221 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391590-1 KE8424 | BLACK | 120D | S2608MR0906A | 694 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391590 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903391595-1 IN1156 | BLACK | 105D | S2408MR1600 | 353 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT SUB PROCESS_V1 | 0903391595 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391613-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 873 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391613 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903391682-1 IC5188 | BLACK | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903391682 IC5188 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 29/10/2026 | OWN THE RUN TEE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 217 |  | 217 |  |  | 27/10/2026 | 28/10/2026 |  |  | 217 |  | 217 |  |  | 26/10/2026 | 27/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903391828-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903391828 LD0908 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903392043-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 650 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903392043 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903392090-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 374 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903392090 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903392151-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 1380 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516442 | PAD+HT SUB PROCESS_V3 | 0903392151 KA0247 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903392177-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903392177 JD1877 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903392298-1 KB5965 | BLACK | 120D | S2608MR0900A | 1240 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903392298 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903392317-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 303 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903392317 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903392343-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 315 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903392343 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903392385-1 KA0235 | BLACK | 105D | S2608WR0901 | 602 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903392385 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903393666-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 216 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393666 KY6616 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393674-1 KE8424 | BLACK | 120D | S2608MR0906A | 1120 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903393674 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903393700-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393700 KY6616 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393729-1 LG9666 | BLACK | 120D | S2754WAS512C | 301 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393729 LG9666 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903393736-1 KW5050 | MAROON | 90D | F2625M101 | 104 | 46214 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393736 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393740-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 600 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393740 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903393756-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 176 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393756 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903393785-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 8427 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903393785 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903393789-1 KW5050 | MAROON | 90D | F2625M101 | 1832 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393789 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393794-1 LG9675 | BLACK | 120D | S2754WAS513C | 277 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903393794 LG9675 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903393812-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 579 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393812 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903393816-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 104 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393816 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393839-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 500 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393839 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903393853-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 936 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393853 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393868-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 219 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393868 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903393909-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1153 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393909 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903393950-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 109 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903393950 KB5966 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903394317-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 250 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394317 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394379-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 183 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903394379 KB0235 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903394471-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 240 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394471 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903394497-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 956 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394497 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903394744-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 509 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903394744 JF3604 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903394844-1 KA4331 | BLACK | 90D | S2608MR0902 | 1140 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394844 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903394868-1 KA4331 | BLACK | 90D | S2608MR0902 | 1142 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394868 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903394896-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394896 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903394920-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394920 KA5090 |  | KAHATEX CIJERAH | CANADA | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903395342-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 509 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903395342 KA6260 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903395364-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 481 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395364 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395391-1 IN1173 | WHITE | 105D | S2408WR1600 | 1079 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903395391 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395411-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 333 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395411 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395435-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 477 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903395435 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395456-1 KA4331 | BLACK | 90D | S2608MR0902 | 424 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903395456 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903395478-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 370 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 672027 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903395478 JD1877 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903395497-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 455 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395497 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903395527-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 172 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395527 LC6339 |  | KAHATEX CIJERAH | ITALY | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903395560-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 434 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395560 LD0292 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903395581-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 1983 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395581 LD0277 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903395611-1 KX8877 | WHITE | 90D | S27GMGFX100 | 210 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395611 KX8877 |  | KAHATEX CIJERAH | ITALY | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903395619-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 832 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395619 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903395640-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 432 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903395640 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903396155-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 204 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903396155 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903396318-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 304 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396318 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | K BLANK TEE |  | SS27
ADIDAS | 0903396350-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric (NYK warehouse). T2 New Wide, PI Date 11-Sep. 800005 | HT SUB PROCESS_V1 | 0903396350 IN2961 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903397029-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 475 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397029 KE8424 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903397047-1 KG8547 | ONIX | 105D | S2408WR1600 | 347 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397047 KG8547 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397069-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 892 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397069 KG8548 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397096-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 461 | 30/10/2026 | 461 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903397096 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 28/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 461 |  | 461 |  |  | 26/10/2026 | 27/10/2026 |  |  | 461 |  | 461 |  |  | 24/10/2026 | 26/10/2026 |  |  | 461 |  | 461
ADIDAS | 0903397121-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA31/07/2026 | G1C | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903397121 KT4839 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903397145-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 442 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397145 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397664-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903397664 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903397668-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 460 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397668 KX3655 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903397694-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903397694-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903397701-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 2364 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397701 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903397762-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1097 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903397762 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903397793-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1335 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397793 KF5311 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903397808-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 105 | 31/10/2026 | 105 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903397808 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 46064 | OWN THE RUN TEE |  | SS27 | 46064 | 46092 |  |  | 105 |  | 105 |  |  | 30/10/2026 | 31/10/2026 |  |  | 105 |  | 105 |  |  | 29/10/2026 | 30/10/2026 |  |  | 105 |  | 105
ADIDAS | 0903397824-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 1062 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397824 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903397854-1 KA4331 | BLACK | 90D | S2608MR0902 | 1280 | 31/10/2026 | 1280 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903397854 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 46214 | Run Ess 21 S M BLACK |  | SS27-TRAX | 46214 | 46306 |  |  | 1280 |  | 1280 |  |  | 46123 | 46184 |  |  | 1280 |  | 1280 |  |  | 46092 | 46153 |  |  | 1280 |  | 1280
ADIDAS | 0903397858-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 434 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903397858 LE7650 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903397879-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397879 KB5965 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903397901-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 3558 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903397901 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903397924-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 566 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903397924 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903397937-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 304 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903397937 KU0090 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903397945-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903397945 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903397973-1 LG9675 | BLACK | 120D | S2754WAS513C | 613 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903397973 LG9675 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903397998-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 406 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397998 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903398085-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 114 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398085 JD9944 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903398113-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398113 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398140-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398140 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398370-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 129 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398370 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903398417-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 341 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398417 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398667-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 609 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398667 KV7863 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398692-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 827 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398692 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903398713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 685 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398713 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903398767-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 796 | 31/10/2026 | 796 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903398767 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 46153 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 46153 | 46276 |  |  | 796 |  | 796 |  |  | 46064 | 46153 |  |  | 796 |  | 796
ADIDAS | 0903399989-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 365 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903399989 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400022-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903400022 KY6510 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400198-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 102 | 31/10/2026 | 102 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903400198 IU0217 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 102 |  | 102 |  |  | 14/10/2026 | 14/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903400227-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400227 IW8374 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903400251-1 IN2961 | BLACK | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400251 IN2961 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903400316-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 121 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400316 HB7454 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903400396-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400396 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903400450-1 IK7442 | WHITE | 105D | S2408WR2400 | 149 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400450 IK7442 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903400498-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 200 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903400498 KD3676 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903400562-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 839055 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903400562 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903400617-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 142 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400617 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903400639-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903400639-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903401786-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401786 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903401814-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 161 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401814 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903401845-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 402 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903401845 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903402717-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 118 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903402717 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903402796-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | PRINT L1 SUB PROCESS_V3 | 0903402796 KC8559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903408401-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408401 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408420-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408420 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408450-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516462 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408450 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408471-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 710 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408471 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903444660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 2974 | 15/11/2026 |  | SA | SA04/08/2026 |  | PANTS |  | (15/10/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903444660 LE8181 | 46064 | KAHATEX CIJERAH | INDIA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903450147-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 98 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450147 KC9082 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450151-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450151 KC9082 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450968-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450968 IN1159 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27
ADIDAS | 0903450969-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 26 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450969 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450970-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 350 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450970 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450971-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 65 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450971 IN1159 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27
ADIDAS | 0903450972-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903450972 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903452885-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452885 KA6229 | 46367 | KAHATEX CIJERAH | PERU | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452887-1 KA6229 | BLACK | 120D | S2608WR0202 | 312 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452887 KA6229 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452891-1 KA6229 | BLACK | 120D | S2608WR0202 | 6 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | (Mexico). 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452891 KA6229 | 46367 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903466285-1 IC5188 | BLACK | 90D | S23080640 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903466285 IC5188 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903467966-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903467966 HK7319 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468003-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903468003 HR8583 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468058-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903468058 HK7319 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470160-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903470160 HR8583 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470333-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903470333 JE6374 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903470449-1 HK7309 | BLACK | 45D | F2225M402 | 5500 | 46214 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903470449 HK7309 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903473017-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 719 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903473017 JM1775 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903473064-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903473064 JP1528 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903473120-1 JF3606 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS675FT | 6350 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903473120 JF3606 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903473549-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 18 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903473549 KZ0028 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903473588-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 547012 | EMBRO SUB PROCESS_V1 | 0903473588 KW6443 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903473952-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1601 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903473952 IU0217 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903475746-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475746 KZ3200 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903475786-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 100 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903475786 KY1333 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903475858-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903475858 JP1527 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903475913-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475913 JM1776 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903475934-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 1139 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903475934 KW8936 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903475971-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475971 JM1776 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903476015-1 LC9621 | OFF WHITE | 90D | S2725M920 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1 SUB PROCESS_V3 | 0903476015 LC9621 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903476030-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903476030 JP1527 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903476078-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476078 JM1776 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903476096-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 510 | 30/11/2026 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903476096 KW9040 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903476131-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903476131 KA0247 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903476137-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 612 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903476137 LE1842 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476381-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 350 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903476381 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903476426-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903476426 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476607-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903476607 JC9584 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903476632-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 198 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903476632 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476637-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903476637 LE1842 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476845-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 2000 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (08/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903476845 IN0089 |  | KAHATEX CIJERAH | ITALY | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903476874-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 721 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476874 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903478198-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478198 LI7656 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478236-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 1502 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478236 KA4913 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478237-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 206 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478237 LI5438 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478279-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 628 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478279 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478284-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 224 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903478284 LC8943 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903478311-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478311 JE6372 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903478324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 351 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478347-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903478347 KD3936 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903478377-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478377 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478385-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478385 LJ4074 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478389-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478389 KF6290 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903478417-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478417 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478424-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 229 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478424 LI7658 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478453-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 1000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478453 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478482-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 150 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478482 LI7659 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903478521-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 406 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478521 LI7655 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903478661-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 347 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903478661 JG8639 |  | KAHATEX CIJERAH | PERU | SEA |  | W LIN FT SHO |  | SS27
ADIDAS | 0903478686-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903478686 LE1843 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478689-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 208 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903478689 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903478720-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903478720 LI5438 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478739-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1198 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478739 LE8181 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478862-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903478862 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903478906-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 533 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478906 LE8181 | 46367 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478960-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 150 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903478960 LE8189 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903479028-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 145 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903479028 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903479034-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 146 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479034 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479063-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903479063 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903479077-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 133 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903479077 LD0293 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903479108-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 118 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903479108 IL4127 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903479120-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903479120 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903479186-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 3000 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO SUB PROCESS_V1 | 0903479186 JD7999 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903479239-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479239 JM1775 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479287-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479287 JP1528 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903479546-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479546 JM1775 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479588-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479588 JP1527 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903480160-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 113 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 547012 | PAD+HT SUB PROCESS_V3 | 0903480160 LD0293 | 46367 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903480272-1 HZ0747 | BLACK | 90D | F2325M414 | 970 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | EMBRO SUB PROCESS_V1 | 0903480272 HZ0747 |  | KAHATEX CIJERAH | CANADA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903480348-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 714 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480348 JE0055 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903480517-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 378 | 23/10/2026 | 378 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848016 | PRINT L3 SUB PROCESS_V3 | 0903480517 IU0217 |  | KAHATEX CIJERAH | MOROCCO | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 378 |  | 378 |  |  | 14/10/2026 | 14/10/2026 |  |  | 378 |  | 378
ADIDAS | 0903480652-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 543 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480652 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903480678-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903480678 KD3936 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480715-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903480715 KD3936 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480819-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 135 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480819 IN1156 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480875-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 195 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903480875 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903480915-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 117 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480915 IN1157 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480916-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480916 KF6290 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903480931-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480931 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903480973-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480973 IN1172 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903481002-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 46214 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481002 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903481003-1 KG2491 | ACTIVE MAROON F19 | 90D | F2606CHLF011 | 40 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 814006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481003 KG2491 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC DNA SHO |  | SS27
ADIDAS | 0903481051-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 600 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903481051 KG8548 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903481052-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481052 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903481119-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 1390 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903481119 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903481123-1 KA0235 | BLACK | 105D | S2608WR0901 | 668 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 680015 | PAD+HT SUB PROCESS_V3 | 0903481123 KA0235 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903481315-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 138 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481315 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903481374-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 5000 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903481374 JW7182 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903481398-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903481398 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903481585-1 KT7395 | AURORA IVY F25 | 90D | F2625M101 | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903481585 KT7395 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE AURORA IVY F25 |  | SS27-L2L
ADIDAS | 0903481635-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 102 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903481635 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903481790-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481790 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903482152-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 680015 | HT+PAD SUB PROCESS_V3 | 0903482152 KB5964 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903482200-1 IN1159 | BLACK | 90D | S2408MR1601 | 23 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT SUB PROCESS_V1 | 0903482200 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482201-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482201 JM1779 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903482233-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 684009 | HT SUB PROCESS_V1 | 0903482233 KD9849 |  | KAHATEX CIJERAH | PERU | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903482238-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT SUB PROCESS_V1 | 0903482238 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482281-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482281 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482305-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 239 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903482305 LF0725 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903482323-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482323 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482414-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 6500 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903482414 JF3604 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903482462-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 600 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903482462 KF6290 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903482511-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903482511 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482561-1 HK7319 | BLACK | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903482561 HK7319 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482623-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 3781 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903482623 HK7317 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483208-1 IN1173 | WHITE | 105D | S2408WR1600 | 968 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483208 IN1173 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483311-1 KA4331 | BLACK | 90D | S2608MR0902 | 1048 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 680015 | PAD+HT SUB PROCESS_V3 | 0903483311 KA4331 |  | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903483320-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903483320 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483346-1 IN8707 | BLACK | 105D | S2408WR1601A | 580 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903483346 IN8707 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483384-1 IN1156 | BLACK | 105D | S2408MR1600 | 968 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903483384 IN1156 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483459-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 680015 | HT SUB PROCESS_V1 | 0903483459 IN1159 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483478-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903483478 HK7317 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483493-1 IN1172 | BLACK | 105D | S2408WR1600 | 948 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483493 IN1172 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483511-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903483511 HK7317 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483584-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903483584 KD3911 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483676-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 830009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483676 JM1775 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903483703-1 IP2310 | BLACK | 105D | S2450MTR701 | 330 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 830009 | HT SUB PROCESS_V1 | 0903483703 IP2310 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903483721-1 HZ0747 | BLACK | 90D | F2325M414 | 393 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483721 HZ0747 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PL TEE |  | SS27
ADIDAS | 0903483722-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 104 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483722 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903483757-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 226 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483757 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903483798-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 300 | 46214 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903483798 KA5089 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903483831-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 7 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483831 LE5779 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903483884-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 139 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903483884 JE0052 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903483932-1 IN1173 | WHITE | 105D | S2408WR1600 | 423 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 830009 | HT SUB PROCESS_V1 | 0903483932 IN1173 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903484055-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 400 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484055 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903484097-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 745 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484097 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903484129-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 139 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484129 LE5779 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484567-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 1037 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484567 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903484603-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 163 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484603 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903484610-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2640 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484610 KZ3200 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903484626-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 302 | 30/11/2026 | 302 | SI | SI14/08/2026 | G3J | SHORTS | G3 |  |  | 29/09: ex-fty. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903484626 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 302 |  | 302 |  |  | 24/10/2026 | 24/10/2026 |  |  | 302 |  | 302 |  |  | 21/10/2026 | 21/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903484639-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1599 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484639 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484713-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903484713 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484845-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903484845 HK7317 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484940-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484940 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485025-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 2101 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485025 KF6290 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485027-1 HK7309 | BLACK | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903485027 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485046-1 KE9656 | BLACK | 105D | S2608WR0201A | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485046 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485085-1 KE9656 | BLACK | 105D | S2608WR0201A | 7387 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485085 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485092-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 4500 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485092 JW7178 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485117-1 KE9656 | BLACK | 105D | S2608WR0201A | 746 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485117 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485121-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 201 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903485121 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903485469-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485469 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903485504-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 336 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485504 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485529-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 135 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485529 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485559-1 IN2961 | BLACK | 105D | S2408WR2400 | 131 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903485559 IN2961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903485625-1 IN8707 | BLACK | 105D | S2408WR1601A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516443 | HT SUB PROCESS_V1 | 0903485625 IN8707 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903486162-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 129 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486162 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903486211-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1218 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486211 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486240-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 743 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486240 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 243 | 30/10/2026 | 243 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486292 IN1172 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 26/10/2026 | 27/10/2026 |  |  | 243 |  | 243 |  |  | 23/10/2026 | 24/10/2026 |  |  | 243 |  | 243 |  |  | 22/10/2026 | 23/10/2026 |  |  | 243 |  | 243
ADIDAS | 0903486365-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 238 | 30/10/2026 | 238 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486365 IN1157 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 46092 | ADIZERO E TEE |  | SS27-YTI-SLT | 46092 | 46092 |  |  | 238 |  | 238 |  |  | 31/10/2026 | 31/10/2026 |  |  | 238 |  | 238 |  |  | 30/10/2026 | 30/10/2026 |  |  | 238 |  | 238
ADIDAS | 0903486390-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 817 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903486390 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903486405-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 136 | 30/10/2026 | 136 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486405 IN1157 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 46092 | ADIZERO E TEE |  | SS27-YTI-SLT | 46092 | 46092 |  |  | 136 |  | 136 |  |  | 31/10/2026 | 31/10/2026 |  |  | 136 |  | 136 |  |  | 30/10/2026 | 30/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903486424-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903486424 LE1842 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903486448-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 238 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903486448 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903486480-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 138 | 30/10/2026 | 138 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486480 IN1156 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 23/09/2026 | 24/09/2026 |  |  | 138 |  | 138 |  |  | 21/09/2026 | 22/09/2026 |  |  | 138 |  | 138 |  |  | 19/09/2026 | 21/09/2026 |  |  | 138 |  | 138
ADIDAS | 0903486515-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 428 | 30/10/2026 | 428 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486515 IN1156 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 26/10/2026 | 26/10/2026 |  |  | 428 |  | 428 |  |  | 23/10/2026 | 23/10/2026 |  |  | 428 |  | 428 |  |  | 22/10/2026 | 22/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903486538-1 KC8568 | BLACK | 105D | OJS26250839 | 512 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 848016 | PRINT L1 SUB PROCESS_V3 | 0903486538 KC8568 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903486601-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 207 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903486601 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903486653-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 304 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486653 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486667-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 675 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486667 LE8199 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486695-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 174 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486695 LE8199 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486712-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 4334 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486712 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486753-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 2974 | 31/10/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486753 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486778-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486778 IN2961 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903486817-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 537 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486817 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486860-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 106 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903486860 LI7659 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903486892-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 217 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486892 IN1172 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486900-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486900 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486938-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 313 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486938 IN1157 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486940-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486940 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486943-1 IC5188 | BLACK | 90D | S23080640 | 223 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903486943 IC5188 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486967-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486967 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486972-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 102 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486972 IN1172 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487014-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 250 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487014 IN1157 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487018-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487018 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903487045-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1000 | 15/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487045 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487057-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 897 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487057 IN1156 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487080-1 IC5189 | WHITE | 90D | S23080640 | 282 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487080 IC5189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487085-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 1152 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487085 KW2924 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903487088-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487088 IN1156 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487099-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 193 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487099 IL4127 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487117-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 792 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487117 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487139-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2460 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487139 JM1775 | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487150-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1916 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487150 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903487175-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487175 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487239-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 180 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487239 LE8191 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487261-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487261 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487276-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 180 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487276 LE5780 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487306-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2500 | 46214 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487306 IB8688 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903487310-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 5500 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903487310 JE0052 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903487320-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487320 LE8189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903487353-1 HK7319 | BLACK | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487353 HK7319 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487361-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487361 LE5779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487403-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 210 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487403 LE8192 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487447-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487447 LE8190 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 352 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487766 KZ3200 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903487796-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487796 KV7863 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903488043-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 637 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488043 LE8191 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488075-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 637 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488075 LE5780 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488207-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903488207 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488411-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 902 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903488411 JE0055 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903488504-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). 848012 | HT SUB PROCESS_V1 | 0903488504 KG8548 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903488561-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 275 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903488561 LI7655 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903488669-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 221 | 30/10/2026 | 221 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903488669 IN1172 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 26/10/2026 | 27/10/2026 |  |  | 221 |  | 221 |  |  | 23/10/2026 | 24/10/2026 |  |  | 221 |  | 221 |  |  | 22/10/2026 | 23/10/2026 |  |  | 221 |  | 221
ADIDAS | 0903488689-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 104 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488689 LF0725 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488772-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 101 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903488772 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903488783-1 KR2011 | LIGHT GREY HEATHER | 60D | F26KCNYGFX100 | 1179 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (29/09/2026) |  | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488783 KR2011 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903488800-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 102 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903488800 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488806-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 160 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488806 IN1172 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488837-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488837 LF0725 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488855-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488855 IN1172 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488870-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512108 | EMBRO SUB PROCESS_V1 | 0903488870 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488910-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 260 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488910 LF0725 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488914-1 KR2013 | TEAM ROYAL BLUE | 60D | F26KCNYGFX120 | 1047 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488914 KR2013 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488933-1 KS1837 | BLACK | 60D | F26KCNYGFX120 | 272 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488933 KS1837 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488935-1 KE9656 | BLACK | 105D | S2608WR0201A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 848012 | PAD+HT SUB PROCESS_V3 | 0903488935 KE9656 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488952-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488952 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903488971-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 142 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488971 LF0725 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488989-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 594 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488989 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903489018-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 664 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903489018 LD0293 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903489050-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 2092 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489050 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903489070-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 116 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489070 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489080-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 506 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489080 LE8192 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489098-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV | 199 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489098 JM1778 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489106-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1764 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489106 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489115-1 KA0246 | BLACK | 105D | S2608WR0902 | 375 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903489115 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489144-1 KA0246 | BLACK | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903489144 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489188-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 160 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 848012 | PRINT L1 SUB PROCESS_V3 | 0903489188 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489228-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489228 KZ3200 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903489267-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 337 | 23/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489267 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903489318-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 924 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903489318 KC6386 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903489329-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 510 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489329 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903489359-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 349 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903489359 IL4127 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903489679-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489679 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903489712-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 939 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489712 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489746-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489746 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903489781-1 LG8054 | LIGHT GREY HEATHER | 90D | S2762LHME151K | 168 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489781 LG8054 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE K LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489814-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 179 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489814 LG8055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489854-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489854 LI7655 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903489856-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 149 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 678002 | PRINT L1 SUB PROCESS_V3 | 0903489856 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489883-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 60 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L1 SUB PROCESS_V3 | 0903489883 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489886-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 109 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489886 LI7658 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903489914-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 314 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L1 SUB PROCESS_V3 | 0903489914 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489924-1 IN1157 | WHITE | 105D | S2408MR1600 | 304 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 516443 | HT SUB PROCESS_V1 | 0903489924 IN1157 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903489972-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903489972 JE6414 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903490085-1 KA4331 | BLACK | 90D | S2608MR0902 | 345 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903490085 KA4331 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903490142-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490142 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903490324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 150 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903490324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490610-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 1905 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903490610 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490651-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 840 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490651 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903490660-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 109 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 672027 | PRINT L1 SUB PROCESS_V3 | 0903490660 LE1843 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903490766-1 KA0246 | BLACK | 105D | S2608WR0902 | 101 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903490766 KA0246 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491240-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 246 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491240 KG8548 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903491252-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903491252 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903491267-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903491267 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903491398-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 672 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491398 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903491513-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 103 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491513 IN1172 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491552-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 350 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825057 | PRINT L1 SUB PROCESS_V3 | 0903491552 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903491589-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1017 | 31/10/2026 | 1017 | SI | SI14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903491589 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | LA PALMS TEE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 1017 |  | 1017 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1017 |  | 1017
ADIDAS | 0903491769-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903491769 IN1156 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491790-1 KA0246 | BLACK | 105D | S2608WR0902 | 395 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903491790 KA0246 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491835-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 570 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491835 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903491866-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 824 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491866 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903491896-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 15000 | 20/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903491896 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903491932-1 KA0246 | BLACK | 105D | S2608WR0902 | 413 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903491932 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491960-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 800 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491960 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903492007-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 2604 | 20/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903492007 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903492013-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492013 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903492051-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 112 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492051 LE8191 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903492057-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 488 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903492057 LI7656 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903492098-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 600 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492098 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903492214-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 637 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492214 LE8189 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903492261-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 427 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492261 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903492308-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 744 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492308 LI7657 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903492329-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 1200 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). 848012 | HT SUB PROCESS_V1 | 0903492329 KG8548 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903493200-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 184 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903493200 LD0908 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903493244-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 5000 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903493244 JE0055 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903493287-1 IP2310 | BLACK | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493287 IP2310 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903493324-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493324 IW8374 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903493572-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 504 | 23/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493572 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493612-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 162 | 46214 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493612 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493721-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 502 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825056 | PRINT L1 SUB PROCESS_V3 | 0903493721 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493752-1 KR2005 | DARK BLUE | 60D | F26KCMIAGFX100 | 1200 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493752 KR2005 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493772-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 357 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493772 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493807-1 KS2151 | WHITE | 60D | F26KCLAGFX100 | 364 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493807 KS2151 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493891-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1199 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493891 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493893-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 510 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903493893 LD0277 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903493942-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1193 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493942 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493960-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 420 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903493960 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903493998-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903493998 LG8052 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494009-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494009 LG8052 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494023-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494023 LG8051 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 46064 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 46064 | 46064 |  |  | 2 |  | 2 |  |  | 29/10/2026 | 29/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903494054-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 722 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903494054 LG8055 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494081-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494081 LI5438 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903494105-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 762 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903494105 LG8056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494139-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 2 | 29/10/2026 | 2 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494139 LJ4075 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 46064 | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS | 46064 | 46064 |  |  | 2 |  | 2 |  |  | 29/10/2026 | 29/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903494146-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 110 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903494146 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903494166-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 15000 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494166 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494218-1 LG4333 | WHITE | 90D | F2606LEMBU207MF | 12288 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494218 LG4333 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494219-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 118 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903494219 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903494261-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 194 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903494261 IN1156 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494278-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 488 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494278 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 109 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494292 IN1172 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494327-1 LJ9158 | WHITE | 90D | 226205_JZSJ | 8582 | 20/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903494327 LJ9158 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494356-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 1 | 15/11/2026 |  | NT | NT14/08/2026 |  | SWEATSHIRT |  |  |  | (NYK warehouse). 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903494356 KG2925 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC LF HD |  | SS27
ADIDAS | 0903494364-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 170 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494364 IN1156 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494394-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 391 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494394 LI7659 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903494489-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 163 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494489 IN1156 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494517-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 334 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494517 IN1157 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494550-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494550 JE6419 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903494560-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 196 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494560 IN1157 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494587-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1250 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494587 JE0055 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903494709-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 230 | 30/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3 SUB PROCESS_V3 | 0903494709 LE1858 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903494746-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 340 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3+HT SUB PROCESS_V3 | 0903494746 LE4570 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903495154-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 131 | 46214 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495154 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495200-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 124 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495200 JW9678 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903495205-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 390 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495205 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495231-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 473 | 46214 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495231 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495267-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 422 | 15/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3 SUB PROCESS_V3 | 0903495267 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495304-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495304 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495328-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 354 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825065 | PRINT L3+HT SUB PROCESS_V3 | 0903495328 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495368-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 541 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825056 | PRINT L3+HT SUB PROCESS_V3 | 0903495368 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495389-1 IK7442 | WHITE | 105D | S2408WR2400 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495389 IK7442 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903495436-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 732 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3+HT SUB PROCESS_V3 | 0903495436 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495584-1 IN1173 | WHITE | 105D | S2408WR1600 | 390 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 800005 | HT SUB PROCESS_V1 | 0903495584 IN1173 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903495915-1 KA0235 | BLACK | 105D | S2608WR0901 | 373 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903495915 KA0235 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903495966-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 353 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516443 | HT SUB PROCESS_V1 | 0903495966 IN1159 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903496214-1 KS1838 | WHITE | 60D | F26KCNYGFX130 | 370 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496214 KS1838 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496277-1 KR2014 | DARK BLUE | 60D | F26KCNYGFX130 | 1181 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496277 KR2014 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496298-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 870 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 804028 | PRINT L3+HT SUB PROCESS_V3 | 0903496298 LE4570 | 30/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903497678-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1001 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903497678 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903498251-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 216 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498251 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903498288-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498288 LG8055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903498314-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 140 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498314 LI7656 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903498480-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 216 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903498480 LD0908 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498515-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 800 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903498515 LD0908 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498576-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 115 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498576 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903499304-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1938 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499304 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499328-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 2068 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499328 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499369-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 554 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499369 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499422-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 1590 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499422 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499455-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 745 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499455 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499545-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 454 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499545 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499689-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 235 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903499689 LE8181 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903499724-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 154 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499724 KZ3199 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903499864-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903499864 JP1528 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903499962-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 1203 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903499962 LE1842 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903499998-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2987 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903499998 LE1843 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500013-1 IS1413 | BLACK | 60D | S2425M405 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903500013 IS1413 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903500034-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 323 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903500034 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500135-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 193 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (04/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 27-Sep. Waiting fabric. T2 Libolon, PI Date 04-Sep. 839055 | PAD+HT SUB PROCESS_V3 | 0903500135 IT3474 | 46367 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903501707-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 176 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501707 KZ3200 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903501742-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 137 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903501742 JD9944 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903501929-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 274 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501929 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903502116-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 230 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502116 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903502119-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 144 | 15/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 848024 | PRINT L3+HT SUB PROCESS_V3 | 0903502119 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903502153-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 725 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903502153 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903502154-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 424 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502154 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903502968-1 KA6229 | BLACK | 120D | S2608WR0202 | 867 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502968 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903503018-1 KA6229 | BLACK | 120D | S2608WR0202 | 2969 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903503018 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903504266-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 664 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903504266 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903504351-1 IC5188 | BLACK | 90D | S23080640 | 308 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | HT SUB PROCESS_V1 | 0903504351 IC5188 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903504660-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 328 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903504660 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903506204-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 459 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903506204 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903530911-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 824 | 15/11/2026 |  | AN | AN18/08/2026 |  | JACKET |  | (15/09/2026) |  | MOQ Issue 806020 | EMBRO SUB PROCESS_V1 | 0903530911 KW6443 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903535007-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 100 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535007 KC8152 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903535008-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 539 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535008 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903542128-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 106 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903542128 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903542656-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 150 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542656 LG8616 | 46306 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903542705-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 400 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542705 LL1875 | 46306 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903544653-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 377 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903544653 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903545582-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 214 | 31/10/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903545582 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903546294-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 2 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903546294 LG8616 | 46306 | KAHATEX CIJERAH | CHINA | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903547557-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 478 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903547557 IB8686 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903548095-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 129 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903548095 KX0123 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903548343-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 190 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903548343 IU0217 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903549325-1 HZ0747 | BLACK | 90D | F2325M414 | 982 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903549325 HZ0747 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903550204-1 HZ0747 | BLACK | 90D | F2325M414 | 269 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903550204 HZ0747 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | PL TEE |  | SS27
ADIDAS | 0903550456-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 528 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550456 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903552136-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 404 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903552136 LD0278 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903553779-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 891 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903553779 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903554207-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554207 LL1875 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903554250-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554250 LL1874 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903555193-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 265 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903555193 KX9851 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903555378-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 300 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555378 KZ3198 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555407-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 615 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555407 KZ3205 | 46306 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555925-1 HZ0747 | BLACK | 90D | F2325M414 | 2301 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903555925 HZ0747 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903556107-1 IS1413 | BLACK | 60D | S2425M405 | 3000 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903556107 IS1413 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903556385-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 206 | 46214 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903556385 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903558146-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 2400 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903558146 IU0217 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903558231-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558231 JC9346 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558277-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 385 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558277 JC9346 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558320-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558320 JE6414 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558358-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558358 JE6417 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558397-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 661 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558397 JE6419 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558444-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 5339 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558444 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558476-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558476 JE6417 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558515-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558515 JE6419 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558557-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558557 JE9012 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558600-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 386 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558600 JE9012 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903560866-1 JD0957 | BLACK | 60D | S25ORISW311 | 140 | 15/11/2026 |  | ID | ID28/08/2026 |  | SHORTS |  | (30/09/2026) |  | 980004 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903560866 JD0957 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADIC SWIMSH 5IN |  | SS27
ADIDAS | 0903562605-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 3578 | 31/10/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 652001 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903562605 JC5283 |  | KAHATEX CIJERAH | MEXICO | SEA |  | M L SLIDE PKT T |  | SS27
ADIDAS | 0903564830-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 2340 | 30/11/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903564830 KD9849 |  | KAHATEX CIJERAH | MEXICO | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903565164-1 IS1413 | BLACK | 60D | S2425M405 | 1 | 31/10/2026 | 1 | SI | SI28/08/2026 | G2S | T-SHIRT | G2 | (26/09/2026) |  | 672027 | PRINT L3 SUB PROCESS_V3 | 0903565164 IS1413 |  | KAHATEX CIJERAH | BRAZIL | SEA | 20/10/2026 | IN RANGE |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 1 |  | 1 |  |  | 16/10/2026 | 16/10/2026 |  |  | 1 |  | 1
ADIDAS | 0903566142-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 4 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903566142 KZ0028 | 46306 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903566214-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903566214 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903567986-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 390 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903567986 KV7863 |  | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903569115-1 LK0714 | WONDER SAGE S26 | 90D | 226291_EFOA | 3335 | 21/10/2026 | 3335 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (12/09/2026) |  | 800005 | HT SUB PROCESS_V1 | 0903569115 LK0714 | 46306 | KAHATEX CIJERAH | INDONESIA | SEA | 46275 | WF JRF 26 WONDER SAGE S26 |  | SS27-L2L-JRF | 46275 | 14/10/2026 |  |  | 3335 |  | 3335 |  |  | 46213 | 46366 |  |  | 3335 |  | 3335 |  |  | 46183 | 46305 |  |  | 3335 |  | 3335
ADIDAS | 0903569377-1 IN1159 | BLACK | 90D | S2408MR1601 | 1365 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 672027 | HT SUB PROCESS_V1 | 0903569377 IN1159 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569590-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 385 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903569590 JE0055 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903569748-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1300 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569748 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569785-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569785 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569826-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 2499 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569826 HK7303 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903570113-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 155 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903570113 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903571229-1 KA4331 | BLACK | 90D | S2608MR0902 | 764 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903571229 KA4331 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903571671-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 300 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 400147 | PRINT L1 SUB PROCESS_V3 | 0903571671 LG8616 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903571753-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 328 | 15/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571753 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903571791-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 290 | 30/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571791 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903572059-1 KA4331 | BLACK | 90D | S2608MR0902 | 327 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572059 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572124-1 KA4331 | BLACK | 90D | S2608MR0902 | 1163 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572124 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572154-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1052 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903572154 KV7863 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903572157-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 119 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903572157 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903572804-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 902 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903572804 LL1875 | 46306 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903572864-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 180 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  |  |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903572864 LL1875 | 46306 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903573116-1 KA4331 | BLACK | 90D | S2608MR0902 | 188 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903573116 KA4331 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903573472-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 786 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903573472 KZ3205 | 46306 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903574124-1 IN1159 | BLACK | 90D | S2408MR1601 | 318 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903574124 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903574668-1 KA4331 | BLACK | 90D | S2608MR0902 | 968 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903574668 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903574863-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 800187 | PAD+HT SUB PROCESS_V3 | 0903574863 KA4331 | 46306 | KAHATEX CIJERAH | VIETNAM | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 100 |  | 100 |  |  | 14/11/2026 | 16/11/2026 |  |  | 100 |  | 100 |  |  | 13/11/2026 | 14/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903574889-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 830009 | PAD+HT SUB PROCESS_V3 | 0903574889 KA4331 | 46306 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 100 |  | 100 |  |  | 14/11/2026 | 16/11/2026 |  |  | 100 |  | 100 |  |  | 13/11/2026 | 14/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903576131-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 500 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903576131 KZ0922 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903576180-1 IN1159 | BLACK | 90D | S2408MR1601 | 730 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516333 | HT SUB PROCESS_V1 | 0903576180 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903576238-1 IN1159 | BLACK | 90D | S2408MR1601 | 226 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516471 | HT SUB PROCESS_V1 | 0903576238 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903577664-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 716 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903577664 KZ0922 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903577750-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 600 | 31/10/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903577750 JC5283 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M L SLIDE PKT T |  | SS27
ADIDAS | 0903578729-1 KA4331 | BLACK | 90D | S2608MR0902 | 625 | 30/11/2026 | 625 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 516394 | PAD+HT SUB PROCESS_V3 | 0903578729 KA4331 | 46306 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 625 |  | 625 |  |  | 14/11/2026 | 16/11/2026 |  |  | 625 |  | 625 |  |  | 13/11/2026 | 14/11/2026 |  |  | 625 |  | 625
ADIDAS | 0903578772-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 7 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516029 | PRINT L1 SUB PROCESS_V3 | 0903578772 LI6133 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903578813-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 4673 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516027 | PRINT L1 SUB PROCESS_V3 | 0903578813 LI6133 | 46306 | KAHATEX CIJERAH | BRAZIL | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903580940-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 369 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580940 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903580989-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1772 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580989 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581132-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1657 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581132 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903582940-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1357 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903582940 KV7863 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903583205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 608 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903583205 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903595557-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 643 | 30/11/2026 |  | SI | SI03/09/2026 |  | T-SHIRT |  | (10/10/2026) |  | 857010 | PRINT L1 SUB PROCESS_V3 | 0903595557 LE1843 | 16/11/2026 | KAHATEX CIJERAH | INDIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903597586-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 108 | 31/10/2026 | 108 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 650034 | HT SUB PROCESS_V1 | 0903597586 KG8553 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 28/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 108 |  | 108 |  |  | 26/10/2026 | 27/10/2026 |  |  | 108 |  | 108 |  |  | 24/10/2026 | 26/10/2026 |  |  | 108 |  | 108
ADIDAS | 0903600165-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 254 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903600165 KY6510 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903600283-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 177 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600283 LI2646 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600284-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 162 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600284 LI2667 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600285-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 324 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600285 LI2668 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600286-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 201 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600286 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600287-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 132 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600287 LI2670 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600288-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 155 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600288 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600289-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 194 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600289 LI2668 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600290-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 126 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600290 LI2667 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600291-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 157 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600291 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903600292-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 137 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600292 LI2671 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903610424-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 101 | 31/10/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610424 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610455-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 100 | 46214 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903610455 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903610469-1 IS1413 | BLACK | 60D | S2425M405 | 526 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903610469 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610478-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 100 | 31/10/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610478 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610504-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 100 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610504 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610537-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 203 | 30/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610537 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610563-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 257 | 46214 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903610563 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903610663-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 518 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903610663 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903611417-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 652 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611417 KA0544 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611450-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 592 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611450 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611531-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611531 KA0544 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611537-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 300 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611537 KA5088 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611561-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611561 KA0546 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611568-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 2669 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611568 KA5090 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611604-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 2492 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611604 KA5089 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611635-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 308 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611635 KA5089 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611652-1 HK2890 | BLACK | 90D | F2225M270 | 2 | 14/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 825054 | HT+PPH L1 SUB PROCESS_V3 | 0903611652 HK2890 |  | KAHATEX CIJERAH | CHINA | SEA |  | C TEE |  | SS27
ADIDAS | 0903612849-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 203 | 30/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903612849 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903612871-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 442 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612871 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612931-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 368 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612931 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612957-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 220 | 30/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612957 KA6229 | 23/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903613004-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 173 | 15/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903613004 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903613665-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 1700 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613665 KA5088 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903613678-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 497 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903613678 JC5282 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M L SLIDE PKT T |  | SS27
ADIDAS | 0903613692-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 329 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613692 KA5090 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903614230-1 HK7309 | BLACK | 45D | F2225M402 | 2400 | 46214 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614230 HK7309 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903614477-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 101 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614477 KB5961 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903614597-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903614597 KA5088 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903614814-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 451 | 31/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614814 KA6229 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903614843-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 200 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614843 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903615872-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 120 | 46214 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903615872 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903626403-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 751 | 15/11/2026 |  | SI | SI11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626403 LJ2754 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903626428-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 751 | 15/11/2026 |  | SA | SA11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626428 LE4570 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 4501928388-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 14/11/2026 |  | ID | ID29/05/2026 |  | SKIRT |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928388 LG9668 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 4501928489-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 444 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501928489 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 4502066600-1 LF0727 | BLACK | 120D | S2754MAS510B | 181 | 31/10/2026 | 181 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502066600 LF0727 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 46092 | M SL WV TT BLACK |  | SS27 | 46092 | 46153 |  |  | 181 |  | 181 |  |  | 30/10/2026 | 46064 |  |  | 181 |  | 181
ADIDAS | 4502066601-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1481 | 21/10/2026 | 1481 | SI | SI26/06/2026 | G1P | T-SHIRT | G1 | (08/08/2026) | ok | ZA30 | EMBRO SUB PROCESS_V1 | 4502066601 KD3911 |  | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 26/10/2026 | RELEASED |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 1481 |  | 1481 |  |  | 22/10/2026 | 23/10/2026 |  |  | 1481 |  | 1481
ADIDAS | 4502066684-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). ZA30 | HT+PAD SUB PROCESS_V3 | 4502066684 KB5961 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066730-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 30 | 21/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502066730 KX7716 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066806-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 959 | 21/10/2026 |  | AT | AT26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 4502066806 KA5090 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | MINI EMB T |  | SS27 | [20 empty] | 46062 | 46062 |  | 9 |  | 9
ADIDAS | 4502066844-1 KB5965 | BLACK | 120D | S2608MR0900A | 300 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066844-2 KB5965 | BLACK | 120D | S2608MR0900A | 100 | 14/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066871-1 KE8424 | BLACK | 120D | S2608MR0906A | 164 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 4502066871-2 KE8424 | BLACK | 120D | S2608MR0906A | 100 | 14/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 4502066873-1 KB5960 | WHITE | 120D | S2608MR0900A | 756 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066873-2 KB5960 | WHITE | 120D | S2608MR0900A | 72 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066873-3 KB5960 | WHITE | 120D | S2608MR0900A | 385 | 21/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502069351-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502069351 LI2667 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 4502070409-2 LF0718 | BLACK | 105D | S2754MAS512B | 50 | 14/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 4502070657-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070657 LI2670 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 4502070658-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070658 LI2671 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 4502070659-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070659 LI2645 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 4502070898-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | (04/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070898 LI2669 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 4502070899-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070899 LI2646 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 4502070901-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070901 LI2647 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 4502075076-1 KT4840 | ONIX | 90D | S2408MR1600 | 859 | 21/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075076 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 4502075079-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075079 KR3066 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502075080-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 260 | 21/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502075080 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 4502075923-2 IN1156 | BLACK | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) |  | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 100 |  | 100 |  |  | 27/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 26/10/2026 | 28/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502075929-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 326 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 1st Art (TC 10 pcs) ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075929 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502075930-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 140 | 14/11/2026 |  | AN | AN30/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? ZA30 | PRINT L2+HT SUB PROCESS_V3 | 4502075930 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 4502076908-2 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 21/10/2026 | 100 | SA | SA03/07/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100 |  |  | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100 |  |  | 20/10/2026 | 21/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502076909-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 46214 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502076909-2 JZ7709 | BLACK | 120D | S2608MR0201 | 300 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502077373-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 46214 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077373-2 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 14/11/2026 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077374-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1193 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502077374 KY9384 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 4502347325-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 249 | 14/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4502347325 LH3760 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 4502347613-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1094 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347613 JZ7709 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502347632-1 JZ7711 | BLACK | 120D | S2608MR0202 | 130 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347632 JZ7711 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 4502348815-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 116 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502348815 KR3066 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502349090-1 KD3875 | BLACK | 120D | S2608WR0201 | 142 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502349090 KD3875 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 4502349403-1 KA6229 | BLACK | 120D | S2608WR0202 | 112 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349403 KA6229 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502349501-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 141 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349501 JZ7715 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502364155-1 KZ4389 | WHITE | 120D | F2608MR1500 | 15 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. ZA30 | PAD+HT SUB PROCESS_V3 | 4502364155 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 4502368741-1 JZ7709 | BLACK | 120D | S2608MR0201 | 208 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502368741 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 4502369662-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 251 | 21/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | ZA30 | PRINT L1 SUB PROCESS_V3 | 4502369662 LE1843 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | OFC-07092026-002 | MULTI COLOR | 45D | F213CSIM105FL | 12295 | 31/10/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-002 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-003 | MULTI COLOR | 45D | F213CSIM109FL | 6 | 31/10/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-003 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-012 | MULTI COLOR | 45D | F2225M402 | 991 | 31/10/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-012 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-013 | MULTI COLOR | 45D | F2225M402 | 465 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-013 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-017 | MULTI COLOR | 90D | F2225M403 | 400 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-017 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-020 | MULTI COLOR | 45D | F224CSIM430 | 10836 | 31/10/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-020 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-025 | MULTI COLOR | 75D | F2325M421 | 360 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPS SUB PROCESS_V3 | OFC-07092026-025 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-032 | MULTI COLOR | 45D | F24KLKGFX003 | 268 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-032 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-033 | MULTI COLOR | 45D | F24KLKGFX003 | 2546 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-033 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-035 | MULTI COLOR | 60D | F2525M432 | 594 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-035 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-036 | MULTI COLOR | 60D | F2550WTR422 | 4 | 15/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L3+PAD+HT SUB PROCESS_V3 | OFC-07092026-036 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-037 | MULTI COLOR | 90D | F2554MESS710WV | 90 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-037 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-044 | MULTI COLOR | 60D | F25KIUGFX010 | 1697 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-044 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-048 | MULTI COLOR | 60D | F25KLKGFX011 | 801 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-048 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-049 | MULTI COLOR | 60D | F25KLKGFX011 | 178 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-049 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-055 | MULTI COLOR | 60D | F25SPRMGFX040 | 1166 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-055 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-056 | MULTI COLOR | 60D | F25SPRMGFX041 | 419 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-056 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1130 | MULTI COLOR | 60D | S27FBGFXP101 | 355 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1130 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1131 | MULTI COLOR | 60D | S27FBGFXP102 | 318 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1132 | MULTI COLOR | 60D | S27FBGFXP102 | 181 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1132 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1134 | MULTI COLOR | 60D | S27FBGFXP510 | 5 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1134 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1135 | MULTI COLOR | 60D | S27FBGFXP510 | 171 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1135 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1136 | MULTI COLOR | 60D | S27FBGFXP510 | 1054 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1136 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1139 | MULTI COLOR | 60D | S27FBGFXP600 | 324 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1139 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1142 | MULTI COLOR | 90D | S27SPRMGFXP0600 | 210 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-1142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1176 | MULTI COLOR | 60D | S2762LHAU334 | 564 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1176 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1180 | MULTI COLOR | 60D | S2762LHAU373 | 34 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1180 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1181 | MULTI COLOR | 60D | S2762LHAU373 | 38 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1181 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1185 | MULTI COLOR | 60D | S2762LHMR399 | 661 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1185 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1186 | MULTI COLOR | 60D | S27AOCP101 | 1370 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1186 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1187 | MULTI COLOR | 60D | S27AOCP101 | 15361 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1187 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1188 | MULTI COLOR | 60D | S27AOCP102 | 1171 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1188 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1189 | MULTI COLOR | 60D | S27AOCP102 | 9098 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1189 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1190 | MULTI COLOR | 60D | S27AOCP103 | 840 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1190 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1191 | MULTI COLOR | 60D | S27AOCP103 | 1380 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1191 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-131 | MULTI COLOR | 90D | F2608MR1201BUF | 374 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-142 | MULTI COLOR | 90D | F2625M101 | 232 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-143 | MULTI COLOR | 90D | F2625M101 | 594 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-143 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-144 | MULTI COLOR | 90D | F2625M101 | 536 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-144 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-150 | MULTI COLOR | 90D | F2625W233 | 54 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-150 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-151 | MULTI COLOR | 90D | F2625W233 | 1 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-151 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-157 | MULTI COLOR | 60D | F26FBGFXP101 | 410 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-157 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-158 | MULTI COLOR | 60D | F26FBGFXP104 | 1800 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-158 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-159 | MULTI COLOR | 60D | F26FBGFXP105 | 451 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-159 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-298 | MULTI COLOR | 60D | PH_F_BKB_A | 185 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-298 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-299 | MULTI COLOR | 60D | PH_F_SPW_A | 100 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-299 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-300 | MULTI COLOR | 60D | PH_F_SPW_A | 308 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-300 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-303 | MULTI COLOR | 60D | PH_F_SWK_A | 204 | 31/10/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-303 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-304 | MULTI COLOR | 60D | PH_F_SWK_A | 283 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-304 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-309 | MULTI COLOR | 60D | PH_F_TRA_A | 254 | 15/11/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-309 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-310 | MULTI COLOR | 60D | PH_F_TRA_A | 376 | 30/11/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-310 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-356 | MULTI COLOR | 90D | PHRUN | 1545 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-356 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-385 | MULTI COLOR | 90D | PHSPWM | 720 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-385 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-410 | MULTI COLOR | 90D | PHTRNMEN | 38 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-410 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-426 | MULTI COLOR | 60D | S1954WC511 | 336 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-426 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-427 | MULTI COLOR | 45D | S211CSIM117FLRO | 6 | 31/10/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-427 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-428 | MULTI COLOR | 60D | S211CSIM120FLTC | 2 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-428 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-430 | MULTI COLOR | 45D | S211CSIW114SJ | 215 | 31/10/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PAD SUB PROCESS_V3 | OFC-07092026-430 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-436 | MULTI COLOR | 60D | S2307M501 | 2 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT+PPA+PPH SUB PROCESS_V3 | OFC-07092026-436 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-437 | MULTI COLOR | 90D | S23080640 | 462 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-437 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-443 | MULTI COLOR | 60D | S2315KSWU253 | 723 | 31/10/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-443 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-445 | MULTI COLOR | 45D | S2315KSWU324A | 260 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-445 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-447 | MULTI COLOR | 105D | S2408MR1600 | 495 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-447 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-448 | MULTI COLOR | 105D | S2408MR1600 | 103 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-448 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-459 | MULTI COLOR | 90D | S2408MR1601 | 405 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-459 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-460 | MULTI COLOR | 90D | S2408MR1601 | 1013 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-460 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-476 | MULTI COLOR | 105D | S2408WR1600 | 238 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-476 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-487 | MULTI COLOR | 105D | S2408WR1601A | 109 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-487 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-504 | MULTI COLOR | 60D | S2425M405 | 1295 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-504 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-505 | MULTI COLOR | 60D | S2425M405 | 8325 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-505 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-522 | MULTI COLOR | 60D | S2525M200 | 1 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-522 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-523 | MULTI COLOR | 60D | S2525M200 | 790 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-523 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-530 | MULTI COLOR | 90D | S2554MESS601FT | 1 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-530 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-535 | MULTI COLOR | 90D | S2554MESS605FT | 18 | 31/10/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-535 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-536 | MULTI COLOR | 90D | S2554MESS605FT | 5 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-536 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-541 | MULTI COLOR | 90D | S2554MESS611FT | 91 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-541 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-542 | MULTI COLOR | 90D | S2554MESS611FT | 10 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-542 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-549 | MULTI COLOR | 90D | S2554MESS642WV | 76 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L1+PPH L1 SUB PROCESS_V3 | OFC-07092026-549 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-550 | MULTI COLOR | 90D | S2554MESS663SJ | 1 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-550 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-554 | MULTI COLOR | 90D | S2554MESS675FT | 1158 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-554 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-561 | MULTI COLOR | 90D | S2554WES402FT | 14 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-561 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-566 | MULTI COLOR | 90D | S2554WES403FT | 6 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-566 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-570 | MULTI COLOR | 90D | S2554WES413FTB | 22 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-570 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-574 | MULTI COLOR | 90D | S2554WES421WV | 38 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-574 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-587 | MULTI COLOR | 90D | S2554WES512FT | 120 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-587 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-592 | MULTI COLOR | 60D | S25ORISW311 | 1 | 31/10/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | OFC-07092026-592 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-593 | MULTI COLOR | 60D | S25SPRMGFX230 | 40 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PPH L1+PAD SUB PROCESS_V3 | OFC-07092026-593 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-594 | MULTI COLOR | 60D | S25SPRMGFX233 | 36 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-594 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-595 | MULTI COLOR | 60D | S25SPRMGFX233 | 432 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-595 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-601 | MULTI COLOR | 60D | S25SPRMGFX313 | 957 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-601 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-602 | MULTI COLOR | 90D | S25TEGFX501A | 27 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD+HT SUB PROCESS_V3 | OFC-07092026-602 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-608 | MULTI COLOR | 120D | S2608MR0201 | 173 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-608 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-609 | MULTI COLOR | 120D | S2608MR0201 | 101 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-609 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-647 | MULTI COLOR | 120D | S2608MR0900A | 910 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-647 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-648 | MULTI COLOR | 120D | S2608MR0900A | 37 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-648 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-668 | MULTI COLOR | 90D | S2608MR0902 | 1018 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-668 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-732 | MULTI COLOR | 105D | S2608WR0901 | 30 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-732 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-745 | MULTI COLOR | 105D | S2608WR0902 | 101 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-745 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-756 | MULTI COLOR | 90D | S2608WR0910 | 117 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-756 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-769 | MULTI COLOR | 90D | S2625M018 | 135 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-769 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-770 | MULTI COLOR | 90D | S2625M018 | 586 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-770 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-771 | MULTI COLOR | 90D | S2625M018 | 923 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-771 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-774 | MULTI COLOR | 90D | S2625M036 | 330 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-774 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-775 | MULTI COLOR | 90D | S2625M036 | 101 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-775 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-776 | MULTI COLOR | 90D | S2625M036 | 404 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-776 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-846 | MULTI COLOR | 60D | S26KJGGFX020 | 145 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-846 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-848 | MULTI COLOR | 60D | S26KJUGFX009 | 357 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-848 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-856 | MULTI COLOR | 60D | S26SPRWGFX004 | 4 | 31/10/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | OFC-07092026-856 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-861 | MULTI COLOR | 60D | S26SPRWGFX005 | 829 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-861 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-862 | MULTI COLOR | 60D | S26SPRWGFX023 | 1 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-862 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-866 | MULTI COLOR | 60D | S26SPRWGFX110 | 1120 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-866 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-867 | MULTI COLOR | 60D | S26SPRWGFX111 | 117 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-867 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-871 | MULTI COLOR | 75D | S2706CHRM031 | 1203 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L2+EMBRO SUB PROCESS_V3 | OFC-07092026-871 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-963 | MULTI COLOR | 90D | S2754WESS404WV | 4515 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-963 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-973 | MULTI COLOR | 90D | S2754WESS420WV | 132 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-973 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-979 | MULTI COLOR | 90D | S2754WESS421WV | 1632 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-979 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-988 | MULTI COLOR | 90D | S2754WESS422WV | 108 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-988 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-998 | MULTI COLOR | 90D | S2754WESS703WV | 49 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-998 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27