## Sheet1
JO Tracking Report
Factory: | KAHATEX CIJERAH | Floor | G1,G2,G3,G4,G5,SPL | JO: |  | Style No: |  | Delivery Date: | 01/09/2026 - 31/10/2026 | JO Status: | Uncompleted, Completed, Export | Printed by: | REYNALDI | Print time: | 16/09/2026 00:05:17
Customer Name | Order No. | Color | Lot No | Factory Style | Qty | Delivery Date | Plan Qty | Merchaniser | PO.NO | Line | Product Type | Floor | Fabrics | Auxiliary | JO Remarks | Process Route Name | Cust_Order_No | Pre-production event finish date | Factory | Ship To | Ship Mode | Sewing Start | Style Description | Plan Remarks | Season | SEWING | [8 empty] | COMPLETE ASSEMBLY | [8 empty] | HEAT TRANSFER
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902372325-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 590 | 2026-08-09 | 590 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372325 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 590 | 590 |  |  |  | 2026-03-07 | 15/07/2026 | 29/06/2026 | 2026-09-07 | 590 | 590
ADIDAS | 0902372479-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 186 | 2026-08-09 | 186 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372479 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 22/07/2026 | 2026-09-07 | 21/07/2026 | 186 | 186 |  |  |  | 2026-03-07 | 17/07/2026 | 2026-02-07 | 18/07/2026 | 186 | 186
ADIDAS | 0902497405-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 244 | 2026-08-09 | 244 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497405 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-06-08 | 29/07/2026 | 2026-06-08 | 244 | 244 |  |  |  | 24/07/2026 | 2026-03-08 | 27/07/2026 | 2026-07-08 | 244 | 244
ADIDAS | 0902497408-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2L | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497408 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902497412-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 205 | 2026-08-09 | 205 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497412 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 27/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 205 | 205 |  |  |  | 22/07/2026 | 30/07/2026 | 15/07/2026 | 2026-04-08 | 205 | 205
ADIDAS | 0902497414-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497414 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 100 | 100 |  |  |  | 24/07/2026 | 30/07/2026 | 16/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902545290-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 3000 | 2026-05-09 | 3000 | SA | SA06/02/2026 | G1D,G1K,G3I | PANTS | G1,G3 | ok | ok | 04/09: ex-fty 823016 | EMBRO SUB PROCESS_V1 | 0902545290 GK9267 | 2026-11-03 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 21/07/2026 | M 3S FL O PT |  | FW26 | 21/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 3000 | 3000 |  |  |  | 16/07/2026 | 22/07/2026 | 2026-07-07 | 22/07/2026 | 3000 | 3000
ADIDAS | 0902557495-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 824 | 2026-08-09 | 824 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, using fabric stock (FOC 2147 yd) (switch with fabric from Far Eastern.). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557495 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 15/07/2026 | 23/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824
ADIDAS | 0902622148-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 4220 | 2026-12-09 | 4220 | AT | AT27/02/2026 | G3J,G3K | PANTS | G3 | ok | (19/03/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902622148 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 27/07/2026 | M 3S FT TC PT |  | FW26 | 27/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 4220 | 4220 |  |  |  | 22/07/2026 | 30/07/2026 | 2026-10-07 | 25/07/2026 | 4220 | 4220
ADIDAS | 0902635931-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 602 | 2026-08-09 | 602 | SA | SA27/02/2026 | G2S | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635931 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 20/07/2026 | 602 | 602 |  |  |  | 2026-03-07 | 15/07/2026 | 26/06/2026 | 2026-02-07 | 602 | 602
ADIDAS | 0902636875-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2720 | 15/09/2026 | 2720 | AT | AT04/03/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (28/03/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902636875 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-09-09 | 29/08/2026 | 2026-09-09 | 2720 | 2720 |  |  |  | 24/08/2026 | 2026-05-09 | 28/07/2026 | 2026-09-09 | 2720 | 2720
ADIDAS | 0902652229-1 KD5830 | BLACK | 105D | F2525M009 | 154 | 2026-08-09 | 154 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2-SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652229 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 154 | 154 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-01-07 | 2026-10-07 | 154 | 154
ADIDAS | 0902652411-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652411 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 24/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652437-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652437 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652462-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 205 | 30/09/2026 | 205 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652462 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 15/07/2026 | 205 | 205
ADIDAS | 0902652495-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 241 | 30/09/2026 | 241 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652495 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 30/07/2026 | 20/07/2026 | 29/07/2026 | 241 | 241 |  |  |  | 15/07/2026 | 27/07/2026 | 15/07/2026 | 23/07/2026 | 241 | 241
ADIDAS | 0902769872-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 4240 | 2026-05-09 | 4240 | AT | AT27/03/2026 | G1P,G1Q,G1R | T-SHIRT | G1 | ok | ok | 04/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902769872 LE8199 | 16/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-08 | LFC A F JSY SE |  | FW26-FJ | 2026-05-08 | 19/08/2026 | 2026-10-08 | 18/08/2026 | 4240 | 4240 |  |  |  | 31/07/2026 | 13/08/2026 | 31/07/2026 | 18/08/2026 | 4240 | 4240
ADIDAS | 0902803294-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV-MTF | 233 | 2026-05-09 | 233 | NT | NT10/04/2026 | G3D | PANTS | G3 | ok | (08/05/2026) | 05/09: ex-fty. T2 Libolon, PI Date 21-Jun, actual receives 22-May. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902803294 JM1778 | 30/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | M SL WV PT 1 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 17/07/2026 | 233 | 233 |  |  |  | 2026-09-07 | 16/07/2026 | 13/07/2026 | 17/07/2026 | 233 | 233
ADIDAS | 0902803647-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 30/09/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual reiceves 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803647 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 15/09/2026 | 2026-07-08 | 15/09/2026 | 100 | 100 |  |  | 3 | 2026-03-08 | 2026-11-09 | 22/07/2026 | 2026-05-08 | 100 | 100
ADIDAS | 0902803818-1 KF9922 | TEAM COLL BURGUNDY 2 | 90D | F2606CHMU042 | 377 | 2026-08-09 | 377 | AN | AN10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 08/09: ex-fty (NYK warehouse). T2 Kahatex, material quality issues (creasemark), PI Date 09-May, actual receives 17-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L2+EMBRO SUB PROCESS_V3 | 0902803818 KF9922 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | MUFC LF TEE |  | FW26 | 27/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 377 | 377 |  |  |  | 22/07/2026 | 30/07/2026 | 21/07/2026 | 28/07/2026 | 377 | 377
ADIDAS | 0902803854-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 15/10/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803854 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-04-08 | LFC LF TEE |  | FW26 | 2026-04-08 | 2026-01-09 | 2026-05-08 | 2026-02-09 | 100 | 100 |  |  |  | 30/07/2026 | 28/08/2026 | 22/07/2026 | 2026-02-09 | 100 | 100
ADIDAS | 0902803922-1 KG2924 | BLACK | 90D | F2606CHLF041 | 200 | 15/10/2026 | 200 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803922 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 2026-04-09 | 2026-06-08 | 2026-03-09 | 200 | 200 |  |  |  | 2026-03-08 | 2026-01-09 | 23/07/2026 | 2026-05-08 | 200 | 200
ADIDAS | 0902804254-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 4267 | 2026-05-09 | 4267 | SA | SA10/04/2026 | G2L,G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 04/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804254 LE8211 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 29/08/2026 | 2026-04-09 | 4267 | 4267 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-04-09 | 4267 | 4267
ADIDAS | 0902804368-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 12412 | 2026-05-09 | 12412 | AT | AT10/04/2026 | G1Q,G2K,G2L,G2M,G2O | T-SHIRT | G1,G2 | ok | ok | 05/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804368 LE5779 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSY SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 12412 | 12412 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-01-09 | 2026-05-09 | 12412 | 12412
ADIDAS | 0902808177-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 3220 | 2026-12-09 | 3220 | AT | AT10/04/2026 | G3C,G3D,G3E | PANTS | G3 | ok | (29/04/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902808177 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 3220 | 3220 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 2026-01-08 | 3220 | 3217 | 3
ADIDAS | 0902847822-1 JE3837 | BLACK/WHITE | 90D | S2554MESS682FT | 1348 | 2026-05-09 | 1348 | AT | AT24/04/2026 | G2T | SWEATSHIRT | G2 | ok | (14/05/2026) | 05/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847822 JE3837 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M FEELCOZY SWT |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 21/07/2026 | 1348 | 1348 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-10-07 | 15/07/2026 | 1348 | 1348
ADIDAS | 0902847867-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 1491 | 2026-05-09 | 1491 | AT | AT24/04/2026 | G1D | PANTS | G1 | ok | ok | 04/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847867 JE3854 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M FEELCOZY PANT |  | FW26 | 21/07/2026 | 2026-05-08 | 23/07/2026 | 31/07/2026 | 1491 | 1491 |  |  |  | 16/07/2026 | 31/07/2026 | 18/07/2026 | 23/07/2026 | 1491 | 1491
ADIDAS | 0902853964-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 81 | 15/10/2026 | 81 | AT | AT24/04/2026 | G2P | SWEATSHIRT | G2 | (22/05/2026) | (18/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902853964 KG2925 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-09 | LFC LF HD |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 81 | 81 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-11-08 | 2026-10-09 | 81 | 81
ADIDAS | 0902854036-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 29-May, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902854036 KA8777 | 28/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | TIRO26L SHO M |  | FW26-L2L | 14/07/2026 | 17/07/2026 | 14/07/2026 | 17/07/2026 | 132 | 132 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 16/07/2026 | 132 | 132 |  |  |  | 2026-07-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 132 | 132
ADIDAS | 0902854145-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 430 | 2026-05-09 | 430 | SI | SI24/04/2026 | G1D | JACKET | G1 | ok | ok | 04/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902854145 JE0052 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | W 3S FT FZ HD |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-06-08 | 2026-07-08 | 430 | 430 |  |  |  | 31/07/2026 | 2026-04-08 | 31/07/2026 | 2026-06-08 | 430 | 430
ADIDAS | 0902854237-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 481 | 23/09/2026 | 481 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/09: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854237 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 21/07/2026 | 2026-03-08 | 21/07/2026 | 31/07/2026 | 481 | 481 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 30/07/2026 | 481 | 481 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 23/07/2026 | 481 | 481
ADIDAS | 0902858585-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 114 | 2026-08-09 | 114 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858585 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 31/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 31/07/2026 | 2026-07-08 | 31/07/2026 | 2026-03-08 | 114 | 114 |  |  |  | 28/07/2026 | 2026-04-08 | 17/07/2026 | 28/07/2026 | 114 | 114
ADIDAS | 0902858612-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 777 | 30/09/2026 | 777 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858612 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 22/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 22/07/2026 | 2026-07-08 | 22/07/2026 | 2026-03-08 | 777 | 777 |  |  |  | 17/07/2026 | 2026-04-08 | 16/07/2026 | 21/07/2026 | 777 | 777
ADIDAS | 0902860692-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 101 | 2026-08-09 | 101 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860692 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 101 | 101 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-10-07 | 14/07/2026 | 101 | 101
ADIDAS | 0902860750-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 486 | 30/09/2026 | 486 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860750 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 486 | 486 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-09-07 | 14/07/2026 | 486 | 486
ADIDAS | 0902860782-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 205 | 2026-08-09 | 205 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860782 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 31/07/2026 | 21/07/2026 | 31/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 28/07/2026 | 17/07/2026 | 21/07/2026 | 205 | 205
ADIDAS | 0902862481-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 309 | 31/10/2026 | 309 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (04/06/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, PI Date 07-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862481 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-12-08 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 309 | 309 |  |  |  | 2026-07-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 309 | 309
ADIDAS | 0902882924-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 306 | 31/10/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902882924 KD0677 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887724-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 359 | 2026-05-09 | 359 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 28-May, using fabric stock. 516400 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887724 KD0677 | 22/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 359 | 359 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 29/07/2026 | 359 | 359 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 25/07/2026 | 359 | 359
ADIDAS | 0902899919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 502 | 2026-05-09 | 502 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899919 LD0288 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 31/07/2026 | 502 | 502 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502
ADIDAS | 0902899965-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899965 LD0287 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 369 | 369 |  |  |  | 2026-06-08 | 28/08/2026 | 2026-01-08 | 2026-08-08 | 369 | 369 |  |  |  | 2026-04-08 | 26/08/2026 | 27/07/2026 | 2026-07-08 | 369 | 369
ADIDAS | 0902900771-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 327 | 2026-05-09 | 327 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900771 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 327 | 327 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-02-09 | 327 | 327 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-02-09 | 327 | 327
ADIDAS | 0902900873-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 347 | 2026-05-09 | 347 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902900873 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 31/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-05-08 | 347 | 347
ADIDAS | 0902900910-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 337 | 2026-07-10 | 337 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900910 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 29/09/2026 | 29/09/2026 |  |  | 337 |  | 337 |  |  | 25/09/2026 | 25/09/2026 | 2026-04-08 | 2026-10-08 | 337 | 337 |  |  |  | 23/09/2026 | 23/09/2026 | 2026-01-08 | 2026-10-08 | 337 | 337
ADIDAS | 0902900938-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 358 | 30/09/2026 | 358 | AN | AN15/05/2026 | G2E | T-SHIRT | G2 | ok | (05/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900938 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 358 |  | 358 |  |  | 15/09/2026 | 16/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358 |  |  |  | 2026-12-09 | 14/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358
ADIDAS | 0902900942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 23/10/2026 | 306 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 29/09/2026 | 29/09/2026 |  |  | 306 |  | 306 |  |  | 25/09/2026 | 25/09/2026 | 2026-04-08 | 28/08/2026 | 306 | 305 | 1 |  |  | 23/09/2026 | 23/09/2026 | 2026-01-08 | 27/08/2026 | 306 | 306
ADIDAS | 0902900970-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 2026-05-09 | 306 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902900970 KG3225 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-06-08 | 306 | 306 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 306 | 306 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 306 | 306
ADIDAS | 0902900989-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 741 | 2026-05-09 | 741 | AN | AN15/05/2026 | G2H | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900989 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 741 | 741 |  |  |  | 31/08/2026 | 2026-02-09 | 28/08/2026 | 2026-04-09 | 741 | 741 |  |  |  | 28/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 741 | 741
ADIDAS | 0902901357-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 410 | 2026-09-09 | 410 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901357 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-07-08 | 2026-03-09 | 410 | 410 |  |  |  | 2026-03-08 | 2026-04-09 | 2026-04-08 | 2026-03-09 | 410 | 410
ADIDAS | 0902901389-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 377 | 2026-09-09 | 377 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901389 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-06-08 | 2026-03-09 | 377 | 377 |  |  |  | 2026-03-08 | 2026-04-09 | 30/07/2026 | 2026-05-09 | 377 | 377
ADIDAS | 0902901531-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 312 | 2026-09-09 | 312 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | ok | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901531 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 2026-08-09 | 2026-10-08 | 2026-07-09 | 312 | 312 |  |  |  | 2026-05-08 | 2026-04-09 | 2026-05-08 | 2026-01-09 | 312 | 312
ADIDAS | 0902901569-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 507 | 2026-09-09 | 507 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901569 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-08-09 | 507 | 507 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 2026-02-09 | 507 | 507
ADIDAS | 0902901874-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 6443 | 30/09/2026 | 6443 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 24/09: ex-fty. T2 Libolon, PI Date 09-Jun, actual receives 09-Jul. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901874 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 13/08/2026 | 17/09/2026 | 2026-12-08 | 15/09/2026 | 6443 | 5257 | 1186 |  | 426 | 2026-10-08 | 14/09/2026 | 31/07/2026 | 2026-11-09 | 6443 | 5827 | 616
ADIDAS | 0902902811-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 317 | 15/09/2026 | 317 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902811 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 317 | 317 |  |  |  | 2026-06-08 | 28/08/2026 | 23/07/2026 | 2026-05-08 | 317 | 317 |  |  |  | 2026-04-08 | 26/08/2026 | 22/07/2026 | 2026-04-08 | 317 | 317
ADIDAS | 0902902836-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 595 | 15/09/2026 | 595 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902836 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 595 | 595 |  |  | 3 | 2026-02-09 | 2026-11-09 | 24/08/2026 | 2026-08-09 | 595 | 595 |  |  |  | 31/08/2026 | 2026-09-09 | 24/08/2026 | 2026-08-09 | 595 | 595
ADIDAS | 0902902865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902902865 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 2026-04-08 | 22/07/2026 | 31/07/2026 | 369 | 369 |  |  |  | 16/07/2026 | 30/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369 |  |  |  | 14/07/2026 | 28/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369
ADIDAS | 0902902891-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 15/09/2026 | 322 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902891 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-10-08 | 2026-01-09 | 322 | 322 |  |  |  | 2026-06-08 | 29/08/2026 | 22/07/2026 | 2026-07-08 | 322 | 322 |  |  |  | 2026-04-08 | 27/08/2026 | 22/07/2026 | 2026-06-08 | 322 | 322
ADIDAS | 0902902948-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1044 | 2026-05-09 | 1044 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902902948 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 1044 | 1044 |  |  |  | 27/08/2026 | 2026-02-09 | 21/08/2026 | 2026-01-09 | 1044 | 1044 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 1044 | 1044
ADIDAS | 0902902973-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 30/09/2026 | 880 | SA | SA15/05/2026 | G2M | T-SHIRT | G2 | ok | (08/06/2026) | 23/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902902973 KX3655 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 22/09/2026 |  |  | 880 |  | 880 |  |  | 18/09/2026 | 18/09/2026 | 26/08/2026 | 14/09/2026 | 880 | 581 | 299 |  |  | 16/09/2026 | 16/09/2026 | 21/08/2026 | 14/09/2026 | 880 | 581 | 299
ADIDAS | 0902903045-1 KE8425 | WHITE | 120D | S2608MR0906A | 318 | 23/10/2026 |  | SI | SI15/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902903045 KE8425 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0902903099-1 KE8425 | WHITE | 120D | S2608MR0906A | 305 | 2026-07-10 | 305 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516333 | HT+PAD SUB PROCESS_V3 | 0902903099 KE8425 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess LS M WHITE |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 305 |  | 305 |  |  | 29/09/2026 | 30/09/2026 | 13/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 26/09/2026 | 28/09/2026 | 2026-11-08 | 27/08/2026 | 305 | 305
ADIDAS | 0902904515-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 339 | 2026-05-09 | 339 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904515 LD0287 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 339 | 339 |  |  |  | 2026-06-08 | 29/08/2026 | 2026-01-08 | 31/08/2026 | 339 | 339 |  |  |  | 2026-04-08 | 27/08/2026 | 27/07/2026 | 31/08/2026 | 339 | 339
ADIDAS | 0902904537-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 329 | 15/09/2026 | 329 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904537 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 329 | 329 |  |  |  | 2026-06-08 | 29/08/2026 | 31/07/2026 | 2026-10-08 | 329 | 329 |  |  |  | 2026-04-08 | 27/08/2026 | 30/07/2026 | 2026-10-08 | 329 | 329
ADIDAS | 0902904560-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902904560 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 2026-01-10 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 28/09/2026 | 28/09/2026 | 2026-10-08 | 2026-12-08 | 319 | 319 |  |  |  | 25/09/2026 | 25/09/2026 | 2026-08-08 | 2026-12-08 | 319 | 319
ADIDAS | 0902904602-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 696 | 2026-05-09 | 696 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904602 LD0284 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 696 | 696 |  |  |  | 28/07/2026 | 28/08/2026 | 27/07/2026 | 2026-01-08 | 696 | 696 |  |  |  | 24/07/2026 | 26/08/2026 | 25/07/2026 | 2026-01-08 | 696 | 696
ADIDAS | 0902904645-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 309 | 2026-05-09 | 309 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902904645 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 309 | 309 |  |  |  | 28/07/2026 | 28/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309 |  |  |  | 24/07/2026 | 26/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309
ADIDAS | 0902905667-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 530 | 23/09/2026 | 530 | SA | SA15/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902905667 LD0285 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 27/07/2026 | 21/08/2026 | 27/07/2026 | 20/08/2026 | 530 | 530 |  |  |  | 22/07/2026 | 18/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530 |  |  |  | 20/07/2026 | 13/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530
ADIDAS | 0902905691-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 336 | 2026-12-09 | 336 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902905691 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 24/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 336 | 336 |  |  |  | 21/07/2026 | 24/07/2026 | 16/07/2026 | 23/07/2026 | 336 | 336 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 336 | 336
ADIDAS | 0902906579-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 15 | 23/09/2026 | 15 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902906579 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15 |  |  |  | 21/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15
ADIDAS | 0902906608-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 1321 | 15/09/2026 | 1321 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿) , PI Date 30-Jun, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902906608 LG9669 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-04-09 | W SL WV SK BLACK |  | SS27 | 2026-04-09 | 18/09/2026 | 2026-04-09 | 15/09/2026 | 1321 | 1321 |  |  | 185 | 2026-01-09 | 15/09/2026 | 22/08/2026 | 15/09/2026 | 1321 | 1317 | 4 |  | 41
ADIDAS | 0902906662-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 324 | 2026-05-09 | 324 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906662 LD0288 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 30/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 30/07/2026 | 20/07/2026 | 31/07/2026 | 324 | 324 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 324 | 324
ADIDAS | 0902906685-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 961 | 30/09/2026 | 961 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906685 LD0287 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 15/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 961 | 712 | 249 |  | 240 | 2026-11-09 | 15/09/2026 | 31/07/2026 | 2026-06-08 | 961 | 961 |  |  |  | 2026-09-09 | 2026-12-09 | 30/07/2026 | 2026-06-08 | 961 | 961
ADIDAS | 0902906698-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 3281 | 2026-05-09 | 3281 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0902906698 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 21/08/2026 | 2026-05-09 | 21/08/2026 | 2026-04-09 | 3281 | 3281 |  |  |  | 18/08/2026 | 2026-02-09 | 13/08/2026 | 2026-01-09 | 3281 | 3281 |  |  |  | 13/08/2026 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 3281 | 3281
ADIDAS | 0902906708-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 360 | 15/09/2026 | 360 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902906708 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 360 | 360 |  |  | 20 | 2026-02-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 360 | 360 |  |  |  | 31/08/2026 | 2026-09-09 | 31/07/2026 | 2026-04-08 | 360 | 360
ADIDAS | 0902906721-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 797 | 2026-05-09 | 797 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906721 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 797 | 797 |  |  |  | 2026-12-08 | 29/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797
ADIDAS | 0902906734-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 328 | 2026-05-09 | 328 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902906734 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 328 | 328 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 328 | 328 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 31/07/2026 | 328 | 328
ADIDAS | 0902906748-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 319 | 30/09/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906748 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 16/09/2026 | 14/09/2026 | 15/09/2026 | 319 | 290 | 29 |  | 182 | 2026-10-09 | 2026-12-09 | 26/08/2026 | 2026-02-09 | 319 | 319 |  |  |  | 2026-08-09 | 2026-10-09 | 24/08/2026 | 2026-02-09 | 319 | 319
ADIDAS | 0902906789-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 779 | 2026-05-09 | 779 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906789 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-06-08 | 2026-01-09 | 779 | 779 |  |  |  | 2026-03-08 | 29/08/2026 | 25/07/2026 | 31/08/2026 | 779 | 779 |  |  |  | 30/07/2026 | 27/08/2026 | 22/07/2026 | 31/08/2026 | 779 | 779
ADIDAS | 0902907417-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907417 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 308 | 308 |  |  |  | 23/07/2026 | 30/07/2026 | 18/07/2026 | 24/07/2026 | 308 | 308 |  |  |  | 21/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 308 | 308
ADIDAS | 0902907437-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 332 | 15/09/2026 | 332 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907437 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 29/07/2026 | 2026-03-08 | 332 | 332 |  |  |  | 23/07/2026 | 30/07/2026 | 21/07/2026 | 27/07/2026 | 332 | 332 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 24/07/2026 | 332 | 332
ADIDAS | 0902907453-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 443 | 15/09/2026 | 443 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907453 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-07-09 | 15/09/2026 | 443 | 443 |  |  | 16 | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 14/09/2026 | 443 | 443
ADIDAS | 0902907472-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 812 | 23/09/2026 | 812 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902907472 KX3651 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 812 | 812 |  |  |  | 21/07/2026 | 30/07/2026 | 17/07/2026 | 30/07/2026 | 812 | 812 |  |  |  | 17/07/2026 | 28/07/2026 | 17/07/2026 | 28/07/2026 | 812 | 812
ADIDAS | 0902907504-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 652 | 2026-05-09 | 652 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902907504 KX3654 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-01-09 | 2026-07-08 | 2026-01-09 | 652 | 652 |  |  |  | 2026-03-08 | 28/08/2026 | 25/07/2026 | 2026-05-08 | 652 | 652 |  |  |  | 30/07/2026 | 26/08/2026 | 23/07/2026 | 28/07/2026 | 652 | 652
ADIDAS | 0902907522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 648 | 2026-05-09 | 648 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907522 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/07/2026 | 2026-11-08 | 29/07/2026 | 2026-07-08 | 648 | 648 |  |  |  | 23/07/2026 | 2026-06-08 | 25/07/2026 | 2026-01-08 | 648 | 648 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 28/07/2026 | 648 | 648
ADIDAS | 0902907548-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 671 | 2026-05-09 | 671 | SA | SA15/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907548 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 22/07/2026 | 30/07/2026 | 22/07/2026 | 29/07/2026 | 671 | 671 |  |  |  | 17/07/2026 | 27/07/2026 | 17/07/2026 | 22/07/2026 | 671 | 671 |  |  |  | 15/07/2026 | 23/07/2026 | 17/07/2026 | 28/07/2026 | 671 | 671
ADIDAS | 0902907571-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 12/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907571 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 308 | 308 |  |  | 29 | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-12-09 | 308 | 308 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-12-09 | 308 | 308
ADIDAS | 0902908709-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 684 | 15/09/2026 | 684 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 14-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902908709 LF0726 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 684 | 618 | 66 |  |  | 2026-04-09 | 14/09/2026 | 28/08/2026 | 14/09/2026 | 684 | 610 | 74
ADIDAS | 0902908777-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT15/05/2026 | G3E | SHORTS | G3 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 12-Jun, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902908777 KA8777 | 14/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/07/2026 | TIRO26L SHO M |  | SS27-L2L | 30/07/2026 | 2026-07-08 | 31/07/2026 | 2026-05-08 | 132 | 132 |  |  |  | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 132 | 132 |  |  |  | 23/07/2026 | 31/07/2026 | 13/07/2026 | 13/07/2026 | 132 | 132
ADIDAS | 0902909669-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 30/09/2026 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Jun, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902909669 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 144 | 144 |  |  |  | 29/08/2026 | 2026-04-09 | 26/08/2026 | 2026-07-09 | 144 | 142 | 2
ADIDAS | 0902909771-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902909771 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 13/08/2026 | 14/08/2026 | 8 | 8 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 2026-05-08 | 8 | 8
ADIDAS | 0902909794-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902909794 LG9660 | 31/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 8 | 8 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-11-08 | 18/08/2026 | 8 | 8
ADIDAS | 0902909815-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902909815 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 27/08/2026 | 29/08/2026 | 14/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902910585-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 858 | 2026-05-09 | 858 | SA | SA15/05/2026 | G2G,G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902910585 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 858 | 858 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 2026-03-09 | 858 | 858 |  |  |  | 27/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 858 | 858
ADIDAS | 0902910626-1 KX3712 | LIME TINT S27 | 120D | S2608MR0906A | 420 | 2026-05-09 | 420 | SI | SI15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902910626 KX3712 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess LS M LIME TINT S27 |  | SS27-TI-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 420 | 420 |  |  |  | 27/07/2026 | 2026-11-08 | 17/07/2026 | 24/07/2026 | 420 | 420 |  |  |  | 23/07/2026 | 2026-07-08 | 17/07/2026 | 24/07/2026 | 420 | 420
ADIDAS | 0902911467-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1312 | 23/09/2026 | 1312 | SA | SA15/05/2026 | G2G,G2I,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 834012 | HT+PAD SUB PROCESS_V3 | 0902911467 KF5311 | 14/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-03-08 | 2026-02-09 | 2026-03-08 | 2026-01-09 | 1312 | 1312 |  |  |  | 29/07/2026 | 29/08/2026 | 28/07/2026 | 2026-10-08 | 1312 | 1312 |  |  |  | 27/07/2026 | 27/08/2026 | 25/07/2026 | 2026-10-08 | 1312 | 1312
ADIDAS | 0902911942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 15 | 2026-05-09 | 15 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902911942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI-SPOMA | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 15 | 15 |  |  |  | 27/07/2026 | 30/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15 |  |  |  | 23/07/2026 | 28/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15
ADIDAS | 0902911985-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 351 | 2026-09-09 | 351 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902911985 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 351 | 351 |  |  |  | 29/08/2026 | 2026-01-09 | 13/08/2026 | 2026-07-09 | 351 | 351
ADIDAS | 0902912004-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 652 | 2026-05-09 | 652 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912004 LF0726 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 652 | 652 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 652 | 652
ADIDAS | 0902912022-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 335 | 2026-05-09 | 335 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902912022 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 335 | 335 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 20/08/2026 | 335 | 335
ADIDAS | 0902912038-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1761 | 2026-05-09 | 1761 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912038 LF0727 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 19/08/2026 | 1761 | 1761 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 1761 | 1761
ADIDAS | 0902912063-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 339 | 2026-05-09 | 339 | AN | AN15/05/2026 | G1E | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912063 LF0729 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 18/08/2026 | 339 | 339 |  |  |  | 2026-03-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 339 | 339
ADIDAS | 0902912066-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 544 | 2026-05-09 | 544 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912066 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-07-08 | 2026-12-08 | 544 | 544 |  |  |  | 2026-03-08 | 2026-10-08 | 31/07/2026 | 19/08/2026 | 544 | 544
ADIDAS | 0902912087-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 2026-05-09 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902912087 LG9669 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 144 | 144 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 19/08/2026 | 144 | 144
ADIDAS | 0902912093-1 LG9669 | BLACK | 120D | S2754WAS514C | 789 | 2026-09-09 | 789 | ID | ID15/05/2026 | G3B | SKIRT | G3 | ok | (04/06/2026) | 09/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 659018 | PRINT L3+PPA SUB PROCESS_V3 | 0902912093 LG9669 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 789 | 789 |  |  |  | 27/08/2026 | 2026-04-09 | 13/08/2026 | 2026-07-09 | 789 | 789
ADIDAS | 0902912125-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1399 | 2026-05-09 | 1399 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912125 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 1399 | 1399 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 19/08/2026 | 1399 | 1399
ADIDAS | 0902913684-1 KE8424 | BLACK | 60D | S2608MR0906A-MTF | 304 | 2026-05-09 | 304 | AN | AN15/05/2026 | G2G | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902913684 KE8424 | 2026-02-07 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-09 | Run Ess LS M BLACK |  | FW26 | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 304 | 304 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 304 | 304 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 304 | 304
ADIDAS | 0902913763-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2000 | 2026-12-09 | 2000 | AT | AT15/05/2026 | G3D,G3K | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913763 JD1881 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-08 | M 3S FT TC PT |  | FW26 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 2026-12-08 | 2000 | 2000 |  |  |  | 29/07/2026 | 2026-11-08 | 20/07/2026 | 2026-08-08 | 2000 | 2000
ADIDAS | 0902913788-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 720 | 2026-12-09 | 720 | AT | AT15/05/2026 | G3D | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913788 JE6346 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 720 | 720 |  |  |  | 21/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 720 | 720
ADIDAS | 0902915780-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 60 | 15/09/2026 | 60 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902915780 LF0729 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-09-09 | 2026-10-09 | 60 | 58 | 2 |  |  | 2026-04-09 | 14/09/2026 | 21/08/2026 | 2026-01-09 | 60 | 60
ADIDAS | 0902915810-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 230 | 2026-05-09 | 230 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902915810 KX3713 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 230 | 230 |  |  |  | 29/08/2026 | 2026-02-09 | 30/07/2026 | 2026-06-08 | 230 | 230 |  |  |  | 27/08/2026 | 31/08/2026 | 27/07/2026 | 2026-04-08 | 230 | 230
ADIDAS | 0902915970-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 105 | 2026-05-09 | 105 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902915970 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI-SPOMA | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 21/07/2026 | 30/07/2026 | 22/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 17/07/2026 | 28/07/2026 | 21/07/2026 | 2026-03-08 | 105 | 105
ADIDAS | 0902916014-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 975 | 2026-05-09 | 975 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902916014 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI-SPOMA | 21/07/2026 | 2026-04-08 | 22/07/2026 | 2026-04-08 | 975 | 975 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 22/07/2026 | 975 | 975 |  |  |  | 14/07/2026 | 28/07/2026 | 15/07/2026 | 21/07/2026 | 975 | 975
ADIDAS | 0902916052-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 588 | 2026-05-09 | 588 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902916052 LD0930 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 588 | 588 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-04-09 | 588 | 588 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 588 | 588
ADIDAS | 0902917391-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 327 | 15/09/2026 | 327 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902917391 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 327 | 327 |  |  |  | 2026-03-08 | 29/08/2026 | 30/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 30/07/2026 | 27/08/2026 | 29/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902917424-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 673 | 2026-05-09 | 673 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902917424 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 24/07/2026 | 2026-11-08 | 24/07/2026 | 2026-06-08 | 673 | 673 |  |  |  | 21/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 673 | 673 |  |  |  | 17/07/2026 | 2026-04-08 | 21/07/2026 | 2026-04-08 | 673 | 673
ADIDAS | 0902919030-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 5346 | 15/09/2026 | 5346 | AN | AN15/05/2026 | G3A,G3B,G3F,G3H | PANTS | G3 | ok | (13/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902919030 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 15/09/2026 | 14/08/2026 | 14/09/2026 | 5346 | 5240 | 106 |  |  | 2026-11-08 | 2026-11-09 | 2026-06-08 | 15/09/2026 | 5346 | 5299 | 47 |  | 26
ADIDAS | 0902926321-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 321 | 2026-05-09 | 321 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926321 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-11-08 | 321 | 321 |  |  |  | 2026-03-08 | 2026-10-08 | 30/07/2026 | 19/08/2026 | 321 | 321
ADIDAS | 0902926382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 200 | 30/09/2026 | 200 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 23/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926382 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 2026-08-09 | 29/08/2026 | 2026-07-09 | 200 | 200 |  |  |  | 21/08/2026 | 2026-04-09 | 26/08/2026 | 2026-09-09 | 200 | 200
ADIDAS | 0902930259-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 324 | 2026-07-10 | 324 | SA | SA21/05/2026 | G2Q | T-SHIRT | G2 | ok | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902930259 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 324 |  | 324 |  |  | 26/09/2026 | 28/09/2026 | 14/08/2026 | 2026-08-09 | 324 | 298 | 26 |  |  | 24/09/2026 | 25/09/2026 | 13/08/2026 | 2026-08-09 | 324 | 297 | 27
ADIDAS | 0902931102-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA21/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902931102 LD0285 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-01-10 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 28/09/2026 | 28/09/2026 | 2026-03-08 | 2026-07-08 | 319 | 319 |  |  |  | 25/09/2026 | 25/09/2026 | 2026-03-08 | 2026-05-08 | 319 | 319
ADIDAS | 0902940286-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 30 | 15/09/2026 | 30 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940286 LE0357 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 2026-09-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 30 | 7 | 23 |  | 7 | 2026-05-09 | 2026-11-09 | 26/08/2026 | 2026-04-09 | 30 | 21 | 9
ADIDAS | 0902940338-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 499 | 15/10/2026 | 499 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 31-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940338 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 499 |  | 499 |  |  | 13/10/2026 | 15/10/2026 |  |  | 499 |  | 499
ADIDAS | 0902941400-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941400 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 29/09/2026 |  |  | 4800 |  | 4800 |  |  | 21/09/2026 | 25/09/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902941469-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 3000 | 2026-07-10 | 3000 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941469 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 3000 |  | 3000 |  |  | 18/09/2026 | 21/09/2026 |  |  | 3000 |  | 3000
ADIDAS | 0902942438-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 360 | 15/09/2026 | 360 | SI | SI29/05/2026 | G1O | SHORTS | G1 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942438 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 360 | 165 | 195 |  | 165 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 360 | 351 | 9
ADIDAS | 0902942448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 05/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942448 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 29/08/2026 | 18/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-10-08 | 2026-04-09 | 450 | 450
ADIDAS | 0902942463-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 465 | 2026-09-09 | 465 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516419 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942463 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-07-09 | 465 | 465 |  |  |  | 2026-11-08 | 2026-03-09 | 2026-11-08 | 2026-07-09 | 465 | 465
ADIDAS | 0902942481-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5600 | 15/09/2026 | 5600 | SI | SI29/05/2026 | G3C,G3E | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942481 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | M 3S CHELSEA B7 |  | FW26 | 2026-07-09 | 16/09/2026 | 2026-04-09 | 14/09/2026 | 5600 | 5600 |  |  |  | 2026-03-09 | 2026-12-09 | 2026-03-09 | 14/09/2026 | 5600 | 5557 | 43
ADIDAS | 0902942491-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942491 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-11-09 | 315 | 315
ADIDAS | 0902942496-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942496 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 27/08/2026 | 2026-03-09 | 315 | 315 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-02-09 | 315 | 315
ADIDAS | 0902942511-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942511 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-04-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 400 | 400
ADIDAS | 0902942519-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 390 | 15/09/2026 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942519 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 390 | 274 | 116 |  | 274 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 390 | 303 | 87
ADIDAS | 0902942533-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 2026-09-09 | 900 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942533 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-07-09 | 900 | 900 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-05-09 | 900 | 900
ADIDAS | 0902945010-1 LE8187 | BLACK | 105D | S2754MAS513 | 331 | 15/09/2026 | 331 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945010 LE8187 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 15/09/2026 | 2026-08-09 | 2026-09-09 | 331 | 286 | 45 |  |  | 2026-02-09 | 2026-11-09 | 27/08/2026 | 2026-04-09 | 331 | 292 | 39
ADIDAS | 0902945087-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 401 | 30/09/2026 | 401 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945087 LE8188 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 401 |  | 401 |  |  | 15/09/2026 | 17/09/2026 |  |  | 401 |  | 401
ADIDAS | 0902945143-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945143 LE8186 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902946696-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 856 | 15/09/2026 | 856 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946696 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 856 |  | 856 |  |  | 2026-11-09 | 2026-12-09 | 20/08/2026 | 2026-09-09 | 856 | 834 | 22
ADIDAS | 0902946844-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 357 | 15/09/2026 | 357 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946844 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 357 |  | 357 |  |  | 2026-11-09 | 2026-12-09 | 2026-01-08 | 2026-10-09 | 357 | 352 | 5
ADIDAS | 0902946950-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 400 | 2026-12-09 | 400 | SI | SI29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946950 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/08/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-11-09 | 400 | 400 |  |  |  | 26/08/2026 | 2026-09-09 | 2026-05-08 | 2026-11-09 | 400 | 400
ADIDAS | 0902947050-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1120 | 15/10/2026 | 1120 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902947050 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-11 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 1120 |  | 1120 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902948698-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 561 | 2026-07-10 | 561 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948698 LG9668 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 561 |  | 561 |  |  | 2026-08-10 | 2026-10-10 |  |  | 561 |  | 561
ADIDAS | 0902948720-1 LG9669 | BLACK | 120D | S2754WAS514C | 283 | 30/09/2026 | 283 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902948720 LG9669 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | W SL WV SK BLACK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 283 |  | 283 |  |  | 28/09/2026 | 28/09/2026 | 24/08/2026 | 2026-05-09 | 283 | 240 | 43
ADIDAS | 0902948739-1 LG9669 | BLACK | 120D | S2754WAS514C | 316 | 30/09/2026 | 316 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948739 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV SK BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 316 |  | 316 |  |  | 15/09/2026 | 17/09/2026 | 28/08/2026 | 2026-05-09 | 316 | 307 | 9
ADIDAS | 0902948754-1 LG9669 | BLACK | 120D | S2754WAS514C | 416 | 2026-07-10 | 416 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948754 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W SL WV SK BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 416 |  | 416 |  |  | 2026-08-10 | 2026-10-10 |  |  | 416 |  | 416
ADIDAS | 0902948775-1 LG9669 | BLACK | 120D | S2754WAS514C | 497 | 30/09/2026 | 497 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948775 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV SK BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 497 |  | 497 |  |  | 25/09/2026 | 28/09/2026 | 26/08/2026 | 2026-12-09 | 497 | 460 | 37
ADIDAS | 0902949162-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 377 | 15/09/2026 | 377 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949162 LF0725 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 16/09/2026 | 2026-10-09 | 2026-12-09 | 377 | 372 | 5 |  |  | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 377 | 374 | 3
ADIDAS | 0902949302-1 LF0723 | BLACK | 105D | S2754MAS511B | 402 | 30/09/2026 | 402 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949302 LF0723 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | M SL WV SHO BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 402 |  | 402 |  |  | 19/09/2026 | 21/09/2026 |  |  | 402 |  | 402
ADIDAS | 0902951279-1 LH3758 | BLACK | 120D | S2754WAS518B | 500 | 15/10/2026 | 500 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951279 LH3758 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | W SL WV BR PT BLACK |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 500 |  | 500 |  |  | 14/10/2026 | 15/10/2026 |  |  | 500 |  | 500
ADIDAS | 0902951331-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 500 | 30/09/2026 | 500 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951331 LD5446 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 26/09/2026 |  |  | 500 |  | 500
ADIDAS | 0902951389-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 302 | 31/10/2026 | 302 | SA | SA29/05/2026 | G1H | JACKET | G1 | ok | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951389 LG9664 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 302 |  | 302 |  |  | 2026-04-11 | 2026-06-11 |  |  | 302 |  | 302
ADIDAS | 0902951506-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 304 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951506 LG9673 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902951560-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 302 | 15/10/2026 | 302 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951560 LG9665 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 302 |  | 302 |  |  | 25/09/2026 | 28/09/2026 |  |  | 302 |  | 302
ADIDAS | 0902951622-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 498 | 15/10/2026 | 498 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951622 LG9661 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 498 |  | 498 |  |  | 28/09/2026 | 2026-01-10 |  |  | 498 |  | 498
ADIDAS | 0902952685-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 498 | 31/10/2026 | 498 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 31-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902952685 LG9666 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W SL WV TT BLACK |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 498 |  | 498 |  |  | 2026-02-11 | 2026-05-11 |  |  | 498 |  | 498
ADIDAS | 0902953067-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 327 | 2026-07-10 | 327 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953067 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 327 |  | 327 |  |  | 2026-03-10 | 2026-05-10 |  |  | 327 |  | 327
ADIDAS | 0902953315-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 307 | 23/09/2026 | 307 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953315 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 14/08/2026 | 2026-01-09 | 307 | 307 |  |  |  | 2026-11-08 | 29/08/2026 | 28/07/2026 | 2026-11-08 | 307 | 307 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 28/07/2026 | 307 | 307
ADIDAS | 0902953364-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 472 | 23/09/2026 | 472 | SA | SA29/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953364 LD0288 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 21/08/2026 | 31/07/2026 | 20/08/2026 | 472 | 472 |  |  |  | 27/07/2026 | 18/08/2026 | 25/07/2026 | 30/07/2026 | 472 | 472 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 29/07/2026 | 472 | 472
ADIDAS | 0902953400-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 312 | 23/09/2026 | 312 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 18/09: ex-fty 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902953400 KY5988 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 312 | 312 |  |  |  | 27/07/2026 | 2026-11-08 | 30/07/2026 | 2026-08-08 | 312 | 312 |  |  |  | 20/07/2026 | 2026-04-08 | 30/07/2026 | 2026-06-08 | 312 | 312
ADIDAS | 0902953446-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 542 | 23/09/2026 | 542 | SA | SA29/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953446 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 542 | 542 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 31/07/2026 | 542 | 542 |  |  |  | 28/07/2026 | 2026-04-08 | 24/07/2026 | 30/07/2026 | 542 | 542
ADIDAS | 0902953533-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 327 | 30/09/2026 | 327 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902953533 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 327 |  | 327 |  |  | 16/09/2026 | 17/09/2026 | 27/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 14/09/2026 | 15/09/2026 | 25/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902953571-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 479 | 30/09/2026 | 479 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 23/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953571 KX3651 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 479 |  | 479 |  |  | 22/09/2026 | 23/09/2026 | 31/07/2026 | 2026-08-08 | 479 | 479 |  |  |  | 19/09/2026 | 21/09/2026 | 30/07/2026 | 2026-07-08 | 479 | 479
ADIDAS | 0902954045-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954045 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 313 |  | 313 |  |  | 25/09/2026 | 25/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902954088-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 246 | 15/09/2026 | 246 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954088 LG9661 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 246 | 246 |  |  | 70 | 2026-04-09 | 2026-11-09 | 28/08/2026 | 15/09/2026 | 246 | 240 | 6 |  | 28
ADIDAS | 0902954666-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 2026-07-10 | 200 | SA | SA29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954666 LE8181 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 200 |  | 200 |  |  | 2026-09-10 | 2026-10-10 |  |  | 200 |  | 200
ADIDAS | 0902954719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 162 | 15/09/2026 | 162 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954719 LE8186 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 14/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 162 | 127 | 35 |  | 124 | 2026-10-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 162 | 161 | 1 |  | 60
ADIDAS | 0902954826-1 LE8187 | BLACK | 105D | S2754MAS513 | 152 | 15/09/2026 | 152 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954826 LE8187 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 152 | 143 | 9 |  | 143 | 2026-10-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 152 | 151 | 1 |  | 151
ADIDAS | 0902954882-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 174 | 15/09/2026 | 174 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954882 LE8188 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 174 | 140 | 34 |  | 39 | 2026-10-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 174 | 172 | 2 |  | 44
ADIDAS | 0902954999-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 609 | 2026-07-10 | 609 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954999 LF0726 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 609 |  | 609 |  |  | 2026-05-10 | 2026-07-10 |  |  | 609 |  | 609
ADIDAS | 0902955058-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 206 | 23/09/2026 | 206 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955058 LF0727 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 206 | 206 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-07-08 | 31/08/2026 | 206 | 206
ADIDAS | 0902955123-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 356 | 15/09/2026 | 356 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (S4EU). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955123 LF0726 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-04-09 | 2026-12-09 | 356 | 334 | 22 |  |  | 2026-01-09 | 14/09/2026 | 27/08/2026 | 15/09/2026 | 356 | 346 | 10 |  | 20
ADIDAS | 0902955656-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 590 | 30/09/2026 | 590 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955656 KX3655 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 590 | 487 | 103 |  | 487 | 2026-11-09 | 2026-12-09 | 2026-07-09 | 14/09/2026 | 590 | 568 | 22 |  |  | 2026-09-09 | 2026-10-09 | 2026-07-09 | 14/09/2026 | 590 | 567 | 23
ADIDAS | 0902955699-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 441 | 30/09/2026 | 441 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955699 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 441 | 421 | 20 |  | 8 | 2026-08-09 | 2026-11-09 | 2026-10-08 | 26/08/2026 | 441 | 441 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-10-08 | 24/08/2026 | 441 | 441
ADIDAS | 0902955746-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 324 | 30/09/2026 | 324 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902955746 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-09 | 16/09/2026 | 2026-07-09 | 2026-08-09 | 324 | 278 | 46 |  |  | 2026-04-09 | 2026-12-09 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1 |  |  | 2026-02-09 | 2026-10-09 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1
ADIDAS | 0902955843-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 30/09/2026 | 301 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955843 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M SL WV SHO BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 19/09/2026 | 21/09/2026 | 2026-10-09 | 2026-10-09 | 301 | 120 | 181
ADIDAS | 0902955890-1 LF0723 | BLACK | 105D | S2754MAS511B | 137 | 2026-09-09 | 137 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955890 LF0723 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | M SL WV SHO BLACK |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 137 | 137 |  |  |  | 29/08/2026 | 2026-03-09 | 18/08/2026 | 28/08/2026 | 137 | 137
ADIDAS | 0902955942-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 417 | 2026-07-10 | 417 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955942 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 417 |  | 417 |  |  | 19/10/2026 | 20/10/2026 |  |  | 417 |  | 417
ADIDAS | 0902955987-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 322 | 22/09/2026 | 322 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955987 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-08-09 | 2026-10-09 | 322 | 322 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 14/09/2026 | 322 | 322
ADIDAS | 0902956072-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 187 | 2026-05-09 | 187 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956072 LD5446 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 187 | 187 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 187 | 187
ADIDAS | 0902956169-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 302 | 15/09/2026 | 302 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956169 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | M SL WV TT BLACK |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 264 | 38 |  |  | 2026-04-09 | 14/09/2026 | 2026-06-08 | 15/09/2026 | 302 | 296 | 6 |  | 12
ADIDAS | 0902956226-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 645 | 2026-07-10 | 645 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956226 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TT BLACK |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 645 |  | 645 |  |  | 2026-07-10 | 2026-10-10 |  |  | 645 |  | 645
ADIDAS | 0902956293-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 203 | 23/09/2026 | 203 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956293 LF0729 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 203 | 203 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 203 | 202 | 1
ADIDAS | 0902956352-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 177 | 15/09/2026 | 177 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956352 LF0726 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 17/09/2026 | 2026-04-09 | 14/09/2026 | 177 | 177 |  |  |  | 27/08/2026 | 14/09/2026 | 13/08/2026 | 14/09/2026 | 177 | 177
ADIDAS | 0902956415-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 605 | 2026-07-10 | 605 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956415 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 605 |  | 605 |  |  | 2026-03-10 | 2026-05-10 | 2026-04-09 | 2026-11-09 | 605 | 216 | 389
ADIDAS | 0902956471-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 305 | 2026-07-10 | 305 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956471 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 305 |  | 305 |  |  | 2026-03-10 | 2026-05-10 |  |  | 305 |  | 305
ADIDAS | 0902956678-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 599 | 15/09/2026 | 599 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956678 LG9661 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-09 | 15/09/2026 | 2026-05-09 | 15/09/2026 | 599 | 407 | 192 |  | 6 | 28/08/2026 | 2026-11-09 | 26/08/2026 | 15/09/2026 | 599 | 594 | 5 |  | 147
ADIDAS | 0902956729-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 438 | 2026-07-10 | 438 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956729 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 438 |  | 438 |  |  | 25/09/2026 | 28/09/2026 |  |  | 438 |  | 438
ADIDAS | 0902956767-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 133 | 15/09/2026 | 133 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 24/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956767 LG9664 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 133 |  | 133 |  |  | 16/09/2026 | 18/09/2026 | 2026-10-09 | 2026-10-09 | 133 | 109 | 24
ADIDAS | 0902956798-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 310 | 15/09/2026 | 310 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956798 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 310 |  | 310 |  |  | 15/09/2026 | 16/09/2026 | 2026-01-09 | 2026-08-09 | 310 | 242 | 68
ADIDAS | 0902956842-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 710 | 30/09/2026 | 710 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956842 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W SL WV TT BLACK |  | SS27 | 16/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 710 | 108 | 602 |  | 108 | 2026-12-09 | 15/09/2026 | 29/08/2026 | 2026-07-09 | 710 | 599 | 111
ADIDAS | 0902956889-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 599 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902956889 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956973-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 139 | 30/09/2026 | 139 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956973 LG9666 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 139 |  | 139 |  |  | 15/09/2026 | 15/09/2026 | 31/08/2026 | 2026-04-09 | 139 | 138 | 1
ADIDAS | 0902957021-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 495 | 2026-07-10 | 495 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957021 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 495 |  | 495 |  |  | 2026-05-10 | 2026-07-10 |  |  | 495 |  | 495
ADIDAS | 0902957107-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 334 | 2026-07-10 | 334 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957107 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W SL WV PT LEGEND IVY S19 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 334 |  | 334 |  |  | 2026-03-10 | 2026-05-10 |  |  | 334 |  | 334
ADIDAS | 0902957145-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 300 | 30/09/2026 | 300 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957145 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959184-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 201 | 30/09/2026 | 201 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959184 LG9673 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 201 |  | 201 |  |  | 17/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 201 | 66 | 135 |  | 66
ADIDAS | 0902959230-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 428 | 2026-07-10 | 428 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959230 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 428 |  | 428 |  |  | 2026-05-10 | 2026-07-10 |  |  | 428 |  | 428
ADIDAS | 0902959276-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 205 | 30/09/2026 | 205 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959276 LG9675 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W SL WV PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 205 |  | 205 |  |  | 17/09/2026 | 18/09/2026 |  |  | 205 |  | 205
ADIDAS | 0902959319-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959319 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W SL WV PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959364-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 308 | 2026-07-10 | 308 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959364 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W SL WV PT BLACK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 308 |  | 308 |  |  | 2026-03-10 | 2026-05-10 |  |  | 308 |  | 308
ADIDAS | 0902959405-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 356 | 2026-09-09 | 356 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959405 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-02-09 | 356 | 356 |  |  |  | 20/08/2026 | 31/08/2026 | 2026-12-08 | 2026-07-09 | 356 | 356
ADIDAS | 0902959452-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1380 | 30/09/2026 | 1380 | SI | SI29/05/2026 | G3D | SHORTS | G3 | (12/07/2026) | ok | Waiting fabric. DRC 0002-T2 Gistex, material delayed, PI Date 12-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959452 KY4155 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 17/09/2026 | 18/09/2026 |  |  | 1380 |  | 1380 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0902959473-1 LH3758 | BLACK | 120D | S2754WAS518B | 182 | 30/09/2026 | 182 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959473 LH3758 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W SL WV BR PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 182 |  | 182 |  |  | 17/09/2026 | 18/09/2026 |  |  | 182 |  | 182
ADIDAS | 0902959508-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 3010 | 15/09/2026 | 3010 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959508 KY6510 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | M 3S CHELSEA B7 |  | FW26 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 3010 | 673 | 2337 |  | 673 | 2026-11-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 3010 | 2744 | 266 |  | 37
ADIDAS | 0902959557-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 419 | 2026-09-09 | 419 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959557 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 |  | FW26 | 29/08/2026 | 2026-07-09 | 29/08/2026 | 2026-07-09 | 419 | 419 |  |  |  | 26/08/2026 | 2026-03-09 | 13/08/2026 | 2026-07-09 | 419 | 419
ADIDAS | 0902959562-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 134 | 30/09/2026 | 134 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959562 LH3761 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 134 |  | 134 |  |  | 19/09/2026 | 22/09/2026 |  |  | 134 |  | 134
ADIDAS | 0902959597-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 799 | 15/09/2026 | 799 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959597 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 799 | 502 | 297 |  | 502 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 799 | 735 | 64
ADIDAS | 0902959610-1 LH3758 | BLACK | 120D | S2754WAS518B | 640 | 2026-07-10 | 640 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959610 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV BR PT BLACK |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 640 |  | 640 |  |  | 2026-12-10 | 14/10/2026 |  |  | 640 |  | 640
ADIDAS | 0902959964-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516461 | HT+PAD SUB PROCESS_V3 | 0902959964 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 300 | 300 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-10-08 | 15/08/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-10-08 | 14/08/2026 | 300 | 300
ADIDAS | 0902960005-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902960005 KX3655 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-10 | 2026-03-10 |  |  | 320 |  | 320 |  |  | 30/09/2026 | 30/09/2026 |  |  | 320 |  | 320 |  |  | 28/09/2026 | 28/09/2026 |  |  | 320 |  | 320
ADIDAS | 0902960049-1 LF0723 | BLACK | 105D | S2754MAS511B | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902960049 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 420 |  | 420 |  |  | 20/10/2026 | 22/10/2026 |  |  | 420 |  | 420
ADIDAS | 0902960084-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 2026-03-09 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960084 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 29/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-04-08 | 2026-12-08 | 300 | 300
ADIDAS | 0902960126-1 JZ7808 | BLACK | 120D | S2608WR0900 | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902960126 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-08 | 15/08/2026 | 313 | 312 | 1 |  |  | 16/09/2026 | 17/09/2026 | 2026-07-08 | 14/08/2026 | 313 | 313
ADIDAS | 0902960651-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 480 | 2026-05-09 | 480 | SI | SI29/05/2026 | G3A,G3C | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960651 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 480 | 480 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-04-08 | 13/08/2026 | 480 | 480
ADIDAS | 0902960711-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 500 | 15/09/2026 | 500 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960711 LH4535 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 500 | 482 | 18 |  | 27 | 2026-05-09 | 2026-11-09 | 13/08/2026 | 2026-03-09 | 500 | 497 | 3
ADIDAS | 0902960763-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 244 | 15/09/2026 | 244 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960763 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 244 | 238 | 6 |  |  | 2026-05-09 | 2026-11-09 | 15/08/2026 | 28/08/2026 | 244 | 234 | 10
ADIDAS | 0902961677-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 309 | 2026-07-10 | 309 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961677 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 309 |  | 309 |  |  | 2026-12-10 | 14/10/2026 |  |  | 309 |  | 309
ADIDAS | 0902961728-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 887 | 30/09/2026 | 887 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902961728 LH3759 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 887 |  | 887 |  |  | 18/09/2026 | 19/09/2026 |  |  | 887 |  | 887
ADIDAS | 0902961768-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 313 | 30/09/2026 | 313 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961768 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 19/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902961819-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 341 | 2026-07-10 | 341 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961819 LH3761 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 341 |  | 341 |  |  | 2026-12-10 | 14/10/2026 |  |  | 341 |  | 341
ADIDAS | 0902961860-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 592 | 31/10/2026 | 592 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902961860 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 592 |  | 592 |  |  | 2026-12-10 | 13/10/2026 |  |  | 592 |  | 592 |  |  | 2026-09-10 | 2026-10-10 |  |  | 592 |  | 592
ADIDAS | 0902961984-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 427 | 23/10/2026 | 427 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902961984 LD0287 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 427 |  | 427 |  |  | 29/09/2026 | 29/09/2026 |  |  | 427 |  | 427 |  |  | 26/09/2026 | 26/09/2026 |  |  | 427 |  | 427
ADIDAS | 0902962301-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 500 | 2026-03-09 | 500 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962301 KV7963 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 500 | 500 |  |  |  | 22/07/2026 | 30/07/2026 | 23/07/2026 | 2026-05-08 | 500 | 500
ADIDAS | 0902962328-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962328 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 15/09/2026 | 300 | 300 |  |  | 8 | 27/08/2026 | 2026-02-09 | 20/08/2026 | 15/09/2026 | 300 | 300 |  |  | 10
ADIDAS | 0902962445-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962445 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-08-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-02-09 | 2026-08-09 | 400 | 400
ADIDAS | 0902962469-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962469 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-02-09 | 315 | 315 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-02-09 | 315 | 315
ADIDAS | 0902962488-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 390 | 2026-09-09 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962488 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-07-09 | 2026-08-09 | 390 | 390 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 390 | 390
ADIDAS | 0902962541-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962541 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 330 | 330 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-08-09 | 330 | 330
ADIDAS | 0902962571-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516241 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962571 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-08-09 | 330 | 330 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-09-09 | 330 | 330
ADIDAS | 0902962600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962600 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 450 | 450 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0902962624-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 3000 | 2026-12-09 | 3000 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 27-Aug. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962624 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-11-09 | 3000 | 3000 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 3000 | 3000
ADIDAS | 0902962644-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962644 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-02-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 315 | 315
ADIDAS | 0902966036-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966036 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-08-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-07-09 | 14/09/2026 | 65 | 65
ADIDAS | 0902966052-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966052 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 27 | 20 | 7
ADIDAS | 0902966064-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966064 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-08-09 | 65 | 65 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-04-09 | 65 | 65
ADIDAS | 0902966089-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966089 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-08-09 | 2026-10-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 2026-10-09 | 22 | 22 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-05-09 | 2026-10-09 | 22 | 22
ADIDAS | 0902966098-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966098 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 65 | 65 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 65 | 63 | 2
ADIDAS | 0902966111-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 27 | 30/09/2026 | 27 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902966111 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 27 |  | 27 |  |  | 17/09/2026 | 17/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902966123-1 KY5991 | PURE BLUE S27/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 20-Aug. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966123 KY5991 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 35SSHO PURE BLUE S27/WHITE |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 2026-07-09 | 22 | 22 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-05-09 | 2026-05-09 | 22 | 22
ADIDAS | 0902970651-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 992 | 15/09/2026 | 992 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. T2 Kahatex, PI Date 06-Aug, actual receives 25-Jun. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902970651 KA2571 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 992 | 992 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-07-09 | 2026-11-09 | 992 | 992 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-07-09 | 2026-10-09 | 992 | 992
ADIDAS | 0902970663-1 LG9669 | BLACK | 120D | S2754WAS514C | 27 | 30/09/2026 | 27 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970663 LG9669 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/09/2026 | W SL WV SK BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 27 |  | 27 |  |  | 25/09/2026 | 28/09/2026 | 29/08/2026 | 2026-01-09 | 27 | 17 | 10
ADIDAS | 0902970676-1 LE0355 | BLACK | 105D | S2754MAS514 | 65 | 30/09/2026 | 65 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970676 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | M SL WV CU PT BLACK |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 65 |  | 65 |  |  | 30/09/2026 | 2026-02-10 | 2026-01-09 | 15/09/2026 | 65 | 62 | 3 |  | 1
ADIDAS | 0902970685-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970685 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-08-09 | 65 | 65
ADIDAS | 0902970699-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970699 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 14/09/2026 | 27 | 23 | 4
ADIDAS | 0902970711-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 27 | 30/09/2026 | 27 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | ok | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970711 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | W SL WV PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 27 |  | 27 |  |  | 17/09/2026 | 18/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902970727-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 54 | 30/09/2026 | 54 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970727 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 54 |  | 54 |  |  | 15/09/2026 | 15/09/2026 | 2026-01-09 | 2026-03-09 | 54 | 46 | 8
ADIDAS | 0902970843-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 23/09/2026 | 322 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970843 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-06-08 | 2026-11-08 | 322 | 322 |  |  |  | 2026-03-08 | 2026-06-08 | 29/07/2026 | 31/07/2026 | 322 | 322 |  |  |  | 30/07/2026 | 2026-04-08 | 24/07/2026 | 28/07/2026 | 322 | 322
ADIDAS | 0902970859-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 462 | 30/09/2026 | 462 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970859 KX3654 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 16/09/2026 | 2026-07-09 | 2026-08-09 | 462 | 416 | 46 |  |  | 2026-02-09 | 2026-12-09 | 2026-08-08 | 15/08/2026 | 462 | 462 |  |  |  | 31/08/2026 | 2026-10-09 | 2026-08-08 | 14/08/2026 | 462 | 462
ADIDAS | 0902970876-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 503 | 15/10/2026 | 503 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970876 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 503 |  | 503 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 24/08/2026 | 503 | 503 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 503 | 503
ADIDAS | 0902970893-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 433 | 15/10/2026 | 433 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970893 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 433 |  | 433 |  |  | 26/09/2026 | 26/09/2026 |  |  | 433 |  | 433 |  |  | 24/09/2026 | 24/09/2026 |  |  | 433 |  | 433
ADIDAS | 0902970931-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 365 | 23/09/2026 | 365 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970931 LD0285 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/08/2026 | 24/08/2026 | 24/08/2026 | 24/08/2026 | 365 | 365 |  |  |  | 14/08/2026 | 19/08/2026 | 29/07/2026 | 2026-01-08 | 365 | 365 |  |  |  | 2026-12-08 | 14/08/2026 | 25/07/2026 | 2026-01-08 | 365 | 365
ADIDAS | 0902970945-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 479 | 2026-05-09 | 479 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty 684009 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902970945 KC8152 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 31/08/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 479 | 479 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-09 | 2026-10-09 | 479 | 479 |  |  |  | 19/08/2026 | 27/08/2026 | 2026-03-09 | 2026-07-09 | 479 | 479
ADIDAS | 0902970957-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 658 | 30/09/2026 | 658 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902970957 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 658 |  | 658 |  |  | 2026-12-09 | 14/09/2026 | 31/07/2026 | 2026-05-08 | 658 | 658 |  |  |  | 2026-10-09 | 2026-11-09 | 30/07/2026 | 2026-05-08 | 658 | 658
ADIDAS | 0902970975-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 322 | 30/09/2026 | 322 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970975 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 322 |  | 322 |  |  | 18/09/2026 | 19/09/2026 | 2026-04-09 | 14/09/2026 | 322 | 322 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-03-09 | 14/09/2026 | 322 | 322
ADIDAS | 0902970994-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 65 | 15/09/2026 | 65 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970994 LE0357 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 2026-09-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 65 | 32 | 33 |  | 32 | 2026-05-09 | 2026-11-09 | 24/08/2026 | 14/09/2026 | 65 | 56 | 9
ADIDAS | 0902971007-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 325 | 30/09/2026 | 325 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902971007 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 325 |  | 325 |  |  | 2026-12-09 | 14/09/2026 | 2026-03-08 | 2026-12-08 | 325 | 325 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-12-08 | 325 | 325
ADIDAS | 0902971009-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 433 | 30/09/2026 | 433 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902971009 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 433 | 138 | 295 |  | 138 | 2026-11-09 | 2026-12-09 | 2026-10-08 | 20/08/2026 | 433 | 433 |  |  |  | 2026-09-09 | 2026-10-09 | 2026-10-08 | 19/08/2026 | 433 | 433
ADIDAS | 0902971034-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902971034 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 24/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 65 | 65 |  |  |  | 19/08/2026 | 27/08/2026 | 31/07/2026 | 26/08/2026 | 65 | 65
ADIDAS | 0902971040-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 674 | 30/09/2026 | 674 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902971040 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 674 |  | 674 |  |  | 18/09/2026 | 19/09/2026 |  |  | 674 |  | 674 |  |  | 16/09/2026 | 17/09/2026 |  |  | 674 |  | 674
ADIDAS | 0902971044-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 54 | 30/09/2026 | 54 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902971044 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 54 |  | 54 |  |  | 16/09/2026 | 17/09/2026 |  |  | 54 |  | 54
ADIDAS | 0902971059-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 562 | 15/09/2026 | 562 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902971059 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-11-09 | 562 | 562 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-11-09 | 562 | 562 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-08-09 | 2026-11-09 | 562 | 562
ADIDAS | 0902971713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1094 | 23/09/2026 | 1094 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902971713 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-12-08 | 1094 | 1094 |  |  |  | 2026-03-08 | 2026-10-08 | 2026-04-08 | 14/08/2026 | 1094 | 1094
ADIDAS | 0902972065-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 514 | 30/09/2026 | 514 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972065 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 514 |  | 514 |  |  | 24/09/2026 | 26/09/2026 |  |  | 514 |  | 514
ADIDAS | 0902972095-1 LE8187 | BLACK | 105D | S2754MAS513 | 320 | 15/09/2026 | 320 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972095 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-09 | M SL WV TP PT BLACK |  | SS27 | 2026-08-09 | 18/09/2026 | 2026-11-09 | 15/09/2026 | 320 | 185 | 135 |  | 14 | 2026-04-09 | 15/09/2026 | 29/08/2026 | 2026-12-09 | 320 | 291 | 29
ADIDAS | 0902972376-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 4291 | 2026-05-09 | 4291 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 04/09: ex-fty 516400 | EMBRO SUB PROCESS_V1 | 0902972376 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | M FEELCOZY PANT |  | FW26 | 27/07/2026 | 2026-07-08 | 27/07/2026 | 2026-07-08 | 4291 | 4291 |  |  |  | 22/07/2026 | 2026-04-08 | 18/07/2026 | 2026-05-08 | 4291 | 4291
ADIDAS | 0902972659-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1 | 2026-05-09 | 1 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972659 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1 |  |  |  | 24/08/2026 | 27/08/2026 | 14/08/2026 | 14/08/2026 | 1 | 1
ADIDAS | 0902972672-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1 | 23/09/2026 | 1 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972672 LF0726 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 1 |  | 1 |  |  | 16/09/2026 | 18/09/2026 |  |  | 1 |  | 1
ADIDAS | 0902972711-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 56 | 2026-05-09 | 56 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | ok | 04/09: ex-fty 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902972711 KY5988 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-08 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-07-08 | 56 | 56 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 31/07/2026 | 56 | 56 |  |  |  | 22/07/2026 | 31/07/2026 | 30/07/2026 | 30/07/2026 | 56 | 56
ADIDAS | 0902972724-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 349 | 15/10/2026 | 349 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972724 LG9666 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | W SL WV TT BLACK |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 349 |  | 349 |  |  | 2026-01-10 | 2026-01-10 |  |  | 349 |  | 349
ADIDAS | 0902972758-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 330 | 15/10/2026 | 330 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972758 LG9661 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 330 |  | 330 |  |  | 28/09/2026 | 2026-01-10 |  |  | 330 |  | 330
ADIDAS | 0902972883-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 480 | 15/09/2026 | 480 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972883 LF0727 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 17/09/2026 | 27/08/2026 | 2026-10-09 | 480 | 479 | 1 |  |  | 19/08/2026 | 14/09/2026 | 24/08/2026 | 2026-09-09 | 480 | 480
ADIDAS | 0902972938-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 486 | 23/09/2026 | 486 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902972938 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 486 | 486 |  |  |  | 2026-12-08 | 29/08/2026 | 29/07/2026 | 31/07/2026 | 486 | 486 |  |  |  | 2026-10-08 | 27/08/2026 | 28/07/2026 | 31/07/2026 | 486 | 486
ADIDAS | 0902973524-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1200 | 15/10/2026 | 1200 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 19-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902973524 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1200 |  | 1200 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902973591-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 894 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973591 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902973619-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 1000 | 23/09/2026 | 1000 | AN | AN29/05/2026 | G3G,G3H,G3J | PANTS | G3 | ok | (19/06/2026) | 18/09: ex-fty. T2 Libolon, PI Date 31-May, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973619 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-04-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 1000 | 1000 |  |  |  | 30/07/2026 | 13/08/2026 | 31/07/2026 | 15/08/2026 | 1000 | 1000
ADIDAS | 0902973641-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2142 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973641 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902973776-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 23/09/2026 | 300 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902973776 KF5311 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 300 | 300 |  |  |  | 2026-03-08 | 29/08/2026 | 29/07/2026 | 30/07/2026 | 300 | 300 |  |  |  | 30/07/2026 | 27/08/2026 | 27/07/2026 | 29/07/2026 | 300 | 300
ADIDAS | 0902973810-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 399 | 2026-05-09 | 399 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902973810 LE5609 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/07/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 31/08/2026 | 31/07/2026 | 31/08/2026 | 399 | 399 |  |  |  | 27/07/2026 | 27/08/2026 | 30/07/2026 | 2026-07-08 | 399 | 399 |  |  |  | 20/07/2026 | 19/08/2026 | 30/07/2026 | 2026-06-08 | 399 | 399
ADIDAS | 0902973847-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (07/07/2026) |  | 07/09: ex-fty. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock, T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973847 LC5741 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902973850-1 LF0723 | BLACK | 105D | S2754MAS511B | 433 | 15/09/2026 | 433 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902973850 LF0723 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | M SL WV SHO BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-05-09 | 2026-11-09 | 433 | 433 |  |  |  | 2026-02-09 | 2026-10-09 | 15/08/2026 | 2026-11-09 | 433 | 433
ADIDAS | 0902973860-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (29/06/2026) | ok | 07/09: ex-fty. T2 Kahatex, using fabric stock. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973860 KY6616 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 3S WV WB LND |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 26/08/2026 | 1 | 1 |  |  |  | 19/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 1 | 1
ADIDAS | 0902973878-1 LC5739 | OLIVE FOUR S27/BLACK | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (10/07/2026) |  | 07/09: ex-fty. T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 01-Jul, actual receives 09-Jul. T2 Kahatex, PI Date 07-Jul, using fabric stock. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973878 LC5739 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 3S WV WB LND OLIVE FOUR S27/BLACK |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902974162-1 LE8187 | BLACK | 105D | S2754MAS513 | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974162 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-11-08 | 2026-11-08 | 8 | 8 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-08-08 | 2026-11-08 | 8 | 8
ADIDAS | 0902974179-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974179 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902974202-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 542 | 2026-05-09 | 542 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974202 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 542 | 542 |  |  |  | 29/08/2026 | 2026-02-09 | 14/08/2026 | 28/08/2026 | 542 | 542
ADIDAS | 0902974244-1 LE8187 | BLACK | 105D | S2754MAS513 | 311 | 2026-05-09 | 311 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974244 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-09 | M SL WV TP PT BLACK |  | SS27 | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 311 | 311 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-05-08 | 2026-04-09 | 311 | 311
ADIDAS | 0902974263-1 LE8187 | BLACK | 105D | S2754MAS513 | 1425 | 2026-05-09 | 1425 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974263 LE8187 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 1425 | 1425 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-06-08 | 2026-11-09 | 1425 | 1405 | 20
ADIDAS | 0902974284-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1436 | 15/09/2026 | 1436 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974284 LD5446 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-07-09 | 16/09/2026 | 2026-07-09 | 14/09/2026 | 1436 | 1436 |  |  |  | 2026-03-09 | 2026-12-09 | 2026-12-08 | 14/09/2026 | 1436 | 1436
ADIDAS | 0902974308-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 353 | 2026-09-09 | 353 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974308 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-07-09 | 353 | 353 |  |  |  | 29/08/2026 | 2026-03-09 | 13/08/2026 | 2026-02-09 | 353 | 353
ADIDAS | 0902974332-1 LE8187 | BLACK | 105D | S2754MAS513 | 370 | 2026-05-09 | 370 | SI | SI29/05/2026 | G3D,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974332 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-03-09 | 14/08/2026 | 2026-01-09 | 370 | 370 |  |  |  | 2026-03-08 | 31/08/2026 | 2026-05-08 | 14/09/2026 | 370 | 370
ADIDAS | 0902975286-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 29 | 23/09/2026 | 29 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975286 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-10-08 | 2026-10-08 | 29 | 29 |  |  |  | 2026-03-08 | 2026-06-08 | 2026-01-08 | 2026-01-08 | 29 | 29 |  |  |  | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 29 | 29
ADIDAS | 0902975671-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1236 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902975671 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902975694-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1272 | 30/09/2026 | 1272 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902975694 LD0287 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 1272 |  | 1272 |  |  | 17/09/2026 | 18/09/2026 | 2026-05-09 | 15/09/2026 | 1272 | 1269 | 3 |  | 1 | 15/09/2026 | 16/09/2026 | 2026-04-09 | 14/09/2026 | 1272 | 1269 | 3
ADIDAS | 0902975717-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1200 | 2026-07-10 | 1200 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902975717 LE5390 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1200 |  | 1200 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902975773-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902975773 LE5391 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27 | 30/09/2026 | 2026-03-10 |  |  | 4800 |  | 4800 |  |  | 26/09/2026 | 30/09/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902975811-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 80 | 30/09/2026 | 80 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975811 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 80 |  | 80 |  |  | 2026-12-09 | 14/09/2026 | 2026-04-08 | 2026-04-08 | 80 | 80 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 80 | 80
ADIDAS | 0902975855-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 31 | 30/09/2026 | 31 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975855 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 31 | 31 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 31/07/2026 | 31 | 31 |  |  |  | 31/08/2026 | 2026-03-09 | 27/07/2026 | 28/07/2026 | 31 | 31
ADIDAS | 0902975887-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 2400 | 2026-07-10 | 2400 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975887 LE7510 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-09-10 | 13/10/2026 |  |  | 2400 |  | 2400
ADIDAS | 0902975946-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | 23/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Sep. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975946 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 25/09/2026 | 2026-03-10 |  |  | 2400 |  | 2400 |  |  | 22/09/2026 | 30/09/2026 | 26/08/2026 | 2026-07-09 | 2400 | 1864 | 536
ADIDAS | 0902975975-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975975 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-09 | 19/09/2026 | 2026-03-09 | 15/09/2026 | 2400 | 1665 | 735 |  | 255 | 2026-02-09 | 16/09/2026 | 22/08/2026 | 2026-08-09 | 2400 | 2356 | 44
ADIDAS | 0902976008-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3600 | 2026-07-10 | 3600 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976008 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 19/10/2026 | 23/10/2026 |  |  | 3600 |  | 3600 |  |  | 15/10/2026 | 20/10/2026 |  |  | 3600 |  | 3600
ADIDAS | 0902976049-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 2026-07-10 | 6000 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976049 LE7509 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27 | 2026-06-10 | 14/10/2026 |  |  | 6000 |  | 6000 |  |  | 2026-02-10 | 2026-10-10 |  |  | 6000 |  | 6000
ADIDAS | 0902976088-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 2026-07-10 | 8400 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976088 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 14/10/2026 | 26/10/2026 |  |  | 8400 |  | 8400 |  |  | 2026-10-10 | 22/10/2026 |  |  | 8400 |  | 8400
ADIDAS | 0902976602-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1120 | 31/10/2026 | 1120 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902976602 LD0287 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-10 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 1120 |  | 1120 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1120 |  | 1120 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902976952-1 LG9669 | BLACK | 120D | S2754WAS514C | 8 | 15/10/2026 | 8 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902976952 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 8 |  | 8 |  |  | 2026-10-10 | 2026-12-10 |  |  | 8 |  | 8
ADIDAS | 0902976974-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 8 | 15/10/2026 | 8 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902976974 LF0726 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 8 |  | 8 |  |  | 16/09/2026 | 18/09/2026 |  |  | 8 |  | 8
ADIDAS | 0902977144-1 LE8187 | BLACK | 105D | S2754MAS513 | 342 | 2026-05-09 | 342 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902977144 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 14/08/2026 | 342 | 342 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-05-08 | 2026-04-09 | 342 | 342
ADIDAS | 0902977685-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1796 | 30/09/2026 | 1796 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 29/09: ex-fty (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902977685 KX3655 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 26/09/2026 |  |  | 1796 |  | 1796 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1796 |  | 1796 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1796 |  | 1796
ADIDAS | 0902977729-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 466 | 15/10/2026 | 466 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | HT+PAD SUB PROCESS_V3 | 0902977729 LD0288 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 466 | 466 |  |  |  | 2026-12-08 | 29/08/2026 | 25/07/2026 | 2026-06-08 | 466 | 466 |  |  |  | 2026-10-08 | 27/08/2026 | 24/07/2026 | 2026-05-08 | 466 | 466
ADIDAS | 0902977769-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 497 | 30/09/2026 | 497 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977769 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 497 |  | 497 |  |  | 2026-11-09 | 2026-12-09 |  |  | 497 |  | 497 |  |  | 2026-09-09 | 2026-10-09 |  |  | 497 |  | 497
ADIDAS | 0902977806-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 198 | 23/09/2026 | 198 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977806 LD0288 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 198 | 198 |  |  |  | 2026-12-08 | 29/08/2026 | 30/07/2026 | 2026-07-08 | 198 | 198 |  |  |  | 2026-10-08 | 27/08/2026 | 29/07/2026 | 2026-06-08 | 198 | 198
ADIDAS | 0902977843-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 200 | 15/10/2026 | 200 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902977843 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 200 |  | 200 |  |  | 21/09/2026 | 22/09/2026 |  |  | 200 |  | 200 |  |  | 18/09/2026 | 19/09/2026 |  |  | 200 |  | 200
ADIDAS | 0902977881-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 504 | 31/10/2026 | 504 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 800187 | HT+PAD SUB PROCESS_V3 | 0902977881 LD0287 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 504 |  | 504 |  |  | 29/09/2026 | 30/09/2026 |  |  | 504 |  | 504 |  |  | 26/09/2026 | 28/09/2026 |  |  | 504 |  | 504
ADIDAS | 0902977919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 154 | 30/09/2026 | 154 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977919 LD0288 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 154 | 154 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 2026-01-08 | 154 | 154 |  |  |  | 31/08/2026 | 2026-03-09 | 30/07/2026 | 2026-01-08 | 154 | 154
ADIDAS | 0902977969-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 879 | 30/09/2026 | 879 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977969 KX3655 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 879 |  | 879 |  |  | 17/09/2026 | 18/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879 |  |  |  | 15/09/2026 | 16/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879
ADIDAS | 0902978212-1 LE0355 | BLACK | 105D | S2754MAS514 | 2156 | 30/09/2026 | 2156 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978212 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | M SL WV CU PT BLACK |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 2156 |  | 2156 |  |  | 30/09/2026 | 2026-02-10 | 2026-01-09 | 2026-12-09 | 2156 | 2044 | 112
ADIDAS | 0902978235-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 2398 | 30/09/2026 | 2398 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978235 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 2398 | 927 | 1471 |  | 927 | 2026-10-09 | 2026-12-09 | 2026-11-08 | 20/08/2026 | 2398 | 2398 |  |  |  | 2026-08-09 | 2026-10-09 | 2026-11-08 | 19/08/2026 | 2398 | 2398
ADIDAS | 0902978263-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1644 | 30/09/2026 | 1644 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978263 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 1644 |  | 1644 |  |  | 19/09/2026 | 21/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1557 | 87 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1556 | 88
ADIDAS | 0902978291-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 2268 | 30/09/2026 | 2268 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978291 LD0287 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 2268 |  | 2268 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-09 | 15/09/2026 | 2268 | 2205 | 63 |  | 72 | 16/09/2026 | 17/09/2026 | 2026-07-09 | 14/09/2026 | 2268 | 2209 | 59
ADIDAS | 0902978328-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1623 | 30/09/2026 | 1623 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978328 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-10 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 1623 |  | 1623 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1623 |  | 1623
ADIDAS | 0902978352-1 LF0718 | BLACK | 105D | S2754MAS512B | 1886 | 15/09/2026 | 1886 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978352 LF0718 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 1886 |  | 1886 |  |  | 16/09/2026 | 19/09/2026 | 15/09/2026 | 15/09/2026 | 1886 | 194 | 1692 |  | 194
ADIDAS | 0902978382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1442 | 15/09/2026 | 1442 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978382 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 17/09/2026 | 2026-02-09 | 2026-11-09 | 1442 | 1423 | 19 |  |  | 27/08/2026 | 14/09/2026 | 28/08/2026 | 15/09/2026 | 1442 | 1438 | 4 |  | 3
ADIDAS | 0902978413-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 1394 | 15/09/2026 | 1394 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978413 LG9670 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | W SL WV PT AURORA COFFEE S26 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 1394 | 1321 | 73 |  | 31 | 2026-05-09 | 2026-11-09 | 2026-07-09 | 2026-10-09 | 1394 | 1338 | 56
ADIDAS | 0902978440-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 767 | 30/09/2026 | 767 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978440 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 767 | 241 | 526 |  | 241 | 2026-11-09 | 14/09/2026 | 14/09/2026 | 15/09/2026 | 767 | 576 | 191 |  | 315
ADIDAS | 0902978469-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 491 | 30/09/2026 | 491 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978469 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 491 |  | 491 |  |  | 15/09/2026 | 16/09/2026 |  |  | 491 |  | 491
ADIDAS | 0902978495-1 LE8187 | BLACK | 105D | S2754MAS513 | 1353 | 15/09/2026 | 1353 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978495 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 15/09/2026 | 2026-04-09 | 2026-09-09 | 1353 | 1115 | 238 |  |  | 2026-02-09 | 2026-11-09 | 28/08/2026 | 2026-10-09 | 1353 | 1232 | 121
ADIDAS | 0902978547-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1342 | 15/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978547 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 17/09/2026 | 26/08/2026 | 14/09/2026 | 1342 | 1140 | 202 |  |  | 19/08/2026 | 14/09/2026 | 21/08/2026 | 15/09/2026 | 1342 | 1311 | 31 |  | 135
ADIDAS | 0902978578-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 870 | 30/09/2026 | 870 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 20-Jun, actual receives 06-AUg (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978578 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV TT BLACK |  | SS27 | 22/09/2026 | 26/09/2026 |  |  | 870 |  | 870 |  |  | 18/09/2026 | 23/09/2026 | 28/08/2026 | 2026-03-09 | 870 | 537 | 333
ADIDAS | 0902978872-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 339 | 2026-09-09 | 339 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978872 LD5446 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-03-09 | 339 | 339 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 20/08/2026 | 339 | 339
ADIDAS | 0902978908-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 2026-05-09 | 300 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978908 LE8181 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-03-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0902978941-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 23/09/2026 | 300 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978941 LF0729 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 18/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0902978973-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 347 | 15/09/2026 | 347 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual recieves 27-Jun (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978973 LF0726 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-07-09 | 15/09/2026 | 347 | 344 | 3 |  | 1 | 2026-01-09 | 14/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 347
ADIDAS | 0902978999-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1030 | 2026-12-09 | 1030 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902978999 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 31/08/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1030 | 1030 |  |  |  | 27/08/2026 | 2026-04-09 | 31/07/2026 | 2026-07-08 | 1030 | 1030 |  |  |  | 24/08/2026 | 2026-02-09 | 31/07/2026 | 2026-06-08 | 1030 | 1030
ADIDAS | 0902979020-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 1006 | 2026-12-09 | 1006 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979020 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-05-09 | 2026-08-09 | 1006 | 1006 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-03-08 | 13/08/2026 | 1006 | 1006 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-01-08 | 2026-12-08 | 1006 | 1006
ADIDAS | 0902979825-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 2026-12-09 | 123 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902979825 LD5446 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 123 | 123 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 123 | 123
ADIDAS | 0902980168-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 574 | 30/09/2026 | 574 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980168 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 574 |  | 574 |  |  | 22/09/2026 | 24/09/2026 |  |  | 574 |  | 574
ADIDAS | 0902980203-1 LE8187 | BLACK | 105D | S2754MAS513 | 812 | 15/09/2026 | 812 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980203 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 812 | 9 | 803 |  | 9 | 2026-10-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 812 | 462 | 350
ADIDAS | 0902980461-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 895 | 15/09/2026 | 895 | AN | AN29/05/2026 | G3B,G3E,G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980461 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 15/09/2026 | 895 | 831 | 64 |  | 117 | 20/08/2026 | 2026-11-09 | 2026-06-08 | 26/08/2026 | 895 | 864 | 31
ADIDAS | 0902980492-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1236 | 15/09/2026 | 1236 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980492 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 1236 | 1236 |  |  | 23 | 2026-05-09 | 2026-11-09 | 2026-11-08 | 2026-10-09 | 1236 | 1214 | 22
ADIDAS | 0902980497-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1200 | 30/09/2026 | 1200 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902980497 LD0287 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 17/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1200 |  | 1200 |  |  | 14/09/2026 | 15/09/2026 | 2026-03-08 | 14/09/2026 | 1200 | 1200 |  |  |  | 2026-11-09 | 2026-12-09 | 2026-01-08 | 14/09/2026 | 1200 | 1200
ADIDAS | 0902980516-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2141 | 23/10/2026 | 2141 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980516 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 2026-11-08 | 31/08/2026 | 2141 | 2141 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-08-08 | 21/08/2026 | 2141 | 2125 | 16
ADIDAS | 0902980530-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 901 | 15/09/2026 | 901 | AN | AN29/05/2026 | G1B,G1J | JACKET | G1 | ok | (19/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980530 LG9666 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-09 | W SL WV TT BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-09-09 | 15/09/2026 | 901 | 755 | 146 |  | 40 | 2026-04-09 | 2026-12-09 | 22/08/2026 | 15/09/2026 | 901 | 813 | 88 |  | 8
ADIDAS | 0902980559-1 LH3758 | BLACK | 120D | S2754WAS518B | 800 | 30/09/2026 | 800 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980559 LH3758 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | W SL WV BR PT BLACK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 800 |  | 800 |  |  | 18/09/2026 | 18/09/2026 |  |  | 800 |  | 800
ADIDAS | 0902980595-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 1066 | 15/09/2026 | 1066 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980595 LG9664 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 1066 |  | 1066 |  |  | 2026-11-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 1066 | 968 | 98 |  | 14
ADIDAS | 0902980626-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 1094 | 30/09/2026 | 1094 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980626 LH3761 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1094 |  | 1094 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1094 |  | 1094
ADIDAS | 0902980662-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1530 | 15/09/2026 | 1530 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980662 LE8181 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 19/09/2026 | 2026-12-09 | 2026-12-09 | 1530 | 105 | 1425 |  |  | 2026-10-09 | 16/09/2026 | 2026-11-09 | 14/09/2026 | 1530 | 585 | 945
ADIDAS | 0902980942-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 2026-07-10 | 300 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980942 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TT BLACK |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0902980969-1 LE8187 | BLACK | 105D | S2754MAS513 | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980969 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TP PT BLACK |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 420 |  | 420 |  |  | 2026-07-10 | 2026-09-10 |  |  | 420 |  | 420
ADIDAS | 0902981008-1 LE8187 | BLACK | 105D | S2754MAS513 | 300 | 2026-07-10 | 300 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 08-Jul. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981008 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TP PT BLACK |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0902981035-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 360 | 2026-07-10 | 360 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981035 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-10-09 | 17/09/2026 | 2026-11-09 | 14/09/2026 | 360 | 214 | 146 |  |  | 2026-07-09 | 14/09/2026 | 2026-04-09 | 2026-04-09 | 360 | 293 | 67
ADIDAS | 0902981042-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 120 | 2026-09-09 | 120 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981042 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 120 | 120 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 14/08/2026 | 120 | 120
ADIDAS | 0902981068-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 532 | 2026-05-09 | 532 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 672027 | HT+PAD SUB PROCESS_V3 | 0902981068 KX3650 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 2026-05-08 | 30/07/2026 | 2026-05-08 | 532 | 532 |  |  |  | 27/07/2026 | 31/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532 |  |  |  | 23/07/2026 | 29/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532
ADIDAS | 0902981100-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 672027 | HT+PAD SUB PROCESS_V3 | 0902981100 KX3655 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 17 | 283 |  | 17 | 2026-11-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 300 | 240 | 60 |  |  | 2026-09-09 | 2026-10-09 | 2026-09-09 | 2026-12-09 | 300 | 240 | 60
ADIDAS | 0902981242-1 LG9669 | BLACK | 120D | S2754WAS514C | 15 | 30/09/2026 | 15 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902981242 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/09/2026 | W SL WV SK BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 15 |  | 15 |  |  | 25/09/2026 | 28/09/2026 | 29/08/2026 | 2026-01-09 | 15 | 15
ADIDAS | 0902981317-1 LD0282 | OLIVE TWO S27 | 120D | S2608WR0900 | 185 | 30/09/2026 | 185 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). 1st Art (TC 10 pcs) 650010 | HT+PAD SUB PROCESS_V3 | 0902981317 LD0282 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 18/09/2026 | Run Ess Tee W OLIVE TWO S27 |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 185 |  | 185 |  |  | 15/09/2026 | 16/09/2026 | 2026-01-08 | 2026-08-08 | 185 | 185 |  |  |  | 2026-12-09 | 14/09/2026 | 31/07/2026 | 2026-07-08 | 185 | 185
ADIDAS | 0902981358-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 10 | 15/10/2026 | 10 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0902981358 LD0285 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10
ADIDAS | 0902981395-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 21 | 30/09/2026 | 21 | SI | SI29/05/2026 | G3A | SHORTS | G3 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981395 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-09-09 | 2026-09-09 | 21 | 21 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 21 | 21
ADIDAS | 0902981438-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 30/09/2026 | 120 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0902981438 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV SK BLACK |  | SS27-SPOMA | 29/09/2026 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 25/09/2026 | 28/09/2026 | 28/08/2026 | 2026-05-09 | 120 | 114 | 6
ADIDAS | 0902981755-1 LF0723 | BLACK | 105D | S2754MAS511B | 1697 | 30/09/2026 | 1697 | SI | SI29/05/2026 | G3D | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Kahatex, PI Date 28-Jul, actual 10-Aug. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981755 LF0723 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | M SL WV SHO BLACK |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1697 |  | 1697 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1697 |  | 1697
ADIDAS | 0902981783-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 1824 | 23/09/2026 | 1824 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902981783 LD0288 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 18/08/2026 | 2026-01-09 | 1824 | 1824 |  |  |  | 2026-11-08 | 29/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824
ADIDAS | 0902981811-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 712 | 15/09/2026 | 712 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981811 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 712 |  | 712 |  |  | 16/09/2026 | 18/09/2026 | 2026-11-09 | 15/09/2026 | 712 | 663 | 49 |  | 65
ADIDAS | 0902981835-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 1342 | 30/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981835 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/08/2026 | 2026-10-09 | 20/08/2026 | 2026-10-09 | 1342 | 1342 |  |  |  | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-03-09 | 1342 | 1342
ADIDAS | 0902981856-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 1297 | 15/09/2026 | 1297 | SI | SI29/05/2026 | G3A,G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981856 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 19/09/2026 | 2026-10-09 | 2026-12-09 | 1297 | 1245 | 52 |  |  | 2026-07-09 | 16/09/2026 | 2026-03-09 | 2026-12-09 | 1297 | 1270 | 27
ADIDAS | 0902981919-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 425 | 15/09/2026 | 425 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981919 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 425 | 303 | 122 |  | 59 | 2026-04-09 | 2026-12-09 | 2026-01-09 | 2026-07-09 | 425 | 356 | 69
ADIDAS | 0902981952-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 300 | 30/09/2026 | 300 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902981952 LG9668 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-01-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902981983-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 619 | 15/09/2026 | 619 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981983 LG9661 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 619 | 453 | 166 |  | 182 | 2026-09-09 | 2026-11-09 | 26/08/2026 | 2026-10-09 | 619 | 545 | 74
ADIDAS | 0902982085-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 814 | 30/09/2026 | 814 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902982085 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV PT BLACK |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 814 |  | 814 |  |  | 18/09/2026 | 21/09/2026 |  |  | 814 |  | 814
ADIDAS | 0902982159-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 10 | 2026-05-09 | 10 | AN | AN29/05/2026 | G1E | T-SHIRT | G1 | ok | ok | 04/09: ex-fty (KN GLT). T2 Libolon, actual receives 29-Apr (PO 25063167). T2 Fu Hsun, actual receives 23-Apr (PO 25063168). 650010 | HT SUB PROCESS_V1 | 0902982159 IT1824 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 10 | 10 |  |  |  | 14/07/2026 | 16/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10
ADIDAS | 0902982427-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 363 | 31/10/2026 | 363 | ID | ID29/05/2026 | G2J | T-SHIRT | G2 | (28/07/2026) | (27/06/2026) | DRC 0090-early shipment customer (BTP_12_06_2026 EARLY HOLD SHIPMENT). 800187 | HT+PAD SUB PROCESS_V3 | 0902982427 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-10-10 | Run Ess Tee W BLACK |  | SS27-SLT-TI | 2026-10-10 | 2026-10-10 |  |  | 363 |  | 363 |  |  | 2026-07-10 | 2026-07-10 |  |  | 363 |  | 363 |  |  | 2026-05-10 | 2026-05-10 |  |  | 363 |  | 363
ADIDAS | 0902982687-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902982687 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0902982718-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 400 | 2026-03-09 | 400 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | ok | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982718 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-07-08 | 400 | 400 |  |  |  | 24/07/2026 | 2026-05-08 | 27/07/2026 | 29/08/2026 | 400 | 400
ADIDAS | 0902982774-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 321 | 31/10/2026 | 321 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902982774 LD0285 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 321 |  | 321 |  |  | 2026-02-10 | 2026-03-10 | 2026-04-08 | 2026-07-08 | 321 | 321 |  |  |  | 30/09/2026 | 2026-01-10 | 2026-01-08 | 2026-06-08 | 321 | 321
ADIDAS | 0902982800-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902982800 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902982827-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 524 | 31/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902982827 LD0285 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-06-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 524 |  | 524 |  |  | 2026-02-10 | 2026-03-10 | 2026-04-08 | 2026-10-08 | 524 | 524 |  |  |  | 30/09/2026 | 2026-01-10 | 2026-01-08 | 2026-10-08 | 524 | 524
ADIDAS | 0902982852-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982852 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 320 |  | 320 |  |  | 21/09/2026 | 21/09/2026 | 2026-07-08 | 15/08/2026 | 320 | 320 |  |  |  | 18/09/2026 | 18/09/2026 | 2026-07-08 | 14/08/2026 | 320 | 320
ADIDAS | 0902982880-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982880 LD0287 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 350 |  | 350 |  |  | 19/09/2026 | 19/09/2026 |  |  | 350 |  | 350 |  |  | 17/09/2026 | 17/09/2026 |  |  | 350 |  | 350
ADIDAS | 0902982910-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982910 LD0285 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 19/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902982939-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982939 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 21/09/2026 | 21/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350 |  |  |  | 18/09/2026 | 18/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350
ADIDAS | 0902982968-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 414 | 30/09/2026 | 414 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982968 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 414 |  | 414 |  |  | 16/09/2026 | 17/09/2026 | 25/07/2026 | 2026-01-08 | 414 | 414 |  |  |  | 14/09/2026 | 15/09/2026 | 25/07/2026 | 31/07/2026 | 414 | 414
ADIDAS | 0902982993-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 810 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902982993 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0902983024-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1000 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902983024 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0902983061-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902983061 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902983088-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 320 | 30/09/2026 | 320 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516254 | HT+PAD SUB PROCESS_V3 | 0902983088 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 320 |  | 320 |  |  | 2026-12-09 | 14/09/2026 | 26/08/2026 | 2026-05-09 | 320 | 320 |  |  |  | 2026-10-09 | 2026-11-09 | 26/08/2026 | 2026-05-09 | 320 | 320
ADIDAS | 0902983300-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983300 KX3651 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 108 |  | 108 |  |  | 22/09/2026 | 23/09/2026 | 25/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 19/09/2026 | 21/09/2026 | 24/07/2026 | 31/07/2026 | 108 | 108
ADIDAS | 0902983336-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983336 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 108 |  | 108 |  |  | 2026-12-09 | 14/09/2026 | 26/08/2026 | 2026-08-09 | 108 | 108 |  |  |  | 2026-10-09 | 2026-11-09 | 26/08/2026 | 2026-08-09 | 108 | 108
ADIDAS | 0902983370-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 108 | 23/09/2026 | 108 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983370 KF5311 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 108 | 108 |  |  |  | 2026-06-08 | 29/08/2026 | 30/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 2026-04-08 | 27/08/2026 | 29/07/2026 | 30/07/2026 | 108 | 108
ADIDAS | 0902983535-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F,G3K | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902983535 JE8969 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 1200 | 1200 |  |  |  | 15/07/2026 | 2026-03-08 | 2026-09-07 | 2026-05-08 | 1200 | 1200
ADIDAS | 0902983568-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902983568 JE6346 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 1201 | 1201 |  |  |  | 16/07/2026 | 29/07/2026 | 18/07/2026 | 22/07/2026 | 1201 | 1201
ADIDAS | 0902983877-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 408 | 2026-05-09 | 408 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983877 LE8181 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 408 | 408 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-05-09 | 408 | 408
ADIDAS | 0902983897-1 LE8187 | BLACK | 105D | S2754MAS513 | 1822 | 2026-05-09 | 1822 | SI | SI29/05/2026 | G3D,G3I,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983897 LE8187 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-05-09 | 2026-12-08 | 2026-04-09 | 1822 | 1822 |  |  |  | 2026-03-08 | 2026-02-09 | 2026-07-08 | 2026-04-09 | 1822 | 1822
ADIDAS | 0902983913-1 LF0718 | BLACK | 105D | S2754MAS512B | 647 | 2026-05-09 | 647 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983913 LF0718 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT BLACK |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 647 | 647 |  |  |  | 27/08/2026 | 2026-02-09 | 14/08/2026 | 2026-04-09 | 647 | 647
ADIDAS | 0902983933-1 LF0723 | BLACK | 105D | S2754MAS511B | 471 | 2026-12-09 | 471 | SI | SI29/05/2026 | G3D,G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983933 LF0723 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO BLACK |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 471 | 471 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-09-09 | 471 | 471
ADIDAS | 0902983951-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 15/09/2026 | 100 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983951 LG9664 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 100 |  | 100 |  |  | 16/09/2026 | 18/09/2026 | 2026-11-09 | 2026-11-09 | 100 | 40 | 60
ADIDAS | 0902983960-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 100 | 2026-12-09 | 100 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983960 LF0725 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-12-08 | 2026-03-09 | 100 | 100
ADIDAS | 0902983978-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983978 LG9673 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 21/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 100 |  | 100 |  |  | 17/09/2026 | 17/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902983990-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983990 LG9674 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 100 |  | 100 |  |  | 16/09/2026 | 17/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902984005-1 LH3758 | BLACK | 120D | S2754WAS518B | 400 | 30/09/2026 | 400 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902984005 LH3758 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 21/09/2026 | W SL WV BR PT BLACK |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 400 |  | 400 |  |  | 17/09/2026 | 18/09/2026 |  |  | 400 |  | 400
ADIDAS | 0902984019-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902984019 LG9666 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | W SL WV TT BLACK |  | SS27 | 22/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 23/09/2026 | 31/08/2026 | 2026-03-09 | 300 | 267 | 33
ADIDAS | 0902985687-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985687 JE6374 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 29/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 2026-06-08 | 2026-02-09 | 1201 | 1201
ADIDAS | 0902985715-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 1200 | 15/09/2026 | 1200 | SI | SI29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902985715 JE8949 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-01-09 | M BL FT SWT |  | FW26 | 2026-01-09 | 2026-12-09 | 2026-01-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 28/08/2026 | 2026-09-09 | 29/07/2026 | 2026-03-09 | 1200 | 1200
ADIDAS | 0902985747-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902985747 IN6163 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 23/07/2026 | M BL FT PT |  | FW26 | 23/07/2026 | 2026-03-08 | 22/07/2026 | 30/07/2026 | 1200 | 1200 |  |  |  | 20/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 1200 | 1200
ADIDAS | 0902985818-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1201 | 2026-12-09 | 1201 | AT | AT29/05/2026 | G3C,G3D | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902985818 JD1881 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/07/2026 | M 3S FT TC PT |  | FW26 | 28/07/2026 | 2026-12-08 | 29/07/2026 | 2026-10-08 | 1201 | 1201 |  |  |  | 23/07/2026 | 2026-07-08 | 20/07/2026 | 2026-01-08 | 1201 | 1201
ADIDAS | 0902985931-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985931 JE6372 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 15/07/2026 | 18/08/2026 | 1201 | 1201
ADIDAS | 0902986122-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 112 | 2026-07-10 | 112 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902986122 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-10 | 2026-03-10 |  |  | 112 |  | 112 |  |  | 30/09/2026 | 30/09/2026 |  |  | 112 |  | 112 |  |  | 28/09/2026 | 28/09/2026 |  |  | 112 |  | 112
ADIDAS | 0902987761-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 540 | 15/10/2026 | 540 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987761 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 29/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 25/09/2026 | 26/09/2026 |  |  | 540 |  | 540 |  |  | 23/09/2026 | 24/09/2026 |  |  | 540 |  | 540
ADIDAS | 0902987861-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 529 | 15/10/2026 | 529 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987861 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 29/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 529 |  | 529 |  |  | 25/09/2026 | 26/09/2026 |  |  | 529 |  | 529 |  |  | 23/09/2026 | 24/09/2026 |  |  | 529 |  | 529
ADIDAS | 0902987900-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902987900 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 15/09/2026 | 2026-12-08 | 13/08/2026 | 300 | 244 | 56 |  |  | 2026-05-08 | 2026-11-09 | 2026-10-08 | 31/08/2026 | 300 | 266 | 34
ADIDAS | 0902988860-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 231 | 2026-07-10 | 231 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988860 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 231 |  | 231 |  |  | 20/10/2026 | 21/10/2026 |  |  | 231 |  | 231 |  |  | 14/10/2026 | 15/10/2026 |  |  | 231 |  | 231
ADIDAS | 0902988896-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 481 | 15/09/2026 | 481 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD) 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988896 KC8152 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 481 | 481 |  |  | 4 | 2026-02-09 | 2026-10-09 | 2026-04-09 | 2026-11-09 | 481 | 481 |  |  |  | 27/08/2026 | 2026-04-09 | 2026-04-09 | 2026-09-09 | 481 | 481
ADIDAS | 0902990760-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 144 | 23/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990760 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902990885-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 110 | 15/10/2026 | 110 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990885 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 110 |  | 110 |  |  | 24/09/2026 | 25/09/2026 |  |  | 110 |  | 110 |  |  | 22/09/2026 | 23/09/2026 |  |  | 110 |  | 110
ADIDAS | 0902993705-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 2026-12-09 | 368 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (19/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993705 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-06-08 | 368 | 368 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 19/08/2026 | 368 | 368
ADIDAS | 0902993759-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 405 | 15/09/2026 | 405 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902993759 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 405 | 391 | 14 |  |  | 2026-01-09 | 2026-11-09 | 2026-10-08 | 2026-10-09 | 405 | 405
ADIDAS | 0902993780-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 600 | 2026-05-09 | 600 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993780 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-03-08 | 2026-11-08 | 600 | 600 |  |  |  | 29/07/2026 | 2026-10-08 | 28/07/2026 | 2026-10-08 | 600 | 600
ADIDAS | 0902997868-1 KB5960 | WHITE | 120D | S2608MR0900A | 524 | 15/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902997868 KB5960 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 524 |  | 524 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 27/08/2026 | 524 | 524 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 26/08/2026 | 524 | 524
ADIDAS | 0902997893-1 KB5960 | WHITE | 120D | S2608MR0900A | 500 | 31/10/2026 | 500 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902997893 KB5960 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | Run Ess Tee M |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 500 |  | 500 |  |  | 2026-09-10 | 2026-10-10 | 2026-02-09 | 15/09/2026 | 500 | 455 | 45 |  | 8 | 2026-07-10 | 2026-08-10 | 2026-02-09 | 2026-12-09 | 500 | 500
ADIDAS | 0903017607-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 1100 | 2026-05-09 | 1100 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok |  | 05/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903017607 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV WB |  | SS27 | 29/07/2026 | 31/08/2026 | 29/07/2026 | 31/08/2026 | 1100 | 1100 |  |  |  | 24/07/2026 | 27/08/2026 | 22/07/2026 | 2026-01-09 | 1100 | 1100
ADIDAS | 0903031703-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 2026-05-09 | 313 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031703 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 313 | 313 |  |  |  | 29/07/2026 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 313 | 313
ADIDAS | 0903031747-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 352 | 2026-05-09 | 352 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031747 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 352 | 352 |  |  |  | 24/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 352 | 352
ADIDAS | 0903031828-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 1176 | 30/09/2026 | 1176 | AN | AN12/06/2026 | G1E | T-SHIRT | G1 | ok | (02/07/2026) | 22/09: ex-fty. T2 Libolon, PI Date 29-Aug, actual receives 30-Jul. T2 Fu Hsun, actual receives 14-Jan (PO 25063168). 600000 | HT SUB PROCESS_V1 | 0903031828 IT1824 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 24/09/2026 |  |  | 1176 |  | 1176 |  |  | 19/09/2026 | 22/09/2026 | 2026-09-09 | 15/09/2026 | 1176 | 1154 | 22 |  | 19 | 18/09/2026 | 21/09/2026 | 2026-09-09 | 15/09/2026 | 1176 | 1162 | 14 |  | 7
ADIDAS | 0903031894-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 7560 | 2026-05-09 | 7560 | AN | AN12/06/2026 | G3A,G3B,G3C,G3E,G3F,G3G,G3H,G3J | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jul. T2 Libolon, PI Date 06-Jul, actual receives 22-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031894 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-04-08 | 19/08/2026 | 7560 | 7560 |  |  |  | 29/07/2026 | 18/08/2026 | 30/07/2026 | 20/08/2026 | 7560 | 7560
ADIDAS | 0903031957-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 540 | 2026-12-09 | 540 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903031957 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 540 | 540 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 18/08/2026 | 540 | 540
ADIDAS | 0903032010-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | ok | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 17-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903032010 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-10-08 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 332 | 332 |  |  |  | 2026-05-08 | 13/08/2026 | 2026-11-08 | 18/08/2026 | 332 | 332
ADIDAS | 0903037254-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037254 LH3761 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903037304-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037304 LH3759 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903042722-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 2026-09-09 | 344 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903042722 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 344 | 344 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 344 | 344
ADIDAS | 0903042749-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 300 | 30/09/2026 | 300 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903042749 LE5389 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 18/09/2026 | 2026-11-08 | 26/08/2026 | 300 | 300
ADIDAS | 0903043064-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903043064 LF0729 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903043439-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 15/10/2026 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903043439 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 4002 |  | 4002 |  |  | 2026-02-10 | 2026-06-10 |  |  | 4002 |  | 4002
ADIDAS | 0903043644-1 KB5965 | BLACK | 120D | S2608MR0900A | 1380 | 30/09/2026 | 1380 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 23/09: ex-fty. DRC 0090-early shipment customer (BTP_23_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903043644 KB5965 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | Run Ess Tee M |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 1380 |  | 1380 |  |  | 21/09/2026 | 22/09/2026 |  |  | 1380 |  | 1380 |  |  | 18/09/2026 | 19/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903045739-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 984 | 2026-12-09 | 984 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903045739 KB5960 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | Run Ess Tee M |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-08-09 | 2026-10-09 | 984 | 984
ADIDAS | 0903045869-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 2026-07-10 | 12000 | AN | AN12/06/2026 | G3A,G3B,G3C | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045869 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 2026-06-10 | 22/10/2026 |  |  | 12000 |  | 12000 |  |  | 2026-02-10 | 19/10/2026 | 28/07/2026 | 28/07/2026 | 12000 | 1 | 11999
ADIDAS | 0903045909-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 2026-07-10 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045909 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 4002 |  | 4002 |  |  | 30/09/2026 | 2026-02-10 |  |  | 4002 |  | 4002
ADIDAS | 0903046028-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 15/10/2026 | 12000 | AN | AN12/06/2026 | G3D,G3E,G3F | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046028 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 28/10/2026 | 2026-10-11 |  |  | 12000 |  | 12000 |  |  | 24/10/2026 | 2026-06-11 |  |  | 12000 |  | 12000
ADIDAS | 0903046531-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 301 | 30/09/2026 | 301 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046531 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-02-10 | 2026-02-10 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903046557-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 121 | 2026-12-09 | 121 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046557 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 121 | 121 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 31/08/2026 | 121 | 121
ADIDAS | 0903046577-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 414 | 2026-12-09 | 414 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046577 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 414 | 414 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 2026-10-09 | 414 | 414
ADIDAS | 0903046607-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 360 | 2026-09-09 | 360 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046607 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 360 | 360 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 360 | 360
ADIDAS | 0903046624-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 2083 | 15/09/2026 | 2083 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046624 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 17/09/2026 | 2026-10-08 | 27/08/2026 | 2083 | 1632 | 451 |  |  | 2026-04-08 | 14/09/2026 | 28/07/2026 | 2026-12-09 | 2083 | 2071 | 12
ADIDAS | 0903046936-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 200 | 23/09/2026 | 200 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route. DRC 0010-hold shipment customer (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 1st Art (TC 10 pcs) 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046936 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 15/08/2026 | 200 | 200
ADIDAS | 0903046980-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 286 | 31/10/2026 | 286 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512110 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046980 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-05-09 | 2026-10-09 | 286 | 286 |  |  |  | 2026-01-09 | 14/09/2026 | 2026-10-08 | 24/08/2026 | 286 | 286
ADIDAS | 0903046982-1 KB5965 | BLACK | 120D | S2608MR0900A | 1010 | 30/09/2026 | 1010 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903046982 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | Run Ess Tee M |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 1010 |  | 1010 |  |  | 23/09/2026 | 24/09/2026 |  |  | 1010 |  | 1010 |  |  | 21/09/2026 | 22/09/2026 |  |  | 1010 |  | 1010
ADIDAS | 0903047029-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3E,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_02_07_2026 EARLY HOLD SHIPMENT). 516240 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903047029 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-09 | 16/09/2026 | 14/09/2026 | 15/09/2026 | 300 | 300 |  |  | 10 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 15/09/2026 | 300 | 300 |  |  | 3 | 2026-03-09 | 2026-07-09 | 2026-11-09 | 14/09/2026 | 300 | 300
ADIDAS | 0903047055-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 369 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903047055 KX3654 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903047077-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 350 | 2026-07-10 | 350 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516461 | HT+PAD SUB PROCESS_V3 | 0903047077 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 19/09/2026 | 21/09/2026 |  |  | 350 |  | 350 |  |  | 17/09/2026 | 18/09/2026 |  |  | 350 |  | 350
ADIDAS | 0903047104-1 KB5960 | WHITE | 120D | S2608MR0900A | 634 | 30/09/2026 | 634 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903047104 KB5960 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 634 |  | 634 |  |  | 24/09/2026 | 24/09/2026 | 2026-05-08 | 2026-10-09 | 634 | 614 | 20 |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-10-09 | 634 | 615 | 19
ADIDAS | 0903047150-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516433 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047150 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 | 28/08/2026 | 2026-04-09 | 301 | 14 | 287
ADIDAS | 0903047167-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 468 | 23/10/2026 | 468 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047167 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 468 |  | 468 |  |  | 22/10/2026 | 24/10/2026 |  |  | 468 |  | 468
ADIDAS | 0903047185-1 JZ7808 | BLACK | 120D | S2608WR0900 | 803 | 15/10/2026 | 803 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047185 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 29/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 803 |  | 803 |  |  | 25/09/2026 | 26/09/2026 |  |  | 803 |  | 803 |  |  | 23/09/2026 | 24/09/2026 |  |  | 803 |  | 803
ADIDAS | 0903047214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 2411 | 15/10/2026 | 2411 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047214 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 2026-02-10 |  |  | 2411 |  | 2411 |  |  | 26/09/2026 | 29/09/2026 |  |  | 2411 |  | 2411 |  |  | 24/09/2026 | 26/09/2026 |  |  | 2411 |  | 2411
ADIDAS | 0903047216-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 431 | 30/09/2026 | 431 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047216 KY6616 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 431 |  | 431 |  |  | 18/09/2026 | 19/09/2026 |  |  | 431 |  | 431
ADIDAS | 0903047241-1 KB5965 | BLACK | 120D | S2608MR0900A | 4136 | 15/10/2026 | 4136 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047241 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-08-10 | Run Ess Tee M |  | SS27-TI | 2026-08-10 | 13/10/2026 |  |  | 4136 |  | 4136 |  |  | 2026-05-10 | 2026-09-10 |  |  | 4136 |  | 4136 |  |  | 2026-02-10 | 2026-07-10 |  |  | 4136 |  | 4136
ADIDAS | 0903047261-1 LG9675 | BLACK | 120D | S2754WAS513C | 301 | 15/10/2026 | 301 | SI | SI12/06/2026 | G3G | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047261 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | W SL WV PT BLACK |  | SS27 | 28/10/2026 | 28/10/2026 |  |  | 301 |  | 301 |  |  | 24/10/2026 | 24/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903047275-1 LE8201 | BLACK | 90D | F2606LHLF103FY-MTF | 14000 | 15/09/2026 | 14000 | AN | AN12/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047275 LE8201 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 14000 | 14000 |  |  | 145 | 2026-02-09 | 2026-11-09 | 2026-01-09 | 14/09/2026 | 14000 | 13952 | 48
ADIDAS | 0903047297-1 LG9675 | BLACK | 120D | S2754WAS513C | 348 | 23/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047297 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047299-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2O | T-SHIRT | G2 | ok | (02/07/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047299 LE8208 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 F JSYL SE BLACK |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-05-09 | 14/09/2026 | 3500 | 3500 |  |  |  | 2026-02-09 | 2026-11-09 | 2026-02-09 | 14/09/2026 | 3500 | 3500
ADIDAS | 0903047330-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1R | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 20 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047330 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-02-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 15000 | 15000 |  |  |  | 29/08/2026 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 15000 | 15000
ADIDAS | 0903047342-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2L,G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047342 LE8210 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3500 | 3500 |  |  | 49 | 2026-05-09 | 2026-11-09 | 2026-05-09 | 14/09/2026 | 3500 | 3480 | 20
ADIDAS | 0903047344-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047344 KX0123 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | M ADI RETRO T WHITE |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903047363-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 3678 | 2026-12-09 | 3678 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 11/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047363 LE8194 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL HFY JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 3678 | 3678 |  |  |  | 27/08/2026 | 2026-05-09 | 20/08/2026 | 2026-04-09 | 3678 | 3678
ADIDAS | 0903047367-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047367 LC8882 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | M ADI RETRO T BLACK |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903047388-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1O,G1Q,G1R,G2M | T-SHIRT | G1,G2 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047388 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-02-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 15000 | 15000 |  |  | 272 | 29/08/2026 | 2026-11-09 | 2026-05-09 | 14/09/2026 | 15000 | 14832 | 168
ADIDAS | 0903047414-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 5500 | 15/09/2026 | 5500 | SA | SA12/06/2026 | G1G | T-SHIRT | G1 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047414 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 5500 | 5500 |  |  |  | 2026-05-09 | 2026-11-09 | 31/08/2026 | 2026-12-09 | 5500 | 5483 | 17
ADIDAS | 0903047417-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 121 | 15/10/2026 | 121 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047417 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 121 |  | 121 |  |  | 28/09/2026 | 28/09/2026 |  |  | 121 |  | 121
ADIDAS | 0903047441-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 249 | 15/09/2026 | 249 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903047441 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 249 | 249 |  |  | 10 | 2026-09-09 | 2026-11-09 | 2026-11-08 | 26/08/2026 | 249 | 249
ADIDAS | 0903047468-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 150 | 15/09/2026 | 150 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047468 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 150 | 110 | 40 |  |  | 2026-09-09 | 2026-11-09 | 22/08/2026 | 14/09/2026 | 150 | 140 | 10
ADIDAS | 0903047497-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 15/09/2026 | 101 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047497 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 101 |  | 101 |  |  | 14/09/2026 | 14/09/2026 | 26/08/2026 | 2026-05-09 | 101 | 85 | 16
ADIDAS | 0903047521-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047521 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 101 |  | 101 |  |  | 28/09/2026 | 28/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903048420-1 KB5965 | BLACK | 120D | S2608MR0900A | 456 | 30/09/2026 | 456 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048420 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | Run Ess Tee M |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 456 |  | 456 |  |  | 23/09/2026 | 23/09/2026 |  |  | 456 |  | 456 |  |  | 21/09/2026 | 21/09/2026 |  |  | 456 |  | 456
ADIDAS | 0903048444-1 JZ7808 | BLACK | 120D | S2608WR0900 | 420 | 15/10/2026 | 420 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516461 | HT+PAD SUB PROCESS_V3 | 0903048444 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 420 |  | 420 |  |  | 22/09/2026 | 22/09/2026 |  |  | 420 |  | 420 |  |  | 19/09/2026 | 19/09/2026 |  |  | 420 |  | 420
ADIDAS | 0903048469-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1100 | 15/10/2026 | 1100 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903048469 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 1100 |  | 1100 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1100 |  | 1100 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1100 |  | 1100
ADIDAS | 0903048496-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1018 | 23/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok |  | 804028 | HT+PAD SUB PROCESS_V3 | 0903048496 KX3650 | 2026-11-09 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903048502-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1004 | 2026-07-10 | 1004 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048502 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-10 | 2026-06-10 |  |  | 1004 |  | 1004 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1004 |  | 1004 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1004 |  | 1004
ADIDAS | 0903048525-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 395 | 31/10/2026 | 395 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048525 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 395 |  | 395 |  |  | 2026-03-10 | 2026-05-10 | 20/08/2026 | 20/08/2026 | 395 | 26 | 369
ADIDAS | 0903048540-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 409 | 23/10/2026 | 409 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048540 LD0287 | 2026-11-09 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-10 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 409 |  | 409 |  |  | 29/09/2026 | 29/09/2026 | 2026-08-08 | 29/08/2026 | 409 | 409 |  |  |  | 26/09/2026 | 26/09/2026 | 2026-07-08 | 28/08/2026 | 409 | 409
ADIDAS | 0903048576-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 112 | 15/09/2026 | 112 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048576 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 |  |  | 112 |  | 112 |  |  | 2026-09-09 | 2026-11-09 | 14/09/2026 | 15/09/2026 | 112 | 112 |  |  | 107
ADIDAS | 0903048604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN12/06/2026 | G3F,G3G | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903048604 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 15/09/2026 | 300 | 300 |  |  | 8 | 2026-01-09 | 2026-11-09 | 2026-10-08 | 13/08/2026 | 300 | 300
ADIDAS | 0903048634-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 151 | 23/10/2026 | 151 | AN | AN12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048634 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 151 |  | 151 |  |  | 24/10/2026 | 30/10/2026 |  |  | 151 |  | 151
ADIDAS | 0903048647-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 434 | 2026-09-09 | 434 | AN | AN12/06/2026 | G1H,G1L | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 14-Aug. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048647 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/08/2026 | 2026-08-09 | 24/08/2026 | 2026-05-09 | 434 | 434 |  |  |  | 18/08/2026 | 2026-04-09 | 18/08/2026 | 2026-07-09 | 434 | 434
ADIDAS | 0903049164-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903049164 KB5965 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903049187-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 376 | 15/10/2026 | 376 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903049187 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 376 |  | 376 |  |  | 2026-05-10 | 2026-06-10 |  |  | 376 |  | 376 |  |  | 2026-02-10 | 2026-03-10 |  |  | 376 |  | 376
ADIDAS | 0903049383-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049383 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | PIZZA TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-08-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-07-08 | 2026-07-09 | 450 | 450
ADIDAS | 0903049419-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 341 | 2026-09-09 | 341 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 08/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049419 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M TATTOO SPRT T BLACK |  | SS27 | 2026-03-09 | 2026-09-09 | 2026-04-09 | 2026-08-09 | 341 | 341 |  |  |  | 31/08/2026 | 2026-05-09 | 24/08/2026 | 2026-07-09 | 341 | 341
ADIDAS | 0903049448-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 301 | 30/09/2026 | 301 | AN | AN12/06/2026 | G2N | T-SHIRT | G2 | ok | (02/07/2026) | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049448 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | LA PALMS TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 301 |  | 301 |  |  | 15/09/2026 | 16/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903049482-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 450 | 31/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049482 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903049516-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 301 | 23/09/2026 | 301 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049516 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 301 | 301 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903049584-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049584 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PIZZA TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 301 |  | 301 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 19/08/2026 | 301 | 293 | 8
ADIDAS | 0903049615-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 24/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049615 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | HOU COLL TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 301 |  | 301 |  |  | 2026-01-10 | 2026-01-10 | 2026-10-08 | 2026-07-09 | 301 | 301
ADIDAS | 0903050997-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 558 | 30/09/2026 | 558 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 1st Art (TC 12 pcs) 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903050997 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 558 |  | 558 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-09 | 15/09/2026 | 558 | 481 | 77 |  | 286
ADIDAS | 0903051027-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 236 | 30/09/2026 | 236 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903051027 LE0358 | 2026-11-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 236 |  | 236 |  |  | 29/09/2026 | 30/09/2026 | 2026-04-09 | 2026-11-09 | 236 | 123 | 113
ADIDAS | 0903051176-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903051176 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | HOU COLL TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-08-08 | 2026-12-09 | 450 | 450
ADIDAS | 0903051428-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/09/2026 | 18 | SA | SA12/06/2026 | G3J | SHORTS | G3 | ok |  | 14/09: ex-fty. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. T2 Formosa, PI Date 20-Jul, actual receives 07-Jul. 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903051428 KZ0925 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 18 | 18 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 18 | 18
ADIDAS | 0903051498-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 40 | 15/10/2026 | 40 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051498 LD0283 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 40 |  | 40 |  |  | 26/09/2026 | 28/09/2026 |  |  | 40 |  | 40 |  |  | 24/09/2026 | 25/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903051523-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051523 KX3651 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 50 |  | 50 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 2026-08-08 | 50 | 50 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 50 | 50
ADIDAS | 0903051563-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 40 | 15/10/2026 | 40 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051563 LD0284 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 40 |  | 40 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40
ADIDAS | 0903051592-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 18 | 30/09/2026 | 18 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903051592 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 18 |  | 18 |  |  | 14/09/2026 | 15/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903051620-1 KA0227 | MEDIUM GREY HEATHER | 120D | S2608WR0900 | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0903051620 KA0227 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | Run Ess Tee W MEDIUM GREY HEATHER |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 50 | 50 |  |  |  | 17/09/2026 | 17/09/2026 | 2026-08-08 | 2026-11-08 | 50 | 50
ADIDAS | 0903052489-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 379 | 2026-09-09 | 379 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052489 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-07-09 | 379 | 379 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 31/08/2026 | 379 | 379
ADIDAS | 0903052531-1 LE5038 | BLACK | 105D | S2750MTR104A | 387 | 15/10/2026 | 387 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | (NYK warehouse). T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 1st Art (TC 10 pcs) 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903052531 LE5038 | 2026-11-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-10 | D4T AOP GFX T BLACK |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 387 |  | 387 |  |  | 2026-05-10 | 2026-05-10 |  |  | 387 |  | 387 |  |  | 2026-03-10 | 2026-03-10 |  |  | 387 |  | 387
ADIDAS | 0903052598-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 135 | 2026-05-09 | 135 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 05/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052598 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-05-08 | 2026-06-08 | 135 | 135 |  |  |  | 29/07/2026 | 2026-04-08 | 28/07/2026 | 31/07/2026 | 135 | 135
ADIDAS | 0903052654-1 KB5960 | WHITE | 120D | S2608MR0900A | 459 | 15/10/2026 | 459 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0903052654 KB5960 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 459 |  | 459 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 2026-07-08 | 459 | 459 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 2026-07-08 | 459 | 459
ADIDAS | 0903052671-1 KB5965 | BLACK | 120D | S2608MR0900A | 282 | 15/10/2026 | 282 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903052671 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 282 |  | 282 |  |  | 2026-02-10 | 2026-03-10 |  |  | 282 |  | 282 |  |  | 30/09/2026 | 2026-01-10 |  |  | 282 |  | 282
ADIDAS | 0903052708-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 365 | 22/09/2026 | 365 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052708 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 365 | 365 |  |  |  | 2026-03-09 | 2026-09-09 | 20/08/2026 | 2026-10-09 | 365 | 365
ADIDAS | 0903052721-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 459 | 15/09/2026 | 459 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903052721 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 459 | 459 |  |  |  | 27/08/2026 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 459 | 459
ADIDAS | 0903052745-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 305 | 2026-05-09 | 305 | AN | AN12/06/2026 | G3A,G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052745 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 18/08/2026 | 305 | 305 |  |  |  | 29/07/2026 | 18/08/2026 | 2026-03-08 | 14/08/2026 | 305 | 305
ADIDAS | 0903052755-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 633 | 15/09/2026 | 633 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052755 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 633 | 608 | 25 |  |  | 2026-03-09 | 2026-11-09 | 20/08/2026 | 2026-01-09 | 633 | 609 | 24
ADIDAS | 0903052784-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 15/09/2026 | 390 | AN | AN12/06/2026 | G3C,G3F | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052784 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 15/09/2026 | 390 | 368 | 22 |  | 14 | 20/08/2026 | 2026-11-09 | 2026-06-08 | 15/09/2026 | 390 | 389 | 1 |  | 9
ADIDAS | 0903052813-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903052813 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903053034-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 1170 | 15/09/2026 | 1170 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903053034 KD4899 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 2026-01-09 | 2026-12-09 | 1170 | 1170 |  |  |  | 27/08/2026 | 2026-10-09 | 2026-01-09 | 2026-05-09 | 1170 | 1170
ADIDAS | 0903053050-1 KH0396 | DARK BLUE | 90D | F26SPRMGFX910-MTF | 641 | 2026-12-09 | 641 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty 516318 | PRINT L2+PAD+PPH L1 SUB PROCESS_V3 | 0903053050 KH0396 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | M HIGHLITE T1 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-10-09 | 641 | 641 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 641 | 641
ADIDAS | 0903053086-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 912 | 2026-12-09 | 912 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 10/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053086 KF2398 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV TT |  | FW26 | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-02-09 | 912 | 912 |  |  |  | 27/08/2026 | 2026-04-09 | 22/08/2026 | 2026-09-09 | 912 | 912
ADIDAS | 0903053111-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 5386 | 2026-12-09 | 5386 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053111 JN1956 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT QZ HD |  | SS27 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-10-09 | 5386 | 5386 |  |  |  | 24/08/2026 | 2026-09-09 | 24/08/2026 | 2026-09-09 | 5386 | 5386
ADIDAS | 0903053136-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 780 | 15/09/2026 | 780 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903053136 KD4899 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 31/08/2026 | 2026-12-09 | 780 | 780 |  |  |  | 27/08/2026 | 2026-10-09 | 23/07/2026 | 2026-03-09 | 780 | 780
ADIDAS | 0903053462-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 603 | 2026-05-09 | 603 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053462 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 603 | 603 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-07-09 | 603 | 603
ADIDAS | 0903053919-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 782 | 2026-09-09 | 782 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 08/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0903053919 KE8424 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-09 | Run Ess LS M BLACK |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 782 | 782 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-05-09 | 2026-08-09 | 782 | 782 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-04-09 | 2026-08-09 | 782 | 782
ADIDAS | 0903054030-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 468 | 2026-05-09 | 468 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903054030 KX0123 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 468 | 468 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-01-08 | 2026-02-09 | 468 | 468
ADIDAS | 0903054066-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 410 | 2026-05-09 | 410 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 05/09: ex-fty 980004 | PRINT L3+PAD SUB PROCESS_V3 | 0903054066 LC8882 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/08/2026 | M ADI RETRO T BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 410 | 410 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 410 | 410
ADIDAS | 0903054127-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 408 | 2026-07-10 | 408 | SA | SA12/06/2026 | G3K | SHORTS | G3 | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-Jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054127 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | W 3S WV SHO 74 WHITE/BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 408 |  | 408 |  |  | 2026-09-10 | 2026-10-10 |  |  | 408 |  | 408
ADIDAS | 0903054613-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1450 | 15/09/2026 | 1450 | SA | SA12/06/2026 | G1A | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903054613 LE8202 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1450 | 1450 |  |  |  | 2026-09-09 | 2026-11-09 | 2026-04-09 | 14/09/2026 | 1450 | 1441 | 9
ADIDAS | 0903054711-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 508 | 15/10/2026 | 508 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054711 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 508 |  | 508 |  |  | 26/09/2026 | 26/09/2026 |  |  | 508 |  | 508 |  |  | 24/09/2026 | 24/09/2026 |  |  | 508 |  | 508
ADIDAS | 0903054732-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 127 | 30/09/2026 | 127 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903054732 LE0358 | 2026-11-09 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 127 |  | 127 |  |  | 29/09/2026 | 30/09/2026 |  |  | 127 |  | 127
ADIDAS | 0903054739-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 132 | 15/10/2026 | 132 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054739 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 132 |  | 132 |  |  | 24/09/2026 | 25/09/2026 |  |  | 132 |  | 132 |  |  | 22/09/2026 | 23/09/2026 |  |  | 132 |  | 132
ADIDAS | 0903054752-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 290 | 2026-12-09 | 290 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054752 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 290 | 290 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-09-09 | 290 | 290
ADIDAS | 0903054797-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 217 | 23/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (03/07/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0903054797 KX3655 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903054814-1 JZ7808 | BLACK | 120D | S2608WR0900 | 151 | 15/10/2026 | 151 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 857010 | HT+PAD SUB PROCESS_V3 | 0903054814 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 151 |  | 151 |  |  | 22/09/2026 | 22/09/2026 |  |  | 151 |  | 151 |  |  | 19/09/2026 | 19/09/2026 |  |  | 151 |  | 151
ADIDAS | 0903054844-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1405 | 31/10/2026 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903054844 LG9675 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903054871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2292 | 30/09/2026 | 2292 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty 857010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903054871 KC8152 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 22/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 22/09/2026 | 25/09/2026 |  |  | 2292 |  | 2292 |  |  | 18/09/2026 | 22/09/2026 | 15/09/2026 | 15/09/2026 | 2292 | 13 | 2279 |  | 13 | 2026-12-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 2292 | 1779 | 513 |  | 544
ADIDAS | 0903055171-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 607 | 15/09/2026 | 607 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 14/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055171 KF2398 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 13/08/2026 | 22/07/2026 | 14/08/2026 | 607 | 607 |  |  |  | 15/07/2026 | 2026-10-08 | 21/07/2026 | 29/07/2026 | 607 | 607
ADIDAS | 0903055195-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 371 | 15/09/2026 | 371 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055195 KV7963 | 28/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 371 | 371 |  |  |  | 22/07/2026 | 2026-03-08 | 22/07/2026 | 2026-05-08 | 371 | 371
ADIDAS | 0903055207-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 3592 | 15/09/2026 | 3592 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 14/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055207 JN1956 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W 3S FT QZ HD |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 3592 | 3592 |  |  |  | 2026-04-09 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 3592 | 3577 | 15
ADIDAS | 0903055240-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 879 | 23/09/2026 | 879 | AN | AN12/06/2026 | G3J,G3K | SHORTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055240 KV7963 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-10-08 | 879 | 879 |  |  |  | 24/07/2026 | 2026-05-08 | 25/07/2026 | 2026-07-08 | 879 | 879
ADIDAS | 0903055956-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 629 | 31/10/2026 | 629 | SA | SA12/06/2026 | G2S | JACKET | G2 | ok | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903055956 JE6338 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | M 3S FT FZ HD |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 629 |  | 629 |  |  | 24/10/2026 | 26/10/2026 |  |  | 629 |  | 629
ADIDAS | 0903055994-1 LG9675 | BLACK | 120D | S2754WAS513C | 498 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903055994 LG9675 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903056002-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 472 | 15/10/2026 | 472 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903056002 LD0287 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 24/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 472 |  | 472 |  |  | 21/09/2026 | 22/09/2026 | 2026-05-08 | 29/08/2026 | 472 | 472 |  |  |  | 18/09/2026 | 19/09/2026 | 2026-05-08 | 28/08/2026 | 472 | 472
ADIDAS | 0903056023-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 797 | 23/09/2026 | 797 | SA | SA12/06/2026 | G2T | JACKET | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056023 JE6338 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 3S FT FZ HD |  | SS27 | 28/07/2026 | 28/08/2026 | 29/07/2026 | 31/08/2026 | 797 | 797 |  |  |  | 23/07/2026 | 24/08/2026 | 23/07/2026 | 15/08/2026 | 797 | 797
ADIDAS | 0903056060-1 LF0723 | BLACK | 105D | S2754MAS511B | 325 | 31/10/2026 |  | SI | SI12/06/2026 |  | SHORTS |  | ok | (04/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 04-Sep. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903056060 LF0723 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903056094-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 161 | 15/10/2026 | 161 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (02/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056094 KX3653 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 161 |  | 161 |  |  | 2026-06-10 | 2026-07-10 | 2026-10-09 | 2026-10-09 | 161 | 138 | 23 |  |  | 2026-03-10 | 2026-05-10 | 2026-09-09 | 2026-09-09 | 161 | 138 | 23
ADIDAS | 0903056095-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1009 | 30/09/2026 | 1009 | SA | SA12/06/2026 | G2B | JACKET | G2 | ok | (03/07/2026) | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056095 JD1877 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 1009 |  | 1009 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903056120-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 427 | 30/09/2026 | 427 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (03/07/2026) | 24/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903056120 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 427 |  | 427 |  |  | 15/09/2026 | 15/09/2026 | 2026-01-08 | 13/08/2026 | 427 | 421 | 6
ADIDAS | 0903056133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 939 | 15/10/2026 | 939 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903056133 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 939 |  | 939 |  |  | 2026-05-10 | 2026-06-10 |  |  | 939 |  | 939 |  |  | 2026-02-10 | 2026-03-10 |  |  | 939 |  | 939
ADIDAS | 0903056140-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1431 | 31/10/2026 | 1431 | SA | SA12/06/2026 | G2Q | JACKET | G2 | (22/07/2026) | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056140 JD1877 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | M 3S FT FZ HD |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 1431 |  | 1431 |  |  | 17/10/2026 | 20/10/2026 |  |  | 1431 |  | 1431
ADIDAS | 0903056160-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 521 | 2026-05-09 | 521 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903056160 LC8882 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T BLACK |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 521 | 521 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-05-08 | 26/08/2026 | 521 | 521
ADIDAS | 0903056304-1 KX8877 | WHITE | 90D | S27GMGFX100 | 376 | 30/09/2026 | 376 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903056304 KX8877 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M CHIP T WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 376 |  | 376 |  |  | 18/09/2026 | 19/09/2026 | 22/08/2026 | 24/08/2026 | 376 | 45 | 331
ADIDAS | 0903056585-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 110 | 30/09/2026 | 110 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056585 KY5988 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 15/09/2026 | 17/09/2026 |  |  | 110 |  | 110 |  |  | 2026-11-09 | 14/09/2026 |  |  | 110 |  | 110 |  |  | 2026-05-09 | 2026-08-09 |  |  | 110 |  | 110
ADIDAS | 0903056609-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 320 | 2026-07-10 | 320 | SA | SA12/06/2026 | G3E | PANTS | G3 | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056609 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 320 |  | 320 |  |  | 2026-09-10 | 2026-10-10 |  |  | 320 |  | 320 |  |  | 2026-03-10 | 2026-05-10 |  |  | 320 |  | 320
ADIDAS | 0903056658-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 208 | 30/09/2026 | 208 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903056658 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 208 |  | 208 |  |  | 29/09/2026 | 30/09/2026 | 2026-05-09 | 2026-11-09 | 208 | 186 | 22
ADIDAS | 0903056767-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 311 | 15/10/2026 | 311 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056767 KX3654 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 311 |  | 311 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102 |  |  | 2026-01-10 | 2026-02-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102
ADIDAS | 0903056781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 444 | 30/09/2026 | 444 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 21/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056781 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S CHELSEA B7 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 444 |  | 444 |  |  | 17/09/2026 | 18/09/2026 |  |  | 444 |  | 444
ADIDAS | 0903056795-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 402 | 15/10/2026 | 402 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516343 | HT+PAD SUB PROCESS_V3 | 0903056795 KX3654 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 402 |  | 402 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-10-09 | 402 | 371 | 31 |  |  | 2026-01-10 | 2026-02-10 | 27/08/2026 | 2026-09-09 | 402 | 371 | 31
ADIDAS | 0903056811-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1919 | 30/09/2026 | 1919 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 23/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056811 KY6510 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 3S CHELSEA B7 |  | SS27 | 22/09/2026 | 25/09/2026 |  |  | 1919 |  | 1919 |  |  | 18/09/2026 | 22/09/2026 |  |  | 1919 |  | 1919
ADIDAS | 0903056816-1 KE8424 | BLACK | 120D | S2608MR0906A | 321 | 15/10/2026 | 321 | SI | SI12/06/2026 | G2N | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056816 KE8424 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 321 |  | 321 |  |  | 2026-05-10 | 2026-07-10 |  |  | 321 |  | 321 |  |  | 2026-02-10 | 2026-05-10 |  |  | 321 |  | 321
ADIDAS | 0903056835-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 351 | 30/09/2026 | 351 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056835 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 351 |  | 351 |  |  | 15/09/2026 | 16/09/2026 |  |  | 351 |  | 351 |  |  | 2026-09-09 | 2026-10-09 | 15/09/2026 | 15/09/2026 | 351 | 12 | 339 |  | 12
ADIDAS | 0903056841-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 119 | 30/09/2026 | 119 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056841 KC8152 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 119 |  | 119 |  |  | 15/09/2026 | 16/09/2026 |  |  | 119 |  | 119 |  |  | 2026-09-09 | 2026-10-09 | 15/09/2026 | 15/09/2026 | 119 | 27 | 92 |  | 27
ADIDAS | 0903056853-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1356 | 2026-05-09 | 1356 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056853 KV7863 | 28/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 21/08/2026 | 30/07/2026 | 18/08/2026 | 1356 | 1356 |  |  |  | 23/07/2026 | 18/08/2026 | 27/07/2026 | 20/08/2026 | 1356 | 1356
ADIDAS | 0903056865-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 443 | 23/09/2026 | 443 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056865 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 443 |  | 443 |  |  | 15/09/2026 | 16/09/2026 |  |  | 443 |  | 443 |  |  | 2026-09-09 | 2026-10-09 |  |  | 443 |  | 443
ADIDAS | 0903056887-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 30/09/2026 | 300 | AN | AN12/06/2026 | G1H | JACKET | G1 | (13/07/2026) | (03/07/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056887 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 29/09/2026 | 2026-05-09 | 2026-05-09 | 300 | 97 | 203
ADIDAS | 0903056914-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 314 | 2026-12-09 | 314 | AN | AN12/06/2026 | G1G,G1H | JACKET | G1 | ok | (03/07/2026) | 10/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056914 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-10-09 | 314 | 314 |  |  |  | 27/08/2026 | 2026-05-09 | 27/08/2026 | 2026-07-09 | 314 | 314
ADIDAS | 0903056942-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 304 | 2026-09-09 | 304 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056942 KV8005 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 304 | 304 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-09-09 | 304 | 304
ADIDAS | 0903056963-1 JZ7808 | BLACK | 120D | S2608WR0900 | 312 | 15/10/2026 | 312 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056963 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 312 |  | 312 |  |  | 26/09/2026 | 28/09/2026 |  |  | 312 |  | 312 |  |  | 24/09/2026 | 25/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903057195-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 499 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903057195 LG9669 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903057469-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 323 | 15/10/2026 | 323 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903057469 LD0285 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 323 |  | 323 |  |  | 19/09/2026 | 19/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323 |  |  |  | 17/09/2026 | 17/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323
ADIDAS | 0903057500-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 30/09/2026 | 123 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 24/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 19-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057500 LD5446 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 123 |  | 123 |  |  | 22/09/2026 | 24/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903057529-1 LE8187 | BLACK | 105D | S2754MAS513 | 385 | 30/09/2026 | 385 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 13-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057529 LE8187 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | M SL WV TP PT BLACK |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 385 |  | 385 |  |  | 15/09/2026 | 17/09/2026 |  |  | 385 |  | 385
ADIDAS | 0903057535-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 30/09/2026 | 512 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057535 LF0718 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 512 |  | 512 |  |  | 16/09/2026 | 17/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903057574-1 LF0723 | BLACK | 105D | S2754MAS511B | 221 | 30/09/2026 | 221 | SI | SI12/06/2026 | G3F | SHORTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057574 LF0723 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | M SL WV SHO BLACK |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 221 |  | 221 |  |  | 22/09/2026 | 22/09/2026 |  |  | 221 |  | 221
ADIDAS | 0903057608-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 379 | 15/10/2026 | 379 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057608 LF0726 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 379 |  | 379 |  |  | 16/09/2026 | 18/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903057614-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 653 | 15/10/2026 | 653 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057614 LH3759 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 653 |  | 653 |  |  | 14/10/2026 | 14/10/2026 |  |  | 653 |  | 653
ADIDAS | 0903057632-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 309 | 15/10/2026 | 309 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057632 LH3761 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 309 |  | 309 |  |  | 14/10/2026 | 15/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903058035-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 292 | 2026-12-09 | 292 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903058035 LE8194 | 28/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-12-09 | 2026-07-09 | 2026-10-09 | 292 | 292 |  |  |  | 29/08/2026 | 2026-09-09 | 24/08/2026 | 2026-12-09 | 292 | 292
ADIDAS | 0903058072-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 402 | 30/09/2026 | 402 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058072 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 402 |  | 402 |  |  | 14/09/2026 | 15/09/2026 |  |  | 402 |  | 402
ADIDAS | 0903058091-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 597 | 15/10/2026 | 597 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058091 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 597 |  | 597 |  |  | 19/09/2026 | 22/09/2026 | 2026-04-08 | 20/08/2026 | 597 | 399 | 198
ADIDAS | 0903058157-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 900 | 15/10/2026 | 900 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058157 KX3650 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-10 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 900 |  | 900 |  |  | 2026-06-10 | 2026-07-10 | 31/08/2026 | 2026-04-09 | 900 | 360 | 540 |  |  | 2026-03-10 | 2026-05-10 | 29/08/2026 | 2026-04-09 | 900 | 360 | 540
ADIDAS | 0903058189-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 541 | 31/10/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | (11/07/2026) | (03/07/2026) | 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903058189 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA |  | M RESORT T OLIVE FOUR S27 |  | SS27
ADIDAS | 0903058216-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 610 | 31/10/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058216 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903058691-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 415 | 15/10/2026 | 415 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903058691 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 415 |  | 415 |  |  | 24/09/2026 | 25/09/2026 |  |  | 415 |  | 415 |  |  | 22/09/2026 | 23/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903058943-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 331 | 2026-07-10 | 331 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058943 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 21/08/2026 | 331 | 331 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-05-08 | 20/08/2026 | 331 | 331
ADIDAS | 0903058963-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 539 | 30/09/2026 | 539 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058963 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 539 | 539 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-03-08 | 2026-06-08 | 539 | 539
ADIDAS | 0903058992-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jul (PO NT-351). T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058992 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 332 | 332 |  |  |  | 27/07/2026 | 2026-11-08 | 28/07/2026 | 2026-04-08 | 332 | 332
ADIDAS | 0903059036-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 355 | 2026-05-09 | 355 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059036 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 19/08/2026 | 31/07/2026 | 18/08/2026 | 355 | 355 |  |  |  | 24/07/2026 | 13/08/2026 | 29/07/2026 | 2026-11-08 | 355 | 355
ADIDAS | 0903059059-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 306 | 2026-05-09 | 306 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059059 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 306 | 306 |  |  |  | 2026-04-08 | 2026-11-08 | 29/07/2026 | 2026-11-08 | 306 | 306
ADIDAS | 0903059081-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 519 | 15/10/2026 | 519 | SI | SI12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059081 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 519 |  | 519 |  |  | 2026-03-10 | 2026-05-10 |  |  | 519 |  | 519
ADIDAS | 0903059085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/09/2026 | 300 | AN | AN12/06/2026 | G3A | PANTS | G3 | ok | (03/07/2026) | 21/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059085 KV7863 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 300 | 300 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-01-08 | 14/08/2026 | 300 | 300
ADIDAS | 0903059107-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 253 | 2026-07-10 | 253 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059107 LE4307 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 253 |  | 253 |  |  | 24/09/2026 | 28/09/2026 | 2026-04-09 | 2026-07-09 | 253 | 27 | 226
ADIDAS | 0903059113-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 1150 | 15/09/2026 | 1150 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903059113 LE8210 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-11-09 | 2026-12-09 | 1150 | 1150 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-07-09 | 15/09/2026 | 1150 | 1150 |  |  | 3
ADIDAS | 0903059133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059133 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 27/08/2026 | 15/09/2026 | 300 | 299 | 1 |  | 4
ADIDAS | 0903059183-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3J,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516403 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903059183 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 300 |  |  |  | 2026-09-09 | 2026-11-09 | 13/09/2026 | 14/09/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-12-09 | 14/09/2026 | 300 | 300
ADIDAS | 0903059345-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 147 | 15/09/2026 | 147 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (02/07/2026) | 14/09: ex-fty. T2 Libolon, using PO 26000011, body actual receives 11-Feb, 3S actual receives 10-Feb. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059345 JE1309 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | W 3S WV SHO |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-09-09 | 2026-11-09 | 147 | 147 |  |  |  | 2026-02-09 | 2026-09-09 | 24/07/2026 | 2026-10-09 | 147 | 147
ADIDAS | 0903059367-1 KB5965 | BLACK | 120D | S2608MR0900A | 360 | 15/10/2026 | 360 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903059367 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 360 |  | 360 |  |  | 2026-02-10 | 2026-03-10 |  |  | 360 |  | 360 |  |  | 30/09/2026 | 2026-01-10 |  |  | 360 |  | 360
ADIDAS | 0903059372-1 LE8187 | BLACK | 105D | S2754MAS513 | 170 | 2026-07-10 | 170 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059372 LE8187 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | M SL WV TP PT BLACK |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 170 |  | 170 |  |  | 2026-07-10 | 2026-09-10 |  |  | 170 |  | 170
ADIDAS | 0903059402-1 LE8187 | BLACK | 105D | S2754MAS513 | 494 | 2026-07-10 | 494 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059402 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TP PT BLACK |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 494 |  | 494 |  |  | 2026-05-10 | 2026-07-10 |  |  | 494 |  | 494
ADIDAS | 0903059416-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 111 | 15/10/2026 | 111 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059416 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 111 |  | 111 |  |  | 22/10/2026 | 23/10/2026 |  |  | 111 |  | 111
ADIDAS | 0903059460-1 LE8187 | BLACK | 105D | S2754MAS513 | 465 | 2026-07-10 | 465 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059460 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TP PT BLACK |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 465 |  | 465 |  |  | 2026-05-10 | 2026-07-10 |  |  | 465 |  | 465
ADIDAS | 0903059485-1 LF0718 | BLACK | 105D | S2754MAS512B | 170 | 31/10/2026 |  | SA | SA12/06/2026 |  | PANTS |  | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 31-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059485 LF0718 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903059491-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 362 | 15/10/2026 | 362 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059491 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 26/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 362 |  | 362 |  |  | 22/10/2026 | 23/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903059517-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 365 | 23/10/2026 | 365 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059517 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | M SL WV TT BLACK |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 365 |  | 365 |  |  | 26/10/2026 | 28/10/2026 |  |  | 365 |  | 365
ADIDAS | 0903059522-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 218 | 15/10/2026 | 218 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059522 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 218 |  | 218 |  |  | 22/10/2026 | 23/10/2026 |  |  | 218 |  | 218
ADIDAS | 0903059553-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059553 LF0718 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 100 |  | 100 |  |  | 16/09/2026 | 17/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903059578-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (13/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059578 LG9669 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903059583-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 309 | 15/10/2026 | 309 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059583 LF0726 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 309 |  | 309 |  |  | 16/09/2026 | 18/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903059595-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 161 | 23/10/2026 | 161 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059595 LF0727 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | M SL WV TT BLACK |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 161 |  | 161 |  |  | 26/10/2026 | 28/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903059626-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 299 | 15/10/2026 | 299 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059626 LF0726 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 299 |  | 299 |  |  | 13/10/2026 | 16/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903059656-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 457 | 15/10/2026 | 457 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059656 LF0727 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M SL WV TT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 457 |  | 457 |  |  | 2026-10-10 | 13/10/2026 |  |  | 457 |  | 457
ADIDAS | 0903059680-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 283 | 15/10/2026 | 283 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059680 LF0729 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 20/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 283 |  | 283 |  |  | 16/10/2026 | 17/10/2026 | 2026-07-09 | 2026-07-09 | 283 | 200 | 83
ADIDAS | 0903059710-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/10/2026 | 100 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059710 LH3759 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 17/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 14/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903059734-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/10/2026 | 200 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059734 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200 |  |  | 30/09/2026 | 2026-01-10 |  |  | 200 |  | 200
ADIDAS | 0903059757-1 JZ7808 | BLACK | 120D | S2608WR0900 | 811 | 15/10/2026 | 811 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059757 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 811 |  | 811 |  |  | 26/09/2026 | 28/09/2026 |  |  | 811 |  | 811 |  |  | 24/09/2026 | 25/09/2026 |  |  | 811 |  | 811
ADIDAS | 0903059786-1 KB5965 | BLACK | 120D | S2608MR0900A | 1790 | 15/10/2026 | 1790 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059786 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-10 | Run Ess Tee M |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 1790 |  | 1790 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1790 |  | 1790 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1790 |  | 1790
ADIDAS | 0903059867-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 750 | 31/10/2026 | 750 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903059867 LD0285 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 750 |  | 750 |  |  | 2026-03-10 | 2026-05-10 | 24/08/2026 | 15/09/2026 | 750 | 750 |  |  | 6 | 2026-01-10 | 2026-02-10 | 24/08/2026 | 2026-12-09 | 750 | 750
ADIDAS | 0903060200-1 LF0723 | BLACK | 105D | S2754MAS511B | 552 | 15/10/2026 | 552 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060200 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 552 |  | 552 |  |  | 22/10/2026 | 24/10/2026 |  |  | 552 |  | 552
ADIDAS | 0903060220-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 309 | 2026-07-10 | 309 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 30/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060220 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 19/09/2026 | 2026-04-08 | 20/08/2026 | 309 | 198 | 111
ADIDAS | 0903060279-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 152 | 31/10/2026 | 152 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060279 LF0729 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 152 |  | 152 |  |  | 23/10/2026 | 26/10/2026 |  |  | 152 |  | 152
ADIDAS | 0903060359-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 315 | 23/10/2026 | 315 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (30/06/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060359 LF0729 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 315 |  | 315 |  |  | 23/10/2026 | 26/10/2026 |  |  | 315 |  | 315
ADIDAS | 0903060814-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 325 | 23/10/2026 | 325 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903060814 LD0285 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 325 |  | 325 |  |  | 28/09/2026 | 29/09/2026 | 20/08/2026 | 31/08/2026 | 325 | 324 | 1 |  |  | 25/09/2026 | 26/09/2026 | 19/08/2026 | 31/08/2026 | 325 | 324 | 1
ADIDAS | 0903060841-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 455 | 2026-07-10 | 455 | AN | AN12/06/2026 | G3K | SHORTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903060841 KV7963 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 455 |  | 455 |  |  | 2026-09-10 | 2026-10-10 |  |  | 455 |  | 455
ADIDAS | 0903060907-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 819 | 30/09/2026 | 819 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 1st Art (TC 10 pcs) 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060907 LD6542 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 819 |  | 819 |  |  | 15/09/2026 | 18/09/2026 |  |  | 819 |  | 819
ADIDAS | 0903060936-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060936 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV OH PT BLACK |  | SS27-SPOMA | 2026-01-10 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 28/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903060943-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 200 | 30/09/2026 | 200 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060943 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 200 |  | 200 |  |  | 14/09/2026 | 15/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903060967-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 77 | 15/10/2026 | 77 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903060967 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | W SL WV PT BLACK |  | SS27-SPOMA | 28/10/2026 | 28/10/2026 |  |  | 77 |  | 77 |  |  | 24/10/2026 | 24/10/2026 |  |  | 77 |  | 77
ADIDAS | 0903060981-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 117 | 30/09/2026 | 117 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060981 LD6542 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 117 |  | 117 |  |  | 14/09/2026 | 15/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903061148-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 100 | 15/09/2026 | 100 | SI | SI12/06/2026 | G1G | T-SHIRT | G1 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903061148 LE8194 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-05-09 | 21/08/2026 | 2026-03-09 | 100 | 100
ADIDAS | 0903061664-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 303 | 15/10/2026 | 303 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061664 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M SL WV TT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-10-10 | 13/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903061878-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 816 | 15/10/2026 | 816 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (01/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061878 LF0726 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 16/10/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 816 |  | 816 |  |  | 13/10/2026 | 16/10/2026 |  |  | 816 |  | 816
ADIDAS | 0903061908-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1613 | 30/09/2026 | 1613 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 25/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 20-Aug. 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061908 LD5446 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 30/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1613 |  | 1613 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903061936-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 559 | 30/09/2026 | 559 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903061936 LE0358 | 2026-11-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 24/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 559 |  | 559 |  |  | 21/09/2026 | 22/09/2026 | 2026-05-09 | 2026-11-09 | 559 | 451 | 108
ADIDAS | 0903062015-1 LE5038 | BLACK | 105D | S2750MTR104A | 141 | 23/10/2026 | 141 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903062015 LE5038 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/10/2026 | D4T AOP GFX T BLACK |  | SS27-TI | 26/10/2026 | 26/10/2026 |  |  | 141 |  | 141 |  |  | 22/10/2026 | 22/10/2026 |  |  | 141 |  | 141 |  |  | 21/10/2026 | 21/10/2026 |  |  | 141 |  | 141
ADIDAS | 0903062303-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5037 | 30/09/2026 | 5037 | SI | SI12/06/2026 | G1Q | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062303 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | M 3S CHELSEA B7 |  | SS27 | 16/09/2026 | 24/09/2026 |  |  | 5037 |  | 5037 |  |  | 2026-12-09 | 21/09/2026 |  |  | 5037 |  | 5037
ADIDAS | 0903062323-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 857 | 2026-09-09 | 857 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (03/07/2026) | 09/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903062323 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 857 | 857 |  |  |  | 2026-01-09 | 2026-05-09 | 30/07/2026 | 2026-04-09 | 857 | 857
ADIDAS | 0903062337-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 6000 | 30/09/2026 | 6000 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062337 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | M 3S CHELSEA B7 |  | SS27 | 25/09/2026 | 2026-03-10 |  |  | 6000 |  | 6000 |  |  | 22/09/2026 | 30/09/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903063242-1 KX8877 | WHITE | 90D | S27GMGFX100 | 191 | 2026-12-09 | 191 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903063242 KX8877 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | M CHIP T WHITE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 191 | 191 |  |  |  | 2026-05-09 | 2026-09-09 | 22/08/2026 | 2026-10-09 | 191 | 191
ADIDAS | 0903063361-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 301 | 15/10/2026 | 301 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063361 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV SK BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 301 |  | 301 |  |  | 2026-12-10 | 13/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903063462-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 347 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063462 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903063503-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 310 | 15/10/2026 | 310 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063503 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV SK BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 310 |  | 310 |  |  | 2026-12-10 | 13/10/2026 |  |  | 310 |  | 310
ADIDAS | 0903086049-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 752 | 15/09/2026 | 752 | SA | SA17/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903086049 LE8193 | 2026-01-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-08-09 | 752 | 752 |  |  |  | 27/08/2026 | 2026-04-09 | 26/08/2026 | 2026-08-09 | 752 | 752
ADIDAS | 0903086050-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 459 | 15/09/2026 | 459 | SA | SA17/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903086050 LE8193 | 2026-01-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-09 | REAL H F JSY SE WHITE |  | FW26-FJ | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-11-09 | 459 | 459 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-01-09 | 2026-10-09 | 459 | 459
ADIDAS | 0903089629-1 LF0718 | BLACK | 105D | S2754MAS512B | 301 | 2026-07-10 | 301 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089629 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 301 |  | 301 |  |  | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301
ADIDAS | 0903089630-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 2026-07-10 | 301 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089630 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 301 |  | 301 |  |  | 20/10/2026 | 22/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903089631-1 LF0723 | BLACK | 105D | S2754MAS511B | 17 | 2026-07-10 | 17 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089631 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 17 |  | 17 |  |  | 20/10/2026 | 22/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903089632-1 LF0718 | BLACK | 105D | S2754MAS512B | 59 | 2026-07-10 | 59 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089632 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M SL WV OH PT BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 59 |  | 59 |  |  | 2026-09-10 | 2026-10-10 |  |  | 59 |  | 59
ADIDAS | 0903091452-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 808 | 23/09/2026 | 808 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903091452 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 21/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 808 |  | 808 |  |  | 17/09/2026 | 18/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903093104-1 JZ7711 | BLACK | 120D | S2608MR0202 | 149 | 2026-07-10 | 149 | SA | SA23/06/2026 | G3E | SHORTS | G3 | ok | (04/08/2026) | T2 Hua Feng, PI Date 31-Jul, actual receives 04-Sep. T2 Far Easten, PI Date 14-Aug, actual receives 03-Sep. 1st Art (TC 10 pcs) 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093104 JZ7711 | 21/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 2026-05-10 | 2026-06-10 |  |  | 149 |  | 149 |  |  | 2026-01-10 | 2026-02-10 |  |  | 149 |  | 149 |  |  | 28/09/2026 | 29/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903093139-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 376 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (25/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093139 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903093140-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 303 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (04/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093140 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903093145-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 392 | 15/10/2026 | 392 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903093145 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 392 |  | 392 |  |  | 2026-05-10 | 2026-06-10 |  |  | 392 |  | 392 |  |  | 2026-03-10 | 2026-05-10 |  |  | 392 |  | 392
ADIDAS | 0903093460-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 481 | 15/10/2026 | 481 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093460 KY9384 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 481 |  | 481 |  |  | 17/10/2026 | 19/10/2026 |  |  | 481 |  | 481 |  |  | 14/10/2026 | 15/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903093463-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 600 | 15/10/2026 | 600 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093463 KY9384 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 600 |  | 600 |  |  | 17/10/2026 | 19/10/2026 |  |  | 600 |  | 600 |  |  | 14/10/2026 | 15/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903093466-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 300 | 15/10/2026 | 300 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093466 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 16/10/2026 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0903093469-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 579 | 15/10/2026 | 579 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093469 KD3854 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 579 |  | 579 |  |  | 14/10/2026 | 15/10/2026 |  |  | 579 |  | 579 |  |  | 2026-10-10 | 2026-12-10 |  |  | 579 |  | 579
ADIDAS | 0903093480-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 350 | 15/10/2026 | 350 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 24-Jul, ETD ?? 516241 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093480 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 350 |  | 350 |  |  | 13/10/2026 | 14/10/2026 |  |  | 350 |  | 350 |  |  | 2026-09-10 | 2026-10-10 |  |  | 350 |  | 350
ADIDAS | 0903093503-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 5119 | 15/10/2026 | 5119 | SI | SI23/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | 28/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093503 KC9082 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 15/10/2026 | 26/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-12-10 | 22/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-08-10 | 19/10/2026 |  |  | 5119 |  | 5119
ADIDAS | 0903093882-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1600 | 30/09/2026 | 1600 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903093882 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 1600 |  | 1600 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1600 |  | 1600 |  |  | 16/09/2026 | 17/09/2026 |  |  | 1600 |  | 1600
ADIDAS | 0903093883-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 500 | 30/09/2026 | 500 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 839055 | PRINT L2+HT SUB PROCESS_V3 | 0903093883 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 23/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 19/09/2026 |  |  | 500 |  | 500 |  |  | 18/09/2026 | 18/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903093884-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 250 | 23/09/2026 | 250 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093884 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 250 |  | 250 |  |  | 16/09/2026 | 17/09/2026 |  |  | 250 |  | 250 |  |  | 15/09/2026 | 16/09/2026 |  |  | 250 |  | 250
ADIDAS | 0903093889-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 157 | 23/09/2026 | 157 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093889 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 17/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/09/2026 | 19/09/2026 |  |  | 157 |  | 157 |  |  | 14/09/2026 | 16/09/2026 |  |  | 157 |  | 157 |  |  | 2026-12-09 | 15/09/2026 |  |  | 157 |  | 157
ADIDAS | 0903093890-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 403 | 23/09/2026 | 403 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093890 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/09/2026 | 21/09/2026 |  |  | 403 |  | 403 |  |  | 16/09/2026 | 17/09/2026 |  |  | 403 |  | 403 |  |  | 15/09/2026 | 16/09/2026 |  |  | 403 |  | 403
ADIDAS | 0903093891-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 533 | 23/09/2026 | 533 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093891 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 17/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/09/2026 | 19/09/2026 |  |  | 533 |  | 533 |  |  | 14/09/2026 | 16/09/2026 |  |  | 533 |  | 533 |  |  | 2026-12-09 | 15/09/2026 |  |  | 533 |  | 533
ADIDAS | 0903093893-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 107 | 22/09/2026 | 107 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 08-Sep. 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093893 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/09/2026 | 19/09/2026 |  |  | 107 |  | 107 |  |  | 14/09/2026 | 16/09/2026 |  |  | 107 |  | 107 |  |  | 2026-12-09 | 15/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903093894-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 202 | 31/10/2026 | 202 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 516333 | PRINT L2+HT SUB PROCESS_V3 | 0903093894 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 202 |  | 202 |  |  | 15/10/2026 | 15/10/2026 |  |  | 202 |  | 202 |  |  | 14/10/2026 | 14/10/2026 |  |  | 202 |  | 202
ADIDAS | 0903093895-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 583 | 15/10/2026 | 583 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093895 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 583 |  | 583 |  |  | 13/10/2026 | 14/10/2026 |  |  | 583 |  | 583 |  |  | 2026-12-10 | 13/10/2026 |  |  | 583 |  | 583
ADIDAS | 0903093898-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 731 | 31/10/2026 | 731 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093898 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 2026-04-11 | 2026-05-11 |  |  | 731 |  | 731 |  |  | 31/10/2026 | 2026-02-11 |  |  | 731 |  | 731 |  |  | 30/10/2026 | 31/10/2026 |  |  | 731 |  | 731
ADIDAS | 0903093899-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 208 | 31/10/2026 | 208 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903093899 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-11 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 2026-04-11 | 2026-05-11 |  |  | 208 |  | 208 |  |  | 31/10/2026 | 2026-02-11 |  |  | 208 |  | 208 |  |  | 30/10/2026 | 31/10/2026 |  |  | 208 |  | 208
ADIDAS | 0903093900-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 300 | 31/10/2026 | 300 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093900 LG1784 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 23/10/2026 |  |  | 300 |  | 300 |  |  | 21/10/2026 | 22/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903093901-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 162 | 23/10/2026 | 162 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093901 LG1784 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/10/2026 | 27/10/2026 |  |  | 162 |  | 162 |  |  | 22/10/2026 | 23/10/2026 |  |  | 162 |  | 162 |  |  | 21/10/2026 | 22/10/2026 |  |  | 162 |  | 162
ADIDAS | 0903093906-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 559 | 15/10/2026 | 559 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093906 KV0333 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 559 |  | 559 |  |  | 21/09/2026 | 22/09/2026 |  |  | 559 |  | 559 |  |  | 19/09/2026 | 21/09/2026 |  |  | 559 |  | 559
ADIDAS | 0903093907-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 309 | 15/10/2026 | 309 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093907 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 309 |  | 309 |  |  | 21/09/2026 | 22/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903093908-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 345 | 15/10/2026 | 345 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903093908 LG1784 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 345 |  | 345 |  |  | 22/09/2026 | 23/09/2026 |  |  | 345 |  | 345 |  |  | 21/09/2026 | 22/09/2026 |  |  | 345 |  | 345
ADIDAS | 0903093909-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 158 | 15/10/2026 | 158 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093909 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 158 |  | 158 |  |  | 22/09/2026 | 23/09/2026 |  |  | 158 |  | 158 |  |  | 21/09/2026 | 22/09/2026 |  |  | 158 |  | 158
ADIDAS | 0903093910-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 425 | 15/10/2026 | 425 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093910 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 425 |  | 425 |  |  | 23/09/2026 | 24/09/2026 |  |  | 425 |  | 425 |  |  | 22/09/2026 | 23/09/2026 |  |  | 425 |  | 425
ADIDAS | 0903093911-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 354 | 15/10/2026 | 354 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093911 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 354 |  | 354 |  |  | 23/09/2026 | 24/09/2026 |  |  | 354 |  | 354 |  |  | 22/09/2026 | 23/09/2026 |  |  | 354 |  | 354
ADIDAS | 0903093912-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 105 | 15/10/2026 | 105 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093912 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 105 |  | 105 |  |  | 22/09/2026 | 23/09/2026 |  |  | 105 |  | 105 |  |  | 21/09/2026 | 22/09/2026 |  |  | 105 |  | 105
ADIDAS | 0903095162-1 KE9656 | BLACK | 105D | S2608WR0201A | 7 | 15/10/2026 | 7 | SI | SI23/06/2026 | G3D | SHORTS | G3 | ok |  | 23/09: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 22-Aug, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 10-Sep. T2 Y.R.C, PI Date 15-Aug, actual receives 03-Sep (using fabric from TRAX). T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095162 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 7 |  | 7 |  |  | 13/10/2026 | 13/10/2026 |  |  | 7 |  | 7 |  |  | 2026-12-10 | 2026-12-10 |  |  | 7 |  | 7
ADIDAS | 0903095174-1 KE9656 | BLACK | 105D | S2608WR0201A | 5411 | 15/10/2026 | 5411 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (15/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095174 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 29/10/2026 |  |  | 5411 |  | 5411 |  |  | 13/10/2026 | 26/10/2026 |  |  | 5411 |  | 5411 |  |  | 2026-12-10 | 24/10/2026 |  |  | 5411 |  | 5411
ADIDAS | 0903095176-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 503 | 15/10/2026 | 503 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095176 LC6791 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX | 23/10/2026 | 24/10/2026 |  |  | 503 |  | 503 |  |  | 20/10/2026 | 21/10/2026 |  |  | 503 |  | 503 |  |  | 16/10/2026 | 17/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903095186-1 KA6229 | BLACK | 120D | S2608WR0202 | 448 | 23/09/2026 | 448 | SA | SA23/06/2026 | G1N | SHORTS | G1 | ok | ok | 21/09: ex-fty. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095186 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 448 |  | 448 |  |  | 2026-11-09 | 2026-12-09 |  |  | 448 |  | 448 |  |  | 2026-08-09 | 2026-09-09 | 14/09/2026 | 14/09/2026 | 448 | 287 | 161
ADIDAS | 0903095189-1 KA6229 | BLACK | 120D | S2608WR0202 | 301 | 22/09/2026 | 301 | SA | SA23/06/2026 | G1P | SHORTS | G1 | ok | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual recieves 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Aug (switch fabric from TREX). 1st Art (TC 10 pcs) 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095189 KA6229 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 15/09/2026 | 18/09/2026 |  |  | 301 |  | 301 |  |  | 2026-11-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 301 | 269 | 32
ADIDAS | 0903095193-1 KA6229 | BLACK | 120D | S2608WR0202 | 339 | 15/10/2026 | 339 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 07-Sep, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095193 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 339 |  | 339 |  |  | 2026-06-10 | 2026-08-10 |  |  | 339 |  | 339 |  |  | 2026-02-10 | 2026-05-10 | 2026-09-09 | 2026-09-09 | 339 | 322 | 17
ADIDAS | 0903095197-1 KA6229 | BLACK | 120D | S2608WR0202 | 765 | 22/09/2026 | 765 | SA | SA23/06/2026 | G1P | SHORTS | G1 | (14/08/2026) | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095197 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 22/09/2026 |  |  | 765 |  | 765 |  |  | 15/09/2026 | 18/09/2026 |  |  | 765 |  | 765 |  |  | 2026-11-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 765 | 558 | 207
ADIDAS | 0903095199-1 KA6229 | BLACK | 120D | S2608WR0202 | 277 | 15/10/2026 | 277 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095199 KA6229 | 21/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 277 |  | 277 |  |  | 2026-06-10 | 2026-08-10 |  |  | 277 |  | 277 |  |  | 2026-02-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903095204-1 KC4947 | BLACK | 105D | S2608WR0216 | 523 | 15/10/2026 | 523 | SA | SA23/06/2026 | G3G | PANTS | G3 | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903095204 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/10/2026 | adi365 Astro W |  | SS27-TRAX | 14/10/2026 | 17/10/2026 |  |  | 523 |  | 523 |  |  | 2026-10-10 | 14/10/2026 |  |  | 523 |  | 523 |  |  | 2026-09-10 | 13/10/2026 |  |  | 523 |  | 523
ADIDAS | 0903110773-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 580 | 31/10/2026 | 580 | SI | SI26/06/2026 | G1L | JACKET | G1 | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110773 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-11 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-11-11 | 13/11/2026 |  |  | 580 |  | 580 |  |  | 2026-07-11 | 2026-10-11 |  |  | 580 |  | 580
ADIDAS | 0903110856-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1103 | 26/09/2026 | 1103 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 22-Jul, ETD ?? Waiting fabric. T2 Formosa, PI Date 26-Jul, ETD 03-Aug, ETA-Kaha 14-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110856 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1103 |  | 1103 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1103 |  | 1103
ADIDAS | 0903110887-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 5118 | 15/10/2026 | 5118 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110887 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-08-10 | 28/10/2026 |  |  | 5118 |  | 5118 |  |  | 2026-05-10 | 24/10/2026 |  |  | 5118 |  | 5118
ADIDAS | 0903128588-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903128588 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-09-09 | 420 | 420
ADIDAS | 0903129024-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 400 | 31/10/2026 | 400 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903129024 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 400 |  | 400 |  |  | 2026-04-11 | 2026-06-11 |  |  | 400 |  | 400
ADIDAS | 0903129074-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 152 | 23/10/2026 | 152 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129074 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 152 |  | 152 |  |  | 2026-05-11 | 2026-06-11 |  |  | 152 |  | 152
ADIDAS | 0903129078-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 399 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903129078 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903129093-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 792 | 15/09/2026 | 792 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129093 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 16/09/2026 | 2026-02-09 | 15/09/2026 | 792 | 792 |  |  | 6 | 27/08/2026 | 2026-12-09 | 2026-05-08 | 22/08/2026 | 792 | 792
ADIDAS | 0903129376-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 550 | 15/10/2026 | 550 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129376 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 550 |  | 550 |  |  | 2026-07-10 | 2026-08-10 |  |  | 550 |  | 550
ADIDAS | 0903129444-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 750 | 23/10/2026 | 750 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129444 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 750 |  | 750 |  |  | 15/10/2026 | 16/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903129505-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 303 | 15/10/2026 | 303 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129505 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-10-10 | 13/10/2026 | 2026-02-09 | 2026-02-09 | 303 | 19 | 284
ADIDAS | 0903130488-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 2026-07-10 | 103 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130488 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-03-10 |  |  | 103 |  | 103 |  |  | 30/09/2026 | 30/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903130527-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130527 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 500 |  | 500 |  |  | 2026-06-10 | 2026-07-10 |  |  | 500 |  | 500
ADIDAS | 0903130582-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 106 | 2026-07-10 | 106 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130582 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 106 |  | 106 |  |  | 2026-02-10 | 2026-03-10 | 20/08/2026 | 29/08/2026 | 106 | 34 | 72
ADIDAS | 0903130615-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130615 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903130651-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 698 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903130651 LG9672 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903130696-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 387 | 31/10/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130696 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903130740-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 325 | 30/09/2026 | 325 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130740 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W 3S FT OH PT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 325 |  | 325 |  |  | 2026-05-10 | 2026-06-10 | 14/08/2026 | 2026-07-09 | 325 | 294 | 31
ADIDAS | 0903130742-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 208 | 15/09/2026 | 208 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130742 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 2026-03-09 | 24/08/2026 | 2026-03-09 | 208 | 208 |  |  |  | 19/08/2026 | 31/08/2026 | 2026-07-08 | 2026-11-08 | 208 | 208
ADIDAS | 0903130761-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 550 | 15/10/2026 | 550 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130761 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 550 |  | 550 |  |  | 20/10/2026 | 21/10/2026 | 2026-03-09 | 2026-09-09 | 550 | 85 | 465
ADIDAS | 0903130786-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 101 | 2026-07-10 | 101 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130786 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 101 |  | 101 |  |  | 17/09/2026 | 18/09/2026 | 2026-02-09 | 2026-02-09 | 101 | 101
ADIDAS | 0903130839-1 LF0723 | BLACK | 105D | S2754MAS511B | 358 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130839 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130929-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 15/10/2026 | 103 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130929 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 103 |  | 103 |  |  | 2026-07-10 | 2026-07-10 |  |  | 103 |  | 103
ADIDAS | 0903130954-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 144 | 23/10/2026 | 144 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130954 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 144 |  | 144 |  |  | 28/10/2026 | 30/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903130982-1 LF0723 | BLACK | 105D | S2754MAS511B | 308 | 15/10/2026 | 308 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130982 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 308 |  | 308 |  |  | 22/10/2026 | 24/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903131041-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 343 | 23/09/2026 | 343 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131041 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 343 |  | 343 |  |  | 17/09/2026 | 18/09/2026 | 31/08/2026 | 2026-03-09 | 343 | 292 | 51
ADIDAS | 0903131046-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 103 | 15/10/2026 | 103 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131046 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 103 |  | 103 |  |  | 20/10/2026 | 21/10/2026 | 2026-02-09 | 2026-10-09 | 103 | 103
ADIDAS | 0903131080-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 120 | 23/10/2026 | 120 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131080 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 120 |  | 120 |  |  | 17/10/2026 | 19/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903131111-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 254 | 30/09/2026 | 254 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903131111 LE4307 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 254 |  | 254 |  |  | 23/09/2026 | 25/09/2026 |  |  | 254 |  | 254
ADIDAS | 0903131716-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131716 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 303 |  | 303 |  |  | 2026-09-10 | 2026-10-10 |  |  | 303 |  | 303
ADIDAS | 0903131801-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 744 | 15/10/2026 | 744 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131801 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 744 |  | 744 |  |  | 15/10/2026 | 17/10/2026 |  |  | 744 |  | 744
ADIDAS | 0903131943-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 580 | 23/10/2026 | 580 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131943 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 580 |  | 580 |  |  | 2026-06-11 | 2026-07-11 |  |  | 580 |  | 580
ADIDAS | 0903132003-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 586 | 23/10/2026 | 586 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132003 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 586 |  | 586 |  |  | 17/10/2026 | 19/10/2026 |  |  | 586 |  | 586
ADIDAS | 0903132049-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 270 | 15/10/2026 | 270 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132049 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 270 |  | 270 |  |  | 17/10/2026 | 19/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903132130-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 450 | 23/10/2026 | 450 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132130 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 450 |  | 450 |  |  | 17/10/2026 | 19/10/2026 |  |  | 450 |  | 450
ADIDAS | 0903132419-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 106 | 2026-07-10 | 106 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132419 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 106 |  | 106 |  |  | 2026-06-10 | 2026-07-10 |  |  | 106 |  | 106
ADIDAS | 0903132455-1 LD5424 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS614WVB | 331 | 15/10/2026 | 331 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Formosa, PI Date 12-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 12-Aug, actual receives 28-Aug. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132455 LD5424 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | M 95S WV WB LND OLIVE FOUR S27/OFF WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 331 |  | 331 |  |  | 13/10/2026 | 15/10/2026 |  |  | 331 |  | 331
ADIDAS | 0903132482-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 150 | 2026-12-09 | 150 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132482 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 150 | 150 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-03-09 | 150 | 150
ADIDAS | 0903132522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 634 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903132522 KX3654 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903132534-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 255 | 15/09/2026 | 255 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132534 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 2026-04-09 | 255 | 255 |  |  |  | 29/08/2026 | 31/08/2026 | 15/08/2026 | 24/08/2026 | 255 | 255
ADIDAS | 0903132553-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132553 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 200 | 200 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 22/08/2026 | 200 | 200
ADIDAS | 0903132571-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 704 | 30/09/2026 | 704 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132571 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 3S FT FZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 704 |  | 704 |  |  | 14/09/2026 | 15/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903132573-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132573 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 20/08/2026 | 27/08/2026 | 200 | 200
ADIDAS | 0903132592-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 170 | 2026-12-09 | 170 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132592 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 170 | 170 |  |  |  | 29/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 170 | 170
ADIDAS | 0903132607-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 339 | 31/10/2026 |  | SI | SI26/06/2026 |  | JACKET |  | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132607 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903132697-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 691 | 15/09/2026 | 691 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132697 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 2026-03-09 | 24/08/2026 | 2026-01-09 | 691 | 691 |  |  |  | 18/08/2026 | 31/08/2026 | 2026-04-08 | 2026-07-08 | 691 | 691
ADIDAS | 0903132705-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 170 | 30/09/2026 | 170 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 22/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132705 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 170 |  | 170 |  |  | 23/09/2026 | 25/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903132709-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 15/10/2026 | 600 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132709 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 14/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 600 |  | 600 |  |  | 2026-10-10 | 13/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903132754-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 278 | 15/10/2026 | 278 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132754 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 278 |  | 278 |  |  | 2026-09-10 | 2026-10-10 |  |  | 278 |  | 278
ADIDAS | 0903132786-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 369 | 15/10/2026 | 369 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132786 KY6510 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 369 |  | 369 |  |  | 2026-02-10 | 2026-03-10 |  |  | 369 |  | 369
ADIDAS | 0903132803-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132803 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 266 |  | 266 |  |  | 2026-07-10 | 2026-07-10 |  |  | 266 |  | 266
ADIDAS | 0903132827-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132827 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 271 |  | 271 |  |  | 2026-05-10 | 2026-06-10 | 28/08/2026 | 2026-03-09 | 271 | 268 | 3
ADIDAS | 0903132837-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 143 | 2026-07-10 | 143 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132837 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 | 2026-01-09 | 2026-04-09 | 143 | 36 | 107
ADIDAS | 0903132864-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 15/10/2026 | 316 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132864 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 19/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 316 |  | 316 |  |  | 15/10/2026 | 17/10/2026 |  |  | 316 |  | 316
ADIDAS | 0903132871-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 358 | 15/10/2026 | 358 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Kahatex, PI Date 12-Aug, actual receives 05-Sep. T2 Formosa, PI Date 12-Aug, actual receives 03-Sep. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132871 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 358 |  | 358 |  |  | 15/10/2026 | 16/10/2026 |  |  | 358 |  | 358
ADIDAS | 0903132916-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 900 | 15/10/2026 | 900 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132916 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 900 |  | 900 |  |  | 19/10/2026 | 20/10/2026 |  |  | 900 |  | 900
ADIDAS | 0903132921-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 615 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903132921 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903132931-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 308 | 2026-07-10 | 308 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132931 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 308 |  | 308 |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 29/08/2026 | 308 | 308
ADIDAS | 0903132951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 830 | 31/10/2026 | 830 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903132951 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 830 |  | 830 |  |  | 2026-10-11 | 2026-12-11 |  |  | 830 |  | 830
ADIDAS | 0903132955-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132955 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 266 |  | 266 |  |  | 2026-09-10 | 2026-10-10 |  |  | 266 |  | 266
ADIDAS | 0903132969-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132969 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 1000 |  | 1000 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1000 |  | 1000
ADIDAS | 0903132997-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132997 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-01-09 | 2026-10-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-09-09 | 2026-04-08 | 26/08/2026 | 420 | 420
ADIDAS | 0903133002-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1375 | 2026-07-10 | 1375 | SI | SI26/06/2026 | G1H | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133002 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 1375 |  | 1375 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 24/08/2026 | 1375 | 1293 | 82
ADIDAS | 0903133009-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133009 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 1000 |  | 1000 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903133055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1218 | 2026-07-10 | 1218 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1218 |  | 1218 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1218 |  | 1218
ADIDAS | 0903133059-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 367 | 15/10/2026 | 367 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133059 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 367 |  | 367 |  |  | 13/10/2026 | 14/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903133068-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 312 | 31/10/2026 | 312 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903133068 LG9661 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 312 |  | 312 |  |  | 2026-05-11 | 2026-07-11 |  |  | 312 |  | 312
ADIDAS | 0903133104-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 2450 | 2026-07-10 | 2450 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133104 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 2450 |  | 2450 |  |  | 2026-03-10 | 2026-06-10 | 26/08/2026 | 28/08/2026 | 2450 | 2432 | 18
ADIDAS | 0903133114-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 282 | 15/09/2026 | 282 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133114 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 15/09/2026 | 282 | 282 |  |  | 5 | 29/08/2026 | 2026-11-09 | 20/08/2026 | 24/08/2026 | 282 | 282
ADIDAS | 0903133128-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 500 | 15/10/2026 | 500 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133128 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 500 |  | 500 |  |  | 2026-09-10 | 2026-09-10 |  |  | 500 |  | 500
ADIDAS | 0903133146-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133146 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903133194-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 103 | 2026-07-10 | 103 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133194 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 103 |  | 103 |  |  | 2026-02-10 | 2026-03-10 | 31/08/2026 | 2026-05-09 | 103 | 101 | 2
ADIDAS | 0903133260-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 194 | 2026-07-10 | 194 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133260 LI2646 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 194 |  | 194 |  |  | 29/09/2026 | 30/09/2026 | 28/08/2026 | 28/08/2026 | 194 | 181 | 13
ADIDAS | 0903133331-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133331 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 500 |  | 500 |  |  | 2026-02-10 | 2026-03-10 | 31/08/2026 | 2026-04-09 | 500 | 484 | 16
ADIDAS | 0903133357-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 675 | 2026-02-09 | 675 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133357 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 675 | 675 |  |  |  | 27/08/2026 | 28/08/2026 | 21/08/2026 | 2026-03-09 | 675 | 675
ADIDAS | 0903133374-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 143 | 2026-07-10 | 143 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133374 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-03-10 |  |  | 143 |  | 143 |  |  | 30/09/2026 | 30/09/2026 |  |  | 143 |  | 143
ADIDAS | 0903133397-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 115 | 2026-02-09 | 115 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133397 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 115 | 115 |  |  |  | 27/08/2026 | 28/08/2026 | 26/08/2026 | 2026-01-09 | 115 | 115
ADIDAS | 0903133475-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133475 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100
ADIDAS | 0903133506-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E,G2R | ACCESSORIES | G1,G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133506 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-03-09 | 24/08/2026 | 31/08/2026 | 420 | 420
ADIDAS | 0903133517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133517 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 19/08/2026 | 26/08/2026 | 220 | 220
ADIDAS | 0903133575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 220 | 220 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 220 | 220
ADIDAS | 0903133589-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 586 | 23/09/2026 | 586 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133589 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 586 |  | 586 |  |  | 17/09/2026 | 18/09/2026 | 2026-01-09 | 2026-04-09 | 586 | 393 | 193
ADIDAS | 0903133603-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 84 | 15/10/2026 | 84 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133603 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 84 | 84 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 84 | 84
ADIDAS | 0903133644-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133644 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 28/08/2026 | 2026-03-09 | 27/08/2026 | 2026-02-09 | 295 | 295
ADIDAS | 0903133706-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 251 | 15/10/2026 | 251 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133706 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 251 |  | 251 |  |  | 2026-07-10 | 2026-07-10 |  |  | 251 |  | 251
ADIDAS | 0903133715-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 545 | 23/10/2026 | 545 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133715 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 545 |  | 545 |  |  | 26/10/2026 | 27/10/2026 | 2026-03-09 | 2026-03-09 | 545 | 545
ADIDAS | 0903133759-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 15/09/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133759 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-01-09 | 249 | 249 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-04-08 | 2026-05-08 | 249 | 249
ADIDAS | 0903133849-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 423 | 2026-07-10 | 423 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133849 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 423 |  | 423 |  |  | 30/09/2026 | 2026-02-10 |  |  | 423 |  | 423
ADIDAS | 0903133851-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 2026-07-10 | 156 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133851 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 156 |  | 156 |  |  | 17/09/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 156 | 150 | 6
ADIDAS | 0903133871-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133871 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 234 | 234 |  |  |  | 28/08/2026 | 31/08/2026 | 26/08/2026 | 2026-03-09 | 234 | 234
ADIDAS | 0903133886-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 888 | 23/10/2026 | 888 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133886 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 888 |  | 888 |  |  | 24/10/2026 | 26/10/2026 | 31/08/2026 | 2026-07-09 | 888 | 687 | 201
ADIDAS | 0903133936-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 358 | 2026-07-10 | 358 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133936 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 358 |  | 358 |  |  | 29/09/2026 | 30/09/2026 | 15/08/2026 | 2026-10-09 | 358 | 349 | 9
ADIDAS | 0903133965-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133965 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-08 | 2026-10-08 | 420 | 420
ADIDAS | 0903134033-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 284 | 15/09/2026 | 284 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134033 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 2026-05-09 | 284 | 284 |  |  |  | 29/08/2026 | 2026-11-09 | 19/08/2026 | 2026-09-09 | 284 | 284
ADIDAS | 0903134047-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2000 | 2026-07-10 | 2000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134047 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-12-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 2000 |  | 2000 |  |  | 2026-08-10 | 2026-12-10 |  |  | 2000 |  | 2000
ADIDAS | 0903134049-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 980 | 15/10/2026 | 980 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134049 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 980 |  | 980 |  |  | 14/10/2026 | 15/10/2026 |  |  | 980 |  | 980
ADIDAS | 0903134104-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 142 | 2026-02-09 | 142 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134104 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 142 | 142 |  |  |  | 27/08/2026 | 29/08/2026 | 18/08/2026 | 27/08/2026 | 142 | 142
ADIDAS | 0903134120-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1000 | 2026-07-10 | 1000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134120 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1000 |  | 1000 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1000 |  | 1000
ADIDAS | 0903134126-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 203 | 15/10/2026 | 203 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134126 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 203 |  | 203 |  |  | 2026-05-10 | 2026-06-10 | 19/08/2026 | 31/08/2026 | 203 | 203
ADIDAS | 0903134200-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 225 | 15/09/2026 | 225 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134200 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 225 | 225 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-07-09 | 225 | 225
ADIDAS | 0903134339-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 210 | 2026-12-09 | 210 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134339 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 210 | 210 |  |  |  | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-10-09 | 210 | 210
ADIDAS | 0903134404-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134404 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 100 | 100 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-04-09 | 100 | 100
ADIDAS | 0903134448-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134448 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 28/08/2026 | 31/08/2026 | 27/08/2026 | 2026-07-09 | 100 | 100
ADIDAS | 0903134486-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134486 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 29/08/2026 | 2026-02-09 | 28/08/2026 | 2026-12-09 | 295 | 295
ADIDAS | 0903134529-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134529 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-03-09 | 2026-04-09 | 220 | 220 |  |  |  | 28/08/2026 | 2026-03-09 | 2026-02-09 | 2026-10-09 | 220 | 220
ADIDAS | 0903134690-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 150 | 2026-12-09 | 150 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134690 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 150 | 150 |  |  |  | 29/08/2026 | 31/08/2026 | 31/08/2026 | 2026-02-09 | 150 | 150
ADIDAS | 0903134709-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 2191 | 15/10/2026 | 2191 | AN | AN26/06/2026 | G1B | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. T2 Formosa, PI Date 26-Jul, actual receives 27-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134709 KW2909 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 2191 |  | 2191 |  |  | 22/09/2026 | 26/09/2026 |  |  | 2191 |  | 2191
ADIDAS | 0903134753-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 265 | 15/09/2026 | 265 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134753 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-07-09 | 265 | 265 |  |  |  | 29/08/2026 | 2026-02-09 | 22/08/2026 | 27/08/2026 | 265 | 265
ADIDAS | 0903134783-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 225 | 15/09/2026 | 225 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134783 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-09 | 15/09/2026 | 2026-05-09 | 15/09/2026 | 225 | 225 |  |  | 77 | 31/08/2026 | 2026-11-09 | 2026-03-09 | 2026-04-09 | 225 | 216 | 9
ADIDAS | 0903134821-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134821 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 15/08/2026 | 29/08/2026 | 220 | 220
ADIDAS | 0903134827-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (15/08/2026(10)) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134827 KS1804 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 28/09/2026 | 2026-07-08 | 20/08/2026 | 1072 | 334 | 738 |  |  | 2026-04-08 | 24/09/2026 | 2026-01-08 | 2026-07-09 | 1072 | 1056 | 16
ADIDAS | 0903134857-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 67 | 15/10/2026 | 67 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134857 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 67 | 67 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-08-09 | 67 | 67
ADIDAS | 0903134876-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 31/10/2026 | 803 | SI | SI26/06/2026 | G2H | T-SHIRT | G2 | ok | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134876 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | BIG APPLE TEE |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 803 |  | 803 |  |  | 2026-03-10 | 2026-03-10 |  |  | 803 |  | 803
ADIDAS | 0903134905-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 56 | 15/10/2026 | 56 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134905 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 56 | 56 |  |  |  | 29/08/2026 | 2026-03-09 | 31/08/2026 | 13/09/2026 | 56 | 55 | 1
ADIDAS | 0903134935-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 31/10/2026 | 804 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134935 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | ARCH SEAL TEE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 804 |  | 804 |  |  | 17/10/2026 | 19/10/2026 |  |  | 804 |  | 804
ADIDAS | 0903134982-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 105 | 30/09/2026 | 105 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134982 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 105 |  | 105 |  |  | 2026-02-10 | 2026-02-10 |  |  | 105 |  | 105
ADIDAS | 0903135003-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 634 | 2026-08-09 | 634 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135003 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 634 | 634 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 634 | 634
ADIDAS | 0903135049-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 744 | 2026-08-09 | 744 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135049 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 744 | 744 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 744 | 744
ADIDAS | 0903135083-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 26/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135083 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1072 |  | 1072 |  |  | 2026-02-10 | 2026-03-10 | 26/08/2026 | 2026-02-09 | 1072 | 1067 | 5
ADIDAS | 0903135108-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 642 | 2026-08-09 | 642 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135108 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 642 | 642 |  |  |  | 2026-10-08 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 642 | 642
ADIDAS | 0903135147-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 270 | 15/09/2026 | 270 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135147 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 270 | 270 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-08 | 2026-12-08 | 270 | 270
ADIDAS | 0903135150-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 125 | 2026-07-10 | 125 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135150 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 125 |  | 125 |  |  | 29/09/2026 | 30/09/2026 | 28/08/2026 | 29/08/2026 | 125 | 125
ADIDAS | 0903135182-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 171 | 23/10/2026 | 171 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | (04/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135182 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 171 |  | 171 |  |  | 20/10/2026 | 21/10/2026 |  |  | 171 |  | 171
ADIDAS | 0903135184-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135184 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/08/2026 | 2026-12-09 | 29/08/2026 | 2026-10-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-09-09 | 20/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135185-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 15/10/2026 | 259 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135185 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 30/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 259 |  | 259 |  |  | 27/10/2026 | 28/10/2026 | 2026-02-09 | 2026-12-09 | 259 | 228 | 31
ADIDAS | 0903135215-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 258 | 15/10/2026 | 258 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135215 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 258 |  | 258 |  |  | 2026-05-10 | 2026-06-10 | 15/08/2026 | 2026-01-09 | 258 | 252 | 6
ADIDAS | 0903135229-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 184 | 23/10/2026 | 184 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135229 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 184 |  | 184 |  |  | 15/10/2026 | 16/10/2026 |  |  | 184 |  | 184
ADIDAS | 0903135251-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 233 | 15/10/2026 | 233 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135251 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 233 |  | 233 |  |  | 13/10/2026 | 14/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903135264-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 596 | 31/10/2026 | 596 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135264 LG9664 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-11 | 2026-12-11 |  |  | 596 |  | 596 |  |  | 2026-06-11 | 2026-09-11 |  |  | 596 |  | 596
ADIDAS | 0903135286-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135286 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 230 |  | 230 |  |  | 30/09/2026 | 2026-01-10 |  |  | 230 |  | 230
ADIDAS | 0903135352-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 310 | 2026-07-10 | 310 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135352 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 310 |  | 310 |  |  | 30/09/2026 | 2026-01-10 |  |  | 310 |  | 310
ADIDAS | 0903135358-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 750 | 23/10/2026 | 750 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135358 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 750 |  | 750 |  |  | 28/10/2026 | 30/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903135402-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 377 | 31/10/2026 | 377 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135402 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 377 |  | 377 |  |  | 2026-05-11 | 2026-07-11 |  |  | 377 |  | 377
ADIDAS | 0903135472-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 115 | 15/09/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135472 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 115 | 115 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-10-08 | 115 | 115
ADIDAS | 0903135480-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 148 | 15/10/2026 | 148 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135480 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 30/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 148 |  | 148 |  |  | 27/10/2026 | 28/10/2026 | 31/08/2026 | 2026-09-09 | 148 | 148
ADIDAS | 0903135498-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 980 | 15/10/2026 | 980 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135498 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 980 |  | 980 |  |  | 2026-10-10 | 2026-12-10 |  |  | 980 |  | 980
ADIDAS | 0903135544-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 169 | 2026-07-10 | 169 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135544 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 169 |  | 169 |  |  | 2026-06-10 | 2026-07-10 | 31/08/2026 | 2026-07-09 | 169 | 169
ADIDAS | 0903135569-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 189 | 2026-07-10 | 189 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135569 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 189 |  | 189 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-07-09 | 189 | 188 | 1
ADIDAS | 0903135588-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135588 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 29/08/2026 | 420 | 420
ADIDAS | 0903135590-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 811 | 15/10/2026 | 811 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135590 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 811 |  | 811 |  |  | 2026-06-10 | 2026-07-10 | 28/08/2026 | 2026-09-09 | 811 | 779 | 32
ADIDAS | 0903135646-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 84 | 15/10/2026 | 84 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135646 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 84 | 84 |  |  |  | 29/08/2026 | 31/08/2026 | 19/08/2026 | 26/08/2026 | 84 | 84
ADIDAS | 0903135659-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135659 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135683-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 67 | 15/10/2026 | 67 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135683 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 67 | 67 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 28/08/2026 | 67 | 67
ADIDAS | 0903135743-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 282 | 15/09/2026 | 282 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135743 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 282 | 282 |  |  |  | 27/08/2026 | 31/08/2026 | 24/08/2026 | 2026-03-09 | 282 | 282
ADIDAS | 0903135819-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 122 | 2026-02-09 | 122 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135819 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 122 | 122 |  |  |  | 27/08/2026 | 29/08/2026 | 26/08/2026 | 2026-04-09 | 122 | 122
ADIDAS | 0903135839-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135839 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 19/08/2026 | 24/08/2026 | 18/08/2026 | 2026-07-09 | 660 | 660
ADIDAS | 0903135865-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 247 | 23/10/2026 | 247 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135865 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 247 |  | 247 |  |  | 2026-05-11 | 2026-06-11 |  |  | 247 |  | 247
ADIDAS | 0903135961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 292 | 15/09/2026 | 292 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 292 | 292 |  |  |  | 29/08/2026 | 2026-01-09 | 21/08/2026 | 31/08/2026 | 292 | 292
ADIDAS | 0903136044-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136044 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 660 | 660
ADIDAS | 0903136117-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 778 | 2026-08-09 | 778 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136117 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 778 | 778 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 28/08/2026 | 778 | 778
ADIDAS | 0903136141-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 119 | 2026-02-09 | 119 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136141 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 119 | 119 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-03-09 | 119 | 119
ADIDAS | 0903136653-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 136 | 23/10/2026 | 136 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136653 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 136 |  | 136 |  |  | 14/10/2026 | 14/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903136661-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 800 | 2026-07-10 | 800 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136661 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 800 |  | 800 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-12-09 | 800 | 791 | 9
ADIDAS | 0903136713-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 580 | 23/10/2026 | 580 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136713 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 580 |  | 580 |  |  | 13/10/2026 | 14/10/2026 | 22/08/2026 | 2026-09-09 | 580 | 534 | 46
ADIDAS | 0903136726-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 308 | 2026-07-10 | 308 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136726 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 308 |  | 308 |  |  | 30/09/2026 | 2026-02-10 |  |  | 308 |  | 308
ADIDAS | 0903136848-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 249 | 23/10/2026 | 249 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136848 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 249 |  | 249 |  |  | 28/10/2026 | 30/10/2026 |  |  | 249 |  | 249
ADIDAS | 0903136900-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 254 | 23/10/2026 | 254 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136900 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 254 |  | 254 |  |  | 13/10/2026 | 14/10/2026 | 27/08/2026 | 2026-01-09 | 254 | 254
ADIDAS | 0903136925-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 104 | 2026-07-10 | 104 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136925 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 104 |  | 104 |  |  | 2026-07-10 | 2026-08-10 |  |  | 104 |  | 104
ADIDAS | 0903136961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 422 | 2026-07-10 | 422 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 422 |  | 422 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-07-09 | 422 | 419 | 3
ADIDAS | 0903136981-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 417 | 23/10/2026 | 417 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136981 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 417 |  | 417 |  |  | 17/10/2026 | 19/10/2026 |  |  | 417 |  | 417
ADIDAS | 0903136996-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 277 | 15/09/2026 | 277 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136996 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 277 | 277 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 26/08/2026 | 277 | 277
ADIDAS | 0903137027-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137027 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903137049-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 117 | 15/09/2026 | 117 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137049 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 117 | 117 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-12-09 | 117 | 117
ADIDAS | 0903137111-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 194 | 15/09/2026 | 194 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137111 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 194 | 194 |  |  | 194 | 2026-09-09 | 2026-11-09 | 2026-03-09 | 2026-10-09 | 194 | 163 | 31
ADIDAS | 0903137134-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 358 | 15/09/2026 | 358 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137134 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 17/09/2026 | 2026-03-09 | 15/09/2026 | 358 | 358 |  |  | 9 | 29/08/2026 | 14/09/2026 | 31/08/2026 | 2026-07-09 | 358 | 358
ADIDAS | 0903137310-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 382 | 30/09/2026 | 382 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137310 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 382 |  | 382 |  |  | 15/09/2026 | 16/09/2026 |  |  | 382 |  | 382
ADIDAS | 0903137434-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 4525 | 15/10/2026 | 4525 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137434 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/10/2026 | 2026-04-11 |  |  | 4525 |  | 4525 |  |  | 17/10/2026 | 31/10/2026 |  |  | 4525 |  | 4525
ADIDAS | 0903137501-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 320 | 30/09/2026 | 320 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137501 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 320 |  | 320 |  |  | 25/09/2026 | 29/09/2026 | 28/08/2026 | 2026-01-09 | 320 | 51 | 269
ADIDAS | 0903137540-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 401 | 15/10/2026 | 401 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137540 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 401 |  | 401 |  |  | 28/09/2026 | 30/09/2026 |  |  | 401 |  | 401
ADIDAS | 0903137727-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 132 | 2026-07-10 | 132 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137727 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 132 |  | 132 |  |  | 29/09/2026 | 30/09/2026 | 27/08/2026 | 2026-07-09 | 132 | 132
ADIDAS | 0903138028-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138028 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 420 | 420 |  |  |  | 29/08/2026 | 2026-09-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903138063-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 137 | 2026-07-10 | 137 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138063 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 137 |  | 137 |  |  | 30/09/2026 | 2026-01-10 |  |  | 137 |  | 137
ADIDAS | 0903138297-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 266 | 2026-02-09 | 266 | SA | SA26/06/2026 | G1B,G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138297 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 266 | 266 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 266 | 266
ADIDAS | 0903138432-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 158 | 2026-02-09 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138432 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 158 | 158 |  |  |  | 27/08/2026 | 28/08/2026 | 22/08/2026 | 29/08/2026 | 158 | 158
ADIDAS | 0903138575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 276 | 15/10/2026 | 276 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 21/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 276 |  | 276 |  |  | 17/10/2026 | 19/10/2026 |  |  | 276 |  | 276
ADIDAS | 0903138615-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 158 | 2026-07-10 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138615 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 158 |  | 158 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-07-09 | 158 | 155 | 3
ADIDAS | 0903139177-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 107 | 23/10/2026 | 107 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139177 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 107 |  | 107 |  |  | 17/10/2026 | 19/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903139269-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 563 | 2026-07-10 | 563 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139269 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 563 |  | 563 |  |  | 28/09/2026 | 28/09/2026 | 15/08/2026 | 2026-07-09 | 563 | 550 | 13
ADIDAS | 0903139328-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 707 | 23/09/2026 | 707 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139328 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 707 |  | 707 |  |  | 21/09/2026 | 22/09/2026 | 27/08/2026 | 31/08/2026 | 707 | 706 | 1
ADIDAS | 0903139403-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 112 | 2026-02-09 | 112 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139403 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 112 | 112 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-03-09 | 112 | 112
ADIDAS | 0903139439-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 584 | 23/09/2026 | 584 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139439 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 19/09/2026 | 15/09/2026 | 15/09/2026 | 584 | 32 | 552 |  | 32 | 2026-10-09 | 16/09/2026 | 31/08/2026 | 2026-04-09 | 584 | 580 | 4
ADIDAS | 0903139469-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 105 | 2026-07-10 | 105 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139469 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 105 |  | 105 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-07-09 | 105 | 105
ADIDAS | 0903139660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139660 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-04-09 | 234 | 234 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-02-09 | 234 | 234
ADIDAS | 0903139767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 136 | 2026-02-09 | 136 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 136 | 136 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 136 | 136
ADIDAS | 0903140620-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 500 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903140620 KG3190 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903140969-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 5996 | 23/10/2026 | 5996 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140969 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 20/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 20/10/2026 | 26/10/2026 |  |  | 5996 |  | 5996 |  |  | 16/10/2026 | 22/10/2026 |  |  | 5996 |  | 5996
ADIDAS | 0903140992-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 2091 | 23/10/2026 | 2091 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140992 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 22/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 22/10/2026 | 27/10/2026 |  |  | 2091 |  | 2091 |  |  | 19/10/2026 | 23/10/2026 |  |  | 2091 |  | 2091
ADIDAS | 0903141018-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141018 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 17/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/10/2026 | 21/10/2026 |  |  | 3656 |  | 3656 |  |  | 14/10/2026 | 17/10/2026 |  |  | 3656 |  | 3656
ADIDAS | 0903141059-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2521 | 23/10/2026 | 2521 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141059 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-11-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-11-11 | 16/11/2026 |  |  | 2521 |  | 2521 |  |  | 2026-07-11 | 2026-12-11 |  |  | 2521 |  | 2521
ADIDAS | 0903141111-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3286 | 23/10/2026 | 3286 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141111 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-03-11 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-11 | 2026-09-11 |  |  | 3286 |  | 3286 |  |  | 30/10/2026 | 2026-05-11 |  |  | 3286 |  | 3286
ADIDAS | 0903142132-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 250 | 2026-12-09 | 250 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142132 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 250 | 250 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 250 | 250
ADIDAS | 0903142255-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142255 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 22/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 3656 |  | 3656 |  |  | 19/10/2026 | 22/10/2026 |  |  | 3656 |  | 3656
ADIDAS | 0903142438-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142438 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 28/08/2026 | 24/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142507-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 100 | 26/09/2026 | 100 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142507 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 100 | 100 |  |  |  | 2026-05-09 | 2026-10-09 | 13/08/2026 | 13/08/2026 | 100 | 100
ADIDAS | 0903142516-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142516 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 21/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142526-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142526 LI2645 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 15/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/09/2026 | 23/09/2026 |  |  | 8900 |  | 8900 |  |  | 2026-11-09 | 19/09/2026 |  |  | 8900 |  | 8900
ADIDAS | 0903142537-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 24/09: ex-fty. Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142537 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 150 |  | 150 |  |  | 25/09/2026 | 29/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903142574-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142574 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903142580-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 2026-12-09 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142580 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 160 | 160 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 2026-04-09 | 160 | 160
ADIDAS | 0903142605-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142605 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-02-10 | 2026-02-09 | 2026-02-09 | 100 | 2 | 98
ADIDAS | 0903142631-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 2950 | 30/09/2026 | 2950 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 24/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142631 LI2647 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 26/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 2950 |  | 2950 |  |  | 23/09/2026 | 25/09/2026 |  |  | 2950 |  | 2950
ADIDAS | 0903142728-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 680 | 31/10/2026 | 680 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | (07/08/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903142728 LD0288 | 25/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 16/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 680 |  | 680 |  |  | 13/10/2026 | 14/10/2026 |  |  | 680 |  | 680 |  |  | 2026-10-10 | 2026-12-10 |  |  | 680 |  | 680
ADIDAS | 0903142768-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 1350 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142768 KB5959 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142831-1 KB5962 | WONDER CARGO S26 | 120D | S2608MR0900A | 1250 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142831 KB5962 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142841-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903142841 JD1877 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 25/09/2026 |  |  | 1759 |  | 1759 |  |  | 18/09/2026 | 22/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903142873-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 30/09/2026 | 1079 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142873 JD5302 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S FT CF PT |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 1079 |  | 1079 |  |  | 15/09/2026 | 16/09/2026 | 27/08/2026 | 15/09/2026 | 1079 | 1005 | 74 |  | 677
ADIDAS | 0903142903-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142903 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S FT FZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 400 |  | 400 |  |  | 14/09/2026 | 15/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903142926-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 399 | 30/09/2026 | 399 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142926 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 399 | 111 | 288 |  |  | 27/08/2026 | 15/09/2026 | 22/08/2026 | 2026-09-09 | 399 | 399
ADIDAS | 0903142998-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 718 | 30/09/2026 | 718 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516204 | EMBRO SUB PROCESS_V1 | 0903142998 JE6419 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-05-09 | 2026-08-09 | 718 | 718 |  |  |  | 31/08/2026 | 2026-04-09 | 15/08/2026 | 2026-07-09 | 718 | 718
ADIDAS | 0903143026-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 899 | 2026-02-09 | 899 | SA | SA26/06/2026 | G2D,G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903143026 GK8824 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 29/08/2026 | 2026-01-09 | 899 | 899 |  |  |  | 24/08/2026 | 28/08/2026 | 21/08/2026 | 31/08/2026 | 899 | 899
ADIDAS | 0903143086-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 719 | 30/09/2026 | 719 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143086 JE1309 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S WV SHO |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 719 |  | 719 |  |  | 15/09/2026 | 16/09/2026 |  |  | 719 |  | 719
ADIDAS | 0903143118-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903143118 JE6419 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 1318 | 1318 |  |  |  | 31/08/2026 | 2026-04-09 | 29/08/2026 | 31/08/2026 | 1318 | 1318
ADIDAS | 0903143145-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, PI Date 26-Jul, actual receives 17-Jul. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143145 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S WV SHO |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903143303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 600 | 23/09/2026 | 600 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 600 | 600 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 600 | 600
ADIDAS | 0903143351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143351 LI2669 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 800 | 800 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 800 | 800
ADIDAS | 0903143380-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 23/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143380 LI2646 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-03-09 | 21/09/2026 | 2026-04-09 | 15/09/2026 | 8900 | 2134 | 6766 |  | 138 | 31/08/2026 | 17/09/2026 | 15/08/2026 | 2026-08-09 | 8900 | 8886 | 14
ADIDAS | 0903143435-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1100 | 30/09/2026 | 1100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143435 LI2668 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-09 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-05-09 | 18/09/2026 | 2026-05-09 | 2026-08-09 | 1100 | 1085 | 15 |  |  | 2026-02-09 | 15/09/2026 | 19/08/2026 | 2026-03-09 | 1100 | 1091 | 9
ADIDAS | 0903143462-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3900 | 30/09/2026 | 3900 | SA | SA26/06/2026 | G1E,G1I,G1O | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143462 LI2670 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-09 | 25/09/2026 | 2026-03-09 | 2026-07-09 | 3900 | 2209 | 1691 |  |  | 29/08/2026 | 22/09/2026 | 24/08/2026 | 2026-10-09 | 3900 | 2354 | 1546
ADIDAS | 0903143489-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 5100 | 30/09/2026 | 5100 | SA | SA26/06/2026 | G1E,G1G,G1I | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143489 LI2671 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-09 | 19/09/2026 | 2026-07-09 | 15/09/2026 | 5100 | 634 | 4466 |  | 267 | 2026-03-09 | 16/09/2026 | 24/08/2026 | 14/09/2026 | 5100 | 5101 | -1 | 1
ADIDAS | 0903144181-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-02-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144181 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 28/08/2026 | 20/08/2026 | 2026-01-09 | 220 | 220
ADIDAS | 0903144303-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144303 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 200 | 195 | 5
ADIDAS | 0903144813-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 260 | 2026-02-09 | 260 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144813 LI2672 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 260 | 260 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-05-09 | 260 | 260
ADIDAS | 0903144953-1 LG9669 | BLACK | 120D | S2754WAS514C | 756 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903144953 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903145092-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 144 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903145092 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903145124-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 258 | 31/10/2026 | 258 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145124 LF0726 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 17/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 17/11/2026 | 19/11/2026 |  |  | 258 |  | 258 |  |  | 13/11/2026 | 16/11/2026 |  |  | 258 |  | 258
ADIDAS | 0903145175-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO SUB PROCESS_V1 | 0903145175 JE6414 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1319 |  | 1319 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1319 |  | 1319
ADIDAS | 0903145234-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 1050 | 2026-12-09 | 1050 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 12/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145234 IM0081 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | U FI LOGO PT |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050
ADIDAS | 0903145265-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 480 | 30/09/2026 | 480 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145265 JE6341 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 480 |  | 480 |  |  | 18/09/2026 | 21/09/2026 |  |  | 480 |  | 480
ADIDAS | 0903145293-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903145293 JE6419 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 2026-10-09 | 1318 | 1082 | 236 |  |  | 2026-04-09 | 2026-12-09 | 29/08/2026 | 2026-02-09 | 1318 | 1294 | 24
ADIDAS | 0903145318-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 499 | 30/09/2026 | 499 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145318 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 499 |  | 499 |  |  | 17/09/2026 | 19/09/2026 |  |  | 499 |  | 499
ADIDAS | 0903145343-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 451 | 2026-09-09 | 451 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145343 IM0081 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | U FI LOGO PT |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 451 | 451 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-07-09 | 451 | 451
ADIDAS | 0903145368-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 450 | 2026-09-09 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145368 IS4395 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 450 | 450
ADIDAS | 0903145380-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 15/10/2026 | 315 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145380 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 315 |  | 315 |  |  | 2026-02-10 | 2026-03-10 |  |  | 315 |  | 315
ADIDAS | 0903145392-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145392 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-05-10 |  |  | 330 |  | 330
ADIDAS | 0903145395-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 09/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145395 IS4395 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-09-09 | 1051 | 1051 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-03-09 | 1051 | 1051
ADIDAS | 0903145433-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 15/10/2026 | 450 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145433 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 450 |  | 450 |  |  | 2026-03-10 | 2026-05-10 |  |  | 450 |  | 450
ADIDAS | 0903145448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145448 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 420 |  | 420 |  |  | 2026-05-10 | 2026-07-10 |  |  | 420 |  | 420
ADIDAS | 0903145462-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145462 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 345 |  | 345 |  |  | 2026-05-10 | 2026-07-10 |  |  | 345 |  | 345
ADIDAS | 0903145473-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145473 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | M 3S CHELSEA B7 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 420 |  | 420 |  |  | 2026-07-10 | 2026-08-10 |  |  | 420 |  | 420
ADIDAS | 0903145504-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 960 | 30/09/2026 | 960 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145504 JD1877 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 21/09/2026 |  |  | 960 |  | 960 |  |  | 14/09/2026 | 17/09/2026 |  |  | 960 |  | 960
ADIDAS | 0903145534-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 401 | 30/09/2026 | 401 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145534 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S FT FZ HD |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 401 |  | 401 |  |  | 24/09/2026 | 25/09/2026 | 28/08/2026 | 2026-11-09 | 401 | 386 | 15
ADIDAS | 0903145568-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145568 JE6340 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 15/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903145571-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145571 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | M 3S CHELSEA B7 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 435 |  | 435 |  |  | 2026-07-10 | 2026-08-10 |  |  | 435 |  | 435
ADIDAS | 0903145609-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 23/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145609 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | M 3S CHELSEA B7 |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 330 |  | 330 |  |  | 27/10/2026 | 28/10/2026 |  |  | 330 |  | 330
ADIDAS | 0903145625-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 23/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145625 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | M 3S CHELSEA B7 |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903145627-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 30/09/2026 | 359 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145627 JE6340 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 359 |  | 359 |  |  | 16/09/2026 | 19/09/2026 |  |  | 359 |  | 359
ADIDAS | 0903145643-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 235 | 31/10/2026 | 235 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145643 LF0729 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 29/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 235 |  | 235 |  |  | 26/10/2026 | 28/10/2026 |  |  | 235 |  | 235
ADIDAS | 0903146197-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 30/09/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903146197 LC8884 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M RESORT T BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 128 |  | 128 |  |  | 15/09/2026 | 15/09/2026 | 28/07/2026 | 2026-11-08 | 128 | 99 | 29
ADIDAS | 0903146288-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 222 | 30/09/2026 | 222 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (07/08/2026) | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146288 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 222 |  | 222 |  |  | 18/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 222 | 220 | 2 |  | 220
ADIDAS | 0903146309-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Cargoport). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146309 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 24/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 150 |  | 150 |  |  | 21/09/2026 | 22/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903146335-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 402 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146335 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903146354-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 215 | 23/09/2026 | 215 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903146354 KX0126 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 16/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 215 |  | 215 |  |  | 2026-12-09 | 15/09/2026 | 2026-05-08 | 2026-12-08 | 215 | 205 | 10
ADIDAS | 0903146356-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 414 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146356 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903146377-1 KB5965 | BLACK | 120D | S2608MR0900A | 930 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146377 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146398-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Cargoport). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146398 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 174 |  | 174 |  |  | 21/10/2026 | 22/10/2026 |  |  | 174 |  | 174 |  |  | 15/10/2026 | 16/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146415-1 KB5960 | WHITE | 120D | S2608MR0900A | 360 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146415 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146436-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 120 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Cargoport). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650036 | HT+PAD SUB PROCESS_V3 | 0903146436 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146478-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Cargoport). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 650036 | HT+PAD SUB PROCESS_V3 | 0903146478 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903146484-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 308 | 15/10/2026 | 308 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146484 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 308 |  | 308 |  |  | 19/10/2026 | 20/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903146497-1 KE8424 | BLACK | 120D | S2608MR0906A | 438 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146497 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903146520-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 274 | 15/10/2026 | 274 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146520 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 274 |  | 274 |  |  | 24/10/2026 | 26/10/2026 |  |  | 274 |  | 274
ADIDAS | 0903146532-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146532 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 174 |  | 174 |  |  | 29/10/2026 | 30/10/2026 |  |  | 174 |  | 174 |  |  | 23/10/2026 | 24/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146599-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 895 | 15/10/2026 | 895 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903146599 KY5988 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 895 |  | 895 |  |  | 2026-10-10 | 2026-12-10 |  |  | 895 |  | 895 |  |  | 2026-05-10 | 2026-06-10 |  |  | 895 |  | 895
ADIDAS | 0903146631-1 KB5960 | WHITE | 120D | S2608MR0900A | 1601 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903146631 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146633-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 226 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903146633 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903146708-1 LG9669 | BLACK | 120D | S2754WAS514C | 235 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903146708 LG9669 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146738-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 126 | 30/09/2026 | 126 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903146738 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 126 |  | 126 |  |  | 18/09/2026 | 19/09/2026 |  |  | 126 |  | 126 |  |  | 17/09/2026 | 18/09/2026 |  |  | 126 |  | 126
ADIDAS | 0903146764-1 LG9669 | BLACK | 120D | S2754WAS514C | 333 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903146764 LG9669 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146791-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 15/10/2026 | 100 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 512108 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903146791 KX7715 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 24/09/2026 | 28/09/2026 |  |  | 100 |  | 100 |  |  | 21/09/2026 | 24/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903146836-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 174 | 30/09/2026 | 174 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Damco offline). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 688010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146836 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 24/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 174 |  | 174 |  |  | 21/09/2026 | 22/09/2026 | 26/08/2026 | 31/08/2026 | 174 | 151 | 23
ADIDAS | 0903146867-1 JZ7711 | BLACK | 120D | S2608MR0202 | 274 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146867 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146909-1 KB5960 | WHITE | 120D | S2608MR0900A | 796 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903146909 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146928-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 956 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903146928 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903146963-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 220 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146963 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903147001-1 KB5965 | BLACK | 120D | S2608MR0900A | 922 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147001 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903147020-1 KT4840 | ONIX | 90D | S2408MR1600 | 386 | 15/10/2026 | 386 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903147020 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 386 |  | 386 |  |  | 13/10/2026 | 14/10/2026 |  |  | 386 |  | 386 |  |  | 2026-12-10 | 13/10/2026 |  |  | 386 |  | 386
ADIDAS | 0903147025-1 KE6712 | BLACK | 105D | S2608MR0601A | 448 | 15/10/2026 | 448 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147025 KE6712 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 23/10/2026 | 24/10/2026 |  |  | 448 |  | 448 |  |  | 20/10/2026 | 21/10/2026 |  |  | 448 |  | 448 |  |  | 19/10/2026 | 20/10/2026 |  |  | 448 |  | 448
ADIDAS | 0903147045-1 JD0957 | BLACK | 60D | S25ORISW311 | 800 | 15/10/2026 | 800 | ID | ID26/06/2026 | G3J | SHORTS | G3 | ok | ok | T2 Fu Hsun, PI Date 29-Jul, actual receives 14-Aug. T2 Libolon, PI Date 29-Jul, actual receives 09-Jul. 960006 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903147045 JD0957 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIC SWIMSH 5IN |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 800 |  | 800 |  |  | 2026-06-10 | 2026-08-10 |  |  | 800 |  | 800
ADIDAS | 0903147053-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 382 | 15/10/2026 | 382 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147053 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 382 |  | 382 |  |  | 17/10/2026 | 20/10/2026 |  |  | 382 |  | 382 |  |  | 16/10/2026 | 19/10/2026 |  |  | 382 |  | 382
ADIDAS | 0903147074-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 304 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903147074 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903147100-1 KE8424 | BLACK | 120D | S2608MR0906A | 306 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147100 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903147122-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 820 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147122 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903147253-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147253 KD3911 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | RELEASED |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 881 |  | 881 |  |  | 2026-12-09 | 14/09/2026 | 13/09/2026 | 15/09/2026 | 881 | 874 | 7 |  | 50
ADIDAS | 0903147280-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1560 | 30/09/2026 | 1560 | SI | SI26/06/2026 | G3E | PANTS | G3 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903147280 HK7317 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | ESS SWTP |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1560 |  | 1560 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1560 |  | 1560
ADIDAS | 0903147309-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147309 JW7177 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 30/09/2026 | W 3S FT OH PT |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 1541 |  | 1541 |  |  | 26/09/2026 | 28/09/2026 | 2026-07-09 | 14/09/2026 | 1541 | 1340 | 201
ADIDAS | 0903147338-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903147338 HK7319 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | ESS SWTP |  | SS27 | 25/09/2026 | 2026-01-10 |  |  | 2641 |  | 2641 |  |  | 22/09/2026 | 28/09/2026 |  |  | 2641 |  | 2641
ADIDAS | 0903147369-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 599 | 2026-02-09 | 599 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147369 HL2270 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | IN RANGE |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 599 | 599 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 599 | 599
ADIDAS | 0903147489-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 597 | 2026-02-09 | 597 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147489 H57046 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 2026-01-09 | 26/08/2026 | 29/08/2026 | 597 | 597 |  |  |  | 20/08/2026 | 28/08/2026 | 22/08/2026 | 27/08/2026 | 597 | 597
ADIDAS | 0903147513-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903147513 KD3911 | 2026-10-08 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | RELEASED |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 881 |  | 881 |  |  | 14/09/2026 | 15/09/2026 | 13/09/2026 | 15/09/2026 | 881 | 866 | 15 |  | 141
ADIDAS | 0903147569-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 601 | 2026-02-09 | 601 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147569 GK8823 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 601 | 601 |  |  |  | 24/08/2026 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 601 | 601
ADIDAS | 0903147631-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3E | PANTS | G3 | (29/07/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903147631 HK7317 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-05-10 |  |  | 2860 |  | 2860 |  |  | 25/09/2026 | 2026-01-10 |  |  | 2860 |  | 2860
ADIDAS | 0903147665-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516442 | EMBRO SUB PROCESS_V1 | 0903147665 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1320 |  | 1320 |  |  | 15/09/2026 | 17/09/2026 | 2026-11-08 | 31/08/2026 | 1320 | 1320
ADIDAS | 0903147675-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 895 | 30/09/2026 | 895 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903147675 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 895 |  | 895 |  |  | 19/09/2026 | 21/09/2026 |  |  | 895 |  | 895 |  |  | 18/09/2026 | 19/09/2026 |  |  | 895 |  | 895
ADIDAS | 0903147765-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 900 | 30/09/2026 | 900 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147765 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 900 |  | 900 |  |  | 15/09/2026 | 17/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903147789-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 30/09/2026 | 720 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903147789 JE6414 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 720 |  | 720 |  |  | 2026-11-09 | 15/09/2026 | 29/08/2026 | 2026-01-09 | 720 | 634 | 86
ADIDAS | 0903147800-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 838 | 15/10/2026 | 838 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147800 KX7716 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 20/10/2026 | 23/10/2026 |  |  | 838 |  | 838 |  |  | 16/10/2026 | 20/10/2026 |  |  | 838 |  | 838
ADIDAS | 0903147835-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 675 | 15/10/2026 | 675 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516443 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147835 KX7716 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 2026-01-10 | 2026-07-10 |  |  | 675 |  | 675 |  |  | 28/09/2026 | 2026-03-10 |  |  | 675 |  | 675
ADIDAS | 0903147850-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903147850 JE6340 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 15/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903147881-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147881 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1319 |  | 1319 |  |  | 17/09/2026 | 21/09/2026 | 2026-11-08 | 2026-01-09 | 1319 | 493 | 826
ADIDAS | 0903147940-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 241 | 15/09/2026 | 241 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903147940 LE8193 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 241 | 241 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-07-09 | 241 | 241
ADIDAS | 0903147997-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 335 | 23/09/2026 | 335 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903147997 LC8884 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 16/09/2026 | M RESORT T BLACK |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 335 |  | 335 |  |  | 2026-12-09 | 15/09/2026 | 28/07/2026 | 2026-11-08 | 335 | 335
ADIDAS | 0903148037-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 1321 | 30/09/2026 | 1321 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148037 JE1309 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV SHO |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 1321 |  | 1321 |  |  | 16/09/2026 | 18/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903148050-1 KE8424 | BLACK | 120D | S2608MR0906A | 1085 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903148050 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903148066-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903148066 JE6338 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 30/09/2026 |  |  | 1760 |  | 1760 |  |  | 23/09/2026 | 26/09/2026 | 2026-03-09 | 2026-05-09 | 1760 | 486 | 1274
ADIDAS | 0903148083-1 LC6583 | GREY | 105D | S2750MTR051 | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 830009 | HT SUB PROCESS_V1 | 0903148083 LC6583 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D4T ESS T GREY |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 110 |  | 110 |  |  | 2026-03-10 | 2026-05-10 |  |  | 110 |  | 110 |  |  | 2026-02-10 | 2026-03-10 |  |  | 110 |  | 110
ADIDAS | 0903148089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 719 | 30/09/2026 | 719 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903148089 JE6417 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 719 |  | 719 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-08 | 2026-01-09 | 719 | 715 | 4
ADIDAS | 0903148210-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 15/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516471 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148210 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 300 | 300 |  |  | 37 | 2026-05-09 | 2026-11-09 | 26/08/2026 | 2026-11-09 | 300 | 300
ADIDAS | 0903148659-1 LF0727 | BLACK | 120D | S2754MAS510B | 143 | 31/10/2026 | 143 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148659 LF0727 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-11 | M SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 143 |  | 143 |  |  | 2026-05-11 | 2026-07-11 |  |  | 143 |  | 143
ADIDAS | 0903148669-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 150 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 826010 | HT+PAD SUB PROCESS_V3 | 0903148669 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148695-1 KE8424 | BLACK | 120D | S2608MR0906A | 146 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148695 KE8424 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903148707-1 LG9675 | BLACK | 120D | S2754WAS513C | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903148707 LG9675 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903148758-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 393 | 30/10/2026 | 393 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148758 LG9666 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-05-11 | W SL WV TT BLACK |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 393 |  | 393 |  |  | 2026-02-11 | 2026-05-11 |  |  | 393 |  | 393
ADIDAS | 0903148776-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 561 | 15/10/2026 | 561 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148776 KY5988 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 561 |  | 561 |  |  | 2026-09-10 | 2026-10-10 |  |  | 561 |  | 561 |  |  | 2026-03-10 | 2026-05-10 |  |  | 561 |  | 561
ADIDAS | 0903148797-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 603 | 30/09/2026 | 603 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903148797 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 21/09/2026 | 14/08/2026 | 2026-03-09 | 603 | 603 |  |  |  | 2026-11-08 | 18/09/2026 | 30/07/2026 | 2026-06-08 | 603 | 603 |  |  |  | 2026-10-08 | 17/09/2026 | 29/07/2026 | 13/08/2026 | 603 | 603
ADIDAS | 0903148818-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 318 | 23/09/2026 | 318 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148818 LE8181 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 318 |  | 318 |  |  | 15/09/2026 | 15/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903148821-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 443 | 15/09/2026 | 443 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903148821 LE8193 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-02-09 | 443 | 443
ADIDAS | 0903148878-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148878 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 15/10/2026 | W 3S FT OH PT |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 437 |  | 437 |  |  | 2026-12-10 | 13/10/2026 |  |  | 437 |  | 437
ADIDAS | 0903148893-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 312 | 23/09/2026 | 312 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148893 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 17/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 312 |  | 312 |  |  | 14/09/2026 | 14/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903148919-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 383 | 31/10/2026 | 383 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148919 LG9661 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-11-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-11-11 | 13/11/2026 |  |  | 383 |  | 383 |  |  | 2026-07-11 | 2026-10-11 |  |  | 383 |  | 383
ADIDAS | 0903148948-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 142 | 15/10/2026 | 142 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903148948 LD6542 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 142 |  | 142 |  |  | 13/10/2026 | 15/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903148963-1 LE8187 | BLACK | 105D | S2754MAS513 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148963 LE8187 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 174 |  | 174 |  |  | 20/10/2026 | 22/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903148974-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 948 | 2026-02-10 | 948 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903148974 LD0930 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 30/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 948 |  | 948 |  |  | 26/09/2026 | 28/09/2026 |  |  | 948 |  | 948 |  |  | 24/09/2026 | 25/09/2026 |  |  | 948 |  | 948
ADIDAS | 0903148990-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 455 | 15/10/2026 | 455 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148990 LF0718 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 455 |  | 455 |  |  | 2026-10-10 | 2026-12-10 |  |  | 455 |  | 455
ADIDAS | 0903148994-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903148994 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 13/10/2026 | M 3S FT TC PT |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 437 |  | 437 |  |  | 2026-09-10 | 2026-10-10 |  |  | 437 |  | 437
ADIDAS | 0903149007-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 101 | 30/09/2026 | 101 | SA | SA26/06/2026 | G2J | T-SHIRT | G2 | (28/08/2026) | ok | 23/09: ex-fty 838103 | PAD+HT SUB PROCESS_V3 | 0903149007 JG5832 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/09/2026 | SQUA133 JSY M BLACK/WHITE |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 101 |  | 101 |  |  | 23/09/2026 | 23/09/2026 |  |  | 101 |  | 101 |  |  | 22/09/2026 | 22/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903149019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Aug. T2 Libolon, PI Date 22-Jul, actual receives 25-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149019 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 |  |  | 1 |  | 1
ADIDAS | 0903149035-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1 | 30/10/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. Waiting fabric. DRC 0064-T2 Libolon, PI Date 08-Sep, ETD ?? T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149035 KZ3231 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 1 |  | 1 |  |  | 2026-09-10 | 2026-09-10 |  |  | 1 |  | 1
ADIDAS | 0903149036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 660 | 15/10/2026 | 660 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903149036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 26/10/2026 | 27/10/2026 |  |  | 660 |  | 660 |  |  | 22/10/2026 | 23/10/2026 |  |  | 660 |  | 660 |  |  | 16/10/2026 | 17/10/2026 |  |  | 660 |  | 660
ADIDAS | 0903149043-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149043 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 1 |  | 1 |  |  | 23/09/2026 | 25/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149056-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 1 | 30/09/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149056 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 1 |  | 1 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1 |  | 1
ADIDAS | 0903149084-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 712 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 659018 | HT+PAD SUB PROCESS_V3 | 0903149084 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903149090-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3H | PANTS | G3 | ok | (07/08/2026(3)) | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149090 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 | 2026-07-08 | 2026-07-08 | 1 | 1
ADIDAS | 0903149104-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149104 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1 |  | 1 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149132-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 387 | 29/09/2026 | 387 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149132 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 24/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 387 |  | 387 |  |  | 21/09/2026 | 23/09/2026 | 26/08/2026 | 2026-03-09 | 387 | 369 | 18
ADIDAS | 0903149247-1 KT4840 | ONIX | 90D | S2408MR1600 | 150 | 15/10/2026 | 150 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903149247 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 150 |  | 150 |  |  | 13/10/2026 | 14/10/2026 | 2026-12-09 | 2026-12-09 | 150 | 2 | 148 |  |  | 2026-12-10 | 13/10/2026 | 2026-05-09 | 2026-05-09 | 150 | 2 | 148
ADIDAS | 0903149255-1 KT4840 | ONIX | 90D | S2408MR1600 | 352 | 31/10/2026 | 352 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903149255 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 26/10/2026 |  |  | 352 |  | 352 |  |  | 21/10/2026 | 23/10/2026 |  |  | 352 |  | 352 |  |  | 20/10/2026 | 22/10/2026 |  |  | 352 |  | 352
ADIDAS | 0903149303-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149303 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149363-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 158 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149363 KR3066 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149419-1 KT4840 | ONIX | 90D | S2408MR1600 | 2315 | 23/09/2026 | 2315 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903149419 KT4840 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 2315 | 265 | 2050 |  | 265 | 2026-12-09 | 18/09/2026 | 2026-08-09 | 15/09/2026 | 2315 | 1961 | 354 |  | 15 | 2026-11-09 | 17/09/2026 | 2026-07-09 | 14/09/2026 | 2315 | 1961 | 354
ADIDAS | 0903149656-1 HK7319 | BLACK | 90D | F2225M403 | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149656 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 400 |  | 400 |  |  | 21/09/2026 | 22/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903149744-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149744 HK7319 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | ESS SWTP |  | SS27 | 2026-01-10 | 2026-07-10 |  |  | 2641 |  | 2641 |  |  | 28/09/2026 | 2026-03-10 | 15/09/2026 | 15/09/2026 | 2641 | 800 | 1841 |  | 800
ADIDAS | 0903149771-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 600 | 30/09/2026 | 600 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149771 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 600 |  | 600 |  |  | 21/09/2026 | 24/09/2026 |  |  | 600 |  | 600
ADIDAS | 0903149833-1 HZ0747 | BLACK | 90D | F2325M414 | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903149833 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 399 |  | 399 |  |  | 2026-12-09 | 14/09/2026 | 31/08/2026 | 2026-02-09 | 399 | 398 | 1
ADIDAS | 0903149866-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149866 HR8583 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | ESS SWTP |  | SS27 | 2026-07-10 | 13/10/2026 |  |  | 3300 |  | 3300 |  |  | 2026-03-10 | 2026-09-10 |  |  | 3300 |  | 3300
ADIDAS | 0903149894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 25/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149894 IB8686 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | ESS TEE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 2200 |  | 2200 |  |  | 2026-12-09 | 15/09/2026 | 2026-12-08 | 2026-12-09 | 2200 | 2187 | 13
ADIDAS | 0903149953-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903149953 IB8686 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | ESS TEE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 1200 |  | 1200 |  |  | 2026-11-09 | 2026-12-09 | 26/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903149971-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 820 | 15/10/2026 | 820 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903149971 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 820 |  | 820 |  |  | 27/10/2026 | 28/10/2026 |  |  | 820 |  | 820 |  |  | 26/10/2026 | 27/10/2026 |  |  | 820 |  | 820
ADIDAS | 0903149978-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149978 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | PL TEE |  | SS27 | 17/09/2026 | 22/09/2026 |  |  | 4543 |  | 4543 |  |  | 14/09/2026 | 18/09/2026 |  |  | 4543 |  | 4543
ADIDAS | 0903150021-1 KA0246 | BLACK | 90D | S2608WR0902 | 399 | 2026-07-10 | 399 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903150021 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 22/09/2026 | 24/09/2026 |  |  | 399 |  | 399 |  |  | 21/09/2026 | 23/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903150041-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 900 | 2026-02-09 | 900 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903150041 GK8821 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 900 | 900 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 2026-02-09 | 900 | 900
ADIDAS | 0903150045-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1980 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516415 | HT+PAD SUB PROCESS_V3 | 0903150045 KX3651 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0903150068-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150068 IB8686 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | ESS TEE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 2200 |  | 2200 |  |  | 15/09/2026 | 17/09/2026 | 2026-11-08 | 31/08/2026 | 2200 | 2200
ADIDAS | 0903150072-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 1200 | 2026-07-10 | 1200 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516260 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903150072 KY5988 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-10-10 | 13/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1200 |  | 1200 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1200 |  | 1200
ADIDAS | 0903150101-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 360 | 30/09/2026 | 360 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903150101 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 360 |  | 360 |  |  | 25/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 360 | 332 | 28
ADIDAS | 0903150103-1 HZ0747 | BLACK | 90D | F2325M414 | 2478 | 30/09/2026 | 2478 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903150103 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 2478 | 265 | 2213 |  | 265 | 2026-11-09 | 14/09/2026 | 2026-01-09 | 13/09/2026 | 2478 | 2472 | 6
ADIDAS | 0903150130-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1800 | 30/09/2026 | 1800 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903150130 HR8583 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | ESS SWTP |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1800 |  | 1800 |  |  | 17/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 1800 | 102 | 1698 |  | 102
ADIDAS | 0903150152-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 26/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150152 JE6341 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 881 |  | 881 |  |  | 21/09/2026 | 23/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150214-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | (08/08/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150214 JD1877 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1759 |  | 1759 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903150279-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 901 | 30/09/2026 | 901 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150279 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | W 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 901 |  | 901 |  |  | 25/09/2026 | 28/09/2026 | 28/08/2026 | 2026-11-09 | 901 | 862 | 39
ADIDAS | 0903150285-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 31/10/2026 |  | AN | AN26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPA SUB PROCESS_V3 | 0903150285 LG9669 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903150304-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150304 JE6338 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | M 3S FT FZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1760 |  | 1760 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903150319-1 LF0727 | BLACK | 120D | S2754MAS510B | 1245 | 31/10/2026 | 1245 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150319 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 16/11/2026 | M SL WV TT BLACK |  | SS27 | 16/11/2026 | 19/11/2026 |  |  | 1245 |  | 1245 |  |  | 2026-12-11 | 16/11/2026 |  |  | 1245 |  | 1245
ADIDAS | 0903150340-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150340 JE6341 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 881 |  | 881 |  |  | 17/09/2026 | 18/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150366-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 959 | 30/09/2026 | 959 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150366 JE6338 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 959 |  | 959 |  |  | 16/09/2026 | 19/09/2026 |  |  | 959 |  | 959
ADIDAS | 0903150392-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1321 | 30/09/2026 | 1321 | SI | SI26/06/2026 | G3J | SHORTS | G3 | (10/08/2026) | ok | 26/09: ex-fty. Waiting fabric. T2 Gistex, (3S) PI Date 10-Aug, ETD ?? T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150392 JE1309 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | W 3S WV SHO |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1321 |  | 1321 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903150418-1 KB5960 | WHITE | 120D | S2608MR0900A | 1040 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150418 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903150471-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 28/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150471 JE6417 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 1320 |  | 1320 |  |  | 19/09/2026 | 23/09/2026 | 2026-11-08 | 2026-01-09 | 1320 | 1320
ADIDAS | 0903150495-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150495 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 500 |  | 500 |  |  | 2026-12-09 | 14/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903150517-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 372 | 29/09/2026 | 372 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | ok | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150517 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 16/09/2026 |  |  | 372 |  | 372 |  |  | 2026-11-09 | 2026-12-09 |  |  | 372 |  | 372 |  |  | 2026-09-09 | 2026-10-09 |  |  | 372 |  | 372
ADIDAS | 0903150541-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1148 | 14/10/2026 | 1148 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150541 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-06-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 1148 |  | 1148 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1148 |  | 1148 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1148 |  | 1148
ADIDAS | 0903150606-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 850 | 30/10/2026 | 850 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150606 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 850 |  | 850 |  |  | 2026-03-10 | 2026-03-10 |  |  | 850 |  | 850 |  |  | 2026-01-10 | 2026-01-10 |  |  | 850 |  | 850
ADIDAS | 0903150629-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1235 | 14/10/2026 | 1235 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150629 LD0283 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-01-10 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 1235 |  | 1235 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1235 |  | 1235 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1235 |  | 1235
ADIDAS | 0903150630-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 648 | 15/09/2026 | 648 | SA | SA26/06/2026 | G2L,G2M | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903150630 LE8210 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 648 | 535 | 113 |  | 223 | 2026-09-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 648 | 561 | 87
ADIDAS | 0903150899-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 181 | 30/09/2026 | 181 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903150899 LC6339 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 181 |  | 181 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 181 | 157 | 24
ADIDAS | 0903150944-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 345 | 30/09/2026 | 345 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150944 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 345 |  | 345 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 345 | 335 | 10
ADIDAS | 0903150972-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 126 | 15/10/2026 | 126 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150972 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 126 |  | 126 |  |  | 20/10/2026 | 22/10/2026 |  |  | 126 |  | 126
ADIDAS | 0903150974-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 534 | 31/10/2026 | 534 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150974 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 534 |  | 534 |  |  | 13/10/2026 | 13/10/2026 | 2026-08-09 | 2026-09-09 | 534 | 467 | 67
ADIDAS | 0903151028-1 IS1413 | BLACK | 60D | S2425M405 | 378 | 2026-12-09 | 378 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903151028 IS1413 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 378 | 378 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-11-08 | 2026-03-09 | 378 | 378
ADIDAS | 0903151067-1 HK7319 | BLACK | 90D | F2225M403 | 378 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | 848016 | EMBRO+PPA SUB PROCESS_V3 | 0903151067 HK7319 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903151088-1 KC4947 | BLACK | 105D | S2608WR0216 | 566 | 15/10/2026 | 566 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903151088 KC4947 | 24/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA | 14/10/2026 | adi365 Astro W |  | SS27-TRAX | 14/10/2026 | 17/10/2026 |  |  | 566 |  | 566 |  |  | 2026-10-10 | 14/10/2026 |  |  | 566 |  | 566 |  |  | 2026-09-10 | 13/10/2026 |  |  | 566 |  | 566
ADIDAS | 0903151096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903151096 IZ0443 | 28/07/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-02-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903151127-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2C | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903151127 JE6419 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 25/09/2026 | 26/09/2026 | 18/08/2026 | 29/08/2026 | 540 | 540
ADIDAS | 0903151171-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151171 LC8884 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 100 |  | 100 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-08 | 2026-11-08 | 100 | 96 | 4
ADIDAS | 0903151195-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1684 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903151195 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903151218-1 JZ7766 | MEDIUM GREY HEATHER | 90D | S2608MR0901 | 112 | 31/10/2026 | 112 | AN | AN26/06/2026 | G1E | SHORTS | G1 |  |  | (NYK warehouse). Waiting fabric. T2 Formosa, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 07-Sep. 800005 | PAD+HT SUB PROCESS_V3 | 0903151218 JZ7766 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-07-11 | Run Ess Shor M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-07-11 | 2026-09-11 |  |  | 112 |  | 112 |  |  | 2026-04-11 | 2026-05-11 |  |  | 112 |  | 112 |  |  | 2026-03-11 | 2026-04-11 |  |  | 112 |  | 112
ADIDAS | 0903151219-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 327 | 15/10/2026 | 327 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903151219 LE5609 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/10/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 327 |  | 327 |  |  | 17/10/2026 | 19/10/2026 |  |  | 327 |  | 327 |  |  | 2026-12-10 | 13/10/2026 |  |  | 327 |  | 327
ADIDAS | 0903151248-1 LF0723 | BLACK | 105D | S2754MAS511B | 373 | 15/10/2026 | 373 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151248 LF0723 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 373 |  | 373 |  |  | 22/10/2026 | 24/10/2026 |  |  | 373 |  | 373
ADIDAS | 0903151275-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 991 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903151275 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903151295-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151295 KX0126 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-08-10 | 2026-08-10 | 2026-05-08 | 20/08/2026 | 100 | 94 | 6
ADIDAS | 0903151312-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 434 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903151312 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903151313-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151313 JN1958 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W 3S FT QZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 1540 |  | 1540 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151330-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 26/09: ex-fty 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151330 JN1958 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | W 3S FT QZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1540 |  | 1540 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151539-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151539 JN1958 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | W 3S FT QZ HD |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 840 | 674 | 166 |  |  | 2026-09-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 840 | 764 | 76 |  | 6
ADIDAS | 0903151579-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151579 JW7177 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | W 3S FT OH PT |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1541 |  | 1541 |  |  | 28/09/2026 | 30/09/2026 | 31/08/2026 | 2026-08-09 | 1541 | 1533 | 8
ADIDAS | 0903151624-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151624 JW7178 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | W 3S FT OH PT |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 1431 |  | 1431 |  |  | 2026-07-10 | 2026-09-10 | 2026-12-09 | 15/09/2026 | 1431 | 1355 | 76 |  | 160
ADIDAS | 0903151645-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 355 | 15/10/2026 | 355 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903151645 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 355 |  | 355 |  |  | 29/10/2026 | 30/10/2026 |  |  | 355 |  | 355 |  |  | 23/10/2026 | 24/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903152156-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1054 | 29/09/2026 | 1054 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152156 KX3650 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1054 |  | 1054 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1054 |  | 1054 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1054 |  | 1054
ADIDAS | 0903152165-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 752 | 30/09/2026 | 752 | SA | SA26/06/2026 | G2K,G2M | T-SHIRT | G2 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152165 LE8201 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 752 | 682 | 70 |  | 197 | 2026-02-09 | 2026-11-09 | 2026-03-09 | 13/09/2026 | 752 | 752
ADIDAS | 0903152177-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 370 | 29/09/2026 | 370 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152177 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 370 |  | 370 |  |  | 2026-12-09 | 14/09/2026 |  |  | 370 |  | 370 |  |  | 2026-10-09 | 2026-11-09 |  |  | 370 |  | 370
ADIDAS | 0903152204-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 4012 | 15/09/2026 | 4012 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152204 LE8202 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 4012 | 3905 | 107 |  | 289 | 2026-02-09 | 2026-11-09 | 21/08/2026 | 15/09/2026 | 4012 | 3890 | 122 |  | 46
ADIDAS | 0903152214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 756 | 29/09/2026 | 756 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152214 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 756 |  | 756 |  |  | 16/09/2026 | 17/09/2026 |  |  | 756 |  | 756 |  |  | 14/09/2026 | 15/09/2026 |  |  | 756 |  | 756
ADIDAS | 0903152235-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 351 | 15/09/2026 | 351 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152235 LE8208 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 351 | 351 |  |  | 127 | 2026-05-09 | 2026-11-09 | 2026-12-09 | 15/09/2026 | 351 | 348 | 3 |  | 10
ADIDAS | 0903152248-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 870 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152248 KY9384 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903152275-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 1600 | 30/09/2026 | 1600 | SI | SI26/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152275 LE8194 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 1600 | 1600 |  |  |  | 29/08/2026 | 2026-09-09 | 2026-03-09 | 2026-10-09 | 1600 | 1600
ADIDAS | 0903152279-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 875 | 15/09/2026 | 875 | AN | AN26/06/2026 | G3J,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152279 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-08-09 | 14/09/2026 | 875 | 875
ADIDAS | 0903152318-1 KE6712 | BLACK | 105D | S2608MR0601A | 1026 | 15/10/2026 | 1026 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 678002 | PAD+HT SUB PROCESS_V3 | 0903152318 KE6712 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 24/10/2026 | 28/10/2026 |  |  | 1026 |  | 1026 |  |  | 21/10/2026 | 24/10/2026 |  |  | 1026 |  | 1026 |  |  | 20/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903152321-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 4210 | 15/09/2026 | 4210 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152321 LE8193 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL H F JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 4210 | 4210 |  |  | 465 | 29/08/2026 | 2026-11-09 | 18/08/2026 | 14/09/2026 | 4210 | 4210
ADIDAS | 0903152349-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 533 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152349 HK7317 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152351-1 KE6899 | BLACK | 105D | S2608WR0601B | 661 | 15/10/2026 | 661 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903152351 KE6899 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 661 |  | 661 |  |  | 29/10/2026 | 31/10/2026 |  |  | 661 |  | 661 |  |  | 28/10/2026 | 30/10/2026 |  |  | 661 |  | 661
ADIDAS | 0903152378-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 731 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152378 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152382-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 828 | 29/09/2026 | 828 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152382 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 16/09/2026 | 16/09/2026 |  |  | 828 |  | 828 |  |  | 2026-12-09 | 2026-12-09 |  |  | 828 |  | 828 |  |  | 2026-10-09 | 2026-10-09 |  |  | 828 |  | 828
ADIDAS | 0903152402-1 KB5965 | BLACK | 120D | S2608MR0900A | 551 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152402 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152458-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 396 | 29/09/2026 | 396 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152458 LD0930 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 18/09/2026 | 18/09/2026 |  |  | 396 |  | 396 |  |  | 15/09/2026 | 15/09/2026 |  |  | 396 |  | 396 |  |  | 2026-12-09 | 2026-12-09 |  |  | 396 |  | 396
ADIDAS | 0903152475-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 568 | 31/10/2026 | 568 | AN | AN26/06/2026 | G1J | JACKET | G1 | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jul, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152475 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 17/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 17/11/2026 | 19/11/2026 |  |  | 568 |  | 568 |  |  | 13/11/2026 | 16/11/2026 |  |  | 568 |  | 568
ADIDAS | 0903152502-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 300 | 29/09/2026 | 300 | SA | SA26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152502 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/09/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 2026-10-09 | 2026-11-09 |  |  | 300 |  | 300
ADIDAS | 0903152519-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 897 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152519 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152532-1 LG9669 | BLACK | 120D | S2754WAS514C | 319 | 29/09/2026 | 319 | ID | ID26/06/2026 | G3C | SKIRT | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 12-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152532 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/09/2026 | W SL WV SK BLACK |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 25/09/2026 | 28/09/2026 | 29/08/2026 | 2026-02-09 | 319 | 236 | 83
ADIDAS | 0903152551-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 2026-09-09 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903152551 IS1413 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | IN RANGE |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 300 | 300 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-05-08 | 2026-03-09 | 300 | 300
ADIDAS | 0903152558-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 324 | 29/09/2026 | 324 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152558 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 324 |  | 324 |  |  | 15/09/2026 | 16/09/2026 |  |  | 324 |  | 324
ADIDAS | 0903152588-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 731 | 30/09/2026 | 731 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 21/09: ex-fty 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152588 HK7317 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 731 |  | 731 |  |  | 21/09/2026 | 24/09/2026 |  |  | 731 |  | 731
ADIDAS | 0903152621-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 285 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152621 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903152648-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152648 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 28/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152660-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152660 HR8583 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 3300 |  | 3300 |  |  | 21/09/2026 | 26/09/2026 |  |  | 3300 |  | 3300
ADIDAS | 0903152687-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 2112 | 15/10/2026 | 2112 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152687 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 20/10/2026 | 26/10/2026 |  |  | 2112 |  | 2112 |  |  | 16/10/2026 | 22/10/2026 |  |  | 2112 |  | 2112
ADIDAS | 0903152692-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152692 HK7317 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-02-10 |  |  | 2860 |  | 2860 |  |  | 24/09/2026 | 29/09/2026 |  |  | 2860 |  | 2860
ADIDAS | 0903152712-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 300 | 2026-07-10 | 300 | AN | AN26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152712 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 28/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152716-1 HK7319 | BLACK | 90D | F2225M403 | 1439 | 30/09/2026 | 1439 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 26/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903152716 HK7319 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | ESS SWTP |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 1439 |  | 1439 |  |  | 19/09/2026 | 23/09/2026 |  |  | 1439 |  | 1439
ADIDAS | 0903152733-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152733 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152759-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152759 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 330 |  | 330 |  |  | 2026-08-10 | 2026-09-10 |  |  | 330 |  | 330
ADIDAS | 0903152760-1 KB5960 | WHITE | 120D | S2608MR0900A | 430 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903152760 KB5960 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152773-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152773 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903152781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152781 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903152806-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 1128 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152806 KD3854 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152841-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152841 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903152843-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 750 | 30/09/2026 | 750 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | HT SUB PROCESS_V1 | 0903152843 HU1551 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 750 | 366 | 384 |  | 366 | 2026-12-09 | 15/09/2026 | 26/08/2026 | 14/09/2026 | 750 | 747 | 3 |  |  | 2026-11-09 | 14/09/2026 | 24/08/2026 | 14/09/2026 | 750 | 747 | 3
ADIDAS | 0903152870-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903152870 HR6286 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | U FI LOGO PT |  | SS27 | 28/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 1051 | 1051 |  |  |  | 24/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 1051 | 1051
ADIDAS | 0903152887-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 435 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903152887 KY9391 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152912-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 100 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903152912 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152983-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903152983 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | PL TEE |  | SS27 | 23/09/2026 | 29/09/2026 |  |  | 4543 |  | 4543 |  |  | 19/09/2026 | 25/09/2026 | 2026-12-09 | 15/09/2026 | 4543 | 3783 | 760 |  | 1189
ADIDAS | 0903153088-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 389 | 30/09/2026 | 389 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153088 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 389 |  | 389 |  |  | 2026-05-10 | 2026-06-10 |  |  | 389 |  | 389
ADIDAS | 0903153111-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 550 | 30/09/2026 | 550 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | ok | 23/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 28-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153111 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 550 |  | 550 |  |  | 30/09/2026 | 2026-02-10 | 28/08/2026 | 2026-08-09 | 550 | 538 | 12
ADIDAS | 0903153139-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 447 | 31/10/2026 | 447 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903153139 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-07-11 | 2026-11-11 |  |  | 447 |  | 447 |  |  | 2026-04-11 | 2026-07-11 |  |  | 447 |  | 447 |  |  | 31/10/2026 | 2026-04-11 |  |  | 447 |  | 447
ADIDAS | 0903153147-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153147 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 25/09/2026 | 26/09/2026 | 2026-01-08 | 2026-03-09 | 540 | 540
ADIDAS | 0903153178-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 576 | 30/09/2026 | 576 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153178 JE6414 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 576 |  | 576 |  |  | 2026-11-09 | 15/09/2026 | 2026-01-08 | 31/08/2026 | 576 | 555 | 21
ADIDAS | 0903153208-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 414 | 30/09/2026 | 414 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153208 LC6339 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 414 |  | 414 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 414 | 405 | 9
ADIDAS | 0903153249-1 LC6341 | BLACK | 90D | S27GMGFX130 | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153249 LC6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 468 |  | 468 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 14/09/2026 | 468 | 386 | 82
ADIDAS | 0903153273-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153273 JE0052 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | W 3S FT FZ HD |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 308 |  | 308 |  |  | 2026-11-09 | 14/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153303-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153303 JE6338 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 468 |  | 468 |  |  | 17/09/2026 | 19/09/2026 |  |  | 468 |  | 468
ADIDAS | 0903153333-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 504 | 30/09/2026 | 504 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153333 JE6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 504 |  | 504 |  |  | 21/09/2026 | 23/09/2026 |  |  | 504 |  | 504
ADIDAS | 0903153362-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 378 | 23/09/2026 | 378 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153362 JD5302 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 378 | 378 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 378 | 378
ADIDAS | 0903153392-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153392 JE0055 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | W 3S FT FZ HD |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 308 |  | 308 |  |  | 24/09/2026 | 25/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153425 JD1877 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 540 |  | 540 |  |  | 2026-12-09 | 14/09/2026 |  |  | 540 |  | 540
ADIDAS | 0903153431-1 KC4947 | BLACK | 105D | S2608WR0216 | 1524 | 15/10/2026 | 1524 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 823016 | PAD+HT SUB PROCESS_V3 | 0903153431 KC4947 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 17/10/2026 | adi365 Astro W |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 1524 |  | 1524 |  |  | 14/10/2026 | 17/10/2026 |  |  | 1524 |  | 1524 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1524 |  | 1524
ADIDAS | 0903153447-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153447 KA5089 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 2026-04-09 | 2026-12-09 | 266 | 266
ADIDAS | 0903153486-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153486 KA5090 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 26/08/2026 | 2026-12-09 | 266 | 266
ADIDAS | 0903153519-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 17 | 31/10/2026 | 17 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153519 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27-SPOMA | 17/11/2026 | 19/11/2026 |  |  | 17 |  | 17 |  |  | 13/11/2026 | 16/11/2026 |  |  | 17 |  | 17
ADIDAS | 0903153557-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 17 | 15/10/2026 | 17 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153557 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 28/10/2026 | 29/10/2026 |  |  | 17 |  | 17 |  |  | 24/10/2026 | 26/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903153563-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 844 | 2026-12-09 | 844 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 688010 | HT+PAD SUB PROCESS_V3 | 0903153563 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 844 | 844 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 844 | 844 |  |  |  | 28/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 844 | 844
ADIDAS | 0903153585-1 LG9675 | BLACK | 120D | S2754WAS513C | 17 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903153585 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27-SPOMA
ADIDAS | 0903153623-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 17 | 31/10/2026 | 17 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153623 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | W SL WV TT KHAKI THREE F26 |  | SS27-SPOMA | 2026-04-11 | 2026-07-11 |  |  | 17 |  | 17 |  |  | 31/10/2026 | 2026-04-11 |  |  | 17 |  | 17
ADIDAS | 0903153653-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 780 | 30/09/2026 | 780 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153653 JW7178 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | W 3S FT OH PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 780 |  | 780 |  |  | 2026-06-10 | 2026-07-10 | 2026-12-09 | 2026-12-09 | 780 | 698 | 82
ADIDAS | 0903153676-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153676 JW7177 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 840 |  | 840 |  |  | 18/09/2026 | 19/09/2026 | 31/08/2026 | 2026-09-09 | 840 | 798 | 42
ADIDAS | 0903153692-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903153692 KC8152 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 300 |  | 300 |  |  | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903153702-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153702 JW7178 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 13/10/2026 | W 3S FT OH PT |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 1431 |  | 1431 |  |  | 2026-09-10 | 2026-10-10 | 2026-01-09 | 2026-02-09 | 1431 | 1427 | 4
ADIDAS | 0903153713-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 207 | 2026-05-09 | 207 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 04/09: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153713 IN1172 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 207 | 207 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 23/07/2026 | 207 | 207 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 23/07/2026 | 207 | 207
ADIDAS | 0903153721-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 348 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903153721 KE6716 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903153722-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 355 | 15/10/2026 | 355 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153722 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 355 |  | 355 |  |  | 21/10/2026 | 22/10/2026 |  |  | 355 |  | 355 |  |  | 15/10/2026 | 16/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903153738-1 JZ5129 | CRYSTAL LINEN S26 | 120D | S2608WR0201 | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Best Pacific, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD 30-Jul, ETA-Kaha 14-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903153738 JZ5129 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W CRYSTAL LINEN S26 |  | SS27-TRAX
ADIDAS | 0903153739-1 KE8424 | BLACK | 120D | S2608MR0906A | 463 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153739 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903153754-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 201 | 2026-09-09 | 201 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153754 IN1157 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-04-09 | 201 | 201 |  |  |  | 27/08/2026 | 31/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201 |  |  |  | 26/08/2026 | 29/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201
ADIDAS | 0903153765-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 360 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153765 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903153773-1 KB5965 | BLACK | 120D | S2608MR0900A | 1585 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153773 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903153793-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1153 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153793 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903153803-1 KE8424 | BLACK | 120D | S2608MR0906A | 580 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153803 KE8424 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903153815-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1477 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153815 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903153840-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 540 | 30/10/2026 | 540 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903153840 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 14/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 540 |  | 540 |  |  | 2026-10-10 | 2026-12-10 |  |  | 540 |  | 540 |  |  | 2026-08-10 | 2026-09-10 |  |  | 540 |  | 540
ADIDAS | 0903153843-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 480 | 30/09/2026 | 480 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903153843 KD3911 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | RELEASED |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 480 |  | 480 |  |  | 14/09/2026 | 15/09/2026 | 31/08/2026 | 15/09/2026 | 480 | 435 | 45 |  | 30
ADIDAS | 0903153852-1 KE6899 | BLACK | 105D | S2608WR0601B | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903153852 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903153861-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 906 | 30/09/2026 | 906 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153861 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 906 |  | 906 |  |  | 25/09/2026 | 29/09/2026 | 29/08/2026 | 2026-03-09 | 906 | 360 | 546
ADIDAS | 0903153888-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 364 | 30/09/2026 | 364 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153888 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 364 |  | 364 |  |  | 23/09/2026 | 25/09/2026 | 31/08/2026 | 2026-03-09 | 364 | 255 | 109
ADIDAS | 0903153890-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 1504 | 15/10/2026 | 1504 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153890 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-03-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-03-11 | 2026-05-11 |  |  | 1504 |  | 1504 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1504 |  | 1504 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1504 |  | 1504
ADIDAS | 0903153893-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 481 | 15/10/2026 | 481 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 650010 | PAD+HT SUB PROCESS_V3 | 0903153893 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 481 |  | 481 |  |  | 14/10/2026 | 17/10/2026 |  |  | 481 |  | 481 |  |  | 13/10/2026 | 16/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903153906-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153906 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S FT QZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 399 |  | 399 |  |  | 14/09/2026 | 15/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903153959-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 609 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153959 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903153995-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 401 | 31/10/2026 | 401 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153995 LD0285 | 25/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 401 |  | 401 |  |  | 2026-03-10 | 2026-05-10 |  |  | 401 |  | 401 |  |  | 2026-01-10 | 2026-02-10 |  |  | 401 |  | 401
ADIDAS | 0903154027-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 23/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154027 JE0052 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W 3S FT FZ HD |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 400 |  | 400 |  |  | 2026-11-09 | 14/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903154028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 393 | 30/09/2026 | 393 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154028 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 24/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 393 |  | 393 |  |  | 21/09/2026 | 22/09/2026 | 26/08/2026 | 2026-12-09 | 393 | 324 | 69
ADIDAS | 0903154066-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 1951 | 15/10/2026 | 1951 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903154066 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 26/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 26/10/2026 | 29/10/2026 |  |  | 1951 |  | 1951 |  |  | 22/10/2026 | 26/10/2026 |  |  | 1951 |  | 1951 |  |  | 16/10/2026 | 20/10/2026 |  |  | 1951 |  | 1951
ADIDAS | 0903154077-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154077 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 435 |  | 435 |  |  | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435
ADIDAS | 0903154087-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 510 | 15/10/2026 | 510 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154087 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 510 |  | 510 |  |  | 2026-12-10 | 13/10/2026 |  |  | 510 |  | 510
ADIDAS | 0903154119-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154119 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 15/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903154124-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 533 | 23/09/2026 | 533 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154124 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 533 | 489 | 44 |  | 35 | 2026-09-09 | 2026-11-09 | 2026-11-09 | 13/09/2026 | 533 | 516 | 17
ADIDAS | 0903154136-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154136 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W 3S FT OH PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 399 |  | 399 |  |  | 2026-06-10 | 2026-07-10 | 2026-01-09 | 2026-01-09 | 399 | 351 | 48
ADIDAS | 0903154672-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154672 JE0055 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 29/09/2026 | W 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903154696-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 68 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903154696 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903154711-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 1265 | 30/09/2026 | 1265 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154711 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 15/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 1265 | 257 | 1008 |  | 257 | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 1265 | 1263 | 2 |  | 332
ADIDAS | 0903154728-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 58 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903154728 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903154744-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA26/06/2026 | G1G,G1I,G1O,G1Q | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154744 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | LFC 3 F JSY SE |  | SS27-FJ | 31/08/2026 | 15/09/2026 | 31/08/2026 | 15/09/2026 | 15000 | 15000 |  |  | 125 | 27/08/2026 | 2026-11-09 | 21/08/2026 | 14/09/2026 | 15000 | 14760 | 240
ADIDAS | 0903154754-1 KB5965 | BLACK | 120D | S2608MR0900A | 270 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903154754 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903154788-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 2110 | 2026-12-09 | 2110 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 12/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154788 LE8201 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 2026-12-09 | 2026-07-09 | 2026-12-09 | 2110 | 2110 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-03-09 | 14/09/2026 | 2110 | 2110
ADIDAS | 0903154833-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 6345 | 15/09/2026 | 6345 | SA | SA26/06/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154833 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 6345 | 6345 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-04-09 | 15/09/2026 | 6345 | 6283 | 62 |  | 56
ADIDAS | 0903154839-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 924 | 15/10/2026 | 924 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903154839 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 27/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 924 |  | 924 |  |  | 23/10/2026 | 24/10/2026 |  |  | 924 |  | 924 |  |  | 17/10/2026 | 19/10/2026 |  |  | 924 |  | 924
ADIDAS | 0903154867-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3701 | 15/09/2026 | 3701 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154867 LE8208 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3701 | 3701 |  |  | 32 | 2026-05-09 | 2026-11-09 | 2026-07-09 | 15/09/2026 | 3701 | 3701 |  |  | 14
ADIDAS | 0903154898-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 760 | 15/09/2026 | 760 | SA | SA26/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154898 LE8210 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 760 | 760 |  |  | 26 | 2026-02-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 760 | 760
ADIDAS | 0903154925-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 200 | 2026-12-09 | 200 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903154925 LE8193 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-02-09 | 2026-10-09 | 200 | 200 |  |  |  | 27/08/2026 | 2026-07-09 | 21/08/2026 | 2026-10-09 | 200 | 200
ADIDAS | 0903154942-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 313 | 30/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903154942 KX3654 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903154950-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 1096 | 2026-12-09 | 1096 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903154950 LE8193 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1096 | 1096 |  |  |  | 27/08/2026 | 2026-07-09 | 20/08/2026 | 2026-10-09 | 1096 | 1096
ADIDAS | 0903154953-1 KA0235 | BLACK | 90D | S2608WR0901 | 1036 | 2026-07-10 | 1036 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 28-Aug. 516276 | PAD+HT SUB PROCESS_V3 | 0903154953 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-01-10 | 2026-05-10 |  |  | 1036 |  | 1036 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1036 |  | 1036 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903154980-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 14142 | 2026-12-09 | 14142 | SA | SA26/06/2026 | G1I,G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 12/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903154980 LE8193 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-12-09 | 2026-02-09 | 2026-12-09 | 14142 | 14142 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-11-09 | 14142 | 14142
ADIDAS | 0903155169-1 KB5960 | WHITE | 120D | S2608MR0900A | 2500 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903155169 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155196-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G3E | PANTS | G3 | ok | ok | 834012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155196 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903155209-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 834012 | HT+PAD SUB PROCESS_V3 | 0903155209 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155389-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 380 | 15/09/2026 | 380 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155389 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-10-09 | 380 | 380 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 380 | 380
ADIDAS | 0903155422-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1482 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903155422 KX3654 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155457-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1114 | 30/09/2026 | 1114 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 25/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 678002 | PRINT L2+HT SUB PROCESS_V3 | 0903155457 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 1114 |  | 1114 |  |  | 21/09/2026 | 22/09/2026 |  |  | 1114 |  | 1114 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1114 |  | 1114
ADIDAS | 0903155494-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 14 | 15/10/2026 | 14 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155494 LE8187 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 14 |  | 14 |  |  | 20/10/2026 | 20/10/2026 |  |  | 14 |  | 14
ADIDAS | 0903155496-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 407 | 30/09/2026 | 407 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155496 LG9660 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 407 |  | 407 |  |  | 2026-11-09 | 2026-12-09 |  |  | 407 |  | 407
ADIDAS | 0903155525-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 24 | 15/10/2026 | 24 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155525 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 24 |  | 24 |  |  | 24/10/2026 | 26/10/2026 |  |  | 24 |  | 24
ADIDAS | 0903155581-1 KB5960 | WHITE | 120D | S2608MR0900A | 3741 | 29/09/2026 | 3741 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155581 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee M |  | SS27-TI | 16/09/2026 | 19/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-12-09 | 16/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-10-09 | 14/09/2026 |  |  | 3741 |  | 3741
ADIDAS | 0903155586-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903155586 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903155606-1 KB5965 | BLACK | 120D | S2608MR0900A | 989 | 29/09/2026 | 989 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155606 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/09/2026 | Run Ess Tee M |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 989 |  | 989 |  |  | 19/09/2026 | 21/09/2026 |  |  | 989 |  | 989 |  |  | 17/09/2026 | 18/09/2026 |  |  | 989 |  | 989
ADIDAS | 0903155635-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 467 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Airowes). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650034 | HT+PAD SUB PROCESS_V3 | 0903155635 KB5961 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155643-1 KB5965 | BLACK | 120D | S2608MR0900A | 5978 | 29/09/2026 | 5978 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155643 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | Run Ess Tee M |  | SS27-TI | 18/09/2026 | 23/09/2026 |  |  | 5978 |  | 5978 |  |  | 15/09/2026 | 19/09/2026 |  |  | 5978 |  | 5978 |  |  | 2026-12-09 | 17/09/2026 |  |  | 5978 |  | 5978
ADIDAS | 0903155770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 558 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903155848-1 KB5965 | BLACK | 120D | S2608MR0900A | 985 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155848 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155908-1 KB5960 | WHITE | 120D | S2608MR0900A | 460 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155908 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155916-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155916 KW9039 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 24/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 224 |  | 224 |  |  | 21/09/2026 | 22/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903155939-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 908 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 684009 | HT+PAD SUB PROCESS_V3 | 0903155939 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155960-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903155960 JD1877 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903155978-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 1218 | 2026-09-09 | 1218 | ID | ID26/06/2026 | G2S | SHORTS | G2 | ok | ok | 08/09: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155978 KY7184 | 2026-11-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-09 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 2026-01-09 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1218 | 1218 |  |  |  | 28/08/2026 | 2026-04-09 | 31/08/2026 | 2026-08-09 | 1218 | 1218
ADIDAS | 0903155986-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903155986 KY3734 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 29/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903156009-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903156009 JE6341 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903156065-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 344 | 30/09/2026 | 344 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO SUB PROCESS_V1 | 0903156065 JD1881 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | M 3S FT TC PT |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 344 |  | 344 |  |  | 2026-05-10 | 2026-05-10 | 15/09/2026 | 15/09/2026 | 344 | 341 | 3 |  | 341
ADIDAS | 0903156091-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 126 | 31/10/2026 | 126 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156091 LG9666 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-05-11 | W SL WV TT BLACK |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 126 |  | 126 |  |  | 2026-02-11 | 2026-05-11 |  |  | 126 |  | 126
ADIDAS | 0903156120-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 131 | 31/10/2026 | 131 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156120 LG9664 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-10-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-11 | 2026-12-11 |  |  | 131 |  | 131 |  |  | 2026-06-11 | 2026-09-11 |  |  | 131 |  | 131
ADIDAS | 0903156157-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 401 | 30/09/2026 | 401 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156157 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 401 |  | 401 |  |  | 18/09/2026 | 19/09/2026 | 14/08/2026 | 2026-08-09 | 401 | 394 | 7
ADIDAS | 0903156162-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156162 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 435 |  | 435 |  |  | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435
ADIDAS | 0903156174-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 938 | 2026-07-10 | 938 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156174 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 938 |  | 938 |  |  | 2026-07-10 | 2026-08-10 |  |  | 938 |  | 938
ADIDAS | 0903156181-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 375 | 15/10/2026 | 375 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156181 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 375 |  | 375 |  |  | 2026-12-10 | 13/10/2026 |  |  | 375 |  | 375
ADIDAS | 0903156184-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 23/09/2026 | 610 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156184 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 610 | 509 | 101 |  | 224 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 610 | 610
ADIDAS | 0903156224-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1251 | 2026-07-10 | 1251 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156224 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1251 |  | 1251 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1251 |  | 1251
ADIDAS | 0903156225-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 360 | 15/10/2026 | 360 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156225 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 360 |  | 360 |  |  | 13/10/2026 | 14/10/2026 |  |  | 360 |  | 360
ADIDAS | 0903156247-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156247 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 345 |  | 345 |  |  | 13/10/2026 | 14/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156282-1 KA4331 | BLACK | 90D | S2608MR0902 | 399 | 2026-07-10 | 399 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903156282 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 22/09/2026 | 24/09/2026 |  |  | 399 |  | 399 |  |  | 21/09/2026 | 23/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903156297-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156297 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 345 |  | 345 |  |  | 14/10/2026 | 16/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156313-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 525 | 15/10/2026 | 525 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156313 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 525 |  | 525 |  |  | 14/10/2026 | 16/10/2026 |  |  | 525 |  | 525
ADIDAS | 0903156320-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1051 | 30/09/2026 | 1051 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156320 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1051 |  | 1051 |  |  | 24/09/2026 | 26/09/2026 | 2026-11-09 | 2026-12-09 | 1051 | 822 | 229
ADIDAS | 0903156341-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 624 | 30/09/2026 | 624 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156341 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 624 |  | 624 |  |  | 23/09/2026 | 24/09/2026 | 2026-10-09 | 2026-12-09 | 624 | 623 | 1
ADIDAS | 0903156375-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 349 | 30/09/2026 | 349 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156375 KW2924 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 349 |  | 349 |  |  | 16/09/2026 | 18/09/2026 |  |  | 349 |  | 349
ADIDAS | 0903156407-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 741 | 30/09/2026 | 741 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156407 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 16/09/2026 | 16/09/2026 |  |  | 741 |  | 741 |  |  | 2026-12-09 | 2026-12-09 |  |  | 741 |  | 741
ADIDAS | 0903156431-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 1249 | 30/09/2026 | 1249 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156431 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 17/09/2026 | 18/09/2026 |  |  | 1249 |  | 1249 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1249 |  | 1249
ADIDAS | 0903156456-1 LC7300 | WHITE | 90D | S2725M926A | 207 | 23/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903156456 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903156487-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156487 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 110 |  | 110 |  |  | 30/09/2026 | 30/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903156511-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903156511 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 26/09/2026 | 2026-01-09 | 2026-01-09 | 100 | 100
ADIDAS | 0903156518-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 122 | 2026-07-10 | 122 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156518 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 122 |  | 122 |  |  | 24/09/2026 | 24/09/2026 |  |  | 122 |  | 122
ADIDAS | 0903156531-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903156531 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300
ADIDAS | 0903156547-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 800 | 15/10/2026 | 800 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903156547 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 800 |  | 800 |  |  | 26/10/2026 | 27/10/2026 |  |  | 800 |  | 800 |  |  | 24/10/2026 | 26/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903156549-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 198 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156549 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX
ADIDAS | 0903156595-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 150 | 30/09/2026 | 150 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156595 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | W 3S FT OH PT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 150 |  | 150 |  |  | 2026-05-10 | 2026-06-10 | 20/08/2026 | 28/08/2026 | 150 | 140 | 10
ADIDAS | 0903156599-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 300 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156599 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX
ADIDAS | 0903156613-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 540 | 15/10/2026 | 540 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Mexico). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903156613 KE6716 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 540 |  | 540 |  |  | 14/10/2026 | 17/10/2026 |  |  | 540 |  | 540 |  |  | 13/10/2026 | 16/10/2026 |  |  | 540 |  | 540
ADIDAS | 0903156885-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 416 | 30/09/2026 | 416 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Airowes). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156885 KV7863 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 25/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 416 |  | 416 |  |  | 22/09/2026 | 23/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903157062-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 124 | 15/10/2026 | 124 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157062 KU8797 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 124 |  | 124 |  |  | 2026-01-10 | 2026-01-10 |  |  | 124 |  | 124
ADIDAS | 0903157093-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 148 | 15/10/2026 | 148 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157093 KW8934 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 148 |  | 148 |  |  | 30/09/2026 | 30/09/2026 |  |  | 148 |  | 148
ADIDAS | 0903157098-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903157098 KX0126 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-10 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 128 |  | 128 |  |  | 2026-08-10 | 2026-08-10 | 2026-10-08 | 2026-11-08 | 128 | 84 | 44
ADIDAS | 0903157127-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 273 | 30/09/2026 | 273 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (04/08/2026) | 29/09: ex-fty (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157127 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 22/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 273 |  | 273 |  |  | 18/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 273 | 171 | 102 |  | 171
ADIDAS | 0903157138-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 106 | 23/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903157138 LC8943 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903157647-1 KE8424 | BLACK | 120D | S2608MR0906A | 890 | 2026-02-10 | 890 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903157647 KE8424 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 890 |  | 890 |  |  | 28/09/2026 | 29/09/2026 |  |  | 890 |  | 890 |  |  | 25/09/2026 | 26/09/2026 |  |  | 890 |  | 890
ADIDAS | 0903157666-1 KB5965 | BLACK | 120D | S2608MR0900A | 1085 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157666 KB5965 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157667-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 1500 | 2026-12-09 | 1500 | SA | SA26/06/2026 | G2Q,G2S,G2T | SHORTS | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 678002 | PRINT L1 SUB PROCESS_V3 | 0903157667 JC9346 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-09 | M LIN SJ SHO |  | SS27 | 2026-02-09 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1500 | 1500 |  |  |  | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-10-09 | 1500 | 1500
ADIDAS | 0903157694-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 909 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903157694 KE8420 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903157699-1 KB5960 | WHITE | 120D | S2608MR0900A | 191 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157699 KB5960 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157718-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 850 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903157718 KF5311 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157733-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 198 | 15/10/2026 | 198 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903157733 KD0738 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 198 |  | 198 |  |  | 21/10/2026 | 22/10/2026 |  |  | 198 |  | 198 |  |  | 15/10/2026 | 16/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903157738-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 306 | 23/09/2026 | 306 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157738 JD5302 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 306 | 306 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 27/08/2026 | 306 | 306
ADIDAS | 0903157739-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1210 | 23/10/2026 | 1210 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157739 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 1210 |  | 1210 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903157745-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | SHORTS | G3 | ok | ok | 23/09: ex-fty. T2 Gistex, PI Date 10-Aug, actual receives 22-Aug. 1st Art (TC 10 pcs) 678002 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0903157745 JE9016 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-06-10 | M LIN CHELSEA |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1500 |  | 1500 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1500 |  | 1500
ADIDAS | 0903157766-1 KE6899 | BLACK | 105D | S2608WR0601B | 120 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Airowes). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903157766 KE6899 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903157768-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157768 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 303 |  | 303 |  |  | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903157787-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 546 | 30/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT+PAD SUB PROCESS_V3 | 0903157787 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903157799-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157799 KF5311 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157804-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 118 | 30/09/2026 | 118 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903157804 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 118 |  | 118 |  |  | 17/09/2026 | 21/09/2026 | 31/08/2026 | 2026-05-09 | 118 | 104 | 14
ADIDAS | 0903157810-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157810 JE0052 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903157899-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 108 | 15/10/2026 | 108 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | (Airowes). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157899 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 108 |  | 108 |  |  | 20/10/2026 | 20/10/2026 |  |  | 108 |  | 108
ADIDAS | 0903157900-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 961 | 31/10/2026 | 961 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157900 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 961 |  | 961 |  |  | 2026-12-11 | 14/11/2026 |  |  | 961 |  | 961
ADIDAS | 0903157925-1 LG9669 | BLACK | 120D | S2754WAS514C | 100 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric (Airowes). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903157925 LG9669 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903157926-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 1091 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 60000 | PRINT L3+PPA SUB PROCESS_V3 | 0903157926 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903157953-1 KE8424 | BLACK | 120D | S2608MR0906A | 489 | 29/09/2026 | 489 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903157953 KE8424 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess LS M BLACK |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 489 |  | 489 |  |  | 14/09/2026 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 489 | 417 | 72 |  | 171 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 15/09/2026 | 489 | 432 | 57 |  | 4
ADIDAS | 0903158029-1 KE6712 | BLACK | 105D | S2608MR0601A | 102 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric (Airowes). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903158029 KE6712 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 SHORT M BLACK |  | SS27-TRAX
ADIDAS | 0903158101-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 266 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158101 KX3655 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 379 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158133 KX3654 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903158148-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 162 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158148 LG9673 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158151-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 436 | 23/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158151 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B SJ LF T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903158174-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 142 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903158174 KE8420 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903158195-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 160 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903158195 KF5311 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903158219-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 168 | 23/10/2026 | 168 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158219 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/10/2026 | 23/10/2026 |  |  | 168 |  | 168 |  |  | 20/10/2026 | 20/10/2026 |  |  | 168 |  | 168
ADIDAS | 0903158261-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903158261 JG8639 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 194 | 106 |  | 194 | 2026-11-09 | 2026-12-09 | 2026-03-08 | 24/08/2026 | 300 | 300
ADIDAS | 0903158265-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 11222 | 30/09/2026 | 11222 | AT | AT26/06/2026 | G2C | T-SHIRT | G2 | ok | (30/07/2026) | 25/09: ex-fty 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903158265 KA5089 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | MINI EMB T |  | SS27 | 21/09/2026 | 29/09/2026 |  |  | 11222 |  | 11222 |  |  | 17/09/2026 | 25/09/2026 | 2026-11-09 | 2026-11-09 | 11222 | 123 | 11099 |  |  | 15/09/2026 | 23/09/2026 | 2026-07-09 | 14/09/2026 | 11222 | 142 | 11080
ADIDAS | 0903158287-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 624 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158287 LG9672 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903158297-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 482 | 15/10/2026 | 482 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158297 JE0052 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | W 3S FT FZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 482 |  | 482 |  |  | 27/10/2026 | 28/10/2026 |  |  | 482 |  | 482
ADIDAS | 0903158314-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 492 | 31/10/2026 | 492 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158314 LC6790 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-07-11 | 2026-11-11 |  |  | 492 |  | 492 |  |  | 2026-04-11 | 2026-07-11 |  |  | 492 |  | 492 |  |  | 31/10/2026 | 2026-04-11 |  |  | 492 |  | 492
ADIDAS | 0903158394-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 571 | 31/10/2026 | 571 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903158394 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 571 |  | 571 |  |  | 2026-10-10 | 2026-12-10 |  |  | 571 |  | 571 |  |  | 2026-08-10 | 2026-09-10 |  |  | 571 |  | 571
ADIDAS | 0903158432-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 2411 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158432 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903158445-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 900 | 31/10/2026 | 900 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158445 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 23/11/2026 | 26/11/2026 |  |  | 900 |  | 900 |  |  | 19/11/2026 | 23/11/2026 |  |  | 900 |  | 900
ADIDAS | 0903158467-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 347 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903158467 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903158492-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 332 | 15/10/2026 | 332 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158492 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 332 |  | 332 |  |  | 20/10/2026 | 22/10/2026 |  |  | 332 |  | 332
ADIDAS | 0903158495-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158495 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-08-10 | 28/10/2026 |  |  | 101 |  | 101 |  |  | 2026-05-10 | 24/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903158556-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1004 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158556 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903158646-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 507 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903158646 LD0930 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158663-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 107 | 2026-07-10 | 107 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158663 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 107 |  | 107 |  |  | 19/09/2026 | 21/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903158671-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 319 | 31/10/2026 | 319 | SA | SA26/06/2026 | G1N | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158671 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 319 |  | 319 |  |  | 2026-07-11 | 2026-10-11 |  |  | 319 |  | 319 |  |  | 2026-04-11 | 2026-06-11 |  |  | 319 |  | 319
ADIDAS | 0903158691-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 118 | 2026-07-10 | 118 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158691 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 26/09/2026 | 26/09/2026 |  |  | 118 |  | 118 |  |  | 23/09/2026 | 23/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903158714-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 300 | 29/09/2026 | 300 | AN | AN26/06/2026 | G2R | SHORTS | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158714 LG9660 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 |  |  | 300 |  | 300
ADIDAS | 0903158739-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 332 | 15/10/2026 | 332 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158739 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 332 |  | 332 |  |  | 2026-12-10 | 13/10/2026 |  |  | 332 |  | 332
ADIDAS | 0903158761-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 239 | 23/09/2026 | 239 | SA | SA26/06/2026 | G3C | PANTS | G3 | (08/08/2026(13)) |  | 18/09: ex-fty 806020 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158761 JW7177 | 2026-10-09 | KAHATEX CIJERAH | HONGKONG | SEA | 28/07/2026 | W 3S FT OH PT |  | SS27 | 28/07/2026 | 2026-04-08 | 29/07/2026 | 29/07/2026 | 239 | 239 |  |  |  | 23/07/2026 | 30/07/2026 | 28/07/2026 | 29/07/2026 | 239 | 239
ADIDAS | 0903158798-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 229 | 15/10/2026 | 229 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158798 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 229 |  | 229 |  |  | 2026-12-10 | 13/10/2026 |  |  | 229 |  | 229
ADIDAS | 0903158825-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 451 | 15/10/2026 | 451 | SA | SA26/06/2026 | G3B | PANTS | G3 | (28/08/2026) | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158825 LE8181 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 451 |  | 451 |  |  | 13/10/2026 | 14/10/2026 |  |  | 451 |  | 451
ADIDAS | 0903158829-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | (17/07/2026) | 25/09: ex-fty 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158829 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | DICE TEE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 415 |  | 415 |  |  | 16/09/2026 | 17/09/2026 |  |  | 415 |  | 415 |  |  | 14/09/2026 | 15/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903158854-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 107 | 31/10/2026 | 107 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158854 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PDX HBR TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 107 |  | 107 |  |  | 17/09/2026 | 18/09/2026 | 15/08/2026 | 26/08/2026 | 107 | 107
ADIDAS | 0903158880-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158880 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | DICE TEE |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 311 |  | 311 |  |  | 20/10/2026 | 20/10/2026 |  |  | 311 |  | 311 |  |  | 17/10/2026 | 17/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903158907-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 245 | 30/09/2026 | 245 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158907 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PDX HBR TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 245 |  | 245 |  |  | 17/09/2026 | 18/09/2026 | 2026-11-08 | 2026-11-08 | 245 | 244 | 1
ADIDAS | 0903158935-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158935 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PIZZA TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 415 |  | 415 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 19/08/2026 | 415 | 414 | 1
ADIDAS | 0903158955-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 187 | 30/09/2026 | 187 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158955 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PDX HBR TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 187 |  | 187 |  |  | 17/09/2026 | 18/09/2026 | 2026-11-08 | 15/08/2026 | 187 | 187
ADIDAS | 0903158980-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 1203 | 30/09/2026 | 1203 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158980 KS2152 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | LA PALMS TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 1203 |  | 1203 |  |  | 15/09/2026 | 16/09/2026 | 2026-08-09 | 2026-12-09 | 1203 | 1020 | 183
ADIDAS | 0903159040-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 862 | 30/09/2026 | 862 | ID | ID26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159040 KR2006 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | SPORT GOODS T |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 862 |  | 862 |  |  | 17/09/2026 | 17/09/2026 | 2026-08-09 | 2026-11-09 | 862 | 838 | 24
ADIDAS | 0903159048-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 340 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903159048 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903159067-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159067 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | PIZZA TEE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 311 |  | 311 |  |  | 15/10/2026 | 16/10/2026 | 21/08/2026 | 22/08/2026 | 311 | 308 | 3
ADIDAS | 0903159157-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159157 KW8932 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 30/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903159180-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 274 | 15/10/2026 | 274 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159180 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 274 |  | 274 |  |  | 2026-01-10 | 2026-02-10 |  |  | 274 |  | 274
ADIDAS | 0903159200-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 346 | 15/10/2026 | 346 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159200 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 346 |  | 346 |  |  | 2026-01-10 | 2026-01-10 |  |  | 346 |  | 346
ADIDAS | 0903159205-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159205 LC8884 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 128 |  | 128 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-08 | 2026-11-08 | 128 | 126 | 2
ADIDAS | 0903159207-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 257 | 15/10/2026 | 257 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Airowes). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903159207 KA2571 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 257 |  | 257 |  |  | 29/10/2026 | 30/10/2026 |  |  | 257 |  | 257 |  |  | 23/10/2026 | 24/10/2026 |  |  | 257 |  | 257
ADIDAS | 0903159239-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 238 | 15/10/2026 | 238 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159239 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 238 |  | 238 |  |  | 2026-01-10 | 2026-02-10 |  |  | 238 |  | 238
ADIDAS | 0903159261-1 KT4840 | ONIX | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903159261 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 26/10/2026 |  |  | 324 |  | 324 |  |  | 21/10/2026 | 23/10/2026 |  |  | 324 |  | 324 |  |  | 20/10/2026 | 22/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903159282-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 132 | 15/10/2026 | 132 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159282 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 132 |  | 132 |  |  | 24/10/2026 | 26/10/2026 |  |  | 132 |  | 132
ADIDAS | 0903159289-1 KA0235 | BLACK | 90D | S2608WR0901 | 1180 | 23/10/2026 | 1180 | SI | SI26/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 516415 | PAD+HT SUB PROCESS_V3 | 0903159289 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 1180 |  | 1180 |  |  | 2026-07-11 | 2026-10-11 |  |  | 1180 |  | 1180 |  |  | 2026-06-11 | 2026-09-11 |  |  | 1180 |  | 1180
ADIDAS | 0903159308-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 102 | 15/10/2026 | 102 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (Cargoport). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159308 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 16/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 102 |  | 102 |  |  | 13/10/2026 | 14/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903159320-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 222 | 30/09/2026 | 222 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650036 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159320 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-02-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 222 |  | 222 |  |  | 29/09/2026 | 30/09/2026 | 28/08/2026 | 28/08/2026 | 222 | 221 | 1
ADIDAS | 0903159340-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 313 | 30/09/2026 | 313 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 838103 | PRINT L1 SUB PROCESS_V3 | 0903159340 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 22/09/2026 | 22/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 18/09/2026 |  |  | 313 |  | 313
ADIDAS | 0903159374-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 100 | 15/10/2026 | 100 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903159374 KW8932 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903159424-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric (Cargoport). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650036 | PRINT L3+PPA SUB PROCESS_V3 | 0903159424 LG9669 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903159447-1 KE6899 | BLACK | 105D | S2608WR0601B | 102 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Cargoport). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903159447 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903159551-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159551 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 | 2026-02-09 | 2026-10-09 | 300 | 92 | 208
ADIDAS | 0903159571-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 2026-12-09 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159571 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 2026-05-09 | 29/08/2026 | 31/08/2026 | 522 | 522 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-08-09 | 522 | 522
ADIDAS | 0903159587-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 30/09/2026 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159587 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 522 | 215 | 307 |  |  | 27/08/2026 | 15/09/2026 | 27/08/2026 | 2026-09-09 | 522 | 518 | 4
ADIDAS | 0903159678-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 159 | 23/10/2026 | 159 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903159678 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 19/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 159 |  | 159 |  |  | 15/10/2026 | 15/10/2026 |  |  | 159 |  | 159 |  |  | 14/10/2026 | 14/10/2026 |  |  | 159 |  | 159
ADIDAS | 0903159703-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 23/10/2026 | 101 | AN | AN26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159703 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 101 |  | 101 |  |  | 24/10/2026 | 30/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903159732-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 155 | 23/10/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 512106 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159732 KU8975 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903159856-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 606 | 30/09/2026 | 606 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 630001 | PAD+HT SUB PROCESS_V3 | 0903159856 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 606 |  | 606 |  |  | 18/09/2026 | 19/09/2026 |  |  | 606 |  | 606 |  |  | 17/09/2026 | 18/09/2026 |  |  | 606 |  | 606
ADIDAS | 0903159879-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 300 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903159879 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903159916-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 305 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159916 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903159937-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 920 | 31/10/2026 | 920 | SA | SA26/06/2026 | G1I | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903159937 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-10-11 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-10-11 | 2026-12-11 |  |  | 920 |  | 920 |  |  | 2026-06-11 | 2026-09-11 |  |  | 920 |  | 920 |  |  | 2026-05-11 | 2026-07-11 |  |  | 920 |  | 920
ADIDAS | 0903159964-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 607 | 15/10/2026 | 607 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903159964 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 607 |  | 607 |  |  | 29/09/2026 | 30/09/2026 |  |  | 607 |  | 607 |  |  | 28/09/2026 | 29/09/2026 |  |  | 607 |  | 607
ADIDAS | 0903159994-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 328 | 15/10/2026 | 328 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159994 KX7716 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-01-10 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 2026-01-10 | 2026-07-10 |  |  | 328 |  | 328 |  |  | 28/09/2026 | 2026-03-10 |  |  | 328 |  | 328
ADIDAS | 0903160003-1 KA3530 | BLACK | 105D | S2650MTR402 | 237 | 15/10/2026 | 237 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903160003 KA3530 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | WE FR T BLACK |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 237 |  | 237 |  |  | 28/09/2026 | 29/09/2026 |  |  | 237 |  | 237 |  |  | 26/09/2026 | 28/09/2026 |  |  | 237 |  | 237
ADIDAS | 0903160021-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 328 | 15/10/2026 | 328 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160021 KX7715 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 28/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 28/09/2026 | 2026-01-10 |  |  | 328 |  | 328 |  |  | 24/09/2026 | 28/09/2026 |  |  | 328 |  | 328
ADIDAS | 0903160116-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 364 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903160116 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903160143-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 382 | 31/10/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160143 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903160371-1 KA0246 | BLACK | 90D | S2608WR0902 | 1181 | 15/10/2026 | 1181 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516267 | PAD+HT SUB PROCESS_V3 | 0903160371 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-06-10 | 2026-08-10 |  |  | 1181 |  | 1181 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1181 |  | 1181 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1181 |  | 1181
ADIDAS | 0903160415-1 KA0246 | BLACK | 90D | S2608WR0902 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516404 | PAD+HT SUB PROCESS_V3 | 0903160415 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903160502-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 852 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516267 | PAD+HT SUB PROCESS_V3 | 0903160502 LD0908 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903160693-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 359 | 31/10/2026 | 359 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160693 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-11 | W SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 359 |  | 359 |  |  | 2026-05-11 | 2026-07-11 |  |  | 359 |  | 359
ADIDAS | 0903160711-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 758 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903160711 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903160743-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 594 | 31/10/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903160743 KX3655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903160769-1 LG9675 | BLACK | 120D | S2754WAS513C | 392 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903160769 LG9675 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903160834-1 LE8187 | BLACK | 105D | S2754MAS513 | 217 | 15/10/2026 | 217 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160834 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 23/10/2026 | M SL WV TP PT BLACK |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 217 |  | 217 |  |  | 20/10/2026 | 20/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903160891-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 317 | 31/10/2026 | 317 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160891 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 19/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/11/2026 | 23/11/2026 |  |  | 317 |  | 317 |  |  | 16/11/2026 | 19/11/2026 |  |  | 317 |  | 317
ADIDAS | 0903161081-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (KN GLT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903161081 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903161114-1 KS0802 | TECH INDIGO S20/WHITE | 105D | S2608WR0601B | 7 | 15/10/2026 | 7 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903161114 KS0802 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | adi365 Short W TECH INDIGO S20/WHITE |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 7 |  | 7 |  |  | 29/10/2026 | 31/10/2026 |  |  | 7 |  | 7 |  |  | 28/10/2026 | 30/10/2026 |  |  | 7 |  | 7
ADIDAS | 0903161148-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 5352 | 15/10/2026 | 5352 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Libolon, PI Date 22-Jul. actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 29-Jul. T2 Formosa, PI Date 09-Jun, actual receives 22-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161148 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 27/10/2026 | 2026-04-11 |  |  | 5352 |  | 5352 |  |  | 23/10/2026 | 31/10/2026 |  |  | 5352 |  | 5352
ADIDAS | 0903161212-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 8768 | 30/09/2026 | 8768 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161212 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 25/09/2026 | 2026-07-10 |  |  | 8768 |  | 8768 |  |  | 22/09/2026 | 2026-03-10 |  |  | 8768 |  | 8768
ADIDAS | 0903161277-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 141 | 30/09/2026 | 141 | AN | AN26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 21/09: ex-fty 516342 | PRINT L3+PAD SUB PROCESS_V3 | 0903161277 LC8882 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T BLACK |  | SS27 | 15/09/2026 | 23/09/2026 | 15/09/2026 | 15/09/2026 | 141 | 139 | 2 |  | 139 | 2026-11-09 | 19/09/2026 | 2026-11-08 | 13/08/2026 | 141 | 141
ADIDAS | 0903162196-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 313 | 23/09/2026 | 313 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 23/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162196 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 313 | 313 |  |  |  | 2026-05-09 | 2026-10-09 | 14/08/2026 | 31/08/2026 | 313 | 297 | 16
ADIDAS | 0903162215-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 846 | 30/09/2026 | 846 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162215 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 19/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 846 |  | 846 |  |  | 16/09/2026 | 18/09/2026 |  |  | 846 |  | 846
ADIDAS | 0903162243-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 321 | 15/10/2026 | 321 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162243 LE8188 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 19/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 321 |  | 321 |  |  | 15/10/2026 | 16/10/2026 |  |  | 321 |  | 321
ADIDAS | 0903162307-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162307 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-06-11 | 2026-07-11 |  |  | 153 |  | 153 |  |  | 2026-03-11 | 2026-04-11 |  |  | 153 |  | 153 |  |  | 2026-02-11 | 2026-03-11 |  |  | 153 |  | 153
ADIDAS | 0903162341-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 205 | 15/10/2026 | 205 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162341 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 205 |  | 205 |  |  | 29/09/2026 | 30/09/2026 |  |  | 205 |  | 205 |  |  | 28/09/2026 | 29/09/2026 |  |  | 205 |  | 205
ADIDAS | 0903162369-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 1229 | 30/09/2026 | 1229 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162369 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 19/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 1229 |  | 1229 |  |  | 16/09/2026 | 19/09/2026 |  |  | 1229 |  | 1229
ADIDAS | 0903162384-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162384 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/11/2026 | M SERENO SHO WHITE |  | SS27-STX | 13/11/2026 | 14/11/2026 |  |  | 327 |  | 327 |  |  | 2026-10-11 | 2026-11-11 |  |  | 327 |  | 327 |  |  | 2026-09-11 | 2026-10-11 |  |  | 327 |  | 327
ADIDAS | 0903162397-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 1526 | 31/10/2026 | 1526 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162397 LD0285 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 1526 |  | 1526 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1526 |  | 1526 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1526 |  | 1526
ADIDAS | 0903162420-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 100 | 15/10/2026 | 100 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162420 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903162423-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 1500 | 31/10/2026 | 1500 | AN | AN29/06/2026 | G2H | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162423 LD0287 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-10 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-05-10 | 2026-06-10 |  |  | 1500 |  | 1500 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1500 |  | 1500 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903162450-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 31/10/2026 | 300 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162450 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0903162460-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162460 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/11/2026 | M SERENO SHO BLACK |  | SS27-STX | 13/11/2026 | 14/11/2026 |  |  | 327 |  | 327 |  |  | 2026-10-11 | 2026-11-11 |  |  | 327 |  | 327 |  |  | 2026-09-11 | 2026-10-11 |  |  | 327 |  | 327
ADIDAS | 0903162479-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 20-Jul, actual receives 31-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162479 LF0727 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-11 | M SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 300 |  | 300 |  |  | 2026-05-11 | 2026-07-11 |  |  | 300 |  | 300
ADIDAS | 0903162500-1 LC6341 | BLACK | 90D | S27GMGFX130 | 246 | 30/09/2026 | 246 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 630001 | PRINT L3+PAD SUB PROCESS_V3 | 0903162500 LC6341 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 246 |  | 246 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 2026-09-09 | 246 | 226 | 20
ADIDAS | 0903162572-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162572 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 29/09/2026 | 29/09/2026 |  |  | 153 |  | 153 |  |  | 25/09/2026 | 25/09/2026 |  |  | 153 |  | 153 |  |  | 24/09/2026 | 24/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903162593-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 624 | 15/10/2026 | 624 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162593 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-06-11 | 2026-07-11 |  |  | 624 |  | 624 |  |  | 2026-03-11 | 2026-04-11 |  |  | 624 |  | 624 |  |  | 2026-02-11 | 2026-03-11 |  |  | 624 |  | 624
ADIDAS | 0903162621-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 512 | 15/10/2026 | 512 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162621 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 29/09/2026 | 29/09/2026 |  |  | 512 |  | 512 |  |  | 25/09/2026 | 25/09/2026 |  |  | 512 |  | 512 |  |  | 24/09/2026 | 24/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903162642-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 195 | 30/09/2026 | 195 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 814006 | PRINT L1 SUB PROCESS_V3 | 0903162642 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 22/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 22/09/2026 | 22/09/2026 |  |  | 195 |  | 195 |  |  | 18/09/2026 | 18/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903163124-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 372 | 31/10/2026 | 372 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903163124 LG9661 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA | 2026-11-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-11-11 | 13/11/2026 |  |  | 372 |  | 372 |  |  | 2026-07-11 | 2026-10-11 |  |  | 372 |  | 372
ADIDAS | 0903163142-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 344 | 15/10/2026 | 344 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903163142 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-01-10 | 2026-01-10 |  |  | 344 |  | 344 |  |  | 28/09/2026 | 28/09/2026 |  |  | 344 |  | 344
ADIDAS | 0903163156-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 8 | 15/10/2026 | 8 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163156 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 8 |  | 8 |  |  | 14/10/2026 | 17/10/2026 |  |  | 8 |  | 8 |  |  | 13/10/2026 | 16/10/2026 |  |  | 8 |  | 8
ADIDAS | 0903163238-1 KB5960 | WHITE | 120D | S2608MR0900A | 887 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163238 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903163335-1 KB5965 | BLACK | 120D | S2608MR0900A | 1228 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163335 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903163398-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903163398 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903163494-1 KE6899 | BLACK | 105D | S2608WR0601B | 1139 | 15/10/2026 | 1139 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163494 KE6899 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 1139 |  | 1139 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1139 |  | 1139 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1139 |  | 1139
ADIDAS | 0903163534-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 688 | 15/10/2026 | 688 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163534 KE6716 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 688 |  | 688 |  |  | 17/10/2026 | 20/10/2026 |  |  | 688 |  | 688 |  |  | 16/10/2026 | 19/10/2026 |  |  | 688 |  | 688
ADIDAS | 0903163589-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 336 | 30/09/2026 | 336 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric (KN GLT). T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 650010 | PRINT L2+HT SUB PROCESS_V3 | 0903163589 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 336 |  | 336 |  |  | 19/09/2026 | 21/09/2026 |  |  | 336 |  | 336 |  |  | 18/09/2026 | 19/09/2026 |  |  | 336 |  | 336
ADIDAS | 0903163782-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 1st Art (TC 10 pcs) 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903163782 JM1772 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903164375-1 KW5050 | MAROON | 90D | F2625M101 | 1414 | 23/10/2026 | 1414 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | (29/07/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164375 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | ESS REG |  | SS27-STX | 2026-10-10 | 2026-12-10 |  |  | 1414 |  | 1414 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1414 |  | 1414
ADIDAS | 0903164418-1 KW5050 | MAROON | 90D | F2625M101 | 230 | 15/10/2026 | 230 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164418 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | ESS REG |  | SS27-STX | 2026-10-10 | 2026-12-10 |  |  | 230 |  | 230 |  |  | 2026-07-10 | 2026-08-10 |  |  | 230 |  | 230
ADIDAS | 0903164473-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 776 | 23/10/2026 | 776 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164473 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-12-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-12-10 | 13/10/2026 |  |  | 776 |  | 776 |  |  | 2026-08-10 | 2026-09-10 |  |  | 776 |  | 776
ADIDAS | 0903164544-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 214 | 15/10/2026 | 214 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164544 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-01-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-01-10 | 2026-01-10 |  |  | 214 |  | 214 |  |  | 28/09/2026 | 28/09/2026 |  |  | 214 |  | 214
ADIDAS | 0903164569-1 KW5050 | MAROON | 90D | F2625M101 | 170 | 2026-07-10 | 170 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164569 KW5050 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | ESS REG |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 170 |  | 170 |  |  | 29/09/2026 | 29/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903164595-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 416 | 2026-07-10 | 416 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903164595 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 416 |  | 416 |  |  | 19/09/2026 | 21/09/2026 |  |  | 416 |  | 416 |  |  | 18/09/2026 | 19/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903164629-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 808 | 2026-07-10 | 808 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164629 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 808 |  | 808 |  |  | 24/09/2026 | 25/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903164697-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 133 | 2026-07-10 | 133 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164697 IN1172 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 133 | 133 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 133 | 133 |  |  |  | 2026-11-08 | 26/08/2026 | 15/07/2026 | 23/07/2026 | 133 | 133
ADIDAS | 0903164732-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 264 | 2026-07-10 | 264 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164732 IN1156 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 264 | 264 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 264 | 264 |  |  |  | 2026-11-08 | 26/08/2026 | 13/07/2026 | 27/07/2026 | 264 | 264
ADIDAS | 0903164830-1 KT4840 | ONIX | 90D | S2408MR1600 | 102 | 30/09/2026 | 102 | SA | SA26/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 830009 | HT SUB PROCESS_V1 | 0903164830 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 102 |  | 102 |  |  | 28/09/2026 | 29/09/2026 |  |  | 102 |  | 102 |  |  | 26/09/2026 | 28/09/2026 | 14/09/2026 | 14/09/2026 | 102 | 24 | 78
ADIDAS | 0903164987-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 110 | 2026-07-10 | 110 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 800187 | EMBRO SUB PROCESS_V1 | 0903164987 KT7396 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-01-10 | 2026-01-10 |  |  | 110 |  | 110 |  |  | 28/09/2026 | 28/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903165005-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 135 | 15/10/2026 | 135 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165005 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 135 |  | 135 |  |  | 17/10/2026 | 20/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903165033-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 408 | 2026-07-10 | 408 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903165033 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 26/09/2026 | 29/09/2026 |  |  | 408 |  | 408 |  |  | 23/09/2026 | 25/09/2026 |  |  | 408 |  | 408 |  |  | 22/09/2026 | 24/09/2026 |  |  | 408 |  | 408
ADIDAS | 0903165037-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 273 | 31/10/2026 | 273 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165037 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/11/2026 | 23/11/2026 |  |  | 273 |  | 273 |  |  | 16/11/2026 | 19/11/2026 |  |  | 273 |  | 273
ADIDAS | 0903165054-1 KW5050 | MAROON | 90D | F2625M101 | 447 | 15/10/2026 | 447 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903165054 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | ESS REG |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 447 |  | 447 |  |  | 29/09/2026 | 29/09/2026 |  |  | 447 |  | 447
ADIDAS | 0903165062-1 LF0727 | BLACK | 120D | S2754MAS510B | 562 | 31/10/2026 | 562 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165062 LF0727 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | M SL WV TT BLACK |  | SS27 | 2026-11-11 | 16/11/2026 |  |  | 562 |  | 562 |  |  | 2026-07-11 | 2026-12-11 |  |  | 562 |  | 562
ADIDAS | 0903165070-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 309 | 30/09/2026 | 309 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903165070 LD0908 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309 |  |  | 18/09/2026 | 19/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903165085-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 303 | 31/10/2026 | 303 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165085 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/11/2026 | 23/11/2026 |  |  | 303 |  | 303 |  |  | 16/11/2026 | 19/11/2026 |  |  | 303 |  | 303
ADIDAS | 0903165109-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 495 | 15/10/2026 | 495 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165109 LE8187 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 495 |  | 495 |  |  | 17/10/2026 | 20/10/2026 |  |  | 495 |  | 495
ADIDAS | 0903165167-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 900 | 30/09/2026 | 900 | SA | SA26/06/2026 | G1C | JACKET | G1 | (29/07/2026) | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903165167 JM1772 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 19/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903165226-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 999 | 30/09/2026 | 999 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165226 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 999 |  | 999 |  |  | 2026-06-10 | 2026-07-10 |  |  | 999 |  | 999
ADIDAS | 0903165306-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 168 | 2026-07-10 | 168 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165306 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 168 |  | 168 |  |  | 2026-10-10 | 2026-12-10 |  |  | 168 |  | 168
ADIDAS | 0903165362-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165362 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903165408-1 LG9675 | BLACK | 120D | S2754WAS513C | 384 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903165408 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903165425-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 315 | 30/09/2026 | 315 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165425 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 315 |  | 315 |  |  | 2026-03-10 | 2026-05-10 |  |  | 315 |  | 315
ADIDAS | 0903165470-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 1248 | 30/09/2026 | 1248 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165470 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 16/09/2026 | 17/09/2026 |  |  | 1248 |  | 1248 |  |  | 2026-12-09 | 14/09/2026 |  |  | 1248 |  | 1248
ADIDAS | 0903165496-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 300 | 31/10/2026 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165496 LF0729 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903165506-1 LC7300 | WHITE | 90D | S2725M926A | 318 | 2026-07-10 | 318 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903165506 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 318 |  | 318 |  |  | 26/09/2026 | 28/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903165542-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 517 | 2026-07-10 | 517 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903165542 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 517 |  | 517 |  |  | 19/09/2026 | 21/09/2026 |  |  | 517 |  | 517
ADIDAS | 0903165585-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 1245 | 30/09/2026 | 1245 | SI | SI26/06/2026 | G1K | POLO SHIRT | G1 | (12/08/2026) | ok | 25/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165585 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 25/09/2026 |  |  | 1245 |  | 1245 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1245 |  | 1245
ADIDAS | 0903165644-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 243 | 23/09/2026 | 243 | AN | AN26/06/2026 | G1Q | T-SHIRT | G1 | (28/07/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903165644 KX0123 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T WHITE |  | SS27 | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 243 | 234 | 9 |  | 234 | 2026-11-09 | 2026-12-09 | 31/07/2026 | 2026-08-08 | 243 | 243
ADIDAS | 0903165645-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 428 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903165645 KG3190 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903166391-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903166391 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 300 | 253 | 47 |  | 3 | 2026-09-09 | 2026-11-09 | 29/08/2026 | 15/09/2026 | 300 | 300 |  |  | 4
ADIDAS | 0903166456-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 704 | 2026-07-10 | 704 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903166456 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 704 |  | 704 |  |  | 22/09/2026 | 23/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903166626-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 123 | 16/10/2026 | 123 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903166626 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | W SL WV TT BLACK |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 123 |  | 123 |  |  | 26/10/2026 | 26/10/2026 |  |  | 123 |  | 123
ADIDAS | 0903166659-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 319 | 2026-07-10 | 319 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903166659 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 26/09/2026 | 28/09/2026 |  |  | 319 |  | 319
ADIDAS | 0903167086-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 523 | 15/10/2026 | 523 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 516199 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167086 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 523 |  | 523 |  |  | 21/10/2026 | 22/10/2026 |  |  | 523 |  | 523 |  |  | 15/10/2026 | 16/10/2026 |  |  | 523 |  | 523
ADIDAS | 0903167126-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 1460 | 15/10/2026 | 1460 | AN | AN26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167126 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 24/10/2026 |  |  | 1460 |  | 1460 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1460 |  | 1460 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1460 |  | 1460
ADIDAS | 0903167166-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167166 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-01-10 |  |  | 271 |  | 271
ADIDAS | 0903167173-1 LF0727 | BLACK | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167173 LF0727 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | M SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 127 |  | 127 |  |  | 2026-05-11 | 2026-07-11 |  |  | 127 |  | 127
ADIDAS | 0903167196-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 182 | 15/10/2026 | 182 | AN | AN26/06/2026 | G1M | T-SHIRT | G1 |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903167196 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/10/2026 | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 182 |  | 182 |  |  | 27/10/2026 | 28/10/2026 |  |  | 182 |  | 182 |  |  | 26/10/2026 | 27/10/2026 |  |  | 182 |  | 182
ADIDAS | 0903167198-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 116 | 15/10/2026 | 116 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167198 LF0718 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 116 |  | 116 |  |  | 2026-10-10 | 2026-12-10 |  |  | 116 |  | 116
ADIDAS | 0903167227-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 410 | 2026-07-10 | 410 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903167227 KT7396 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 410 |  | 410 |  |  | 28/09/2026 | 29/09/2026 |  |  | 410 |  | 410
ADIDAS | 0903167251-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 31/10/2026 | 311 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167251 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | LV COLLEGIATE T |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 311 |  | 311 |  |  | 17/10/2026 | 17/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903167268-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 415 | 30/09/2026 | 415 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167268 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | LV COLLEGIATE T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 415 |  | 415 |  |  | 2026-01-10 | 2026-02-10 | 2026-10-09 | 2026-10-09 | 415 | 394 | 21
ADIDAS | 0903167275-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 267 | 2026-07-10 | 267 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167275 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 267 |  | 267 |  |  | 23/09/2026 | 24/09/2026 |  |  | 267 |  | 267
ADIDAS | 0903167316-1 KY5866 | BLACK | 90D | S2750MTR052 | 139 | 15/10/2026 | 139 | SI | SI26/06/2026 | G2C | SHORTS | G2 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903167316 KY5866 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D18T ESS SHORTS BLACK |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 139 |  | 139 |  |  | 2026-03-10 | 2026-05-10 |  |  | 139 |  | 139 |  |  | 2026-02-10 | 2026-03-10 |  |  | 139 |  | 139
ADIDAS | 0903167324-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 255 | 15/10/2026 | 255 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903167324 KD0738 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 255 |  | 255 |  |  | 21/10/2026 | 22/10/2026 |  |  | 255 |  | 255 |  |  | 15/10/2026 | 16/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903167339-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 673 | 2026-07-10 | 673 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167339 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 673 |  | 673 |  |  | 24/09/2026 | 24/09/2026 |  |  | 673 |  | 673
ADIDAS | 0903167370-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 210 | 15/10/2026 | 210 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903167370 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 210 |  | 210 |  |  | 2026-01-10 | 2026-02-10 |  |  | 210 |  | 210
ADIDAS | 0903167433-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 501 | 2026-07-10 | 501 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167433 KW8934 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 26/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 26/09/2026 | 26/09/2026 |  |  | 501 |  | 501 |  |  | 23/09/2026 | 23/09/2026 |  |  | 501 |  | 501
ADIDAS | 0903167439-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1157 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903167439 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167457-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 405 | 2026-07-10 | 405 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167457 KW8932 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 26/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 405 |  | 405 |  |  | 23/09/2026 | 24/09/2026 |  |  | 405 |  | 405
ADIDAS | 0903167485-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 130 | 2026-07-10 | 130 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167485 KW9039 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 130 |  | 130 |  |  | 19/09/2026 | 21/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903167519-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 733 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167519 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167551-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 700 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167551 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903167564-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 652 | 15/10/2026 | 652 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167564 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 26/09/2026 | 29/09/2026 |  |  | 652 |  | 652 |  |  | 23/09/2026 | 25/09/2026 |  |  | 652 |  | 652 |  |  | 22/09/2026 | 24/09/2026 |  |  | 652 |  | 652
ADIDAS | 0903167589-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 554 | 15/10/2026 | 554 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167589 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 554 |  | 554 |  |  | 29/09/2026 | 30/09/2026 |  |  | 554 |  | 554
ADIDAS | 0903167609-1 LF0727 | BLACK | 120D | S2754MAS510B | 718 | 31/10/2026 | 718 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167609 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-11 | M SL WV TT BLACK |  | SS27 | 2026-11-11 | 16/11/2026 |  |  | 718 |  | 718 |  |  | 2026-07-11 | 2026-12-11 |  |  | 718 |  | 718
ADIDAS | 0903167625-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 494 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167625 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167678-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167678 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903167694-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 362 | 15/10/2026 | 362 | SI | SI26/06/2026 | G3I | PANTS | G3 | (28/08/2026) | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 04-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167694 LE8188 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 362 |  | 362 |  |  | 15/10/2026 | 16/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903167696-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/09/2026 | 500 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167696 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 23/09/2026 | 2026-12-09 | 2026-12-09 | 500 | 122 | 378
ADIDAS | 0903167722-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 754 | 15/10/2026 | 754 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167722 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 754 |  | 754 |  |  | 19/09/2026 | 21/09/2026 |  |  | 754 |  | 754 |  |  | 18/09/2026 | 19/09/2026 |  |  | 754 |  | 754
ADIDAS | 0903167723-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 517 | 15/10/2026 | 517 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167723 LE8188 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 517 |  | 517 |  |  | 16/10/2026 | 17/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903167736-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 356 | 2026-07-10 | 356 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877)., ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167736 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 356 |  | 356 |  |  | 2026-08-10 | 2026-09-10 |  |  | 356 |  | 356
ADIDAS | 0903167751-1 KW5050 | MAROON | 90D | F2625M101 | 2163 | 15/09/2026 | 2163 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 15/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO SUB PROCESS_V1 | 0903167751 KW5050 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-09 | ESS REG |  | SS27-STX | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 2163 | 2163 |  |  | 698 | 2026-09-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 2163 | 2159 | 4 |  | 26
ADIDAS | 0903167760-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167760 LF0729 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 127 |  | 127 |  |  | 26/10/2026 | 28/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903167776-1 KA4331 | BLACK | 90D | S2608MR0902 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 1st Art (TC 10 pcs) 516267 | PAD+HT SUB PROCESS_V3 | 0903167776 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 1200 |  | 1200 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1200 |  | 1200 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903167792-1 KA4331 | BLACK | 90D | S2608MR0902 | 335 | 2026-07-10 | 335 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516400 | PAD+HT SUB PROCESS_V3 | 0903167792 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 335 |  | 335 |  |  | 22/09/2026 | 24/09/2026 |  |  | 335 |  | 335 |  |  | 21/09/2026 | 23/09/2026 |  |  | 335 |  | 335
ADIDAS | 0903167804-1 KW5050 | MAROON | 90D | F2625M101 | 334 | 15/10/2026 | 334 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903167804 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-10 | ESS REG |  | SS27-STX | 2026-10-10 | 2026-12-10 |  |  | 334 |  | 334 |  |  | 2026-07-10 | 2026-08-10 |  |  | 334 |  | 334
ADIDAS | 0903167827-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 504 | 31/10/2026 | 504 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167827 LG9665 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-04-11 | 2026-07-11 |  |  | 504 |  | 504 |  |  | 31/10/2026 | 2026-04-11 |  |  | 504 |  | 504
ADIDAS | 0903167883-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 262 | 15/10/2026 | 262 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167883 LD6542 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 262 |  | 262 |  |  | 13/10/2026 | 15/10/2026 |  |  | 262 |  | 262
ADIDAS | 0903167908-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 627 | 15/10/2026 | 627 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167908 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | W SL WV TT BLACK |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 627 |  | 627 |  |  | 23/10/2026 | 26/10/2026 |  |  | 627 |  | 627
ADIDAS | 0903167943-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 555 | 15/10/2026 | 555 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167943 KX7715 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 28/09/2026 | 2026-01-10 |  |  | 555 |  | 555 |  |  | 24/09/2026 | 28/09/2026 |  |  | 555 |  | 555
ADIDAS | 0903167963-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 332 | 31/10/2026 | 332 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167963 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-04-11 | 2026-07-11 |  |  | 332 |  | 332 |  |  | 31/10/2026 | 2026-04-11 |  |  | 332 |  | 332
ADIDAS | 0903168065-1 KB5960 | WHITE | 120D | S2608MR0900A | 304 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0903168065 KB5960 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903168109-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 26/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168109 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 400 | 400 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-11-08 | 15/09/2026 | 400 | 387 | 13 |  | 19
ADIDAS | 0903168155-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 209 | 23/10/2026 | 209 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168155 KT7396 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-12-10 | 13/10/2026 |  |  | 209 |  | 209 |  |  | 2026-08-10 | 2026-09-10 |  |  | 209 |  | 209
ADIDAS | 0903168201-1 KW5050 | MAROON | 90D | F2625M101 | 339 | 23/10/2026 | 339 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168201 KW5050 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-09-10 | ESS REG |  | SS27-STX | 2026-09-10 | 2026-10-10 |  |  | 339 |  | 339 |  |  | 2026-06-10 | 2026-07-10 |  |  | 339 |  | 339
ADIDAS | 0903168275-1 KA0246 | BLACK | 90D | S2608WR0902 | 339 | 2026-07-10 | 339 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 15-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903168275 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 339 |  | 339 |  |  | 22/09/2026 | 24/09/2026 |  |  | 339 |  | 339 |  |  | 21/09/2026 | 23/09/2026 |  |  | 339 |  | 339
ADIDAS | 0903168299-1 KA0246 | BLACK | 90D | S2608WR0902 | 608 | 15/10/2026 | 608 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903168299 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 608 |  | 608 |  |  | 2026-05-10 | 2026-06-10 |  |  | 608 |  | 608 |  |  | 2026-03-10 | 2026-05-10 |  |  | 608 |  | 608
ADIDAS | 0903168302-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168302 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903168327-1 KA0246 | BLACK | 90D | S2608WR0902 | 301 | 30/09/2026 | 301 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168327 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 19/09/2026 | 21/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903168356-1 KA0246 | BLACK | 90D | S2608WR0902 | 314 | 2026-07-10 | 314 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168356 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 314 |  | 314 |  |  | 24/09/2026 | 25/09/2026 |  |  | 314 |  | 314 |  |  | 23/09/2026 | 24/09/2026 |  |  | 314 |  | 314
ADIDAS | 0903168388-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 186 | 30/09/2026 | 186 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168388 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 19/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 186 | 161 | 25 |  | 161 | 16/09/2026 | 17/09/2026 | 27/08/2026 | 2026-07-09 | 186 | 168 | 18
ADIDAS | 0903168468-1 KA4331 | BLACK | 90D | S2608MR0902 | 364 | 2026-07-10 | 364 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168468 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 364 |  | 364 |  |  | 24/09/2026 | 25/09/2026 |  |  | 364 |  | 364 |  |  | 23/09/2026 | 24/09/2026 |  |  | 364 |  | 364
ADIDAS | 0903168653-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 190 | 31/10/2026 | 190 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903168653 LG9666 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | W SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 190 |  | 190 |  |  | 2026-05-11 | 2026-07-11 |  |  | 190 |  | 190
ADIDAS | 0903169170-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 204 | 15/10/2026 | 204 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516443 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169170 KU8975 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 22/10/2026 | 26/10/2026 |  |  | 204 |  | 204 |  |  | 19/10/2026 | 22/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903169256-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 701 | 15/10/2026 | 701 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169256 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 22/10/2026 | 26/10/2026 |  |  | 701 |  | 701 |  |  | 19/10/2026 | 22/10/2026 |  |  | 701 |  | 701
ADIDAS | 0903169653-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 438 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903169653 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903169715-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 328 | 15/10/2026 | 328 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169715 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 328 |  | 328 |  |  | 30/09/2026 | 2026-01-10 |  |  | 328 |  | 328
ADIDAS | 0903169772-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169772 KY3734 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903169855-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 150 | 15/10/2026 | 150 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169855 KW9039 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 24/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 150 |  | 150 |  |  | 21/09/2026 | 22/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903169976-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 259 | 15/10/2026 | 259 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903169976 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 259 |  | 259 |  |  | 30/09/2026 | 2026-01-10 |  |  | 259 |  | 259
ADIDAS | 0903170085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 538 | 15/09/2026 | 538 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 14-Jul. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170085 LD5446 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 538 | 538 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-05-09 | 14/09/2026 | 538 | 527 | 11
ADIDAS | 0903170105-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 1240 | 15/09/2026 | 1240 | SA | SA26/06/2026 | G3E,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903170105 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-09 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-09 | 16/09/2026 | 2026-11-09 | 15/09/2026 | 1240 | 1240 |  |  | 28 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 1240 | 1240 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-09-09 | 14/09/2026 | 1240 | 1240
ADIDAS | 0903170139-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 574 | 15/09/2026 | 574 | AN | AN26/06/2026 | G3A | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170139 LE8181 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 14/09/2026 | 2026-10-09 | 2026-11-09 | 574 | 574 |  |  |  | 2026-07-09 | 2026-10-09 | 2026-07-09 | 2026-11-09 | 574 | 574
ADIDAS | 0903170160-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 15/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170160 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 400 | 400 |  |  | 21 | 2026-05-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 400 | 280 | 120
ADIDAS | 0903170187-1 KB5965 | BLACK | 120D | S2608MR0900A | 509 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170187 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI | [20 empty] | 2026-11-09 | 2026-11-09
ADIDAS | 0903170289-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170289 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 283 | 17 |  | 283 | 2026-11-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 299 | 1
ADIDAS | 0903170312-1 KB5960 | WHITE | 120D | S2608MR0900A | 164 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170312 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903170946-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 260 | 15/10/2026 | 260 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903170946 KD5507 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | WE FR T GREY FIVE F17 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 260 |  | 260 |  |  | 28/09/2026 | 29/09/2026 |  |  | 260 |  | 260 |  |  | 26/09/2026 | 28/09/2026 |  |  | 260 |  | 260
ADIDAS | 0903170968-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 160 | 23/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903170968 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903170993-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 327 | 2026-07-10 | 327 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903170993 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 327 |  | 327 |  |  | 22/09/2026 | 23/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903171021-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 500 | 15/10/2026 | 500 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903171021 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 500 |  | 500 |  |  | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903172164-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 1591 | 15/09/2026 | 1591 | AN | AN26/06/2026 | G3B,G3J | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 13-Aug. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 13-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903172164 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1591 | 1591 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-03-09 | 15/09/2026 | 1591 | 1578 | 13 |  | 8
ADIDAS | 0903173197-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 1686 | 30/09/2026 | 1686 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903173197 KW8932 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 18/09/2026 | 19/09/2026 |  |  | 1686 |  | 1686 |  |  | 15/09/2026 | 16/09/2026 |  |  | 1686 |  | 1686
ADIDAS | 0903173246-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1225 | 30/09/2026 | 1225 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173246 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1225 |  | 1225 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1225 |  | 1225
ADIDAS | 0903173302-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 410 | 30/09/2026 | 410 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516461 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173302 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 410 |  | 410 |  |  | 23/09/2026 | 24/09/2026 | 2026-12-09 | 14/09/2026 | 410 | 400 | 10
ADIDAS | 0903173331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2400 | 2026-07-10 | 2400 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 24-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173331 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/10/2026 | 19/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-12-10 | 15/10/2026 |  |  | 2400 |  | 2400
ADIDAS | 0903173353-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173353 KV7863 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 1500 | 384 | 1116 |  | 384 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 1500 | 1470 | 30 |  | 991
ADIDAS | 0903173426-1 LG9669 | BLACK | 120D | S2754WAS514C | 276 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903173426 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903173473-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173473 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903173490-1 LG9669 | BLACK | 120D | S2754WAS514C | 161 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903173490 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903173515-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173515 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903173545-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173545 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 800 |  | 800 |  |  | 2026-03-10 | 2026-05-10 | 14/09/2026 | 15/09/2026 | 800 | 797 | 3 |  | 792
ADIDAS | 0903173563-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-12-09 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173563 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 300 | 300 |  |  |  | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 300 | 300
ADIDAS | 0903174134-1 KA4331 | BLACK | 90D | S2608MR0902 | 303 | 30/09/2026 | 303 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903174134 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 303 |  | 303 |  |  | 19/09/2026 | 21/09/2026 |  |  | 303 |  | 303 |  |  | 18/09/2026 | 19/09/2026 |  |  | 303 |  | 303
ADIDAS | 0903174404-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 400 | 31/10/2026 |  | AN | AN26/06/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 21-Jul, ETD ?? T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903174404 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903176681-1 KA4331 | BLACK | 90D | S2608MR0902 | 371 | 2026-07-10 | 371 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516394 | PAD+HT SUB PROCESS_V3 | 0903176681 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 371 |  | 371 |  |  | 24/09/2026 | 25/09/2026 |  |  | 371 |  | 371 |  |  | 23/09/2026 | 24/09/2026 |  |  | 371 |  | 371
ADIDAS | 0903176702-1 KA4331 | BLACK | 90D | S2608MR0902 | 700 | 30/09/2026 | 700 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903176702 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 700 |  | 700 |  |  | 19/09/2026 | 21/09/2026 |  |  | 700 |  | 700 |  |  | 18/09/2026 | 19/09/2026 |  |  | 700 |  | 700
ADIDAS | 0903176748-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 309 | 15/10/2026 | 309 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176748 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 309 |  | 309 |  |  | 13/10/2026 | 14/10/2026 |  |  | 309 |  | 309 |  |  | 2026-07-10 | 2026-08-10 |  |  | 309 |  | 309
ADIDAS | 0903176770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2305 | 15/10/2026 | 2305 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 28/10/2026 |  |  | 2305 |  | 2305 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2305 |  | 2305 |  |  | 15/10/2026 | 19/10/2026 |  |  | 2305 |  | 2305
ADIDAS | 0903176795-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 459 | 15/10/2026 | 459 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176795 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 459 |  | 459 |  |  | 2026-12-10 | 13/10/2026 |  |  | 459 |  | 459 |  |  | 2026-06-10 | 2026-07-10 |  |  | 459 |  | 459
ADIDAS | 0903176816-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 314 | 23/10/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176816 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903176840-1 IN1159 | BLACK | 90D | S2408MR1601 | 223 | 2026-07-10 | 223 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516443 | HT SUB PROCESS_V1 | 0903176840 IN1159 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 223 |  | 223 |  |  | 19/09/2026 | 21/09/2026 |  |  | 223 |  | 223 |  |  | 18/09/2026 | 19/09/2026 |  |  | 223 |  | 223
ADIDAS | 0903176865-1 KA0246 | BLACK | 90D | S2608WR0902 | 450 | 2026-07-10 | 450 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 26-Aug. 516244 | PAD+HT SUB PROCESS_V3 | 0903176865 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 450 |  | 450 |  |  | 24/09/2026 | 25/09/2026 |  |  | 450 |  | 450 |  |  | 23/09/2026 | 24/09/2026 |  |  | 450 |  | 450
ADIDAS | 0903194096-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 249 | 31/10/2026 | 249 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194096 LC6790 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-11-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 249 |  | 249 |  |  | 2026-07-11 | 2026-10-11 |  |  | 249 |  | 249 |  |  | 2026-04-11 | 2026-06-11 |  |  | 249 |  | 249
ADIDAS | 0903194098-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 317 | 31/10/2026 | 317 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194098 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 317 |  | 317 |  |  | 2026-07-11 | 2026-10-11 |  |  | 317 |  | 317 |  |  | 2026-04-11 | 2026-06-11 |  |  | 317 |  | 317
ADIDAS | 0903194100-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194100 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194104-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 314 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194104 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194107-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1210 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194107 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194109-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194109 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194115-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 900 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903194115 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194119-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1516 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194119 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903194120-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 399 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516277 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194120 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194122-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 660 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194122 LF9775 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX
ADIDAS | 0903194123-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1198 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903194123 KY9391 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194130-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 107 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194130 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194137-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1214 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194137 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194145-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 133 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194145 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194293-1 IN1156 | BLACK | 90D | S2408MR1600 | 532 | 31/10/2026 | 532 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194293 IN1156 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 532 |  | 532 |  |  | 24/10/2026 | 26/10/2026 |  |  | 532 |  | 532 |  |  | 23/10/2026 | 24/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903194295-1 IN1157 | WHITE | 90D | S2408MR1600 | 328 | 31/10/2026 | 328 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194295 IN1157 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 328 |  | 328 |  |  | 24/10/2026 | 26/10/2026 |  |  | 328 |  | 328 |  |  | 23/10/2026 | 24/10/2026 |  |  | 328 |  | 328
ADIDAS | 0903194296-1 IN1172 | BLACK | 90D | S2408WR1600 | 645 | 31/10/2026 | 645 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194296 IN1172 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 645 |  | 645 |  |  | 26/10/2026 | 27/10/2026 |  |  | 645 |  | 645 |  |  | 24/10/2026 | 26/10/2026 |  |  | 645 |  | 645
ADIDAS | 0903194298-1 IN1173 | WHITE | 90D | S2408WR1600 | 356 | 31/10/2026 | 356 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194298 IN1173 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 356 |  | 356 |  |  | 2026-10-10 | 2026-12-10 |  |  | 356 |  | 356 |  |  | 2026-09-10 | 2026-10-10 |  |  | 356 |  | 356
ADIDAS | 0903194299-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 116 | 31/10/2026 | 116 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194299 IT1828 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI | 2026-03-11 | 2026-04-11 |  |  | 116 |  | 116 |  |  | 31/10/2026 | 2026-02-11 |  |  | 116 |  | 116 |  |  | 30/10/2026 | 31/10/2026 |  |  | 116 |  | 116
ADIDAS | 0903194300-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 31/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194300 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 120 |  | 120 |  |  | 24/10/2026 | 26/10/2026 |  |  | 120 |  | 120 |  |  | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194302-1 IN1173 | WHITE | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194302 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 120 |  | 120 |  |  | 2026-09-10 | 2026-10-10 |  |  | 120 |  | 120 |  |  | 2026-08-10 | 2026-09-10 |  |  | 120 |  | 120
ADIDAS | 0903194303-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194303 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 324 |  | 324 |  |  | 24/10/2026 | 26/10/2026 |  |  | 324 |  | 324 |  |  | 23/10/2026 | 24/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903194305-1 IN1156 | BLACK | 90D | S2408MR1600 | 180 | 15/10/2026 | 180 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194305 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 180 |  | 180 |  |  | 23/09/2026 | 24/09/2026 | 2026-09-09 | 2026-12-09 | 180 | 17 | 163 |  |  | 22/09/2026 | 23/09/2026 | 31/08/2026 | 2026-10-09 | 180 | 179 | 1
ADIDAS | 0903194307-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194307 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 120 |  | 120 |  |  | 29/09/2026 | 30/09/2026 | 2026-09-09 | 2026-11-09 | 120 | 119 | 1 |  |  | 28/09/2026 | 29/09/2026 | 2026-03-09 | 2026-10-09 | 120 | 119 | 1
ADIDAS | 0903194308-1 IN1172 | BLACK | 90D | S2408WR1600 | 120 | 15/10/2026 | 120 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194308 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 | 2026-05-09 | 2026-05-09 | 120 | 117 | 3
ADIDAS | 0903194309-1 IN1156 | BLACK | 90D | S2408MR1600 | 1308 | 15/10/2026 | 1308 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194309 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-10-10 |  |  | 1308 |  | 1308 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1308 |  | 1308 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1308 |  | 1308
ADIDAS | 0903194311-1 IN1172 | BLACK | 90D | S2408WR1600 | 1174 | 15/10/2026 | 1174 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903194311 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 1174 |  | 1174 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1174 |  | 1174 |  |  | 20/10/2026 | 21/10/2026 | 2026-03-09 | 2026-12-09 | 1174 | 1146 | 28
ADIDAS | 0903194312-1 IN1157 | WHITE | 90D | S2408MR1600 | 1525 | 15/10/2026 | 1525 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194312 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 1525 |  | 1525 |  |  | 30/09/2026 | 2026-02-10 | 2026-09-09 | 2026-12-09 | 1525 | 696 | 829 |  |  | 29/09/2026 | 2026-01-10 | 2026-02-09 | 15/09/2026 | 1525 | 928 | 597 |  | 232
ADIDAS | 0903194314-1 IN1173 | WHITE | 90D | S2408WR1600 | 1776 | 30/09/2026 | 1776 | SI | SI30/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 28/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. 672027 | HT SUB PROCESS_V1 | 0903194314 IN1173 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 28/09/2026 |  |  | 1776 |  | 1776 |  |  | 23/09/2026 | 25/09/2026 | 2026-10-08 | 24/08/2026 | 1776 | 1776 |  |  |  | 22/09/2026 | 24/09/2026 | 2026-08-08 | 24/08/2026 | 1776 | 1776
ADIDAS | 0903194315-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 1508 | 15/10/2026 | 1508 | SA | SA30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903194315 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-05-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-05-10 | 2026-08-10 |  |  | 1508 |  | 1508 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1508 |  | 1508 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1508 |  | 1508
ADIDAS | 0903194317-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1167 | 15/10/2026 | 1167 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903194317 IT1828 | 14/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 1167 |  | 1167 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1167 |  | 1167 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1167 |  | 1167
ADIDAS | 0903194318-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 443 | 15/10/2026 | 443 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 672027 | PAD+HT SUB PROCESS_V3 | 0903194318 KA0248 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 443 |  | 443 |  |  | 2026-08-10 | 2026-09-10 |  |  | 443 |  | 443 |  |  | 2026-07-10 | 2026-08-10 |  |  | 443 |  | 443
ADIDAS | 0903194321-1 KA4331 | BLACK | 90D | S2608MR0902 | 239 | 15/10/2026 | 239 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194321 KA4331 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 239 |  | 239 |  |  | 2026-05-10 | 2026-06-10 |  |  | 239 |  | 239 |  |  | 2026-03-10 | 2026-05-10 |  |  | 239 |  | 239
ADIDAS | 0903194323-1 IN8707 | BLACK | 90D | S2408WR1601A | 194 | 15/10/2026 | 194 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903194323 IN8707 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 194 |  | 194 |  |  | 14/10/2026 | 15/10/2026 |  |  | 194 |  | 194 |  |  | 13/10/2026 | 14/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903194325-1 IN1156 | BLACK | 90D | S2408MR1600 | 566 | 15/10/2026 | 566 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903194325 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 566 |  | 566 |  |  | 26/09/2026 | 29/09/2026 |  |  | 566 |  | 566 |  |  | 25/09/2026 | 28/09/2026 |  |  | 566 |  | 566
ADIDAS | 0903194326-1 KA0246 | BLACK | 90D | S2608WR0902 | 377 | 15/10/2026 | 377 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | PAD+HT SUB PROCESS_V3 | 0903194326 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 377 |  | 377 |  |  | 28/09/2026 | 29/09/2026 |  |  | 377 |  | 377 |  |  | 26/09/2026 | 28/09/2026 |  |  | 377 |  | 377
ADIDAS | 0903194330-1 KA0235 | BLACK | 90D | S2608WR0901 | 348 | 15/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194330 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 348 |  | 348 |  |  | 23/10/2026 | 26/10/2026 |  |  | 348 |  | 348 |  |  | 22/10/2026 | 24/10/2026 |  |  | 348 |  | 348
ADIDAS | 0903194331-1 IN1156 | BLACK | 90D | S2408MR1600 | 231 | 15/10/2026 | 231 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516343 | HT SUB PROCESS_V1 | 0903194331 IN1156 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 231 |  | 231 |  |  | 23/09/2026 | 24/09/2026 | 2026-08-09 | 2026-11-09 | 231 | 198 | 33 |  |  | 22/09/2026 | 23/09/2026 | 31/08/2026 | 2026-11-09 | 231 | 198 | 33
ADIDAS | 0903194332-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903194332 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194333-1 IN1172 | BLACK | 90D | S2408WR1600 | 423 | 15/10/2026 | 423 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 516443 | HT SUB PROCESS_V1 | 0903194333 IN1172 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 423 |  | 423 |  |  | 20/10/2026 | 21/10/2026 |  |  | 423 |  | 423 |  |  | 19/10/2026 | 20/10/2026 | 2026-07-09 | 2026-12-09 | 423 | 414 | 9
ADIDAS | 0903194334-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/10/2026 | 200 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903194334 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 22/10/2026 |  |  | 200 |  | 200 |  |  | 20/10/2026 | 21/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903194337-1 IN8707 | BLACK | 90D | S2408WR1601A | 1643 | 23/10/2026 | 1643 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 823016 | HT SUB PROCESS_V1 | 0903194337 IN8707 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 24/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 24/10/2026 | 28/10/2026 |  |  | 1643 |  | 1643 |  |  | 22/10/2026 | 26/10/2026 |  |  | 1643 |  | 1643 |  |  | 21/10/2026 | 24/10/2026 |  |  | 1643 |  | 1643
ADIDAS | 0903194338-1 IN1156 | BLACK | 90D | S2408MR1600 | 697 | 23/10/2026 | 697 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194338 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 697 |  | 697 |  |  | 14/10/2026 | 16/10/2026 |  |  | 697 |  | 697 |  |  | 13/10/2026 | 15/10/2026 |  |  | 697 |  | 697
ADIDAS | 0903194339-1 KA0235 | BLACK | 90D | S2608WR0901 | 229 | 23/10/2026 | 229 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194339 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 229 |  | 229 |  |  | 2026-05-11 | 2026-07-11 |  |  | 229 |  | 229 |  |  | 2026-04-11 | 2026-06-11 |  |  | 229 |  | 229
ADIDAS | 0903194340-1 IN1157 | WHITE | 90D | S2408MR1600 | 375 | 15/10/2026 | 375 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 06-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903194340 IN1157 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 375 |  | 375 |  |  | 29/09/2026 | 30/09/2026 | 2026-10-09 | 2026-11-09 | 375 | 373 | 2 |  |  | 28/09/2026 | 29/09/2026 | 2026-07-09 | 2026-10-09 | 375 | 374 | 1
ADIDAS | 0903194342-1 KA0246 | BLACK | 90D | S2608WR0902 | 106 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | PAD+HT SUB PROCESS_V3 | 0903194342 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194343-1 IN1173 | WHITE | 90D | S2408WR1600 | 613 | 23/10/2026 | 613 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194343 IN1173 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 613 |  | 613 |  |  | 2026-09-10 | 2026-10-10 |  |  | 613 |  | 613 |  |  | 2026-08-10 | 2026-09-10 |  |  | 613 |  | 613
ADIDAS | 0903194344-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 568 | 23/10/2026 | 568 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 804028 | PAD+HT SUB PROCESS_V3 | 0903194344 KA0238 | 14/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-11 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-07-11 | 2026-09-11 |  |  | 568 |  | 568 |  |  | 2026-04-11 | 2026-05-11 |  |  | 568 |  | 568 |  |  | 2026-03-11 | 2026-04-11 |  |  | 568 |  | 568
ADIDAS | 0903194347-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 112 | 23/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 838103 | PAD+HT SUB PROCESS_V3 | 0903194347 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194349-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194349 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 26/10/2026 | 27/10/2026 |  |  | 500 |  | 500 |  |  | 22/10/2026 | 23/10/2026 |  |  | 500 |  | 500 |  |  | 21/10/2026 | 22/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903194351-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194351 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 26/10/2026 | 27/10/2026 |  |  | 500 |  | 500 |  |  | 22/10/2026 | 23/10/2026 |  |  | 500 |  | 500 |  |  | 21/10/2026 | 22/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903194354-1 KA0235 | BLACK | 90D | S2608WR0901 | 518 | 23/10/2026 | 518 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194354 KA0235 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-09-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 518 |  | 518 |  |  | 2026-05-11 | 2026-07-11 |  |  | 518 |  | 518 |  |  | 2026-04-11 | 2026-06-11 |  |  | 518 |  | 518
ADIDAS | 0903194356-1 KG8549 | ONIX | 90D | S2408WR1601A | 264 | 31/10/2026 | 264 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903194356 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 264 |  | 264 |  |  | 29/10/2026 | 30/10/2026 |  |  | 264 |  | 264 |  |  | 28/10/2026 | 29/10/2026 |  |  | 264 |  | 264
ADIDAS | 0903194358-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194358 KX9851 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 102 |  | 102 |  |  | 30/10/2026 | 31/10/2026 |  |  | 102 |  | 102 |  |  | 29/10/2026 | 30/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903194360-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 104 | 31/10/2026 | 104 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194360 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-03-11 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 104 |  | 104 |  |  | 31/10/2026 | 2026-03-11 |  |  | 104 |  | 104 |  |  | 30/10/2026 | 2026-02-11 |  |  | 104 |  | 104
ADIDAS | 0903194361-1 IN1156 | BLACK | 90D | S2408MR1600 | 4002 | 15/10/2026 | 4002 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516438 | HT SUB PROCESS_V1 | 0903194361 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-07-10 |  |  | 4002 |  | 4002 |  |  | 30/09/2026 | 2026-05-10 | 2026-08-09 | 2026-12-09 | 4002 | 3250 | 752 |  |  | 29/09/2026 | 2026-03-10 | 29/08/2026 | 2026-11-09 | 4002 | 3259 | 743
ADIDAS | 0903194363-1 KA0246 | BLACK | 90D | S2608WR0902 | 228 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650034 | PAD+HT SUB PROCESS_V3 | 0903194363 KA0246 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194364-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516404 | HT SUB PROCESS_V1 | 0903194364 IN1172 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 300 |  | 300 |  |  | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 20/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903194365-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 394 | 31/10/2026 | 394 | SA | SA30/06/2026 | G1I | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903194365 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-11 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-10-11 | 2026-12-11 |  |  | 394 |  | 394 |  |  | 2026-06-11 | 2026-09-11 |  |  | 394 |  | 394 |  |  | 2026-05-11 | 2026-07-11 |  |  | 394 |  | 394
ADIDAS | 0903194367-1 KA0235 | BLACK | 90D | S2608WR0901 | 459 | 31/10/2026 | 459 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194367 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 459 |  | 459 |  |  | 2026-11-11 | 13/11/2026 |  |  | 459 |  | 459 |  |  | 2026-10-11 | 2026-12-11 |  |  | 459 |  | 459
ADIDAS | 0903194370-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 543 | 31/10/2026 | 543 | SA | SA30/06/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194370 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-11-11 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 2026-11-11 | 2026-12-11 |  |  | 543 |  | 543 |  |  | 2026-07-11 | 2026-09-11 |  |  | 543 |  | 543 |  |  | 2026-06-11 | 2026-07-11 |  |  | 543 |  | 543
ADIDAS | 0903194372-1 KA0235 | BLACK | 90D | S2608WR0901 | 434 | 31/10/2026 | 434 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194372 KA0235 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 14/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 434 |  | 434 |  |  | 2026-11-11 | 13/11/2026 |  |  | 434 |  | 434 |  |  | 2026-10-11 | 2026-12-11 |  |  | 434 |  | 434
ADIDAS | 0903194375-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 348 | 31/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903194375 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-09-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 348 |  | 348 |  |  | 2026-05-11 | 2026-07-11 |  |  | 348 |  | 348 |  |  | 2026-04-11 | 2026-06-11 |  |  | 348 |  | 348
ADIDAS | 0903194378-1 KG8549 | ONIX | 90D | S2408WR1601A | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903194378 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 120 |  | 120 |  |  | 29/10/2026 | 30/10/2026 |  |  | 120 |  | 120 |  |  | 28/10/2026 | 29/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194380-1 KA0246 | BLACK | 90D | S2608WR0902 | 564 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650036 | PAD+HT SUB PROCESS_V3 | 0903194380 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194383-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 452 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903194383 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903194384-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 450 | 31/10/2026 | 450 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194384 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-09-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 450 |  | 450 |  |  | 2026-05-11 | 2026-07-11 |  |  | 450 |  | 450 |  |  | 2026-04-11 | 2026-06-11 |  |  | 450 |  | 450
ADIDAS | 0903194387-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 330 | 31/10/2026 | 330 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903194387 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 330 |  | 330 |  |  | 30/10/2026 | 31/10/2026 |  |  | 330 |  | 330 |  |  | 29/10/2026 | 30/10/2026 |  |  | 330 |  | 330
ADIDAS | 0903194391-1 IN8707 | BLACK | 90D | S2408WR1601A | 201 | 31/10/2026 | 201 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194391 IN8707 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 201 |  | 201 |  |  | 26/10/2026 | 27/10/2026 |  |  | 201 |  | 201 |  |  | 24/10/2026 | 26/10/2026 |  |  | 201 |  | 201
ADIDAS | 0903194394-1 KG8549 | ONIX | 90D | S2408WR1601A | 144 | 31/10/2026 | 144 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194394 KG8549 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 144 |  | 144 |  |  | 29/10/2026 | 30/10/2026 |  |  | 144 |  | 144 |  |  | 28/10/2026 | 29/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903194397-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 319 | 31/10/2026 | 319 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194397 LD0292 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-09-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 319 |  | 319 |  |  | 2026-05-11 | 2026-07-11 |  |  | 319 |  | 319 |  |  | 2026-04-11 | 2026-06-11 |  |  | 319 |  | 319
ADIDAS | 0903194400-1 KA0246 | BLACK | 90D | S2608WR0902 | 591 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903194400 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903194402-1 KA0235 | BLACK | 90D | S2608WR0901 | 807 | 31/10/2026 | 807 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194402 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 17/11/2026 | 18/11/2026 |  |  | 807 |  | 807 |  |  | 13/11/2026 | 14/11/2026 |  |  | 807 |  | 807 |  |  | 2026-12-11 | 13/11/2026 |  |  | 807 |  | 807
ADIDAS | 0903194405-1 KA4331 | BLACK | 90D | S2608MR0902 | 628 | 31/10/2026 | 628 | SA | SA30/06/2026 | G1G | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194405 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-03-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 628 |  | 628 |  |  | 30/10/2026 | 2026-02-11 |  |  | 628 |  | 628 |  |  | 29/10/2026 | 31/10/2026 |  |  | 628 |  | 628
ADIDAS | 0903194447-1 KA6229 | BLACK | 120D | S2608WR0202 | 1079 | 31/10/2026 | 1079 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194447 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-04-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-04-11 | 2026-07-11 |  |  | 1079 |  | 1079 |  |  | 31/10/2026 | 2026-04-11 |  |  | 1079 |  | 1079 |  |  | 28/10/2026 | 31/10/2026 |  |  | 1079 |  | 1079
ADIDAS | 0903194453-1 KA6229 | BLACK | 120D | S2608WR0202 | 516 | 23/10/2026 | 516 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194453 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 516 |  | 516 |  |  | 23/10/2026 | 26/10/2026 |  |  | 516 |  | 516 |  |  | 20/10/2026 | 22/10/2026 |  |  | 516 |  | 516
ADIDAS | 0903194462-1 KA6229 | BLACK | 120D | S2608WR0202 | 150 | 23/10/2026 | 150 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194462 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 150 |  | 150 |  |  | 23/10/2026 | 26/10/2026 |  |  | 150 |  | 150 |  |  | 20/10/2026 | 22/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903194468-1 KA6229 | BLACK | 120D | S2608WR0202 | 880 | 31/10/2026 | 880 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194468 KA6229 | 28/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 2026-02-11 |  |  | 880 |  | 880 |  |  | 26/10/2026 | 29/10/2026 |  |  | 880 |  | 880 |  |  | 22/10/2026 | 26/10/2026 |  |  | 880 |  | 880
ADIDAS | 0903194475-1 KA6229 | BLACK | 120D | S2608WR0202 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194475 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 631 |  | 631 |  |  | 2026-08-10 | 2026-12-10 |  |  | 631 |  | 631 |  |  | 2026-05-10 | 2026-08-10 | 15/09/2026 | 15/09/2026 | 631 | 303 | 328 |  | 303
ADIDAS | 0903194486-1 KA6229 | BLACK | 120D | S2608WR0202 | 526 | 15/10/2026 | 526 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194486 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 526 |  | 526 |  |  | 2026-08-10 | 2026-12-10 |  |  | 526 |  | 526 |  |  | 2026-05-10 | 2026-08-10 |  |  | 526 |  | 526
ADIDAS | 0903194488-1 KA6229 | BLACK | 120D | S2608WR0202 | 310 | 15/10/2026 | 310 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194488 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 310 |  | 310 |  |  | 2026-12-10 | 13/10/2026 |  |  | 310 |  | 310 |  |  | 2026-08-10 | 2026-09-10 |  |  | 310 |  | 310
ADIDAS | 0903194490-1 KA6229 | BLACK | 120D | S2608WR0202 | 369 | 15/10/2026 | 369 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194490 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 369 |  | 369 |  |  | 2026-12-10 | 13/10/2026 |  |  | 369 |  | 369 |  |  | 2026-08-10 | 2026-09-10 | 14/09/2026 | 14/09/2026 | 369 | 147 | 222
ADIDAS | 0903194492-1 KA6229 | BLACK | 120D | S2608WR0202 | 926 | 2026-07-10 | 926 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194492 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 16/09/2026 | 19/09/2026 |  |  | 926 |  | 926 |  |  | 2026-12-09 | 16/09/2026 |  |  | 926 |  | 926 |  |  | 2026-09-09 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 926 | 689 | 237 |  | 689
ADIDAS | 0903194495-1 KA6229 | BLACK | 120D | S2608WR0202 | 321 | 2026-07-10 | 321 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194495 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 19/09/2026 | 22/09/2026 |  |  | 321 |  | 321 |  |  | 16/09/2026 | 18/09/2026 |  |  | 321 |  | 321 |  |  | 2026-12-09 | 15/09/2026 |  |  | 321 |  | 321
ADIDAS | 0903194496-1 KA6229 | BLACK | 120D | S2608WR0202 | 779 | 15/10/2026 | 779 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194496 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 779 |  | 779 |  |  | 13/10/2026 | 16/10/2026 |  |  | 779 |  | 779 |  |  | 2026-09-10 | 13/10/2026 | 14/09/2026 | 15/09/2026 | 779 | 623 | 156 |  | 226
ADIDAS | 0903194499-1 KA6229 | BLACK | 120D | S2608WR0202 | 346 | 2026-07-10 | 346 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194499 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 19/09/2026 | 22/09/2026 |  |  | 346 |  | 346 |  |  | 16/09/2026 | 18/09/2026 |  |  | 346 |  | 346 |  |  | 2026-12-09 | 15/09/2026 |  |  | 346 |  | 346
ADIDAS | 0903194501-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194501 KA6229 | 28/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 2026-02-11 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903194663-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1069 | 29/09/2026 | 1069 | AN | AN26/06/2026 | G1D | JACKET | G1 | ok | (07/08/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194663 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 17/09/2026 | 2026-10-09 | 15/09/2026 | 1069 | 285 | 784 |  | 1 | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 1069 | 383 | 686
ADIDAS | 0903194835-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 623 | 30/09/2026 | 623 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903194835 KV7863 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 623 |  | 623 |  |  | 26/09/2026 | 28/09/2026 | 2026-10-09 | 15/09/2026 | 623 | 613 | 10 |  | 4
ADIDAS | 0903195508-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 471 | 30/09/2026 | 471 | AN | AN30/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903195508 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 471 |  | 471 |  |  | 18/09/2026 | 19/09/2026 |  |  | 471 |  | 471 |  |  | 17/09/2026 | 18/09/2026 |  |  | 471 |  | 471
ADIDAS | 0903196020-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 891 | 15/10/2026 | 891 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196020 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 891 |  | 891 |  |  | 25/09/2026 | 26/09/2026 |  |  | 891 |  | 891 |  |  | 24/09/2026 | 25/09/2026 |  |  | 891 |  | 891
ADIDAS | 0903196021-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 12 | 15/10/2026 | 12 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196021 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 12 |  | 12 |  |  | 25/09/2026 | 26/09/2026 |  |  | 12 |  | 12 |  |  | 24/09/2026 | 25/09/2026 |  |  | 12 |  | 12
ADIDAS | 0903196022-1 IN1172 | BLACK | 90D | S2408WR1600 | 2616 | 15/10/2026 | 2616 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 823016 | HT SUB PROCESS_V1 | 0903196022 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 28/10/2026 |  |  | 2616 |  | 2616 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2616 |  | 2616 |  |  | 21/10/2026 | 24/10/2026 | 2026-04-09 | 15/09/2026 | 2616 | 2550 | 66 |  | 1
ADIDAS | 0903196023-1 IN1156 | BLACK | 90D | S2408MR1600 | 3287 | 15/10/2026 | 3287 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 823016 | HT SUB PROCESS_V1 | 0903196023 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 2026-02-10 |  |  | 3287 |  | 3287 |  |  | 25/09/2026 | 30/09/2026 |  |  | 3287 |  | 3287 |  |  | 24/09/2026 | 29/09/2026 |  |  | 3287 |  | 3287
ADIDAS | 0903196024-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960006 | HT SUB PROCESS_V1 | 0903196024 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 | 2026-05-09 | 2026-05-09 | 100 | 97 | 3
ADIDAS | 0903196025-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960006 | HT SUB PROCESS_V1 | 0903196025 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 200 |  | 200 |  |  | 23/09/2026 | 24/09/2026 | 2026-09-09 | 2026-11-09 | 200 | 199 | 1 |  |  | 22/09/2026 | 23/09/2026 | 31/08/2026 | 2026-10-09 | 200 | 199 | 1
ADIDAS | 0903196026-1 IN1172 | BLACK | 90D | S2408WR1600 | 134 | 15/10/2026 | 134 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960026 | HT SUB PROCESS_V1 | 0903196026 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 134 |  | 134 |  |  | 19/10/2026 | 20/10/2026 |  |  | 134 |  | 134 |  |  | 17/10/2026 | 19/10/2026 | 2026-05-09 | 2026-12-09 | 134 | 134
ADIDAS | 0903196027-1 IN1156 | BLACK | 90D | S2408MR1600 | 143 | 15/10/2026 | 143 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960026 | HT SUB PROCESS_V1 | 0903196027 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 143 |  | 143 |  |  | 26/09/2026 | 29/09/2026 | 2026-08-09 | 2026-10-09 | 143 | 142 | 1 |  |  | 25/09/2026 | 28/09/2026 | 29/08/2026 | 2026-10-09 | 143 | 142 | 1
ADIDAS | 0903196028-1 IN1156 | BLACK | 90D | S2408MR1600 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 980004 | HT SUB PROCESS_V1 | 0903196028 IN1156 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 631 |  | 631 |  |  | 29/09/2026 | 30/09/2026 |  |  | 631 |  | 631 |  |  | 28/09/2026 | 29/09/2026 |  |  | 631 |  | 631
ADIDAS | 0903196030-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1200 | 15/10/2026 | 1200 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196030 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 1200 |  | 1200 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1200 |  | 1200 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1200 |  | 1200
ADIDAS | 0903196031-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 1200 | 15/10/2026 | 1200 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196031 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 20/10/2026 |  |  | 1200 |  | 1200 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1200 |  | 1200 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903196032-1 IN1157 | WHITE | 90D | S2408MR1600 | 290 | 15/10/2026 | 290 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | (Damco offline). T2 Y.T.I, body & mesh actual receives 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196032 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-02-10 |  |  | 290 |  | 290 |  |  | 30/09/2026 | 30/09/2026 | 2026-09-09 | 2026-12-09 | 290 | 288 | 2 |  |  | 29/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 290 | 288 | 2
ADIDAS | 0903196033-1 IN1156 | BLACK | 90D | S2408MR1600 | 236 | 15/10/2026 | 236 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196033 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 236 |  | 236 |  |  | 26/09/2026 | 29/09/2026 |  |  | 236 |  | 236 |  |  | 25/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 236 | 197 | 39
ADIDAS | 0903196034-1 IN1173 | WHITE | 90D | S2408WR1600 | 114 | 15/10/2026 | 114 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 01-Aug. 688010 | HT SUB PROCESS_V1 | 0903196034 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 114 |  | 114 |  |  | 2026-08-10 | 2026-09-10 | 13/08/2026 | 26/08/2026 | 114 | 114 |  |  |  | 2026-07-10 | 2026-08-10 | 13/08/2026 | 22/08/2026 | 114 | 114
ADIDAS | 0903196035-1 IN1172 | BLACK | 90D | S2408WR1600 | 528 | 15/10/2026 | 528 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196035 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 528 |  | 528 |  |  | 2026-03-10 | 2026-05-10 |  |  | 528 |  | 528 |  |  | 2026-02-10 | 2026-03-10 | 2026-05-09 | 14/09/2026 | 528 | 516 | 12
ADIDAS | 0903196036-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 144 | 15/10/2026 | 144 | SI | SI30/06/2026 | G1H | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196036 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 144 |  | 144 |  |  | 15/10/2026 | 16/10/2026 |  |  | 144 |  | 144 |  |  | 14/10/2026 | 15/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903196037-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196037 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 248 |  | 248 |  |  | 24/09/2026 | 25/09/2026 |  |  | 248 |  | 248 |  |  | 23/09/2026 | 24/09/2026 |  |  | 248 |  | 248
ADIDAS | 0903196038-1 IN1172 | BLACK | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196038 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 138 |  | 138 |  |  | 24/10/2026 | 24/10/2026 |  |  | 138 |  | 138 |  |  | 23/10/2026 | 23/10/2026 |  |  | 138 |  | 138
ADIDAS | 0903196039-1 IN1173 | WHITE | 90D | S2408WR1600 | 142 | 31/10/2026 | 142 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196039 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 142 |  | 142 |  |  | 2026-10-10 | 2026-12-10 |  |  | 142 |  | 142 |  |  | 2026-09-10 | 2026-10-10 |  |  | 142 |  | 142
ADIDAS | 0903196040-1 IN1156 | BLACK | 90D | S2408MR1600 | 496 | 31/10/2026 | 496 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196040 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 496 |  | 496 |  |  | 26/10/2026 | 27/10/2026 |  |  | 496 |  | 496 |  |  | 24/10/2026 | 26/10/2026 |  |  | 496 |  | 496
ADIDAS | 0903197147-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 652 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903197147 KY9391 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197425-1 IN8707 | BLACK | 90D | S2408WR1601A | 156 | 15/10/2026 | 156 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197425 IN8707 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 156 |  | 156 |  |  | 14/10/2026 | 15/10/2026 |  |  | 156 |  | 156 |  |  | 13/10/2026 | 14/10/2026 |  |  | 156 |  | 156
ADIDAS | 0903197427-1 KA0235 | BLACK | 90D | S2608WR0901 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197427 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 27/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 200 |  | 200 |  |  | 23/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 24/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903197429-1 KA0246 | BLACK | 90D | S2608WR0902 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197429 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 28/09/2026 | 29/09/2026 |  |  | 200 |  | 200 |  |  | 26/09/2026 | 28/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903197431-1 IN8707 | BLACK | 90D | S2408WR1601A | 361 | 15/10/2026 | 361 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903197431 IN8707 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 361 |  | 361 |  |  | 14/10/2026 | 15/10/2026 |  |  | 361 |  | 361 |  |  | 13/10/2026 | 14/10/2026 |  |  | 361 |  | 361
ADIDAS | 0903197433-1 KA0246 | BLACK | 90D | S2608WR0902 | 264 | 15/10/2026 | 264 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 688010 | PAD+HT SUB PROCESS_V3 | 0903197433 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 264 |  | 264 |  |  | 28/09/2026 | 29/09/2026 |  |  | 264 |  | 264 |  |  | 26/09/2026 | 28/09/2026 |  |  | 264 |  | 264
ADIDAS | 0903197435-1 KA0235 | BLACK | 90D | S2608WR0901 | 708 | 15/10/2026 | 708 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197435 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 708 |  | 708 |  |  | 30/10/2026 | 2026-02-11 |  |  | 708 |  | 708 |  |  | 29/10/2026 | 31/10/2026 |  |  | 708 |  | 708
ADIDAS | 0903197436-1 KA0246 | BLACK | 90D | S2608WR0902 | 268 | 15/10/2026 | 268 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197436 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 268 |  | 268 |  |  | 29/09/2026 | 30/09/2026 |  |  | 268 |  | 268 |  |  | 28/09/2026 | 29/09/2026 |  |  | 268 |  | 268
ADIDAS | 0903197439-1 KA0235 | BLACK | 90D | S2608WR0901 | 155 | 15/10/2026 | 155 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197439 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 27/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 155 |  | 155 |  |  | 23/10/2026 | 26/10/2026 |  |  | 155 |  | 155 |  |  | 22/10/2026 | 24/10/2026 |  |  | 155 |  | 155
ADIDAS | 0903197440-1 KA4331 | BLACK | 90D | S2608MR0902 | 277 | 15/10/2026 | 277 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197440 KA4331 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 277 |  | 277 |  |  | 2026-05-10 | 2026-06-10 |  |  | 277 |  | 277 |  |  | 2026-03-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903197442-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 335 | 15/10/2026 | 335 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197442 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 335 |  | 335 |  |  | 2026-08-10 | 2026-09-10 |  |  | 335 |  | 335 |  |  | 2026-07-10 | 2026-08-10 |  |  | 335 |  | 335
ADIDAS | 0903197444-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 520 | 15/10/2026 | 520 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 680015 | PAD+HT SUB PROCESS_V3 | 0903197444 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 25/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 520 |  | 520 |  |  | 22/09/2026 | 24/09/2026 |  |  | 520 |  | 520 |  |  | 21/09/2026 | 23/09/2026 |  |  | 520 |  | 520
ADIDAS | 0903197446-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 630 | 15/10/2026 | 630 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197446 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 630 |  | 630 |  |  | 2026-08-10 | 2026-09-10 |  |  | 630 |  | 630 |  |  | 2026-07-10 | 2026-08-10 |  |  | 630 |  | 630
ADIDAS | 0903197448-1 KA0235 | BLACK | 90D | S2608WR0901 | 675 | 15/10/2026 | 675 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197448 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 31/10/2026 | 2026-03-11 |  |  | 675 |  | 675 |  |  | 28/10/2026 | 30/10/2026 |  |  | 675 |  | 675 |  |  | 27/10/2026 | 29/10/2026 |  |  | 675 |  | 675
ADIDAS | 0903197449-1 KA0246 | BLACK | 90D | S2608WR0902 | 547 | 15/10/2026 | 547 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197449 KA0246 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 547 |  | 547 |  |  | 29/09/2026 | 30/09/2026 |  |  | 547 |  | 547 |  |  | 28/09/2026 | 29/09/2026 |  |  | 547 |  | 547
ADIDAS | 0903197451-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197451 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903197453-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 681 | 15/10/2026 | 681 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197453 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 681 |  | 681 |  |  | 22/09/2026 | 24/09/2026 |  |  | 681 |  | 681 |  |  | 21/09/2026 | 23/09/2026 |  |  | 681 |  | 681
ADIDAS | 0903197455-1 KA4331 | BLACK | 90D | S2608MR0902 | 346 | 15/10/2026 | 346 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903197455 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 346 |  | 346 |  |  | 2026-05-10 | 2026-06-10 |  |  | 346 |  | 346 |  |  | 2026-03-10 | 2026-05-10 |  |  | 346 |  | 346
ADIDAS | 0903197456-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 822 | 15/10/2026 | 822 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 659018 | HT SUB PROCESS_V1 | 0903197456 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 822 |  | 822 |  |  | 19/10/2026 | 21/10/2026 |  |  | 822 |  | 822 |  |  | 17/10/2026 | 20/10/2026 |  |  | 822 |  | 822
ADIDAS | 0903197458-1 KA0235 | BLACK | 90D | S2608WR0901 | 999 | 15/10/2026 | 999 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903197458 KA0235 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-05-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-05-11 | 2026-07-11 |  |  | 999 |  | 999 |  |  | 2026-02-11 | 2026-04-11 |  |  | 999 |  | 999 |  |  | 31/10/2026 | 2026-03-11 |  |  | 999 |  | 999
ADIDAS | 0903197459-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 102 | 15/10/2026 | 102 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903197459 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 102 |  | 102 |  |  | 20/10/2026 | 21/10/2026 |  |  | 102 |  | 102 |  |  | 19/10/2026 | 20/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903197461-1 KA0235 | BLACK | 90D | S2608WR0901 | 420 | 15/10/2026 | 420 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903197461 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 29/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 420 |  | 420 |  |  | 26/10/2026 | 28/10/2026 |  |  | 420 |  | 420 |  |  | 24/10/2026 | 27/10/2026 |  |  | 420 |  | 420
ADIDAS | 0903197465-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 307 | 15/10/2026 | 307 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903197465 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-10 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 2026-12-10 | 2026-12-10 |  |  | 307 |  | 307 |  |  | 2026-08-10 | 2026-08-10 |  |  | 307 |  | 307 |  |  | 2026-07-10 | 2026-07-10 |  |  | 307 |  | 307
ADIDAS | 0903197467-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 478 | 15/10/2026 | 478 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 659018 | PAD+HT SUB PROCESS_V3 | 0903197467 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 21/09/2026 | 23/09/2026 |  |  | 478 |  | 478 |  |  | 17/09/2026 | 19/09/2026 |  |  | 478 |  | 478 |  |  | 16/09/2026 | 18/09/2026 |  |  | 478 |  | 478
ADIDAS | 0903197472-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 408 | 15/10/2026 | 408 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197472 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 408 |  | 408 |  |  | 20/10/2026 | 21/10/2026 |  |  | 408 |  | 408 |  |  | 19/10/2026 | 20/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903197475-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 498 | 15/10/2026 | 498 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197475 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 498 |  | 498 |  |  | 2026-03-10 | 2026-06-10 |  |  | 498 |  | 498 |  |  | 2026-02-10 | 2026-05-10 |  |  | 498 |  | 498
ADIDAS | 0903197478-1 KA4331 | BLACK | 90D | S2608MR0902 | 18 | 15/10/2026 | 18 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197478 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 18 |  | 18 |  |  | 19/09/2026 | 22/09/2026 |  |  | 18 |  | 18 |  |  | 18/09/2026 | 21/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903197480-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 530 | 15/10/2026 | 530 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197480 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-09-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 530 |  | 530 |  |  | 2026-06-10 | 2026-08-10 |  |  | 530 |  | 530 |  |  | 2026-05-10 | 2026-07-10 |  |  | 530 |  | 530
ADIDAS | 0903197482-1 KA0235 | BLACK | 90D | S2608WR0901 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903197482 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 27/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197484-1 KA0246 | BLACK | 90D | S2608WR0902 | 611 | 15/10/2026 | 611 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650010 | PAD+HT SUB PROCESS_V3 | 0903197484 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 611 |  | 611 |  |  | 2026-05-10 | 2026-06-10 |  |  | 611 |  | 611 |  |  | 2026-03-10 | 2026-05-10 |  |  | 611 |  | 611
ADIDAS | 0903197486-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 544 | 15/10/2026 | 544 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197486 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 544 |  | 544 |  |  | 2026-03-10 | 2026-06-10 |  |  | 544 |  | 544 |  |  | 2026-02-10 | 2026-05-10 |  |  | 544 |  | 544
ADIDAS | 0903197487-1 KA0235 | BLACK | 90D | S2608WR0901 | 106 | 15/10/2026 | 106 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197487 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 31/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 31/10/2026 | 2026-03-11 |  |  | 106 |  | 106 |  |  | 28/10/2026 | 30/10/2026 |  |  | 106 |  | 106 |  |  | 27/10/2026 | 29/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903197489-1 KA0246 | BLACK | 90D | S2608WR0902 | 204 | 15/10/2026 | 204 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 834012 | PAD+HT SUB PROCESS_V3 | 0903197489 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 204 |  | 204 |  |  | 30/09/2026 | 2026-02-10 |  |  | 204 |  | 204 |  |  | 29/09/2026 | 2026-01-10 |  |  | 204 |  | 204
ADIDAS | 0903197490-1 KA4331 | BLACK | 90D | S2608MR0902 | 790 | 15/10/2026 | 790 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197490 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 790 |  | 790 |  |  | 19/09/2026 | 22/09/2026 |  |  | 790 |  | 790 |  |  | 18/09/2026 | 21/09/2026 |  |  | 790 |  | 790
ADIDAS | 0903197491-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 118 | 15/10/2026 | 118 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197491 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 21/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 21/09/2026 | 23/09/2026 |  |  | 118 |  | 118 |  |  | 17/09/2026 | 19/09/2026 |  |  | 118 |  | 118 |  |  | 16/09/2026 | 18/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903197494-1 KA0246 | BLACK | 90D | S2608WR0902 | 772 | 15/10/2026 | 772 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197494 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 772 |  | 772 |  |  | 30/09/2026 | 2026-02-10 |  |  | 772 |  | 772 |  |  | 29/09/2026 | 2026-01-10 |  |  | 772 |  | 772
ADIDAS | 0903197496-1 KA0235 | BLACK | 90D | S2608WR0901 | 6000 | 15/10/2026 | 6000 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197496 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 27/10/2026 | 2026-06-11 |  |  | 6000 |  | 6000 |  |  | 23/10/2026 | 2026-03-11 |  |  | 6000 |  | 6000 |  |  | 22/10/2026 | 2026-02-11 |  |  | 6000 |  | 6000
ADIDAS | 0903197498-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 636 | 15/10/2026 | 636 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197498 KA0238 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 636 |  | 636 |  |  | 2026-09-10 | 2026-10-10 |  |  | 636 |  | 636 |  |  | 2026-08-10 | 2026-09-10 |  |  | 636 |  | 636
ADIDAS | 0903197499-1 KA0235 | BLACK | 90D | S2608WR0901 | 1428 | 15/10/2026 | 1428 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197499 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 1428 |  | 1428 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1428 |  | 1428 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1428 |  | 1428
ADIDAS | 0903197500-1 KA4331 | BLACK | 90D | S2608MR0902 | 1450 | 15/10/2026 | 1450 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197500 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 2026-01-10 |  |  | 1450 |  | 1450 |  |  | 24/09/2026 | 28/09/2026 |  |  | 1450 |  | 1450 |  |  | 23/09/2026 | 26/09/2026 |  |  | 1450 |  | 1450
ADIDAS | 0903197502-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 653 | 15/10/2026 | 653 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197502 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 21/09/2026 | 23/09/2026 |  |  | 653 |  | 653 |  |  | 17/09/2026 | 19/09/2026 |  |  | 653 |  | 653 |  |  | 16/09/2026 | 18/09/2026 |  |  | 653 |  | 653
ADIDAS | 0903197745-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 1860 | 31/10/2026 | 1860 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197745 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-03-11 | 2026-10-11 |  |  | 1860 |  | 1860 |  |  | 30/10/2026 | 2026-06-11 |  |  | 1860 |  | 1860 |  |  | 27/10/2026 | 2026-03-11 |  |  | 1860 |  | 1860
ADIDAS | 0903197746-1 JZ7711 | BLACK | 120D | S2608MR0202 | 3000 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197746 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197760-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 600 | 15/10/2026 | 600 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903197760 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-10-10 | 14/10/2026 |  |  | 600 |  | 600 |  |  | 2026-07-10 | 2026-10-10 |  |  | 600 |  | 600 |  |  | 2026-06-10 | 2026-09-10 |  |  | 600 |  | 600
ADIDAS | 0903197762-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 778 | 15/10/2026 | 778 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (25/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197762 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-10-10 | 14/10/2026 |  |  | 778 |  | 778 |  |  | 2026-07-10 | 2026-10-10 |  |  | 778 |  | 778 |  |  | 2026-06-10 | 2026-09-10 |  |  | 778 |  | 778
ADIDAS | 0903197769-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 1700 | 15/10/2026 | 1700 | SI | SI30/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197769 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 1700 |  | 1700 |  |  | 2026-08-10 | 2026-12-10 |  |  | 1700 |  | 1700 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1700 |  | 1700
ADIDAS | 0903197773-1 KE9656 | BLACK | 105D | S2608WR0201A | 7617 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903197773 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903197775-1 KE9656 | BLACK | 105D | S2608WR0201A | 322 | 15/10/2026 | 322 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 27-Jul. 600000 | PAD+HT SUB PROCESS_V3 | 0903197775 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 322 |  | 322 |  |  | 13/10/2026 | 13/10/2026 |  |  | 322 |  | 322 |  |  | 2026-12-10 | 2026-12-10 |  |  | 322 |  | 322
ADIDAS | 0903197777-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 2329 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197777 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197785-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1015 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197785 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197798-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 527 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197798 KY9391 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197807-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 341 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197807 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197811-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 249 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197811 KY9391 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197815-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 390 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197815 KY9393 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197818-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1039 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516267 | PAD+HT SUB PROCESS_V3 | 0903197818 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197829-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 445 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197829 KY9385 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903197840-1 JZ7711 | BLACK | 120D | S2608MR0202 | 615 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197840 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197849-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197849 KY9384 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903197853-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1291 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197853 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197856-1 JZ7711 | BLACK | 120D | S2608MR0202 | 330 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197856 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197859-1 JZ7711 | BLACK | 120D | S2608MR0202 | 601 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197859 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197863-1 JZ7711 | BLACK | 120D | S2608MR0202 | 366 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197863 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197870-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197870 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903197872-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 695 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197872 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903197875-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516403 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197875 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197879-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 408 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197879 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197886-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1556 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903197886 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197889-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 816 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197889 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903201074-1 JZ7711 | BLACK | 120D | S2608MR0202 | 211 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201074 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903201075-1 JZ7711 | BLACK | 120D | S2608MR0202 | 102 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201075 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903203165-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 251 | 31/10/2026 |  | SI | SI29/05/2026 |  | SHORTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903203165 LF0725 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903203168-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 186 | 2026-05-09 | 186 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203168 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 186 | 186 |  |  |  | 2026-03-08 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 186 | 186
ADIDAS | 0903203169-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 425 | 30/09/2026 | 425 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok |  | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903203169 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 425 |  | 425 |  |  | 26/09/2026 | 28/09/2026 |  |  | 425 |  | 425
ADIDAS | 0903203170-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 240 | 15/09/2026 | 240 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203170 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-07-09 | 2026-10-09 | 240 | 240 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 14/09/2026 | 240 | 240 |  |  |  | 27/08/2026 | 2026-02-09 | 28/07/2026 | 15/09/2026 | 240 | 240 |  |  | 10
ADIDAS | 0903203171-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 347 | 15/10/2026 | 347 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203171 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 347 |  | 347 |  |  | 2026-12-10 | 13/10/2026 |  |  | 347 |  | 347 |  |  | 2026-06-10 | 2026-07-10 |  |  | 347 |  | 347
ADIDAS | 0903205276-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516403 | HT SUB PROCESS_V1 | 0903205276 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 21/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 18/09/2026 | 13/08/2026 | 26/08/2026 | 300 | 300 |  |  |  | 17/09/2026 | 17/09/2026 | 13/08/2026 | 24/08/2026 | 300 | 300
ADIDAS | 0903208394-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 152 | 2026-12-09 | 152 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 10/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516342 | HT SUB PROCESS_V1 | 0903208394 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-01-09 | 2026-04-09 | 2026-04-09 | 2026-10-09 | 152 | 152 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 21/08/2026 | 152 | 152 |  |  |  | 28/08/2026 | 2026-01-09 | 13/08/2026 | 20/08/2026 | 152 | 152
ADIDAS | 0903208396-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 459 | 23/09/2026 | 459 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208396 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 17/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 17/09/2026 | 17/09/2026 |  |  | 459 |  | 459 |  |  | 15/09/2026 | 15/09/2026 | 19/08/2026 | 2026-01-09 | 459 | 458 | 1 |  |  | 14/09/2026 | 14/09/2026 | 18/08/2026 | 2026-01-09 | 459 | 458 | 1
ADIDAS | 0903208397-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 494 | 15/10/2026 | 494 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903208397 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 494 |  | 494 |  |  | 24/10/2026 | 24/10/2026 | 19/08/2026 | 2026-12-09 | 494 | 490 | 4 |  |  | 23/10/2026 | 23/10/2026 | 18/08/2026 | 2026-02-09 | 494 | 490 | 4
ADIDAS | 0903208398-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 13 | 2026-02-10 | 13 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208398 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-05-10 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-05-10 | 2026-05-10 |  |  | 13 |  | 13 |  |  | 2026-02-10 | 2026-02-10 |  |  | 13 |  | 13 |  |  | 2026-01-10 | 2026-01-10 |  |  | 13 |  | 13
ADIDAS | 0903208399-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 80 | 31/10/2026 | 80 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208399 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-11 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-03-11 | 2026-04-11 |  |  | 80 |  | 80 |  |  | 31/10/2026 | 2026-02-11 |  |  | 80 |  | 80 |  |  | 30/10/2026 | 31/10/2026 |  |  | 80 |  | 80
ADIDAS | 0903208400-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1268 | 31/10/2026 | 1268 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208400 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-04-11 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-04-11 | 2026-06-11 |  |  | 1268 |  | 1268 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1268 |  | 1268 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1268 |  | 1268
ADIDAS | 0903208407-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 302 | 30/09/2026 | 302 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903208407 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 302 |  | 302 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 15/09/2026 | 302 | 296 | 6 |  | 28 | 17/09/2026 | 18/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 296 | 6
ADIDAS | 0903208408-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 597 | 30/09/2026 | 597 | SA | SA03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903208408 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 597 |  | 597 |  |  | 26/09/2026 | 28/09/2026 | 2026-08-09 | 15/09/2026 | 597 | 595 | 2 |  | 7 | 25/09/2026 | 26/09/2026 | 2026-08-09 | 14/09/2026 | 597 | 596 | 1
ADIDAS | 0903208410-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 361 | 2026-07-10 | 361 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516443 | HT SUB PROCESS_V1 | 0903208410 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 23/09/2026 |  |  | 361 |  | 361 |  |  | 19/09/2026 | 21/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 356 | 5 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 358 | 3
ADIDAS | 0903208411-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1107 | 15/10/2026 | 1107 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 678002 | HT SUB PROCESS_V1 | 0903208411 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 1107 |  | 1107 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1107 |  | 1107 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1107 |  | 1107
ADIDAS | 0903208412-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1026 | 15/10/2026 | 1026 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug.. 834012 | HT SUB PROCESS_V1 | 0903208412 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 1026 |  | 1026 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1026 |  | 1026 |  |  | 22/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903208413-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 266 | 15/10/2026 | 266 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, body & mesh actual receives 12-Aug. 688010 | HT SUB PROCESS_V1 | 0903208413 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 266 |  | 266 |  |  | 2026-08-10 | 2026-09-10 |  |  | 266 |  | 266 |  |  | 2026-07-10 | 2026-08-10 |  |  | 266 |  | 266
ADIDAS | 0903208414-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 415 | 14/10/2026 | 415 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903208414 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 415 |  | 415 |  |  | 24/09/2026 | 25/09/2026 |  |  | 415 |  | 415 |  |  | 23/09/2026 | 24/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903208415-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 138 | 31/10/2026 | 138 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650031 | HT SUB PROCESS_V1 | 0903208415 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-11 | ADIZERO E TEE |  | SS27-YTI | 2026-05-11 | 2026-06-11 |  |  | 138 |  | 138 |  |  | 2026-03-11 | 2026-04-11 |  |  | 138 |  | 138 |  |  | 2026-02-11 | 2026-03-11 |  |  | 138 |  | 138
ADIDAS | 0903208416-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 143 | 31/10/2026 | 143 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Airowes). T2 Y.T.I, body & mesh actual receives 12-Aug. 650034 | HT SUB PROCESS_V1 | 0903208416 IT1469 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-05-11 | ADIZERO E TEE |  | SS27-YTI | 2026-05-11 | 2026-06-11 |  |  | 143 |  | 143 |  |  | 2026-03-11 | 2026-04-11 |  |  | 143 |  | 143 |  |  | 2026-02-11 | 2026-03-11 |  |  | 143 |  | 143
ADIDAS | 0903208419-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903208419 KG8548 | 17/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/08/2026 | ADIZERO E TEE |  | SS27-YTI | 27/08/2026 | 2026-01-09 | 27/08/2026 | 2026-01-09 | 300 | 300 |  |  |  | 24/08/2026 | 29/08/2026 | 2026-12-08 | 21/08/2026 | 300 | 300 |  |  |  | 21/08/2026 | 28/08/2026 | 2026-11-08 | 21/08/2026 | 300 | 300
ADIDAS | 0903208420-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 301 | 2026-09-09 | 301 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208420 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-12-08 | 2026-12-08 | 301 | 301 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-11-08 | 20/08/2026 | 301 | 301
ADIDAS | 0903208421-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208421 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-01-09 | 31/08/2026 | 2026-04-09 | 300 | 300 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-10-08 | 2026-12-08 | 300 | 300 |  |  |  | 26/08/2026 | 28/08/2026 | 2026-08-08 | 2026-11-08 | 300 | 300
ADIDAS | 0903208423-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 244 | 30/09/2026 | 244 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 516342 | HT SUB PROCESS_V1 | 0903208423 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 21/09/2026 | 2026-01-09 | 2026-07-09 | 244 | 239 | 5 |  |  | 27/08/2026 | 18/09/2026 | 2026-10-08 | 2026-12-08 | 244 | 244 |  |  |  | 26/08/2026 | 17/09/2026 | 2026-08-08 | 2026-11-08 | 244 | 244
ADIDAS | 0903208424-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 176 | 2026-07-10 | 176 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 814006 | HT SUB PROCESS_V1 | 0903208424 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 176 |  | 176 |  |  | 15/10/2026 | 16/10/2026 | 2026-12-08 | 26/08/2026 | 176 | 176 |  |  |  | 14/10/2026 | 15/10/2026 | 2026-11-08 | 24/08/2026 | 176 | 176
ADIDAS | 0903208425-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 220 | 2026-07-10 | 220 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 838103 | HT SUB PROCESS_V1 | 0903208425 KG8548 | 17/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 220 |  | 220 |  |  | 15/10/2026 | 16/10/2026 | 2026-11-08 | 2026-01-09 | 220 | 220 |  |  |  | 14/10/2026 | 15/10/2026 | 2026-10-08 | 31/08/2026 | 220 | 220
ADIDAS | 0903208426-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 616 | 15/10/2026 | 616 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 800187 | HT SUB PROCESS_V1 | 0903208426 KG8548 | 17/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 616 |  | 616 |  |  | 2026-08-10 | 2026-10-10 | 14/08/2026 | 2026-02-09 | 616 | 616 |  |  |  | 2026-07-10 | 2026-09-10 | 13/08/2026 | 2026-02-09 | 616 | 616
ADIDAS | 0903208427-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 839055 | HT SUB PROCESS_V1 | 0903208427 KG8548 | 17/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 248 |  | 248 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 26/08/2026 | 248 | 248 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 24/08/2026 | 248 | 248
ADIDAS | 0903208428-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 2070 | 15/10/2026 | 2070 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 678002 | HT SUB PROCESS_V1 | 0903208428 KG8548 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 30/10/2026 |  |  | 2070 |  | 2070 |  |  | 24/10/2026 | 28/10/2026 |  |  | 2070 |  | 2070 |  |  | 23/10/2026 | 27/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903208429-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 466 | 23/09/2026 | 466 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 680015 | HT SUB PROCESS_V1 | 0903208429 KG8548 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 21/09/2026 |  |  | 466 |  | 466 |  |  | 18/09/2026 | 18/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 465 | 1 |  |  | 17/09/2026 | 17/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 466
ADIDAS | 0903208430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 648 | 15/10/2026 | 648 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208430 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 648 |  | 648 |  |  | 2026-08-10 | 2026-10-10 | 13/08/2026 | 14/09/2026 | 648 | 648 |  |  |  | 2026-07-10 | 2026-09-10 | 13/08/2026 | 2026-03-09 | 648 | 648
ADIDAS | 0903208431-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 424 | 15/10/2026 | 424 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, Body & mesh actual receives 05-Aug. s650010 | HT SUB PROCESS_V1 | 0903208431 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 19/10/2026 |  |  | 424 |  | 424 |  |  | 16/10/2026 | 16/10/2026 | 2026-12-08 | 27/08/2026 | 424 | 424 |  |  |  | 15/10/2026 | 15/10/2026 | 2026-12-08 | 26/08/2026 | 424 | 424
ADIDAS | 0903208432-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 550 | 2026-12-09 | 550 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (PODD Improvement Request). T2 Y.T.I, body & mesh actual receives 18-Aug. 688010 | HT SUB PROCESS_V1 | 0903208432 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/08/2026 | ADIZERO E TEE |  | SS27-YTI | 26/08/2026 | 29/08/2026 | 26/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 21/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 20/08/2026 | 26/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903208433-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 240 | 15/10/2026 | 240 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 05-Aug. 688010 | HT SUB PROCESS_V1 | 0903208433 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 240 |  | 240 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 22/08/2026 | 240 | 240 |  |  |  | 2026-07-10 | 2026-09-10 | 15/08/2026 | 22/08/2026 | 240 | 240
ADIDAS | 0903208434-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 472 | 14/10/2026 | 472 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208434 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 15/10/2026 |  |  | 472 |  | 472 |  |  | 13/10/2026 | 13/10/2026 | 18/08/2026 | 29/08/2026 | 472 | 470 | 2 |  |  | 2026-12-10 | 2026-12-10 | 15/08/2026 | 28/08/2026 | 472 | 472
ADIDAS | 0903208435-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1324 | 15/10/2026 | 1324 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 814006 | HT SUB PROCESS_V1 | 0903208435 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 1324 |  | 1324 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1324 |  | 1324 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1324 |  | 1324
ADIDAS | 0903208436-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 102 | 31/10/2026 | 102 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208436 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 102 |  | 102 |  |  | 2026-04-11 | 2026-04-11 |  |  | 102 |  | 102 |  |  | 2026-03-11 | 2026-03-11 |  |  | 102 |  | 102
ADIDAS | 0903208437-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 163 | 31/10/2026 | 163 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208437 KG8548 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 163 |  | 163 |  |  | 2026-04-11 | 2026-04-11 |  |  | 163 |  | 163 |  |  | 2026-03-11 | 2026-03-11 |  |  | 163 |  | 163
ADIDAS | 0903208440-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 456 | 15/10/2026 | 456 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 678002 | HT SUB PROCESS_V1 | 0903208440 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 456 |  | 456 |  |  | 2026-05-10 | 2026-06-10 | 24/08/2026 | 2026-04-09 | 456 | 456 |  |  |  | 2026-03-10 | 2026-05-10 | 24/08/2026 | 2026-04-09 | 456 | 456
ADIDAS | 0903208441-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 459 | 15/10/2026 | 459 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 07-Aug. 650010 | HT SUB PROCESS_V1 | 0903208441 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 459 |  | 459 |  |  | 2026-03-10 | 2026-05-10 | 28/08/2026 | 13/09/2026 | 459 | 459 |  |  |  | 2026-02-10 | 2026-03-10 | 26/08/2026 | 2026-03-09 | 459 | 459
ADIDAS | 0903208442-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 518 | 15/10/2026 | 518 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 688010 | HT SUB PROCESS_V1 | 0903208442 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 518 |  | 518 |  |  | 2026-05-10 | 2026-06-10 |  |  | 518 |  | 518 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 14/09/2026 | 518 | 517 | 1
ADIDAS | 0903208443-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 653 | 14/10/2026 | 653 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 684009 | HT SUB PROCESS_V1 | 0903208443 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 653 |  | 653 |  |  | 2026-02-10 | 2026-03-10 |  |  | 653 |  | 653 |  |  | 2026-01-10 | 2026-02-10 | 28/08/2026 | 2026-03-09 | 653 | 653
ADIDAS | 0903208444-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 102 | 31/10/2026 | 102 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208444 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 102 |  | 102 |  |  | 2026-04-11 | 2026-04-11 |  |  | 102 |  | 102 |  |  | 2026-03-11 | 2026-03-11 |  |  | 102 |  | 102
ADIDAS | 0903208445-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 136 | 31/10/2026 | 136 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208445 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 136 |  | 136 |  |  | 2026-04-11 | 2026-04-11 |  |  | 136 |  | 136 |  |  | 2026-03-11 | 2026-03-11 |  |  | 136 |  | 136
ADIDAS | 0903209735-1 KT4840 | ONIX | 90D | S2408MR1600 | 1046 | 14/10/2026 | 1046 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 684009 | HT SUB PROCESS_V1 | 0903209735 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 1046 |  | 1046 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1046 |  | 1046 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1046 |  | 1046
ADIDAS | 0903209736-1 KT4840 | ONIX | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug. 650010 | HT SUB PROCESS_V1 | 0903209736 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903209737-1 KT4840 | ONIX | 90D | S2408MR1600 | 2722 | 15/10/2026 | 2722 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, Body: PI Date 21-Sep (2380 yd). Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug, ETD ?? Waiting fabric. T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug (480 yd). 678002 | HT SUB PROCESS_V1 | 0903209737 KT4840 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 22/10/2026 |  |  | 2722 |  | 2722 |  |  | 16/10/2026 | 20/10/2026 |  |  | 2722 |  | 2722 |  |  | 15/10/2026 | 19/10/2026 |  |  | 2722 |  | 2722
ADIDAS | 0903209739-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 15/09/2026 | 324 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903209739 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 15/09/2026 | 324 | 324 |  |  | 2 | 29/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 324 | 324 |  |  |  | 28/08/2026 | 29/08/2026 | 22/08/2026 | 2026-11-09 | 324 | 324
ADIDAS | 0903209741-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 30/09/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209741 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 21/09/2026 | 2026-05-09 | 15/09/2026 | 300 | 221 | 79 |  | 15 | 29/08/2026 | 18/09/2026 | 24/08/2026 | 2026-03-09 | 300 | 300 |  |  |  | 28/08/2026 | 17/09/2026 | 22/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0903209742-1 IN1156 | BLACK | 90D | S2408MR1600 | 319 | 30/09/2026 | 319 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516443 | HT SUB PROCESS_V1 | 0903209742 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 21/09/2026 | 2026-05-09 | 15/09/2026 | 319 | 319 |  |  | 7 | 29/08/2026 | 18/09/2026 | 24/08/2026 | 2026-03-09 | 319 | 319 |  |  |  | 28/08/2026 | 17/09/2026 | 22/08/2026 | 2026-08-09 | 319 | 319
ADIDAS | 0903209744-1 IN1156 | BLACK | 90D | S2408MR1600 | 3278 | 15/10/2026 | 3278 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209744 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 27/10/2026 |  |  | 3278 |  | 3278 |  |  | 20/10/2026 | 24/10/2026 |  |  | 3278 |  | 3278 |  |  | 19/10/2026 | 23/10/2026 |  |  | 3278 |  | 3278
ADIDAS | 0903209745-1 IN1156 | BLACK | 90D | S2408MR1600 | 145 | 23/09/2026 | 145 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209745 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 |  |  | 145 |  | 145 |  |  | 2026-12-09 | 18/09/2026 |  |  | 145 |  | 145 |  |  | 2026-11-09 | 17/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903209746-1 IN1156 | BLACK | 90D | S2408MR1600 | 726 | 15/10/2026 | 726 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209746 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 726 |  | 726 |  |  | 29/09/2026 | 30/09/2026 |  |  | 726 |  | 726 |  |  | 28/09/2026 | 29/09/2026 |  |  | 726 |  | 726
ADIDAS | 0903209747-1 IN1156 | BLACK | 90D | S2408MR1600 | 6000 | 15/10/2026 | 6000 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209747 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 23/10/2026 |  |  | 6000 |  | 6000 |  |  | 14/10/2026 | 21/10/2026 |  |  | 6000 |  | 6000 |  |  | 13/10/2026 | 20/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903209748-1 IN1156 | BLACK | 90D | S2408MR1600 | 1095 | 15/10/2026 | 1095 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209748 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-07-10 |  |  | 1095 |  | 1095 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1095 |  | 1095 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1095 |  | 1095
ADIDAS | 0903209749-1 IN1156 | BLACK | 90D | S2408MR1600 | 1353 | 15/10/2026 | 1353 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903209749 IN1156 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 1353 |  | 1353 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1353 |  | 1353 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1353 |  | 1353
ADIDAS | 0903209750-1 IN1156 | BLACK | 90D | S2408MR1600 | 1119 | 15/10/2026 | 1119 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209750 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-05-10 |  |  | 1119 |  | 1119 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1119 |  | 1119 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1119 |  | 1119
ADIDAS | 0903209751-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903209751 IN1156 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903209752-1 IN1156 | BLACK | 90D | S2408MR1600 | 1969 | 31/10/2026 | 1969 | SA | SA07/07/2026 | G1O | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209752 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 16/11/2026 | ADIZERO E TEE |  | SS27-YTI | 16/11/2026 | 18/11/2026 |  |  | 1969 |  | 1969 |  |  | 13/11/2026 | 16/11/2026 |  |  | 1969 |  | 1969 |  |  | 2026-12-11 | 14/11/2026 |  |  | 1969 |  | 1969
ADIDAS | 0903209755-1 IN1157 | WHITE | 90D | S2408MR1600 | 2425 | 15/10/2026 | 2425 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209755 IN1157 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-08-10 |  |  | 2425 |  | 2425 |  |  | 2026-02-10 | 2026-06-10 |  |  | 2425 |  | 2425 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2425 |  | 2425
ADIDAS | 0903209756-1 IN1157 | WHITE | 90D | S2408MR1600 | 310 | 15/10/2026 | 310 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Far Eastern, PI Date 21-Sep, actual recieves 06-Aug (using fabric from Y.T.I.) T2 Y.T.I, Mesh: ETD 10-Jul, actual recieves 06-Aug. 650010 | HT SUB PROCESS_V1 | 0903209756 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-02-10 |  |  | 310 |  | 310 |  |  | 30/09/2026 | 30/09/2026 | 2026-10-09 | 2026-12-09 | 310 | 302 | 8 |  |  | 29/09/2026 | 29/09/2026 | 2026-03-09 | 2026-08-09 | 310 | 302 | 8
ADIDAS | 0903209757-1 IN1157 | WHITE | 90D | S2408MR1600 | 8000 | 30/09/2026 | 8000 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric (Damco offline). T2 Far Eastern, Body: PI Date 21-Sep (1389 yd). Waiting fabric. T2 Y.T.I, body&mesh ETD 10-Jul, ETA-Kaha 08-Aug (body: 6202yd). 688010 | HT SUB PROCESS_V1 | 0903209757 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 2026-01-10 |  |  | 8000 |  | 8000 |  |  | 19/09/2026 | 29/09/2026 |  |  | 8000 |  | 8000 |  |  | 18/09/2026 | 28/09/2026 |  |  | 8000 |  | 8000
ADIDAS | 0903209758-1 IN1157 | WHITE | 90D | S2408MR1600 | 1268 | 14/10/2026 | 1268 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903209758 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 2026-01-10 |  |  | 1268 |  | 1268 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1268 |  | 1268 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903209760-1 IN1172 | BLACK | 90D | S2408WR1600 | 302 | 15/09/2026 | 302 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516406 | HT SUB PROCESS_V1 | 0903209760 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 2026-07-09 | 302 | 302 |  |  |  | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-09-09 | 302 | 302 |  |  |  | 28/08/2026 | 29/08/2026 | 29/08/2026 | 2026-05-09 | 302 | 302
ADIDAS | 0903209762-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209762 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 16/09/2026 | 27/08/2026 | 28/08/2026 | 300 | 300 |  |  |  | 14/09/2026 | 15/09/2026 | 26/08/2026 | 28/08/2026 | 300 | 300
ADIDAS | 0903209764-1 IN1172 | BLACK | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516254 | HT SUB PROCESS_V1 | 0903209764 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 349 |  | 349 |  |  | 19/10/2026 | 20/10/2026 |  |  | 349 |  | 349 |  |  | 17/10/2026 | 19/10/2026 |  |  | 349 |  | 349
ADIDAS | 0903209765-1 IN1172 | BLACK | 90D | S2408WR1600 | 2646 | 15/10/2026 | 2646 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209765 IN1172 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 27/10/2026 |  |  | 2646 |  | 2646 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2646 |  | 2646 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2646 |  | 2646
ADIDAS | 0903209766-1 IN1172 | BLACK | 90D | S2408WR1600 | 428 | 15/10/2026 | 428 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 672027 | HT SUB PROCESS_V1 | 0903209766 IN1172 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 428 |  | 428 |  |  | 19/10/2026 | 20/10/2026 |  |  | 428 |  | 428 |  |  | 17/10/2026 | 19/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903209767-1 IN1172 | BLACK | 90D | S2408WR1600 | 945 | 15/10/2026 | 945 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 680015 | HT SUB PROCESS_V1 | 0903209767 IN1172 |  | KAHATEX CIJERAH | CHILE | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 945 |  | 945 |  |  | 20/10/2026 | 21/10/2026 |  |  | 945 |  | 945 |  |  | 19/10/2026 | 20/10/2026 |  |  | 945 |  | 945
ADIDAS | 0903209768-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 15/10/2026 | 760 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209768 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 760 |  | 760 |  |  | 17/10/2026 | 19/10/2026 |  |  | 760 |  | 760 |  |  | 16/10/2026 | 17/10/2026 |  |  | 760 |  | 760
ADIDAS | 0903209769-1 IN1172 | BLACK | 90D | S2408WR1600 | 677 | 14/10/2026 | 677 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT SUB PROCESS_V1 | 0903209769 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 677 |  | 677 |  |  | 17/10/2026 | 19/10/2026 |  |  | 677 |  | 677 |  |  | 16/10/2026 | 17/10/2026 |  |  | 677 |  | 677
ADIDAS | 0903209770-1 IN1172 | BLACK | 90D | S2408WR1600 | 400 | 23/10/2026 | 400 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | 516205 | HT SUB PROCESS_V1 | 0903209770 IN1172 |  | KAHATEX CIJERAH | SPAIN | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 24/10/2026 |  |  | 400 |  | 400 |  |  | 22/10/2026 | 22/10/2026 |  |  | 400 |  | 400 |  |  | 21/10/2026 | 21/10/2026 |  |  | 400 |  | 400
ADIDAS | 0903209777-1 KG8547 | ONIX | 90D | S2408WR1600 | 319 | 31/10/2026 | 319 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Airowes). 650034 | HT SUB PROCESS_V1 | 0903209777 KG8547 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 319 |  | 319 |  |  | 30/10/2026 | 31/10/2026 |  |  | 319 |  | 319 |  |  | 29/10/2026 | 30/10/2026 |  |  | 319 |  | 319
ADIDAS | 0903209778-1 KG8547 | ONIX | 90D | S2408WR1600 | 150 | 31/10/2026 | 150 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650031 | HT SUB PROCESS_V1 | 0903209778 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 150 |  | 150 |  |  | 30/10/2026 | 31/10/2026 |  |  | 150 |  | 150 |  |  | 29/10/2026 | 30/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903209779-1 KG8547 | ONIX | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Cargoport). 650036 | HT SUB PROCESS_V1 | 0903209779 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 120 |  | 120 |  |  | 30/10/2026 | 31/10/2026 |  |  | 120 |  | 120 |  |  | 29/10/2026 | 30/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903209780-1 KG8547 | ONIX | 90D | S2408WR1600 | 278 | 15/10/2026 | 278 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (Damco offline). 688010 | HT SUB PROCESS_V1 | 0903209780 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 278 |  | 278 |  |  | 14/10/2026 | 15/10/2026 |  |  | 278 |  | 278 |  |  | 13/10/2026 | 14/10/2026 |  |  | 278 |  | 278
ADIDAS | 0903209781-1 KG8547 | ONIX | 90D | S2408WR1600 | 532 | 15/10/2026 | 532 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209781 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 532 |  | 532 |  |  | 14/10/2026 | 15/10/2026 |  |  | 532 |  | 532 |  |  | 13/10/2026 | 14/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903209782-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903209782 KG8547 | 21/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903209783-1 KG8547 | ONIX | 90D | S2408WR1600 | 382 | 15/10/2026 | 382 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 960026 | HT SUB PROCESS_V1 | 0903209783 KG8547 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-09-10 |  |  | 382 |  | 382 |  |  | 2026-07-10 | 2026-07-10 |  |  | 382 |  | 382 |  |  | 2026-06-10 | 2026-06-10 |  |  | 382 |  | 382
ADIDAS | 0903209784-1 KG8547 | ONIX | 90D | S2408WR1600 | 902 | 15/10/2026 | 902 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209784 KG8547 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 902 |  | 902 |  |  | 15/10/2026 | 16/10/2026 |  |  | 902 |  | 902 |  |  | 14/10/2026 | 15/10/2026 |  |  | 902 |  | 902
ADIDAS | 0903209785-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 104 | 30/09/2026 | 104 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903209785 KX9838 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 104 |  | 104 |  |  | 26/09/2026 | 28/09/2026 | 21/08/2026 | 27/08/2026 | 104 | 104 |  |  |  | 25/09/2026 | 26/09/2026 | 15/08/2026 | 26/08/2026 | 104 | 104
ADIDAS | 0903209787-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 512 | 15/10/2026 | 512 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903209787 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 512 |  | 512 |  |  | 24/10/2026 | 26/10/2026 | 21/08/2026 | 31/08/2026 | 512 | 512 |  |  |  | 23/10/2026 | 24/10/2026 | 21/08/2026 | 29/08/2026 | 512 | 512
ADIDAS | 0903209788-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 628 | 15/10/2026 | 628 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903209788 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 628 |  | 628 |  |  | 2026-05-10 | 2026-06-10 | 21/08/2026 | 31/08/2026 | 628 | 628 |  |  |  | 2026-03-10 | 2026-05-10 | 21/08/2026 | 29/08/2026 | 628 | 628
ADIDAS | 0903209790-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 397 | 31/10/2026 | 397 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209790 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 397 |  | 397 |  |  | 27/10/2026 | 28/10/2026 |  |  | 397 |  | 397 |  |  | 26/10/2026 | 27/10/2026 |  |  | 397 |  | 397
ADIDAS | 0903209791-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 840 | 31/10/2026 | 840 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903209791 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 30/10/2026 | 2026-02-11 |  |  | 840 |  | 840 |  |  | 28/10/2026 | 30/10/2026 |  |  | 840 |  | 840 |  |  | 27/10/2026 | 29/10/2026 |  |  | 840 |  | 840
ADIDAS | 0903209792-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 114 | 31/10/2026 | 114 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903209792 KX9838 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 114 |  | 114 |  |  | 27/10/2026 | 28/10/2026 |  |  | 114 |  | 114 |  |  | 26/10/2026 | 27/10/2026 |  |  | 114 |  | 114
ADIDAS | 0903209799-1 KG8547 | ONIX | 90D | S2408WR1600 | 1750 | 30/09/2026 | 1750 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 08-Aug. 672027 | HT SUB PROCESS_V1 | 0903209799 KG8547 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 21/09/2026 |  |  | 1750 |  | 1750 |  |  | 16/09/2026 | 18/09/2026 | 2026-09-09 | 14/09/2026 | 1750 | 1496 | 254 |  |  | 15/09/2026 | 17/09/2026 | 2026-09-09 | 14/09/2026 | 1750 | 1533 | 217
ADIDAS | 0903209801-1 IN1173 | WHITE | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516254 | HT SUB PROCESS_V1 | 0903209801 IN1173 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 349 |  | 349 |  |  | 2026-08-10 | 2026-09-10 | 14/08/2026 | 2026-01-09 | 349 | 349 |  |  |  | 2026-07-10 | 2026-08-10 | 13/08/2026 | 31/08/2026 | 349 | 349
ADIDAS | 0903209802-1 IN1173 | WHITE | 90D | S2408WR1600 | 1288 | 15/10/2026 | 1288 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 678002 | HT SUB PROCESS_V1 | 0903209802 IN1173 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 15/10/2026 |  |  | 1288 |  | 1288 |  |  | 2026-10-10 | 13/10/2026 | 15/08/2026 | 2026-04-09 | 1288 | 1288 |  |  |  | 2026-09-10 | 2026-12-10 | 14/08/2026 | 31/08/2026 | 1288 | 1288
ADIDAS | 0903209803-1 IN1173 | WHITE | 90D | S2408WR1600 | 550 | 14/10/2026 | 550 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 680015 | HT SUB PROCESS_V1 | 0903209803 IN1173 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 15/10/2026 |  |  | 550 |  | 550 |  |  | 2026-10-10 | 13/10/2026 | 15/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 2026-09-10 | 2026-12-10 | 14/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903209804-1 IN1173 | WHITE | 90D | S2408WR1600 | 1445 | 15/10/2026 | 1445 | SI | SI07/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 659018 | HT SUB PROCESS_V1 | 0903209804 IN1173 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 1445 |  | 1445 |  |  | 24/09/2026 | 25/09/2026 | 19/08/2026 | 2026-02-09 | 1445 | 1445 |  |  |  | 23/09/2026 | 24/09/2026 | 15/08/2026 | 2026-02-09 | 1445 | 1445
ADIDAS | 0903209805-1 IN1173 | WHITE | 90D | S2408WR1600 | 555 | 15/10/2026 | 555 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209805 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-07-10 |  |  | 555 |  | 555 |  |  | 2026-05-10 | 2026-05-10 |  |  | 555 |  | 555 |  |  | 2026-03-10 | 2026-03-10 |  |  | 555 |  | 555
ADIDAS | 0903209806-1 IN1173 | WHITE | 90D | S2408WR1600 | 892 | 14/10/2026 | 892 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 684009 | HT SUB PROCESS_V1 | 0903209806 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 892 |  | 892 |  |  | 2026-09-10 | 2026-10-10 | 19/08/2026 | 27/08/2026 | 892 | 890 | 2 |  |  | 2026-08-10 | 2026-09-10 | 15/08/2026 | 27/08/2026 | 892 | 890 | 2
ADIDAS | 0903209808-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 1211 | 30/09/2026 | 1211 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903209808 IT1462 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 1211 |  | 1211 |  |  | 22/09/2026 | 23/09/2026 | 2026-07-09 | 15/09/2026 | 1211 | 1192 | 19 |  | 17 | 21/09/2026 | 22/09/2026 | 2026-07-09 | 15/09/2026 | 1211 | 1200 | 11 |  | 2
ADIDAS | 0903209809-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 451 | 15/10/2026 | 451 | SI | SI07/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903209809 IT1462 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 451 |  | 451 |  |  | 15/10/2026 | 16/10/2026 | 2026-09-09 | 15/09/2026 | 451 | 439 | 12 |  | 4 | 14/10/2026 | 15/10/2026 | 2026-09-09 | 14/09/2026 | 451 | 439 | 12
ADIDAS | 0903245372-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903245372 IN8707 | 2026-08-10 | KAHATEX CIJERAH | CHILE | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903245395-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 680015 | PAD+HT SUB PROCESS_V3 | 0903245395 KA4331 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903245423-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 680015 | HT SUB PROCESS_V1 | 0903245423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300
ADIDAS | 0903247791-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 501 | 15/10/2026 | 501 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247791 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 501 |  | 501 |  |  | 29/09/2026 | 2026-01-10 |  |  | 501 |  | 501
ADIDAS | 0903247818-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 118 | 15/10/2026 | 118 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 630001 | PRINT L1 SUB PROCESS_V3 | 0903247818 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 118 |  | 118 |  |  | 2026-02-10 | 2026-03-10 |  |  | 118 |  | 118
ADIDAS | 0903247851-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247851 LG8052 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-12-10 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903247873-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247873 LI7657 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903247906-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 630001 | PRINT L3 SUB PROCESS_V3 | 0903247906 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903247928-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 210 | 15/10/2026 | 210 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247928 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-03-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 210 |  | 210 |  |  | 30/09/2026 | 2026-01-10 |  |  | 210 |  | 210
ADIDAS | 0903247950-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 377 | 15/10/2026 | 377 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247950 LI7659 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 377 |  | 377 |  |  | 2026-03-10 | 2026-03-10 |  |  | 377 |  | 377
ADIDAS | 0903247975-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 15/10/2026 | 65 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247975 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 65 |  | 65 |  |  | 2026-07-10 | 2026-08-10 |  |  | 65 |  | 65 |  |  | 2026-06-10 | 2026-07-10 |  |  | 65 |  | 65
ADIDAS | 0903247991-1 IN1159 | BLACK | 90D | S2408MR1601 | 15 | 15/10/2026 | 15 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247991 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 15 |  | 15 |  |  | 2026-07-10 | 2026-08-10 |  |  | 15 |  | 15 |  |  | 2026-06-10 | 2026-07-10 |  |  | 15 |  | 15
ADIDAS | 0903248016-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 14 | 30/09/2026 | 14 | AN | AN10/07/2026 | G1H | JACKET | G1 | (10/08/2026) | ok | 29/09: ex-fty. T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248016 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 14 |  | 14 |  |  | 21/09/2026 | 23/09/2026 |  |  | 14 |  | 14
ADIDAS | 0903248036-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 12 | 31/10/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903248036 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903248063-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 36 | 30/10/2026 | 36 | AN | AN10/07/2026 | G2R | SHORTS | G2 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Kahatex, PI Date 22-Sep. Waiting fabrIc. T2 Formosa, PI Date 12-Sep. T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248063 LG9660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 36 |  | 36 |  |  | 2026-09-10 | 2026-09-10 |  |  | 36 |  | 36
ADIDAS | 0903248578-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 485 | 15/10/2026 | 485 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903248578 KV7863 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-10-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 485 |  | 485 |  |  | 2026-06-11 | 2026-07-11 |  |  | 485 |  | 485
ADIDAS | 0903248603-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1020 | 23/10/2026 | 1020 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248603 JN1948 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/10/2026 | W 3S FT QZ HD |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 1020 |  | 1020 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1020 |  | 1020
ADIDAS | 0903248633-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 256 | 23/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903248633 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903248979-1 IN1160 | WHITE | 90D | S2408MR1601 | 1173 | 15/10/2026 | 1173 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903248979 IN1160 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 13/10/2026 | 16/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-10-10 | 14/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1173 |  | 1173
ADIDAS | 0903249024-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 383 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249024 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249045-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 337 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249045 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249675-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249675 JE6338 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1150 |  | 1150 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1150 |  | 1150
ADIDAS | 0903249702-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516442 | PAD+HT SUB PROCESS_V3 | 0903249702 IT3474 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 30/10/2026 | 2026-02-11 |  |  | 1795 |  | 1795 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1795 |  | 1795 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249724-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516318 | PAD+HT SUB PROCESS_V3 | 0903249724 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903249752-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249752 JD1877 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 1610 |  | 1610 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1610 |  | 1610
ADIDAS | 0903249777-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249777 JE6341 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 432 |  | 432 |  |  | 29/09/2026 | 2026-02-10 |  |  | 432 |  | 432
ADIDAS | 0903249802-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 600 | 15/10/2026 | 600 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249802 JE6338 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 600 |  | 600 |  |  | 2026-01-10 | 2026-02-10 |  |  | 600 |  | 600
ADIDAS | 0903249832-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 299 | 15/10/2026 | 299 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249832 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 299 |  | 299 |  |  | 26/10/2026 | 27/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903249858-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249858 JM1776 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | M SL WV PT 2 |  | SS27 | 30/10/2026 | 2026-03-11 |  |  | 575 |  | 575 |  |  | 27/10/2026 | 30/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903249889-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516205 | PAD+HT SUB PROCESS_V3 | 0903249889 IT3474 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-11 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 2026-02-11 | 2026-05-11 |  |  | 1795 |  | 1795 |  |  | 29/10/2026 | 2026-02-11 |  |  | 1795 |  | 1795 |  |  | 28/10/2026 | 31/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249918-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 600 | 31/10/2026 | 600 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249918 KA0237 | 2026-08-10 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-11 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 2026-12-11 | 14/11/2026 |  |  | 600 |  | 600 |  |  | 2026-09-11 | 2026-11-11 |  |  | 600 |  | 600 |  |  | 2026-07-11 | 2026-10-11 |  |  | 600 |  | 600
ADIDAS | 0903249936-1 IN2961 | BLACK | 105D | S2408WR2400 | 460 | 31/10/2026 | 460 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249936 IN2961 | 2026-08-10 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-11 | OTR B TEE BLACK |  | SS27 | 2026-10-11 | 2026-10-11 |  |  | 460 |  | 460 |  |  | 2026-07-11 | 2026-07-11 |  |  | 460 |  | 460 |  |  | 2026-06-11 | 2026-06-11 |  |  | 460 |  | 460
ADIDAS | 0903249960-1 IK7442 | WHITE | 105D | S2408WR2400 | 476 | 31/10/2026 | 476 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249960 IK7442 | 2026-08-10 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-04-11 | OTR B TEE WHITE |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 476 |  | 476 |  |  | 2026-02-11 | 2026-03-11 |  |  | 476 |  | 476 |  |  | 31/10/2026 | 2026-02-11 |  |  | 476 |  | 476
ADIDAS | 0903249963-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/10/2026 | 300 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249963 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 15/10/2026 | 17/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903249983-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 679 | 31/10/2026 | 679 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249983 LD0277 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 679 |  | 679 |  |  | 2026-10-11 | 2026-11-11 |  |  | 679 |  | 679 |  |  | 2026-09-11 | 2026-10-11 |  |  | 679 |  | 679
ADIDAS | 0903250004-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 23/09/2026 | 300 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903250004 JG8642 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 300 | 162 | 138
ADIDAS | 0903250015-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250015 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 30/10/2026 | M SL WV PT 2 |  | SS27 | 30/10/2026 | 2026-03-11 |  |  | 575 |  | 575 |  |  | 27/10/2026 | 30/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903250038-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 326 | 2026-12-09 | 326 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250038 KA0544 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 326 | 326 |  |  |  | 31/08/2026 | 2026-09-09 | 31/08/2026 | 31/08/2026 | 326 | 326
ADIDAS | 0903250069-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 304 | 2026-12-09 | 304 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250069 KA0546 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-03-09 | 304 | 304
ADIDAS | 0903250091-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 840 | 15/10/2026 | 840 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250091 JD1877 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 840 |  | 840 |  |  | 25/09/2026 | 28/09/2026 |  |  | 840 |  | 840
ADIDAS | 0903250102-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 378 | 15/10/2026 | 378 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250102 JM1775 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 378 |  | 378 |  |  | 15/10/2026 | 17/10/2026 |  |  | 378 |  | 378
ADIDAS | 0903250117-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250117 JE6341 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 828 |  | 828 |  |  | 29/09/2026 | 2026-02-10 |  |  | 828 |  | 828
ADIDAS | 0903250128-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250128 JM1776 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 342 |  | 342 |  |  | 26/10/2026 | 27/10/2026 |  |  | 342 |  | 342
ADIDAS | 0903250411-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 116 | 15/10/2026 | 116 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903250411 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 116 |  | 116 |  |  | 2026-03-10 | 2026-03-10 |  |  | 116 |  | 116
ADIDAS | 0903250431-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 157 | 31/10/2026 | 157 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903250431 KU7520 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 157 |  | 157 |  |  | 30/10/2026 | 31/10/2026 |  |  | 157 |  | 157 |  |  | 29/10/2026 | 30/10/2026 |  |  | 157 |  | 157
ADIDAS | 0903250451-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 503 | 31/10/2026 | 503 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516342 | HT SUB PROCESS_V1 | 0903250451 KU7520 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 503 |  | 503 |  |  | 30/10/2026 | 31/10/2026 |  |  | 503 |  | 503 |  |  | 29/10/2026 | 30/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903250476-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 264 | 16/10/2026 | 264 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L1 SUB PROCESS_V3 | 0903250476 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-07-10 |  |  | 264 |  | 264 |  |  | 2026-01-10 | 2026-03-10 |  |  | 264 |  | 264
ADIDAS | 0903250503-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903250503 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 107 |  | 107 |  |  | 24/09/2026 | 25/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903250530-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250530 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 107 |  | 107 |  |  | 2026-02-10 | 2026-03-10 |  |  | 107 |  | 107
ADIDAS | 0903250563-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 449 | 15/10/2026 | 449 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (03/08/2026) | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250563 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 449 |  | 449 |  |  | 23/09/2026 | 24/09/2026 |  |  | 449 |  | 449
ADIDAS | 0903250948-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 127 | 31/10/2026 | 127 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903250948 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 127 |  | 127 |  |  | 27/10/2026 | 28/10/2026 |  |  | 127 |  | 127 |  |  | 26/10/2026 | 27/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903250949-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L1 SUB PROCESS_V3 | 0903250949 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 28/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250973-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903250973 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250977-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250977 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 372 |  | 372 |  |  | 2026-06-10 | 2026-08-10 |  |  | 372 |  | 372
ADIDAS | 0903250999-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903250999 LE4307 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-11-11 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-11-11 | 13/11/2026 |  |  | 100 |  | 100 |  |  | 2026-07-11 | 2026-10-11 |  |  | 100 |  | 100
ADIDAS | 0903251020-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251020 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | W 3S FT FZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 230 |  | 230 |  |  | 27/10/2026 | 28/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903251026-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251026 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/09/2026 | MINI EMB T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 590 |  | 590 |  |  | 25/09/2026 | 26/09/2026 |  |  | 590 |  | 590 |  |  | 23/09/2026 | 24/09/2026 |  |  | 590 |  | 590
ADIDAS | 0903251047-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903251047 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 396 |  | 396 |  |  | 24/09/2026 | 25/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903251051-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G3D | SHORTS | G3 | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 848012 | PAD+HT SUB PROCESS_V3 | 0903251051 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | RUN IT SHORT BLACK |  | SS27-TI | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903251082-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1720 | 15/10/2026 | 1720 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903251082 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1720 |  | 1720 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1720 |  | 1720
ADIDAS | 0903251098-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 277 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877).. 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251098 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903251111-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1136 | 15/10/2026 | 1136 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251111 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | W 3S FT CF PT |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 1136 |  | 1136 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1136 |  | 1136
ADIDAS | 0903251135-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251135 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 1610 |  | 1610 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1610 |  | 1610
ADIDAS | 0903251161-1 KA0246 | BLACK | 105D | S2608WR0902 | 600 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 684009 | PAD+HT SUB PROCESS_V3 | 0903251161 KA0246 | 2026-08-10 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251312-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 230 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903251312 KD0738 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903251454-1 KA0246 | BLACK | 105D | S2608WR0902 | 322 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903251454 KA0246 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251481-1 KA0246 | BLACK | 105D | S2608WR0902 | 636 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251481 KA0246 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251540-1 KA0246 | BLACK | 105D | S2608WR0902 | 491 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251540 KA0246 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251605-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 200 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251605 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251695-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 714 | 15/10/2026 | 714 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251695 JE0052 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 31/10/2026 | W 3S FT FZ HD |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 714 |  | 714 |  |  | 28/10/2026 | 29/10/2026 |  |  | 714 |  | 714
ADIDAS | 0903251716-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 848 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 960006 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903251716 KA4914 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903251728-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251728 KA5089 | 26/08/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/09/2026 | MINI EMB T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 602 |  | 602 |  |  | 25/09/2026 | 26/09/2026 |  |  | 602 |  | 602 |  |  | 23/09/2026 | 24/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903251751-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 124 | 15/10/2026 | 124 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903251751 IU0217 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 124 |  | 124 |  |  | 21/09/2026 | 21/09/2026 | 2026-10-09 | 2026-11-09 | 124 | 20 | 104
ADIDAS | 0903251769-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 890 | 15/10/2026 | 890 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251769 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S FT FZ HD |  | SS27 | 28/10/2026 | 30/10/2026 |  |  | 890 |  | 890 |  |  | 24/10/2026 | 27/10/2026 |  |  | 890 |  | 890
ADIDAS | 0903251816-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 800 | 23/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251816 KC5231 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903251842-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1686 | 15/10/2026 | 1686 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251842 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 1686 |  | 1686 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1686 |  | 1686
ADIDAS | 0903251866-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1760 | 23/10/2026 | 1760 | SA | SA10/07/2026 | G2A | SHORTS | G2 | (20/08/2026) | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903251866 KD4872 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-01-10 | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 1760 |  | 1760 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1760 |  | 1760
ADIDAS | 0903251870-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 118 | 31/10/2026 | 118 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251870 KV8005 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 118 |  | 118 |  |  | 30/10/2026 | 2026-02-11 |  |  | 118 |  | 118
ADIDAS | 0903251936-1 KT4839 | ONIX | 90D | S2408MR1601 | 566 | 31/10/2026 | 566 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903251936 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 566 |  | 566 |  |  | 27/10/2026 | 29/10/2026 |  |  | 566 |  | 566 |  |  | 26/10/2026 | 28/10/2026 |  |  | 566 |  | 566
ADIDAS | 0903251958-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 469 | 15/10/2026 | 469 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 826010 | PRINT L2+PAD SUB PROCESS_V3 | 0903251958 LC8884 |  | KAHATEX CIJERAH | TURKEY | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 469 |  | 469 |  |  | 2026-08-10 | 2026-09-10 | 26/08/2026 | 2026-03-09 | 469 | 314 | 155
ADIDAS | 0903251993-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 187 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251993 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903252040-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 324 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903252040 IN0088 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903252045-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 229 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 547012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903252045 KY5988 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903252061-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 481 | 15/10/2026 | 481 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252061 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 481 |  | 481 |  |  | 2026-05-11 | 2026-06-11 |  |  | 481 |  | 481
ADIDAS | 0903252085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 354 | 15/10/2026 | 354 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252085 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 354 |  | 354 |  |  | 2026-06-11 | 2026-07-11 |  |  | 354 |  | 354
ADIDAS | 0903252116-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 128 | 15/10/2026 | 128 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903252116 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M ADI RETRO T WHITE |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 128 |  | 128 |  |  | 2026-08-10 | 2026-08-10 | 2026-11-09 | 2026-11-09 | 128 | 110 | 18
ADIDAS | 0903252138-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 141 | 31/10/2026 | 141 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252138 KA0237 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-12-11 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 2026-12-11 | 14/11/2026 |  |  | 141 |  | 141 |  |  | 2026-09-11 | 2026-11-11 |  |  | 141 |  | 141 |  |  | 2026-07-11 | 2026-10-11 |  |  | 141 |  | 141
ADIDAS | 0903252154-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 468 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252154 IN0088 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903252175-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252175 JM1775 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | M SL WV PT 2 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 576 |  | 576 |  |  | 19/10/2026 | 20/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903252182-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 360 | 15/10/2026 | 360 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903252182 KX8875 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-12-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 360 |  | 360 |  |  | 2026-08-10 | 2026-08-10 |  |  | 360 |  | 360
ADIDAS | 0903252230-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 826010 | HT SUB PROCESS_V1 | 0903252230 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 200 |  | 200 |  |  | 22/09/2026 | 23/09/2026 |  |  | 200 |  | 200 |  |  | 21/09/2026 | 22/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903252254-1 IN1156 | BLACK | 90D | S2408MR1600 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903252254 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-03-10 |  |  | 590 |  | 590 |  |  | 30/09/2026 | 2026-01-10 |  |  | 590 |  | 590 |  |  | 29/09/2026 | 30/09/2026 |  |  | 590 |  | 590
ADIDAS | 0903252275-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 126 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252275 KY9383 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903252439-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252439 LI7657 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 101 |  | 101 |  |  | 2026-05-10 | 2026-06-10 |  |  | 101 |  | 101
ADIDAS | 0903252473-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252473 LI7658 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 117 |  | 117 |  |  | 29/09/2026 | 30/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903252503-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252503 LI7656 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 101 |  | 101 |  |  | 28/09/2026 | 29/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903252539-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252539 LI7659 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 117 |  | 117 |  |  | 2026-03-10 | 2026-03-10 |  |  | 117 |  | 117
ADIDAS | 0903252570-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 230 | 2026-12-09 | 230 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 1st Art (TC 10 pcs) 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903252570 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-04-09 | 2026-09-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-10-09 | 230 | 230
ADIDAS | 0903252595-1 IN1172 | BLACK | 90D | S2408WR1600 | 264 | 31/10/2026 | 264 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903252595 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 264 |  | 264 |  |  | 24/10/2026 | 24/10/2026 |  |  | 264 |  | 264 |  |  | 23/10/2026 | 23/10/2026 |  |  | 264 |  | 264
ADIDAS | 0903252620-1 IN1157 | WHITE | 90D | S2408MR1600 | 1027 | 31/10/2026 | 1027 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903252620 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | ADIZERO E TEE |  | SS27-YTI | 30/10/2026 | 2026-02-11 |  |  | 1027 |  | 1027 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1027 |  | 1027 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1027 |  | 1027
ADIDAS | 0903252644-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/10/2026 | 140 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252644 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 140 |  | 140 |  |  | 26/10/2026 | 27/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903253096-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 201 | 15/10/2026 | 201 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903253096 KV0458 |  | KAHATEX CIJERAH | THAILAND | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 201 |  | 201 |  |  | 22/09/2026 | 24/09/2026 |  |  | 201 |  | 201
ADIDAS | 0903253164-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1421 | 15/10/2026 | 1421 | SA | SA10/07/2026 | G2O | JACKET | G2 | ok | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253164 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M 3S FT FZ HD |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1421 |  | 1421 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1421 |  | 1421
ADIDAS | 0903253174-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253174 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 288 |  | 288 |  |  | 26/10/2026 | 27/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903253193-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1909 | 15/10/2026 | 1909 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903253193 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-08-10 | 2026-12-10 |  |  | 1909 |  | 1909 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1909 |  | 1909
ADIDAS | 0903253200-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 267 | 31/10/2026 | 267 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903253200 LD0278 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-11-11 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 2026-11-11 | 2026-12-11 |  |  | 267 |  | 267 |  |  | 2026-07-11 | 2026-09-11 |  |  | 267 |  | 267 |  |  | 2026-06-11 | 2026-07-11 |  |  | 267 |  | 267
ADIDAS | 0903253221-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253221 LE8188 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253229-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253229 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-11 | M SL WV PT 2 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 600 |  | 600 |  |  | 30/10/2026 | 31/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253259-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 650 | 15/10/2026 | 650 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253259 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 650 |  | 650 |  |  | 2026-07-10 | 2026-09-10 |  |  | 650 |  | 650
ADIDAS | 0903253286-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253286 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 27/10/2026 | W 3S FT FZ HD |  | SS27 | 27/10/2026 | 27/10/2026 |  |  | 600 |  | 600 |  |  | 23/10/2026 | 23/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253287-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 200 | 15/10/2026 | 200 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903253287 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 200 |  | 200 |  |  | 14/10/2026 | 14/10/2026 |  |  | 200 |  | 200 |  |  | 13/10/2026 | 13/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903253302-1 KT4840 | ONIX | 90D | S2408MR1600 | 181 | 31/10/2026 | 181 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253302 KT4840 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 26/10/2026 |  |  | 181 |  | 181 |  |  | 21/10/2026 | 23/10/2026 |  |  | 181 |  | 181 |  |  | 20/10/2026 | 22/10/2026 |  |  | 181 |  | 181
ADIDAS | 0903253312-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 374 | 15/10/2026 | 374 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253312 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 374 |  | 374 |  |  | 26/10/2026 | 27/10/2026 |  |  | 374 |  | 374
ADIDAS | 0903253327-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253327 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 23/10/2026 | M SL WV PT 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 600 |  | 600 |  |  | 20/10/2026 | 21/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253337-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 105 | 15/10/2026 | 105 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903253337 KX0123 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M ADI RETRO T WHITE |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 105 |  | 105 |  |  | 2026-08-10 | 2026-08-10 | 2026-11-09 | 2026-11-09 | 105 | 91 | 14
ADIDAS | 0903253341-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 582 | 15/10/2026 | 582 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253341 JE6341 |  | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 582 |  | 582 |  |  | 2026-06-10 | 2026-08-10 |  |  | 582 |  | 582
ADIDAS | 0903253374-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253374 JD5302 |  | KAHATEX CIJERAH | UKRAINE | SEA | 29/10/2026 | W 3S FT CF PT |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 1000 |  | 1000 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903253396-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253396 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 26/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 558 |  | 558 |  |  | 23/09/2026 | 24/09/2026 |  |  | 558 |  | 558
ADIDAS | 0903253447-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512110 | PRINT L2+HT SUB PROCESS_V3 | 0903253447 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 13/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903253455-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 191 | 15/10/2026 | 191 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 516342 | PAD+HT SUB PROCESS_V3 | 0903253455 LD0277 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 21/09/2026 | 21/09/2026 |  |  | 191 |  | 191 |  |  | 17/09/2026 | 17/09/2026 |  |  | 191 |  | 191 |  |  | 16/09/2026 | 16/09/2026 |  |  | 191 |  | 191
ADIDAS | 0903253468-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 331 | 23/10/2026 | 331 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512106 | PRINT L2+PAD SUB PROCESS_V3 | 0903253468 LC8884 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 13/10/2026 | M RESORT T BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 331 |  | 331 |  |  | 2026-09-10 | 2026-10-10 | 26/08/2026 | 27/08/2026 | 331 | 160 | 171
ADIDAS | 0903253478-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 266 | 31/10/2026 | 266 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 516342 | HT SUB PROCESS_V1 | 0903253478 KX9838 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 30/10/2026 | 30/10/2026 |  |  | 266 |  | 266 |  |  | 28/10/2026 | 28/10/2026 |  |  | 266 |  | 266 |  |  | 27/10/2026 | 27/10/2026 |  |  | 266 |  | 266
ADIDAS | 0903253530-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 216 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903253530 LI7658 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903253532-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 20 | 15/10/2026 | 20 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903253532 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 20 |  | 20 |  |  | 13/10/2026 | 14/10/2026 |  |  | 20 |  | 20 |  |  | 2026-12-10 | 13/10/2026 |  |  | 20 |  | 20
ADIDAS | 0903253536-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 542 | 31/10/2026 | 542 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903253536 IT1467 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 542 |  | 542 |  |  | 27/10/2026 | 29/10/2026 |  |  | 542 |  | 542 |  |  | 26/10/2026 | 28/10/2026 |  |  | 542 |  | 542
ADIDAS | 0903253551-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 637 | 2026-07-10 | 637 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253551 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 637 |  | 637 |  |  | 23/09/2026 | 24/09/2026 | 2026-04-09 | 15/09/2026 | 637 | 570 | 67 |  | 44
ADIDAS | 0903253557-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 268 | 15/10/2026 | 268 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253557 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 268 |  | 268 |  |  | 2026-01-10 | 2026-03-10 |  |  | 268 |  | 268
ADIDAS | 0903253577-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 347 | 2026-07-10 | 347 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253577 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 347 |  | 347 |  |  | 23/09/2026 | 24/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 192 | 155
ADIDAS | 0903253578-1 IN1157 | WHITE | 90D | S2408MR1600 | 1664 | 31/10/2026 | 1664 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253578 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 1664 |  | 1664 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1664 |  | 1664 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1664 |  | 1664
ADIDAS | 0903253594-1 KG8547 | ONIX | 90D | S2408WR1600 | 194 | 31/10/2026 | 194 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903253594 KG8547 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 194 |  | 194 |  |  | 30/10/2026 | 31/10/2026 |  |  | 194 |  | 194 |  |  | 29/10/2026 | 30/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903253608-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT SUB PROCESS_V1 | 0903253608 IT1467 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 102 |  | 102 |  |  | 27/10/2026 | 29/10/2026 |  |  | 102 |  | 102 |  |  | 26/10/2026 | 28/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903253610-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 351 | 30/09/2026 | 351 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253610 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 351 |  | 351 |  |  | 18/09/2026 | 18/09/2026 | 28/08/2026 | 2026-04-09 | 351 | 294 | 57
ADIDAS | 0903253635-1 IN8707 | BLACK | 105D | S2408WR1601A | 781 | 31/10/2026 | 781 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253635 IN8707 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 29/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 781 |  | 781 |  |  | 27/10/2026 | 29/10/2026 |  |  | 781 |  | 781 |  |  | 26/10/2026 | 28/10/2026 |  |  | 781 |  | 781
ADIDAS | 0903253654-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 382 | 23/10/2026 | 382 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253654 LF1392 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 382 |  | 382 |  |  | 24/10/2026 | 30/10/2026 |  |  | 382 |  | 382
ADIDAS | 0903253694-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903253694 JC8238 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903253780-1 IN1173 | WHITE | 90D | S2408WR1600 | 152 | 31/10/2026 | 152 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903253780 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 152 |  | 152 |  |  | 2026-10-10 | 2026-12-10 |  |  | 152 |  | 152 |  |  | 2026-09-10 | 2026-10-10 |  |  | 152 |  | 152
ADIDAS | 0903253801-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903253801 KG8547 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI | 2026-03-11 | 2026-03-11 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 31/10/2026 |  |  | 100 |  | 100 |  |  | 30/10/2026 | 30/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903253810-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903253810 KX8875 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 368 |  | 368 |  |  | 2026-08-10 | 2026-08-10 |  |  | 368 |  | 368
ADIDAS | 0903253860-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 163 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253860 KY5988 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253870-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 936 | 15/10/2026 | 936 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516204 | PAD+HT SUB PROCESS_V3 | 0903253870 IT3474 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 936 |  | 936 |  |  | 26/10/2026 | 27/10/2026 |  |  | 936 |  | 936 |  |  | 24/10/2026 | 26/10/2026 |  |  | 936 |  | 936
ADIDAS | 0903253904-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253904 JE6338 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 1150 |  | 1150 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1150 |  | 1150
ADIDAS | 0903253915-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 118 | 31/10/2026 | 118 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903253915 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 118 |  | 118 |  |  | 2026-04-11 | 2026-04-11 |  |  | 118 |  | 118 |  |  | 2026-03-11 | 2026-03-11 |  |  | 118 |  | 118
ADIDAS | 0903253948-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253948 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253967-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253967 JE6341 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M 3S FT FZ HD |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 828 |  | 828 |  |  | 2026-08-10 | 2026-10-10 |  |  | 828 |  | 828
ADIDAS | 0903253995-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253995 JD1877 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 1610 |  | 1610 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1610 |  | 1610
ADIDAS | 0903254003-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 425 | 23/10/2026 | 425 | SI | SI10/07/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254003 KV8005 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 425 |  | 425 |  |  | 24/10/2026 | 30/10/2026 |  |  | 425 |  | 425
ADIDAS | 0903254029-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1232 | 23/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254029 JW7178 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903254049-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254049 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | W 3S FT FZ HD |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 230 |  | 230 |  |  | 22/10/2026 | 23/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903254053-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 116 | 15/10/2026 | 116 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903254053 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 116 |  | 116 |  |  | 14/10/2026 | 14/10/2026 |  |  | 116 |  | 116 |  |  | 13/10/2026 | 13/10/2026 |  |  | 116 |  | 116
ADIDAS | 0903254056-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254056 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 576 |  | 576 |  |  | 17/10/2026 | 19/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903254089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903254089 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 396 |  | 396 |  |  | 30/09/2026 | 2026-02-10 |  |  | 396 |  | 396
ADIDAS | 0903254114-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 990 | 23/10/2026 | 990 | SI | SI10/07/2026 | G2M | SWEATSHIRT | G2 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254114 KD4874 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | M 3S FT SWT |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 990 |  | 990 |  |  | 2026-03-10 | 2026-05-10 |  |  | 990 |  | 990
ADIDAS | 0903254125-1 IN1156 | BLACK | 90D | S2408MR1600 | 335 | 31/10/2026 | 335 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903254125 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 335 |  | 335 |  |  | 26/10/2026 | 27/10/2026 |  |  | 335 |  | 335 |  |  | 24/10/2026 | 26/10/2026 |  |  | 335 |  | 335
ADIDAS | 0903254175-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1182 | 15/10/2026 | 1182 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877).. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254175 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-11 | 14/11/2026 |  |  | 1182 |  | 1182 |  |  | 2026-09-11 | 2026-11-11 |  |  | 1182 |  | 1182
ADIDAS | 0903254182-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903254182 KG3234 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-11 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 2026-09-11 | 2026-12-11 |  |  | 100 |  | 100 |  |  | 2026-05-11 | 2026-09-11 |  |  | 100 |  | 100 |  |  | 2026-04-11 | 2026-07-11 |  |  | 100 |  | 100
ADIDAS | 0903254188-1 IN1157 | WHITE | 90D | S2408MR1600 | 621 | 31/10/2026 | 621 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254188 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 621 |  | 621 |  |  | 26/10/2026 | 27/10/2026 |  |  | 621 |  | 621 |  |  | 24/10/2026 | 26/10/2026 |  |  | 621 |  | 621
ADIDAS | 0903254192-1 KT4839 | ONIX | 90D | S2408MR1601 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848024 | HT SUB PROCESS_V1 | 0903254192 KT4839 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 275 |  | 275 |  |  | 26/10/2026 | 27/10/2026 |  |  | 275 |  | 275 |  |  | 24/10/2026 | 26/10/2026 |  |  | 275 |  | 275
ADIDAS | 0903254214-1 IN1156 | BLACK | 90D | S2408MR1600 | 572 | 31/10/2026 | 572 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254214 IN1156 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 572 |  | 572 |  |  | 27/10/2026 | 29/10/2026 |  |  | 572 |  | 572 |  |  | 26/10/2026 | 28/10/2026 |  |  | 572 |  | 572
ADIDAS | 0903254241-1 IN1173 | WHITE | 90D | S2408WR1600 | 217 | 31/10/2026 | 217 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848024 | HT SUB PROCESS_V1 | 0903254241 IN1173 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 217 |  | 217 |  |  | 2026-12-10 | 13/10/2026 |  |  | 217 |  | 217 |  |  | 2026-10-10 | 2026-12-10 |  |  | 217 |  | 217
ADIDAS | 0903254247-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 31/10/2026 | 512 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254247 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-11 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 2026-12-11 | 14/11/2026 |  |  | 512 |  | 512 |  |  | 2026-09-11 | 2026-11-11 |  |  | 512 |  | 512 |  |  | 2026-07-11 | 2026-10-11 |  |  | 512 |  | 512
ADIDAS | 0903254266-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512102 | HT SUB PROCESS_V1 | 0903254266 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 100 |  | 100 |  |  | 30/10/2026 | 31/10/2026 |  |  | 100 |  | 100 |  |  | 29/10/2026 | 30/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903254325-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903254325 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 340 |  | 340 |  |  | 24/09/2026 | 25/09/2026 |  |  | 340 |  | 340
ADIDAS | 0903254326-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1080 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254326 JZ7709 | 2026-08-10 | KAHATEX CIJERAH | HONGKONG | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 0903254356-1 KZ3049 | BLACK | 90D | S2762LHMEDR109W | 330 | 15/10/2026 | 330 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903254356 KZ3049 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER GR GFCTP W BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-03-10 |  |  | 330 |  | 330
ADIDAS | 0903254368-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254368 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | J FOOTBALL T |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 100 | 8 | 92
ADIDAS | 0903254387-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254387 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 372 |  | 372 |  |  | 2026-02-10 | 2026-03-10 |  |  | 372 |  | 372
ADIDAS | 0903254402-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 130 | 15/10/2026 | 130 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903254402 KV0458 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 130 |  | 130 |  |  | 22/09/2026 | 24/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903254520-1 IN1156 | BLACK | 90D | S2408MR1600 | 422 | 31/10/2026 | 422 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903254520 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 422 |  | 422 |  |  | 27/10/2026 | 29/10/2026 |  |  | 422 |  | 422 |  |  | 26/10/2026 | 28/10/2026 |  |  | 422 |  | 422
ADIDAS | 0903254581-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 457 | 15/10/2026 | 457 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254581 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 457 |  | 457 |  |  | 2026-03-10 | 2026-05-10 |  |  | 457 |  | 457
ADIDAS | 0903254614-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 380 | 15/10/2026 | 380 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L3 SUB PROCESS_V3 | 0903254614 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 380 |  | 380 |  |  | 2026-05-10 | 2026-05-10 |  |  | 380 |  | 380
ADIDAS | 0903254634-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 355 | 31/10/2026 | 355 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254634 KY4155 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 355 |  | 355 |  |  | 19/10/2026 | 21/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903254722-1 LF0723 | BLACK | 105D | S2754MAS511B | 505 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254722 LF0723 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903254741-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903254741 JD1881 |  | KAHATEX CIJERAH | ISRAEL | SEA | 14/10/2026 | M 3S FT TC PT |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1203 |  | 1203 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903254769-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 271 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | PAD+HT SUB PROCESS_V3 | 0903254769 LD0908 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903254804-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 353 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254804 LE8181 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903254860-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 229 | 15/10/2026 | 229 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254860 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M ADI RETRO T BLACK |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 229 |  | 229 |  |  | 2026-08-10 | 2026-08-10 | 2026-11-09 | 2026-11-09 | 229 | 201 | 28
ADIDAS | 0903254861-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 312 | 15/10/2026 | 312 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254861 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | W 3S FT FZ HD |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 312 |  | 312 |  |  | 22/10/2026 | 23/10/2026 |  |  | 312 |  | 312
ADIDAS | 0903254872-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903254872 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 558 |  | 558 |  |  | 30/09/2026 | 2026-02-10 |  |  | 558 |  | 558
ADIDAS | 0903254887-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 108 | 15/10/2026 | 108 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254887 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 108 |  | 108 |  |  | 29/09/2026 | 2026-01-10 |  |  | 108 |  | 108
ADIDAS | 0903254895-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 263 | 31/10/2026 | 263 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254895 LD0292 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 263 |  | 263 |  |  | 2026-07-11 | 2026-10-11 |  |  | 263 |  | 263 |  |  | 2026-06-11 | 2026-09-11 |  |  | 263 |  | 263
ADIDAS | 0903254914-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 1750 | 15/10/2026 | 1750 | AN | AN10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 09-Jun, ETD 10-Aug, ETA-Kaha 21-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254914 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/10/2026 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 24/10/2026 | 29/10/2026 |  |  | 1750 |  | 1750 |  |  | 21/10/2026 | 26/10/2026 |  |  | 1750 |  | 1750
ADIDAS | 0903254921-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254921 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 288 |  | 288 |  |  | 15/10/2026 | 17/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903254929-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 233 | 31/10/2026 | 233 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903254929 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-11 | 2026-04-11 |  |  | 233 |  | 233 |  |  | 31/10/2026 | 2026-02-11 |  |  | 233 |  | 233 |  |  | 30/10/2026 | 31/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903254967-1 KT4839 | ONIX | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512108 | HT SUB PROCESS_V1 | 0903254967 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 26/10/2026 | 27/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903254980-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 619 | 15/10/2026 | 619 | SI | SI10/07/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254980 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 619 |  | 619 |  |  | 15/10/2026 | 17/10/2026 |  |  | 619 |  | 619
ADIDAS | 0903255005-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 494 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255005 LF0721 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255009-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 389 | 15/10/2026 | 389 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255009 LG8051 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 29/09/2026 | 29/09/2026 |  |  | 389 |  | 389 |  |  | 25/09/2026 | 25/09/2026 |  |  | 389 |  | 389
ADIDAS | 0903255022-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 135 | 15/10/2026 | 135 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903255022 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 135 |  | 135 |  |  | 2026-07-10 | 2026-09-10 |  |  | 135 |  | 135
ADIDAS | 0903255023-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1203 | 2026-09-09 | 1203 | SA | SA10/07/2026 | G3G | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255023 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 29/08/2026 | 2026-05-09 | 1203 | 1203 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-04-09 | 1203 | 1203
ADIDAS | 0903255038-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255038 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-07-10 |  |  | 169 |  | 169 |  |  | 2026-01-10 | 2026-03-10 |  |  | 169 |  | 169
ADIDAS | 0903255050-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255050 IZ0443 | 2026-11-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-02-09 | 2026-09-09 | 276 | 276
ADIDAS | 0903255078-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 161 | 15/10/2026 | 161 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903255078 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 161 |  | 161 |  |  | 14/10/2026 | 15/10/2026 |  |  | 161 |  | 161 |  |  | 13/10/2026 | 14/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903255083-1 IL7232 | BLACK | 105D | S2408MR3202 | 468 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 512102 | PAD+HT SUB PROCESS_V3 | 0903255083 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903255103-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 276 | 2026-12-09 | 276 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255103 KA0546 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 276 | 276 |  |  |  | 28/08/2026 | 2026-09-09 | 13/08/2026 | 2026-03-09 | 276 | 276
ADIDAS | 0903255107-1 KT4840 | ONIX | 90D | S2408MR1600 | 770 | 31/10/2026 | 770 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903255107 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 770 |  | 770 |  |  | 23/10/2026 | 24/10/2026 |  |  | 770 |  | 770 |  |  | 22/10/2026 | 23/10/2026 |  |  | 770 |  | 770
ADIDAS | 0903255118-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 344 | 15/10/2026 | 344 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255118 LG8052 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 2026-12-10 | 2026-12-10 |  |  | 344 |  | 344 |  |  | 2026-08-10 | 2026-08-10 |  |  | 344 |  | 344
ADIDAS | 0903255151-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903255151 LI7657 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903255192-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 492 | 15/10/2026 | 492 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | T2 Formosa, PI Date 08-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255192 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-05-11 | 2026-05-11 |  |  | 492 |  | 492 |  |  | 2026-02-11 | 2026-02-11 |  |  | 492 |  | 492
ADIDAS | 0903255212-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1894 | 15/10/2026 | 1894 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Formosa, PI Date 08-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255212 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 1894 |  | 1894 |  |  | 2026-02-11 | 2026-05-11 |  |  | 1894 |  | 1894
ADIDAS | 0903255230-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 287 | 15/10/2026 | 287 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255230 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 287 |  | 287 |  |  | 2026-03-10 | 2026-03-10 |  |  | 287 |  | 287
ADIDAS | 0903255239-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 16/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L1 SUB PROCESS_V3 | 0903255239 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 120 |  | 120 |  |  | 2026-01-10 | 2026-02-10 |  |  | 120 |  | 120
ADIDAS | 0903255277-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 234 | 15/10/2026 | 234 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255277 LI7658 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 234 |  | 234 |  |  | 30/09/2026 | 2026-01-10 |  |  | 234 |  | 234
ADIDAS | 0903255316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 365 | 15/10/2026 | 365 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 365 |  | 365 |  |  | 30/09/2026 | 2026-01-10 |  |  | 365 |  | 365
ADIDAS | 0903255344-1 IN1173 | WHITE | 90D | S2408WR1600 | 2980 | 15/10/2026 | 2980 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 960006 | HT SUB PROCESS_V1 | 0903255344 IN1173 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-12-10 |  |  | 2980 |  | 2980 |  |  | 2026-05-10 | 2026-09-10 |  |  | 2980 |  | 2980 |  |  | 2026-03-10 | 2026-08-10 |  |  | 2980 |  | 2980
ADIDAS | 0903255352-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 180 | 15/10/2026 | 180 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255352 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-07-10 |  |  | 180 |  | 180 |  |  | 2026-01-10 | 2026-03-10 |  |  | 180 |  | 180
ADIDAS | 0903255377-1 IN1157 | WHITE | 90D | S2408MR1600 | 3100 | 15/10/2026 | 3100 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903255377 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 14/10/2026 |  |  | 3100 |  | 3100 |  |  | 2026-07-10 | 2026-12-10 | 2026-09-09 | 14/09/2026 | 3100 | 565 | 2535 |  |  | 2026-06-10 | 2026-10-10 | 2026-04-09 | 15/09/2026 | 3100 | 581 | 2519 |  | 7
ADIDAS | 0903255384-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 204 | 15/10/2026 | 204 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903255384 LI7658 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 204 |  | 204 |  |  | 29/09/2026 | 30/09/2026 |  |  | 204 |  | 204
ADIDAS | 0903255415-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255415 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903255423-1 IN1159 | BLACK | 90D | S2408MR1601 | 3310 | 15/10/2026 | 3310 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 21/10/2026 |  |  | 3310 |  | 3310 |  |  | 13/10/2026 | 19/10/2026 |  |  | 3310 |  | 3310 |  |  | 2026-12-10 | 17/10/2026 |  |  | 3310 |  | 3310
ADIDAS | 0903255441-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 960 | 15/10/2026 | 960 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L3 SUB PROCESS_V3 | 0903255441 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 960 |  | 960 |  |  | 30/09/2026 | 2026-01-10 |  |  | 960 |  | 960
ADIDAS | 0903255459-1 JZ7774 | TECH INDIGO S20 | 90D | S2608MR0902 | 1200 | 31/10/2026 | 1200 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 834012 | PAD+HT SUB PROCESS_V3 | 0903255459 JZ7774 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 14/11/2026 | Run Ess 21 S M TECH INDIGO S20 |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 1200 |  | 1200 |  |  | 2026-11-11 | 13/11/2026 |  |  | 1200 |  | 1200 |  |  | 2026-10-11 | 2026-12-11 |  |  | 1200 |  | 1200
ADIDAS | 0903255467-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 1080 | 15/10/2026 | 1080 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L1 SUB PROCESS_V3 | 0903255467 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 1080 |  | 1080 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1080 |  | 1080
ADIDAS | 0903255507-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 23/10/2026 | 200 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255507 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 26/10/2026 | 26/10/2026 |  |  | 200 |  | 200 |  |  | 24/10/2026 | 24/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903255515-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255515 LF0718 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255565-1 IN1173 | WHITE | 90D | S2408WR1600 | 219 | 31/10/2026 | 219 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903255565 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 219 |  | 219 |  |  | 2026-12-10 | 13/10/2026 |  |  | 219 |  | 219 |  |  | 2026-10-10 | 2026-12-10 |  |  | 219 |  | 219
ADIDAS | 0903255580-1 KT4839 | ONIX | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT SUB PROCESS_V1 | 0903255580 KT4839 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 26/10/2026 | 26/10/2026 |  |  | 125 |  | 125 |  |  | 24/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903255584-1 IN1156 | BLACK | 90D | S2408MR1600 | 543 | 31/10/2026 | 543 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903255584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 543 |  | 543 |  |  | 29/10/2026 | 30/10/2026 |  |  | 543 |  | 543 |  |  | 28/10/2026 | 29/10/2026 |  |  | 543 |  | 543
ADIDAS | 0903255589-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903255589 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903255616-1 IN1172 | BLACK | 90D | S2408WR1600 | 4574 | 15/10/2026 | 4574 | SI | SI10/07/2026 | G1I | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255616 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 16/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-07-10 | 14/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-06-10 | 13/10/2026 |  |  | 4574 |  | 4574
ADIDAS | 0903255630-1 KA4331 | BLACK | 90D | S2608MR0902 | 1734 | 15/10/2026 | 1734 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255630 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-01-10 | 2026-05-10 |  |  | 1734 |  | 1734 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1734 |  | 1734 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1734 |  | 1734
ADIDAS | 0903255643-1 IN1173 | WHITE | 90D | S2408WR1600 | 4544 | 15/10/2026 | 4544 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255643 IN1173 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 17/10/2026 |  |  | 4544 |  | 4544 |  |  | 2026-09-10 | 15/10/2026 |  |  | 4544 |  | 4544 |  |  | 2026-08-10 | 14/10/2026 |  |  | 4544 |  | 4544
ADIDAS | 0903255648-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 251 | 31/10/2026 | 251 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255648 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-11 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 251 |  | 251 |  |  | 2026-04-11 | 2026-06-11 |  |  | 251 |  | 251
ADIDAS | 0903255693-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1026 | 15/10/2026 | 1026 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516204 | PAD+HT SUB PROCESS_V3 | 0903255693 KF5295 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 2026-10-10 | 13/10/2026 |  |  | 1026 |  | 1026 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1026 |  | 1026 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1026 |  | 1026
ADIDAS | 0903255699-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 509 | 15/10/2026 | 509 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255699 KV7863 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 509 |  | 509 |  |  | 2026-07-11 | 2026-09-11 |  |  | 509 |  | 509
ADIDAS | 0903255746-1 IN1157 | WHITE | 90D | S2408MR1600 | 414 | 31/10/2026 | 414 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903255746 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 414 |  | 414 |  |  | 27/10/2026 | 28/10/2026 |  |  | 414 |  | 414 |  |  | 26/10/2026 | 27/10/2026 |  |  | 414 |  | 414
ADIDAS | 0903255776-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1452 | 15/10/2026 | 1452 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255776 JE6414 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 1452 |  | 1452 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1452 |  | 1452
ADIDAS | 0903255794-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 367 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903255794 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903255800-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 149 | 15/10/2026 | 149 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512102 | PRINT L2+HT SUB PROCESS_V3 | 0903255800 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 149 |  | 149 |  |  | 14/10/2026 | 15/10/2026 |  |  | 149 |  | 149 |  |  | 13/10/2026 | 14/10/2026 |  |  | 149 |  | 149
ADIDAS | 0903255801-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1140 | 15/10/2026 | 1140 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255801 JE6338 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1140 |  | 1140 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1140 |  | 1140
ADIDAS | 0903255833-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 918 | 15/10/2026 | 918 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255833 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 918 |  | 918 |  |  | 17/10/2026 | 20/10/2026 |  |  | 918 |  | 918
ADIDAS | 0903255882-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1546 | 15/10/2026 | 1546 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255882 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-12-10 |  |  | 1546 |  | 1546 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1546 |  | 1546
ADIDAS | 0903255908-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255908 JE6419 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1278 |  | 1278
ADIDAS | 0903255912-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903255912 KF5295 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 15/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 15/10/2026 | 19/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-12-10 | 15/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-10-10 | 14/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903255968-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516442 | PAD+HT SUB PROCESS_V3 | 0903255968 KF5295 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 13/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 13/10/2026 | 15/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1967 |  | 1967 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1967 |  | 1967
ADIDAS | 0903255969-1 IN1156 | BLACK | 90D | S2408MR1600 | 1798 | 31/10/2026 | 1798 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903255969 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI | 2026-03-11 | 2026-06-11 |  |  | 1798 |  | 1798 |  |  | 31/10/2026 | 2026-04-11 |  |  | 1798 |  | 1798 |  |  | 30/10/2026 | 2026-03-11 |  |  | 1798 |  | 1798
ADIDAS | 0903255971-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 803 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903255971 KA0247 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903255977-1 LF0718 | BLACK | 105D | S2754MAS512B | 453 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255977 LF0718 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255999-1 IN1173 | WHITE | 90D | S2408WR1600 | 1056 | 31/10/2026 | 1056 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903255999 IN1173 |  | KAHATEX CIJERAH | ISRAEL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 1056 |  | 1056 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1056 |  | 1056 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1056 |  | 1056
ADIDAS | 0903256009-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903256009 KA0237 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 14/11/2026 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 14/11/2026 | 18/11/2026 |  |  | 1250 |  | 1250 |  |  | 2026-11-11 | 14/11/2026 |  |  | 1250 |  | 1250 |  |  | 2026-10-11 | 13/11/2026 |  |  | 1250 |  | 1250
ADIDAS | 0903256022-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256022 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-11 | M SL WV PT 2 |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 896 |  | 896 |  |  | 2026-02-11 | 2026-04-11 |  |  | 896 |  | 896
ADIDAS | 0903256042-1 IK7442 | WHITE | 105D | S2408WR2400 | 2500 | 31/10/2026 | 2500 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903256042 IK7442 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-06-11 | OTR B TEE WHITE |  | SS27 | 2026-06-11 | 2026-09-11 |  |  | 2500 |  | 2500 |  |  | 2026-04-11 | 2026-06-11 |  |  | 2500 |  | 2500 |  |  | 2026-03-11 | 2026-05-11 |  |  | 2500 |  | 2500
ADIDAS | 0903256045-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 181 | 15/10/2026 | 181 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848024 | PRINT L2+HT SUB PROCESS_V3 | 0903256045 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 181 |  | 181 |  |  | 14/10/2026 | 15/10/2026 |  |  | 181 |  | 181 |  |  | 13/10/2026 | 14/10/2026 |  |  | 181 |  | 181
ADIDAS | 0903256052-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 107 | 23/10/2026 | 107 | AN | AN10/07/2026 | G2E | T-SHIRT | G2 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256052 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L | 2026-12-10 | 13/10/2026 |  |  | 107 |  | 107 |  |  | 2026-08-10 | 2026-09-10 |  |  | 107 |  | 107
ADIDAS | 0903256056-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 455 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256056 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256058-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 564 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256058 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256065-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1251 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256065 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256137-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256137 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903256160-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 154 | 31/10/2026 | 154 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT SUB PROCESS_V1 | 0903256160 KG8553 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 154 |  | 154 |  |  | 24/10/2026 | 27/10/2026 |  |  | 154 |  | 154 |  |  | 23/10/2026 | 26/10/2026 |  |  | 154 |  | 154
ADIDAS | 0903256216-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 160 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903256216 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903256347-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256347 JD5302 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/10/2026 | W 3S FT CF PT |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 896 |  | 896 |  |  | 24/10/2026 | 26/10/2026 |  |  | 896 |  | 896
ADIDAS | 0903256411-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | (20/08/2026) | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903256411 JE6417 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1278 |  | 1278 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1278 |  | 1278
ADIDAS | 0903256435-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1230 | 15/10/2026 | 1230 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903256435 JE6341 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 1230 |  | 1230 |  |  | 25/09/2026 | 29/09/2026 |  |  | 1230 |  | 1230
ADIDAS | 0903256461-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 792 | 15/10/2026 | 792 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256461 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-04-11 | M SL WV PT 2 |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 792 |  | 792 |  |  | 31/10/2026 | 2026-02-11 |  |  | 792 |  | 792
ADIDAS | 0903256486-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 113 | 15/10/2026 | 113 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903256486 LC8882 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M ADI RETRO T BLACK |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 113 |  | 113 |  |  | 2026-08-10 | 2026-08-10 |  |  | 113 |  | 113
ADIDAS | 0903256510-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1210 | 15/10/2026 | 1210 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256510 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | M SL WV PT 2 |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 1210 |  | 1210 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903256620-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 14/10/2026 | 610 | AN | AN10/07/2026 | G3D | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256620 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 610 |  | 610 |  |  | 26/10/2026 | 26/10/2026 |  |  | 610 |  | 610
ADIDAS | 0903256659-1 KT4840 | ONIX | 90D | S2408MR1600 | 200 | 31/10/2026 | 200 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256659 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 200 |  | 200 |  |  | 23/10/2026 | 24/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903256662-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 557 | 31/10/2026 | 557 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 12-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256662 KY4155 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 557 |  | 557 |  |  | 19/10/2026 | 21/10/2026 |  |  | 557 |  | 557
ADIDAS | 0903256720-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 302 | 31/10/2026 | 302 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256720 KY6510 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | M 3S CHELSEA B7 |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 302 |  | 302 |  |  | 28/10/2026 | 29/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903256755-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 209 | 15/10/2026 | 209 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256755 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 209 |  | 209 |  |  | 24/09/2026 | 25/09/2026 |  |  | 209 |  | 209
ADIDAS | 0903256760-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1957 | 31/10/2026 | 1957 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256760 KY6510 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | M 3S CHELSEA B7 |  | SS27 | 2026-02-11 | 2026-05-11 |  |  | 1957 |  | 1957 |  |  | 29/10/2026 | 2026-02-11 |  |  | 1957 |  | 1957
ADIDAS | 0903256777-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 280 | 23/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903256777 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903256779-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 119 | 15/10/2026 | 119 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903256779 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 119 |  | 119 |  |  | 24/09/2026 | 25/09/2026 |  |  | 119 |  | 119
ADIDAS | 0903256801-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 121 | 15/10/2026 | 121 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256801 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 121 |  | 121 |  |  | 24/09/2026 | 25/09/2026 |  |  | 121 |  | 121
ADIDAS | 0903256825-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 132 | 15/10/2026 | 132 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903256825 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 132 |  | 132 |  |  | 2026-02-10 | 2026-03-10 |  |  | 132 |  | 132
ADIDAS | 0903256829-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 364 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256829 LE8188 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903256846-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 216 | 15/10/2026 | 216 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256846 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 216 |  | 216 |  |  | 2026-01-10 | 2026-02-10 |  |  | 216 |  | 216
ADIDAS | 0903256847-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 210 | 15/10/2026 | 210 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256847 JE6346 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | M 3S FT TC PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 210 |  | 210 |  |  | 2026-06-10 | 2026-07-10 |  |  | 210 |  | 210
ADIDAS | 0903256851-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256851 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 288 |  | 288 |  |  | 2026-01-10 | 2026-03-10 |  |  | 288 |  | 288
ADIDAS | 0903256866-1 KA0246 | BLACK | 105D | S2608WR0902 | 230 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | PAD+HT SUB PROCESS_V3 | 0903256866 KA0246 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903256871-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 124 | 15/10/2026 | 124 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256871 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 124 |  | 124 |  |  | 2026-01-10 | 2026-02-10 |  |  | 124 |  | 124
ADIDAS | 0903256876-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 266 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848024 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256876 KY5988 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903256878-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 299 | 15/10/2026 | 299 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256878 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | M 3S FT TC PT |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 299 |  | 299 |  |  | 2026-09-10 | 2026-10-10 |  |  | 299 |  | 299
ADIDAS | 0903256884-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256884 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 342 |  | 342 |  |  | 2026-05-11 | 2026-06-11 |  |  | 342 |  | 342
ADIDAS | 0903256891-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 269 | 15/10/2026 | 269 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903256891 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 269 |  | 269 |  |  | 2026-03-10 | 2026-05-10 |  |  | 269 |  | 269
ADIDAS | 0903256901-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256901 LF1392 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-05-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 107 |  | 107 |  |  | 2026-01-10 | 2026-06-10 |  |  | 107 |  | 107
ADIDAS | 0903256903-1 LE8187 | BLACK | 105D | S2754MAS513 | 212 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256903 LE8187 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903256918-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 31/10/2026 | 148 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256918 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 148 |  | 148 |  |  | 2026-04-11 | 2026-04-11 |  |  | 148 |  | 148 |  |  | 2026-03-11 | 2026-03-11 |  |  | 148 |  | 148
ADIDAS | 0903256955-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 219 | 15/10/2026 | 219 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256955 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 30/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 219 |  | 219 |  |  | 27/10/2026 | 28/10/2026 |  |  | 219 |  | 219
ADIDAS | 0903256972-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 123 | 15/10/2026 | 123 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512102 | PRINT L2+PAD SUB PROCESS_V3 | 0903256972 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 123 |  | 123 |  |  | 2026-08-10 | 2026-09-10 |  |  | 123 |  | 123
ADIDAS | 0903257022-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257022 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-05-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 120 |  | 120 |  |  | 2026-01-10 | 2026-06-10 |  |  | 120 |  | 120
ADIDAS | 0903257051-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 144 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257051 KC5231 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903257161-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 176 | 15/10/2026 | 176 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257161 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 176 |  | 176 |  |  | 24/09/2026 | 25/09/2026 |  |  | 176 |  | 176
ADIDAS | 0903257172-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 119 | 15/10/2026 | 119 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257172 LG8055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 119 |  | 119 |  |  | 2026-02-10 | 2026-02-10 |  |  | 119 |  | 119
ADIDAS | 0903257177-1 IS1413 | BLACK | 60D | S2425M405 | 1203 | 2026-12-09 | 1203 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903257177 IS1413 | 26/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | IN RANGE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 1203 | 1203 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-03-09 | 2026-11-09 | 1203 | 1203
ADIDAS | 0903257182-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 336 | 15/10/2026 | 336 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257182 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 336 |  | 336 |  |  | 2026-01-10 | 2026-02-10 |  |  | 336 |  | 336
ADIDAS | 0903257188-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 246 | 23/10/2026 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903257188 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903257198-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 404 | 15/10/2026 | 404 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257198 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 404 |  | 404 |  |  | 2026-02-10 | 2026-03-10 |  |  | 404 |  | 404
ADIDAS | 0903257203-1 HK7309 | BLACK | 45D | F2225M402 | 1653 | 2026-09-09 | 1653 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257203 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 31/08/2026 | 2026-07-09 | 1653 | 1653 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-10-09 | 1653 | 1653
ADIDAS | 0903257220-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257220 KU7520 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-02-11 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 180 |  | 180 |  |  | 30/10/2026 | 31/10/2026 |  |  | 180 |  | 180 |  |  | 29/10/2026 | 30/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257227-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 101 | 15/10/2026 | 101 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257227 LG8056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-02-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903257245-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 848016 | HT SUB PROCESS_V1 | 0903257245 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-11 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-03-11 | 2026-04-11 |  |  | 180 |  | 180 |  |  | 31/10/2026 | 2026-02-11 |  |  | 180 |  | 180 |  |  | 30/10/2026 | 31/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257251-1 IN1159 | BLACK | 90D | S2408MR1601 | 162 | 31/10/2026 | 162 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903257251 IN1159 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-06-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-11 | 2026-06-11 |  |  | 162 |  | 162 |  |  | 2026-04-11 | 2026-04-11 |  |  | 162 |  | 162 |  |  | 2026-03-11 | 2026-03-11 |  |  | 162 |  | 162
ADIDAS | 0903257252-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 848 | 15/10/2026 | 848 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257252 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 848 |  | 848 |  |  | 2026-01-10 | 2026-02-10 |  |  | 848 |  | 848
ADIDAS | 0903257264-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257264 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 30/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 30/10/2026 | 2026-02-11 |  |  | 100 |  | 100 |  |  | 28/10/2026 | 30/10/2026 |  |  | 100 |  | 100 |  |  | 27/10/2026 | 29/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903257280-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1098 | 15/10/2026 | 1098 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903257280 IB8686 |  | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 1098 |  | 1098 |  |  | 26/09/2026 | 28/09/2026 |  |  | 1098 |  | 1098
ADIDAS | 0903257284-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257284 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 169 |  | 169 |  |  | 29/09/2026 | 29/09/2026 |  |  | 169 |  | 169
ADIDAS | 0903257292-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903257292 JC8238 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 195 |  | 195 |  |  | 25/09/2026 | 26/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903257307-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 177 | 15/10/2026 | 177 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257307 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 177 |  | 177 |  |  | 28/09/2026 | 28/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903257329-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903257329 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-05-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-05-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903257350-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 140 | 15/10/2026 | 140 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257350 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 21/09/2026 | 21/09/2026 |  |  | 140 |  | 140 |  |  | 17/09/2026 | 17/09/2026 |  |  | 140 |  | 140 |  |  | 16/09/2026 | 16/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903257370-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 302 | 15/10/2026 | 302 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257370 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | W 3S WV SHO |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 302 |  | 302 |  |  | 2026-06-10 | 2026-06-10 |  |  | 302 |  | 302
ADIDAS | 0903257378-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 178 | 15/10/2026 | 178 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257378 LF1392 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-05-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 178 |  | 178 |  |  | 2026-01-10 | 2026-06-10 |  |  | 178 |  | 178
ADIDAS | 0903257558-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 296 | 2026-12-09 | 296 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903257558 KA0544 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 296 | 296 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-01-09 | 296 | 296
ADIDAS | 0903257658-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 272 | 15/10/2026 | 272 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257658 KY3737 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 25/09/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 25/09/2026 | 25/09/2026 |  |  | 272 |  | 272 |  |  | 22/09/2026 | 22/09/2026 |  |  | 272 |  | 272
ADIDAS | 0903257668-1 IN1173 | WHITE | 90D | S2408WR1600 | 269 | 31/10/2026 | 269 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257668 IN1173 |  | KAHATEX CIJERAH | MOROCCO | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 269 |  | 269 |  |  | 2026-12-10 | 13/10/2026 |  |  | 269 |  | 269 |  |  | 2026-10-10 | 2026-12-10 |  |  | 269 |  | 269
ADIDAS | 0903257671-1 IN1159 | BLACK | 90D | S2408MR1601 | 2727 | 15/10/2026 | 2727 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903257671 IN1159 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-10-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-10-10 | 15/10/2026 |  |  | 2727 |  | 2727 |  |  | 2026-08-10 | 13/10/2026 |  |  | 2727 |  | 2727 |  |  | 2026-07-10 | 2026-12-10 |  |  | 2727 |  | 2727
ADIDAS | 0903257687-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257687 KV0458 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 224 |  | 224 |  |  | 22/09/2026 | 24/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903257700-1 IN8707 | BLACK | 105D | S2408WR1601A | 2203 | 15/10/2026 | 2203 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903257700 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 17/10/2026 | 22/10/2026 |  |  | 2203 |  | 2203 |  |  | 15/10/2026 | 20/10/2026 |  |  | 2203 |  | 2203 |  |  | 14/10/2026 | 19/10/2026 |  |  | 2203 |  | 2203
ADIDAS | 0903257706-1 IS1413 | BLACK | 60D | S2425M405 | 396 | 2026-07-10 | 396 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903257706 IS1413 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 396 |  | 396 |  |  | 21/09/2026 | 21/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903257710-1 IN1159 | BLACK | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT SUB PROCESS_V1 | 0903257710 IN1159 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 26/10/2026 | 26/10/2026 |  |  | 125 |  | 125 |  |  | 24/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903257728-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903257728 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300
ADIDAS | 0903257736-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 636 | 15/10/2026 | 636 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257736 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 636 |  | 636 |  |  | 29/09/2026 | 30/09/2026 |  |  | 636 |  | 636
ADIDAS | 0903257739-1 LF0723 | BLACK | 105D | S2754MAS511B | 207 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257739 LF0723 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257740-1 KA4331 | BLACK | 90D | S2608MR0902 | 483 | 15/10/2026 | 483 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257740 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 483 |  | 483 |  |  | 2026-06-10 | 2026-07-10 |  |  | 483 |  | 483 |  |  | 2026-05-10 | 2026-06-10 |  |  | 483 |  | 483
ADIDAS | 0903257744-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903257744 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 23/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903257763-1 IN1157 | WHITE | 90D | S2408MR1600 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903257763 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 275 |  | 275 |  |  | 24/10/2026 | 26/10/2026 |  |  | 275 |  | 275 |  |  | 23/10/2026 | 24/10/2026 |  |  | 275 |  | 275
ADIDAS | 0903257766-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 727 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257766 KV7863 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903257771-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 534 | 15/10/2026 | 534 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257771 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 534 |  | 534 |  |  | 2026-01-10 | 2026-01-10 |  |  | 534 |  | 534
ADIDAS | 0903257777-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 441 | 31/10/2026 | 441 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903257777 KX9855 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-11 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-03-11 | 2026-04-11 |  |  | 441 |  | 441 |  |  | 31/10/2026 | 2026-02-11 |  |  | 441 |  | 441 |  |  | 30/10/2026 | 31/10/2026 |  |  | 441 |  | 441
ADIDAS | 0903257785-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 218 | 15/10/2026 | 218 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848024 | PRINT L2+PAD SUB PROCESS_V3 | 0903257785 LC8884 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 218 |  | 218 |  |  | 2026-08-10 | 2026-09-10 | 26/08/2026 | 29/08/2026 | 218 | 199 | 19
ADIDAS | 0903257807-1 KA4331 | BLACK | 90D | S2608MR0902 | 334 | 15/10/2026 | 334 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903257807 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 334 |  | 334 |  |  | 2026-03-10 | 2026-05-10 |  |  | 334 |  | 334 |  |  | 2026-02-10 | 2026-03-10 |  |  | 334 |  | 334
ADIDAS | 0903257817-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 113 | 15/10/2026 | 113 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257817 LE4307 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 113 |  | 113 |  |  | 2026-01-10 | 2026-03-10 |  |  | 113 |  | 113
ADIDAS | 0903257826-1 KA4331 | BLACK | 90D | S2608MR0902 | 395 | 23/10/2026 | 395 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257826 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 395 |  | 395 |  |  | 21/10/2026 | 22/10/2026 |  |  | 395 |  | 395 |  |  | 20/10/2026 | 21/10/2026 |  |  | 395 |  | 395
ADIDAS | 0903257828-1 IN2961 | BLACK | 105D | S2408WR2400 | 3750 | 31/10/2026 | 3750 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903257828 IN2961 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-11-11 | OTR B TEE BLACK |  | SS27 | 2026-11-11 | 14/11/2026 |  |  | 3750 |  | 3750 |  |  | 2026-09-11 | 2026-12-11 |  |  | 3750 |  | 3750 |  |  | 2026-07-11 | 2026-11-11 |  |  | 3750 |  | 3750
ADIDAS | 0903257833-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 128 | 15/10/2026 | 128 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 848012 | EMBRO SUB PROCESS_V1 | 0903257833 HK7303 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 128 |  | 128 |  |  | 26/09/2026 | 26/09/2026 |  |  | 128 |  | 128
ADIDAS | 0903257836-1 IN1159 | BLACK | 90D | S2408MR1601 | 130 | 31/10/2026 | 130 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903257836 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-06-11 | 2026-06-11 |  |  | 130 |  | 130 |  |  | 2026-04-11 | 2026-04-11 |  |  | 130 |  | 130 |  |  | 2026-03-11 | 2026-03-11 |  |  | 130 |  | 130
ADIDAS | 0903257863-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 111 | 15/10/2026 | 111 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903257863 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 111 |  | 111 |  |  | 26/09/2026 | 26/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903257892-1 LE8187 | BLACK | 105D | S2754MAS513 | 180 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257892 LE8187 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257897-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257897 JD1877 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-03-10 | M 3S FT FZ HD |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278
ADIDAS | 0903257898-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3008 | 15/10/2026 | 3008 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257898 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 29/09/2026 | 2026-03-10 |  |  | 3008 |  | 3008 |  |  | 25/09/2026 | 30/09/2026 |  |  | 3008 |  | 3008
ADIDAS | 0903257900-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903257900 KG3234 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-11 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 2026-09-11 | 2026-12-11 |  |  | 1250 |  | 1250 |  |  | 2026-05-11 | 2026-09-11 |  |  | 1250 |  | 1250 |  |  | 2026-04-11 | 2026-07-11 |  |  | 1250 |  | 1250
ADIDAS | 0903257913-1 KA4331 | BLACK | 90D | S2608MR0902 | 306 | 15/10/2026 | 306 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257913 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 306 |  | 306 |  |  | 2026-03-10 | 2026-05-10 |  |  | 306 |  | 306 |  |  | 2026-02-10 | 2026-03-10 |  |  | 306 |  | 306
ADIDAS | 0903257952-1 IN1172 | BLACK | 90D | S2408WR1600 | 380 | 31/10/2026 | 380 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257952 IN1172 |  | KAHATEX CIJERAH | MOROCCO | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 380 |  | 380 |  |  | 24/10/2026 | 24/10/2026 |  |  | 380 |  | 380 |  |  | 23/10/2026 | 23/10/2026 |  |  | 380 |  | 380
ADIDAS | 0903257978-1 IN1159 | BLACK | 90D | S2408MR1601 | 163 | 31/10/2026 | 163 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903257978 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-05-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 163 |  | 163 |  |  | 2026-03-11 | 2026-04-11 |  |  | 163 |  | 163 |  |  | 2026-02-11 | 2026-03-11 |  |  | 163 |  | 163
ADIDAS | 0903257985-1 IK7442 | WHITE | 105D | S2408WR2400 | 1056 | 31/10/2026 | 1056 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903257985 IK7442 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-05-11 | OTR B TEE WHITE |  | SS27 | 2026-05-11 | 2026-06-11 |  |  | 1056 |  | 1056 |  |  | 2026-03-11 | 2026-04-11 |  |  | 1056 |  | 1056 |  |  | 2026-02-11 | 2026-03-11 |  |  | 1056 |  | 1056
ADIDAS | 0903258010-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1100 | 15/10/2026 | 1100 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903258010 JG8642 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | W LIN FT SHO |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1100 |  | 1100 |  |  | 26/09/2026 | 29/09/2026 | 2026-09-09 | 2026-11-09 | 1100 | 1056 | 44
ADIDAS | 0903258044-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 304 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258044 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258059-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 1550 | 31/10/2026 | 1550 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903258059 JW9678 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-11 | OTR B TEE POWDER PLUM F25 |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 1550 |  | 1550 |  |  | 2026-06-11 | 2026-07-11 |  |  | 1550 |  | 1550 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1550 |  | 1550
ADIDAS | 0903258064-1 KA0527 | PURE RUBY S25 | 60D | S26KJUGFX003 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 1st Art (TC 10 pcs) 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258064 KA0527 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | J SUMMER T |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 100 |  | 100 |  |  | 2026-09-10 | 2026-09-10 | 15/09/2026 | 15/09/2026 | 100 | 59 | 41 |  | 59
ADIDAS | 0903258089-1 LE8187 | BLACK | 105D | S2754MAS513 | 1030 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258089 LE8187 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903258094-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 100 | 31/10/2026 | 100 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 10-Aug, ETD 10-Aug, ETA KH 21-Aug. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258094 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 100 |  | 100 |  |  | 30/10/2026 | 2026-02-11 |  |  | 100 |  | 100
ADIDAS | 0903258118-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903258118 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 368 |  | 368 |  |  | 2026-07-10 | 2026-08-10 | 2026-09-09 | 2026-09-09 | 368 | 349 | 19
ADIDAS | 0903258121-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 117 | 15/10/2026 | 117 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258121 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 117 |  | 117 |  |  | 2026-01-10 | 2026-06-10 |  |  | 117 |  | 117
ADIDAS | 0903258126-1 IN1157 | WHITE | 90D | S2408MR1600 | 319 | 23/10/2026 | 319 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903258126 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 319 |  | 319 |  |  | 24/10/2026 | 24/10/2026 |  |  | 319 |  | 319 |  |  | 23/10/2026 | 23/10/2026 |  |  | 319 |  | 319
ADIDAS | 0903258151-1 IN1160 | WHITE | 90D | S2408MR1601 | 585 | 31/10/2026 | 585 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903258151 IN1160 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 31/10/2026 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 585 |  | 585 |  |  | 29/10/2026 | 30/10/2026 |  |  | 585 |  | 585 |  |  | 28/10/2026 | 29/10/2026 |  |  | 585 |  | 585
ADIDAS | 0903258170-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258170 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 23/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 23/10/2026 | 23/10/2026 |  |  | 107 |  | 107 |  |  | 20/10/2026 | 20/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903258209-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 272 | 15/10/2026 | 272 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903258209 LI7655 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 272 |  | 272 |  |  | 2026-01-10 | 2026-01-10 |  |  | 272 |  | 272
ADIDAS | 0903258217-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 584 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 516343 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258217 KC8152 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258233-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1002 | 15/10/2026 | 1002 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903258233 JE6419 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1002 |  | 1002 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1002 |  | 1002
ADIDAS | 0903258257-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1403 | 2026-09-09 | 1403 | SA | SA10/07/2026 | G3H | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258257 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403
ADIDAS | 0903258260-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258260 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 23/10/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 23/10/2026 | 23/10/2026 |  |  | 107 |  | 107 |  |  | 20/10/2026 | 20/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903258292-1 KT4839 | ONIX | 90D | S2408MR1601 | 161 | 31/10/2026 | 161 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT SUB PROCESS_V1 | 0903258292 KT4839 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 161 |  | 161 |  |  | 26/10/2026 | 27/10/2026 |  |  | 161 |  | 161 |  |  | 24/10/2026 | 26/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903258321-1 IN1172 | BLACK | 90D | S2408WR1600 | 1722 | 31/10/2026 | 1722 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903258321 IN1172 |  | KAHATEX CIJERAH | ISRAEL | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 31/10/2026 |  |  | 1722 |  | 1722 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1722 |  | 1722 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1722 |  | 1722
ADIDAS | 0903258325-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 111 | 15/10/2026 | 111 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903258325 LI7660 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 111 |  | 111 |  |  | 29/09/2026 | 29/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903258342-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 1448 | 15/10/2026 | 1448 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258342 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 1448 |  | 1448 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1448 |  | 1448
ADIDAS | 0903258375-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258375 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903258612-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 2 | 15/10/2026 | 2 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903258612 IT1469 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 2 |  | 2 |  |  | 2026-08-10 | 2026-09-10 |  |  | 2 |  | 2 |  |  | 2026-07-10 | 2026-08-10 |  |  | 2 |  | 2
ADIDAS | 0903258647-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 4605 | 15/10/2026 | 4605 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903258647 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 13/10/2026 |  |  | 4605 |  | 4605 |  |  | 2026-06-10 | 2026-10-10 |  |  | 4605 |  | 4605 |  |  | 2026-05-10 | 2026-09-10 |  |  | 4605 |  | 4605
ADIDAS | 0903258660-1 KT4839 | ONIX | 90D | S2408MR1601 | 112 | 31/10/2026 | 112 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903258660 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 28/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 112 |  | 112 |  |  | 26/10/2026 | 27/10/2026 |  |  | 112 |  | 112 |  |  | 24/10/2026 | 26/10/2026 |  |  | 112 |  | 112
ADIDAS | 0903258675-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 2130 | 15/10/2026 | 2130 | SI | SI10/07/2026 | G1D | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258675 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 23/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 23/10/2026 | 27/10/2026 |  |  | 2130 |  | 2130 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2130 |  | 2130 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2130 |  | 2130
ADIDAS | 0903258696-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 510 | 14/10/2026 | 510 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258696 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 510 |  | 510 |  |  | 30/09/2026 | 2026-01-10 |  |  | 510 |  | 510
ADIDAS | 0903258702-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258702 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 120 |  | 120 |  |  | 2026-07-10 | 2026-08-10 | 2026-11-09 | 2026-11-09 | 120 | 19 | 101
ADIDAS | 0903258720-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1066 | 15/10/2026 | 1066 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903258720 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 1066 |  | 1066 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1066 |  | 1066
ADIDAS | 0903258750-1 IN1157 | WHITE | 90D | S2408MR1600 | 6183 | 15/10/2026 | 6183 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903258750 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 21/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-12-10 | 19/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-10-10 | 17/10/2026 |  |  | 6183 |  | 6183
ADIDAS | 0903258776-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 488 | 15/10/2026 | 488 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258776 LF1392 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-05-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 488 |  | 488 |  |  | 2026-01-10 | 2026-06-10 |  |  | 488 |  | 488
ADIDAS | 0903258807-1 IN8707 | BLACK | 105D | S2408WR1601A | 65 | 15/10/2026 | 65 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258807 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 17/10/2026 | 22/10/2026 |  |  | 65 |  | 65 |  |  | 15/10/2026 | 20/10/2026 |  |  | 65 |  | 65 |  |  | 14/10/2026 | 19/10/2026 |  |  | 65 |  | 65
ADIDAS | 0903258822-1 IN1156 | BLACK | 90D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258822 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 1 |  | 1 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1 |  | 1 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903258858-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 672027 | HT SUB PROCESS_V1 | 0903258858 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 250 |  | 250 |  |  | 19/10/2026 | 20/10/2026 |  |  | 250 |  | 250 |  |  | 17/10/2026 | 19/10/2026 | 2026-04-09 | 2026-12-09 | 250 | 81 | 169
ADIDAS | 0903258880-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903258880 KZ2984 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 138 |  | 138 |  |  | 2026-04-11 | 2026-04-11 |  |  | 138 |  | 138 |  |  | 2026-03-11 | 2026-03-11 |  |  | 138 |  | 138
ADIDAS | 0903258889-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903258889 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903258929-1 IN1157 | WHITE | 90D | S2408MR1600 | 145 | 15/10/2026 | 145 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258929 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-02-10 |  |  | 145 |  | 145 |  |  | 30/09/2026 | 30/09/2026 |  |  | 145 |  | 145 |  |  | 29/09/2026 | 29/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903258964-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 05-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258964 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 13/10/2026 | 20/08/2026 | 29/08/2026 | 100 | 99 | 1 |  |  | 2026-12-10 | 2026-12-10 | 19/08/2026 | 28/08/2026 | 100 | 99 | 1
ADIDAS | 0903258997-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903258997 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 60 |  | 60 |  |  | 2026-06-10 | 2026-07-10 |  |  | 60 |  | 60 |  |  | 2026-05-10 | 2026-06-10 |  |  | 60 |  | 60
ADIDAS | 0903259051-1 KA4331 | BLACK | 90D | S2608MR0902 | 62 | 15/10/2026 | 62 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903259051 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 62 |  | 62 |  |  | 2026-06-10 | 2026-07-10 |  |  | 62 |  | 62 |  |  | 2026-05-10 | 2026-06-10 |  |  | 62 |  | 62
ADIDAS | 0903259083-1 KT4839 | ONIX | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903259083 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 2026-01-10 | 2026-05-10 |  |  | 60 |  | 60 |  |  | 29/09/2026 | 2026-02-10 |  |  | 60 |  | 60 |  |  | 28/09/2026 | 2026-01-10 |  |  | 60 |  | 60
ADIDAS | 0903259087-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259087 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 200 |  | 200 |  |  | 2026-01-10 | 2026-02-10 |  |  | 200 |  | 200
ADIDAS | 0903259113-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 228 | 15/10/2026 | 228 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259113 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 228 |  | 228 |  |  | 2026-03-10 | 2026-05-10 |  |  | 228 |  | 228
ADIDAS | 0903259117-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 135 | 15/10/2026 | 135 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903259117 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 16/10/2026 | 17/10/2026 |  |  | 135 |  | 135 |  |  | 13/10/2026 | 14/10/2026 |  |  | 135 |  | 135 |  |  | 2026-12-10 | 13/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903259145-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I., PI Date 14-Aug, material quality issues body: stain), body&mesh actual receives 18-Aug. 672027 | HT SUB PROCESS_V1 | 0903259145 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-03-10 | 2026-04-09 | 2026-07-09 | 100 | 98 | 2 |  |  | 2026-01-10 | 2026-02-10 | 29/08/2026 | 15/09/2026 | 100 | 100 |  |  | 2
ADIDAS | 0903259225-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 101 | 15/10/2026 | 101 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903259225 JE6419 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 101 |  | 101 |  |  | 24/09/2026 | 25/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903259421-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 35000 | 30/09/2026 | 35000 | SA | SA10/07/2026 | G2I,G2J,G2L | T-SHIRT | G2 | ok | ok | 29/09: ex-fty (1x20). DRC 0090-early shipment customer (GTS89140-1 Early Shipment Order 0903259421). 834012 | HT+PAD SUB PROCESS_V3 | 0903259421 KB5966 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 18/09/2026 | Run Ess Tee M |  | SS27-TI | 18/09/2026 | 2026-03-10 |  |  | 35000 |  | 35000 |  |  | 15/09/2026 | 30/09/2026 | 2026-10-09 | 15/09/2026 | 35000 | 17340 | 17660 |  | 8936 | 2026-12-09 | 28/09/2026 | 2026-10-09 | 15/09/2026 | 35000 | 21130 | 13870 |  | 8068
ADIDAS | 0903259496-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1820 | 15/10/2026 | 1820 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903259496 JE6346 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-10 | M 3S FT TC PT |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 1820 |  | 1820 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1820 |  | 1820
ADIDAS | 0903259552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 440 | 15/10/2026 | 440 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259552 KV7963 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 440 |  | 440 |  |  | 2026-10-10 | 2026-12-10 |  |  | 440 |  | 440
ADIDAS | 0903259561-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903259561 KC8152 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903259603-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 900 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903259603 KF5295 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903259631-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 425 | 15/10/2026 | 425 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259631 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 425 |  | 425 |  |  | 2026-10-10 | 2026-12-10 |  |  | 425 |  | 425
ADIDAS | 0903259633-1 KA0246 | BLACK | 105D | S2608WR0902 | 300 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | PAD+HT SUB PROCESS_V3 | 0903259633 KA0246 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903259656-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259656 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 396 |  | 396 |  |  | 25/09/2026 | 28/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903259689-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 270 | 15/10/2026 | 270 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259689 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S FT CF PT |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 270 |  | 270 |  |  | 24/10/2026 | 26/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903259717-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903259717 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 432 |  | 432 |  |  | 2026-06-10 | 2026-07-10 |  |  | 432 |  | 432
ADIDAS | 0903259814-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 371 | 15/10/2026 | 371 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259814 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 371 |  | 371 |  |  | 2026-07-11 | 2026-09-11 |  |  | 371 |  | 371
ADIDAS | 0903259841-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 225 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259841 JW7178 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903259865-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259865 JC8239 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 195 |  | 195 |  |  | 24/09/2026 | 25/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903259916-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 346 | 23/10/2026 | 346 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259916 LE4307 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 28/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 346 |  | 346 |  |  | 24/10/2026 | 30/10/2026 |  |  | 346 |  | 346
ADIDAS | 0903259938-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 200 | 15/10/2026 | 200 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259938 JG8642 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | W LIN FT SHO |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 26/09/2026 | 29/09/2026 | 2026-11-09 | 2026-11-09 | 200 | 60 | 140
ADIDAS | 0903260151-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 84 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 02-Sep. T2 Teijin Nantong, PI Date 30-Aug, actual receives 31-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260151 LD5446 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903260153-1 IN8707 | BLACK | 105D | S2408WR1601A | 135 | 31/10/2026 | 135 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903260153 IN8707 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 135 |  | 135 |  |  | 26/10/2026 | 27/10/2026 |  |  | 135 |  | 135 |  |  | 24/10/2026 | 26/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903260154-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 208 | 23/10/2026 | 208 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 03-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260154 KZ3204 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 208 |  | 208 |  |  | 24/10/2026 | 30/10/2026 |  |  | 208 |  | 208
ADIDAS | 0903260162-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 160 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 980004 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903260162 KA4914 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903260176-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 647 | 31/10/2026 | 647 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903260176 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 30/10/2026 | 30/10/2026 |  |  | 647 |  | 647 |  |  | 28/10/2026 | 28/10/2026 |  |  | 647 |  | 647 |  |  | 27/10/2026 | 27/10/2026 |  |  | 647 |  | 647
ADIDAS | 0903260189-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 180 | 31/10/2026 | 180 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260189 JN1948 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/10/2026 | W 3S FT QZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 180 |  | 180 |  |  | 27/10/2026 | 28/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903260199-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903260199 JD1877 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1203 |  | 1203 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903260204-1 IN1156 | BLACK | 90D | S2408MR1600 | 445 | 31/10/2026 | 445 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903260204 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 445 |  | 445 |  |  | 29/10/2026 | 30/10/2026 |  |  | 445 |  | 445 |  |  | 28/10/2026 | 29/10/2026 |  |  | 445 |  | 445
ADIDAS | 0903260210-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G2A | SHORTS | G2 | (20/08/2026) | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903260210 KD4872 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-05-10 | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-03-10 |  |  | 100 |  | 100
ADIDAS | 0903260217-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 703 | 15/10/2026 | 703 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260217 JE0052 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 27/10/2026 | W 3S FT FZ HD |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 703 |  | 703 |  |  | 23/10/2026 | 24/10/2026 |  |  | 703 |  | 703
ADIDAS | 0903260237-1 IN1173 | WHITE | 90D | S2408WR1600 | 663 | 31/10/2026 | 663 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260237 IN1173 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 14/10/2026 |  |  | 663 |  | 663 |  |  | 2026-12-10 | 2026-12-10 |  |  | 663 |  | 663 |  |  | 2026-10-10 | 2026-10-10 |  |  | 663 |  | 663
ADIDAS | 0903260251-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903260251 LD0277 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 13/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 102 |  | 102 |  |  | 2026-10-11 | 2026-11-11 |  |  | 102 |  | 102 |  |  | 2026-09-11 | 2026-10-11 |  |  | 102 |  | 102
ADIDAS | 0903260280-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903260280 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 300 |  | 300 |  |  | 2026-03-11 | 2026-04-11 |  |  | 300 |  | 300 |  |  | 2026-02-11 | 2026-03-11 |  |  | 300 |  | 300
ADIDAS | 0903260281-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 285 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260281 LF0721 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260282-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 302 | 15/10/2026 | 302 | SA | SA10/07/2026 | G3K | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260282 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | W 3S FT OH PT |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 302 |  | 302 |  |  | 2026-12-10 | 13/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903260342-1 KG8547 | ONIX | 90D | S2408WR1600 | 209 | 31/10/2026 | 209 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903260342 KG8547 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI | 2026-03-11 | 2026-03-11 |  |  | 209 |  | 209 |  |  | 31/10/2026 | 31/10/2026 |  |  | 209 |  | 209 |  |  | 30/10/2026 | 30/10/2026 |  |  | 209 |  | 209
ADIDAS | 0903260350-1 LF0723 | BLACK | 105D | S2754MAS511B | 252 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260350 LF0723 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903260366-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 400 | 31/10/2026 | 400 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260366 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 400 |  | 400 |  |  | 30/10/2026 | 2026-02-11 |  |  | 400 |  | 400
ADIDAS | 0903260410-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 252 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260410 LE8181 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903260434-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260434 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 327 |  | 327 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 311 | 16 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 313 | 14
ADIDAS | 0903260463-1 IN1172 | BLACK | 90D | S2408WR1600 | 676 | 31/10/2026 | 676 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260463 IN1172 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 676 |  | 676 |  |  | 24/10/2026 | 26/10/2026 |  |  | 676 |  | 676 |  |  | 23/10/2026 | 24/10/2026 |  |  | 676 |  | 676
ADIDAS | 0903260486-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 473 | 31/10/2026 | 473 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260486 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-11 | ADIZERO E TEE |  | SS27-YTI | 2026-05-11 | 2026-06-11 |  |  | 473 |  | 473 |  |  | 2026-03-11 | 2026-04-11 |  |  | 473 |  | 473 |  |  | 2026-02-11 | 2026-03-11 |  |  | 473 |  | 473
ADIDAS | 0903260517-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 331 | 23/10/2026 |  | AN | AN10/07/2026 |  | SHORTS |  | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260517 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903260543-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 252 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260543 LF0718 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903260741-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 212 | 15/10/2026 | 212 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903260741 KV0458 |  | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 212 |  | 212 |  |  | 22/09/2026 | 24/09/2026 |  |  | 212 |  | 212
ADIDAS | 0903261098-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903261098 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261108-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261108 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261122-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261122 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 15/09/2026 | MER KA GFSWT M BLACK |  | SS27-MS | 15/09/2026 | 15/09/2026 |  |  | 2 |  | 2 |  |  | 2026-11-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903261168-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 35 | 15/10/2026 | 35 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903261168 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 35 |  | 35 |  |  | 20/10/2026 | 21/10/2026 |  |  | 35 |  | 35 |  |  | 19/10/2026 | 20/10/2026 |  |  | 35 |  | 35
ADIDAS | 0903261379-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 434 | 31/10/2026 | 434 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903261379 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-11 | 2026-04-11 |  |  | 434 |  | 434 |  |  | 31/10/2026 | 2026-02-11 |  |  | 434 |  | 434 |  |  | 30/10/2026 | 31/10/2026 |  |  | 434 |  | 434
ADIDAS | 0903261439-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 700 | 31/10/2026 | 700 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261439 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-11 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-06-11 | 2026-09-11 |  |  | 700 |  | 700 |  |  | 2026-03-11 | 2026-05-11 |  |  | 700 |  | 700 |  |  | 2026-02-11 | 2026-04-11 |  |  | 700 |  | 700
ADIDAS | 0903261459-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 531 | 31/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903261459 KX3654 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903261492-1 IN1157 | WHITE | 90D | S2408MR1600 | 507 | 31/10/2026 | 507 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261492 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 507 |  | 507 |  |  | 27/10/2026 | 28/10/2026 |  |  | 507 |  | 507 |  |  | 26/10/2026 | 27/10/2026 |  |  | 507 |  | 507
ADIDAS | 0903261529-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261529 LD0292 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 300 |  | 300 |  |  | 2026-07-11 | 2026-10-11 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-09-11 |  |  | 300 |  | 300
ADIDAS | 0903261558-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 1889 | 31/10/2026 | 1889 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (Mexico). T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 652001 | HT SUB PROCESS_V1 | 0903261558 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-11 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 2026-02-11 | 2026-04-11 |  |  | 1889 |  | 1889 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1889 |  | 1889 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1889 |  | 1889
ADIDAS | 0903261586-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 360 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903261586 KY5988 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903261602-1 KA0246 | BLACK | 105D | S2608WR0902 | 12 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | PAD+HT SUB PROCESS_V3 | 0903261602 KA0246 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903261626-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 349 | 15/10/2026 | 349 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903261626 KG8553 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 349 |  | 349 |  |  | 2026-06-10 | 2026-07-10 |  |  | 349 |  | 349 |  |  | 2026-05-10 | 2026-06-10 |  |  | 349 |  | 349
ADIDAS | 0903261645-1 KT4840 | ONIX | 90D | S2408MR1600 | 2134 | 31/10/2026 | 2134 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261645 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 29/10/2026 |  |  | 2134 |  | 2134 |  |  | 24/10/2026 | 27/10/2026 |  |  | 2134 |  | 2134 |  |  | 23/10/2026 | 26/10/2026 |  |  | 2134 |  | 2134
ADIDAS | 0903262069-1 IS1413 | BLACK | 60D | S2425M405 | 944 | 2026-09-09 | 944 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903262069 IS1413 | 26/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 944 | 944 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 944 | 944
ADIDAS | 0903262104-1 IL7232 | BLACK | 105D | S2408MR3202 | 367 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 804028 | PAD+HT SUB PROCESS_V3 | 0903262104 IL7232 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903262266-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 395 | 15/10/2026 | 395 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903262266 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 395 |  | 395 |  |  | 29/09/2026 | 29/09/2026 |  |  | 395 |  | 395
ADIDAS | 0903262302-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 285 | 15/10/2026 | 285 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903262302 LI7656 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 285 |  | 285 |  |  | 28/09/2026 | 29/09/2026 |  |  | 285 |  | 285
ADIDAS | 0903262654-1 KA4331 | BLACK | 90D | S2608MR0902 | 1174 | 30/10/2026 | 1174 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  | ok | (Mexico). DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262654 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 31/10/2026 | 2026-03-11 |  |  | 1174 |  | 1174 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1174 |  | 1174 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1174 |  | 1174
ADIDAS | 0903262676-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 878 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262676 KD3854 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903262703-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 126 | 15/10/2026 | 126 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262703 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 126 |  | 126 |  |  | 2026-07-11 | 2026-09-11 |  |  | 126 |  | 126
ADIDAS | 0903262736-1 KG8547 | ONIX | 90D | S2408WR1600 | 343 | 31/10/2026 | 343 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262736 KG8547 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI | 2026-03-11 | 2026-03-11 |  |  | 343 |  | 343 |  |  | 31/10/2026 | 31/10/2026 |  |  | 343 |  | 343 |  |  | 30/10/2026 | 30/10/2026 |  |  | 343 |  | 343
ADIDAS | 0903262752-1 IK7442 | WHITE | 105D | S2408WR2400 | 190 | 31/10/2026 | 190 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903262752 IK7442 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-04-11 | OTR B TEE WHITE |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 190 |  | 190 |  |  | 2026-02-11 | 2026-03-11 |  |  | 190 |  | 190 |  |  | 31/10/2026 | 2026-02-11 |  |  | 190 |  | 190
ADIDAS | 0903262767-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 1656 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903262767 KY5988 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903262778-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 125 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903262778 KF5295 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903262788-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1466 | 31/10/2026 | 1466 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262788 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-09-11 |  |  | 1466 |  | 1466 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1466 |  | 1466 |  |  | 2026-03-11 | 2026-05-11 |  |  | 1466 |  | 1466
ADIDAS | 0903262820-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 190 | 15/10/2026 | 190 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903262820 JE6346 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-09-10 | M 3S FT TC PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 190 |  | 190 |  |  | 2026-06-10 | 2026-07-10 |  |  | 190 |  | 190
ADIDAS | 0903262839-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 31/10/2026 | 300 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262839 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-11 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 2026-12-11 | 14/11/2026 |  |  | 300 |  | 300 |  |  | 2026-09-11 | 2026-11-11 |  |  | 300 |  | 300 |  |  | 2026-07-11 | 2026-10-11 |  |  | 300 |  | 300
ADIDAS | 0903262846-1 LE8187 | BLACK | 105D | S2754MAS513 | 329 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262846 LE8187 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903262866-1 KT4839 | ONIX | 90D | S2408MR1601 | 2542 | 30/10/2026 | 2542 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903262866 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-05-11 |  |  | 2542 |  | 2542 |  |  | 29/10/2026 | 2026-03-11 |  |  | 2542 |  | 2542 |  |  | 28/10/2026 | 2026-02-11 |  |  | 2542 |  | 2542
ADIDAS | 0903262869-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262869 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903262892-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262892 IN8707 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903262893-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 407 | 23/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903262893 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903262897-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262897 LE8181 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262920-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 1163 | 31/10/2026 | 1163 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262920 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-09-11 |  |  | 1163 |  | 1163 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1163 |  | 1163 |  |  | 2026-03-11 | 2026-05-11 |  |  | 1163 |  | 1163
ADIDAS | 0903262943-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 406 | 31/10/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903262943 KX3655 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262965-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 1142 | 31/10/2026 | 1142 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262965 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-11 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 1142 |  | 1142 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1142 |  | 1142 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1142 |  | 1142
ADIDAS | 0903262992-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 572 | 30/09/2026 | 572 | SI | SI10/07/2026 | G1E | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). IMPROVE. DRC 0010-T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 652001 | HT SUB PROCESS_V1 | 0903262992 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 572 |  | 572 |  |  | 18/09/2026 | 19/09/2026 | 29/08/2026 | 2026-04-09 | 572 | 569 | 3 |  |  | 17/09/2026 | 18/09/2026 | 24/08/2026 | 2026-04-09 | 572 | 569 | 3
ADIDAS | 0903263275-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 160 | 15/10/2026 | 160 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903263275 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 160 |  | 160 |  |  | 14/10/2026 | 15/10/2026 |  |  | 160 |  | 160 |  |  | 13/10/2026 | 14/10/2026 |  |  | 160 |  | 160
ADIDAS | 0903263330-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 160 | 31/10/2026 | 160 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263330 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI | 2026-06-11 | 2026-06-11 |  |  | 160 |  | 160 |  |  | 2026-04-11 | 2026-04-11 |  |  | 160 |  | 160 |  |  | 2026-03-11 | 2026-03-11 |  |  | 160 |  | 160
ADIDAS | 0903263545-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 31/10/2026 | 250 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903263545 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 250 |  | 250 |  |  | 26/10/2026 | 27/10/2026 |  |  | 250 |  | 250 |  |  | 24/10/2026 | 26/10/2026 |  |  | 250 |  | 250
ADIDAS | 0903263584-1 IN1156 | BLACK | 90D | S2408MR1600 | 1058 | 31/10/2026 | 1058 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 1058 |  | 1058 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1058 |  | 1058 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1058 |  | 1058
ADIDAS | 0903263669-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 568 | 30/10/2026 | 568 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903263669 IT1467 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 568 |  | 568 |  |  | 27/10/2026 | 29/10/2026 |  |  | 568 |  | 568 |  |  | 26/10/2026 | 28/10/2026 |  |  | 568 |  | 568
ADIDAS | 0903263698-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2330 | 15/10/2026 | 2330 | AN | AN10/07/2026 | G3B | PANTS | G3 | ok | ok | (Mexico). T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 03-Jul, actual receives 28-Jul. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263698 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/11/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 14/11/2026 | 18/11/2026 |  |  | 2330 |  | 2330 |  |  | 2026-11-11 | 14/11/2026 |  |  | 2330 |  | 2330
ADIDAS | 0903263747-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903263747 JG8639 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 250 |  | 250 |  |  | 29/09/2026 | 2026-01-10 |  |  | 250 |  | 250
ADIDAS | 0903263877-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263877 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 340 |  | 340 |  |  | 2026-10-10 | 2026-10-10 |  |  | 340 |  | 340
ADIDAS | 0903264038-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264038 JC8239 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 1500 |  | 1500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903264065-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 301 | 15/10/2026 | 301 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903264065 JE6414 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301 |  |  | 2026-06-10 | 2026-07-10 |  |  | 301 |  | 301
ADIDAS | 0903264103-1 IN2961 | BLACK | 105D | S2408WR2400 | 1320 | 31/10/2026 | 1320 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903264103 IN2961 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-11 | OTR B TEE BLACK |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 1320 |  | 1320 |  |  | 2026-07-11 | 2026-09-11 |  |  | 1320 |  | 1320 |  |  | 2026-06-11 | 2026-07-11 |  |  | 1320 |  | 1320
ADIDAS | 0903264129-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903264129 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903264137-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264137 JG8639 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1000 |  | 1000 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1000 |  | 1000
ADIDAS | 0903265194-1 KA4331 | BLACK | 90D | S2608MR0902 | 5581 | 15/10/2026 | 5581 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903265194 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 30/09/2026 | 2026-07-10 |  |  | 5581 |  | 5581 |  |  | 26/09/2026 | 2026-03-10 |  |  | 5581 |  | 5581 |  |  | 25/09/2026 | 2026-02-10 |  |  | 5581 |  | 5581
ADIDAS | 0903265258-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 831 | 15/10/2026 | 831 | SI | SI10/07/2026 | G3K | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265258 KD3854 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 19/10/2026 | 21/10/2026 |  |  | 831 |  | 831 |  |  | 15/10/2026 | 17/10/2026 |  |  | 831 |  | 831 |  |  | 2026-12-10 | 14/10/2026 |  |  | 831 |  | 831
ADIDAS | 0903265296-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265296 KF5311 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-09-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903265322-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 572 | 15/10/2026 | 572 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265322 KE8424 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 572 |  | 572 |  |  | 2026-05-10 | 2026-07-10 |  |  | 572 |  | 572 |  |  | 2026-02-10 | 2026-05-10 |  |  | 572 |  | 572
ADIDAS | 0903265342-1 KG8547 | ONIX | 90D | S2408WR1600 | 3535 | 15/10/2026 | 3535 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903265342 KG8547 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 17/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-10-10 | 15/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-09-10 | 14/10/2026 |  |  | 3535 |  | 3535
ADIDAS | 0903265374-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 5948 | 15/10/2026 | 5948 | SA | SA10/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903265374 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 26/10/2026 |  |  | 5948 |  | 5948 |  |  | 16/10/2026 | 23/10/2026 | 2026-12-08 | 14/09/2026 | 5948 | 5867 | 81 |  |  | 15/10/2026 | 22/10/2026 | 2026-12-08 | 14/09/2026 | 5948 | 5944 | 4
ADIDAS | 0903265404-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 1408 | 15/10/2026 | 1408 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265404 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-09-10 | 13/10/2026 |  |  | 1408 |  | 1408 |  |  | 2026-07-10 | 2026-10-10 |  |  | 1408 |  | 1408 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1408 |  | 1408
ADIDAS | 0903265435-1 KT4840 | ONIX | 90D | S2408MR1600 | 5404 | 15/10/2026 | 5404 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903265435 KT4840 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 16/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-07-10 | 14/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-06-10 | 13/10/2026 |  |  | 5404 |  | 5404
ADIDAS | 0903265463-1 KT4839 | ONIX | 90D | S2408MR1601 | 1613 | 15/10/2026 | 1613 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265463 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 2026-01-10 | 2026-05-10 |  |  | 1613 |  | 1613 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1613 |  | 1613 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1613 |  | 1613
ADIDAS | 0903266153-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 309 | 15/10/2026 | 309 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266153 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 309 |  | 309 |  |  | 2026-03-10 | 2026-03-10 |  |  | 309 |  | 309
ADIDAS | 0903266170-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 285 | 15/10/2026 | 285 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266170 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 285 |  | 285 |  |  | 2026-03-10 | 2026-03-10 |  |  | 285 |  | 285
ADIDAS | 0903266198-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 177 | 15/10/2026 | 177 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (06/08/2026) | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266198 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 177 |  | 177 |  |  | 23/09/2026 | 24/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903266331-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266331 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903266349-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266349 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 |  |  | 143 |  | 143
ADIDAS | 0903266371-1 IN1157 | WHITE | 90D | S2408MR1600 | 350 | 23/10/2026 | 350 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516290 | HT SUB PROCESS_V1 | 0903266371 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 27/10/2026 |  |  | 350 |  | 350 |  |  | 24/10/2026 | 24/10/2026 |  |  | 350 |  | 350 |  |  | 23/10/2026 | 23/10/2026 |  |  | 350 |  | 350
ADIDAS | 0903266377-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 355 | 23/10/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903266377 LI7659 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903266421-1 IN1172 | BLACK | 90D | S2408WR1600 | 1030 | 23/10/2026 | 1030 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 516438 | HT SUB PROCESS_V1 | 0903266421 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 1030 |  | 1030 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1030 |  | 1030 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1030 |  | 1030
ADIDAS | 0903266452-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 23/10/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903266452 LC6339 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903266525-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 310 | 15/10/2026 | 310 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266525 LH4535 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 310 |  | 310 |  |  | 2026-10-10 | 2026-10-10 |  |  | 310 |  | 310
ADIDAS | 0903266526-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 273 | 15/10/2026 | 273 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266526 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 273 |  | 273 |  |  | 2026-01-10 | 2026-02-10 |  |  | 273 |  | 273
ADIDAS | 0903266546-1 IN2961 | BLACK | 105D | S2408WR2400 | 240 | 31/10/2026 | 240 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903266546 IN2961 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-10-11 | OTR B TEE BLACK |  | SS27 | 2026-10-11 | 2026-10-11 |  |  | 240 |  | 240 |  |  | 2026-07-11 | 2026-07-11 |  |  | 240 |  | 240 |  |  | 2026-06-11 | 2026-06-11 |  |  | 240 |  | 240
ADIDAS | 0903266548-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266548 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 120 |  | 120 |  |  | 29/09/2026 | 2026-01-10 |  |  | 120 |  | 120
ADIDAS | 0903266578-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266578 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 143 |  | 143 |  |  | 29/09/2026 | 2026-01-10 |  |  | 143 |  | 143
ADIDAS | 0903266593-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 210 | 31/10/2026 | 210 | SI | SI10/07/2026 | G2M | SWEATSHIRT | G2 | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266593 KD4874 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-08-10 | M 3S FT SWT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 210 |  | 210 |  |  | 2026-05-10 | 2026-06-10 |  |  | 210 |  | 210
ADIDAS | 0903266599-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266599 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903269490-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269490 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 28/09/2026 | 28/09/2026 |  |  | 120 |  | 120
ADIDAS | 0903269545-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903269545 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903269592-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 337 | 15/10/2026 | 337 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269592 LI7656 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 337 |  | 337 |  |  | 28/09/2026 | 29/09/2026 |  |  | 337 |  | 337
ADIDAS | 0903269617-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 103 | 15/10/2026 | 103 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903269617 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 103 |  | 103 |  |  | 28/09/2026 | 28/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903270238-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 29 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270238 LF0718 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27-SPOMA
ADIDAS | 0903271653-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903271653 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 107 |  | 107 |  |  | 28/09/2026 | 28/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903271675-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 150 | 15/10/2026 | 150 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903271675 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 150 |  | 150 |  |  | 29/09/2026 | 29/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903272051-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 179 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903272051 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903273743-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 309 | 15/10/2026 | 309 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273743 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 309 |  | 309 |  |  | 27/10/2026 | 28/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903273803-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 305 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273803 KV7863 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903274149-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 607 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903274149 KV7863 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903274607-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903274607 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 29/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903274622-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2L | T-SHIRT | G2 | (09/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274622 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-08-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 2 |  | 2 |  |  | 2026-05-10 | 2026-05-10 | 26/08/2026 | 26/08/2026 | 2 | 1 | 1
ADIDAS | 0903274637-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 2 | 2026-07-10 | 2 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274637 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 2 |  | 2 |  |  | 28/09/2026 | 28/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903276235-1 KY5870 | GREY | 90D | S2750MTR052 | 114 | 15/10/2026 | 114 | SI | SI10/07/2026 | G2C | SHORTS | G2 | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 830009 | HT SUB PROCESS_V1 | 0903276235 KY5870 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D74T ESS SHORTS GREY |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 114 |  | 114 |  |  | 2026-03-10 | 2026-05-10 |  |  | 114 |  | 114 |  |  | 2026-02-10 | 2026-03-10 |  |  | 114 |  | 114
ADIDAS | 0903305162-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 158 | 15/10/2026 | 158 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848016 | PRINT L2+PAD SUB PROCESS_V3 | 0903305162 LC8884 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 158 |  | 158 |  |  | 2026-08-10 | 2026-09-10 | 15/09/2026 | 15/09/2026 | 158 | 144 | 14 |  | 144
ADIDAS | 0903305163-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 198 | 15/10/2026 | 198 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848012 | PRINT L2+PAD SUB PROCESS_V3 | 0903305163 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M RESORT T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 198 |  | 198 |  |  | 2026-08-10 | 2026-09-10 | 26/08/2026 | 26/08/2026 | 198 | 8 | 190
ADIDAS | 0903305164-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 317 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903305164 KY5988 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903306652-1 KA6229 | BLACK | 120D | S2608WR0202 | 255 | 15/10/2026 | 255 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306652 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 255 |  | 255 |  |  | 13/10/2026 | 16/10/2026 |  |  | 255 |  | 255 |  |  | 2026-09-10 | 13/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903306653-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 15/10/2026 | 1009 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306653 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 20/10/2026 | 23/10/2026 |  |  | 1009 |  | 1009 |  |  | 16/10/2026 | 20/10/2026 |  |  | 1009 |  | 1009 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903309141-1 KA4331 | BLACK | 90D | S2608MR0902 | 6720 | 15/10/2026 | 6720 | SA | SA20/07/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. DRC 0064-T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand tex, PI Date 16-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903309141 KA4331 | 2026-02-10 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess 21 S M BLACK |  | SS27 | 29/09/2026 | 2026-09-10 |  |  | 6720 |  | 6720 |  |  | 25/09/2026 | 2026-06-10 |  |  | 6720 |  | 6720 |  |  | 24/09/2026 | 2026-05-10 |  |  | 6720 |  | 6720
ADIDAS | 0903309142-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 3 | 15/10/2026 | 3 | AN | AN20/07/2026 | G2R | SHORTS | G2 |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? Waiting fabroc. T2 Formosa, PI Date ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309142 KZ3231 | 2026-02-10 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 3 |  | 3 |  |  | 2026-09-10 | 2026-09-10 |  |  | 3 |  | 3
ADIDAS | 0903309143-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 28 | 15/10/2026 | 28 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309143 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 28 |  | 28 |  |  | 2026-08-10 | 2026-09-10 |  |  | 28 |  | 28 |  |  | 2026-07-10 | 2026-08-10 |  |  | 28 |  | 28
ADIDAS | 0903309144-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309144 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 1 |  | 1 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1 |  | 1 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1 |  | 1
ADIDAS | 0903309880-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309880 JE6414 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 24/09/2026 | 29/09/2026 |  |  | 2637 |  | 2637 |  |  | 21/09/2026 | 25/09/2026 | 31/08/2026 | 2026-01-09 | 2637 | 2637
ADIDAS | 0903309881-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 6599 | 30/09/2026 | 6599 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309881 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S FT FZ HD |  | SS27 | 21/09/2026 | 28/09/2026 |  |  | 6599 |  | 6599 |  |  | 17/09/2026 | 24/09/2026 |  |  | 6599 |  | 6599
ADIDAS | 0903309882-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 4400 | 30/09/2026 | 4400 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309882 IB8686 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | ESS TEE |  | SS27 | 21/09/2026 | 25/09/2026 |  |  | 4400 |  | 4400 |  |  | 17/09/2026 | 22/09/2026 | 2026-02-09 | 2026-10-09 | 4400 | 4395 | 5
ADIDAS | 0903309883-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3522 | 30/09/2026 | 3522 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309883 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 3522 |  | 3522 |  |  | 22/09/2026 | 26/09/2026 |  |  | 3522 |  | 3522
ADIDAS | 0903309884-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1321 | 30/09/2026 | 1321 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309884 JE6340 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 1321 |  | 1321 |  |  | 2026-12-09 | 15/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903309885-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 3277 | 31/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 14-Aug. 516318 | PAD+HT SUB PROCESS_V3 | 0903309885 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903309886-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 7920 | 30/09/2026 | 7920 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309886 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | W 3S FT CF PT |  | SS27 | 19/09/2026 | 29/09/2026 |  |  | 7920 |  | 7920 |  |  | 16/09/2026 | 25/09/2026 | 15/09/2026 | 15/09/2026 | 7920 | 234 | 7686 |  | 234
ADIDAS | 0903309887-1 HZ0747 | BLACK | 90D | F2325M414 | 9088 | 30/09/2026 | 9088 | SA | SA26/06/2026 | G2R | T-SHIRT | G2 | (29/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309887 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 25/09/2026 |  |  | 9088 |  | 9088 |  |  | 2026-12-09 | 22/09/2026 | 15/09/2026 | 15/09/2026 | 9088 | 395 | 8693 |  | 395
ADIDAS | 0903309888-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 3520 | 30/09/2026 | 3520 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309888 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-05-10 |  |  | 3520 |  | 3520 |  |  | 26/09/2026 | 2026-01-10 |  |  | 3520 |  | 3520
ADIDAS | 0903309889-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 6600 | 30/09/2026 | 6600 | SI | SI26/06/2026 | G3G,G3H | JACKET | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309889 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-07-10 |  |  | 6600 |  | 6600 |  |  | 28/09/2026 | 2026-03-10 | 13/08/2026 | 2026-11-09 | 6600 | 5277 | 1323
ADIDAS | 0903309890-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1050 | 15/10/2026 | 1050 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309890 JM1776 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-11 | M SL WV PT 2 |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 1050 |  | 1050 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1050 |  | 1050
ADIDAS | 0903309891-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1760 | 30/09/2026 | 1760 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309891 KD3911 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | RELEASED |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1760 |  | 1760 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903309892-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1761 | 30/09/2026 | 1761 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309892 JE6341 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 21/09/2026 |  |  | 1761 |  | 1761 |  |  | 2026-12-09 | 17/09/2026 |  |  | 1761 |  | 1761
ADIDAS | 0903309893-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 6602 | 30/09/2026 | 6602 | SI | SI26/06/2026 | G3E,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309893 HR8583 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | ESS SWTP |  | SS27 | 16/09/2026 | 2026-05-10 |  |  | 6602 |  | 6602 |  |  | 2026-12-09 | 2026-01-10 |  |  | 6602 |  | 6602
ADIDAS | 0903309894-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309894 JE6417 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 2637 |  | 2637 |  |  | 23/09/2026 | 28/09/2026 |  |  | 2637 |  | 2637
ADIDAS | 0903309895-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2638 | 30/09/2026 | 2638 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309895 JE6419 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 23/09/2026 | 28/09/2026 |  |  | 2638 |  | 2638 |  |  | 19/09/2026 | 24/09/2026 | 29/08/2026 | 2026-08-09 | 2638 | 2484 | 154
ADIDAS | 0903309897-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 5722 | 30/09/2026 | 5722 | SI | SI26/06/2026 | G3D,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309897 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | ESS SWTP |  | SS27 | 2026-02-10 | 2026-09-10 |  |  | 5722 |  | 5722 |  |  | 29/09/2026 | 2026-06-10 |  |  | 5722 |  | 5722
ADIDAS | 0903309899-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 24312 | 19/09/2026 | 24312 | SA | SA10/07/2026 | G1D, G1E, G1F, G1K, G1L, G1N, G1P, G2A, G2R, G2T, G3A, G3D, G3G, G3H, G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309899 IB8688 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 31/08/2026 | 15/09/2026 | 24312 | 19968 | 4344 |  | 4995 | 27/08/2026 | 19/09/2026 | 24/08/2026 | 15/09/2026 | 24312 | 23142 | 1170 |  | 2263
ADIDAS | 0903309900-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2100 | 15/10/2026 | 2100 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309900 JE6338 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M 3S FT FZ HD |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 2100 |  | 2100 |  |  | 2026-08-10 | 2026-10-10 |  |  | 2100 |  | 2100
ADIDAS | 0903309901-1 HK7319 | BLACK | 90D | F2225M403 | 5282 | 30/09/2026 | 5282 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309901 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ESS SWTP |  | SS27 | 26/09/2026 | 2026-07-10 |  |  | 5282 |  | 5282 |  |  | 23/09/2026 | 2026-03-10 | 15/09/2026 | 15/09/2026 | 5282 | 476 | 4806 |  | 476
ADIDAS | 0903309902-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2940 | 15/10/2026 | 2940 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309902 JD1877 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-09-10 |  |  | 2940 |  | 2940 |  |  | 2026-01-10 | 2026-06-10 |  |  | 2940 |  | 2940
ADIDAS | 0903309903-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1051 | 15/10/2026 | 1051 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309903 JM1775 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV PT 2 |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1051 |  | 1051 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1051 |  | 1051
ADIDAS | 0903309904-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 24142 | 19/09/2026 | 24142 | SA | SA10/07/2026 | G1E,G1F,G1K,G1N,G1P,G2A,G2R,G2T,G3G,G3H,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309904 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 2026-01-09 | 15/09/2026 | 24142 | 20285 | 3857 |  | 3305 | 27/08/2026 | 19/09/2026 | 2026-01-09 | 15/09/2026 | 24142 | 23624 | 518 |  | 2180
ADIDAS | 0903309905-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2642 | 30/09/2026 | 2642 | SI | SI26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Gistex, (3S) PI Date 10-Aug, actual receives 06-Aug (using fabric stock from libolon). T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309905 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV SHO |  | SS27 | 24/09/2026 | 29/09/2026 |  |  | 2642 |  | 2642 |  |  | 21/09/2026 | 25/09/2026 |  |  | 2642 |  | 2642
ADIDAS | 0903309907-1 HK7309 | BLACK | 45D | F2225M402 | 24310 | 19/09/2026 | 24310 | SA | SA10/07/2026 | G1D,G1E,G1F,G1K,G1N,G1P,G2T,G3G,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309907 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 28/08/2026 | 15/09/2026 | 24310 | 21182 | 3128 |  | 2013 | 27/08/2026 | 19/09/2026 | 27/08/2026 | 15/09/2026 | 24310 | 23859 | 451 |  | 1662
ADIDAS | 0903309908-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 3591 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516318 | PAD+HT SUB PROCESS_V3 | 0903309908 KF5295 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX
ADIDAS | 0903309910-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1512 | 15/10/2026 | 1512 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309910 JE6341 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1512 |  | 1512 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1512 |  | 1512
ADIDAS | 0903316928-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) |  | 29/09: ex-fty (NYK warehouse). T2 Y.T.I, Body & mesh actual receives 05-Aug. 800005 | HT SUB PROCESS_V1 | 0903316928 KG8548 | 17/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 21/09/2026 | 2026-05-09 | 15/09/2026 | 327 | 325 | 2 |  | 21 | 29/08/2026 | 18/09/2026 | 2026-11-08 | 22/08/2026 | 327 | 327 |  |  |  | 28/08/2026 | 17/09/2026 | 2026-11-08 | 21/08/2026 | 327 | 327
ADIDAS | 0903316929-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 585 | 30/09/2026 | 585 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) |  | Waiting fabric (NYK warehouse). DRC 0064-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800005 | PRINT L2+HT SUB PROCESS_V3 | 0903316929 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | INDONESIA | SEA | 17/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/09/2026 | 19/09/2026 |  |  | 585 |  | 585 |  |  | 14/09/2026 | 16/09/2026 |  |  | 585 |  | 585 |  |  | 2026-12-09 | 15/09/2026 |  |  | 585 |  | 585
ADIDAS | 0903316930-1 KG8547 | ONIX | 90D | S2408WR1600 | 107 | 15/10/2026 | 107 | SI | SI30/06/2026 | G1I | T-SHIRT | G1 | ok |  | (NYK warehouse). T2 Y.T.I, body & mesh actual receives 08-Aug. 800005 | HT SUB PROCESS_V1 | 0903316930 KG8547 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-09-10 |  |  | 107 |  | 107 |  |  | 2026-07-10 | 2026-07-10 |  |  | 107 |  | 107 |  |  | 2026-06-10 | 2026-06-10 |  |  | 107 |  | 107
ADIDAS | 0903316932-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 798 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903316932 KY9391 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903322460-1 IN1159 | BLACK | 90D | S2408MR1601 | 331 | 2026-07-10 | 331 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT SUB PROCESS_V1 | 0903322460 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 331 |  | 331 |  |  | 19/09/2026 | 21/09/2026 |  |  | 331 |  | 331 |  |  | 18/09/2026 | 19/09/2026 |  |  | 331 |  | 331
ADIDAS | 0903322461-1 IN1157 | WHITE | 90D | S2408MR1600 | 335 | 15/10/2026 | 335 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 06-Aug. 516471 | HT SUB PROCESS_V1 | 0903322461 IN1157 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 335 |  | 335 |  |  | 29/09/2026 | 30/09/2026 | 2026-09-09 | 2026-12-09 | 335 | 308 | 27 |  |  | 28/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 335 | 308 | 27
ADIDAS | 0903322476-1 IN1157 | WHITE | 90D | S2408MR1600 | 845 | 2026-07-10 | 845 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, actual receives 06-Aug. T2 Fu Hsun, Mesh PI Date 03-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322476 IN1157 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 845 |  | 845 |  |  | 25/09/2026 | 26/09/2026 | 2026-10-09 | 14/09/2026 | 845 | 808 | 37 |  |  | 24/09/2026 | 25/09/2026 | 2026-03-09 | 14/09/2026 | 845 | 831 | 14
ADIDAS | 0903322477-1 IN1156 | BLACK | 90D | S2408MR1600 | 553 | 18/09/2026 | 553 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322477 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-02-09 | 2026-05-09 | 553 | 553 |  |  |  | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553
ADIDAS | 0903322478-1 IN1173 | WHITE | 90D | S2408WR1600 | 304 | 15/09/2026 | 304 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516471 | HT SUB PROCESS_V1 | 0903322478 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 304 | 304 |  |  | 7 | 29/08/2026 | 2026-12-09 | 15/08/2026 | 15/08/2026 | 304 | 304 |  |  |  | 28/08/2026 | 2026-11-09 | 2026-11-08 | 2026-11-08 | 304 | 304
ADIDAS | 0903322479-1 IN1172 | BLACK | 90D | S2408WR1600 | 807 | 15/09/2026 | 807 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322479 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 15/09/2026 | 807 | 807 |  |  | 5 | 29/08/2026 | 31/08/2026 | 26/08/2026 | 14/09/2026 | 807 | 806 | 1 |  |  | 28/08/2026 | 29/08/2026 | 26/08/2026 | 2026-12-09 | 807 | 807
ADIDAS | 0903322480-1 IN1156 | BLACK | 90D | S2408MR1600 | 924 | 15/09/2026 | 924 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) 516471 | HT SUB PROCESS_V1 | 0903322480 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-01-09 | 15/09/2026 | 924 | 924 |  |  | 2 | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-09-09 | 924 | 924 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-08-09 | 924 | 924
ADIDAS | 0903322484-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 2026-07-10 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322484 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 24/09/2026 | 26/08/2026 | 2026-02-09 | 300 | 297 | 3 |  |  | 22/09/2026 | 23/09/2026 | 24/08/2026 | 2026-05-09 | 300 | 300
ADIDAS | 0903322486-1 IN1172 | BLACK | 90D | S2408WR1600 | 265 | 15/10/2026 | 265 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322486 IN1172 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 265 |  | 265 |  |  | 20/10/2026 | 21/10/2026 |  |  | 265 |  | 265 |  |  | 19/10/2026 | 20/10/2026 | 2026-05-09 | 15/09/2026 | 265 | 204 | 61 |  | 16
ADIDAS | 0903322488-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 352 | 2026-07-10 | 352 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516471 | HT SUB PROCESS_V1 | 0903322488 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 23/09/2026 |  |  | 352 |  | 352 |  |  | 19/09/2026 | 21/09/2026 | 2026-07-09 | 14/09/2026 | 352 | 175 | 177 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-09 | 2026-12-09 | 352 | 177 | 175
ADIDAS | 0903322491-1 IN1172 | BLACK | 90D | S2408WR1600 | 324 | 30/09/2026 | 324 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322491 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 324 |  | 324 |  |  | 25/09/2026 | 26/09/2026 | 26/08/2026 | 2026-07-09 | 324 | 324 |  |  |  | 24/09/2026 | 25/09/2026 | 26/08/2026 | 2026-04-09 | 324 | 324
ADIDAS | 0903322492-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 254 | 2026-07-10 | 254 | NT | NT24/04/2026 | G1M | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516471 | HT SUB PROCESS_V1 | 0903322492 IT1824 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | ADIZERO E TEE |  | FW26 | 2026-09-10 | 2026-10-10 |  |  | 254 |  | 254 |  |  | 2026-07-10 | 2026-08-10 | 2026-05-08 | 2026-10-08 | 254 | 254 |  |  |  | 2026-06-10 | 2026-07-10 | 2026-05-08 | 2026-10-08 | 254 | 254
ADIDAS | 0903322493-1 IN1156 | BLACK | 90D | S2408MR1600 | 372 | 23/10/2026 | 372 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322493 IN1156 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 372 |  | 372 |  |  | 14/10/2026 | 16/10/2026 |  |  | 372 |  | 372 |  |  | 13/10/2026 | 15/10/2026 |  |  | 372 |  | 372
ADIDAS | 0903348712-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 634 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348712 KU0073 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903348833-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 1013 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348833 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903348882-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 858 | 31/10/2026 | 858 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903348882 KY1335 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-11-11 | M PANCAKE T OFF WHITE |  | SS27-STX | 2026-11-11 | 2026-11-11 |  |  | 858 |  | 858 |  |  | 2026-07-11 | 2026-07-11 |  |  | 858 |  | 858
ADIDAS | 0903351210-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 285 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903351210 KS4777 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903353792-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 117 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353792 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903353862-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353862 KC6387 |  | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 400 |  | 400 |  |  | 26/09/2026 | 26/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903354120-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 244 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903354120 KU3269 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356221-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 594 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903356221 KU3274 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356606-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 104 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903356606 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903357761-1 KA4331 | BLACK | 90D | S2608MR0902 | 1089 | 31/10/2026 | 1089 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357761 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-06-11 | 2026-09-11 |  |  | 1089 |  | 1089 |  |  | 2026-03-11 | 2026-05-11 |  |  | 1089 |  | 1089 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1089 |  | 1089
ADIDAS | 0903357814-1 KA4331 | BLACK | 90D | S2608MR0902 | 343 | 31/10/2026 | 343 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903357814 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 343 |  | 343 |  |  | 30/10/2026 | 2026-02-11 |  |  | 343 |  | 343 |  |  | 29/10/2026 | 31/10/2026 |  |  | 343 |  | 343
ADIDAS | 0903357841-1 KA4331 | BLACK | 90D | S2608MR0902 | 816 | 31/10/2026 | 816 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357841 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-05-11 | 2026-06-11 |  |  | 816 |  | 816 |  |  | 2026-02-11 | 2026-03-11 |  |  | 816 |  | 816 |  |  | 31/10/2026 | 2026-02-11 |  |  | 816 |  | 816
ADIDAS | 0903361428-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 369 | 30/09/2026 | 369 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361428 KT7554 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | M CLUB AM TAT |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 369 |  | 369 |  |  | 23/09/2026 | 23/09/2026 | 2026-11-09 | 2026-12-09 | 369 | 341 | 28
ADIDAS | 0903361463-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 887 | 31/10/2026 | 887 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361463 KT7554 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | M CLUB AM TAT |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 887 |  | 887 |  |  | 19/10/2026 | 19/10/2026 | 2026-12-09 | 14/09/2026 | 887 | 862 | 25
ADIDAS | 0903361907-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1504 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361907 KD7980 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903361937-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361937 KD9090 |  | KAHATEX CIJERAH | VIETNAM | SEA | 29/09/2026 | K BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 400 |  | 400 |  |  | 25/09/2026 | 26/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903362010-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 237 | 31/10/2026 | 237 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903362010 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-10-11 | M PANCAKE T OFF WHITE |  | SS27-STX | 2026-10-11 | 2026-11-11 |  |  | 237 |  | 237 |  |  | 2026-06-11 | 2026-07-11 |  |  | 237 |  | 237
ADIDAS | 0903362075-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 531 | 15/09/2026 | 531 | ID | ID31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 14/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903362075 KB5965 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee M |  | SS27-TI-SLT | 2026-05-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 531 | 531 |  |  |  | 2026-02-09 | 2026-04-09 | 29/08/2026 | 2026-08-09 | 531 | 531 |  |  |  | 31/08/2026 | 2026-02-09 | 29/08/2026 | 2026-07-09 | 531 | 531
ADIDAS | 0903363689-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 2740 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903363689 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903364417-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 367 | 31/10/2026 | 367 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903364417 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 15/10/2026 | IN RANGE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 367 |  | 367 |  |  | 2026-12-10 | 13/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903364604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 702 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903364604 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903365140-1 IS1413 | BLACK | 60D | S2425M405 | 241 | 31/10/2026 | 241 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903365140 IS1413 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/10/2026 | IN RANGE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 241 |  | 241 |  |  | 13/10/2026 | 14/10/2026 |  |  | 241 |  | 241
ADIDAS | 0903365289-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 650 | 2026-07-10 | 650 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365289 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-03-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-03-10 | 2026-05-10 |  |  | 650 |  | 650 |  |  | 30/09/2026 | 2026-01-10 |  |  | 650 |  | 650 |  |  | 28/09/2026 | 29/09/2026 |  |  | 650 |  | 650
ADIDAS | 0903365322-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 500 | 2026-07-10 | 500 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365322 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-02-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-02-10 | 2026-03-10 |  |  | 500 |  | 500 |  |  | 29/09/2026 | 30/09/2026 | 27/08/2026 | 31/08/2026 | 500 | 340 | 160 |  |  | 26/09/2026 | 28/09/2026 | 27/08/2026 | 29/08/2026 | 500 | 500
ADIDAS | 0903366562-1 IS1413 | BLACK | 60D | S2425M405 | 7 | 30/09/2026 | 7 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903366562 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 7 |  | 7 |  |  | 2026-12-09 | 2026-12-09 |  |  | 7 |  | 7
ADIDAS | 0903366668-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 101 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366668 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903367183-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1603 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367183 KD7980 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903367215-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 303 | 21/10/2026 | 303 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | PRINT L3 SUB PROCESS_V3 | 0903367215 IU0217 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/10/2026 | IN RANGE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-12-10 | 13/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903367328-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 277 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367328 KD3683 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903368244-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903368244 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903368357-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 | 690 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368357 JE6340 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 21/10/2026 | M 3S FT FZ HD |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 690 |  | 690 |  |  | 17/10/2026 | 20/10/2026 |  |  | 690 |  | 690
ADIDAS | 0903368397-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 | 461 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516205 | HT SUB PROCESS_V1 | 0903368397 JC9584 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 13/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 13/10/2026 | 15/10/2026 |  |  | 461 |  | 461 |  |  | 2026-10-10 | 13/10/2026 |  |  | 461 |  | 461 |  |  | 2026-09-10 | 2026-12-10 |  |  | 461 |  | 461
ADIDAS | 0903368443-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 | 1150 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368443 JE6341 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 20/10/2026 | M 3S FT FZ HD |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1150 |  | 1150 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1150 |  | 1150
ADIDAS | 0903368477-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 | 2070 | SA | SA31/07/2026 | G2R | JACKET | G2 | (16/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368477 JE6338 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 24/10/2026 |  |  | 2070 |  | 2070 |  |  | 15/10/2026 | 21/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903368508-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4599 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903368508 JE0052 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903368552-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2520 | 15/09/2026 | 2520 | SA | SA31/07/2026 | G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368552 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 2520 | 2520 |  |  | 142 | 2026-03-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 2520 | 2497 | 23 |  | 62
ADIDAS | 0903368598-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903368598 JE6414 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 1380 |  | 1380 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903368635-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 401 | 15/09/2026 | 401 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368635 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 401 | 401 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-10-09 | 15/09/2026 | 401 | 395 | 6 |  | 4
ADIDAS | 0903369017-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 535 | 30/09/2026 | 535 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 25/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369017 IU0217 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 535 |  | 535 |  |  | 2026-12-09 | 2026-12-09 |  |  | 535 |  | 535
ADIDAS | 0903369058-1 IS1413 | BLACK | 60D | S2425M405 | 374 | 30/09/2026 | 374 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369058 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 374 |  | 374 |  |  | 2026-12-09 | 2026-12-09 |  |  | 374 |  | 374
ADIDAS | 0903369096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 514 | 30/09/2026 | 514 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 24/09: ex-fty 672027 | PRINT L3+PAD SUB PROCESS_V3 | 0903369096 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | BRAZIL | SEA | 24/09/2026 | POS TABLE LK |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 514 |  | 514 |  |  | 21/09/2026 | 21/09/2026 | 2026-08-09 | 2026-09-09 | 514 | 506 | 8
ADIDAS | 0903369734-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 100 | 28/10/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | PRINT L3 SUB PROCESS_V3 | 0903369734 IU0217 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903370112-1 IS1413 | BLACK | 60D | S2425M405 | 109 | 31/10/2026 | 109 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903370112 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA | 16/10/2026 | IN RANGE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 109 |  | 109 |  |  | 13/10/2026 | 14/10/2026 |  |  | 109 |  | 109
ADIDAS | 0903370723-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 | 2300 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370723 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 23/10/2026 | M 3S FT FZ HD |  | SS27 | 23/10/2026 | 27/10/2026 |  |  | 2300 |  | 2300 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2300 |  | 2300
ADIDAS | 0903370771-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903370771 JW7178 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903370821-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 2100 | 31/10/2026 | 2100 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370821 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 28/10/2026 |  |  | 2100 |  | 2100 |  |  | 19/10/2026 | 24/10/2026 |  |  | 2100 |  | 2100
ADIDAS | 0903370885-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370885 IB8688 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 1840 | 1840 |  |  | 244 | 2026-03-09 | 2026-11-09 | 2026-12-09 | 15/09/2026 | 1840 | 1741 | 99 |  | 38
ADIDAS | 0903370934-1 HK7309 | BLACK | 45D | F2225M402 | 399 | 15/09/2026 | 399 | SA | SA31/07/2026 | G1K | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370934 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 14/09/2026 | 399 | 399 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 14/09/2026 | 399 | 399
ADIDAS | 0903370987-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 600 | 15/09/2026 | 600 | SA | SA31/07/2026 | G2A | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370987 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-10-09 | 15/09/2026 | 600 | 600 |  |  | 27 | 2026-04-09 | 2026-12-09 | 2026-08-09 | 15/09/2026 | 600 | 598 | 2 |  | 3
ADIDAS | 0903371005-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 124 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371005 JD5308 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903371033-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 4200 | 31/10/2026 | 4200 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903371033 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 22/10/2026 |  |  | 4200 |  | 4200 |  |  | 13/10/2026 | 19/10/2026 |  |  | 4200 |  | 4200
ADIDAS | 0903371106-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1800 | 15/10/2026 | 1800 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903371106 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | RELEASED |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1800 |  | 1800 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1800 |  | 1800
ADIDAS | 0903371252-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371252 JE6377 |  | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | M 3S FT SWT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903371280-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (16/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371280 JE6374 |  | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | M 3S FT SWT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903371315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 310 | 31/10/2026 | 310 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371315 JE6372 |  | KAHATEX CIJERAH | PERU | SEA | 2026-09-10 | M 3S FT SWT |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 310 |  | 310 |  |  | 2026-06-10 | 2026-06-10 |  |  | 310 |  | 310
ADIDAS | 0903371346-1 IC5188 | BLACK | 90D | S23080640 | 802 | 31/10/2026 | 802 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371346 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 802 |  | 802 |  |  | 28/10/2026 | 30/10/2026 |  |  | 802 |  | 802 |  |  | 27/10/2026 | 29/10/2026 |  |  | 802 |  | 802
ADIDAS | 0903371391-1 IC5189 | WHITE | 90D | S23080640 | 601 | 31/10/2026 | 601 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371391 IC5189 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-11 | OWN THE RUN TEE |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 601 |  | 601 |  |  | 30/10/2026 | 31/10/2026 |  |  | 601 |  | 601 |  |  | 29/10/2026 | 30/10/2026 |  |  | 601 |  | 601
ADIDAS | 0903371424-1 IC5188 | BLACK | 90D | S23080640 | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371424 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 30/10/2026 |  |  | 301 |  | 301 |  |  | 28/10/2026 | 28/10/2026 |  |  | 301 |  | 301 |  |  | 27/10/2026 | 27/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903371472-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 400 | 2026-02-10 | 400 | SI | SI31/07/2026 | G2P | SWEATSHIRT | G2 | (16/09/2026) |  | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371472 JE6374 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA | 22/09/2026 | M 3S FT SWT |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 400 |  | 400 |  |  | 18/09/2026 | 18/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903371511-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903371511 IW2479 | 2026-03-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903372005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 389 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903372035-1 JC5948 | BLACK/WHITE | 90D | S2554WES428FT | 2021 | 31/10/2026 | 2021 | SA | SA31/07/2026 | G1A | PANTS | G1 | (12/09/2026) |  | (Mexico). 1st Art (TC 10 pcs) 652001 | PRINT L1 SUB PROCESS_V3 | 0903372035 JC5948 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-11 | W LIN FT CF PT |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 2021 |  | 2021 |  |  | 2026-02-11 | 2026-05-11 |  |  | 2021 |  | 2021
ADIDAS | 0903372134-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2083 | 31/10/2026 | 2083 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | (Mexico). 652001 | EMBRO SUB PROCESS_V1 | 0903372134 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 22/10/2026 | 27/10/2026 |  |  | 2083 |  | 2083 |  |  | 19/10/2026 | 23/10/2026 |  |  | 2083 |  | 2083
ADIDAS | 0903372828-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT-SLT | 149 | 2026-09-09 | 149 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 09/09: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903372828 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27-SLT | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 149 | 149 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 149 | 149
ADIDAS | 0903372885-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372885 HK7309 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-04-09 | ESS HDY |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-09-09 | 15/09/2026 | 1495 | 1495 |  |  | 3 | 2026-01-09 | 14/09/2026 | 2026-08-09 | 15/09/2026 | 1495 | 1473 | 22 |  | 11
ADIDAS | 0903372932-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 959 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372932 JW7178 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903372967-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 296 | 30/09/2026 | 296 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903372967 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 296 |  | 296 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 296 | 247 | 49
ADIDAS | 0903372970-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372970 JD5302 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903373006-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373006 HK7311 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-09 | ESS HDY |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  |  | 29/08/2026 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1379 | 1372 | 7 |  | 67
ADIDAS | 0903373044-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1200 | 31/10/2026 | 1200 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373044 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1200 |  | 1200 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903373080-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373080 JE6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 600 |  | 600 |  |  | 19/10/2026 | 21/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903373118-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug.. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373118 IB8688 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 1840 | 1840 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1840 | 1812 | 28 |  | 13
ADIDAS | 0903373141-1 HK7319 | BLACK | 90D | F2225M403 | 276 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 512102 | EMBRO+PPA SUB PROCESS_V3 | 0903373141 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903373659-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1680 | 31/10/2026 | 1680 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903373659 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 1680 |  | 1680 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903373776-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 199 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903373776 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903373810-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373810 LI2671 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 10 |  | 10 |  |  | 23/09/2026 | 24/09/2026 | 2026-09-09 | 2026-09-09 | 10 | 6 | 4
ADIDAS | 0903373816-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1K,G1P | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373816 HK7309 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 1495 | 1495 |  |  |  | 2026-04-09 | 2026-11-09 | 2026-09-09 | 14/09/2026 | 1495 | 1488 | 7
ADIDAS | 0903373846-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373846 LI2645 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 10 |  | 10 |  |  | 17/09/2026 | 18/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373872-1 HK7309 | BLACK | 45D | F2225M402 | 2730 | 15/09/2026 | 2730 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373872 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-10-09 | 15/09/2026 | 2730 | 2730 |  |  | 2 | 2026-03-09 | 14/09/2026 | 2026-10-09 | 15/09/2026 | 2730 | 2661 | 69 |  | 44
ADIDAS | 0903373878-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373878 LI2672 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 10 |  | 10 |  |  | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373912-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373912 LI2647 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 10 |  | 10 |  |  | 26/09/2026 | 28/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373917-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1080 | 31/10/2026 | 1080 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516318 | HT SUB PROCESS_V1 | 0903373917 JC9584 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 1080 |  | 1080 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1080 |  | 1080 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1080 |  | 1080
ADIDAS | 0903373945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373945 LI2646 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 10 |  | 10 |  |  | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373958-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2520 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903373958 HK7317 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903374005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4199 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903374005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903374039-1 HK7309 | BLACK | 45D | F2225M402 | 3000 | 15/09/2026 | 3000 | SA | SA31/07/2026 | G1D,G1E,G1F,G1K,G1L,G1N,G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903374039 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 14/09/2026 | 15/09/2026 | 3000 | 3000 |  |  | 120 | 2026-03-09 | 14/09/2026 | 13/09/2026 | 15/09/2026 | 3000 | 2867 | 133 |  | 23
ADIDAS | 0903374083-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903374083 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | ESS TEE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 600 |  | 600 |  |  | 2026-07-10 | 2026-08-10 |  |  | 600 |  | 600
ADIDAS | 0903374122-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3779 | 31/10/2026 | 3779 | SA | SA31/07/2026 | G2R | JACKET | G2 | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903374122 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M 3S FT FZ HD |  | SS27 | 24/10/2026 | 29/10/2026 |  |  | 3779 |  | 3779 |  |  | 21/10/2026 | 26/10/2026 |  |  | 3779 |  | 3779
ADIDAS | 0903374608-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374608 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 460 |  | 460 |  |  | 19/09/2026 | 21/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903374636-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 140 | 23/10/2026 | 140 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374636 LI2647 |  | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 140 |  | 140 |  |  | 17/10/2026 | 19/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903374883-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 103 | 30/09/2026 | 103 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374883 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 103 |  | 103 |  |  | 22/09/2026 | 23/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903374887-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 604 | 31/10/2026 | 604 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903374887 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-06-11 | 2026-09-11 |  |  | 604 |  | 604 |  |  | 2026-03-11 | 2026-05-11 |  |  | 604 |  | 604 |  |  | 2026-02-11 | 2026-04-11 |  |  | 604 |  | 604
ADIDAS | 0903374908-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374908 LI2668 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 107 |  | 107 |  |  | 19/09/2026 | 21/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903374971-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 111 | 30/09/2026 | 111 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374971 LI2669 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 111 |  | 111 |  |  | 19/09/2026 | 21/09/2026 | 2026-12-09 | 2026-12-09 | 111 | 29 | 82
ADIDAS | 0903375052-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 200 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903375052 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903375054-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 519 | 30/09/2026 | 519 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903375054 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 519 |  | 519 |  |  | 2026-03-10 | 2026-05-10 |  |  | 519 |  | 519 |  |  | 2026-01-10 | 2026-02-10 | 15/09/2026 | 15/09/2026 | 519 | 464 | 55 |  | 464
ADIDAS | 0903375259-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 599 | 31/10/2026 | 599 | SA | SA31/07/2026 | G2B | SHORTS | G2 | (12/09/2026) |  | 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375259 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | AFA DNA SHO |  | SS27-WC | 14/10/2026 | 15/10/2026 |  |  | 599 |  | 599 |  |  | 2026-10-10 | 2026-12-10 |  |  | 599 |  | 599
ADIDAS | 0903375527-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 128 | 31/10/2026 | 128 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375527 JN1958 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 128 |  | 128 |  |  | 28/10/2026 | 29/10/2026 |  |  | 128 |  | 128
ADIDAS | 0903375654-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 720 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375654 HR8583 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375690-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1800 | 31/10/2026 | 1800 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375690 IB8686 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | ESS TEE |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 1800 |  | 1800 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1800 |  | 1800
ADIDAS | 0903375727-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1079 | 31/10/2026 | 1079 | SA | SA31/07/2026 | G2R | JACKET | G2 | (16/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375727 JE6338 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1079 |  | 1079 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1079 |  | 1079
ADIDAS | 0903375762-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 481 | 31/10/2026 | 481 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375762 JE6417 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 481 |  | 481 |  |  | 2026-03-10 | 2026-06-10 |  |  | 481 |  | 481
ADIDAS | 0903375797-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 31/10/2026 | 359 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375797 JE6340 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | M 3S FT FZ HD |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 359 |  | 359 |  |  | 17/10/2026 | 20/10/2026 |  |  | 359 |  | 359
ADIDAS | 0903375840-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375840 JN1948 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | W 3S FT QZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 600 |  | 600 |  |  | 27/10/2026 | 28/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903375868-1 HK7309 | BLACK | 45D | F2225M402 | 780 | 15/09/2026 | 780 | SA | SA31/07/2026 | G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375868 HK7309 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | ESS HDY |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 14/09/2026 | 780 | 780 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-11-09 | 15/09/2026 | 780 | 751 | 29 |  | 40
ADIDAS | 0903375907-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 719 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375907 HK7317 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375937-1 HK7319 | BLACK | 90D | F2225M403 | 720 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375937 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903375980-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903375980 HK7317 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903376012-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 960 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376012 JE0055 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903376053-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376053 JN1948 |  | KAHATEX CIJERAH | SPAIN | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 1151 |  | 1151 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903376092-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376092 JE1309 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903376133-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903376133 JV5068 |  | KAHATEX CIJERAH | SPAIN | SEA | 20/10/2026 | I ADIRAPTOR T |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 919 |  | 919 |  |  | 16/10/2026 | 17/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903376163-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 3358 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376163 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903376197-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 6300 | 31/10/2026 | 6300 | SA | SA31/07/2026 | G2O | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376197 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | ESS TEE |  | SS27 | 24/10/2026 | 2026-02-11 |  |  | 6300 |  | 6300 |  |  | 21/10/2026 | 29/10/2026 |  |  | 6300 |  | 6300
ADIDAS | 0903376238-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 200 | 31/10/2026 | 200 | SA | SA31/07/2026 | G2S | JACKET | G2 | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376238 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | M 3S FT FZ HD |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 200 |  | 200 |  |  | 24/10/2026 | 26/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903376260-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 246 | 30/09/2026 | 246 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903376260 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 246 |  | 246 |  |  | 25/09/2026 | 26/09/2026 |  |  | 246 |  | 246
ADIDAS | 0903376273-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 300 | 31/10/2026 | 300 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376273 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 15/10/2026 | 17/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903376325-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903376325 JV5069 |  | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | I ADIRAPTOR T |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1680 |  | 1680 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903376368-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3359 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376368 JE0055 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903376414-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 361 | 31/10/2026 | 361 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376414 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 361 |  | 361 |  |  | 2026-03-10 | 2026-06-10 |  |  | 361 |  | 361
ADIDAS | 0903376447-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 6033 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376447 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903376448-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1080 | 31/10/2026 | 1080 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376448 JN1958 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | W 3S FT QZ HD |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 1080 |  | 1080 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1080 |  | 1080
ADIDAS | 0903376489-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2521 | 31/10/2026 | 2521 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (16/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376489 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 22/10/2026 | 28/10/2026 |  |  | 2521 |  | 2521 |  |  | 19/10/2026 | 24/10/2026 |  |  | 2521 |  | 2521
ADIDAS | 0903376520-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 400 | 31/10/2026 | 400 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376520 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 400 |  | 400 |  |  | 2026-10-10 | 13/10/2026 |  |  | 400 |  | 400
ADIDAS | 0903376565-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 2099 | 31/10/2026 | 2099 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376565 JN1948 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | W 3S FT QZ HD |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 2099 |  | 2099 |  |  | 31/10/2026 | 2026-03-11 |  |  | 2099 |  | 2099
ADIDAS | 0903376600-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 401 | 31/10/2026 | 401 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376600 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 401 |  | 401 |  |  | 19/10/2026 | 21/10/2026 |  |  | 401 |  | 401
ADIDAS | 0903377291-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 301 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377291 KV7863 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903377363-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 155 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377363 JW7182 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903377539-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1560 | 31/10/2026 | 1560 | SI | SI31/07/2026 | G2M | SHORTS | G2 | ok |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903377539 JG8642 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-10 | W LIN FT SHO |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 1560 |  | 1560 |  |  | 2026-08-10 | 2026-10-10 | 15/09/2026 | 15/09/2026 | 1560 | 392 | 1168 |  | 392
ADIDAS | 0903377653-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 167 | 30/09/2026 | 167 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377653 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 167 |  | 167 |  |  | 22/09/2026 | 23/09/2026 |  |  | 167 |  | 167
ADIDAS | 0903377680-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 175 | 30/09/2026 | 175 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377680 LI2671 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 175 |  | 175 |  |  | 23/09/2026 | 24/09/2026 | 2026-09-09 | 2026-11-09 | 175 | 168 | 7
ADIDAS | 0903377733-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 1230 | 31/10/2026 | 1230 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903377733 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-11 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-11-11 | 13/11/2026 |  |  | 1230 |  | 1230 |  |  | 2026-07-11 | 2026-10-11 |  |  | 1230 |  | 1230 |  |  | 2026-06-11 | 2026-09-11 |  |  | 1230 |  | 1230
ADIDAS | 0903377770-1 KA4331 | BLACK | 90D | S2608MR0902 | 1737 | 31/10/2026 | 1737 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903377770 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-06-11 | 2026-10-11 |  |  | 1737 |  | 1737 |  |  | 2026-03-11 | 2026-06-11 |  |  | 1737 |  | 1737 |  |  | 2026-02-11 | 2026-05-11 |  |  | 1737 |  | 1737
ADIDAS | 0903377912-1 KG2951 | NIGHT NAVY | 90D | F2606CHRM009 | 70 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377912 KG2951 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | REAL DNA PNT |  | SS27
ADIDAS | 0903378225-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378225 JV5068 |  | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | I ADIRAPTOR T |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 1680 |  | 1680 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903378242-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 506 | 31/10/2026 | 506 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903378242 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-11 | M PANCAKE T OFF WHITE |  | SS27-STX | 2026-10-11 | 2026-11-11 |  |  | 506 |  | 506 |  |  | 2026-06-11 | 2026-07-11 |  |  | 506 |  | 506
ADIDAS | 0903378264-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 201 | 31/10/2026 | 201 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (16/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378264 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 201 |  | 201 |  |  | 2026-01-10 | 2026-03-10 |  |  | 201 |  | 201
ADIDAS | 0903378323-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 923 | 23/09/2026 | 923 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378323 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 923 |  | 923 |  |  | 17/09/2026 | 18/09/2026 |  |  | 923 |  | 923
ADIDAS | 0903378350-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2940 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378350 JE1309 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903378381-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 657 | 23/09/2026 | 657 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378381 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 657 |  | 657 |  |  | 18/09/2026 | 19/09/2026 |  |  | 657 |  | 657
ADIDAS | 0903378390-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2519 | 31/10/2026 | 2519 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378390 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 27/10/2026 | 31/10/2026 |  |  | 2519 |  | 2519 |  |  | 23/10/2026 | 28/10/2026 |  |  | 2519 |  | 2519
ADIDAS | 0903378401-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 140 | 30/09/2026 | 140 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378401 LI2646 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 140 |  | 140 |  |  | 22/09/2026 | 23/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903378425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 200 | 31/10/2026 | 200 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378425 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | M 3S FT FZ HD |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 200 |  | 200 |  |  | 14/10/2026 | 15/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903378433-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI31/07/2026 | G1M | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378433 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 230 |  | 230 |  |  | 30/09/2026 | 2026-01-10 |  |  | 230 |  | 230
ADIDAS | 0903378460-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 151 | 23/10/2026 | 151 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | (12/09/2026) |  | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378460 LI2671 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 151 |  | 151 |  |  | 2026-05-11 | 2026-06-11 |  |  | 151 |  | 151
ADIDAS | 0903378462-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 3780 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378462 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378476-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378476 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 113 |  | 113 |  |  | 22/09/2026 | 23/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903378501-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 114 | 30/09/2026 | 114 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378501 LI2667 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 114 |  | 114 |  |  | 18/09/2026 | 19/09/2026 |  |  | 114 |  | 114
ADIDAS | 0903378502-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1260 | 31/10/2026 | 1260 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378502 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M 3S FT FZ HD |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1260 |  | 1260 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1260 |  | 1260
ADIDAS | 0903378523-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 121 | 30/09/2026 | 121 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378523 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 121 |  | 121 |  |  | 19/09/2026 | 21/09/2026 | 2026-12-09 | 2026-12-09 | 121 | 109 | 12
ADIDAS | 0903378534-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2520 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903378534 HR8583 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903378548-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 145 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903378548 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903378553-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 131 | 23/10/2026 | 131 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378553 LI2669 |  | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 131 |  | 131 |  |  | 20/10/2026 | 21/10/2026 |  |  | 131 |  | 131
ADIDAS | 0903378584-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1890 | 31/10/2026 | 1890 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378584 JV5067 |  | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | I ADIRAPTOR T |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1890 |  | 1890 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1890 |  | 1890
ADIDAS | 0903378603-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 351 | 23/09/2026 | 351 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378603 LI2646 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 351 |  | 351 |  |  | 21/09/2026 | 22/09/2026 |  |  | 351 |  | 351
ADIDAS | 0903378612-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378612 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378670-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 1200 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378670 JE0052 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903378692-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 132 | 23/09/2026 | 132 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378692 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 132 |  | 132 |  |  | 16/09/2026 | 17/09/2026 |  |  | 132 |  | 132
ADIDAS | 0903378707-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903378707 JV5067 |  | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | I ADIRAPTOR T |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1036 |  | 1036 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903378741-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 721 | 15/09/2026 | 721 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378741 HK7311 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 721 | 721 |  |  | 18 | 2026-03-09 | 2026-11-09 | 2026-10-09 | 15/09/2026 | 721 | 713 | 8 |  | 9
ADIDAS | 0903378787-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903378787 IB8686 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | ESS TEE |  | SS27 | 14/10/2026 | 17/10/2026 |  |  | 3452 |  | 3452 |  |  | 2026-10-10 | 14/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903378816-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903378816 HR8583 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903378844-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 4140 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378844 JD5302 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903378881-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 539 | 31/10/2026 | 539 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903378881 JV5067 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | I ADIRAPTOR T |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 539 |  | 539 |  |  | 13/10/2026 | 13/10/2026 |  |  | 539 |  | 539
ADIDAS | 0903378923-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 840 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378923 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903378980-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 153 | 2026-07-10 | 153 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | (12/09/2026) |  | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378980 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 153 |  | 153 |  |  | 30/09/2026 | 2026-02-10 |  |  | 153 |  | 153
ADIDAS | 0903379027-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 960 | 15/09/2026 | 960 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379027 IB8688 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-09 | ESS HDY |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 960 | 960 |  |  |  | 29/08/2026 | 2026-11-09 | 2026-08-09 | 15/09/2026 | 960 | 934 | 26 |  | 14
ADIDAS | 0903379058-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 719 | 31/10/2026 | 719 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (16/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379058 JE6419 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 719 |  | 719 |  |  | 2026-01-10 | 2026-03-10 |  |  | 719 |  | 719
ADIDAS | 0903379083-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/09/2026 | 2000 | SA | SA31/07/2026 | G2A,G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379083 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 16/09/2026 | 2026-12-09 | 15/09/2026 | 2000 | 2000 |  |  | 71 | 2026-03-09 | 2026-12-09 | 2026-11-09 | 15/09/2026 | 2000 | 1991 | 9 |  | 48
ADIDAS | 0903379104-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 3360 | 15/09/2026 | 3360 | SA | SA31/07/2026 | G2A,G2R,G2T,G3A,G3H,G3I | SWEATSHIRT | G2,G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379104 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 19/09/2026 | 2026-12-09 | 15/09/2026 | 3360 | 3360 |  |  | 104 | 2026-03-09 | 16/09/2026 | 2026-12-09 | 15/09/2026 | 3360 | 3312 | 48 |  | 200
ADIDAS | 0903379129-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 31/10/2026 | 720 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379129 JE6414 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 720 |  | 720 |  |  | 2026-10-10 | 13/10/2026 |  |  | 720 |  | 720
ADIDAS | 0903379176-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 197 | 31/10/2026 | 197 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379176 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 197 |  | 197 |  |  | 2026-10-11 | 2026-12-11 |  |  | 197 |  | 197
ADIDAS | 0903379338-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 471 | 31/10/2026 | 471 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379338 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/11/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 471 |  | 471 |  |  | 2026-10-11 | 2026-12-11 |  |  | 471 |  | 471
ADIDAS | 0903379415-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 324 | 31/10/2026 | 324 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379415 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 324 |  | 324 |  |  | 2026-02-11 | 2026-04-11 |  |  | 324 |  | 324
ADIDAS | 0903379576-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 152 | 31/10/2026 | 152 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379576 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 152 |  | 152 |  |  | 2026-02-11 | 2026-04-11 |  |  | 152 |  | 152
ADIDAS | 0903379743-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 127 | 31/10/2026 | 127 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 839055 | HT SUB PROCESS_V1 | 0903379743 IL4127 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 127 |  | 127 |  |  | 31/10/2026 | 2026-02-11 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 31/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903380052-1 IC5189 | WHITE | 90D | S23080640 | 297 | 31/10/2026 | 297 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380052 IC5189 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-11 | OWN THE RUN TEE |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 297 |  | 297 |  |  | 30/10/2026 | 31/10/2026 |  |  | 297 |  | 297 |  |  | 29/10/2026 | 30/10/2026 |  |  | 297 |  | 297
ADIDAS | 0903380079-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 198 | 31/10/2026 | 198 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380079 IL4127 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 198 |  | 198 |  |  | 31/10/2026 | 2026-02-11 |  |  | 198 |  | 198 |  |  | 30/10/2026 | 31/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903380268-1 KE8425 | WHITE | 120D | S2608MR0906A | 873 | 31/10/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903380268 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0903380322-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380322 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 109 |  | 109 |  |  | 26/09/2026 | 28/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380373-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 109 | 30/09/2026 | 109 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380373 LI2672 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 109 |  | 109 |  |  | 22/09/2026 | 23/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380418-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 187 | 23/10/2026 | 187 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380418 LI2646 |  | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 187 |  | 187 |  |  | 14/10/2026 | 14/10/2026 |  |  | 187 |  | 187
ADIDAS | 0903380504-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380504 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 460 |  | 460 |  |  | 21/09/2026 | 22/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903380507-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 180 | 23/10/2026 | 180 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380507 LI2667 |  | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 180 |  | 180 |  |  | 20/10/2026 | 21/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903380516-1 KT7552 | BLACK | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903380516 KT7552 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | SOC CAT GFX T BLACK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 2099 |  | 2099 |  |  | 2026-05-10 | 2026-06-10 |  |  | 2099 |  | 2099
ADIDAS | 0903380521-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380521 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 32 |  | 32 |  |  | 22/09/2026 | 23/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380549-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 32 | 30/09/2026 | 32 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380549 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 32 |  | 32 |  |  | 22/09/2026 | 23/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380551-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 1254 | 2026-09-09 | 1254 | NT | NT31/07/2026 | G2Q | PANTS | G2 | ok |  | 09/09: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903380551 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-09 | M FEELCOZY PANT |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 1254 | 1254 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 1254 | 1254
ADIDAS | 0903380577-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380577 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 32 |  | 32 |  |  | 25/09/2026 | 26/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380597-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 15544 | 31/10/2026 | 15544 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380597 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/10/2026 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 20/10/2026 | 30/10/2026 |  |  | 15544 |  | 15544 |  |  | 16/10/2026 | 27/10/2026 |  |  | 15544 |  | 15544
ADIDAS | 0903380602-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 65 | 30/09/2026 | 65 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380602 LI2645 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 65 |  | 65 |  |  | 17/09/2026 | 18/09/2026 |  |  | 65 |  | 65
ADIDAS | 0903380624-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 442 | 23/09/2026 | 442 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380624 LI2668 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 442 |  | 442 |  |  | 15/09/2026 | 17/09/2026 |  |  | 442 |  | 442
ADIDAS | 0903380631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 50 | 30/09/2026 | 50 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380631 LI2667 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 18/09/2026 | 19/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903380644-1 LI7744 | WHITE | 90D | F2606LEMPM107MF | 8870 | 31/10/2026 | 8870 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380644 LI7744 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-10 | PSMM A JSY FAN WHITE |  | SS27-L2L | 2026-09-10 | 19/10/2026 |  |  | 8870 |  | 8870 |  |  | 2026-06-10 | 15/10/2026 |  |  | 8870 |  | 8870
ADIDAS | 0903380648-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380648 HK7311 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1379 | 1377 | 2 |  | 50
ADIDAS | 0903380681-1 HK7319 | BLACK | 90D | F2225M403 | 2519 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903380681 HK7319 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903380684-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 393 | 30/09/2026 | 393 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380684 LI2647 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 393 |  | 393 |  |  | 26/09/2026 | 28/09/2026 |  |  | 393 |  | 393
ADIDAS | 0903380713-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903380713 IB8686 |  | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | ESS TEE |  | SS27 | 17/10/2026 | 22/10/2026 |  |  | 3452 |  | 3452 |  |  | 14/10/2026 | 19/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903380751-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 204 | 31/10/2026 | 204 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903380751 IL4127 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 204 |  | 204 |  |  | 31/10/2026 | 2026-02-11 |  |  | 204 |  | 204 |  |  | 30/10/2026 | 31/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903380795-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 1477 | 31/10/2026 | 1477 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380795 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 19/10/2026 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 19/10/2026 | 20/10/2026 |  |  | 1477 |  | 1477 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1477 |  | 1477
ADIDAS | 0903380896-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380896 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-11 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-06-11 | 2026-11-11 |  |  | 301 |  | 301 |  |  | 2026-03-11 | 2026-07-11 |  |  | 301 |  | 301
ADIDAS | 0903380949-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 130 | 30/09/2026 | 130 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380949 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 130 |  | 130 |  |  | 26/09/2026 | 28/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903380973-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 327 | 30/09/2026 | 327 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380973 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 327 |  | 327 |  |  | 25/09/2026 | 26/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903380993-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 154 | 31/10/2026 | 154 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380993 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 154 |  | 154 |  |  | 31/10/2026 | 2026-02-11 |  |  | 154 |  | 154 |  |  | 30/10/2026 | 31/10/2026 |  |  | 154 |  | 154
ADIDAS | 0903381000-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381000 LI2671 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 113 |  | 113 |  |  | 23/09/2026 | 24/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903381024-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 379 | 30/09/2026 | 379 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381024 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 379 |  | 379 |  |  | 25/09/2026 | 26/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903381048-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 265 | 30/09/2026 | 265 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381048 LI2672 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 265 |  | 265 |  |  | 22/09/2026 | 23/09/2026 |  |  | 265 |  | 265
ADIDAS | 0903381059-1 KT7550 | BLACK | 90D | F26FBGFXP103 | 1228 | 31/10/2026 | 1228 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903381059 KT7550 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | M MX LIFESTL T |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 1228 |  | 1228 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1228 |  | 1228 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1228 |  | 1228
ADIDAS | 0903381067-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 271 | 15/10/2026 | 271 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381067 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-01-10 |  |  | 271 |  | 271
ADIDAS | 0903381072-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 241 | 2026-07-10 | 241 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381072 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 241 |  | 241 |  |  | 17/09/2026 | 18/09/2026 |  |  | 241 |  | 241
ADIDAS | 0903381112-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 307 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381112 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903381150-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3678 | 31/10/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381150 JE0055 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903381183-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 479 | 31/10/2026 | 479 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381183 JV5068 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | I ADIRAPTOR T |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 479 |  | 479 |  |  | 15/10/2026 | 16/10/2026 |  |  | 479 |  | 479
ADIDAS | 0903381211-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381211 JN1958 |  | KAHATEX CIJERAH | SPAIN | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 460 |  | 460 |  |  | 28/10/2026 | 29/10/2026 |  |  | 460 |  | 460
ADIDAS | 0903381242-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 | 919 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381242 JE6417 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 919 |  | 919 |  |  | 2026-07-10 | 2026-09-10 |  |  | 919 |  | 919
ADIDAS | 0903381274-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903381274 JV5069 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 919 |  | 919 |  |  | 2026-10-10 | 2026-12-10 |  |  | 919 |  | 919
ADIDAS | 0903381304-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (16/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381304 JE6419 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 1380 |  | 1380 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903381342-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 480 | 31/10/2026 | 480 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381342 JV5069 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 480 |  | 480 |  |  | 2026-10-10 | 2026-10-10 |  |  | 480 |  | 480
ADIDAS | 0903381645-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 1400 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381645 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA |  | UCH DNA PNT |  | SS27
ADIDAS | 0903381685-1 JE6353 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS605FT | 1200 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903381685 JE6353 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903381705-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 173 | 23/10/2026 | 173 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381705 LI2668 |  | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 173 |  | 173 |  |  | 20/10/2026 | 21/10/2026 |  |  | 173 |  | 173
ADIDAS | 0903381723-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 130 | 30/09/2026 | 130 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381723 LI2668 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 130 |  | 130 |  |  | 19/09/2026 | 21/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903381732-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 2104 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 1st Art (TC 10 pcs) 804028 | PRINT L1 SUB PROCESS_V3 | 0903381732 JE8969 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M BL FT PT |  | SS27
ADIDAS | 0903381751-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 798 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381751 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA |  | UCH DNA PNT |  | SS27
ADIDAS | 0903381763-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 23/09/2026 | 150 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381763 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 150 |  | 150 |  |  | 16/09/2026 | 17/09/2026 | 2026-09-09 | 2026-12-09 | 150 | 150
ADIDAS | 0903381776-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 1200 | 31/10/2026 | 1200 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381776 JE6377 |  | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-10 | M 3S FT SWT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 1200 |  | 1200 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1200 |  | 1200
ADIDAS | 0903381784-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1091 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 1st Art (TC 10 pcs) 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381784 KG5347 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | COLO DNA PNT |  | SS27
ADIDAS | 0903381803-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 498 | 23/09/2026 | 498 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381803 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 498 |  | 498 |  |  | 15/09/2026 | 17/09/2026 |  |  | 498 |  | 498
ADIDAS | 0903381815-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 532 | 31/10/2026 | 532 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381815 HK7311 |  | KAHATEX CIJERAH | CANADA | SEA | 2026-06-11 | ESS HDY |  | SS27 | 2026-06-11 | 2026-07-11 |  |  | 532 |  | 532 |  |  | 2026-03-11 | 2026-04-11 |  |  | 532 |  | 532
ADIDAS | 0903381828-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 568 | 23/09/2026 | 568 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381828 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 568 |  | 568 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 568 | 544 | 24
ADIDAS | 0903381848-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 732 | 31/10/2026 | 732 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381848 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA | 2026-07-11 | ESS HDY |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 732 |  | 732 |  |  | 2026-04-11 | 2026-05-11 |  |  | 732 |  | 732
ADIDAS | 0903381881-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 732 | 30/09/2026 | 732 | SA | SA31/07/2026 | G1F | SWEATSHIRT | G1 | (02/09/2026) |  | 21/09: ex-fty 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381881 HK7311 | 2026-03-09 | KAHATEX CIJERAH | CANADA | SEA | 15/09/2026 | ESS HDY |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 732 |  | 732 |  |  | 2026-11-09 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 732 | 540 | 192 |  | 540
ADIDAS | 0903382074-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 314 | 31/10/2026 | 314 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382074 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 314 |  | 314 |  |  | 2026-02-11 | 2026-04-11 |  |  | 314 |  | 314
ADIDAS | 0903382140-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 420 | 2026-09-09 | 420 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903382140 IW2479 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 420 | 420 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 420 | 420
ADIDAS | 0903382660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 40 | 30/09/2026 | 40 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382660 LI2671 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 40 |  | 40 |  |  | 23/09/2026 | 24/09/2026 | 2026-11-09 | 2026-11-09 | 40 | 23 | 17
ADIDAS | 0903382688-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 50 | 30/09/2026 | 50 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382688 LI2646 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 50 |  | 50 |  |  | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903382689-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 149 | 30/09/2026 | 149 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382689 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 149 |  | 149 |  |  | 22/09/2026 | 23/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903382714-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 40 | 30/09/2026 | 40 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382714 LI2668 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 40 |  | 40 |  |  | 19/09/2026 | 21/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903382830-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2D,G2G,G2N,G2O,G2P,G2S | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382830 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M FEELCOZY HD |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 15000 |  |  | 3832 | 2026-04-09 | 2026-12-09 | 2026-08-09 | 15/09/2026 | 15000 | 14961 | 39 |  | 19
ADIDAS | 0903383170-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 325 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383170 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903383240-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 23/09/2026 | 234 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903383240 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 234 |  | 234 |  |  | 16/09/2026 | 17/09/2026 |  |  | 234 |  | 234
ADIDAS | 0903383252-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 292 | 15/10/2026 | 292 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383252 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 292 |  | 292 |  |  | 2026-01-10 | 2026-02-10 |  |  | 292 |  | 292
ADIDAS | 0903383295-1 KT7539 | CARBON S18 | 60D | F26FBGFXP101 | 1225 | 31/10/2026 | 1225 | AN | AN31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903383295 KT7539 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-11 | IN RANGE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 1225 |  | 1225 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1225 |  | 1225
ADIDAS | 0903383996-1 JZ6293 | CREW BLUE S21 | 90D | S2606CHAG011-MTF | 361 | 31/10/2026 | 361 | AN | AN31/07/2026 | G1B | PANTS | G1 | (12/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903383996 JZ6293 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-04-11 | AFA DNA PNT |  | SS27-WC | 2026-04-11 | 2026-04-11 |  |  | 361 |  | 361 |  |  | 31/10/2026 | 31/10/2026 |  |  | 361 |  | 361
ADIDAS | 0903384024-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 915 | 31/10/2026 | 915 | SA | SA31/07/2026 | G2B | SHORTS | G2 | (12/09/2026) |  | 1st Art (TC 10 pcs) 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384024 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | AFA DNA SHO |  | SS27-WC | 13/10/2026 | 14/10/2026 |  |  | 915 |  | 915 |  |  | 2026-09-10 | 2026-10-10 |  |  | 915 |  | 915
ADIDAS | 0903384123-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 82 | 31/10/2026 | 82 | SI | SI31/07/2026 | G1L | T-SHIRT | G1 | (07/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903384123 LE8210 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-11 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-06-11 | 2026-06-11 |  |  | 82 |  | 82 |  |  | 2026-03-11 | 2026-03-11 |  |  | 82 |  | 82
ADIDAS | 0903384138-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 104 | 30/09/2026 | 104 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 29/09: ex-fty 839055 | PRINT L2 SUB PROCESS_V3 | 0903384138 KB7172 | 16/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-08-10 | HOT COMMUNITY |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 104 |  | 104 |  |  | 2026-05-10 | 2026-05-10 |  |  | 104 |  | 104
ADIDAS | 0903384176-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 480 | 2026-09-09 | 480 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903384176 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 480 | 480 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-04-09 | 2026-08-09 | 480 | 480
ADIDAS | 0903384240-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SHORTS | G2 | ok |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903384240 JG8642 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-10-10 | W LIN FT SHO |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 | 15/09/2026 | 15/09/2026 | 300 | 275 | 25 |  | 275
ADIDAS | 0903384315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384315 JE6372 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-10 | M 3S FT SWT |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903384565-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903384565 KX8877 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903384949-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 1138 | 2026-07-10 | 1138 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903384949 JC5283 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-10 | M L SLIDE PKT T |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 1138 |  | 1138 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1138 |  | 1138 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1138 |  | 1138
ADIDAS | 0903385022-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 1278 | 2026-07-10 | 1278 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385022 JC5282 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-08-10 | M L SLIDE PKT T |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 1278 |  | 1278 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1278 |  | 1278
ADIDAS | 0903385097-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 1076 | 2026-07-10 | 1076 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 1st Art (TC 10 pcs) 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385097 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-10-10 | M L SLIDE PKT T |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 1076 |  | 1076 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1076 |  | 1076 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1076 |  | 1076
ADIDAS | 0903385671-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903385671 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903385727-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 1635 | 31/10/2026 | 1635 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 838103 | PRINT L1+PAD SUB PROCESS_V3 | 0903385727 KY1335 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-11-11 | M PANCAKE T OFF WHITE |  | SS27-STX | 2026-11-11 | 2026-12-11 |  |  | 1635 |  | 1635 |  |  | 2026-07-11 | 2026-09-11 |  |  | 1635 |  | 1635
ADIDAS | 0903385935-1 KX8877 | WHITE | 90D | S27GMGFX100 | 110 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903385935 KX8877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903385968-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 100 | 15/10/2026 | 100 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903385968 KD3936 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | RELEASED |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-07-10 |  |  | 100 |  | 100
ADIDAS | 0903385970-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1400 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385970 KG5347 |  | KAHATEX CIJERAH | CHILE | SEA |  | COLO DNA PNT |  | SS27
ADIDAS | 0903385989-1 IS1413 | BLACK | 60D | S2425M405 | 598 | 31/10/2026 | 598 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903385989 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 598 |  | 598 |  |  | 14/10/2026 | 14/10/2026 |  |  | 598 |  | 598
ADIDAS | 0903386031-1 KY7166 | BLACK | 75D | S2706CHCC008 | 1328 | 15/10/2026 | 1328 | ID | ID31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386031 KY7166 |  | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | CC DNA SHO BLACK |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1328 |  | 1328 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1328 |  | 1328
ADIDAS | 0903386106-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 300 | 31/10/2026 | 300 | AN | AN31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386106 LF1392 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-07-11 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 300 |  | 300 |  |  | 2026-04-11 | 2026-06-11 |  |  | 300 |  | 300
ADIDAS | 0903386123-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 304 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386123 KV7863 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386150-1 LC6341 | BLACK | 90D | S27GMGFX130 | 368 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903386150 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903386171-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2E,G2F,G2Q,G2S | PANTS | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903386171 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M FEELCOZY PANT |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 15000 |  |  | 1654 | 2026-05-09 | 2026-12-09 | 2026-07-09 | 15/09/2026 | 15000 | 15000 |  |  | 39
ADIDAS | 0903386195-1 KT7553 | WHITE | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903386195 KT7553 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | SOC CAT GFX T WHITE |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 2099 |  | 2099 |  |  | 2026-06-10 | 2026-08-10 |  |  | 2099 |  | 2099
ADIDAS | 0903386246-1 IS1413 | BLACK | 60D | S2425M405 | 385 | 31/10/2026 | 385 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903386246 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 16/10/2026 | IN RANGE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 385 |  | 385 |  |  | 13/10/2026 | 14/10/2026 |  |  | 385 |  | 385
ADIDAS | 0903386305-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 230 | 30/09/2026 | 230 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 22/09: ex-fty 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903386305 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 230 |  | 230 |  |  | 21/09/2026 | 22/09/2026 |  |  | 230 |  | 230 |  |  | 18/09/2026 | 19/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903386331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 680 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516462 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386331 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386485-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 104 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386485 JD9944 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903387168-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903387168 LI2667 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 107 |  | 107 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 107 | 81 | 26
ADIDAS | 0903387206-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 463 | 23/09/2026 | 463 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903387206 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 463 |  | 463 |  |  | 16/09/2026 | 17/09/2026 |  |  | 463 |  | 463
ADIDAS | 0903387271-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 71 | 31/10/2026 | 71 | SA | SA31/07/2026 | G1B | SHORTS | G1 |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Men Chuen, PI Date ?? 547012 | HT SUB PROCESS_V1 | 0903387271 KX9851 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-11 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-11 | 2026-04-11 |  |  | 71 |  | 71 |  |  | 31/10/2026 | 2026-02-11 |  |  | 71 |  | 71 |  |  | 30/10/2026 | 31/10/2026 |  |  | 71 |  | 71
ADIDAS | 0903387336-1 HK7319 | BLACK | 90D | F2225M403 | 500 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 547012 | EMBRO+PPA SUB PROCESS_V3 | 0903387336 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903387369-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 | 690 | SA | SA31/07/2026 | G2T | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387369 JE6340 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 690 |  | 690 |  |  | 15/10/2026 | 17/10/2026 |  |  | 690 |  | 690
ADIDAS | 0903387402-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387402 JE6414 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1380 |  | 1380 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903387487-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 | 461 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516442 | HT SUB PROCESS_V1 | 0903387487 JC9584 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 13/10/2026 | 15/10/2026 |  |  | 461 |  | 461 |  |  | 2026-10-10 | 13/10/2026 |  |  | 461 |  | 461 |  |  | 2026-09-10 | 2026-12-10 |  |  | 461 |  | 461
ADIDAS | 0903387523-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903387523 HR8583 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903387560-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903387560 JV5067 |  | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | I ADIRAPTOR T |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 1036 |  | 1036 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903387602-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 | 919 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387602 JE6417 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 919 |  | 919 |  |  | 2026-06-10 | 2026-07-10 |  |  | 919 |  | 919
ADIDAS | 0903387638-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 | 1150 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387638 JE6341 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | M 3S FT FZ HD |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 1150 |  | 1150 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1150 |  | 1150
ADIDAS | 0903387764-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387764 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903388131-1 IC5189 | WHITE | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903388131 IC5189 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-11 | OWN THE RUN TEE |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 217 |  | 217 |  |  | 30/10/2026 | 31/10/2026 |  |  | 217 |  | 217 |  |  | 29/10/2026 | 30/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903388403-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388403 KX8875 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903388432-1 KX8877 | WHITE | 90D | S27GMGFX100 | 416 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388432 KX8877 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903388455-1 LC6341 | BLACK | 90D | S27GMGFX130 | 100 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388455 LC6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903388544-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 773 | 31/10/2026 | 773 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388544 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 14/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 773 |  | 773 |  |  | 2026-11-11 | 13/11/2026 |  |  | 773 |  | 773 |  |  | 2026-10-11 | 2026-12-11 |  |  | 773 |  | 773
ADIDAS | 0903388567-1 KA4331 | BLACK | 90D | S2608MR0902 | 1066 | 31/10/2026 | 1066 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903388567 KA4331 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-04-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 1066 |  | 1066 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1066 |  | 1066 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1066 |  | 1066
ADIDAS | 0903388591-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 770 | 31/10/2026 | 770 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388591 LD0277 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-11 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 770 |  | 770 |  |  | 2026-05-11 | 2026-07-11 |  |  | 770 |  | 770 |  |  | 2026-04-11 | 2026-06-11 |  |  | 770 |  | 770
ADIDAS | 0903388611-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 158 | 31/10/2026 | 158 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903388611 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-11 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 158 |  | 158 |  |  | 2026-05-11 | 2026-07-11 |  |  | 158 |  | 158 |  |  | 2026-04-11 | 2026-06-11 |  |  | 158 |  | 158
ADIDAS | 0903388672-1 IC5188 | BLACK | 90D | S23080640 | 473 | 31/10/2026 | 473 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903388672 IC5188 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 30/10/2026 |  |  | 473 |  | 473 |  |  | 28/10/2026 | 28/10/2026 |  |  | 473 |  | 473 |  |  | 27/10/2026 | 27/10/2026 |  |  | 473 |  | 473
ADIDAS | 0903388692-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 104 | 31/10/2026 | 104 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903388692 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | M 3S FT FZ HD |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 104 |  | 104 |  |  | 14/10/2026 | 15/10/2026 |  |  | 104 |  | 104
ADIDAS | 0903388840-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 110 | 31/10/2026 | 110 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388840 KW2909 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-09-11 |  |  | 110 |  | 110 |  |  | 2026-05-11 | 2026-05-11 |  |  | 110 |  | 110
ADIDAS | 0903388861-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 116 | 31/10/2026 | 116 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388861 KW2909 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-09-11 |  |  | 116 |  | 116 |  |  | 2026-05-11 | 2026-05-11 |  |  | 116 |  | 116
ADIDAS | 0903388888-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 166 | 31/10/2026 | 166 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388888 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 16/11/2026 | 17/11/2026 |  |  | 166 |  | 166 |  |  | 2026-12-11 | 13/11/2026 |  |  | 166 |  | 166
ADIDAS | 0903388890-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 430 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388890 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388903-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 150 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388903 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388929-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 125 | 31/10/2026 | 125 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388929 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 16/11/2026 | 17/11/2026 |  |  | 125 |  | 125 |  |  | 2026-12-11 | 13/11/2026 |  |  | 125 |  | 125
ADIDAS | 0903388990-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 10048 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388990 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389129-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903389129 KW1544 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 800 |  | 800 |  |  | 2026-01-10 | 2026-02-10 |  |  | 800 |  | 800
ADIDAS | 0903389677-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389677 JN1958 |  | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 460 |  | 460 |  |  | 28/10/2026 | 29/10/2026 |  |  | 460 |  | 460
ADIDAS | 0903389678-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 207 | 30/09/2026 | 207 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 29/09: ex-fty (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903389678 KD3911 | 16/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 207 |  | 207 |  |  | 2026-11-09 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 207 | 205 | 2 |  | 205
ADIDAS | 0903389747-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 | 2070 | SA | SA31/07/2026 | G2T | JACKET | G2 | (16/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903389747 JE6338 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | M 3S FT FZ HD |  | SS27 | 26/10/2026 | 29/10/2026 |  |  | 2070 |  | 2070 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903389758-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 25/09: ex-fty 814006 | EMBRO SUB PROCESS_V1 | 0903389758 KD3911 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 109 |  | 109 |  |  | 2026-11-09 | 2026-12-09 | 14/09/2026 | 15/09/2026 | 109 | 99 | 10 |  | 40
ADIDAS | 0903389769-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 232 | 30/09/2026 | 232 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903389769 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 232 |  | 232 |  |  | 23/09/2026 | 24/09/2026 |  |  | 232 |  | 232
ADIDAS | 0903389788-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903389788 JV5068 |  | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | I ADIRAPTOR T |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 919 |  | 919 |  |  | 17/10/2026 | 19/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903389808-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 415 | 23/09/2026 | 415 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903389808 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 415 |  | 415 |  |  | 15/09/2026 | 15/09/2026 | 2026-11-09 | 2026-11-09 | 415 | 354 | 61
ADIDAS | 0903389891-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389891 JN1948 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-03-11 | W 3S FT QZ HD |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 1151 |  | 1151 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903389932-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389932 HK7319 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903389964-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903389964 JE1309 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903389996-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389996 HK7317 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903390024-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (16/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903390024 JE6419 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1380 |  | 1380 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903390063-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903390063 JV5069 |  | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | I ADIRAPTOR T |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 919 |  | 919 |  |  | 2026-12-10 | 13/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903390099-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390099 JW7178 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903390198-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 377 | 31/10/2026 | 377 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903390198 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 14/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 377 |  | 377 |  |  | 2026-11-11 | 13/11/2026 |  |  | 377 |  | 377 |  |  | 2026-10-11 | 2026-12-11 |  |  | 377 |  | 377
ADIDAS | 0903390259-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390259 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 24/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 22/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903390291-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903390291 IW2479 | 2026-03-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-08-09 | 276 | 276
ADIDAS | 0903390301-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 2062 | 15/10/2026 | 2062 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903390301 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-12-10 | M L SLIDE PKT T |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 2062 |  | 2062 |  |  | 2026-08-10 | 2026-09-10 |  |  | 2062 |  | 2062 |  |  | 2026-06-10 | 2026-07-10 |  |  | 2062 |  | 2062
ADIDAS | 0903390768-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 233 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390768 JD5302 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903390837-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 106 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390837 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903391146-1 HK7319 | BLACK | 90D | F2225M403 | 1122 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903391146 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903391266-1 HK7319 | BLACK | 90D | F2225M403 | 900 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848024 | EMBRO+PPA SUB PROCESS_V3 | 0903391266 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903391415-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 604 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391415 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903391521-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 190 | 31/10/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 512114 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391521 JW7182 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903391655-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903391655 KW1543 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 800 |  | 800 |  |  | 2026-01-10 | 2026-01-10 |  |  | 800 |  | 800
ADIDAS | 0903391682-1 IC5188 | BLACK | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903391682 IC5188 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 217 |  | 217 |  |  | 28/10/2026 | 30/10/2026 |  |  | 217 |  | 217 |  |  | 27/10/2026 | 29/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903392177-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 | 2300 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903392177 JD1877 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/10/2026 | M 3S FT FZ HD |  | SS27 | 27/10/2026 | 31/10/2026 |  |  | 2300 |  | 2300 |  |  | 23/10/2026 | 28/10/2026 |  |  | 2300 |  | 2300
ADIDAS | 0903392343-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 315 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903392343 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903393703-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 1833 | 2026-12-09 | 1833 | NT | NT31/07/2026 | G2P | SWEATSHIRT | G2 | ok |  | 10/09: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393703 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M FEELCOZY HD |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-10-09 | 1833 | 1833 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-04-09 | 2026-11-09 | 1833 | 1833
ADIDAS | 0903393839-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 500 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393839 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903393868-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 219 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393868 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903393909-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1153 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393909 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903394744-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 509 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903394744 JF3604 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903394768-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 891 | 30/09/2026 | 891 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394768 KA5090 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 891 |  | 891 |  |  | 21/09/2026 | 22/09/2026 |  |  | 891 |  | 891 |  |  | 18/09/2026 | 19/09/2026 | 2026-09-09 | 2026-09-09 | 891 |  | 891
ADIDAS | 0903394796-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 940 | 30/09/2026 | 940 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394796 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 25/09/2026 | MINI EMB T |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 940 |  | 940 |  |  | 22/09/2026 | 23/09/2026 |  |  | 940 |  | 940 |  |  | 19/09/2026 | 21/09/2026 |  |  | 940 |  | 940
ADIDAS | 0903394896-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394896 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903394920-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394920 KA5090 |  | KAHATEX CIJERAH | CANADA | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903395478-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 370 | 31/10/2026 | 370 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 672027 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903395478 JD1877 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | M 3S FT FZ HD |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 370 |  | 370 |  |  | 14/10/2026 | 15/10/2026 |  |  | 370 |  | 370
ADIDAS | 0903395527-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 172 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395527 LC6339 |  | KAHATEX CIJERAH | ITALY | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903395611-1 KX8877 | WHITE | 90D | S27GMGFX100 | 210 | 31/10/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395611 KX8877 |  | KAHATEX CIJERAH | ITALY | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903396292-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 316 | 15/10/2026 | 316 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396292 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 316 |  | 316 |  |  | 26/09/2026 | 26/09/2026 |  |  | 316 |  | 316
ADIDAS | 0903396384-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 435 | 15/10/2026 | 435 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396384 KD9090 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 29/09/2026 | K BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 435 |  | 435 |  |  | 25/09/2026 | 26/09/2026 |  |  | 435 |  | 435
ADIDAS | 0903397096-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 461 | 30/10/2026 | 461 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903397096 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 461 |  | 461 |  |  | 24/10/2026 | 27/10/2026 |  |  | 461 |  | 461 |  |  | 23/10/2026 | 26/10/2026 |  |  | 461 |  | 461
ADIDAS | 0903397121-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA31/07/2026 | G1C | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903397121 KT4839 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903397664-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903397664 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903397808-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 105 | 31/10/2026 | 105 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903397808 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 105 |  | 105 |  |  | 31/10/2026 | 2026-02-11 |  |  | 105 |  | 105 |  |  | 30/10/2026 | 31/10/2026 |  |  | 105 |  | 105
ADIDAS | 0903397832-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 356 | 30/09/2026 | 356 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397832 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 356 |  | 356 |  |  | 2026-03-10 | 2026-05-10 |  |  | 356 |  | 356 |  |  | 2026-01-10 | 2026-02-10 | 15/09/2026 | 15/09/2026 | 356 | 351 | 5 |  | 351
ADIDAS | 0903397854-1 KA4331 | BLACK | 90D | S2608MR0902 | 1280 | 31/10/2026 | 1280 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903397854 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 1280 |  | 1280 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1280 |  | 1280 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1280 |  | 1280
ADIDAS | 0903397883-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 258 | 30/09/2026 | 258 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 28/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397883 JC5282 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 258 |  | 258 |  |  | 2026-03-10 | 2026-05-10 |  |  | 258 |  | 258 |  |  | 2026-01-10 | 2026-02-10 | 2026-04-09 | 2026-04-09 | 258 | 1 | 257
ADIDAS | 0903397901-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 3558 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903397901 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903398085-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 114 | 31/10/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398085 JD9944 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903398370-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 129 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398370 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903398417-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 341 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398417 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398667-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 609 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398667 KV7863 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398692-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 827 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398692 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903398713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 685 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398713 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903398767-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 796 | 31/10/2026 | 796 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903398767 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-11 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-06-11 | 2026-11-11 |  |  | 796 |  | 796 |  |  | 2026-03-11 | 2026-07-11 |  |  | 796 |  | 796
ADIDAS | 0903400198-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 102 | 31/10/2026 | 102 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903400198 IU0217 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | IN RANGE |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 102 |  | 102 |  |  | 2026-12-10 | 2026-12-10 |  |  | 102 |  | 102
ADIDAS | 0903400562-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 839055 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903400562 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 17/10/2026 | M 3S FT FZ HD |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903401786-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401786 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903401814-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 161 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401814 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903445381-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 2861 | 30/09/2026 | 2861 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445381 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 2861 |  | 2861 |  |  | 15/09/2026 | 18/09/2026 | 2026-02-09 | 14/09/2026 | 2861 | 2509 | 352
ADIDAS | 0903445382-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 24/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445382 LC6339 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 100 |  | 100 |  |  | 19/09/2026 | 19/09/2026 | 2026-09-09 | 2026-09-09 | 100 | 100
ADIDAS | 0903445383-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | (11/07/2026) | (04/07/2026) | 25/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445383 KX8877 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M CHIP T WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 100 |  | 100 |  |  | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903445384-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 3083 | 30/09/2026 | 3083 | SA | SA26/06/2026 | G3B | PANTS | G3 | (08/08/2026) | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445384 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | W 3S FT OH PT |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 3083 |  | 3083 |  |  | 30/09/2026 | 2026-03-10 | 15/09/2026 | 15/09/2026 | 3083 | 1930 | 1153 |  | 1930
ADIDAS | 0903445385-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 3082 | 30/09/2026 | 3082 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903445385 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S FT QZ HD |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 3082 |  | 3082 |  |  | 19/09/2026 | 23/09/2026 |  |  | 3082 |  | 3082
ADIDAS | 0903450147-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 98 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450147 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450148-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1114 | 2026-05-09 | 1114 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450148 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-04-09 | 1114 | 1114 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-03-09 | 1114 | 1114 |  |  |  | 24/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 1114 | 1114
ADIDAS | 0903450149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 3791 | 2026-05-09 | 3791 | SA | SA15/05/2026 | G2J,G2K | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450149 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-04-09 | 3791 | 3791 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-02-09 | 3791 | 3791 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-02-09 | 3791 | 3791
ADIDAS | 0903450150-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 129 | 23/09/2026 | 129 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 21/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450150 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 129 | 129 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 29/08/2026 | 129 | 129
ADIDAS | 0903450151-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450151 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450152-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 172 | 23/09/2026 | 172 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 18/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450152 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 2026-12-08 | 2026-06-08 | 2026-07-08 | 172 | 172 |  |  |  | 2026-04-08 | 2026-07-08 | 31/07/2026 | 29/08/2026 | 172 | 168 | 4
ADIDAS | 0903450153-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 942 | 15/10/2026 | 942 | SA | SA24/01/2026 | G1M | T-SHIRT | G1 | ok |  | DRC 0010-hold shipment customer (BTP_24_06_2026 -> Req. PO Cancel & Quantity Change). T2 Far Eastern, PI Date 21-Sep (switch with fabric from Libolon for 500pcs). T2 Fu Hsun, PI Date 18-Aug. 814006 | HT SUB PROCESS_V1 | 0903450153 KG8548 | 2026-08-04 | KAHATEX CIJERAH | THAILAND | SEA | 30/06/2026 | ADIZERO E TEE |  | FW26 | 30/06/2026 | 21/09/2026 | 30/06/2026 | 2026-07-07 | 942 | 273 | 669 |  |  | 26/06/2026 | 18/09/2026 | 20/06/2026 | 20/06/2026 | 942 | 273 | 669 |  |  | 25/06/2026 | 17/09/2026 | 2026-12-08 | 2026-12-08 | 942 | 273 | 669
ADIDAS | 0903467951-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903467951 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 920 |  | 920 |  |  | 2026-08-10 | 2026-10-10 |  |  | 920 |  | 920
ADIDAS | 0903472791-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1P | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472791 IB8688 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ESS HDY |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 2000 |  | 2000 |  |  | 19/09/2026 | 23/09/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903472864-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472864 IB8688 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 480 |  | 480 |  |  | 2026-08-10 | 2026-10-10 |  |  | 480 |  | 480
ADIDAS | 0903476466-1 JZ7711 | BLACK | 120D | S2608MR0202 | 249 | 23/09/2026 | 249 | SA | SA14/08/2026 | G3G | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903476466 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 15/09/2026 | 17/09/2026 |  |  | 249 |  | 249 |  |  | 2026-11-09 | 14/09/2026 |  |  | 249 |  | 249 |  |  | 2026-08-09 | 2026-10-09 |  |  | 249 |  | 249
ADIDAS | 0903478300-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 24/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478300 HK7311 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | ESS HDY |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 2001 |  | 2001 |  |  | 30/09/2026 | 2026-03-10 |  |  | 2001 |  | 2001
ADIDAS | 0903478487-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 202 | 15/09/2026 | 202 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478487 IN1172 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 202 | 202 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 202 | 202 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 202 | 202
ADIDAS | 0903478570-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478570 HK7311 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 29/09/2026 | ESS HDY |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 2001 |  | 2001 |  |  | 25/09/2026 | 29/09/2026 |  |  | 2001 |  | 2001
ADIDAS | 0903478582-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 139 | 15/09/2026 | 139 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478582 IN1156 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 139 | 139 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 139 | 139 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 139 | 139
ADIDAS | 0903478609-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 164 | 15/09/2026 | 164 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478609 IN1157 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 164 | 164 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 164 | 164 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 164 | 164
ADIDAS | 0903478627-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478627 HK7311 |  | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 19/10/2026 |  |  | 920 |  | 920 |  |  | 2026-12-10 | 15/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903480271-1 IS1413 | BLACK | 60D | S2425M405 | 900 | 15/10/2026 | 900 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848024 | PRINT L3 SUB PROCESS_V3 | 0903480271 IS1413 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 21/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903480314-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903480314 KA5090 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 602 |  | 602 |  |  | 24/09/2026 | 24/09/2026 |  |  | 602 |  | 602 |  |  | 22/09/2026 | 22/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903480517-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 378 | 23/10/2026 | 378 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848016 | PRINT L3 SUB PROCESS_V3 | 0903480517 IU0217 |  | KAHATEX CIJERAH | MOROCCO | SEA | 15/10/2026 | IN RANGE |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 378 |  | 378 |  |  | 2026-12-10 | 2026-12-10 |  |  | 378 |  | 378
ADIDAS | 0903480831-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 335 | 15/10/2026 | 335 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480831 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | W BLANK TEE |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 335 |  | 335 |  |  | 2026-09-10 | 2026-10-10 |  |  | 335 |  | 335
ADIDAS | 0903480958-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1F | SWEATSHIRT | G1 | (15/09/2026(1)) |  | 26/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480958 HK7309 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | ESS HDY |  | SS27 | 16/09/2026 | 21/09/2026 |  |  | 2250 |  | 2250 |  |  | 2026-12-09 | 17/09/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903480993-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1679 | 15/10/2026 | 1679 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480993 HK7311 |  | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | ESS HDY |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1679 |  | 1679 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1679 |  | 1679
ADIDAS | 0903481767-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 5210 | 15/10/2026 | 5210 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903481767 KD9097 |  | KAHATEX CIJERAH | VIETNAM | SEA | 14/10/2026 | W BLANK TEE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 5210 |  | 5210 |  |  | 2026-10-10 | 13/10/2026 |  |  | 5210 |  | 5210
ADIDAS | 0903482244-1 HK7309 | BLACK | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482244 HK7309 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 480 |  | 480 |  |  | 2026-01-10 | 2026-03-10 |  |  | 480 |  | 480
ADIDAS | 0903482398-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482398 HK7311 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 920 |  | 920 |  |  | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920
ADIDAS | 0903482505-1 HK7309 | BLACK | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482505 HK7309 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | ESS HDY |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1680 |  | 1680 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1680 |  | 1680
ADIDAS | 0903483394-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483394 HK7309 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 920 |  | 920 |  |  | 2026-01-10 | 2026-03-10 |  |  | 920 |  | 920
ADIDAS | 0903483669-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483669 IB8688 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | ESS HDY |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 2000 |  | 2000 |  |  | 28/09/2026 | 30/09/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903483726-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483726 IB8688 |  | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1680 |  | 1680 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903484758-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484758 HK7309 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | ESS HDY |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 2250 |  | 2250 |  |  | 24/09/2026 | 28/09/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903484802-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 481 | 15/10/2026 | 481 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484802 HK7311 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 19/10/2026 |  |  | 481 |  | 481 |  |  | 2026-12-10 | 15/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903484985-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484985 IB8688 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | ESS HDY |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920 |  |  | 2026-07-10 | 2026-08-10 |  |  | 920 |  | 920
ADIDAS | 0903485610-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 23/09/2026 | 100 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485610 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA | 18/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 16/09/2026 |  |  | 100 |  | 100 |  |  | 2026-11-09 | 2026-12-09 |  |  | 100 |  | 100
ADIDAS | 0903486292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 243 | 30/10/2026 | 243 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486292 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 31/10/2026 | 2026-02-11 |  |  | 243 |  | 243 |  |  | 29/10/2026 | 30/10/2026 |  |  | 243 |  | 243 |  |  | 28/10/2026 | 29/10/2026 |  |  | 243 |  | 243
ADIDAS | 0903486365-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 238 | 30/10/2026 | 238 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486365 IN1157 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-03-11 | 2026-04-11 |  |  | 238 |  | 238 |  |  | 31/10/2026 | 2026-02-11 |  |  | 238 |  | 238 |  |  | 30/10/2026 | 31/10/2026 |  |  | 238 |  | 238
ADIDAS | 0903486405-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 136 | 30/10/2026 | 136 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486405 IN1157 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-03-11 | 2026-04-11 |  |  | 136 |  | 136 |  |  | 31/10/2026 | 2026-02-11 |  |  | 136 |  | 136 |  |  | 30/10/2026 | 31/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903486465-1 IS1413 | BLACK | 60D | S2425M405 | 1322 | 15/10/2026 | 1322 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903486465 IS1413 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | IN RANGE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1322 |  | 1322 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1322 |  | 1322
ADIDAS | 0903486480-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 138 | 30/10/2026 | 138 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486480 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 24/09/2026 | 25/09/2026 |  |  | 138 |  | 138 |  |  | 22/09/2026 | 23/09/2026 |  |  | 138 |  | 138 |  |  | 21/09/2026 | 22/09/2026 |  |  | 138 |  | 138
ADIDAS | 0903486515-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 428 | 30/10/2026 | 428 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903486515 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 27/10/2026 | 27/10/2026 |  |  | 428 |  | 428 |  |  | 24/10/2026 | 24/10/2026 |  |  | 428 |  | 428 |  |  | 23/10/2026 | 23/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903486554-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 207 | 15/09/2026 | 207 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 830009 | HT SUB PROCESS_V1 | 0903486554 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 207 | 207 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-08-09 | 14/09/2026 | 207 | 207 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 207 | 207
ADIDAS | 0903486586-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 23/09/2026 | 106 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486586 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 17/09/2026 | 18/09/2026 |  |  | 106 |  | 106 |  |  | 14/09/2026 | 15/09/2026 |  |  | 106 |  | 106 |  |  | 2026-10-09 | 2026-11-09 |  |  | 106 |  | 106
ADIDAS | 0903486633-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 103 | 16/09/2026 | 103 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 16/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, PI Date 23-Oct, switch from order 0903443493). T2 Fu Hsun, PI Date 11-Sep, switch from order 903443493). 830009 | HT SUB PROCESS_V1 | 0903486633 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 103 | 103 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 103 | 103 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 103 | 103
ADIDAS | 0903486753-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 2974 | 31/10/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486753 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486870-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1164 | 15/10/2026 | 1164 | SI | SI14/08/2026 | G3J | SHORTS | G3 | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486870 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 1164 |  | 1164 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1164 |  | 1164 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1164 |  | 1164
ADIDAS | 0903487218-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487218 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | ESS HDY |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 920 |  | 920 |  |  | 30/09/2026 | 2026-01-10 |  |  | 920 |  | 920
ADIDAS | 0903487925-1 JZ7709 | BLACK | 120D | S2608MR0201 | 249 | 23/09/2026 | 249 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487925 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 15/09/2026 | 17/09/2026 |  |  | 249 |  | 249 |  |  | 2026-11-09 | 14/09/2026 |  |  | 249 |  | 249 |  |  | 2026-08-09 | 2026-10-09 |  |  | 249 |  | 249
ADIDAS | 0903488008-1 JZ7709 | BLACK | 120D | S2608MR0201 | 706 | 23/09/2026 | 706 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488008 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 15/09/2026 | 17/09/2026 |  |  | 706 |  | 706 |  |  | 2026-11-09 | 14/09/2026 |  |  | 706 |  | 706 |  |  | 2026-08-09 | 2026-10-09 |  |  | 706 |  | 706
ADIDAS | 0903488538-1 JZ7711 | BLACK | 120D | S2608MR0202 | 690 | 23/09/2026 | 690 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488538 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 17/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 17/09/2026 | 18/09/2026 |  |  | 690 |  | 690 |  |  | 14/09/2026 | 15/09/2026 |  |  | 690 |  | 690 |  |  | 2026-10-09 | 2026-11-09 |  |  | 690 |  | 690
ADIDAS | 0903488669-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 221 | 30/10/2026 | 221 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903488669 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 31/10/2026 | 2026-02-11 |  |  | 221 |  | 221 |  |  | 29/10/2026 | 30/10/2026 |  |  | 221 |  | 221 |  |  | 28/10/2026 | 29/10/2026 |  |  | 221 |  | 221
ADIDAS | 0903488735-1 JZ7709 | BLACK | 120D | S2608MR0201 | 101 | 23/09/2026 | 101 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488735 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 18/09/2026 | 19/09/2026 |  |  | 101 |  | 101 |  |  | 15/09/2026 | 16/09/2026 |  |  | 101 |  | 101 |  |  | 2026-11-09 | 2026-12-09 |  |  | 101 |  | 101
ADIDAS | 0903489269-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 714 | 15/10/2026 | 714 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903489269 KA5090 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | MINI EMB T |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 714 |  | 714 |  |  | 2026-07-10 | 2026-07-10 |  |  | 714 |  | 714 |  |  | 2026-05-10 | 2026-05-10 |  |  | 714 |  | 714
ADIDAS | 0903490564-1 JZ7711 | BLACK | 120D | S2608MR0202 | 241 | 23/09/2026 | 241 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490564 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 17/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 17/09/2026 | 18/09/2026 |  |  | 241 |  | 241 |  |  | 14/09/2026 | 15/09/2026 |  |  | 241 |  | 241 |  |  | 2026-10-09 | 2026-11-09 |  |  | 241 |  | 241
ADIDAS | 0903491252-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903491252 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903491267-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903491267 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903491589-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1017 | 31/10/2026 | 1017 | SI | SI14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903491589 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | LA PALMS TEE |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 1017 |  | 1017 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1017 |  | 1017
ADIDAS | 0903492007-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 2604 | 15/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903492007 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903492168-1 JM6500 | COLLEGIATE GREEN | 60D | F25SPRMGFX040 | 70 | 15/10/2026 | 70 | NT | NT14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 848012 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903492168 JM6500 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M DDL SKATE T |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 70 |  | 70 |  |  | 2026-02-10 | 2026-02-10 |  |  | 70 |  | 70
ADIDAS | 0903492638-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 120 | 15/10/2026 | 120 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3+HT SUB PROCESS_V3 | 0903492638 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 16/10/2026 | 17/10/2026 |  |  | 120 |  | 120 |  |  | 15/10/2026 | 16/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903492648-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1200 | 2026-12-09 | 1200 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 11/09: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903492648 KX7410 | 2026-04-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-08-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 2026-04-09 | 2026-08-09 | 2026-04-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903492683-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1352 | 15/09/2026 | 1352 | SI | SI14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903492683 KX7410 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1352 | 1352 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 1352 | 1352
ADIDAS | 0903493699-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1299 | 15/10/2026 | 1299 | ID | ID14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493699 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | SPORT GOODS T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 1299 |  | 1299 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1299 |  | 1299
ADIDAS | 0903493969-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 2 | 2026-07-10 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903493969 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494009-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494009 LG8052 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494023-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494023 LG8051 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-05-11 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 2026-05-11 | 2026-05-11 |  |  | 2 |  | 2 |  |  | 2026-02-11 | 2026-02-11 |  |  | 2 |  | 2
ADIDAS | 0903494061-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 2 | 2026-07-10 | 2 | AN | AN14/08/2026 | G2C | T-SHIRT | G2 | (14/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903494061 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 28/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494081-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 2 | 29/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494081 LI5438 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903494139-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 2 | 29/10/2026 | 2 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494139 LJ4075 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-05-11 | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS | 2026-05-11 | 2026-05-11 |  |  | 2 |  | 2 |  |  | 2026-02-11 | 2026-02-11 |  |  | 2 |  | 2
ADIDAS | 0903494327-1 LJ9158 | WHITE | 90D | 226205_JZSJ | 8582 | 15/10/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903494327 LJ9158 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494405-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 116 | 15/09/2026 | 116 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494405 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 116 | 116 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 116 | 116 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 116 | 116
ADIDAS | 0903494445-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 126 | 15/09/2026 | 126 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2-Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494445 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 126 | 126 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 126 | 126 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-11-09 | 14/09/2026 | 126 | 126
ADIDAS | 0903494678-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 100 | 15/10/2026 | 100 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3 SUB PROCESS_V3 | 0903494678 LE1858 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 21/10/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 21/10/2026 | 21/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 17/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903495174-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 2 | 29/09/2026 | 2 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(28)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495174 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 19/09/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 19/09/2026 | 21/09/2026 |  |  | 2 |  | 2 |  |  | 16/09/2026 | 17/09/2026 |  |  | 2 |  | 2 |  |  | 15/09/2026 | 16/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903495387-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 2 | 29/09/2026 | 2 | SI | SI14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(28)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495387 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 19/09/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 19/09/2026 | 21/09/2026 |  |  | 2 |  | 2 |  |  | 16/09/2026 | 17/09/2026 |  |  | 2 |  | 2 |  |  | 15/09/2026 | 16/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903495400-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 2 | 29/09/2026 | 2 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(28)) |  | 825054 | PRINT L3 SUB PROCESS_V3 | 0903495400 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 19/09/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 19/09/2026 | 21/09/2026 |  |  | 2 |  | 2 |  |  | 16/09/2026 | 17/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903496564-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 29 | 15/10/2026 | 29 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496564 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 29 |  | 29 |  |  | 17/10/2026 | 19/10/2026 |  |  | 29 |  | 29 |  |  | 16/10/2026 | 17/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496599-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 29 | 15/10/2026 | 29 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496599 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 29 |  | 29 |  |  | 16/10/2026 | 17/10/2026 |  |  | 29 |  | 29 |  |  | 15/10/2026 | 16/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496637-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 517 | 15/10/2026 | 517 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903496637 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 517 |  | 517 |  |  | 17/10/2026 | 19/10/2026 |  |  | 517 |  | 517 |  |  | 16/10/2026 | 17/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903497305-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 161 | 15/10/2026 | 161 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903497305 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 161 |  | 161 |  |  | 16/10/2026 | 17/10/2026 |  |  | 161 |  | 161 |  |  | 15/10/2026 | 16/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903497830-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 9287 | 15/10/2026 | 9287 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903497830 KA5089 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | MINI EMB T |  | SS27 | 30/09/2026 | 2026-07-10 |  |  | 9287 |  | 9287 |  |  | 26/09/2026 | 2026-03-10 |  |  | 9287 |  | 9287 |  |  | 24/09/2026 | 2026-01-10 |  |  | 9287 |  | 9287
ADIDAS | 0903500463-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 889 | 15/10/2026 | 889 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903500463 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 24/10/2026 |  |  | 889 |  | 889 |  |  | 19/10/2026 | 21/10/2026 |  |  | 889 |  | 889 |  |  | 17/10/2026 | 20/10/2026 |  |  | 889 |  | 889
ADIDAS | 0903501618-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 122 | 15/10/2026 | 122 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903501618 LE4570 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 122 |  | 122 |  |  | 16/10/2026 | 17/10/2026 |  |  | 122 |  | 122 |  |  | 15/10/2026 | 16/10/2026 |  |  | 122 |  | 122
ADIDAS | 0903502054-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 823 | 15/10/2026 | 823 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903502054 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 19/10/2026 | 20/10/2026 |  |  | 823 |  | 823 |  |  | 15/10/2026 | 16/10/2026 |  |  | 823 |  | 823 |  |  | 14/10/2026 | 15/10/2026 |  |  | 823 |  | 823
ADIDAS | 0903502085-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 166 | 15/10/2026 | 166 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 848012 | PRINT L3+HT SUB PROCESS_V3 | 0903502085 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 166 |  | 166 |  |  | 16/10/2026 | 17/10/2026 |  |  | 166 |  | 166 |  |  | 15/10/2026 | 16/10/2026 |  |  | 166 |  | 166
ADIDAS | 0903502271-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 842 | 2026-12-09 | 842 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903502271 KC6386 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-09 | M BLANK TEE |  | SS27 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 842 | 842 |  |  |  | 2026-05-09 | 2026-08-09 | 31/08/2026 | 2026-09-09 | 842 | 839 | 3
ADIDAS | 0903502599-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 324 | 15/10/2026 | 324 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903502599 KD9094 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M BLANK TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 324 |  | 324 |  |  | 30/09/2026 | 2026-01-10 |  |  | 324 |  | 324
ADIDAS | 0903503153-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 124 | 15/10/2026 | 124 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 1st Art (TC 10 pcs) 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503153 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 124 |  | 124 |  |  | 16/10/2026 | 17/10/2026 |  |  | 124 |  | 124 |  |  | 15/10/2026 | 16/10/2026 |  |  | 124 |  | 124
ADIDAS | 0903503177-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 204 | 15/10/2026 | 204 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503177 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 204 |  | 204 |  |  | 16/10/2026 | 17/10/2026 |  |  | 204 |  | 204 |  |  | 15/10/2026 | 16/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903503204-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 244 | 15/10/2026 | 244 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503204 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 244 |  | 244 |  |  | 17/10/2026 | 19/10/2026 |  |  | 244 |  | 244 |  |  | 16/10/2026 | 17/10/2026 |  |  | 244 |  | 244
ADIDAS | 0903503236-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 226 | 15/10/2026 | 226 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503236 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 24/10/2026 |  |  | 226 |  | 226 |  |  | 19/10/2026 | 21/10/2026 |  |  | 226 |  | 226 |  |  | 17/10/2026 | 20/10/2026 |  |  | 226 |  | 226
ADIDAS | 0903503267-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 127 | 15/10/2026 | 127 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903503267 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 127 |  | 127 |  |  | 17/10/2026 | 19/10/2026 |  |  | 127 |  | 127 |  |  | 16/10/2026 | 17/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903503360-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2004 | 15/09/2026 | 2004 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503360 KD4066 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | M BLANK TEE BLACK |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2004 | 2004 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-01-09 | 2026-08-09 | 2004 | 2004
ADIDAS | 0903503397-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2503 | 15/09/2026 | 2503 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503397 KE3742 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2503 | 2503 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-07-09 | 14/09/2026 | 2503 | 2503
ADIDAS | 0903503800-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 300 | 15/10/2026 | 300 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903503800 KC6386 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M BLANK TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903504690-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 1006 | 2026-12-09 | 1006 | SA | SA14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504690 KD9094 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | M BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 1006 | 1006 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-12-09 | 1006 | 1006
ADIDAS | 0903504729-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 2022 | 2026-12-09 | 2022 | SI | SI14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504729 KD9097 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | W BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2022 | 2022 |  |  |  | 2026-07-09 | 2026-09-09 | 31/08/2026 | 2026-08-09 | 2022 | 2022
ADIDAS | 0903535974-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 804028 | PRINT L3 SUB PROCESS_V3 | 0903535974 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | JAPAN | AIR-COLLECT | 15/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 15/09/2026 | 16/09/2026 |  |  | 500 |  | 500 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 500 | 290 | 210
ADIDAS | 0903535975-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 960026 | PRINT L3 SUB PROCESS_V3 | 0903535975 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | AUSTRALIA | AIR-COLLECT | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 16/09/2026 | 17/09/2026 |  |  | 500 |  | 500 |  |  | 2026-12-09 | 14/09/2026 | 2026-11-09 | 2026-11-09 | 500 | 500
ADIDAS | 0903545582-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 214 | 31/10/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903545582 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903548414-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 141 | 30/09/2026 | 141 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 29/09: ex-fty 800005 | HT+PAD SUB PROCESS_V3 | 0903548414 KB5961 | 24/11/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 22/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 22/09/2026 | 22/09/2026 |  |  | 141 |  | 141 |  |  | 18/09/2026 | 18/09/2026 |  |  | 141 |  | 141 |  |  | 16/09/2026 | 16/09/2026 |  |  | 141 |  | 141
ADIDAS | 0903550837-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ-SLT | 898 | 30/09/2026 | 898 | ID | ID28/08/2026 | G2J | T-SHIRT | G2 | ok |  | 23/09: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903550837 JC8239 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W LIN SJ T |  | SS27-SLT | 26/09/2026 | 28/09/2026 |  |  | 898 |  | 898 |  |  | 23/09/2026 | 24/09/2026 | 14/09/2026 | 15/09/2026 | 898 | 848 | 50 |  | 317
ADIDAS | 0903553857-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 123 | 30/09/2026 | 123 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553857 KB5965 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 123 |  | 123 |  |  | 17/09/2026 | 18/09/2026 |  |  | 123 |  | 123 |  |  | 15/09/2026 | 16/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903553911-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 134 | 30/09/2026 | 134 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553911 KB5961 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 22/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 22/09/2026 | 22/09/2026 |  |  | 134 |  | 134 |  |  | 18/09/2026 | 18/09/2026 |  |  | 134 |  | 134 |  |  | 16/09/2026 | 16/09/2026 |  |  | 134 |  | 134
ADIDAS | 0903554010-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 108 | 30/09/2026 | 108 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 814006 | HT+PAD SUB PROCESS_V3 | 0903554010 KB5965 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 108 |  | 108 |  |  | 17/09/2026 | 18/09/2026 |  |  | 108 |  | 108 |  |  | 15/09/2026 | 16/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903556417-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 107 | 30/09/2026 | 107 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0903556417 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 22/09/2026 | 22/09/2026 |  |  | 107 |  | 107 |  |  | 18/09/2026 | 18/09/2026 |  |  | 107 |  | 107 |  |  | 16/09/2026 | 16/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903557215-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 19/09/2026 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | Waiting LO (By Air-Collect). DRC 0047-hold shipment customer. 859013 | PRINT L3 SUB PROCESS_V3 | 0903557215 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | TAIWAN | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-11-09 | 300 | 300
ADIDAS | 0903557229-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2 | 30/09/2026 | 2 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 18/09: ex-fty (CMA test) (By Air-Express). DRC 0064-other customer related delay reason. 825054 | PRINT L3 SUB PROCESS_V3 | 0903557229 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | AIR-EXPRESS | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 2 | 2 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 2 | 2
ADIDAS | 0903557263-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2600 | 30/09/2026 | 2600 | SI | SI28/08/2026 | G2K,G2N | T-SHIRT | G2 | (25/09/2026(12)) |  | 18/09: ex-fty (China) (By Air-Collect). DRC 0064-other customer related delay reason. 825066 | PRINT L3 SUB PROCESS_V3 | 0903557263 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | SEA | 15/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 15/09/2026 | 17/09/2026 | 2026-12-09 | 15/09/2026 | 2600 | 1777 | 823 |  | 1046 | 2026-11-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 2600 | 2597 | 3
ADIDAS | 0903562605-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 3578 | 31/10/2026 | 3578 | SA | SA28/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 652001 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903562605 JC5283 |  | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | M L SLIDE PKT T |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 3578 |  | 3578 |  |  | 19/10/2026 | 22/10/2026 |  |  | 3578 |  | 3578 |  |  | 16/10/2026 | 20/10/2026 |  |  | 3578 |  | 3578
ADIDAS | 0903565164-1 IS1413 | BLACK | 60D | S2425M405 | 1 | 31/10/2026 | 1 | SI | SI28/08/2026 | G2S | T-SHIRT | G2 | (26/09/2026) |  | 672027 | PRINT L3 SUB PROCESS_V3 | 0903565164 IS1413 |  | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | IN RANGE |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 1 |  | 1 |  |  | 14/10/2026 | 14/10/2026 |  |  | 1 |  | 1
ADIDAS | 0903565505-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 1473 | 30/09/2026 | 1473 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 960026 | HT+PAD SUB PROCESS_V3 | 0903565505 KB5965 | 24/11/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 1473 |  | 1473 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1473 |  | 1473 |  |  | 15/09/2026 | 16/09/2026 |  |  | 1473 |  | 1473
ADIDAS | 0903566115-1 HL2231 | LEGEND INK F17/WHITE | 45D | F224CSIM430 | 71 | 15/10/2026 | 71 | NT | NT28/08/2026 | G2M | PANTS | G2 | (02/10/2026) |  | 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903566115 HL2231 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-10 | IN RANGE |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 71 |  | 71 |  |  | 2026-03-10 | 2026-03-10 |  |  | 71 |  | 71
ADIDAS | 0903569115-1 LK0714 | WONDER SAGE S26 | 90D | 226291_EFOA | 3335 | 21/10/2026 | 3335 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (12/09/2026) |  | 800005 | HT SUB PROCESS_V1 | 0903569115 LK0714 | 2026-10-11 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-10 | WF JRF 26 WONDER SAGE S26 |  | SS27-L2L-JRF | 2026-12-10 | 16/10/2026 |  |  | 3335 |  | 3335 |  |  | 2026-09-10 | 14/10/2026 |  |  | 3335 |  | 3335 |  |  | 2026-08-10 | 13/10/2026 |  |  | 3335 |  | 3335
ADIDAS | 0903577750-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 600 | 31/10/2026 | 600 | SA | SA28/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903577750 JC5283 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 22/10/2026 | M L SLIDE PKT T |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 600 |  | 600 |  |  | 19/10/2026 | 19/10/2026 |  |  | 600 |  | 600 |  |  | 16/10/2026 | 16/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903595003-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 4024 | 15/09/2026 | 4024 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595003 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 4024 | 2875 | 1149 |  | 241 | 2026-08-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 4024 | 4024
ADIDAS | 0903595010-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 5004 | 15/09/2026 | 5004 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595010 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 5004 | 4995 | 9 |  |  | 2026-07-09 | 2026-11-09 | 2026-02-09 | 2026-02-09 | 5004 | 5004
ADIDAS | 0903595012-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 890 | 15/09/2026 | 890 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595012 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 890 | 497 | 393 |  |  | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 890 | 890
ADIDAS | 0903595017-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 310 | 19/09/2026 | 310 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | Waiting LO. DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595017 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 310 | 310 |  |  |  | 2026-07-09 | 2026-11-09 | 2026-02-09 | 2026-04-09 | 310 | 310
ADIDAS | 0903595019-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 2026-12-09 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 12/09: ex-fty (By Air-Collect). 806020 | PRINT L3 SUB PROCESS_V3 | 0903595019 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | HONGKONG | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-11-09 | 2026-12-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-12-09 | 300 | 300
ADIDAS | 0903597586-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 108 | 31/10/2026 | 108 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 650034 | HT SUB PROCESS_V1 | 0903597586 KG8553 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 108 |  | 108 |  |  | 24/10/2026 | 27/10/2026 |  |  | 108 |  | 108 |  |  | 23/10/2026 | 26/10/2026 |  |  | 108 |  | 108
ADIDAS | 0903602357-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 700 | 30/09/2026 | 700 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 800005 | PRINT L3 SUB PROCESS_V3 | 0903602357 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | INDONESIA | AIR-COLLECT | 21/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 21/09/2026 | 22/09/2026 |  |  | 700 |  | 700 |  |  | 17/09/2026 | 18/09/2026 | 2026-10-09 | 2026-10-09 | 700 | 590 | 110
ADIDAS | 0903602358-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1400 | 30/09/2026 | 1400 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 839055 | PRINT L3 SUB PROCESS_V3 | 0903602358 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | SINGAPORE | AIR-COLLECT | 22/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 22/09/2026 | 23/09/2026 |  |  | 1400 |  | 1400 |  |  | 18/09/2026 | 19/09/2026 | 2026-10-09 | 2026-10-09 | 1400 | 1119 | 281
ADIDAS | 0903602359-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1880 | 30/09/2026 | 1880 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 814006 | PRINT L3 SUB PROCESS_V3 | 0903602359 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | THAILAND | AIR-COLLECT | 17/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 17/09/2026 | 18/09/2026 |  |  | 1880 |  | 1880 |  |  | 14/09/2026 | 15/09/2026 | 2026-10-09 | 2026-10-09 | 1880 | 1647 | 233
ADIDAS | 0903602360-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2100 | 30/09/2026 | 2100 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 838103 | PRINT L3 SUB PROCESS_V3 | 0903602360 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | MALAYSIA | AIR-COLLECT | 18/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 18/09/2026 | 21/09/2026 |  |  | 2100 |  | 2100 |  |  | 15/09/2026 | 17/09/2026 | 2026-10-09 | 2026-10-09 | 2100 | 1800 | 300
ADIDAS | 0903602828-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1200 | 30/09/2026 | 1200 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | DRC 0064-other customer related delay reason. 600000 | PRINT L3 SUB PROCESS_V3 | 0903602828 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 17/09/2026 | 17/09/2026 |  |  | 1200 |  | 1200 |  |  | 14/09/2026 | 14/09/2026 | 2026-11-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903603199-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 221 | 15/09/2026 | 221 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603199 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 17/09/2026 | 2026-11-09 | 14/09/2026 | 221 | 126 | 95 |  |  | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-05-09 | 221 | 221
ADIDAS | 0903603200-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 484 | 15/09/2026 | 484 | SI | SI28/08/2026 | G2I | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603200 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 484 | 242 | 242 |  |  | 2026-07-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 484 | 484
ADIDAS | 0903610424-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 101 | 31/10/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610424 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610478-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 100 | 31/10/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610478 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903613329-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 301 | 15/10/2026 | 301 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903613329 KA6229 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 301 |  | 301 |  |  | 2026-05-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-01-10 | 2026-02-10 |  |  | 301 |  | 301
ADIDAS | 0903613711-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 345 | 15/10/2026 | 345 | ID | ID11/09/2026 | G2G | T-SHIRT | G2 |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903613711 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-03-10 | 2026-03-10 |  |  | 345 |  | 345 |  |  | 30/09/2026 | 30/09/2026 |  |  | 345 |  | 345 |  |  | 28/09/2026 | 28/09/2026 |  |  | 345 |  | 345
ADIDAS | 0903613739-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 116 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 838103 | PAD+HT SUB PROCESS_V3 | 0903613739 KA0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903614275-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 241 | 15/10/2026 | 241 | ID | ID11/09/2026 | G3D | SHORTS | G3 |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614275 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-11 | ADI365/// SHO W BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 241 |  | 241 |  |  | 2026-06-11 | 2026-06-11 |  |  | 241 |  | 241 |  |  | 2026-05-11 | 2026-05-11 |  |  | 241 |  | 241
ADIDAS | 0903614393-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 100 | 15/10/2026 | 100 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614393 KA6229 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-08-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903614427-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 111 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614427 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903614814-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 451 | 31/10/2026 | 451 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614814 KA6229 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-10-11 |  |  | 451 |  | 451 |  |  | 2026-05-11 | 2026-06-11 |  |  | 451 |  | 451 |  |  | 2026-02-11 | 2026-03-11 |  |  | 451 |  | 451
ADIDAS | 0903615793-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 117 | 15/10/2026 | 117 | ID | ID11/09/2026 | G3D | SHORTS | G3 |  |  | 839055 | PAD+HT SUB PROCESS_V3 | 0903615793 KD3875 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-11 | ADI365/// SHO W BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 117 |  | 117 |  |  | 2026-06-11 | 2026-06-11 |  |  | 117 |  | 117 |  |  | 2026-05-11 | 2026-05-11 |  |  | 117 |  | 117
ADIDAS | 4501769841-6 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 383 | 2026-05-09 | 383 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 04/09: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 27/07/2026 | IN RANGE |  | FW26 | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 383 | 383 |  |  |  | 22/07/2026 | 29/07/2026 | 2026-08-07 | 27/07/2026 | 383 | 383
ADIDAS | 4501928489-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 444 | 31/10/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501928489 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 4501928501-1 LG9669 | BLACK | 120D | S2754WAS514C | 189 | 14/10/2026 | 189 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928501 LG9669 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 189 |  | 189 |  |  | 2026-10-10 | 2026-12-10 |  |  | 189 |  | 189
ADIDAS | 4501929295-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 160 | 14/10/2026 | 160 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929295 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 160 |  | 160 |  |  | 19/09/2026 | 19/09/2026 |  |  | 160 |  | 160 |  |  | 17/09/2026 | 17/09/2026 |  |  | 160 |  | 160
ADIDAS | 4501929321-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 582 | 14/10/2026 | 582 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929321 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 2026-06-10 | 2026-06-10 |  |  | 582 |  | 582 |  |  | 2026-02-10 | 2026-02-10 |  |  | 582 |  | 582 |  |  | 30/09/2026 | 30/09/2026 |  |  | 582 |  | 582
ADIDAS | 4502065732-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 671 | 14/10/2026 | 671 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 24/09/2026 | 28/09/2026 |  |  | 671 |  | 671 |  |  | 21/09/2026 | 24/09/2026 |  |  | 671 |  | 671
ADIDAS | 4502066600-1 LF0727 | BLACK | 120D | S2754MAS510B | 181 | 31/10/2026 | 181 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502066600 LF0727 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-09-11 | M SL WV TT BLACK |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 181 |  | 181 |  |  | 2026-05-11 | 2026-07-11 |  |  | 181 |  | 181
ADIDAS | 4502066601-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1481 | 21/10/2026 | 1481 | SI | SI26/06/2026 | G1P | T-SHIRT | G1 | (08/08/2026) | ok | ZA30 | EMBRO SUB PROCESS_V1 | 4502066601 KD3911 |  | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/10/2026 | RELEASED |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 1481 |  | 1481 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1481 |  | 1481
ADIDAS | 4502066684-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). ZA30 | HT+PAD SUB PROCESS_V3 | 4502066684 KB5961 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066806-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 959 | 21/10/2026 |  | AT | AT26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 4502066806 KA5090 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | MINI EMB T |  | SS27 | [20 empty] | 2026-02-09 | 2026-02-09 |  | 9 |  | 9
ADIDAS | 4502066844-1 KB5965 | BLACK | 120D | S2608MR0900A | 300 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066871-1 KE8424 | BLACK | 120D | S2608MR0906A | 164 | 31/10/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 4502066873-1 KB5960 | WHITE | 120D | S2608MR0900A | 756 | 31/10/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502070409-1 LF0718 | BLACK | 105D | S2754MAS512B | 140 | 14/10/2026 | 140 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/10/2026 | M SL WV OH PT BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 140 |  | 140 |  |  | 2026-10-10 | 2026-12-10 |  |  | 140 |  | 140
ADIDAS | 4502075077-1 IN1173 | WHITE | 90D | S2408WR1600 | 190 | 2026-07-10 | 190 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075077 IN1173 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 190 |  | 190 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-08 | 26/08/2026 | 190 | 190 |  |  |  | 2026-07-10 | 2026-08-10 | 2026-08-08 | 22/08/2026 | 190 | 190
ADIDAS | 4502075081-1 KA0246 | BLACK | 90D | S2608WR0902 | 961 | 14/10/2026 | 961 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075081 KA0246 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 29/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 961 |  | 961 |  |  | 25/09/2026 | 28/09/2026 |  |  | 961 |  | 961 |  |  | 24/09/2026 | 26/09/2026 |  |  | 961 |  | 961
ADIDAS | 4502075922-1 KT4840 | ONIX | 90D | S2408MR1600 | 100 | 14/10/2026 | 100 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075922 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502075923-1 IN1156 | BLACK | 90D | S2408MR1600 | 413 | 2026-07-10 | 413 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 413 |  | 413 |  |  | 22/09/2026 | 23/09/2026 | 26/08/2026 | 2026-12-09 | 413 | 413 |  |  |  | 21/09/2026 | 22/09/2026 | 18/08/2026 | 2026-05-09 | 413 | 413
ADIDAS | 4502075923-2 IN1156 | BLACK | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) |  | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 100 |  | 100 |  |  | 29/10/2026 | 30/10/2026 |  |  | 100 |  | 100 |  |  | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502075924-1 IN1172 | BLACK | 90D | S2408WR1600 | 212 | 2026-07-10 | 212 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075924 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 212 |  | 212 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-04-09 | 212 | 212 |  |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 2026-04-09 | 212 | 212
ADIDAS | 4502075929-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 326 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 1st Art (TC 10 pcs) ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075929 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502075931-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 179 | 14/10/2026 | 179 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502075931 LD0292 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 179 |  | 179 |  |  | 2026-03-10 | 2026-06-10 |  |  | 179 |  | 179 |  |  | 2026-02-10 | 2026-05-10 |  |  | 179 |  | 179
ADIDAS | 4502075932-1 KA0235 | BLACK | 90D | S2608WR0901 | 971 | 14/10/2026 | 971 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075932 KA0235 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 23/10/2026 | 27/10/2026 |  |  | 971 |  | 971 |  |  | 20/10/2026 | 23/10/2026 |  |  | 971 |  | 971 |  |  | 19/10/2026 | 22/10/2026 |  |  | 971 |  | 971
ADIDAS | 4502076908-1 KA4331 | BLACK | 90D | S2608MR0902 | 1102 | 14/10/2026 | 1102 | SA | SA03/07/2026 | G1C | SHORTS | G1 | (26/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-05-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 1102 |  | 1102 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1102 |  | 1102 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1102 |  | 1102
ADIDAS | 4502076908-2 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 21/10/2026 | 100 | SA | SA03/07/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100 |  |  | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100 |  |  | 20/10/2026 | 21/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502077517-1 IN1172 | BLACK | 90D | S2408WR1600 | 292 | 30/09/2026 | 292 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077517 IN1172 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 292 |  | 292 |  |  | 25/09/2026 | 26/09/2026 | 27/08/2026 | 2026-10-09 | 292 | 292 |  |  |  | 24/09/2026 | 25/09/2026 | 24/08/2026 | 2026-09-09 | 292 | 292
ADIDAS | 4502077518-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 30/09/2026 | 167 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502077518 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 167 |  | 167 |  |  | 28/09/2026 | 29/09/2026 | 24/08/2026 | 2026-07-09 | 167 | 167 |  |  |  | 26/09/2026 | 28/09/2026 | 22/08/2026 | 2026-05-09 | 167 | 167
ADIDAS | 4502077519-1 IN1157 | WHITE | 90D | S2408MR1600 | 706 | 30/09/2026 | 706 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 06-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077519 IN1157 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 706 |  | 706 |  |  | 28/09/2026 | 29/09/2026 | 2026-09-09 | 2026-11-09 | 706 | 703 | 3 |  |  | 26/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 706 | 703 | 3
ADIDAS | 4502080370-1 IN1156 | BLACK | 90D | S2408MR1600 | 527 | 30/09/2026 | 527 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502080370 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 527 | 511 | 16 |  | 511 | 2026-12-09 | 18/09/2026 | 26/08/2026 | 2026-10-09 | 527 | 527 |  |  |  | 2026-11-09 | 17/09/2026 | 24/08/2026 | 2026-09-09 | 527 | 527
ADIDAS | 4502080372-1 IN1173 | WHITE | 90D | S2408WR1600 | 109 | 30/09/2026 | 109 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. ZA30 | HT SUB PROCESS_V1 | 4502080372 IN1173 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 18/09/2026 |  |  | 109 |  | 109 |  |  | 15/09/2026 | 16/09/2026 | 2026-12-08 | 21/08/2026 | 109 | 109 |  |  |  | 14/09/2026 | 15/09/2026 | 2026-11-08 | 20/08/2026 | 109 | 109
ADIDAS | 4502347774-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 800 | 15/09/2026 | 800 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3+PAD SUB PROCESS_V3 | 4502347774 KA0546 | 26/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 800 | 800 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-09-09 | 800 | 800
ADIDAS | 46075347-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1622 | 30/09/2026 | 1622 | SI | SI22/08/2026 | G2F | T-SHIRT | G2 |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 46075347 LZ9161 | 2026-04-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 17/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 1622 |  | 1622 |  |  | 14/09/2026 | 15/09/2026 | 29/08/2026 | 2026-11-09 | 1622 | 4200 | -2578 | 2578
ADIDAS | OFC-07092026-002 | MULTI COLOR | 45D | F213CSIM105FL | 12295 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-002 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-003 | MULTI COLOR | 45D | F213CSIM109FL | 6 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-003 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-012 | MULTI COLOR | 45D | F2225M402 | 991 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-012 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-020 | MULTI COLOR | 45D | F224CSIM430 | 10836 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-020 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-032 | MULTI COLOR | 45D | F24KLKGFX003 | 268 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-032 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-048 | MULTI COLOR | 60D | F25KLKGFX011 | 801 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-048 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1134 | MULTI COLOR | 60D | S27FBGFXP510 | 5 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1134 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-142 | MULTI COLOR | 90D | F2625M101 | 232 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-303 | MULTI COLOR | 60D | PH_F_SWK_A | 204 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-303 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-427 | MULTI COLOR | 45D | S211CSIM117FLRO | 6 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-427 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-430 | MULTI COLOR | 45D | S211CSIW114SJ | 215 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PAD SUB PROCESS_V3 | OFC-07092026-430 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-443 | MULTI COLOR | 60D | S2315KSWU253 | 723 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-443 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-522 | MULTI COLOR | 60D | S2525M200 | 1 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-522 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-535 | MULTI COLOR | 90D | S2554MESS605FT | 18 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-535 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-592 | MULTI COLOR | 60D | S25ORISW311 | 1 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | OFC-07092026-592 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-769 | MULTI COLOR | 90D | S2625M018 | 135 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-769 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-774 | MULTI COLOR | 90D | S2625M036 | 330 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-774 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-848 | MULTI COLOR | 60D | S26KJUGFX009 | 357 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-848 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-856 | MULTI COLOR | 60D | S26SPRWGFX004 | 4 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | OFC-07092026-856 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902859677-1 JZ7808 | BLACK | 60D | S2608WR0900 | 364 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902859677 JZ7808 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862146-1 JZ7808 | BLACK | 60D | S2608WR0900 | 332 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902862146 JZ7808 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862401-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 425 | 46215 |  | SI | SI24/04/2026 |  | SHORTS |  | ok | (04/06/2026) | T2 Formosa, material quality issues (shading), PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, material quality issues (shading), PI Date 07-Jun, actual receives 01-Jul (FOC 327yd). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862401 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27
ADIDAS | 0902887722-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 329 | 46214 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887722 KD0677 | 22/07/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887725-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 759 | 30/11/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887725 KA3521 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902900852-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 312 | 30/11/2026 |  | SI | SI15/05/2026 |  | T-SHIRT |  | (13/07/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0902900852 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902901036-1 JZ7808 | BLACK | 120D | S2608WR0900 | 483 | 46214 |  | SA | SA15/05/2026 |  | T-SHIRT |  | (13/07/2026) | ok | 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902901036 JZ7808 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902902915-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 306 | 46214 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | (08/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902902915 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902904621-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 315 | 46215 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902904621 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902905709-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 322 | 46215 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902905709 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902930249-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 563 | 46214 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930249 KX3713 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930252-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 342 | 23/11/2026 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902930252 KX3713 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930257-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 483 | 46215 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902930257 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902930261-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 326 | 46215 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930261 LD0283 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902930263-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 334 | 46214 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930263 LD0283 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902931103-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 483 | 46215 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902931103 LD0285 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902931104-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 335 | 46214 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902931104 LD0285 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902931105-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 324 | 46215 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902931105 LD0285 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902933084-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 429 | 46215 |  | SI | SI15/05/2026 |  | JACKET |  | ok |  | T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May.. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933084 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER WHITE/BLACK |  | SS27
ADIDAS | 0902954134-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 322 | 46214 |  | SA | SA29/05/2026 |  | JACKET |  | (15/07/2026) | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954134 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0902954770-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 453 | 46214 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954770 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902954935-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 340 | 46214 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954935 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956034-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 355 | 46214 |  | SI | SI29/05/2026 |  | SHORTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956034 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0902956935-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 370 | 46214 |  | AN | AN29/05/2026 |  | JACKET |  | (29/06/2026) | (19/06/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Jun, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jun, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956935 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0902957063-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 696 | 46215 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957063 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0902959310-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 1615 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902959310 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902959425-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 707 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902959425 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902959517-1 LH3758 | BLACK | 120D | S2754WAS518B | 365 | 46215 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959517 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0902960904-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 410 | 15/12/2026 |  | SA | SA29/05/2026 |  | SHORTS |  | ok | (25/06/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960904 LH4535 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0902960952-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 110 | 15/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902960952 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961002-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 120 | 46214 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961002 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961906-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 856 | 15/12/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902961906 LD0283 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902961947-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 136 | 23/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961947 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902962237-1 JZ7808 | BLACK | 120D | S2608WR0900 | 300 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902962237 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902962367-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 105 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902962367 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902969632-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 535 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 672027 | HT+PAD SUB PROCESS_V3 | 0902969632 KF5311 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0902975836-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 2400 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0902975836 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0902982744-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 15/12/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902982744 LD0283 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902987712-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 319 | 46214 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987712 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987796-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 451 | 23/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987796 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987830-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987830 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902988826-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 229 | 46214 |  | SA | SA29/05/2026 |  | PANTS |  | (27/07/2026) | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988826 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0902988871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 199 | 46215 |  | SA | SA29/05/2026 |  | PANTS |  | (27/07/2026) | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988871 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0902990823-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 128 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990823 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902990853-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990853 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0903043395-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4200 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043395 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903043496-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043496 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903043590-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 4800 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043590 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903045667-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4800 | 46214 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045667 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903045765-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 4800 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045765 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903045811-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1200 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045811 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903045956-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4800 | 46214 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045956 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27
ADIDAS | 0903046008-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 948 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903046008 KX3650 | 46335 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903046882-1 KB5965 | BLACK | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046882 KB5965 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903046898-1 KB5960 | WHITE | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046898 KB5960 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047008-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 282 | 46214 |  | AN | AN12/06/2026 |  | JACKET |  | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047008 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903047031-1 LG9675 | BLACK | 120D | S2754WAS513C | 208 | 30/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047031 LG9675 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047059-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 120 | 30/11/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047059 LG9669 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903047122-1 KB5960 | WHITE | 120D | S2608MR0900A | 300 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903047122 KB5960 | 46335 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047142-1 KB5965 | BLACK | 120D | S2608MR0900A | 400 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903047142 KB5965 | 46335 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047322-1 LG9675 | BLACK | 120D | S2754WAS513C | 383 | 46214 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047322 LG9675 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047397-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903047397 LH3759 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903048584-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 459 | 30/11/2026 | 459 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048584 LD0287 | 46335 | KAHATEX CIJERAH | JAPAN | SEA | 31/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 31/10/2026 | 31/10/2026 |  |  | 459 |  | 459 |  |  | 28/10/2026 | 28/10/2026 | 27/08/2026 | 46304 | 459 | 458 | 1 |  |  | 26/10/2026 | 26/10/2026 | 26/08/2026 | 46304 | 459 | 458 | 1
ADIDAS | 0903049235-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 508 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049235 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903053818-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 450 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903053818 KX3650 | 46335 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903054588-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054588 LH3759 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903054623-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054623 LH3761 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903056025-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056025 KB5965 | 46335 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903056057-1 KB5965 | BLACK | 120D | S2608MR0900A | 138 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056057 KB5965 | 46335 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903056557-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 141 | 15/11/2026 |  | AN | AN12/06/2026 |  | SWEATSHIRT |  | ok | (17/07/2026) | 516205 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903056557 KY1361 | 29/07/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | REAL HER CR BLACK/BLACK |  | SS27
ADIDAS | 0903058736-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 303 | 46215 |  | SA | SA12/06/2026 |  | PANTS |  | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903058736 KY5988 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903059435-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 109 | 46215 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059435 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059465-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 865 | 46214 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059465 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059549-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 118 | 46215 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059549 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059897-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 480 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903059897 LD0285 | 46335 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0903060334-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 46215 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (03/07/2026) | Waiting fabric. T2 Kahatex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060334 LF0729 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903060669-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 188 | 46215 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 20-Jul, ETD ?? T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060669 LF0726 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903060691-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 275 | 46215 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060691 LF0727 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903060718-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 100 | 46215 |  | AN | AN12/06/2026 |  | SKIRT |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903060718 LG9669 | 46335 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903060727-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 200 | 46215 |  | SA | SA12/06/2026 |  | SHORTS |  | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060727 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 74 WHITE/BLACK |  | SS27
ADIDAS | 0903061680-1 LE5038 | BLACK | 105D | S2750MTR104A | 180 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903061680 LE5038 | 46335 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061955-1 LE5038 | BLACK | 105D | S2750MTR104A | 241 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061955 LE5038 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061985-1 LE5038 | BLACK | 105D | S2750MTR104A | 221 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061985 LE5038 | 46335 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903062051-1 LE5038 | BLACK | 105D | S2750MTR104A | 252 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903062051 LE5038 | 46335 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903063396-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 394 | 46214 |  | AN | AN12/06/2026 |  | SKIRT |  | (20/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063396 LG9669 | 46335 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903093131-1 KF5803 | BLACK | 105D | S2608MR0602A | 727 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903093131 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093134-1 KF5803 | BLACK | 105D | S2608MR0602A | 302 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093134 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093432-1 KZ4392 | WHITE | 120D | F2608WR1500 | 50 | 30/11/2026 | 50 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. DRC 0064-T2 Men Chuen, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093432 KZ4392 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46184 | ADIZERO A TEE W WHITE |  | SS27-TRAX | 46184 | 46184 |  |  | 50 |  | 50 |  |  | 46092 | 46092 |  |  | 50 |  | 50 |  |  | 46064 | 46064 |  |  | 50 |  | 50
ADIDAS | 0903093481-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1637 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093481 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903093484-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 350 | 46214 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093484 KY9384 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903093496-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 379 | 46215 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093496 KD3854 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903093497-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 333 | 46215 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 24-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093497 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903093896-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 6 | 23/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 960026 | PRINT L2+HT SUB PROCESS_V3 | 0903093896 KZ0028 | 46212 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093897-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 478 | 15/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 830009 | PRINT L2+HT SUB PROCESS_V3 | 0903093897 KZ0028 | 46212 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093913-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 749 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093913 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093914-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 323 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093914 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093915-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 179 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903093915 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093916-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 320 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516254 | PAD+HT SUB PROCESS_V3 | 0903093916 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903093917-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 61 | 46215 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093917 LG1784 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903093918-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 324 | 46215 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093918 LG1784 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903095148-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 366 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903095148 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903095159-1 KZ1333 | HAZE CORAL S17 | 105D | S2608WR0201A | 60 | 15/11/2026 | 60 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903095159 KZ1333 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46306 | ADI365 SHO W HAZE CORAL S17 |  | SS27-TRAX | 46306 | 46337 |  |  | 60 |  | 60 |  |  | 46184 | 46214 |  |  | 60 |  | 60 |  |  | 46153 | 46184 |  |  | 60 |  | 60
ADIDAS | 0903095166-1 LF4208 | TEAM ROYAL BLUE | 105D | S2608WR0201A | 50 | 15/11/2026 | 50 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903095166 LF4208 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 46306 | ADI365 SHO W TEAM ROYAL BLUE |  | SS27-TRAX | 46306 | 46337 |  |  | 50 |  | 50 |  |  | 46184 | 46214 |  |  | 50 |  | 50 |  |  | 46153 | 46184 |  |  | 50 |  | 50
ADIDAS | 0903095181-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 235 | 46214 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095181 LC6791 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903095207-1 KC4947 | BLACK | 105D | S2608WR0216 | 304 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903095207 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095212-1 KC4947 | BLACK | 105D | S2608WR0216 | 100 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 512110 | PAD+HT SUB PROCESS_V3 | 0903095212 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095214-1 KC4947 | BLACK | 105D | S2608WR0216 | 109 | 15/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | PAD+HT SUB PROCESS_V3 | 0903095214 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903110808-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1204 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (29/07/2026) | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110808 LE4307 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903128980-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 367 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903128980 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903130792-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1497 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? T2 Libolon, PI Date 06-Aug, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903130792 LC5741 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 72S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27
ADIDAS | 0903130818-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130818 LI2646 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903130858-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130858 LI2645 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903130900-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 2415 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | (04/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130900 LI2668 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903130905-1 LF0723 | BLACK | 105D | S2754MAS511B | 427 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130905 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130944-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 300 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130944 LF0725 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903131188-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 200 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131188 LI2647 | 46303 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903133687-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1580 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133687 LI2667 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903133962-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1891 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133962 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903134663-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 582 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. T2 Libolon, PI Date 23-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134663 KW2909 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV WB BLACK/WHITE |  | SS27
ADIDAS | 0903134760-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134760 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903135025-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (29/07/2026) | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135025 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARCH SEAL TEE |  | SS27
ADIDAS | 0903135275-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 119 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135275 LI2669 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135319-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 532 | 46215 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903135319 LG9673 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135338-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 182 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135338 LI2645 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903135342-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 568 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135342 LI2669 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135375-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 498 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903135375 LG9673 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135514-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 418 | 46215 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135514 LG9664 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135996-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1281 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135996 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136768-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 529 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136768 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136798-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1276 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136798 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903136945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 127 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136945 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903137343-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 826 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (03/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137343 KZ3227 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903137463-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 465 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (29/07/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137463 KV8005 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903138115-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 719 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138115 LI2647 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903138412-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 525 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138412 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903139689-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 993 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139689 LI2672 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903142659-1 KB5965 | BLACK | 120D | S2608MR0900A | 1804 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142659 KB5965 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142864-1 KB5960 | WHITE | 120D | S2608MR0900A | 677 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142864 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903143517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143517 LI2645 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903143521-1 LF0723 | BLACK | 105D | S2754MAS511B | 564 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143521 LF0723 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903143540-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143540 LI2671 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903143546-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 215 | 46215 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143546 LF0726 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903143571-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 450 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143571 LI2647 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903143577-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 100 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143577 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903143597-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143597 LI2646 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903143604-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 230 | 46215 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143604 LF0718 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903143634-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143634 LI2670 | 46303 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903143641-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 335 | 46215 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143641 LE8181 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903144865-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 173 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903144865 JG5832 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903144982-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1140 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903144982 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145068-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 366 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145068 LF0726 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145411-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 1000 | 46214 |  | AN | AN26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145411 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903145447-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 199 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903145447 KR3066 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903145474-1 LG9669 | BLACK | 120D | S2754WAS514C | 106 | 46214 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903145474 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903145521-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903145521 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903145548-1 LG9675 | BLACK | 120D | S2754WAS513C | 1000 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903145548 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903145603-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 1400 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145603 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903145666-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 204 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145666 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903145710-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 562 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800187 | PRINT L1+HT SUB PROCESS_V3 | 0903145710 KU8361 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903145834-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 503 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903145834 KY5936 | 46334 | KAHATEX CIJERAH | THAILAND | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903145950-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 405 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145950 LE8181 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145998-1 LG9666 | BLACK | 120D | S2754WAS512C | 230 | 15/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145998 LG9666 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903146035-1 LE8187 | BLACK | 105D | S2754MAS513 | 497 | 15/12/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146035 LE8187 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903146070-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 798 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903146070 KU8361 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146104-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 370 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146104 LF0726 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903146143-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 445 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146143 LF0718 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903146231-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 581 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146231 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146256-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146256 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146268-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 132 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146268 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903146275-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 527 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903146275 KU8361 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146301-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146301 LF0725 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903146321-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 355 | 46215 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146321 LF0725 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903146384-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 325 | 46215 |  | AN | AN26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146384 LG9666 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903146405-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 1844 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146405 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903146460-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 192 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146460 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903146508-1 JZ7711 | BLACK | 120D | S2608MR0202 | 144 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (Cargoport). T2 Trax, PI Date 24-Jul, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146508 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146544-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 390 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903146544 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146570-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 1000 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903146570 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146595-1 KU8357 | BLACK | 105D | S2750MTR051 | 733 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903146595 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903146621-1 LC6583 | GREY | 105D | S2750MTR051 | 680 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 814006 | HT SUB PROCESS_V1 | 0903146621 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903146650-1 LE8187 | BLACK | 105D | S2754MAS513 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146650 LE8187 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903146681-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146681 KA3549 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903147883-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 205 | 46215 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903147883 LF0721 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903147919-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 100 | 46215 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903147919 LF0729 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903147964-1 LC6583 | GREY | 105D | S2750MTR051 | 210 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800187 | HT SUB PROCESS_V1 | 0903147964 LC6583 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148024-1 KU8357 | BLACK | 105D | S2750MTR051 | 331 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800187 | HT SUB PROCESS_V1 | 0903148024 KU8357 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148048-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 221 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148048 KY5901 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148127-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 213 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148127 KY5936 | 46334 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148646-1 LC6583 | GREY | 105D | S2750MTR051 | 283 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (01/08/2026) | ok | Waiting fabric replacement. T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903148646 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148668-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148668 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148676-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 2259 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903148676 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903148711-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 285 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148711 LF0721 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903148723-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 120 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148723 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148742-1 KU8357 | BLACK | 105D | S2750MTR051 | 221 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148742 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148757-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 128 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148757 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148774-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 325 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148774 LF0729 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903148833-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1032 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148833 KC8152 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903148848-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 427 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903148848 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148870-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 308 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903148870 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148873-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 390 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148873 LF0725 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903148894-1 KB5965 | BLACK | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148894 KB5965 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148901-1 KU8357 | BLACK | 105D | S2750MTR051 | 450 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148901 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148944-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 732 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903148944 LD0283 | 25/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903149176-1 JZ7711 | BLACK | 120D | S2608MR0202 | 540 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (KN GLT). T2 Trax, PI Date 24-Jul, ETD ?? 650031 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149176 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903149522-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 108 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149522 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149602-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 100 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903149602 JJ0052 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903149641-1 KA3530 | BLACK | 105D | S2650MTR402 | 128 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903149641 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903149843-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 396 | 30/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149843 JW7182 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903149931-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903149931 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903149955-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149955 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903150153-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 125 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150153 LF0725 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903150446-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 340 | 30/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150446 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903150468-1 KE8424 | BLACK | 120D | S2608MR0906A | 487 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150468 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903150575-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1906 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903150575 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903150999-1 LG9669 | BLACK | 120D | S2754WAS514C | 143 | 15/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512102 | PRINT L3+PPA SUB PROCESS_V3 | 0903150999 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151026-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 739 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 659018 | HT+PAD SUB PROCESS_V3 | 0903151026 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903151173-1 KA3530 | BLACK | 105D | S2650MTR402 | 376 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151173 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151201-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 314 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151201 LF0729 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151239-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 240 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151239 LF0721 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151246-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 222 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151246 KD5507 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903151262-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 240 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151262 LF0725 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903151271-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151271 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151331-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 208 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151331 LF0721 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151379-1 LG9669 | BLACK | 120D | S2754WAS514C | 600 | 46214 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903151379 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151446-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1400 | 30/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903151446 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903151598-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 539 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903151598 KU8361 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903151643-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 117 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151643 LF0718 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903152441-1 LF0727 | BLACK | 120D | S2754MAS510B | 813 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152441 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903152456-1 KB5965 | BLACK | 120D | S2608MR0900A | 926 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152456 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152478-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 533 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152478 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152536-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1831 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152536 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903152617-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1627 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903152617 KY9391 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152941-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152941 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903153406-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 477 | 46214 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 823016 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153406 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903153476-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 102 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 680014 | PRINT L2+HT SUB PROCESS_V3 | 0903153476 KZ0028 | 46304 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903153531-1 KT4840 | ONIX | 90D | S2408MR1600 | 348 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903153531 KT4840 | 46304 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903153589-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1010 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903153589 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903153628-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 774 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (Damco offline). 688010 | PRINT L2+PAD SUB PROCESS_V3 | 0903153628 KU2430 | 46303 | KAHATEX CIJERAH | PANAMA | SEA |  | M FB NOVELTY T WHITE |  | SS27
ADIDAS | 0903153664-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 228 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | HT+PAD SUB PROCESS_V3 | 0903153664 KX3655 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903153687-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 212 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153687 LF0718 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903153698-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 409 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903153698 KB5961 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903153817-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 170 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153817 LF0726 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903153919-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 100 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153919 LE8181 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903153964-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 242 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153964 LD5446 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903154007-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 150 | 46215 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903154007 LF0726 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903154776-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 1663 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154776 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154799-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 13 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154799 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154849-1 KA3549 | BLACK | 135D | S2650MTR412 | 108 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154849 KA3549 | 46334 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903154868-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 393 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154868 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903154889-1 KA3549 | BLACK | 135D | S2650MTR412 | 126 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154889 KA3549 | 46334 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903154917-1 KA3549 | BLACK | 135D | S2650MTR412 | 102 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154917 KA3549 | 46334 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903155043-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 210 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903155043 LC8943 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903155243-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 200 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155243 KD3854 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903155535-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 180 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155535 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155567-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155567 KF5311 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903155594-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155594 KX3654 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155612-1 KT4840 | ONIX | 90D | S2408MR1600 | 186 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 680014 | HT SUB PROCESS_V1 | 0903155612 KT4840 | 46304 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903155678-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 224 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155678 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155800-1 LC7300 | WHITE | 90D | S2725M926A | 262 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903155800 LC7300 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903155810-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1129 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155810 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903155820-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 282 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | (Damco offline). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 688010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903155820 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903155831-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 112 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903155831 LC7301 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903155836-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 282 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (Damco offline). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 688010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903155836 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903155872-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155872 KW8933 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903155878-1 KB5960 | WHITE | 120D | S2608MR0900A | 591 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155878 KB5960 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155947-1 KA3549 | BLACK | 135D | S2650MTR412 | 110 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903155947 KA3549 | 46334 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156012-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903156012 KA3549 | 46334 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156032-1 KE8424 | BLACK | 120D | S2608MR0906A | 522 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903156032 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903156064-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903156064 KY5901 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903156098-1 LC6583 | GREY | 105D | S2750MTR051 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 839055 | HT SUB PROCESS_V1 | 0903156098 LC6583 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156126-1 KU8357 | BLACK | 105D | S2750MTR051 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 839055 | HT SUB PROCESS_V1 | 0903156126 KU8357 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156155-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 684 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903156155 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903156632-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 245 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156632 KW8933 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903156637-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 320 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903156637 KB0246 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903156704-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 101 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903156704 LD0908 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903156821-1 LC6583 | GREY | 105D | S2750MTR051 | 196 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903156821 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156916-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 422 | 15/12/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | (04/08/2026) | (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156916 KZ3200 | 46304 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903156923-1 KU8357 | BLACK | 105D | S2750MTR051 | 232 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903156923 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156947-1 KT4840 | ONIX | 90D | S2408MR1600 | 451 | 15/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric (Airowes). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903156947 KT4840 | 46304 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903156956-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 114 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903156956 LC8884 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903156980-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 553 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (29/07/2026) | ok | (Airowes). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156980 KV7863 | 46304 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903157033-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903157033 LC7300 | 46304 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903157034-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 198 | 15/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157034 KF5311 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157056-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903157056 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903157058-1 KE8424 | BLACK | 120D | S2608MR0906A | 165 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157058 KE8424 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903157123-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 312 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903157123 KW8933 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903157615-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 102 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157615 LG9664 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903157637-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 149 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157637 LD5446 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903157760-1 KB5965 | BLACK | 120D | S2608MR0900A | 410 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903157760 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157832-1 KB5960 | WHITE | 120D | S2608MR0900A | 1492 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157832 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157859-1 KB5965 | BLACK | 120D | S2608MR0900A | 3535 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157859 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157884-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 502 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 678002 | HT+PAD SUB PROCESS_V3 | 0903157884 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157922-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 3009 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903157922 KR3066 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903157960-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 198 | 15/12/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157960 KX3655 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158055-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 229 | 15/12/2026 |  | AN | AN26/06/2026 |  | JACKET |  | ok | ok | (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158055 LF1392 | 46304 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903158194-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 838103 | HT SUB PROCESS_V1 | 0903158194 KY5866 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903158242-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 550 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903158242 JZ1089 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903158307-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 310 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903158307 KX3651 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0903158332-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158332 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158354-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158354 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158375-1 LG9666 | BLACK | 120D | S2754WAS512C | 201 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158375 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903158398-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 188 | 23/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158398 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158417-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 738 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158417 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903158426-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903158426 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158447-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 152 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158447 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158468-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158468 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158523-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158523 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158528-1 KB5960 | WHITE | 120D | S2608MR0900A | 450 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903158528 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903158543-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158543 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158570-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158570 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158596-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158596 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158627-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158627 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158788-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158788 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | PDX HBR TEE |  | SS27
ADIDAS | 0903158813-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158813 KR1994 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | DICE TEE |  | SS27
ADIDAS | 0903159008-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159008 KS2145 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | PIZZA TEE |  | SS27
ADIDAS | 0903159089-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | ok | ok | T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159089 KV7963 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903159152-1 JZ7711 | BLACK | 120D | S2608MR0202 | 187 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159152 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903159185-1 KU8357 | BLACK | 105D | S2750MTR051 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903159185 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903159233-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 114 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159233 KX0126 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T OLIVE FOUR S27 |  | SS27
ADIDAS | 0903159243-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 227 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric (Airowes). T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159243 LF0726 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159272-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 228 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159272 LC7301 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903159311-1 LC7300 | WHITE | 90D | S2725M926A | 228 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159311 LC7300 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903159349-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 156 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903159349 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903159476-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 312 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159476 LE8181 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159754-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 584 | 23/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159754 LF0726 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159774-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159774 KR3066 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903159800-1 LG9669 | BLACK | 120D | S2754WAS514C | 396 | 23/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903159800 LG9669 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903160049-1 KA3530 | BLACK | 105D | S2650MTR402 | 244 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903160049 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160055-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 657 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160055 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903160079-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 130 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903160079 KB0237 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903160125-1 KA3530 | BLACK | 105D | S2650MTR402 | 257 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903160125 KA3530 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160245-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160245 KY5866 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160344-1 KY5866 | BLACK | 90D | S2750MTR052 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160344 KY5866 | 46304 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160388-1 KA0246 | BLACK | 90D | S2608WR0902 | 405 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516400 | PAD+HT SUB PROCESS_V3 | 0903160388 KA0246 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903160662-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 1461 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160662 LD6542 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903160682-1 KB5960 | WHITE | 120D | S2608MR0900A | 250 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903160682 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903161120-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 100 | 46215 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903161120 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903161179-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2545 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161179 KZ3202 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903161241-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2662 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | (07/08/2026) | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161241 KZ3200 | 46304 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903162158-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162158 KB0234 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903162234-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 324 | 46214 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162234 JZ1077 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T BLACK |  | SS27-STX
ADIDAS | 0903162276-1 KA3530 | BLACK | 105D | S2650MTR402 | 1263 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903162276 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903162278-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1526 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162278 LD0283 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903162311-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1226 | 15/12/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162311 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903162492-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 348 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162492 KB0247 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903162518-1 KA3549 | BLACK | 135D | S2650MTR412 | 208 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162518 KA3549 | 46334 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903162545-1 KA3549 | BLACK | 135D | S2650MTR412 | 921 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162545 KA3549 | 46334 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903163092-1 KU8357 | BLACK | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 838103 | HT SUB PROCESS_V1 | 0903163092 KU8357 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903163452-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 411 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163452 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903163561-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 610 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163561 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903164394-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 940 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164394 KB0237 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903164435-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 280 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164435 KB0234 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164449-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 892 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164449 KS3009 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903164515-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903164515 KA3530 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903164654-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 651 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903164654 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903164675-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 141 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164675 JZ1090 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164712-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 100 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164712 JZ1090 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164747-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 205 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164747 KB0246 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164777-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 102 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164777 JZ1089 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164808-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 278 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164808 JZ1089 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164853-1 KT4840 | ONIX | 90D | S2408MR1600 | 206 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903164853 KT4840 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903164866-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 522 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903164866 KU8361 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903164923-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 182 | 46214 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164923 KV8149 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164958-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 150 | 46214 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164958 KV8142 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164977-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 845 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903164977 KW8933 | 46304 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903165011-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 112 | 46214 |  | AN | AN26/06/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903165011 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI
ADIDAS | 0903165093-1 KY5866 | BLACK | 90D | S2750MTR052 | 294 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903165093 KY5866 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903165114-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 152 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903165114 KS3009 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903165135-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 378 | 46215 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165135 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903165143-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 120 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903165143 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165365-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 400 | 46214 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165365 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903165453-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 924 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903165453 KV8149 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903165549-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903165549 KD5507 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165577-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 178 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | Request Cancel (BTP_014_09_2026_ Req. PO Cancel & Quantity Change). 838103 | PAD+HT SUB PROCESS_V3 | 0903165577 JG5832 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903165613-1 LC7300 | WHITE | 90D | S2725M926A | 240 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903165613 LC7300 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903166410-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 217 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PAD+HT SUB PROCESS_V3 | 0903166410 JJ0052 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903166569-1 JJ2417 | BLACK/WHITE | 90D | S2506GHTM401Y | 174 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | 1st Art (TC 10 pcs) 838103 | PAD+HT SUB PROCESS_V3 | 0903166569 JJ2417 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 SHO Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903167257-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 852 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903167257 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167292-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167292 KR6693 | 46303 | KAHATEX CIJERAH | UNITED STATES | SEA |  | LV COLLEGIATE T |  | SS27
ADIDAS | 0903167354-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 180 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903167354 KU8361 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903167377-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 475 | 15/12/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903167377 JZ1090 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903167397-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 615 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903167397 LC7301 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903167406-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 160 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903167406 KB0247 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903167413-1 LC7300 | WHITE | 90D | S2725M926A | 354 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903167413 LC7300 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167435-1 LF0727 | BLACK | 120D | S2754MAS510B | 884 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167435 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903167477-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 770 | 46215 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167477 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167515-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 800187 | PRINT L1 SUB PROCESS_V3 | 0903167515 LC7300 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167539-1 KY5866 | BLACK | 90D | S2750MTR052 | 100 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903167539 KY5866 | 46304 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167578-1 KY5866 | BLACK | 90D | S2750MTR052 | 1639 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903167578 KY5866 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167656-1 LC6583 | GREY | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 838103 | HT SUB PROCESS_V1 | 0903167656 LC6583 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903167699-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903167699 KD5507 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167750-1 KA4331 | BLACK | 90D | S2608MR0902 | 668 | 15/12/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903167750 KA4331 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903167765-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 536 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 04-Sep. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516267 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167765 KV7863 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903167819-1 KA4331 | BLACK | 90D | S2608MR0902 | 418 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903167819 KA4331 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903167866-1 LG9675 | BLACK | 120D | S2754WAS513C | 530 | 46214 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167866 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903167978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 344 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167978 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903168007-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1036 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903168007 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903168036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 707 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903168036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903168237-1 KA3530 | BLACK | 105D | S2650MTR402 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903168237 KA3530 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903169208-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 320 | 23/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169208 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903169300-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 150 | 46214 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903169300 KD5507 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903169676-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 310 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903169676 LC7301 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903169815-1 KY5866 | BLACK | 90D | S2750MTR052 | 259 | 46214 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903169815 KY5866 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903170004-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903170004 LC7301 | 46304 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903171050-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 600 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903171050 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903171083-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 689 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903171083 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI
ADIDAS | 0903171134-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 222 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903171134 KS3009 | 46304 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903173165-1 KE9633 | BLACK | 105D | S2650MTR810B | 243 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (02/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 02-Aug, ETD ?? Waiting fabric. T2 Sue's, PI Date 28-Jul, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903173165 KE9633 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHES 2in1 SHO BLACK |  | SS27-TI
ADIDAS | 0903173400-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903173400 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903173451-1 LG9669 | BLACK | 120D | S2754WAS514C | 348 | 46215 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903173451 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903194097-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 533 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194097 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903194102-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194102 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194106-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 415 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194106 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194111-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 320 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194111 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194112-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 329 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194112 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194125-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 100 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194125 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194126-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 289 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194126 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194127-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 221 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194127 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194129-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1331 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903194129 KY9391 | 28/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194131-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 616 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516439 | PAD+HT SUB PROCESS_V3 | 0903194131 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194134-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1011 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194134 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903194139-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1080 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194139 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194143-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 262 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194143 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194144-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 145 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194144 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194289-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/12/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194289 IN1157 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194291-1 IN1156 | BLACK | 90D | S2408MR1600 | 181 | 15/12/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194291 IN1156 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194292-1 IN1172 | BLACK | 90D | S2408WR1600 | 112 | 15/12/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194292 IN1172 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194320-1 KG8547 | ONIX | 90D | S2408WR1600 | 224 | 30/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194320 KG8547 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194322-1 KT4840 | ONIX | 90D | S2408MR1600 | 212 | 30/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194322 KT4840 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194348-1 KT4840 | ONIX | 90D | S2408MR1600 | 243 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194348 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194350-1 KG8547 | ONIX | 90D | S2408WR1600 | 365 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194350 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194353-1 KG8547 | ONIX | 90D | S2408WR1600 | 308 | 46214 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194353 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194355-1 KG8547 | ONIX | 90D | S2408WR1600 | 235 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194355 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194359-1 KT4840 | ONIX | 90D | S2408MR1600 | 414 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194359 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194450-1 KA6229 | BLACK | 120D | S2608WR0202 | 354 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194450 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903194470-1 KA6229 | BLACK | 120D | S2608WR0202 | 130 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194470 KA6229 | 28/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903194986-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 105 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194986 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903195079-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 177 | 46214 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195079 LF0718 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903195509-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 221 | 46214 |  | SA | SA30/06/2026 |  | JACKET |  | (23/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 23-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195509 LG9664 | 28/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903196029-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 46214 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903196029 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903197367-1 KT4839 | ONIX | 90D | S2408MR1601 | 236 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 839055 | HT SUB PROCESS_V1 | 0903197367 KT4839 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197369-1 KG8549 | ONIX | 90D | S2408WR1601A | 265 | 46215 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197369 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197373-1 KT4839 | ONIX | 90D | S2408MR1601 | 317 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197373 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197374-1 KG8549 | ONIX | 90D | S2408WR1601A | 160 | 46215 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 839055 | HT SUB PROCESS_V1 | 0903197374 KG8549 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197375-1 KA4331 | BLACK | 90D | S2608MR0902 | 184 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903197375 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903197377-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 204 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197377 KX9851 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197378-1 KG8549 | ONIX | 90D | S2408WR1601A | 116 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197378 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197380-1 KG8549 | ONIX | 90D | S2408WR1601A | 154 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197380 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197384-1 KT4839 | ONIX | 90D | S2408MR1601 | 237 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197384 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197385-1 KT4839 | ONIX | 90D | S2408MR1601 | 400 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903197385 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197391-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197391 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197393-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 148 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 839055 | PAD+HT SUB PROCESS_V3 | 0903197393 LD0908 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197395-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197395 LD0278 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903197397-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197397 LD0293 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197399-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 190 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197399 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197401-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 305 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | PAD+HT SUB PROCESS_V3 | 0903197401 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197403-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 380 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 838103 | PAD+HT SUB PROCESS_V3 | 0903197403 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197405-1 KG8549 | ONIX | 90D | S2408WR1601A | 181 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197405 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197406-1 KT4839 | ONIX | 90D | S2408MR1601 | 188 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 830009 | HT SUB PROCESS_V1 | 0903197406 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197408-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 8 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 1st Art (TC 10 pcs) 650010 | HT SUB PROCESS_V1 | 0903197408 IT1467 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903197410-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903197410 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903197411-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 102 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903197411 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197413-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 182 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197413 KX9851 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197415-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 116 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197415 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197416-1 KG8549 | ONIX | 90D | S2408WR1601A | 282 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197416 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197418-1 KG8549 | ONIX | 90D | S2408WR1601A | 254 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197418 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197420-1 KT4839 | ONIX | 90D | S2408MR1601 | 233 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197420 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197422-1 KT4839 | ONIX | 90D | S2408MR1601 | 134 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903197422 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197423-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 514 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197423 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903197470-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 708 | 30/11/2026 | 708 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903197470 LD0293 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 18/11/2026 | 21/11/2026 |  |  | 708 |  | 708 |  |  | 14/11/2026 | 18/11/2026 |  |  | 708 |  | 708 |  |  | 13/11/2026 | 17/11/2026 |  |  | 708 |  | 708
ADIDAS | 0903197493-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 676 | 30/11/2026 | 676 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197493 LD0293 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 18/11/2026 | 21/11/2026 |  |  | 676 |  | 676 |  |  | 14/11/2026 | 18/11/2026 |  |  | 676 |  | 676 |  |  | 13/11/2026 | 17/11/2026 |  |  | 676 |  | 676
ADIDAS | 0903197750-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 738 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197750 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903197752-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 951 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197752 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903197755-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 749 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197755 KY9391 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197765-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 104 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197765 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903197780-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 964 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197780 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197782-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1337 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197782 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197791-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 303 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197791 LF9775 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX
ADIDAS | 0903197795-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 197 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903197795 KY9393 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197802-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 321 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903197802 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197832-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 367 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197832 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903197837-1 JZ7711 | BLACK | 120D | S2608MR0202 | 379 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197837 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197843-1 JZ7711 | BLACK | 120D | S2608MR0202 | 622 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197843 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197845-1 JZ7711 | BLACK | 120D | S2608MR0202 | 322 | 46214 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197845 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197882-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 304 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 10-Aug. Waiting fabric. T2 Best Pacific, PI Date 09-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903197882 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903203174-1 KB5960 | WHITE | 120D | S2608MR0900A | 108 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903203174 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903208401-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 100 | 23/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903208401 KX9855 | 17/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208402-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 168 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903208402 KX9855 | 17/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208403-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 182 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903208403 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208404-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 102 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208404 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208405-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 170 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208405 KX9855 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208406-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 332 | 46215 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903208406 KX9855 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208438-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 252 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903208438 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903208439-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 474 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903208439 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209753-1 IN1156 | BLACK | 90D | S2408MR1600 | 640 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 512107 | HT SUB PROCESS_V1 | 0903209753 IN1156 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209759-1 IN1157 | WHITE | 90D | S2408MR1600 | 253 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Y.T.I, Mesh: ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209759 IN1157 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209771-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209771 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209776-1 KG8547 | ONIX | 90D | S2408WR1600 | 234 | 30/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 680014 | HT SUB PROCESS_V1 | 0903209776 KG8547 |  | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209793-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 120 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209793 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209794-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 418 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209794 KX9838 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209795-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903209795 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209796-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 234 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903209796 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209797-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 342 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903209797 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209798-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 9675 | 15/12/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, Body PI Date 21-Sep (6999 yd). T2 Fu Hsun, Mesh PI Date 03-Aug, ETD ?? Waiting fabric. T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug (2017 yd). 814006 | HT SUB PROCESS_V1 | 0903209798 KX9838 | 21/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209807-1 IN1173 | WHITE | 90D | S2408WR1600 | 427 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209807 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209905-1 IN1173 | WHITE | 90D | S2408WR1600 | 338 | 46215 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903209905 IN1173 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209906-1 IN1172 | BLACK | 90D | S2408WR1600 | 321 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903209906 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209908-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 511 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903209908 KZ2984 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209909-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 341 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209909 KG8548 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903244360-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 404 | 46215 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903244360 LF0718 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903245450-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 300 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 680015 | HT+PAD SUB PROCESS_V3 | 0903245450 KB5961 | 46244 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245476-1 KB5965 | BLACK | 120D | S2608MR0900A | 800 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245476 KB5965 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245499-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903245499 KA4331 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903245532-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 600 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245532 KB5959 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903248693-1 LG9666 | BLACK | 120D | S2754WAS512C | 560 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? s516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903248693 LG9666 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903248718-1 LG9675 | BLACK | 120D | S2754WAS513C | 371 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903248718 LG9675 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903248892-1 KG3189 | MAROON | 120D | S2608MR0900A | 699 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248892 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903248948-1 KG3189 | MAROON | 120D | S2608MR0900A | 453 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248948 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903249143-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903249143 KX3655 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903250899-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903250899 LG9665 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903250925-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 322 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903250925 LG9668 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903251000-1 KG3189 | MAROON | 120D | S2608MR0900A | 123 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251000 KG3189 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251073-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 1204 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848012 | HT+PAD SUB PROCESS_V3 | 0903251073 KB5961 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903251123-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 311 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251123 LE8188 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903251133-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1072 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251133 KX3655 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903251145-1 KA0246 | BLACK | 105D | S2608WR0902 | 132 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 848016 | PAD+HT SUB PROCESS_V3 | 0903251145 KA0246 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251361-1 KB5960 | WHITE | 120D | S2608MR0900A | 292 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903251361 KB5960 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903251430-1 KA0246 | BLACK | 105D | S2608WR0902 | 309 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903251430 KA0246 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251511-1 KA0246 | BLACK | 105D | S2608WR0902 | 1186 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903251511 KA0246 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251558-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 321 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903251558 LD0908 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251577-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 298 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903251577 LD0908 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251656-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 148 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903251656 KX0123 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903251702-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251702 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251884-1 LF0723 | BLACK | 105D | S2754MAS511B | 297 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251884 LF0723 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903251890-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 144 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251890 LG9665 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903251904-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251904 LG9666 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903251913-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 46215 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512108 | HT SUB PROCESS_V1 | 0903251913 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903251930-1 KG3189 | MAROON | 120D | S2608MR0900A | 1103 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903251930 KG3189 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251931-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 124 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251931 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251968-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 140 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903251968 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903252016-1 IS1413 | BLACK | 60D | S2425M405 | 1810 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252016 IS1413 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252017-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 265 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848024 | HT+PAD SUB PROCESS_V3 | 0903252017 KB5961 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252024-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 158 | 46215 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252024 LG9661 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903252038-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1900 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252038 IU0217 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252073-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 928 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252073 JE0052 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252080-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252080 LG9661 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903252095-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1760 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252095 JD5302 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903252110-1 LF0727 | BLACK | 120D | S2754MAS510B | 116 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252110 LF0727 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903252125-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1028 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903252125 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903252133-1 LG9666 | BLACK | 120D | S2754WAS512C | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252133 LG9666 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903252140-1 JZ7711 | BLACK | 120D | S2608MR0202 | 194 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252140 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903252145-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1020 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252145 JE0055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252505-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848012 | HT+PAD SUB PROCESS_V3 | 0903252505 KB5961 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252541-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252541 KD3854 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903252572-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 272 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903252572 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903252598-1 KG8547 | ONIX | 90D | S2408WR1600 | 118 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903252598 KG8547 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903252991-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 120 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903252991 KY5900 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253066-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 542 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 814006 | PAD+HT SUB PROCESS_V3 | 0903253066 LD0908 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903253138-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 381 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903253138 KY5900 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253152-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 130 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903253152 LH3760 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253168-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 129 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903253168 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253208-1 KD3875 | BLACK | 120D | S2608WR0201 | 108 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903253208 KD3875 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903253313-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 406 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253313 KC5231 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903253357-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 160 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253357 LF0729 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903253378-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 140 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903253378 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903253434-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 600 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903253434 IN0088 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903253436-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 490 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253436 JE6338 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903253467-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253467 LG9663 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903253486-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 186 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903253486 KX3655 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253492-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253492 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253500-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 378 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253500 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253505-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 140 | 46215 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253505 KY9385 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903253511-1 LH3758 | BLACK | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253511 LH3758 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903253522-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 462 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253522 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253561-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 506 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | TRAX (MOQ Issue)-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903253561 LD0909 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903253570-1 IN1157 | WHITE | 90D | S2408MR1600 | 150 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512108 | HT SUB PROCESS_V1 | 0903253570 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903253631-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 226 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Easten, PI Date 25-Aug. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253631 JZ7715 | 46244 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903253640-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 356 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253640 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M FB NOVELTY T WHITE |  | SS27
ADIDAS | 0903253647-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 1 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253647 LK8779 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903253720-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. DRC 0064-T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253720 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253727-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 220 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253727 LE8181 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253750-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 322 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903253750 KX3655 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253760-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 268 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903253760 KX3650 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253781-1 IL7232 | BLACK | 105D | S2408MR3202 | 800 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 826010 | PAD+HT SUB PROCESS_V3 | 0903253781 IL7232 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903253837-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 131 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253837 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253843-1 IN1156 | BLACK | 90D | S2408MR1600 | 150 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512108 | HT SUB PROCESS_V1 | 0903253843 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903253866-1 IN8707 | BLACK | 105D | S2408WR1601A | 150 | 46215 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 512108 | HT SUB PROCESS_V1 | 0903253866 IN8707 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903253892-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 1513 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903253892 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903253913-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 361 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253913 KD3854 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903253950-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 190 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903253950 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253954-1 KB5960 | WHITE | 120D | S2608MR0900A | 230 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903253954 KB5960 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903253973-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 321 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253973 LG9661 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903253978-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903253978 HK7303 |  | KAHATEX CIJERAH | TURKEY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903254007-1 LF0727 | BLACK | 120D | S2754MAS510B | 1051 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254007 LF0727 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254012-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254012 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903254059-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 109 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903254059 KX3655 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903254074-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254074 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254093-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 290 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254093 KY9385 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254128-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 300 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903254128 JE6338 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903254135-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254135 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903254152-1 LF0727 | BLACK | 120D | S2754MAS510B | 227 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254152 LF0727 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254162-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 220 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254162 JW7182 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903254186-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903254186 KD3911 |  | KAHATEX CIJERAH | TURKEY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903254208-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512108 | HT+PAD SUB PROCESS_V3 | 0903254208 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254210-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 200 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903254210 KD3911 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | RELEASED |  | SS27
ADIDAS | 0903254229-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 151 | 15/12/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254229 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903254234-1 KG3189 | MAROON | 120D | S2608MR0900A | 130 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | Request Cancel (BTP_19_07_2026 -> Req. PO Cancel & Quantity Change). 512109 | HT+PAD SUB PROCESS_V3 | 0903254234 KG3189 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254258-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 160 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254258 LI7657 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903254259-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903254259 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254263-1 IN1156 | BLACK | 90D | S2408MR1600 | 118 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254263 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254271-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254271 IS1413 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254283-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 120 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254283 LI7656 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903254284-1 LH3758 | BLACK | 120D | S2754WAS518B | 125 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903254284 LH3758 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903254294-1 IN1173 | WHITE | 90D | S2408WR1600 | 122 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254294 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254297-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254297 IU0217 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254305-1 KD3875 | BLACK | 120D | S2608WR0201 | 745 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903254305 KD3875 | 46244 | KAHATEX CIJERAH | HONGKONG | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903254314-1 IN1172 | BLACK | 90D | S2408WR1600 | 147 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254314 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 120 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903254327-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 123 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254327 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903254339-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 100 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903254339 KZ1286 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903254342-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 160 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254342 LI7655 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903254352-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254352 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254359-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 175 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254359 JE0052 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254392-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254392 JD5302 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903254416-1 IN1173 | WHITE | 90D | S2408WR1600 | 270 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254416 IN1173 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254417-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254417 JE0055 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254447-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 160 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 859013 | PRINT L3 SUB PROCESS_V3 | 0903254447 LI7660 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903254462-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254462 LG9661 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254473-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254473 KX8875 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903254483-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 78 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254483 LH3760 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254496-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 350 | 46033 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | EMBRO SUB PROCESS_V1 | 0903254496 KV0458 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903254500-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 68 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254500 LC6339 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903254523-1 LF0723 | BLACK | 105D | S2754MAS511B | 100 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | (06/08/2026) | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254523 LF0723 | 46244 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903254528-1 LC6341 | BLACK | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254528 LC6341 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903254540-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 1120 | 30/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903254540 LF5052 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903254654-1 LF0718 | BLACK | 105D | S2754MAS512B | 367 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254654 LF0718 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903254668-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 14-Aug, ETD ?? 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254668 JM1772 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903254676-1 IN1156 | BLACK | 90D | S2408MR1600 | 111 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903254676 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254679-1 LF0727 | BLACK | 120D | S2754MAS510B | 557 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254679 LF0727 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254694-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903254694 KB5965 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903254704-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 100 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903254704 LD0908 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903254734-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254734 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903254737-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 159 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254737 KY9385 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254782-1 IN1172 | BLACK | 90D | S2408WR1600 | 915 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254782 IN1172 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254783-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 359 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254783 LG9663 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254813-1 JZ7711 | BLACK | 120D | S2608MR0202 | 169 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254813 JZ7711 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903254815-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 643 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254815 LG9663 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254818-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 242 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903254818 LD0283 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903254834-1 LF0727 | BLACK | 120D | S2754MAS510B | 140 | 15/12/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254834 LF0727 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254837-1 LG9666 | BLACK | 120D | S2754WAS512C | 941 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254837 LG9666 | 46244 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254839-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 116 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903254839 LD0293 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903254841-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 421 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254841 LG9661 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254883-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903254883 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903254897-1 KB5960 | WHITE | 120D | S2608MR0900A | 361 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903254897 KB5960 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903254912-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254912 LF0721 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903254954-1 LG9675 | BLACK | 120D | S2754WAS513C | 137 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254954 LG9675 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903254957-1 LG9666 | BLACK | 120D | S2754WAS512C | 428 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254957 LG9666 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254971-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254971 LG9668 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255002-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 18 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903255002 LG9670 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27-SPOMA
ADIDAS | 0903255006-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 226 | 15/12/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255006 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903255036-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 123 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903255036 KX3650 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255046-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255046 LG9665 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255047-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 1203 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903255047 KG3190 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903255075-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 600 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903255075 KA4914 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903255082-1 LG9666 | BLACK | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255082 LG9666 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255105-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255105 LH3760 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255106-1 IN8707 | BLACK | 105D | S2408WR1601A | 347 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903255106 IN8707 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903255126-1 LH3758 | BLACK | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255126 LH3758 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903255128-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 220 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255128 LG9668 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255132-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255132 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903255138-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255138 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903255194-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 716 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903255194 LD0908 | 46244 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255241-1 KA0246 | BLACK | 105D | S2608WR0902 | 160 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 512106 | PAD+HT SUB PROCESS_V3 | 0903255241 KA0246 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903255271-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 219 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903255271 KA0544 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903255297-1 JZ7711 | BLACK | 120D | S2608MR0202 | 101 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255297 JZ7711 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255324-1 IN1157 | WHITE | 90D | S2408MR1600 | 493 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255324 IN1157 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255351-1 KA4331 | BLACK | 90D | S2608MR0902 | 158 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903255351 KA4331 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255381-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 101 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848016 | HT+PAD SUB PROCESS_V3 | 0903255381 KB5961 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903255416-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 330 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255416 JE6419 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903255444-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 850 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 29-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255444 JM1775 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903255455-1 IN1157 | WHITE | 90D | S2408MR1600 | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903255455 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255472-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 116 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255472 LG9663 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903255484-1 KA4331 | BLACK | 90D | S2608MR0902 | 546 | 46215 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255484 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255493-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 301 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255493 LG9665 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255505-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 2661 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255505 KX3650 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255516-1 KA4331 | BLACK | 90D | S2608MR0902 | 763 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903255516 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255519-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 202 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903255519 KF5311 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903255537-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 943 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255537 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903255538-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255538 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903255541-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 766 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903255541 KY5935 | 27/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255547-1 KA4331 | BLACK | 90D | S2608MR0902 | 4004 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255547 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255551-1 KD3875 | BLACK | 120D | S2608WR0201 | 131 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903255551 KD3875 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903255562-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 4122 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255562 KX3655 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255576-1 KA4331 | BLACK | 90D | S2608MR0902 | 3363 | 46215 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255576 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255600-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 252 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 839062 | PAD+HT SUB PROCESS_V3 | 0903255600 KY5935 | 27/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255606-1 KT4840 | ONIX | 90D | S2408MR1600 | 105 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255606 KT4840 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255609-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 472 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255609 JE6341 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903255612-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 137 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255612 LG9665 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255624-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 800 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 839055 | HT+PAD SUB PROCESS_V3 | 0903255624 KX3655 | 46244 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255629-1 JZ7711 | BLACK | 120D | S2608MR0202 | 139 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255629 JZ7711 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255640-1 LF0727 | BLACK | 120D | S2754MAS510B | 260 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255640 LF0727 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255641-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255641 JW9678 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255645-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 289 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 547012 | HT+PAD SUB PROCESS_V3 | 0903255645 KX3654 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903255672-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 194 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255672 LG9665 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255675-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255675 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903255687-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 848 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903255687 JW9678 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255711-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255711 LF0726 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903255718-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 546 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255718 KY9384 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903255755-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 687 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255755 LG9674 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255780-1 LG9666 | BLACK | 120D | S2754WAS512C | 285 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255780 LG9666 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255825-1 LG9669 | BLACK | 120D | S2754WAS514C | 270 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255825 LG9669 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903255856-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 152 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 848016 | HT+PAD SUB PROCESS_V3 | 0903255856 KB5961 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903255884-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255884 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T BLACK |  | SS27
ADIDAS | 0903255888-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1370 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255888 JZ7711 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255911-1 IN2961 | BLACK | 105D | S2408WR2400 | 1200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255911 IN2961 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903255932-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 212 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903255932 KY5900 | 46244 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255936-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255936 LF0729 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255945-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 568 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903255945 LD0292 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255947-1 LF0727 | BLACK | 120D | S2754MAS510B | 410 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255947 LF0727 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255991-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 100 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (NYK warehouse). 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903255991 LF5052 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903256003-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256003 LG9665 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903256019-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 136 | 46214 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256019 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256028-1 LG9669 | BLACK | 120D | S2754WAS514C | 291 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903256028 LG9669 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903256109-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1043 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256109 KX3654 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903256111-1 IN8707 | BLACK | 105D | S2408WR1601A | 104 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903256111 IN8707 | 46244 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903256140-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 2846 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256140 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256178-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 168 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256178 JZ7715 | 46244 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903256236-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256236 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903256262-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 803 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256262 KB5959 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256285-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 137 | 46215 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903256285 LD0292 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903256378-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 343 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903256378 KB5960 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256533-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 132 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903256533 KB5959 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256569-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 120 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903256569 LD0292 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903256590-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 200 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903256590 IZ0443 |  | KAHATEX CIJERAH | TURKEY | SEA |  | POS TABLE LK |  | SS27
ADIDAS | 0903256615-1 JM1773 | DARK BLUE/WHITE | 90D | F2554MESS712WV | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 1st Art (TC 10 pcs) 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256615 JM1773 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903256636-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 103 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903256636 LD0283 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903256674-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 451 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516421 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903256674 KD0738 | 46244 | KAHATEX CIJERAH | SPAIN | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903256695-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 384 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256695 KY4155 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903256734-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256734 KA6229 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903256808-1 KD3875 | BLACK | 120D | S2608WR0201 | 203 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903256808 KD3875 | 46244 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256830-1 KD3875 | BLACK | 120D | S2608WR0201 | 454 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903256830 KD3875 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256862-1 KD3875 | BLACK | 120D | S2608WR0201 | 603 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903256862 KD3875 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256873-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 113 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256873 KD3854 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256925-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 226 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903256925 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903256933-1 JZ7711 | BLACK | 120D | S2608MR0202 | 686 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256933 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256939-1 JZ7711 | BLACK | 120D | S2608MR0202 | 319 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256939 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256944-1 KT4840 | ONIX | 90D | S2408MR1600 | 149 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903256944 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903256969-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 105 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903256969 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903256981-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 120 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256981 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903256982-1 JZ7711 | BLACK | 120D | S2608MR0202 | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256982 JZ7711 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256990-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 120 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903256990 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903256991-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 250 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903256991 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903257000-1 JZ7711 | BLACK | 120D | S2608MR0202 | 556 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257000 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257005-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 160 | 46215 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 10-Aug, ETD 10-Aug, ETA KH 21-Aug. 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257005 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903257035-1 JZ7711 | BLACK | 120D | S2608MR0202 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257035 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257067-1 JZ7711 | BLACK | 120D | S2608MR0202 | 378 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257067 JZ7711 | 46244 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257069-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 102 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257069 KX3655 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257106-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1785 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257106 JZ7711 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257118-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257118 KY9385 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257136-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257136 LF0729 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903257138-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 318 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257138 KY9384 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903257149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903257149 KX3654 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257153-1 LG9675 | BLACK | 120D | S2754WAS513C | 727 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257153 LG9675 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903257175-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 182 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257175 KY9385 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257206-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 100 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 512108 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903257206 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903257224-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 292 | 46215 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903257224 LD0277 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903257256-1 IK7442 | WHITE | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903257256 IK7442 | 46244 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903257282-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 267 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512102 | HT+PAD SUB PROCESS_V3 | 0903257282 KX3654 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257305-1 KA4331 | BLACK | 90D | S2608MR0902 | 317 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903257305 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257308-1 LF0718 | BLACK | 105D | S2754MAS512B | 111 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257308 LF0718 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903257351-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 145 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257351 LK8779 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903257417-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 452 | 46214 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L1 SUB PROCESS_V3 | 0903257417 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903257458-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 239 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 512106 | HT+PAD SUB PROCESS_V3 | 0903257458 KB5961 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257584-1 LG9666 | BLACK | 120D | S2754WAS512C | 524 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257584 LG9666 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903257609-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 171 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903257609 LH3760 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257661-1 KA4331 | BLACK | 90D | S2608MR0902 | 1151 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257661 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257667-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 219 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257667 LG9674 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257674-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 599 | 46215 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257674 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903257681-1 IN1156 | BLACK | 90D | S2408MR1600 | 581 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903257681 IN1156 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257689-1 KA4331 | BLACK | 90D | S2608MR0902 | 1781 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257689 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257711-1 KA4331 | BLACK | 90D | S2608MR0902 | 451 | 46215 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903257711 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257712-1 IN1173 | WHITE | 90D | S2408WR1600 | 540 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903257712 IN1173 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257721-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 230 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 547012 | HT+PAD SUB PROCESS_V3 | 0903257721 KX3650 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257743-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 109 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257743 KY9383 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903257757-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 244 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903257757 KU7520 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903257770-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 322 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257770 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903257790-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 410 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257790 JE6417 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903257793-1 LE8187 | BLACK | 105D | S2754MAS513 | 397 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257793 LE8187 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257797-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Fu Hsun, PI Date 14-Aug, ETD 01-Aug, ETA-Kaha 26-Aug. 547012 | HT+PAD SUB PROCESS_V3 | 0903257797 KB5961 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257799-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 406 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257799 JE1309 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903257805-1 KZ1322 | KHAKI SIX F26/KHAKI THREE F26 | 120D | S2608MR0202 | 2388 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257805 KZ1322 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M KHAKI SIX F26/KHAKI THREE F26 |  | SS27-TRAX
ADIDAS | 0903257809-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 116 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257809 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903257812-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 600 | 46215 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903257812 KY3737 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903257823-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 266 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903257823 KX3655 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257827-1 HZ0747 | BLACK | 90D | F2325M414 | 1103 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/08/2026) |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO SUB PROCESS_V1 | 0903257827 HZ0747 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | PL TEE |  | SS27
ADIDAS | 0903257842-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 500 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903257842 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257844-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 460 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257844 JM1776 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903257857-1 LF0723 | BLACK | 105D | S2754MAS511B | 1205 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257857 LF0723 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257864-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 329 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257864 LG9661 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903257865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 578 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257865 KX3650 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257872-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 296 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903257872 LC6339 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903257890-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 126 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT SUB PROCESS_V1 | 0903257890 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903257921-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 157 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257921 KX3650 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257925-1 KA4331 | BLACK | 90D | S2608MR0902 | 253 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257925 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257930-1 KA4331 | BLACK | 90D | S2608MR0902 | 460 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257930 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257947-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 417 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903257947 KX9855 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903257949-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 800 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257949 KD4872 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903257955-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 155 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903257955 KZ1286 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903257981-1 IN1156 | BLACK | 90D | S2408MR1600 | 2281 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903257981 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257984-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 473 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903257984 LD0293 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258004-1 IN1173 | WHITE | 90D | S2408WR1600 | 314 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903258004 IN1173 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258033-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 142 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903258033 LG9668 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903258038-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 183 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258038 LF0726 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258065-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 242 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258065 LG9674 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903258100-1 IN1172 | BLACK | 90D | S2408WR1600 | 282 | 46215 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903258100 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258102-1 LH3758 | BLACK | 120D | S2754WAS518B | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPA SUB PROCESS_V3 | 0903258102 LH3758 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258117-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 160 | 15/12/2026 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903258117 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903258123-1 LG9666 | BLACK | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258123 LG9666 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903258129-1 LF0727 | BLACK | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258129 LF0727 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903258144-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 116 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903258144 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258174-1 IL7232 | BLACK | 105D | S2408MR3202 | 684 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 547012 | PAD+HT SUB PROCESS_V3 | 0903258174 IL7232 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903258181-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 290 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258181 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903258192-1 LF0723 | BLACK | 105D | S2754MAS511B | 144 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258192 LF0723 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903258203-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 845 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258203 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258204-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 360 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 547012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258204 KA0544 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903258219-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 5500 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258219 JD1877 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258228-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 115 | 46214 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258228 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258241-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 340 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258241 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258249-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 319 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258249 KR3066 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258259-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 326 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258259 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258280-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 5000 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258280 JE6338 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258290-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 305 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258290 KR3066 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258291-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 711 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258291 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258294-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258294 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903258324-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 115 | 46214 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258324 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258343-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 283 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903258343 KZ1286 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903258404-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 461 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903258404 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258458-1 KT4840 | ONIX | 90D | S2408MR1600 | 887 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903258458 KT4840 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258484-1 KT4840 | ONIX | 90D | S2408MR1600 | 1410 | 46215 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903258484 KT4840 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258496-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 445 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258496 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258509-1 KT4840 | ONIX | 90D | S2408MR1600 | 611 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903258509 KT4840 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258534-1 KG8547 | ONIX | 90D | S2408WR1600 | 418 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 814006 | HT SUB PROCESS_V1 | 0903258534 KG8547 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258567-1 KT4840 | ONIX | 90D | S2408MR1600 | 470 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903258567 KT4840 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258605-1 KG8547 | ONIX | 90D | S2408WR1600 | 428 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 814006 | HT SUB PROCESS_V1 | 0903258605 KG8547 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258628-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 350 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258628 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903258629-1 KG8547 | ONIX | 90D | S2408WR1600 | 303 | 46215 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 800187 | HT SUB PROCESS_V1 | 0903258629 KG8547 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258682-1 LH3758 | BLACK | 120D | S2754WAS518B | 162 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258682 LH3758 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258718-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258718 LE8188 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258746-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258746 LF0729 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903258772-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 102 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258772 LE8181 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258820-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 147 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903258820 KX3655 | 46244 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903258846-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 334 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258846 LG9675 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903258904-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 261 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903258904 LD0293 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258907-1 KB5965 | BLACK | 120D | S2608MR0900A | 789 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258907 KB5965 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903258933-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 556 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258933 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903258954-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 420 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258954 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903259058-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259058 JD1877 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903259086-1 HZ0747 | BLACK | 90D | F2325M414 | 800 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903259086 HZ0747 |  | KAHATEX CIJERAH | TURKEY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903259111-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259111 JE1309 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903259135-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 826010 | PRINT L3 SUB PROCESS_V3 | 0903259135 IS1413 |  | KAHATEX CIJERAH | TURKEY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903259160-1 IN1157 | WHITE | 90D | S2408MR1600 | 483 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259160 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259172-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 164 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259172 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903259177-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 437 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259177 KY9383 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259204-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 730 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259204 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259211-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259211 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259212-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 316 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259212 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259232-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 380 | 46214 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259232 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903259252-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 529 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259252 KY9383 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259268-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 405 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259268 KR3066 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903259305-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259305 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259338-1 LG9666 | BLACK | 120D | S2754WAS512C | 320 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259338 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903259343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 313 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259343 KY9384 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259378-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259378 KY9385 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903259404-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 315 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259404 LF0726 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903259471-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903259471 KX9851 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903259524-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 125 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259524 KY9384 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259595-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 510 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903259595 LG9675 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903259751-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 204 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903259751 KA0546 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903259789-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903259789 IN1172 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259835-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 249 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903259835 LC6339 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903259864-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 822 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 806020 | HT+PAD SUB PROCESS_V3 | 0903259864 KX3655 | 46244 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259893-1 IN1157 | WHITE | 90D | S2408MR1600 | 138 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903259893 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903260147-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260147 LG9665 | 46244 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903260149-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 160 | 15/12/2026 |  | SI | SI10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | (06/08/2026) | 859013 | PRINT L1 SUB PROCESS_V3 | 0903260149 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903260166-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260166 LF0729 | 46244 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260179-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 252 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260179 LG9675 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903260184-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 160 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903260184 LI7659 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903260320-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260320 LG9661 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903260341-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 452 | 46214 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903260341 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260374-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 139 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903260374 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903260383-1 LG9669 | BLACK | 120D | S2754WAS514C | 252 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260383 LG9669 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260461-1 LF0727 | BLACK | 120D | S2754MAS510B | 114 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260461 LF0727 | 46244 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260513-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 1062 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903260513 JZ7715 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903260544-1 LF0727 | BLACK | 120D | S2754MAS510B | 380 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260544 LF0727 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260564-1 LG9669 | BLACK | 120D | S2754WAS514C | 231 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903260564 LG9669 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260662-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 510 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825057 | PRINT L3 SUB PROCESS_V3 | 0903260662 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260775-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 631 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825056 | PRINT L3 SUB PROCESS_V3 | 0903260775 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260885-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 113 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903260885 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903260989-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 600 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903260989 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903261075-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 355 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | (China). (China). (China). 825057 | PRINT L1 SUB PROCESS_V3 | 0903261075 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903261159-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1000 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261159 JE6414 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903261181-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 300 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261181 JW7182 |  | KAHATEX CIJERAH | TURKEY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903261204-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1609 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261204 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903261255-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1232 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261255 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903261283-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1152 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903261283 KD3911 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | RELEASED |  | SS27
ADIDAS | 0903261414-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261414 LD0293 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903261449-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 298 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261449 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903261505-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 268 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261505 JE0055 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903261530-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 800 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | T2 Gistex, material quality issues (creasemark), PI Date 09-Aug, actual receives 14-Aug (100% QC panel). 826010 | HT SUB PROCESS_V1 | 0903261530 IL4127 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903261559-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1040 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261559 JD5302 |  | KAHATEX CIJERAH | TURKEY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903261581-1 LF0723 | BLACK | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903261581 LF0723 | 46244 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903261610-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 550 | 46214 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903261610 JD1877 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903262124-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 1676 | 46214 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262124 LF0718 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903262659-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 100 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903262659 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903262680-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 550 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903262680 KX3655 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262708-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1006 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug. Waiting fabric. T2 Far Easten, PI Date 25-Aug. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262708 JZ7711 | 46244 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903262726-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 410 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 980004 | HT SUB PROCESS_V1 | 0903262726 IT1469 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903262735-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 309 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | (05/08/2026) | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903262735 KZ1286 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903262802-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 120 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903262802 KX3655 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262938-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 369 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262938 LF0726 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262975-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 1568 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262975 LG9665 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263005-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 410 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263005 LG9661 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903263040-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C-MTF | 1621 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263040 LG9674 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263070-1 LG9669 | BLACK | 120D | S2754WAS514C | 441 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263070 LG9669 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903263086-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1346 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263086 LG9675 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903263117-1 JZ7711 | BLACK | 120D | S2608MR0202 | 2362 | 15/11/2026 | 2362 | SA | SA10/07/2026 | G3E | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. DRC 0010-T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263117 JZ7711 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA | 46183 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 46183 | 46305 |  |  | 2362 |  | 2362 |  |  | 46063 | 46213 |  |  | 2362 |  | 2362 |  |  | 29/09/2026 | 46091 |  |  | 2362 |  | 2362
ADIDAS | 0903263138-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 529 | 15/11/2026 | 529 | SA | SA10/07/2026 | G3E | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. DRC 0010-T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263138 JZ7715 | 46244 | KAHATEX CIJERAH | BRAZIL | SEA | 46152 | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX | 46152 | 46183 |  |  | 529 |  | 529 |  |  | 46032 | 46063 |  |  | 529 |  | 529 |  |  | 28/09/2026 | 29/09/2026 |  |  | 529 |  | 529
ADIDAS | 0903263306-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 430 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 512106 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903263306 KY5988 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903263390-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263390 LF0729 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263420-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 198 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263420 LF0721 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263452-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 130 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903263452 KX9838 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903263473-1 KB5960 | WHITE | 120D | S2608MR0900A | 260 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903263473 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903263497-1 IN1157 | WHITE | 90D | S2408MR1600 | 193 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263497 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903263651-1 IS1413 | BLACK | 60D | S2425M405 | 376 | 46214 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3 SUB PROCESS_V3 | 0903263651 IS1413 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903263677-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 574 | 46214 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263677 JE6414 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903263715-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 500 | 46214 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263715 JE0052 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903263748-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 530 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263748 JD5302 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903263778-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 204 | 46214 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903263778 KA5089 | 26/08/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903263840-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1055 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263840 KY9384 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903263913-1 LH3758 | BLACK | 120D | S2754WAS518B | 246 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903263913 LH3758 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903263936-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 160 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903263936 JW9678 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903264012-1 LG9666 | BLACK | 120D | S2754WAS512C | 135 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264012 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903264121-1 LG9669 | BLACK | 120D | S2754WAS514C | 1 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903264121 LG9669 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903264660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 1032 | 46214 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264660 LE8181 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903264697-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 419 | 46214 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264697 LF0721 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903264733-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 351 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264733 LE8188 | 46244 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903266169-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 226 | 46214 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L1 SUB PROCESS_V3 | 0903266169 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903266211-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 150 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903266211 KX9838 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903266275-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266275 LG9666 | 46244 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903266343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 172 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903266343 KY9384 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903266484-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 28 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903266484 KZ1286 | 46244 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903266504-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903266504 KX3650 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903266573-1 LH3758 | BLACK | 120D | S2754WAS518B | 283 | 46215 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903266573 LH3758 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903266636-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 164 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903266636 LD0292 | 46244 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903269380-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 352 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903269380 KZ1286 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903269421-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903269421 KR3066 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903269458-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 272 | 46215 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903269458 KZ1286 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903269653-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 748 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903269653 LG9668 | 46244 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903269724-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 62 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903269724 LC6339 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903270268-1 LF0728 | LIGHT CINNAMON S27 | 120D | S2754MAS510B | 128 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270268 LF0728 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903270294-1 LG9662 | LIGHT CINNAMON S27 | 120D | S2754WAS512C | 95 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270294 LG9662 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903271870-1 KY5870 | GREY | 90D | S2750MTR052 | 136 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271870 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271911-1 KY5870 | GREY | 90D | S2750MTR052 | 368 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271911 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271953-1 KY5870 | GREY | 90D | S2750MTR052 | 110 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 838103 | HT SUB PROCESS_V1 | 0903271953 KY5870 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271991-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1139 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903271991 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903272018-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 261 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272018 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903272076-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 464 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272076 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903272106-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1252 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272106 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903273766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 545 | 46214 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903273766 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903276188-1 KY5870 | GREY | 90D | S2750MTR052 | 135 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 800187 | HT SUB PROCESS_V1 | 0903276188 KY5870 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903293851-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 387 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903293851 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX
ADIDAS | 0903293875-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 1667 | 46215 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903293875 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX
ADIDAS | 0903305161-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903305161 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903306650-1 KA6229 | BLACK | 120D | S2608WR0202 | 388 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306650 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903306651-1 KA6229 | BLACK | 120D | S2608WR0202 | 222 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306651 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903316926-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 338 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316926 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903316927-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 201 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316927 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903316931-1 KT4839 | ONIX | 90D | S2408MR1601 | 127 | 46215 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903316931 KT4839 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903316933-1 KT4839 | ONIX | 90D | S2408MR1601 | 680 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903316933 KT4839 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903322462-1 IN8707 | BLACK | 105D | S2408WR1601A | 170 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug. 516471 | HT SUB PROCESS_V1 | 0903322462 IN8707 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322463-1 IN1173 | WHITE | 90D | S2408WR1600 | 215 | 15/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322463 IN1173 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322464-1 IN1173 | WHITE | 90D | S2408WR1600 | 303 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322464 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322466-1 IN1173 | WHITE | 90D | S2408WR1600 | 318 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322466 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322471-1 IN1172 | BLACK | 90D | S2408WR1600 | 336 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322471 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322473-1 IN8707 | BLACK | 105D | S2408WR1601A | 339 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516471 | HT SUB PROCESS_V1 | 0903322473 IN8707 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322475-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 154 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516471 | HT SUB PROCESS_V1 | 0903322475 IN1159 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322481-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 339 | 23/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322481 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322483-1 IN1172 | BLACK | 90D | S2408WR1600 | 335 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322483 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322485-1 IN1172 | BLACK | 90D | S2408WR1600 | 299 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322485 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322487-1 IN1172 | BLACK | 90D | S2408WR1600 | 315 | 46215 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322487 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322489-1 IN1159 | BLACK | 90D | S2408MR1601 | 1049 | 15/12/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (01/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT SUB PROCESS_V1 | 0903322489 IN1159 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322494-1 IN1156 | BLACK | 105D | S2408MR1600 | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516471 | HT SUB PROCESS_V1 | 0903322494 IN1156 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322495-1 IN1159 | BLACK | 90D | S2408MR1601 | 257 | 46215 |  | SA | SA26/06/2026 |  | SHORTS |  | (01/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT SUB PROCESS_V1 | 0903322495 IN1159 | 46304 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903324319-1 KT4839 | ONIX | 90D | S2408MR1601 | 320 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 960026 | HT SUB PROCESS_V1 | 0903324319 KT4839 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903346575-1 LC9619 | AURORA IVY F25 | 90D | S2725M920 | 104 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903346575 LC9619 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN AURORA IVY F25 |  | SS27-STX
ADIDAS | 0903348672-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 432 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903348672 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903348762-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 408 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903348762 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903348798-1 KY0907 | SILVER BLUE TINT S27 | 90D | F2625M101 | 313 | 46215 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348798 KY0907 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE SILVER BLUE TINT S27 |  | SS27-L2L
ADIDAS | 0903349016-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 517 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903349016 KA0237 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903349056-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349056 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903349066-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349066 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903350019-1 IN8707 | BLACK | 105D | S2408WR1601A | 1168 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 600000 | HT SUB PROCESS_V1 | 0903350019 IN8707 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903350099-1 IN1172 | BLACK | 105D | S2408WR1600 | 481 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903350099 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903351164-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903351164 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903351248-1 KY0907 | SILVER BLUE TINT S27 | 90D | F2625M101 | 201 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903351248 KY0907 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE SILVER BLUE TINT S27 |  | SS27-L2L
ADIDAS | 0903351281-1 LC9619 | AURORA IVY F25 | 90D | S2725M920 | 221 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903351281 LC9619 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN AURORA IVY F25 |  | SS27-STX
ADIDAS | 0903351318-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 530 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903351318 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903351402-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 320 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903351402 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903351428-1 LH2842 | BLACK | 90D | S2725M993 | 551 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903351428 LH2842 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903351478-1 LH2841 | OFF WHITE | 90D | S2725M993 | 519 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903351478 LH2841 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903351554-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 172 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903351554 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903352148-1 IN1172 | BLACK | 105D | S2408WR1600 | 406 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352148 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352206-1 IN1173 | WHITE | 105D | S2408WR1600 | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352206 IN1173 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352294-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 405 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903352294 LD0292 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903353668-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 424 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903353668 KU3269 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903353747-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 558 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353747 KD7980 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903353928-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 442 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903353928 KU3272 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903354015-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 100 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354015 KS4777 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903354045-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 268 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354045 KD3676 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903354086-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 641 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354086 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903354132-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 211 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903354132 KU3269 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356178-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903356178 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903356305-1 IP2310 | BLACK | 105D | S2450MTR701 | 528 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903356305 IP2310 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903356398-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903356398 JW9678 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903356461-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903356461 KB5966 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903356572-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356572 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903356614-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 126 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356614 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903357612-1 KZ4392 | WHITE | 120D | F2608WR1500 | 1209 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903357612 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903357878-1 KA4331 | BLACK | 90D | S2608MR0902 | 824 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357878 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357917-1 KA4331 | BLACK | 90D | S2608MR0902 | 1177 | 23/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357917 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357951-1 KB5960 | WHITE | 120D | S2608MR0900A | 638 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357951 KB5960 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903357990-1 KB5965 | BLACK | 120D | S2608MR0900A | 451 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357990 KB5965 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358022-1 KB5965 | BLACK | 120D | S2608MR0900A | 347 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903358022 KB5965 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358074-1 KA0246 | BLACK | 105D | S2608WR0902 | 308 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903358074 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358100-1 KA0246 | BLACK | 105D | S2608WR0902 | 434 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903358100 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358135-1 KA0246 | BLACK | 105D | S2608WR0902 | 1865 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903358135 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358700-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 121 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358700 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903358753-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 116 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358753 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903358802-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903358802 KS1493 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903358865-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358865 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903358895-1 IS1413 | BLACK | 60D | S2425M405 | 600 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903358895 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903358997-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 185 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903358997 KU3272 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903359060-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903359060 HB7454 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903359114-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 207 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903359114 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903359674-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903359674-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903359721-1 KZ4389 | WHITE | 120D | F2608MR1500 | 1210 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903359721 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903359778-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359778 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359846-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 938 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359846 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359888-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 547 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359888 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359954-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 486 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359954 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360018-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 318 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360018 KR3066 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360061-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360061 KR3066 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360101-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 112 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 516342 | PRINT L2+HT SUB PROCESS_V3 | 0903360101 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903360129-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 116 | 46215 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 516342 | PRINT L2+HT SUB PROCESS_V3 | 0903360129 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903360666-1 KA0246 | BLACK | 105D | S2608WR0902 | 351 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903360666 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360696-1 KA0246 | BLACK | 105D | S2608WR0902 | 843 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360696 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360725-1 KA0246 | BLACK | 105D | S2608WR0902 | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360725 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360753-1 KA0246 | BLACK | 105D | S2608WR0902 | 360 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903360753 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360794-1 KA0246 | BLACK | 105D | S2608WR0902 | 388 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903360794 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360822-1 KA0246 | BLACK | 105D | S2608WR0902 | 497 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360822 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360848-1 KA0246 | BLACK | 105D | S2608WR0902 | 1003 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903360848 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360897-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 167 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903360897 LE8186 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903360991-1 LE8187 | BLACK | 105D | S2754MAS513 | 501 | 46215 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903360991 LE8187 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361050-1 LE8187 | BLACK | 105D | S2754MAS513 | 383 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361050 LE8187 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361088-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 228 | 46215 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361088 LE8186 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903361129-1 LE8187 | BLACK | 105D | S2754MAS513 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361129 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361503-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 962 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361503 KF5311 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903361592-1 KB5960 | WHITE | 120D | S2608MR0900A | 1902 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361592 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903361661-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361661 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903361766-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 121 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361766 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903361804-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 251 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903361804 IW8374 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903361971-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 1446 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361971 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903362173-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 331 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903362173 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903362231-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 300 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903362231 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903362282-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 606 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903362282 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903363183-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363183 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363246-1 JZ7709 | BLACK | 120D | S2608MR0201 | 2318 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363246 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363301-1 JZ7709 | BLACK | 120D | S2608MR0201 | 340 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363301 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363352-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5618 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363352 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363437-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1124 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363437 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363513-1 JZ7709 | BLACK | 120D | S2608MR0201 | 302 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363513 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363559-1 JZ7709 | BLACK | 120D | S2608MR0201 | 363 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363559 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363609-1 JZ7709 | BLACK | 120D | S2608MR0201 | 383 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363609 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363740-1 KB5965 | BLACK | 120D | S2608MR0900A | 1741 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363740 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903363791-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 594 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363791 KX3655 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903363855-1 KA0235 | BLACK | 105D | S2608WR0901 | 320 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903363855 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903363897-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 641 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903363897 LG9670 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903363970-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 907 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903363970 KY6616 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903364196-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 150 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364196 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364257-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 190 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364257 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903364361-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 838103 | PRINT L1 SUB PROCESS_V3 | 0903364361 KC8559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903364462-1 IK7442 | WHITE | 105D | S2408WR2400 | 105 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903364462 IK7442 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903364491-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 127 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364491 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903364570-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903364570 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903364588-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364588 KU3270 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364991-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903364991 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903365054-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 112 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903365054 JW9678 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903365087-1 IN2961 | BLACK | 105D | S2408WR2400 | 100 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903365087 IN2961 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903365207-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903365207 KA0237 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903365256-1 IP2310 | BLACK | 105D | S2450MTR701 | 500 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903365256 IP2310 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903365665-1 JZ7709 | BLACK | 120D | S2608MR0201 | 456 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365665 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903365788-1 JZ7709 | BLACK | 120D | S2608MR0201 | 446 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365788 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903365824-1 JZ7709 | BLACK | 120D | S2608MR0201 | 308 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365824 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903366512-1 KX8877 | WHITE | 90D | S27GMGFX100 | 246 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903366512 KX8877 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903366592-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 5 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903366592 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903366641-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 110 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903366641 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903366658-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 678 | 46214 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903366658 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903366697-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 101 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366697 KU3272 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366738-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 115 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366738 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366756-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 140 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903366756 KB0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366796-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 106 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366796 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366838-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 376 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366838 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903366871-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 408 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366871 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366911-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 142 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366911 KU3270 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366950-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 308 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366950 KD3684 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903366982-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366982 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903367017-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 221 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903367017 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903367098-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 416 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 830009 | PAD+HT SUB PROCESS_V3 | 0903367098 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903367130-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 101 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 830009 | PAD+HT SUB PROCESS_V3 | 0903367130 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903367252-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903367252 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903367284-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 339 | 46245 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | EMBRO SUB PROCESS_V1 | 0903367284 KD7980 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903367372-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 417 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903367372 IT3474 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903367407-1 IK7442 | WHITE | 105D | S2408WR2400 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903367407 IK7442 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903367462-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903367462 IW8374 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903367498-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367498 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903367624-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 1464 | 46245 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | EMBRO SUB PROCESS_V1 | 0903367624 KD3683 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903368689-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 150 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903368689 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903368737-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 2776 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368737 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368757-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903368757 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368774-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 367 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 672027 | HT SUB PROCESS_V1 | 0903368774 IN1159 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903368797-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 512108 | PAD+HT SUB PROCESS_V3 | 0903368797 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368816-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 1661 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368816 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368842-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 1006 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903368842 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903368857-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 2061 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368857 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368875-1 KZ4392 | WHITE | 120D | F2608WR1500 | 146 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903368875 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368890-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 838 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368890 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368903-1 KZ4392 | WHITE | 120D | F2608WR1500 | 126 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903368903 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368930-1 IN8707 | BLACK | 105D | S2408WR1601A | 617 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT SUB PROCESS_V1 | 0903368930 IN8707 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903368937-1 KZ4392 | WHITE | 120D | F2608WR1500 | 125 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 512106 | PAD+HT SUB PROCESS_V3 | 0903368937 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368963-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 323 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368963 IT1469 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903369000-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 364 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903369000 KY9431 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903369200-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 104 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903369200 KD3684 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903369262-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 224 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903369262 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903369687-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 123 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903369687 JW7182 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903369776-1 IK7442 | WHITE | 105D | S2408WR2400 | 238 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903369776 IK7442 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903369794-1 IS1413 | BLACK | 60D | S2425M405 | 164 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903369794 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903369828-1 IN2961 | BLACK | 105D | S2408WR2400 | 109 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369828 IN2961 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903369857-1 IK7442 | WHITE | 105D | S2408WR2400 | 132 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369857 IK7442 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903369902-1 KE9870 | BLACK | 105D | S2650MTR809B | 300 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 800187 | PRINT L1 SUB PROCESS_V3 | 0903369902 KE9870 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903369942-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 300 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903369942 HB7454 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903369980-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 279 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903369980 KD3676 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903370027-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 497 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 800187 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903370027 JD9944 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903370711-1 KA0235 | BLACK | 105D | S2608WR0901 | 327 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903370711 KA0235 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370756-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903370756 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370854-1 LF0718 | BLACK | 105D | S2754MAS512B | 547 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370854 LF0718 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903370911-1 LF0727 | BLACK | 120D | S2754MAS510B | 440 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370911 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903370963-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 196 | 46215 |  | AN | AN31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370963 LF0726 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903371108-1 LF0727 | BLACK | 120D | S2754MAS510B | 126 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903371108 LF0727 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903371738-1 IN1172 | BLACK | 105D | S2408WR1600 | 2072 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903371738 IN1172 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371825-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 42 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903371825 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903371852-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric (Mexico). T2 Y.T.I, PI Date 10-Jul, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903371852 IT1469 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371889-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 523 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT SUB PROCESS_V1 | 0903371889 KG8553 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903371934-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1088 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903371934 IN1156 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371971-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903371971 KC8152 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903372069-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 546 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep.ity LLT from FAR EASTERN (VNM), ETD: 12-Oct (DOL 30D). 652001 | HT SUB PROCESS_V1 | 0903372069 IN1157 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903372107-1 KA0246 | BLACK | 105D | S2608WR0902 | 460 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (Mexico). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903372107 KA0246 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903372148-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 100 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903372148 KC9016 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903372170-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 239 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903372170 IW8374 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903372265-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 192 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903372265 HB7454 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903372668-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO SUB PROCESS_V1 | 0903372668 JD1881 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372707-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3168 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372707 JE6414 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372751-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2064 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO SUB PROCESS_V1 | 0903372751 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372792-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 1300 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372792 JD5308 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372825-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1328 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903372825 JF3604 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372860-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372860 JD5308 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372905-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 240 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | PRINT L1 SUB PROCESS_V3 | 0903372905 JF3604 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372940-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 3000 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372940 LE7510 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903372958-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 101 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372958 JE6414 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372979-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 128 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903372979 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373000-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 3600 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903373000 LE5391 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27
ADIDAS | 0903373023-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 228 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373023 IN1156 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373054-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 2400 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373054 LE7508 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903373065-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 193 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903373065 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373102-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373102 IN1157 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373109-1 KS7769 | WHITE/BLACK | 90D | S26AAWVL320 | 6000 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903373109 KS7769 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WHITE/BLACK |  | SS27
ADIDAS | 0903373416-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 1200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 826010 | EMBRO SUB PROCESS_V1 | 0903373416 KD3936 |  | KAHATEX CIJERAH | TURKEY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903373455-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903373455 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903373496-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 115 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903373496 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903373718-1 LF0727 | BLACK | 120D | S2754MAS510B | 377 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373718 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903373765-1 LF0718 | BLACK | 105D | S2754MAS512B | 326 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373765 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903374698-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374698 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903374782-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374782 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903374787-1 KA0246 | BLACK | 105D | S2608WR0902 | 617 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516400 | PAD+HT SUB PROCESS_V3 | 0903374787 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374792-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903374792 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903374832-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 684009 | HT+PAD SUB PROCESS_V3 | 0903374832 KB5965 |  | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903374862-1 IN8707 | BLACK | 105D | S2408WR1601A | 301 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT SUB PROCESS_V1 | 0903374862 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374867-1 KA0246 | BLACK | 105D | S2608WR0902 | 346 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516199 | PAD+HT SUB PROCESS_V3 | 0903374867 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374899-1 KA0246 | BLACK | 105D | S2608WR0902 | 451 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516400 | PAD+HT SUB PROCESS_V3 | 0903374899 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374900-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1505 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903374900 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374933-1 KG8547 | ONIX | 105D | S2408WR1600 | 442 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903374933 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374934-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 197 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 848012 | HT SUB PROCESS_V1 | 0903374934 IN1159 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374938-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 202 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374938 LI2667 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903374939-1 JZ7709 | BLACK | 120D | S2608MR0201 | 519 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374939 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903374951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 637 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903374951 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903374962-1 IN8707 | BLACK | 105D | S2408WR1601A | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT SUB PROCESS_V1 | 0903374962 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374969-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1297 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903374969 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903374996-1 KA4331 | BLACK | 90D | S2608MR0902 | 321 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903374996 KA4331 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903375008-1 KA0235 | BLACK | 105D | S2608WR0901 | 312 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903375008 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903375019-1 IL7232 | BLACK | 105D | S2408MR3202 | 1837 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903375019 IL7232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903375027-1 KT4839 | ONIX | 90D | S2408MR1601 | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 684009 | HT SUB PROCESS_V1 | 0903375027 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903375053-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 687 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903375053 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903375063-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516299 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375063 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375096-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 556 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903375096 KA2571 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903375109-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375109 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375126-1 KA0246 | BLACK | 105D | S2608WR0902 | 376 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903375126 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903375499-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 146 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375499 LG9661 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375528-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 226 | 46215 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375528 LI2645 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903375564-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 198 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375564 LI2647 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903375575-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 181 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848024 | HT SUB PROCESS_V1 | 0903375575 IN1157 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903375595-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 136 | 46215 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375595 LI2668 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903375623-1 LF0723 | BLACK | 105D | S2754MAS511B | 126 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375623 LF0723 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903375626-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 130 | 46215 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375626 LI2646 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903375662-1 KS7769 | WHITE/BLACK | 90D | S26AAWVL320 | 6000 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903375662 KS7769 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WHITE/BLACK |  | SS27
ADIDAS | 0903375688-1 KA0235 | BLACK | 105D | S2608WR0901 | 140 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep.848012 | PAD+HT SUB PROCESS_V3 | 0903375688 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903375714-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1800 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903375714 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903375724-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 111 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903375724 LE0357 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903376486-1 LE8187 | BLACK | 105D | S2754MAS513 | 358 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903376486 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903377133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 412 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377133 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377157-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 414 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT SUB PROCESS_V1 | 0903377157 KU7520 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903377184-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377184 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377185-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 332 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 684009 | HT+PAD SUB PROCESS_V3 | 0903377185 KB5961 |  | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903377216-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 552 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377216 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377256-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 555 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377256 KD0738 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377300-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 401 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377300 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377314-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377314 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903377338-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377338 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377349-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 645 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903377349 KX9855 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903377350-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 488 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric (Mexico). T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903377350 IN1173 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377377-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 383 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377377 KA6260 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903377379-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 330 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 684009 | PAD+HT SUB PROCESS_V3 | 0903377379 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903377398-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 756 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377398 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377403-1 KA4331 | BLACK | 90D | S2608MR0902 | 740 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903377403 KA4331 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903377412-1 IN1157 | WHITE | 105D | S2408MR1600 | 1894 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377412 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377437-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 729 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377437 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377443-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 975 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903377443 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377446-1 KG8547 | ONIX | 105D | S2408WR1600 | 569 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903377446 KG8547 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377470-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1907 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903377470 KX3654 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903377476-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377476 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377486-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 2013 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377486 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377504-1 IN8707 | BLACK | 105D | S2408WR1601A | 373 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT SUB PROCESS_V1 | 0903377504 IN8707 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903377510-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377510 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377530-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 463 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377530 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377545-1 IN1173 | WHITE | 105D | S2408WR1600 | 5142 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377545 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377583-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 381 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 650010 | HT SUB PROCESS_V1 | 0903377583 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903377598-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 540 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377598 KD0738 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 773 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377600 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377618-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377618 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377633-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1048 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377633 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377643-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903377643 LE0357 | 29/10/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903377670-1 LF0723 | BLACK | 105D | S2754MAS511B | 192 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377670 LF0723 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903377679-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377679 LG9661 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377730-1 LF0723 | BLACK | 105D | S2754MAS511B | 624 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377730 LF0723 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903377777-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | PRINT L1+PAD SUB PROCESS_V3 | 0903377777 LE7647 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903377805-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 103 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903377805 KG8548 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377842-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 194 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903377842 KT4840 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377883-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 148 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377883 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377939-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 120 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903377939 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903377983-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377983 LD6542 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903378020-1 LG9666 | BLACK | 120D | S2754WAS512C | 299 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903378020 LG9666 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903378068-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 680 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378068 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903378096-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 209 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903378096 KB5961 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903378136-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 214 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378136 KA6260 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903378176-1 IP2310 | BLACK | 105D | S2450MTR701 | 4001 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 New Wide, PI Date ?? 516318 | HT SUB PROCESS_V1 | 0903378176 IP2310 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903378295-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903378295 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903378391-1 KT4840 | ONIX | 105D | S2408MR1600 | 148 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903378391 KT4840 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903378422-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 814006 | EMBRO SUB PROCESS_V1 | 0903378422 KD3683 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903378918-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 477 | 46215 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378918 LI2646 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903379162-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 566 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379162 KY9384 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903379219-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379219 KY9384 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903379258-1 JZ7711 | BLACK | 120D | S2608MR0202 | 7018 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379258 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379288-1 JZ7711 | BLACK | 120D | S2608MR0202 | 522 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379288 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379297-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 392 | 46214 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379297 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379368-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 280 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379368 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903379458-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379458 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379480-1 JZ7711 | BLACK | 120D | S2608MR0202 | 369 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379480 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379504-1 JZ7711 | BLACK | 120D | S2608MR0202 | 362 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379504 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379537-1 JZ7711 | BLACK | 120D | S2608MR0202 | 697 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379537 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379565-1 JZ7711 | BLACK | 120D | S2608MR0202 | 4347 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379565 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379589-1 JZ7711 | BLACK | 120D | S2608MR0202 | 562 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379589 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379620-1 KD3875 | BLACK | 120D | S2608WR0201 | 302 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903379620 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903379629-1 JZ7711 | BLACK | 120D | S2608MR0202 | 227 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379629 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379646-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 470 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379646 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379658-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 1801 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 652001 | HT SUB PROCESS_V1 | 0903379658 IN1159 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903379677-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 362 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379677 IT1469 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379694-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903379694 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903379699-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 7027 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379699 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379708-1 IN8707 | BLACK | 105D | S2408WR1601A | 461 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT SUB PROCESS_V1 | 0903379708 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903379735-1 KT4840 | ONIX | 105D | S2408MR1600 | 674 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 10-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379735 KT4840 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379774-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 1960 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379774 KB5961 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379788-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | PRINT L1+PAD SUB PROCESS_V3 | 0903379788 LE7650 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903379814-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 1260 | 15/12/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379814 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379820-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 304 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379820 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379841-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 548 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379841 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379843-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379843 KB5965 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379876-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379876 KX9855 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903379894-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 398 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379894 LD6542 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903379909-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 401 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379909 KG8548 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379942-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT SUB PROCESS_V1 | 0903379942 KT4839 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903379978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 108 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903379978 LD5446 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903379979-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 1361 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT SUB PROCESS_V1 | 0903379979 KU7520 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380015-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 1104 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903380015 LD0907 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380044-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903380044 LD0278 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903380117-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903380117 KX9838 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903380177-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 169 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903380177 KB5965 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380349-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 501 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903380349 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903380351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 200 | 46215 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380351 LI2669 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903380384-1 KB5960 | WHITE | 120D | S2608MR0900A | 952 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380384 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380417-1 KB5965 | BLACK | 120D | S2608MR0900A | 897 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380417 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380454-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 154 | 23/11/2026 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380454 LI2645 |  | KAHATEX CIJERAH | ITALY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380455-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 398 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380455 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903380474-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 421 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903380474 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380477-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 228 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380477 LI2646 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903380604-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 341 | 46215 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380604 LI2667 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903380647-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 211 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380647 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380663-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 665 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380663 LI2645 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380739-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903380739-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903380774-1 LH2842 | BLACK | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380774 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903380833-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 828 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903380833 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903380843-1 KG3189 | MAROON | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903380843 KG3189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903380864-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 950 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380864 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380881-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 485 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380881 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380897-1 IC5188 | BLACK | 90D | S23080640 | 226 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380897 IC5188 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380911-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380911 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903380935-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 185 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903380935 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903380960-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 196 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380960 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380966-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 407 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380966 KG3190 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903380971-1 KU8358 | WHITE | 105D | S2750MTR051 | 174 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 05-Sep. 830009 | HT SUB PROCESS_V1 | 0903380971 KU8358 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T ESS T WHITE |  | SS27-TI
ADIDAS | 0903381006-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903381006 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903381023-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1724 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381023 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381034-1 LH2841 | OFF WHITE | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381034 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903381091-1 JC5699 | WONDER ALUMINA S25/WHITE | 90D | S2554WES503FT | 123 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381091 JC5699 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903381100-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 104 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381100 LI2645 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381106-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 20/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903381106 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381119-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 121 | 46215 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903381119 LH4744 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381127-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 156 | 46215 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381127 LI2672 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381143-1 LH2842 | BLACK | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381143 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903381653-1 KD3875 | BLACK | 120D | S2608WR0201 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903381653 KD3875 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381658-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1339 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381658 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381700-1 KD3875 | BLACK | 120D | S2608WR0201 | 982 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903381700 KD3875 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381730-1 JZ7711 | BLACK | 120D | S2608MR0202 | 403 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381730 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381750-1 KD3875 | BLACK | 120D | S2608WR0201 | 315 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903381750 KD3875 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381764-1 JZ7711 | BLACK | 120D | S2608MR0202 | 859 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381764 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381802-1 KD3875 | BLACK | 120D | S2608WR0201 | 2262 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903381802 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381812-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 633 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381812 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381817-1 KX8877 | WHITE | 90D | S27GMGFX100 | 337 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903381817 KX8877 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381829-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381829 KV7963 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903381859-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 318 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381859 KA6260 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381892-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903381892 KX8877 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381895-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1315 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903381895 KX3655 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903381903-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 344 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903381903 KY9391 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903381904-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 304 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381904 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381912-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381912 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903381925-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 817 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903381925 KX3653 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903381934-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 335 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903381934 KY9393 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903381939-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 627 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381939 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381949-1 IN1156 | BLACK | 105D | S2408MR1600 | 434 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381949 IN1156 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381966-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 423 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903381966 KY9391 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903381982-1 IN1157 | WHITE | 105D | S2408MR1600 | 1157 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381982 IN1157 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381985-1 LF0718 | BLACK | 105D | S2754MAS512B | 328 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516438 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903381985 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903382018-1 IN1172 | BLACK | 105D | S2408WR1600 | 512 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382018 IN1172 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382031-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 261 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903382031 KY9431 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382039-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382039 LD5446 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903382050-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903382050 KX3655 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382067-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 549 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903382067 KY9393 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903382087-1 IN1173 | WHITE | 105D | S2408WR1600 | 1019 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382087 IN1173 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382094-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 135 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903382094 KY9431 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382097-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903382097 KY9431 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382119-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 359 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382119 KX9855 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903382147-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 1601 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382147 KX3653 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903382178-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382178 KX3655 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382200-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 693 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT SUB PROCESS_V1 | 0903382200 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903382246-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 652 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903382246 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903382454-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 111 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903382454 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903382503-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 462 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903382503 IN0088 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903382608-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 498 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903382608 IN0089 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903382642-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 117 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903382642 JW9678 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903382648-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 294 | 46214 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382648 LI2670 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903382670-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 293 | 46214 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382670 LI2671 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903382686-1 KA0235 | BLACK | 105D | S2608WR0901 | 325 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903382686 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382719 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903382747-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 315 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382747 LI2668 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903382753-1 LH5251 | WHITE/BLACK | 105D | F2654MESS614WVB | 402 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382753 LH5251 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 141S WV WB LND WHITE/BLACK |  | SS27
ADIDAS | 0903382780-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903382780 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382781-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 1902 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382781 KB5965 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382810-1 LG9675 | BLACK | 120D | S2754WAS513C | 420 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903382810 LG9675 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903382812-1 KB5960 | WHITE | 120D | S2608MR0900A | 454 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382812 KB5960 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382838-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 704 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382838 KB5961 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382866-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 496 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382866 KF5311 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903382881-1 KA0235 | BLACK | 105D | S2608WR0901 | 4 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903382881 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382905-1 KA0246 | BLACK | 105D | S2608WR0902 | 8 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903382905 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903382908-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 1200 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 804028 | EMBRO+PAD SUB PROCESS_V3 | 0903382908 KV3559 | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903382908-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 1200 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 804028 | EMBRO+PAD SUB PROCESS_V3 | 0903382908 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903382942-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 12 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382942 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382966-1 KG8547 | ONIX | 105D | S2408WR1600 | 70 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382966 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382983-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 4 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT SUB PROCESS_V1 | 0903382983 KG8553 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903383005-1 KD3875 | BLACK | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903383005 KD3875 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903383011-1 KZ4389 | WHITE | 120D | F2608MR1500 | 160 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848016 | PAD+HT SUB PROCESS_V3 | 0903383011 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903383028-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 8 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383028 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903383050-1 LG9669 | BLACK | 120D | S2754WAS514C | 58 | 30/11/2026 |  | ID | ID31/07/2026 |  | SKIRT |  | (20/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 20-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903383050 LG9669 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903383053-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 100 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903383053 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903383098-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 9 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT SUB PROCESS_V1 | 0903383098 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903383116-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 4 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903383116 LD0292 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383141-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 391 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903383141 KC8152 |  | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903383152-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 268 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383152 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383154-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 559 | 46214 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383154 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903383175-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 46214 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383175 LI2669 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903383208-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 153 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903383208 LH4744 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903383211-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 770 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383211 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383242-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 102 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903383242 KX9855 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903383264-1 JC5699 | WONDER ALUMINA S25/WHITE | 90D | S2554WES503FT | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383264 JC5699 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903383301-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383301 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383327-1 LF4995 | OLIVE TWO S27 | 105D | S2750MTR051 | 182 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 05-Sep. 830009 | HT SUB PROCESS_V1 | 0903383327 LF4995 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T ESS T OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903383333-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383333 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383370-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 662 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT SUB PROCESS_V1 | 0903383370 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383385-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903383385 KA0237 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903383400-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT SUB PROCESS_V1 | 0903383400 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383404-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 167 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903383404 KU0090 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383433-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 160 | 46215 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383433 JE0052 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903383551-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383551 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383552-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 186 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903383552 KY9391 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903383580-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 400 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903383580 IT3474 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903383585-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383585 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383600-1 KA0235 | BLACK | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 800005 | PAD+HT SUB PROCESS_V3 | 0903383600 KA0235 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383614-1 KA0235 | BLACK | 105D | S2608WR0901 | 135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903383614 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383625-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 468 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383625 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383639-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903383639 IW2479 |  | KAHATEX CIJERAH | TURKEY | SEA |  | POS TABLE LK |  | SS27
ADIDAS | 0903383934-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903383934 LE8186 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903383958-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 826010 | HT SUB PROCESS_V1 | 0903383958 JC9584 | 15/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903383982-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903383982 JE6340 | 15/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903383985-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 306 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903383985 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903384003-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 826010 | PRINT L2 SUB PROCESS_V3 | 0903384003 KB7172 |  | KAHATEX CIJERAH | TURKEY | SEA |  | HOT COMMUNITY |  | SS27
ADIDAS | 0903384048-1 IN8707 | BLACK | 105D | S2408WR1601A | 329 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 678002 | HT SUB PROCESS_V1 | 0903384048 IN8707 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384058-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 323 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384058 LH4746 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903384076-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 680 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903384076 KD0738 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903384078-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1972 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903384078 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 269 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384085 LD5446 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903384087-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 144 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903384087 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903384116-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 678002 | HT SUB PROCESS_V1 | 0903384116 IN1159 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384142-1 IN1157 | WHITE | 105D | S2408MR1600 | 823 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903384142 IN1157 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384205-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 490 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903384205 LD0294 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903384218-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 497 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903384218 LG9670 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903384263-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 370 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903384263 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903384268-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 414 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT SUB PROCESS_V1 | 0903384268 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384290-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 348 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384290 KA6260 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903384300-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 710 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384300 KV7863 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903384325-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384325 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384351-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 551 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384351 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384354-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 384 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903384354 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903384380-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903384380 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903384391-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 130 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903384391 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903384406-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT SUB PROCESS_V1 | 0903384406 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384429-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 124 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903384429 KX3713 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903384435-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903384435 LD0278 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903384461-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903384461 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384496-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 142 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384496 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903384678-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 389 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903384678 HB7454 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903384715-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 370 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384715 JW7182 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903384799-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 497 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903384799 KD3684 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903384839-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384839 JD9944 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903384877-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 593 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903384877 JD1881 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903384912-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1200 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384912 JW7178 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903384931-1 IC5189 | WHITE | 90D | S23080640 | 394 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 814006 | HT SUB PROCESS_V1 | 0903384931 IC5189 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903384989-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1550 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | PRINT L1 SUB PROCESS_V3 | 0903384989 JF3604 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903384992-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 510 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903384992 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903385024-1 IP2310 | BLACK | 105D | S2450MTR701 | 295 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903385024 IP2310 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903385058-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 2298 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (03/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 03-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385058 JM1772 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903385096-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 149 | 46215 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 800187 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385096 JE6414 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903385133-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2433 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903385133 JE6338 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903385161-1 KG8547 | ONIX | 105D | S2408WR1600 | 2190 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385161 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385187-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 661 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385187 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385216-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 429 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT SUB PROCESS_V1 | 0903385216 KU7520 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385236-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2986 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385236 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385265-1 KT4839 | ONIX | 90D | S2408MR1601 | 356 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT SUB PROCESS_V1 | 0903385265 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903385289-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 4617 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385289 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903385321-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 550 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385321 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903385346-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 2915 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385346 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385373-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 418 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385373 LD5446 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903385404-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903385404 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385432-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 102 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 688010 | PRINT L2+PAD SUB PROCESS_V3 | 0903385432 LC8884 |  | KAHATEX CIJERAH | PANAMA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903385460-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 20 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385460 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903385648-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 331 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385648 JW7182 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903385684-1 LC9640 | BLACK/SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385684 LC9640 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365 SHO M BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385693-1 LH2842 | BLACK | 90D | S2725M993 | 106 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903385693 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903385716-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 598 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903385716 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385723-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 620 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903385723 KB5966 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903385730-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 101 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385730 LF9808 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385741-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 570 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385741 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903385758-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 160 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385758 LF9808 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385762-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 100 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385762 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903385764-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 669 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385764 LD0278 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903385785-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 202 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903385785 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385792-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 311 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385792 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385799-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 105 | 22/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | EMBRO SUB PROCESS_V1 | 0903385799 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903385806-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 500 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 New Wide, PI Date ?? 800005 | HT SUB PROCESS_V1 | 0903385806 IW8374 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903385813-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385813 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903385818-1 KA0235 | BLACK | 105D | S2608WR0901 | 477 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 806020 | PAD+HT SUB PROCESS_V3 | 0903385818 KA0235 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903385840-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 452 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385840 LF9808 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385844-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 254 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903385844 LD0292 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385886-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 428 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903385886 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903385887-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 122 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385887 KD3683 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903385905-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 170 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385905 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903385915-1 LH2841 | OFF WHITE | 90D | S2725M993 | 117 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903385915 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903385928-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 638 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385928 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903385942-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 328 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903385942 IW8374 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903385963-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 432 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385963 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903385965-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 121 | 46215 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385965 JW7182 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903385992-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 314 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903385992 KB0235 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386004-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 479 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386004 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903386008-1 KA0235 | BLACK | 105D | S2608WR0901 | 450 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 960006 | PAD+HT SUB PROCESS_V3 | 0903386008 KA0235 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386012-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 560 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903386012 KB0235 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386021-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386021 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386035-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 672 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903386035 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903386059-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 305 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 680015 | HT SUB PROCESS_V1 | 0903386059 KT4840 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386060-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386060 KY9391 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903386078-1 IN2961 | BLACK | 105D | S2408WR2400 | 201 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903386078 IN2961 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903386079-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 684009 | PAD+HT SUB PROCESS_V3 | 0903386079 LD0278 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903386080-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 184 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386080 LF9808 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903386099-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 727 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386099 KD3683 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386105-1 LH2841 | OFF WHITE | 90D | S2725M993 | 463 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386105 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903386109-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 180 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386109 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903386130-1 LH2842 | BLACK | 90D | S2725M993 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386130 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386133-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 100 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386133 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386166-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386166 KD3684 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903386183-1 IN1173 | WHITE | 105D | S2408WR1600 | 1024 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386183 IN1173 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386198-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 149 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386198 LE8186 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903386216-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 1447 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386216 IN1172 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386221-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 518 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386221 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386249-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 415 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386249 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386253-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 171 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386253 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903386254-1 IN8707 | BLACK | 105D | S2408WR1601A | 479 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 678002 | HT SUB PROCESS_V1 | 0903386254 IN8707 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903386264-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386264 KD3683 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386278-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386278 IT1469 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386299-1 KA0235 | BLACK | 105D | S2608WR0901 | 510 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386299 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386301-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 659 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386301 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386304-1 KA0235 | BLACK | 105D | S2608WR0901 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903386304 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386327-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 666 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386327 KV7963 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386328-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386328 KB5961 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386337-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 170 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386337 LH4746 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903386345-1 JE6353 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS605FT | 300 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386345 JE6353 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386348-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386348 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386352-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386352 KV7963 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386355-1 KB5960 | WHITE | 120D | S2608MR0900A | 371 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386355 KB5960 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386367-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 400 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903386367 IN0088 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386369-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903386369 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386372-1 IP2310 | BLACK | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903386372 IP2310 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903386387-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 435 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386387 KB5965 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386391-1 KG3189 | MAROON | 120D | S2608MR0900A | 400 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903386391 KG3189 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903386400-1 KE8425 | WHITE | 120D | S2608MR0906A | 718 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903386400 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0903386413-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386413 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903386428-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 109 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903386428 JD1881 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386435-1 KD3875 | BLACK | 120D | S2608WR0201 | 358 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386435 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903386450-1 LH2842 | BLACK | 90D | S2725M993 | 563 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386450 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386490-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386490 KE8424 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903386521-1 KA0235 | BLACK | 105D | S2608WR0901 | 305 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386521 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386540-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 112 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903386540 IN0088 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386556-1 KA0246 | BLACK | 105D | S2608WR0902 | 393 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386556 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903386570-1 LH2842 | BLACK | 90D | S2725M993 | 451 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903386570 LH2842 |  | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386589-1 KT4840 | ONIX | 105D | S2408MR1600 | 405 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386589 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386620-1 KA4331 | BLACK | 90D | S2608MR0902 | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386620 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903386627-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 109 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386627 JD5302 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386672-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 2749 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386672 JE6346 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386704-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 271 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903386704 IU0217 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903386736-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386736 JW7182 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903386741-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 100 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903386741 KD3684 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903386775-1 HK7319 | BLACK | 90D | F2225M403 | 2400 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | 804028 | EMBRO+PPA SUB PROCESS_V3 | 0903386775 HK7319 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903386782-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 988 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386782 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386825-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 3178 | 46214 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386825 JD1881 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386860-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2230 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386860 JD1877 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903386863-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 434 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386863 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386894-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 103 | 46214 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903386894 KS1493 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903386898-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 1250 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386898 JD7999 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903386920-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903386920 IN0088 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386936-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386936 JE6419 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903386967-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903386967 IU0217 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903386983-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1250 | 46214 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386983 JE6340 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903387009-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 889 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903387009 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903387028-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2037 | 46214 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387028 JE6374 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387045-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 397 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903387045 KC9016 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903387071-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2557 | 46214 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387071 JE6372 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387109-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1289 | 46214 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387109 JE6414 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903387118-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 498 | 46214 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387118 JE0052 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903387166-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 37 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387166 LG9663 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387197-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 39 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903387197 LG9672 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387223-1 LD0291 | HAZE CORAL S17 | 105D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903387223 LD0291 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903387244-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387244 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387298-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 75 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387298 LF0725 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903387372-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 156 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387372 LH4744 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903387607-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? Waiting fabric (NYK warehuose). T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387607 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903387643-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387643 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903387704-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 450 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387704 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903387726-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 567 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387726 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903387868-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 111 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903387868 LG9670 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387903-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387903 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903387928-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 204 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903387928 KA5090 | 16/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903387962-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387962 KY6616 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388016-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 410 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388016 LD6542 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388052-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 450 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388052 KY6616 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388072-1 HK7319 | BLACK | 90D | F2225M403 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | 826010 | EMBRO+PPA SUB PROCESS_V3 | 0903388072 HK7319 |  | KAHATEX CIJERAH | TURKEY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903388124-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 162 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388124 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388150-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1187 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903388150 KX3654 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388156-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388156 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903388178-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903388178 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388183-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 382 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388183 JD9944 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903388195-1 KA4331 | BLACK | 90D | S2608MR0902 | 397 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903388195 KA4331 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903388205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2641 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388205 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388219-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 571 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903388219 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903388238-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 1347 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903388238 KX9855 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388262-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 1134 | 15/11/2026 |  | AN | AN31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388262 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388290-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 1800 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388290 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388317-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1096 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388317 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903388347-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 511 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 678002 | PRINT L2+PAD SUB PROCESS_V3 | 0903388347 LC8884 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903388375-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 1000 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903388375 LD0292 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388415-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 823 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903388415 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388488-1 KX8877 | WHITE | 90D | S27GMGFX100 | 42 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903388488 KX8877 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903388556-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 339 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903388556 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903388601-1 KG3189 | MAROON | 120D | S2608MR0900A | 700 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903388601 KG3189 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903388629-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903388629 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388646-1 IC5189 | WHITE | 90D | S23080640 | 254 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 839055 | HT SUB PROCESS_V1 | 0903388646 IC5189 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903388649-1 KB5960 | WHITE | 120D | S2608MR0900A | 1653 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388649 KB5960 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903388657-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903388657 KF5311 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903388679-1 LE8187 | BLACK | 105D | S2754MAS513 | 308 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903388679 LE8187 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903388696-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903388696 KX3654 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388702-1 KD3875 | BLACK | 120D | S2608WR0201 | 610 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903388702 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903388713-1 KA0246 | BLACK | 105D | S2608WR0902 | 133 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 547012 | PAD+HT SUB PROCESS_V3 | 0903388713 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903388719-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 261 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903388719 KX3654 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388725-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 400 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388725 KE8424 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903388738-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 10 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 547012 | PAD+HT SUB PROCESS_V3 | 0903388738 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388740-1 LH2842 | BLACK | 90D | S2725M993 | 131 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903388740 LH2842 |  | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903388755-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1160 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388755 KX3654 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388767-1 JZ7711 | BLACK | 120D | S2608MR0202 | 266 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388767 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903388782-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 482 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388782 KX3655 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903388797-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 183 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903388797 KE8424 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903388813-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 780 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388813 KX3655 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903388823-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 130 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 547012 | HT SUB PROCESS_V1 | 0903388823 KU7520 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903388850-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 130 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388850 KX9855 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388859-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 492 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903388859 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388867-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 646 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903388867 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903388876-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 130 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388876 KX9838 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903388878-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 910 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388878 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903388910-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 380 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903388910 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903388942-1 KG3189 | MAROON | 120D | S2608MR0900A | 800 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903388942 KG3189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903388957-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 795 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388957 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903389019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 321 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389019 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903389062-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 477 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389062 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389087-1 LH2841 | OFF WHITE | 90D | S2725M993 | 284 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903389087 LH2841 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903389159-1 IL7232 | BLACK | 105D | S2408MR3202 | 105 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389159 IL7232 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903389207-1 IS1413 | BLACK | 60D | S2425M405 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903389207 IS1413 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903389253-1 KE9870 | BLACK | 105D | S2650MTR809B | 130 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 814006 | PRINT L1 SUB PROCESS_V3 | 0903389253 KE9870 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903389297-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389297 IN0088 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903389321-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389321 IN0089 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903389360-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 1000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903389360 KB5966 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903389399-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 419 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389399 KD3676 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903389461-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 599 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389461 IT3474 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903389493-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 737 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903389493 IW8374 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903389563-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 400 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389563 KC9016 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903389597-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 229 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389597 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903389635-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 447 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903389635 IN0089 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903389714-1 IC5189 | WHITE | 90D | S23080640 | 100 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903389714 IC5189 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903389876-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 411 | 46215 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903389876 LI2669 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903390163-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 582 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903390163 LE7650 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903390166-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903390166 KE8420 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903390226-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 104 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903390226 KA6260 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903390329-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 493 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT SUB PROCESS_V1 | 0903390329 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903390359-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT SUB PROCESS_V1 | 0903390359 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903390384-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 503 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390384 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903390534-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1795 | 46214 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390534 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390588-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 642 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390588 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390685-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903390685 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903390730-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390730 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903390802-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390802 KA5090 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903390874-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 223 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903390874 JW9678 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903390896-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903390896 KB5966 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903390928-1 IN2961 | BLACK | 105D | S2408WR2400 | 417 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903390928 IN2961 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903390966-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390966 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903391007-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391007 KD3684 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903391036-1 KE9870 | BLACK | 105D | S2650MTR809B | 332 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903391036 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903391094-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 119 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391094 JD1881 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903391161-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 317 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391161 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391179-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 1026 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391179 KX8875 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391201-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903391201 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391209-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 1170 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391209 LC6339 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391236-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 741 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391236 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391240-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1356 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903391240 IN0088 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391269-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 108 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391269 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391298-1 IL7232 | BLACK | 105D | S2408MR3202 | 1512 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391298 IL7232 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903391314-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 999 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391314 LF9808 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391321-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1080 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391321 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391350-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 972 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391350 LC6339 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391352-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 429 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391352 LF9808 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391380-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 808 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391380 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391388-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 595 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391388 LF9808 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391401-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 864 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391401 KX8875 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391419-1 IC5188 | BLACK | 90D | S23080640 | 693 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903391419 IC5188 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903391436-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1080 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391436 LC6341 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903391467-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 235 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391467 LH4744 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903391494-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 826 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391494 KY4221 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391497-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 565 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391497 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903391498-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 181 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391498 KY4221 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391515-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903391515 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391525-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 339 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391525 KY4221 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391547-1 IN1173 | WHITE | 105D | S2408WR1600 | 600 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT SUB PROCESS_V1 | 0903391547 IN1173 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391589-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 100 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391589 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391590-1 KE8424 | BLACK | 120D | S2608MR0906A | 694 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391590 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903391595-1 IN1156 | BLACK | 105D | S2408MR1600 | 353 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT SUB PROCESS_V1 | 0903391595 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391613-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 873 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391613 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903391641-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 403 | 46215 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391641 KY6616 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903391828-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903391828 LD0908 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903391866-1 KG8547 | ONIX | 105D | S2408WR1600 | 109 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903391866 KG8547 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391898-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 814006 | PRINT L1 SUB PROCESS_V3 | 0903391898 KE9870 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903391982-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 101 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903391982 KF5311 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903392043-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 650 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903392043 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903392090-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 374 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903392090 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903392298-1 KB5965 | BLACK | 120D | S2608MR0900A | 1240 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903392298 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903392317-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 303 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903392317 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903392385-1 KA0235 | BLACK | 105D | S2608WR0901 | 602 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903392385 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903392419-1 KB5960 | WHITE | 120D | S2608MR0900A | 578 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903392419 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903393666-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 216 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393666 KY6616 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393674-1 KE8424 | BLACK | 120D | S2608MR0906A | 1120 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903393674 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903393679-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 340 | 46215 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903393679 LI2672 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903393700-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393700 KY6616 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393729-1 LG9666 | BLACK | 120D | S2754WAS512C | 301 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393729 LG9666 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903393736-1 KW5050 | MAROON | 90D | F2625M101 | 104 | 46214 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393736 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393740-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 600 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393740 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903393756-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 176 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393756 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903393785-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 8427 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903393785 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903393789-1 KW5050 | MAROON | 90D | F2625M101 | 1832 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393789 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393794-1 LG9675 | BLACK | 120D | S2754WAS513C | 277 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903393794 LG9675 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903393812-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 579 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393812 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903393816-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 104 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393816 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393853-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 936 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393853 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393882-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 290 | 46215 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903393882 KA0237 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903393918-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 250 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393918 KS4777 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903393950-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 109 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903393950 KB5966 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903394061-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 237 | 46368 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). 800005 | PRINT L1 SUB PROCESS_V3 | 0903394061 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394091-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 404 | 46215 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903394091 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394210-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 400 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394210 KS4777 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903394289-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 487 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394289 KU3270 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394317-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 250 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394317 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394356-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 498 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394356 KU3272 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394379-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 183 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903394379 KB0235 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903394400-1 LF0723 | BLACK | 105D | S2754MAS511B | 284 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903394400 LF0723 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903394471-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 240 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394471 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903394497-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 956 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394497 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903394844-1 KA4331 | BLACK | 90D | S2608MR0902 | 1140 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394844 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903394868-1 KA4331 | BLACK | 90D | S2608MR0902 | 1142 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394868 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903395342-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 509 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903395342 KA6260 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903395364-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 481 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395364 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395391-1 IN1173 | WHITE | 105D | S2408WR1600 | 1079 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903395391 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395411-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 333 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395411 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395435-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 477 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903395435 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395456-1 KA4331 | BLACK | 90D | S2608MR0902 | 424 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903395456 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903395497-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 455 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395497 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903395510-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 359 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395510 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903395545-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 440 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395545 KX3655 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903395560-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 434 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395560 LD0292 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903395572-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 442 | 15/12/2026 |  | AN | AN31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903395572 LF0726 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903395581-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 1983 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395581 LD0277 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903395619-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 832 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395619 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903395640-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 432 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903395640 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395784-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 238 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903395784 LE7647 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903395859-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 533 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903395859 LE7647 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903396155-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 204 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903396155 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903396227-1 IN8707 | BLACK | 105D | S2408WR1601A | 322 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 800005 | HT SUB PROCESS_V1 | 0903396227 IN8707 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903396318-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 304 | 46214 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396318 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | K BLANK TEE |  | SS27
ADIDAS | 0903396350-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric (NYK warehouse). T2 New Wide, PI Date 11-Sep. 800005 | HT SUB PROCESS_V1 | 0903396350 IN2961 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903397029-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 475 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397029 KE8424 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903397047-1 KG8547 | ONIX | 105D | S2408WR1600 | 347 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397047 KG8547 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397069-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 892 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397069 KG8548 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397145-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 442 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397145 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397668-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 460 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397668 KX3655 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903397694-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903397694-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903397701-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 2364 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397701 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903397762-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1097 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903397762 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903397781-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 201 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903397781 LE7650 |  | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903397793-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1335 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397793 KF5311 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903397824-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 1062 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397824 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903397858-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 434 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903397858 LE7650 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903397879-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397879 KB5965 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903397924-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 566 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903397924 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903397937-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 304 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903397937 KU0090 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903397945-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903397945 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903397973-1 LG9675 | BLACK | 120D | S2754WAS513C | 613 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903397973 LG9675 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903397998-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 406 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397998 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903398052-1 KT4840 | ONIX | 105D | S2408MR1600 | 137 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903398052 KT4840 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903398113-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398113 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398140-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398140 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398456-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 652 | 46215 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903398456 LE7647 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903398741-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 360 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT SUB PROCESS_V1 | 0903398741 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903399989-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 365 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903399989 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400022-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903400022 KY6510 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400227-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400227 IW8374 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903400251-1 IN2961 | BLACK | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400251 IN2961 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903400316-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 121 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400316 HB7454 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903400396-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400396 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903400420-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 383 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400420 HB7454 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903400450-1 IK7442 | WHITE | 105D | S2408WR2400 | 149 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400450 IK7442 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903400476-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903400476 KC9016 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903400498-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 200 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903400498 KD3676 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903400589-1 KG8547 | ONIX | 105D | S2408WR1600 | 221 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400589 KG8547 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903400617-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 142 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400617 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903400639-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903400639-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903401845-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 402 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903401845 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903402665-1 LH2841 | OFF WHITE | 90D | S2725M993 | 385 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903402665 LH2841 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903402717-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 118 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903402717 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903402776-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 131 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903402776 KU3270 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903402796-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | PRINT L1 SUB PROCESS_V3 | 0903402796 KC8559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903408401-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408401 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408420-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408420 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408450-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516462 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408450 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408471-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 710 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408471 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903442023-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 1217 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903442023 KB5965 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903444660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 2974 | 15/11/2026 |  | SA | SA04/08/2026 |  | PANTS |  | (15/10/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903444660 LE8181 | 46064 | KAHATEX CIJERAH | INDIA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903450968-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450968 IN1159 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27
ADIDAS | 0903450969-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 26 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450969 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450970-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 350 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450970 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450971-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 65 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450971 IN1159 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27
ADIDAS | 0903450972-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903450972 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903452885-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452885 KA6229 | 46367 | KAHATEX CIJERAH | PERU | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452887-1 KA6229 | BLACK | 120D | S2608WR0202 | 312 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452887 KA6229 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452889-1 KA6229 | BLACK | 120D | S2608WR0202 | 704 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452889 KA6229 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452891-1 KA6229 | BLACK | 120D | S2608WR0202 | 6 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | (Mexico). 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452891 KA6229 | 46367 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903466285-1 IC5188 | BLACK | 90D | S23080640 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903466285 IC5188 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903467966-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903467966 HK7319 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468003-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903468003 HR8583 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468026-1 HZ0747 | BLACK | 90D | F2325M414 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903468026 HZ0747 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PL TEE |  | SS27
ADIDAS | 0903468058-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903468058 HK7319 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468137-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3000 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903468137 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470160-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903470160 HR8583 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470333-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903470333 JE6374 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903470363-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3000 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903470363 HR8583 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470418-1 IC5188 | BLACK | 90D | S23080640 | 4500 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 823016 | HT SUB PROCESS_V1 | 0903470418 IC5188 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903470449-1 HK7309 | BLACK | 45D | F2225M402 | 5500 | 46214 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903470449 HK7309 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903472306-1 IP2310 | BLACK | 105D | S2450MTR701 | 300 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 800187 | HT SUB PROCESS_V1 | 0903472306 IP2310 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903472755-1 JF3606 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS675FT | 5000 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903472755 JF3606 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903473017-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 719 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903473017 JM1775 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903473064-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903473064 JP1528 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903473120-1 JF3606 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS675FT | 6350 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903473120 JF3606 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903473549-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 18 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903473549 KZ0028 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903473588-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 547012 | EMBRO SUB PROCESS_V1 | 0903473588 KW6443 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903473911-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903473911 JE6419 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903473952-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1601 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903473952 IU0217 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903474040-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1749 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903474040 JC9584 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903475709-1 KG3189 | MAROON | 120D | S2608MR0900A | 400 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903475709 KG3189 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903475735-1 LC9677 | OFF WHITE | 90D | S2725M959 | 160 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903475735 LC9677 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | STENCIL TONGUE OFF WHITE |  | SS27-STX
ADIDAS | 0903475746-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475746 KZ3200 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903475786-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 100 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903475786 KY1333 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903475826-1 LC9677 | OFF WHITE | 90D | S2725M959 | 100 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1 SUB PROCESS_V3 | 0903475826 LC9677 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | STENCIL TONGUE OFF WHITE |  | SS27-STX
ADIDAS | 0903475848-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 144 | 46215 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903475848 LI7656 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903475858-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903475858 JP1527 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903475913-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475913 JM1776 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903475934-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 1139 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903475934 KW8936 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903475971-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475971 JM1776 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903475974-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 222 | 46215 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903475974 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903476015-1 LC9621 | OFF WHITE | 90D | S2725M920 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1 SUB PROCESS_V3 | 0903476015 LC9621 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903476030-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903476030 JP1527 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903476078-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476078 JM1776 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903476096-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 510 | 30/11/2026 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903476096 KW9040 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903476131-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903476131 KA0247 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903476137-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 612 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903476137 LE1842 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476139-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 456 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903476139 KY1333 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903476291-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 1370 | 15/12/2026 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903476291 KW9040 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903476381-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 350 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903476381 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903476426-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903476426 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476460-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 396 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 547012 | EMBRO SUB PROCESS_V1 | 0903476460 IB8686 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903476510-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903476510 KB5959 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903476565-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 148 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512106 | HT+PAD SUB PROCESS_V3 | 0903476565 KX3655 | 46367 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903476607-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903476607 JC9584 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903476632-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 198 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903476632 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476637-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903476637 LE1842 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476693-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 750 | 15/12/2026 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903476693 JE6340 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903476831-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516205 | PRINT L1 SUB PROCESS_V3 | 0903476831 JE9012 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903476845-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 2000 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (08/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903476845 IN0089 |  | KAHATEX CIJERAH | ITALY | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903476874-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 721 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476874 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903477003-1 KG3189 | MAROON | 120D | S2608MR0900A | 300 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903477003 KG3189 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903477015-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903477015 IW8374 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903477134-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 3500 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903477134 JE6417 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903478198-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478198 LI7656 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478236-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 1502 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478236 KA4913 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478237-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 206 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478237 LI5438 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478243-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 133 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903478243 KU3272 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903478276-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478276 KA4914 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478279-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 628 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478279 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478284-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 224 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903478284 LC8943 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903478311-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478311 JE6372 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903478324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 351 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478328-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516205 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478328 KA4914 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478347-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903478347 KD3936 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903478377-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478377 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478385-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478385 LJ4074 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478389-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478389 KF6290 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903478417-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478417 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478424-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 229 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478424 LI7658 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478453-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 1000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478453 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478472-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903478472 HK7303 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903478482-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 150 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478482 LI7659 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903478521-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 406 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478521 LI7655 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903478661-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 347 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903478661 JG8639 |  | KAHATEX CIJERAH | PERU | SEA |  | W LIN FT SHO |  | SS27
ADIDAS | 0903478686-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903478686 LE1843 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478689-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 208 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903478689 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903478701-1 LC9638 | BLACK/SEMI SOLAR BLUE S27 | 120D | S2608WR0202 | 476 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478701 LC9638 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903478720-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903478720 LI5438 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478739-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1198 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478739 LE8181 | 46367 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478752-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 125 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478752 JD9944 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903478756-1 KC8568 | BLACK | 105D | OJS26250839 | 331 | 46215 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 547012 | PRINT L1 SUB PROCESS_V3 | 0903478756 KC8568 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903478788-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 344 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478788 KD3854 | 46367 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903478852-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 387 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478852 KD3854 | 46367 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903478862-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903478862 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903478873-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 223 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903478873 KU3272 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903478906-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 533 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478906 LE8181 | 46367 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478960-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 150 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903478960 LE8189 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903478964-1 LC9638 | BLACK/SEMI SOLAR BLUE S27 | 120D | S2608WR0202 | 303 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | (Mexico). 1st Art (TC 10 pcs) 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478964 LC9638 | 46367 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 W BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903478995-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 202 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903478995 LE5780 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903479022-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 150 | 46215 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903479022 LD0293 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903479028-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 145 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903479028 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903479034-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 146 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479034 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479063-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903479063 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903479077-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 133 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903479077 LD0293 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903479094-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 216 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903479094 KW8936 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903479108-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 118 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903479108 IL4127 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903479112-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 102 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903479112 KW8936 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903479120-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903479120 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903479186-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 3000 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO SUB PROCESS_V1 | 0903479186 JD7999 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903479193-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516205 | PRINT L1 SUB PROCESS_V3 | 0903479193 JC9346 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903479239-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479239 JM1775 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479246-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1749 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516205 | HT SUB PROCESS_V1 | 0903479246 JC9584 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903479287-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479287 JP1528 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903479292-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | PRINT L1 SUB PROCESS_V3 | 0903479292 JC9346 |  | KAHATEX CIJERAH | ITALY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903479338-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 2000 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516205 | PAD+HT SUB PROCESS_V3 | 0903479338 KA0247 |  | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903479475-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516205 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903479475 KA4913 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903479546-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479546 JM1775 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479547-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903479547 KA4913 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903479588-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479588 JP1527 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903480160-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 113 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 547012 | PAD+HT SUB PROCESS_V3 | 0903480160 LD0293 | 46367 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903480229-1 KB5960 | WHITE | 120D | S2608MR0900A | 199 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0903480229 KB5960 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480272-1 HZ0747 | BLACK | 90D | F2325M414 | 970 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | EMBRO SUB PROCESS_V1 | 0903480272 HZ0747 |  | KAHATEX CIJERAH | CANADA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903480348-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 714 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480348 JE0055 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903480380-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/12/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 512106 | PRINT L1 SUB PROCESS_V3 | 0903480380 LE1842 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903480440-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 416 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903480440 LE8191 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903480478-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 810 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903480478 KB5959 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480562-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 774 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903480562 KB5959 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480652-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 543 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480652 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903480678-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903480678 KD3936 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480715-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903480715 KD3936 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480748-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 1750 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516205 | HT SUB PROCESS_V1 | 0903480748 KD9849 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903480764-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 366 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903480764 KB5964 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480790-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 2000 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903480790 KA0247 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903480819-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 135 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480819 IN1156 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480833-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480833 JE6419 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903480868-1 IP2310 | BLACK | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516205 | HT SUB PROCESS_V1 | 0903480868 IP2310 | 46367 | KAHATEX CIJERAH | SPAIN | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903480875-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 195 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903480875 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903480885-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903480885 JZ7711 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903480915-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 117 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480915 IN1157 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480916-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480916 KF6290 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903480931-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 20/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903480931 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903480973-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480973 IN1172 | 46367 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480979-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 536 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480979 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903481002-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 46214 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481002 KD9097 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903481003-1 KG2491 | ACTIVE MAROON F19 | 90D | F2606CHLF011 | 40 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 814006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481003 KG2491 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC DNA SHO |  | SS27
ADIDAS | 0903481051-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 600 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903481051 KG8548 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903481052-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481052 KW1543 | 46121 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903481119-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 1390 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903481119 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903481123-1 KA0235 | BLACK | 105D | S2608WR0901 | 668 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 680015 | PAD+HT SUB PROCESS_V3 | 0903481123 KA0235 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903481211-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 645 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481211 LE8199 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903481262-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 450 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903481262 LG1784 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903481315-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 138 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481315 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903481318-1 KB5960 | WHITE | 120D | S2608MR0900A | 1140 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903481318 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481323-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2750 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903481323 HK7317 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903481374-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 5000 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903481374 JW7182 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903481398-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903481398 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903481413-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 5000 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903481413 JF3604 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903481437-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 301 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481437 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903481501-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1153 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903481501 KF5311 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903481504-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 344 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481504 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903481536-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 104 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 830009 | HT+PAD SUB PROCESS_V3 | 0903481536 KB5966 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481568-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 318 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903481568 KB5964 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481585-1 KT7395 | AURORA IVY F25 | 90D | F2625M101 | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903481585 KT7395 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE AURORA IVY F25 |  | SS27-L2L
ADIDAS | 0903481589-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 500 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903481589 KB5964 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481632-1 LC9621 | OFF WHITE | 90D | S2725M920 | 221 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903481632 LC9621 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903481635-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 102 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903481635 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903481652-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | PRINT L1 SUB PROCESS_V3 | 0903481652 JE9012 |  | KAHATEX CIJERAH | ITALY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903481790-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481790 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903482150-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  |  |  | MOQ Issue 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482150 KZ0925 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903482152-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 680015 | HT+PAD SUB PROCESS_V3 | 0903482152 KB5964 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903482169-1 KZ4392 | WHITE | 120D | F2608WR1500 | 19 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903482169 KZ4392 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903482200-1 IN1159 | BLACK | 90D | S2408MR1601 | 23 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT SUB PROCESS_V1 | 0903482200 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482201-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482201 JM1779 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903482233-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 684009 | HT SUB PROCESS_V1 | 0903482233 KD9849 |  | KAHATEX CIJERAH | PERU | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903482238-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT SUB PROCESS_V1 | 0903482238 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482281-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482281 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482305-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 239 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903482305 LF0725 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903482323-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482323 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482414-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 6500 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903482414 JF3604 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903482425-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2750 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903482425 HK7317 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482462-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 600 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903482462 KF6290 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903482511-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903482511 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482547-1 HK7319 | BLACK | 90D | F2225M403 | 3001 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903482547 HK7319 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482561-1 HK7319 | BLACK | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903482561 HK7319 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482623-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 3781 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903482623 HK7317 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482634-1 IC5189 | WHITE | 90D | S23080640 | 4000 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 823016 | HT SUB PROCESS_V1 | 0903482634 IC5189 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903482892-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 670 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482892 KR3066 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903482957-1 KA6229 | BLACK | 120D | S2608WR0202 | 492 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482957 KA6229 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903483164-1 KB5960 | WHITE | 120D | S2608MR0900A | 791 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 680015 | HT+PAD SUB PROCESS_V3 | 0903483164 KB5960 |  | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903483208-1 IN1173 | WHITE | 105D | S2408WR1600 | 968 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483208 IN1173 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483237-1 JZ7711 | BLACK | 120D | S2608MR0202 | 300 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903483237 JZ7711 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903483311-1 KA4331 | BLACK | 90D | S2608MR0902 | 1048 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 680015 | PAD+HT SUB PROCESS_V3 | 0903483311 KA4331 |  | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903483320-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903483320 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483346-1 IN8707 | BLACK | 105D | S2408WR1601A | 580 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903483346 IN8707 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483362-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903483362 HK7303 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903483384-1 IN1156 | BLACK | 105D | S2408MR1600 | 968 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903483384 IN1156 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483459-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 680015 | HT SUB PROCESS_V1 | 0903483459 IN1159 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483478-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903483478 HK7317 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483493-1 IN1172 | BLACK | 105D | S2408WR1600 | 948 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483493 IN1172 | 46367 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483511-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903483511 HK7317 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483546-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903483546 JE6414 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903483584-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903483584 KD3911 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483666-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 144 | 46215 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903483666 LI7659 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903483676-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 830009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483676 JM1775 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903483703-1 IP2310 | BLACK | 105D | S2450MTR701 | 330 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 830009 | HT SUB PROCESS_V1 | 0903483703 IP2310 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903483721-1 HZ0747 | BLACK | 90D | F2325M414 | 393 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483721 HZ0747 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PL TEE |  | SS27
ADIDAS | 0903483722-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 104 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483722 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903483757-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 226 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483757 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903483769-1 LC9621 | OFF WHITE | 90D | S2725M920 | 177 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903483769 LC9621 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903483798-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 300 | 46214 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903483798 KA5089 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903483800-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 939 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483800 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903483831-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 7 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483831 LE5779 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903483841-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 100 | 46215 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903483841 JE6340 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903483884-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 139 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903483884 JE0052 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903483889-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 100 | 46215 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903483889 JC9584 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903483932-1 IN1173 | WHITE | 105D | S2408WR1600 | 423 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 830009 | HT SUB PROCESS_V1 | 0903483932 IN1173 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483940-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 311 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903483940 KY1333 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903483981-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 120 | 46215 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903483981 JE6340 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903483984-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 368 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903483984 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903484021-1 IN2961 | BLACK | 105D | S2408WR2400 | 456 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903484021 IN2961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903484027-1 KT7395 | AURORA IVY F25 | 90D | F2625M101 | 1006 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903484027 KT7395 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE AURORA IVY F25 |  | SS27-L2L
ADIDAS | 0903484055-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 400 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484055 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903484065-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 246 | 46215 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903484065 KW9040 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903484097-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 745 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484097 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903484129-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 139 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484129 LE5779 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484522-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1036 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903484522 KZ1286 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903484567-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 1037 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484567 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903484603-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 163 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484603 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903484610-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2640 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484610 KZ3200 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903484626-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 302 | 30/11/2026 | 302 | SI | SI14/08/2026 | G3J | SHORTS | G3 |  |  | 29/09: ex-fty. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903484626 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 302 |  | 302 |  |  | 24/10/2026 | 26/10/2026 |  |  | 302 |  | 302 |  |  | 21/10/2026 | 22/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903484639-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1599 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484639 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484642-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 4029 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903484642 KZ1286 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903484665-1 HK7319 | BLACK | 90D | F2225M403 | 3001 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903484665 HK7319 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484713-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903484713 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484845-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903484845 HK7317 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3752 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903484894 IB8686 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903484896-1 IP2310 | BLACK | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903484896 IP2310 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903484940-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484940 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485008-1 KE9656 | BLACK | 105D | S2608WR0201A | 308 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485008 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485025-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 2101 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485025 KF6290 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485027-1 HK7309 | BLACK | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903485027 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485046-1 KE9656 | BLACK | 105D | S2608WR0201A | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485046 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485074-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516205 | HT SUB PROCESS_V1 | 0903485074 IW8374 | 46367 | KAHATEX CIJERAH | SPAIN | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903485085-1 KE9656 | BLACK | 105D | S2608WR0201A | 7387 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485085 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485092-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 4500 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485092 JW7178 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485117-1 KE9656 | BLACK | 105D | S2608WR0201A | 746 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903485117 KE9656 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485121-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 201 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903485121 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903485469-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485469 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903485504-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 336 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485504 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485529-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 135 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485529 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485559-1 IN2961 | BLACK | 105D | S2408WR2400 | 131 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903485559 IN2961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903485625-1 IN8707 | BLACK | 105D | S2408WR1601A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516443 | HT SUB PROCESS_V1 | 0903485625 IN8707 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903486162-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 129 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486162 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903486211-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1218 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486211 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486240-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 743 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486240 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486327-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486327 JZ7711 | 46367 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903486390-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 817 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903486390 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903486424-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903486424 LE1842 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903486448-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 238 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903486448 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903486503-1 KB5960 | WHITE | 120D | S2608MR0900A | 159 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903486503 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903486538-1 KC8568 | BLACK | 105D | OJS26250839 | 512 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 848016 | PRINT L1 SUB PROCESS_V3 | 0903486538 KC8568 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903486574-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 588 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848016 | HT+PAD SUB PROCESS_V3 | 0903486574 KX3654 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903486601-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 207 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903486601 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903486617-1 KG3189 | MAROON | 120D | S2608MR0900A | 774 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903486617 KG3189 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903486653-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 304 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486653 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486667-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 675 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486667 LE8199 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486678-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 428 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486678 KC9082 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486695-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 174 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486695 LE8199 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486712-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 4334 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486712 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486725-1 IC5188 | BLACK | 90D | S23080640 | 146 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903486725 IC5188 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486777-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 328 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903486777 IL4127 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486778-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486778 IN2961 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903486789-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1249 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486789 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486817-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 537 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486817 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486860-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 106 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903486860 LI7659 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903486892-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 217 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486892 IN1172 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486900-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486900 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486938-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 313 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486938 IN1157 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486940-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486940 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486943-1 IC5188 | BLACK | 90D | S23080640 | 223 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903486943 IC5188 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486967-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486967 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486972-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 102 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486972 IN1172 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487011-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 500 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903487011 IL4127 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487014-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 250 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487014 IN1157 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487018-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487018 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903487045-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1000 | 15/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487045 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487057-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 897 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487057 IN1156 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487080-1 IC5189 | WHITE | 90D | S23080640 | 282 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487080 IC5189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487085-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 1152 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487085 KW2924 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903487088-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487088 IN1156 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487099-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 193 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487099 IL4127 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487117-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 792 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487117 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487139-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2460 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487139 JM1775 | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487150-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1916 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487150 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903487175-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487175 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487213-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 456 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487213 KQ8640 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903487239-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 180 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487239 LE8191 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487255-1 IP2310 | BLACK | 105D | S2450MTR701 | 600 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487255 IP2310 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903487261-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487261 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487265-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3752 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903487265 IB8686 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903487276-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 180 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487276 LE5780 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487306-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2500 | 46214 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487306 IB8688 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903487310-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 5500 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903487310 JE0052 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903487320-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487320 LE8189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903487353-1 HK7319 | BLACK | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487353 HK7319 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487361-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487361 LE5779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487397-1 HZ0747 | BLACK | 90D | F2325M414 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903487397 HZ0747 |  | KAHATEX CIJERAH | ITALY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903487403-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 210 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487403 LE8192 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487447-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487447 LE8190 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487491-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 165 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 512106 | PRINT L1 SUB PROCESS_V3 | 0903487491 LE1843 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903487543-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 666 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903487543 LE8190 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487580-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 672 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903487580 LE8191 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487621-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 450 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903487621 LE8190 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 352 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487766 KZ3200 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903487767-1 JZ7711 | BLACK | 120D | S2608MR0202 | 972 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487767 JZ7711 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903487796-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487796 KV7863 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903487864-1 JZ7709 | BLACK | 120D | S2608MR0201 | 655 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | ok |  | IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep (swicth from TRAX). T2 Y.R.C, PI Date 14-Sep, actual receives 03-Sep (swicth from TRAX). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487864 JZ7709 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903487940-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | (By Air-Collect). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487940 JZ7709 | 46367 | KAHATEX CIJERAH | AUSTRALIA | AIR-COLLECT |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903488043-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 637 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488043 LE8191 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488075-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 637 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488075 LE5780 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488135-1 JZ7709 | BLACK | 120D | S2608MR0201 | 125 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488135 JZ7709 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903488174-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 400 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903488174 LE8189 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903488196-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 219 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903488196 LH3759 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488207-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903488207 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488242-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 416 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903488242 LE5780 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488269-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 512 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903488269 LE8189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903488273-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 283 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488273 KR3066 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488304-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 450 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903488304 LE5779 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903488315-1 KD3875 | BLACK | 120D | S2608WR0201 | 300 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903488315 KD3875 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488341-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 895 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488341 KR3066 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488343-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 728 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903488343 KX3654 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903488376-1 KD3875 | BLACK | 120D | S2608WR0201 | 962 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903488376 KD3875 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488379-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 195 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 848012 | PRINT L1 SUB PROCESS_V3 | 0903488379 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488411-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 902 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903488411 JE0055 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903488465-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 60 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903488465 LI5438 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488476-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1402 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488476 KR3066 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488504-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 848012 | HT SUB PROCESS_V1 | 0903488504 KG8548 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903488561-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 275 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903488561 LI7655 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903488578-1 KD3875 | BLACK | 120D | S2608WR0201 | 2494 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903488578 KD3875 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488621-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 209 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 672027 | PAD+HT SUB PROCESS_V3 | 0903488621 LG1784 | 46367 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903488668-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 91 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903488668 LE1843 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488689-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 104 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488689 LF0725 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488715-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 52 | 46215 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903488715 LE1842 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488727-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 338 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903488727 LH3759 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488769-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 311 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903488769 LH3759 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488772-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 101 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903488772 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903488783-1 KR2011 | LIGHT GREY HEATHER | 60D | F26KCNYGFX100 | 1179 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (29/09/2026) |  | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488783 KR2011 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903488800-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 102 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903488800 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488806-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 160 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488806 IN1172 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488826-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 291 | 46215 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903488826 LE1842 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488837-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488837 LF0725 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488855-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488855 IN1172 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488870-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512108 | EMBRO SUB PROCESS_V1 | 0903488870 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488877-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 364 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903488877 LE1843 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488902-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 589 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516439 | PAD+HT SUB PROCESS_V3 | 0903488902 KZ1286 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903488910-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 260 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488910 LF0725 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488914-1 KR2013 | TEAM ROYAL BLUE | 60D | F26KCNYGFX120 | 1047 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488914 KR2013 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488933-1 KS1837 | BLACK | 60D | F26KCNYGFX120 | 272 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488933 KS1837 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488935-1 KE9656 | BLACK | 105D | S2608WR0201A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 848012 | PAD+HT SUB PROCESS_V3 | 0903488935 KE9656 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488952-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488952 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903488971-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 142 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488971 LF0725 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488989-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 594 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488989 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903489018-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 664 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | PAD+HT SUB PROCESS_V3 | 0903489018 LD0293 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903489036-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 452 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903489036 LH3759 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903489050-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 2092 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489050 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903489070-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 116 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489070 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489077-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 125 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903489077 LG1784 | 46367 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903489080-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 506 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489080 LE8192 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489083-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 317 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903489083 KZ1286 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903489098-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV | 199 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489098 JM1778 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489106-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1764 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489106 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489115-1 KA0246 | BLACK | 105D | S2608WR0902 | 375 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903489115 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489142-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 150 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489142 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903489144-1 KA0246 | BLACK | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903489144 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489152-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 400 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903489152 LE5780 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903489188-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 160 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 848012 | PRINT L1 SUB PROCESS_V3 | 0903489188 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489228-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489228 KZ3200 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903489267-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 337 | 23/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489267 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903489318-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 924 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903489318 KC6386 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903489329-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 510 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489329 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903489359-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 349 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903489359 IL4127 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903489634-1 JZ7711 | BLACK | 120D | S2608MR0202 | 9365 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489634 JZ7711 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903489679-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489679 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903489684-1 KB5965 | BLACK | 120D | S2608MR0900A | 1484 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903489684 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903489712-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 939 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489712 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489746-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489746 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903489781-1 LG8054 | LIGHT GREY HEATHER | 90D | S2762LHME151K | 168 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489781 LG8054 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE K LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489814-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 179 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489814 LG8055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489854-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489854 LI7655 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903489856-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 149 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 678002 | PRINT L1 SUB PROCESS_V3 | 0903489856 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489883-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 60 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L1 SUB PROCESS_V3 | 0903489883 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489886-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 109 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489886 LI7658 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903489914-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 314 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L1 SUB PROCESS_V3 | 0903489914 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489924-1 IN1157 | WHITE | 105D | S2408MR1600 | 304 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 516443 | HT SUB PROCESS_V1 | 0903489924 IN1157 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903489972-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903489972 JE6414 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903490017-1 KA4331 | BLACK | 90D | S2608MR0902 | 301 | 46215 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903490017 KA4331 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903490085-1 KA4331 | BLACK | 90D | S2608MR0902 | 345 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903490085 KA4331 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903490142-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490142 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903490211-1 JZ7709 | BLACK | 120D | S2608MR0201 | 125 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490211 JZ7709 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903490270-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490270 JZ7711 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903490324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 150 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903490324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490413-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1058 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490413 JZ7709 | 46367 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903490610-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 1905 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903490610 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490651-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 840 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490651 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903490660-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 109 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 672027 | PRINT L1 SUB PROCESS_V3 | 0903490660 LE1843 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903490726-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 2524 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490726 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903490766-1 KA0246 | BLACK | 105D | S2608WR0902 | 101 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903490766 KA0246 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903490854-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 2408 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490854 LE8202 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903490891-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 120 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490891 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903490983-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 205 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490983 LE8202 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903491185-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 705 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491185 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903491231-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 301 | 46215 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491231 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903491240-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 246 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491240 KG8548 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903491398-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 672 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491398 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903491513-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 103 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491513 IN1172 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491552-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 350 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825057 | PRINT L1 SUB PROCESS_V3 | 0903491552 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903491598-1 JZ7711 | BLACK | 120D | S2608MR0202 | 5645 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491598 JZ7711 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903491612-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 358 | 46215 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491612 LJ4075 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903491644-1 JZ7711 | BLACK | 120D | S2608MR0202 | 2005 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491644 JZ7711 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903491720-1 KA0246 | BLACK | 105D | S2608WR0902 | 321 | 46215 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903491720 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491769-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903491769 IN1156 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491790-1 KA0246 | BLACK | 105D | S2608WR0902 | 395 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903491790 KA0246 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491808-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 400 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903491808 JD9944 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903491821-1 KA0246 | BLACK | 105D | S2608WR0902 | 306 | 46215 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903491821 KA0246 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491835-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 570 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491835 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903491866-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 824 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491866 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903491891-1 KB5960 | WHITE | 120D | S2608MR0900A | 379 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903491891 KB5960 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903491896-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 15000 | 20/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903491896 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903491932-1 KA0246 | BLACK | 105D | S2608WR0902 | 413 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903491932 KA0246 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491960-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 800 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491960 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903491970-1 KB5965 | BLACK | 120D | S2608MR0900A | 404 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903491970 KB5965 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903492013-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492013 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903492051-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 112 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492051 LE8191 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903492057-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 488 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903492057 LI7656 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903492098-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 600 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492098 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903492176-1 JZ7711 | BLACK | 120D | S2608MR0202 | 486 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903492176 JZ7711 | 46367 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903492207-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 766 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903492207 KX3654 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903492214-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 637 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492214 LE8189 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903492245-1 KC8568 | BLACK | 105D | OJS26250839 | 357 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0090-early shipment customer (Urgent Egypt GFO - Mid August POs: Support Required for PODD Improvement on Affected POs cb_om). 512102 | PRINT L1 SUB PROCESS_V3 | 0903492245 KC8568 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903492261-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 427 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492261 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903492296-1 KB5965 | BLACK | 120D | S2608MR0900A | 144 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903492296 KB5965 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903492308-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 744 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492308 LI7657 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903492329-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 1200 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 848012 | HT SUB PROCESS_V1 | 0903492329 KG8548 | 46367 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903492373-1 KG3189 | MAROON | 120D | S2608MR0900A | 810 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903492373 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903492599-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 312 | 46215 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 806020 | PRINT L3+HT SUB PROCESS_V3 | 0903492599 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903493200-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 184 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903493200 LD0908 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903493244-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 5000 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903493244 JE0055 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903493287-1 IP2310 | BLACK | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493287 IP2310 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903493324-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493324 IW8374 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903493332-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 669 | 46215 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903493332 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903493415-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 750 | 15/12/2026 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903493415 JE6340 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903493572-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 504 | 23/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493572 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493612-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 162 | 46214 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493612 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493664-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 301 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493664 LI5438 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903493721-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 502 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825056 | PRINT L1 SUB PROCESS_V3 | 0903493721 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493751-1 JZ7711 | BLACK | 120D | S2608MR0202 | 142 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903493751 JZ7711 | 46367 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903493752-1 KR2005 | DARK BLUE | 60D | F26KCMIAGFX100 | 1200 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493752 KR2005 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493772-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 357 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493772 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493807-1 KS2151 | WHITE | 60D | F26KCLAGFX100 | 364 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493807 KS2151 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493831-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 1027 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903493831 KA6260 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903493884-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 350 | 46215 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493884 LG8052 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903493891-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1199 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493891 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493893-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 510 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903493893 LD0277 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903493941-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 400 | 46215 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/10/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493941 LG8051 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903493942-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1193 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493942 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493960-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 420 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903493960 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903493998-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903493998 LG8052 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494030-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 323 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903494030 KA6260 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903494054-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 722 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903494054 LG8055 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494105-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 762 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903494105 LG8056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494115-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 365 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 1st Art (TC 10 pcs) 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903494115 KA6260 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903494146-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 110 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903494146 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903494166-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 15000 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494166 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494205-1 KB5960 | WHITE | 120D | S2608MR0900A | 219 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516205 | HT+PAD SUB PROCESS_V3 | 0903494205 KB5960 |  | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903494218-1 LG4333 | WHITE | 90D | F2606LEMBU207MF | 12288 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494218 LG4333 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494219-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 118 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903494219 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903494261-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 194 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903494261 IN1156 | 46367 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494278-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 488 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494278 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 109 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494292 IN1172 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494356-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 1 | 15/11/2026 |  | NT | NT14/08/2026 |  | SWEATSHIRT |  |  |  | (NYK warehouse). 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903494356 KG2925 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC LF HD |  | SS27
ADIDAS | 0903494364-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 170 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494364 IN1156 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494394-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 391 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494394 LI7659 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903494489-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 163 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494489 IN1156 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494517-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 334 | 46214 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494517 IN1157 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494550-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494550 JE6419 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903494560-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 196 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494560 IN1157 | 46367 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494587-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1250 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494587 JE0055 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903494709-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 230 | 30/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3 SUB PROCESS_V3 | 0903494709 LE1858 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903494746-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 340 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3+HT SUB PROCESS_V3 | 0903494746 LE4570 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903495154-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 131 | 46214 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495154 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495200-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 124 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495200 JW9678 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903495205-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 390 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495205 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495231-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 473 | 46214 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495231 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495267-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 422 | 15/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3 SUB PROCESS_V3 | 0903495267 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495304-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495304 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495328-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 354 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825065 | PRINT L3+HT SUB PROCESS_V3 | 0903495328 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495368-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 541 | 46214 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825056 | PRINT L3+HT SUB PROCESS_V3 | 0903495368 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495389-1 IK7442 | WHITE | 105D | S2408WR2400 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495389 IK7442 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903495436-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 732 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3+HT SUB PROCESS_V3 | 0903495436 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495584-1 IN1173 | WHITE | 105D | S2408WR1600 | 390 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 800005 | HT SUB PROCESS_V1 | 0903495584 IN1173 | 46367 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903495692-1 KA6229 | BLACK | 120D | S2608WR0202 | 155 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495692 KA6229 | 46367 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903495805-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 146 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495805 KD3854 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903495847-1 KA6229 | BLACK | 120D | S2608WR0202 | 885 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495847 KA6229 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903495915-1 KA0235 | BLACK | 105D | S2608WR0901 | 373 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903495915 KA0235 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903495966-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 353 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516443 | HT SUB PROCESS_V1 | 0903495966 IN1159 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903496004-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 1300 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903496004 KY9431 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903496037-1 KA6229 | BLACK | 120D | S2608WR0202 | 7030 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496037 KA6229 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496061-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 1623 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903496061 KY9393 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903496078-1 KA6229 | BLACK | 120D | S2608WR0202 | 4363 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496078 KA6229 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496125-1 KA6229 | BLACK | 120D | S2608WR0202 | 284 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 1st Art (TC 10 pcs) 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496125 KA6229 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496214-1 KS1838 | WHITE | 60D | F26KCNYGFX130 | 370 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496214 KS1838 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496277-1 KR2014 | DARK BLUE | 60D | F26KCNYGFX130 | 1181 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496277 KR2014 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496289-1 JZ7709 | BLACK | 120D | S2608MR0201 | 388 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496289 JZ7709 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903496298-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 870 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 804028 | PRINT L3+HT SUB PROCESS_V3 | 0903496298 LE4570 | 30/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903496341-1 JZ7709 | BLACK | 120D | S2608MR0201 | 3288 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496341 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903496389-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496389 JZ7711 | 46367 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903496490-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 196 | 46215 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 834012 | PRINT L1 SUB PROCESS_V3 | 0903496490 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903497678-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1001 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903497678 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903498196-1 JZ7709 | BLACK | 120D | S2608MR0201 | 9552 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498196 JZ7709 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498235-1 JZ7709 | BLACK | 120D | S2608MR0201 | 208 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498235 JZ7709 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498251-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 216 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498251 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903498284-1 JZ7709 | BLACK | 120D | S2608MR0201 | 419 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498284 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498288-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498288 LG8055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903498314-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 140 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498314 LI7656 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903498332-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1536 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498332 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498480-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 216 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903498480 LD0908 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498515-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 800 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903498515 LD0908 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498576-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 115 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498576 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903499076-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 112 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0903499076 KX3654 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903499118-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 317 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903499118 KX3654 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903499304-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1938 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499304 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499328-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 2068 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499328 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499369-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 554 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499369 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499422-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 1590 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499422 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499455-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 745 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499455 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499530-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 159 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499530 JD9944 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903499545-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 454 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499545 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499689-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 235 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903499689 LE8181 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903499724-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 154 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499724 KZ3199 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903499807-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 926 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499807 KZ3199 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903499822-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 3500 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499822 JE6417 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903499855-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 101 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499855 KZ3200 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903499864-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903499864 JP1528 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903499919-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 1750 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903499919 KD9849 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903499962-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 1203 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903499962 LE1842 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903499969-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499969 JE6414 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903499998-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2987 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903499998 LE1843 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500013-1 IS1413 | BLACK | 60D | S2425M405 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903500013 IS1413 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903500034-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 323 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903500034 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500077-1 LH2842 | BLACK | 90D | S2725M993 | 535 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903500077 LH2842 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903500135-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 193 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (04/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 27-Sep. Waiting fabric. T2 Libolon, PI Date 04-Sep. 839055 | PAD+HT SUB PROCESS_V3 | 0903500135 IT3474 | 46367 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903501707-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 176 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501707 KZ3200 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903501742-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 137 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903501742 JD9944 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903501887-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 108 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903501887 JD9944 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903501929-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 274 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501929 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903501964-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839055 | HT+PAD SUB PROCESS_V3 | 0903501964 KX3655 | 46367 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903502116-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 230 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502116 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903502119-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 144 | 15/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 848024 | PRINT L3+HT SUB PROCESS_V3 | 0903502119 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903502153-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 725 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903502153 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903502154-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 424 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502154 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903502308-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 1469 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502308 KY9383 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-L2L
ADIDAS | 0903502411-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 391 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502411 KY9384 | 46367 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903502498-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1867 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502498 KY9384 | 46367 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903504182-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 301 | 46215 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903504182 KV7863 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903504266-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 664 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903504266 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903504351-1 IC5188 | BLACK | 90D | S23080640 | 308 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | HT SUB PROCESS_V1 | 0903504351 IC5188 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903504660-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 328 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903504660 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903506204-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 459 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903506204 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903530511-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 594 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903530511 LE5779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903530910-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 560 | 46215 |  | AN | AN18/08/2026 |  | SHORTS |  | (15/09/2026) |  | MOQ Issue 806020 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903530910 KW2924 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903530911-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 824 | 15/11/2026 |  | AN | AN18/08/2026 |  | JACKET |  | (15/09/2026) |  | MOQ Issue 806020 | EMBRO SUB PROCESS_V1 | 0903530911 KW6443 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903530914-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 522 | 15/12/2026 |  | SI | SI18/08/2026 |  | PANTS |  |  |  | 806020 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903530914 KZ3200 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903535007-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 100 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535007 KC8152 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903535008-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 539 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535008 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903541106-1 KS7771 | MEDIUM GREY HEATHER/WHITE | 90D | S26AAWVL320 | 6000 | 46215 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (10/10/2026) |  | 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903541106 KS7771 | 46306 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE MEDIUM GREY HEATHER/WHITE |  | SS27
ADIDAS | 0903541995-1 IN8707 | BLACK | 105D | S2408WR1601A | 100 | 15/12/2026 | 100 | SI | SI28/08/2026 | G1E | SHORTS | G1 | (30/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903541995 IN8707 | 24/11/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/11/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 100 |  | 100 |  |  | 46337 | 46367 |  |  | 100 |  | 100 |  |  | 46306 | 46337 |  |  | 100 |  | 100
ADIDAS | 0903542087-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 996 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903542087 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903542128-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 106 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903542128 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903542656-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 150 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542656 LG8616 | 46306 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903542705-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 400 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542705 LL1875 | 46306 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903542903-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 155 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903542903 IU0217 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903544641-1 LE8198 | WHITE/BLACK | 90D | F2606LHJT101MF | 1271 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | MOQ Issue 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903544641 LE8198 | 46306 | KAHATEX CIJERAH | MALAYSIA | SEA |  | JUVE H F JSY SE |  | SS27-FJ
ADIDAS | 0903544653-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 377 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903544653 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903545542-1 IN8707 | BLACK | 105D | S2408WR1601A | 320 | 15/12/2026 | 320 | SI | SI28/08/2026 | G1E | SHORTS | G1 | (30/10/2026) |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903545542 IN8707 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/11/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 320 |  | 320 |  |  | 46337 | 46367 |  |  | 320 |  | 320 |  |  | 46306 | 46337 |  |  | 320 |  | 320
ADIDAS | 0903545628-1 IN8707 | BLACK | 105D | S2408WR1601A | 125 | 15/12/2026 | 125 | SI | SI28/08/2026 | G1E | SHORTS | G1 | (30/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 830009 | HT SUB PROCESS_V1 | 0903545628 IN8707 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/11/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 125 |  | 125 |  |  | 46337 | 46367 |  |  | 125 |  | 125 |  |  | 46306 | 46337 |  |  | 125 |  | 125
ADIDAS | 0903546102-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 245 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903546102 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903546294-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 2 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903546294 LG8616 | 46306 | KAHATEX CIJERAH | CHINA | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903547005-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 526 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903547005 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903547557-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 478 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903547557 IB8686 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903547607-1 HZ0747 | BLACK | 90D | F2325M414 | 200 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903547607 HZ0747 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | PL TEE |  | SS27
ADIDAS | 0903547791-1 IN1172 | BLACK | 105D | S2408WR1600 | 107 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516333 | HT SUB PROCESS_V1 | 0903547791 IN1172 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903547839-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 158 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516471 | HT SUB PROCESS_V1 | 0903547839 IT1469 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903547870-1 IN1157 | WHITE | 105D | S2408MR1600 | 541 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516342 | HT SUB PROCESS_V1 | 0903547870 IN1157 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903548095-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 129 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903548095 KX0123 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903548305-1 IS1413 | BLACK | 60D | S2425M405 | 175 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903548305 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548338-1 IN2961 | BLACK | 105D | S2408WR2400 | 159 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (05/10/2026) |  | 800005 | HT SUB PROCESS_V1 | 0903548338 IN2961 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903548343-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 190 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903548343 IU0217 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548385-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 500 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903548385 IU0217 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548428-1 IS1413 | BLACK | 60D | S2425M405 | 501 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903548428 IS1413 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548466-1 IS1413 | BLACK | 60D | S2425M405 | 381 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903548466 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548545-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 306 | 46215 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903548545 LG8616 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903549325-1 HZ0747 | BLACK | 90D | F2325M414 | 982 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903549325 HZ0747 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903549793-1 KA0246 | BLACK | 105D | S2608WR0902 | 863 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903549793 KA0246 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549825-1 KA0246 | BLACK | 105D | S2608WR0902 | 410 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903549825 KA0246 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549866-1 KA0246 | BLACK | 105D | S2608WR0902 | 663 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903549866 KA0246 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549945-1 KA0246 | BLACK | 105D | S2608WR0902 | 332 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903549945 KA0246 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903550013-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 543 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903550013 KA2571 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903550204-1 HZ0747 | BLACK | 90D | F2325M414 | 269 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903550204 HZ0747 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | PL TEE |  | SS27
ADIDAS | 0903550242-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1086 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550242 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903550415-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 310 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550415 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903550456-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 528 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550456 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903551300-1 HZ0747 | BLACK | 90D | F2325M414 | 789 | 46215 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903551300 HZ0747 |  | KAHATEX CIJERAH | THAILAND | SEA |  | PL TEE |  | SS27
ADIDAS | 0903551497-1 HZ0747 | BLACK | 90D | F2325M414 | 197 | 46215 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903551497 HZ0747 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | PL TEE |  | SS27
ADIDAS | 0903551593-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 206 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903551593 HB7455 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903552136-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 404 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903552136 LD0278 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903552747-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 174 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903552747 HB7455 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903552812-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 189 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903552812 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903553779-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 891 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903553779 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903553825-1 IN2961 | BLACK | 105D | S2408WR2400 | 143 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (05/10/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903553825 IN2961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903553958-1 IN8707 | BLACK | 105D | S2408WR1601A | 424 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 814006 | HT SUB PROCESS_V1 | 0903553958 IN8707 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903554171-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 120 | 46215 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516343 | PAD+HT SUB PROCESS_V3 | 0903554171 LD0278 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903554207-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554207 LL1875 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903554250-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554250 LL1874 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903555046-1 IN1172 | BLACK | 105D | S2408WR1600 | 118 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 547012 | HT SUB PROCESS_V1 | 0903555046 IN1172 | 24/11/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903555100-1 KC8568 | BLACK | 105D | OJS26250839 | 1296 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 848012 | PRINT L1 SUB PROCESS_V3 | 0903555100 KC8568 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903555134-1 KC8568 | BLACK | 105D | OJS26250839 | 1072 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 848024 | PRINT L1 SUB PROCESS_V3 | 0903555134 KC8568 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903555193-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 265 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903555193 KX9851 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903555271-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 1437 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903555271 LD0294 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903555378-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 300 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555378 KZ3198 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555407-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 615 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555407 KZ3205 | 46306 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555925-1 HZ0747 | BLACK | 90D | F2325M414 | 2301 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903555925 HZ0747 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903555985-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 3501 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | PAD+HT SUB PROCESS_V3 | 0903555985 IN0089 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903556026-1 IP2310 | BLACK | 105D | S2450MTR701 | 3000 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903556026 IP2310 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903556061-1 IP2310 | BLACK | 105D | S2450MTR701 | 4001 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903556061 IP2310 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903556107-1 IS1413 | BLACK | 60D | S2425M405 | 3000 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903556107 IS1413 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903556277-1 JC8165 | WONDER ALUMINA S25/WHITE | 90D | S2554WES421WV | 223 | 46215 |  | SI | SI28/08/2026 |  | SHORTS |  |  |  | MOQ Issue 830009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903556277 JC8165 | 46306 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903556341-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903556341 IL7232 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903556385-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 206 | 46214 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903556385 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903558146-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 2400 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903558146 IU0217 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903558188-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 2501 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903558188 IW8374 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903558231-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558231 JC9346 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558277-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 385 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558277 JC9346 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558320-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558320 JE6414 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558358-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558358 JE6417 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558397-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 661 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558397 JE6419 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558412-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 110 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903558412 KD0738 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903558444-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 5339 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558444 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558463-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 2222 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903558463 LD0907 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903558476-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558476 JE6417 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558515-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558515 JE6419 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558517-1 KA0235 | BLACK | 105D | S2608WR0901 | 110 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903558517 KA0235 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903558541-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 303 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | PAD+HT SUB PROCESS_V3 | 0903558541 LD0909 |  | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903558557-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558557 JE9012 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558600-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 386 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558600 JE9012 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558613-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903558613 KA0235 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903559131-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 351 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903559131 KA2571 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903560689-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 582 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903560689 KZ2988 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903560866-1 JD0957 | BLACK | 60D | S25ORISW311 | 140 | 15/11/2026 |  | ID | ID28/08/2026 |  | SHORTS |  | (30/09/2026) |  | 980004 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903560866 JD0957 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADIC SWIMSH 5IN |  | SS27
ADIDAS | 0903561185-1 IN1172 | BLACK | 105D | S2408WR1600 | 395 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 684009 | HT SUB PROCESS_V1 | 0903561185 IN1172 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903561217-1 IN1173 | WHITE | 105D | S2408WR1600 | 406 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 684009 | HT SUB PROCESS_V1 | 0903561217 IN1173 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903562067-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 413 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 659018 | PAD+HT SUB PROCESS_V3 | 0903562067 LD0278 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903562117-1 KA0235 | BLACK | 105D | S2608WR0901 | 622 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 659018 | PAD+HT SUB PROCESS_V3 | 0903562117 KA0235 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903562365-1 KA4331 | BLACK | 90D | S2608MR0902 | 412 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | PAD+HT SUB PROCESS_V3 | 0903562365 KA4331 |  | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903562644-1 IN1172 | BLACK | 105D | S2408WR1600 | 887 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903562644 IN1172 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564682-1 IN1159 | BLACK | 90D | S2408MR1601 | 1539 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903564682 IN1159 |  | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903564726-1 IN1173 | WHITE | 105D | S2408WR1600 | 589 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564726 IN1173 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564763-1 IN1157 | WHITE | 105D | S2408MR1600 | 454 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564763 IN1157 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564830-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 2340 | 30/11/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903564830 KD9849 |  | KAHATEX CIJERAH | MEXICO | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903564907-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 714 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564907 IT1469 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903565184-1 IN1173 | WHITE | 105D | S2408WR1600 | 3 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903565184 IN1173 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903565260-1 IN1157 | WHITE | 105D | S2408MR1600 | 472 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903565260 IN1157 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903566142-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 4 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903566142 KZ0028 | 46306 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903566172-1 JD0957 | BLACK | 60D | S25ORISW311 | 1200 | 46215 |  | ID | ID28/08/2026 |  | SHORTS |  | (30/09/2026) |  | 823016 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903566172 JD0957 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ADIC SWIMSH 5IN |  | SS27
ADIDAS | 0903566214-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903566214 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903567116-1 IN1172 | BLACK | 105D | S2408WR1600 | 1453 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903567116 IN1172 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903567234-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 239 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567234 LE8190 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567294-1 IL7232 | BLACK | 105D | S2408MR3202 | 126 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903567294 IL7232 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903567332-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1976 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567332 LE8190 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567429-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 211 | 46215 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567429 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567468-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 3500 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516318 | PAD+HT SUB PROCESS_V3 | 0903567468 KA0247 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903567514-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 301 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516204 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567514 KA4913 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567535-1 KA0246 | BLACK | 105D | S2608WR0902 | 111 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903567535 KA0246 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903567549-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 4000 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567549 KA4913 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567578-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 2395 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567578 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567590-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 1201 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567590 KA4913 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567620-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 1910 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567620 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567630-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 301 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516204 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567630 KA4914 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567986-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 390 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903567986 KV7863 |  | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903568176-1 IN8707 | BLACK | 105D | S2408WR1601A | 144 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 848012 | HT SUB PROCESS_V1 | 0903568176 IN8707 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569208-1 IN1173 | WHITE | 105D | S2408WR1600 | 1052 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569208 IN1173 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569251-1 KA4331 | BLACK | 90D | S2608MR0902 | 526 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903569251 KA4331 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903569338-1 IN1157 | WHITE | 105D | S2408MR1600 | 1803 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569338 IN1157 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569377-1 IN1159 | BLACK | 90D | S2408MR1601 | 1365 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 672027 | HT SUB PROCESS_V1 | 0903569377 IN1159 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569427-1 IN8707 | BLACK | 105D | S2408WR1601A | 836 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 672027 | HT SUB PROCESS_V1 | 0903569427 IN8707 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569472-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 547 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569472 IT1469 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569590-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 385 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903569590 JE0055 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903569610-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 46215 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903569610 KV7863 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903569670-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 1200 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903569670 KA4914 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903569709-1 KC8559 | WHITE | 105D | OJS26250838 | 2400 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903569709 KC8559 |  | KAHATEX CIJERAH | GERMANY | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903569748-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1300 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569748 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569785-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569785 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569826-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 2499 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903569826 HK7303 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903570113-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 155 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903570113 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903570120-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2976 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903570120 KV7863 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903570368-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 424 | 46215 |  | SI | SI28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903570368 JC9584 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903571229-1 KA4331 | BLACK | 90D | S2608MR0902 | 764 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903571229 KA4331 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903571671-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 300 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 400147 | PRINT L1 SUB PROCESS_V3 | 0903571671 LG8616 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903571753-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 328 | 15/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571753 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903571791-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 290 | 30/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571791 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903572059-1 KA4331 | BLACK | 90D | S2608MR0902 | 327 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572059 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572081-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572081 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572124-1 KA4331 | BLACK | 90D | S2608MR0902 | 1163 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572124 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572145-1 KA4331 | BLACK | 90D | S2608MR0902 | 639 | 46215 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572145 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572154-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1052 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903572154 KV7863 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903572157-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 119 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903572157 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903572221-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 833 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903572221 KZ3198 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903572804-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 902 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903572804 LL1875 | 46306 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903572864-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 180 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  |  |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903572864 LL1875 | 46306 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903573116-1 KA4331 | BLACK | 90D | S2608MR0902 | 188 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903573116 KA4331 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903573217-1 IN1159 | BLACK | 90D | S2408MR1601 | 311 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 678002 | HT SUB PROCESS_V1 | 0903573217 IN1159 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903573341-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 2879 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903573341 LD0278 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903573350-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 2496 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903573350 KA2571 | 24/11/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903573378-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 1555 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903573378 LD0909 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903573381-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 2496 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903573381 KD0738 | 24/11/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903573403-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 2333 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 652001 | PAD+HT SUB PROCESS_V3 | 0903573403 KA0237 |  | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903573411-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 1042 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903573411 LD0907 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903573434-1 KA0246 | BLACK | 105D | S2608WR0902 | 500 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | PAD+HT SUB PROCESS_V3 | 0903573434 KA0246 |  | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903573458-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 2340 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903573458 HB7455 |  | KAHATEX CIJERAH | MEXICO | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903573472-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 786 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903573472 KZ3205 | 46306 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903574124-1 IN1159 | BLACK | 90D | S2408MR1601 | 318 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903574124 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903574442-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 6000 | 46215 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903574442 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27
ADIDAS | 0903574568-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 46215 |  | AN | AN28/08/2026 |  | PANTS |  | (26/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903574568 LE7509 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903574589-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 425 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 814006 | EMBRO SUB PROCESS_V1 | 0903574589 KD9094 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903574668-1 KA4331 | BLACK | 90D | S2608MR0902 | 968 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903574668 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903574807-1 KG8547 | ONIX | 105D | S2408WR1600 | 579 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903574807 KG8547 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903574863-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 800187 | PAD+HT SUB PROCESS_V3 | 0903574863 KA4331 | 46306 | KAHATEX CIJERAH | VIETNAM | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 100 |  | 100 |  |  | 14/11/2026 | 16/11/2026 |  |  | 100 |  | 100 |  |  | 13/11/2026 | 14/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903574889-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 830009 | PAD+HT SUB PROCESS_V3 | 0903574889 KA4331 | 46306 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 100 |  | 100 |  |  | 14/11/2026 | 16/11/2026 |  |  | 100 |  | 100 |  |  | 13/11/2026 | 14/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903575054-1 IN1157 | WHITE | 105D | S2408MR1600 | 683 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 678002 | HT SUB PROCESS_V1 | 0903575054 IN1157 | 24/11/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903576131-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 500 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903576131 KZ0922 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903576180-1 IN1159 | BLACK | 90D | S2408MR1601 | 730 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516333 | HT SUB PROCESS_V1 | 0903576180 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903576204-1 IN1159 | BLACK | 90D | S2408MR1601 | 357 | 46215 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT SUB PROCESS_V1 | 0903576204 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903576238-1 IN1159 | BLACK | 90D | S2408MR1601 | 226 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516471 | HT SUB PROCESS_V1 | 0903576238 IN1159 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903577174-1 IC5188 | BLACK | 90D | S23080640 | 375 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903577174 IC5188 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903577190-1 IC5188 | BLACK | 90D | S23080640 | 125 | 46215 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903577190 IC5188 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903577664-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 716 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903577664 KZ0922 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903578729-1 KA4331 | BLACK | 90D | S2608MR0902 | 625 | 30/11/2026 | 625 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 1st Art (TC 10 pcs) 516394 | PAD+HT SUB PROCESS_V3 | 0903578729 KA4331 | 46306 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 19/11/2026 |  |  | 625 |  | 625 |  |  | 14/11/2026 | 16/11/2026 |  |  | 625 |  | 625 |  |  | 13/11/2026 | 14/11/2026 |  |  | 625 |  | 625
ADIDAS | 0903578772-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 7 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516029 | PRINT L1 SUB PROCESS_V3 | 0903578772 LI6133 | 46306 | KAHATEX CIJERAH | GERMANY | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903578813-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 4673 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516027 | PRINT L1 SUB PROCESS_V3 | 0903578813 LI6133 | 46306 | KAHATEX CIJERAH | BRAZIL | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903580788-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 458 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580788 KZ3200 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903580940-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 369 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580940 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903580989-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1772 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580989 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 416 | 46215 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581028 KV7863 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581080-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 305 | 46215 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581080 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581132-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1657 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581132 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903582940-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1357 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903582940 KV7863 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903583205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 608 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903583205 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903595557-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 643 | 30/11/2026 |  | SI | SI03/09/2026 |  | T-SHIRT |  | (10/10/2026) |  | 857010 | PRINT L1 SUB PROCESS_V3 | 0903595557 LE1843 | 16/11/2026 | KAHATEX CIJERAH | INDIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903595627-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 666 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903595627 KC8152 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903595632-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 736 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903595632 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598944-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 314 | 14/11/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598944 KC8152 | 27/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598947-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 107 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 516394 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598947 KC8152 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598950-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 209 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598950 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598954-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 495 | 14/11/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598954 KC8152 | 27/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598958-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 139 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598958 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598960-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1179 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598960 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903600165-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 254 | 46214 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903600165 KY6510 | 46244 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903600283-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 177 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600283 LI2646 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600284-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 162 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600284 LI2667 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600285-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 324 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600285 LI2668 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600286-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 201 | 46214 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600286 LI2646 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600287-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 132 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600287 LI2670 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600288-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 155 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600288 LI2670 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600289-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 194 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600289 LI2668 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600290-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 126 | 46214 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600290 LI2667 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600291-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 157 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600291 LI2671 | 46303 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903600292-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 137 | 46214 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600292 LI2671 | 46303 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903608631-1 IS1413 | BLACK | 60D | S2425M405 | 572 | 46215 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903608631 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610429-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 496 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903610429 IU0217 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610455-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 100 | 46214 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903610455 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903610469-1 IS1413 | BLACK | 60D | S2425M405 | 526 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903610469 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610504-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 100 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610504 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610537-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 203 | 30/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610537 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610563-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 257 | 46214 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903610563 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903610597-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 348 | 46215 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903610597 KB5960 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610624-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 220 | 46215 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 814006 | PAD+HT SUB PROCESS_V3 | 0903610624 KA0235 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903610638-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 305 | 46215 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903610638 KB5960 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610663-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 518 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903610663 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903611060-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 180 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | MOQ Issue 516254 | HT SUB PROCESS_V1 | 0903611060 KX9851 | 46337 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903611230-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 150 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 630001 | PRINT L3 SUB PROCESS_V3 | 0903611230 LZ9161 | 46337 | KAHATEX CIJERAH | CANADA | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 0903611417-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 652 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611417 KA0544 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611448-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 125 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903611448 LJ4075 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903611450-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 592 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611450 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611477-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 846 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611477 LE8192 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903611492-1 IN1159 | BLACK | 90D | S2408MR1601 | 1212 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516254 | HT SUB PROCESS_V1 | 0903611492 IN1159 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903611507-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 522 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611507 LE8192 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903611531-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611531 KA0544 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611537-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 300 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611537 KA5088 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611554-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1682 | 15/12/2026 |  | SA | SA11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903611554 JE6338 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903611561-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611561 KA0546 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611568-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 2669 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611568 KA5090 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611584-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 1542 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903611584 JE0052 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903611604-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 2492 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611604 KA5089 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611616-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2873 | 15/12/2026 |  | SA | SA11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903611616 JD1877 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903611635-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 308 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611635 KA5089 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611652-1 HK2890 | BLACK | 90D | F2225M270 | 2 | 14/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 825054 | HT+PPH L1 SUB PROCESS_V3 | 0903611652 HK2890 |  | KAHATEX CIJERAH | CHINA | SEA |  | C TEE |  | SS27
ADIDAS | 0903611729-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 100 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 857010 | PRINT L3 SUB PROCESS_V3 | 0903611729 LZ9161 | 46337 | KAHATEX CIJERAH | INDIA | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 0903612070-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 532 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612070 JE0052 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903612091-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 652001 | HT SUB PROCESS_V1 | 0903612091 IT1467 |  | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903612328-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 181 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903612328 LJ4073 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903612449-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 1080 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848012 | EMBRO SUB PROCESS_V1 | 0903612449 HK7303 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612487-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1080 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848012 | EMBRO SUB PROCESS_V1 | 0903612487 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612500-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2750 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L3 SUB PROCESS_V3 | 0903612500 LZ9161 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 0903612510-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1224 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612510 KD4872 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612512-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 238 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516471 | HT SUB PROCESS_V1 | 0903612512 IT1467 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903612524-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 300 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903612524 LJ4074 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903612540-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 900 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848024 | EMBRO SUB PROCESS_V1 | 0903612540 HK7303 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612561-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 900 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848024 | EMBRO SUB PROCESS_V1 | 0903612561 IB8686 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612582-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 269 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 512106 | PRINT L3 SUB PROCESS_V3 | 0903612582 LZ9161 | 46337 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 0903612596-1 IN1159 | BLACK | 90D | S2408MR1601 | 352 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903612596 IN1159 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903612668-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 200 | 46215 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 800187 | PAD+HT SUB PROCESS_V3 | 0903612668 KA0235 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903612689-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 157 | 15/12/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903612689 KB5961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612720-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 402 | 46215 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903612720 KE8424 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903612744-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 500 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612744 KD4872 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612815-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 132 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903612815 LE1843 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903612816-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 350 | 46215 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612816 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612835-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1008 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612835 KD4872 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612849-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 203 | 30/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903612849 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903612868-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 311 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 652001 | PRINT L1 SUB PROCESS_V3 | 0903612868 LE1843 | 46337 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903612871-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 442 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612871 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612931-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 368 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612931 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612957-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 220 | 30/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612957 KA6229 | 23/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903612972-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903612972 JZ7775 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903612977-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 201 | 46215 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612977 KA6229 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903612991-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903612991 KA4331 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903613004-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 173 | 15/11/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903613004 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903613017-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 790 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 630001 | EMBRO SUB PROCESS_V1 | 0903613017 KD3911 |  | KAHATEX CIJERAH | CANADA | SEA |  | RELEASED |  | SS27
ADIDAS | 0903613111-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 513 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903613111 LZ9161 | 46337 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 0903613123-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903613123 LD0278 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903613410-1 LL3375 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS422WV | 720 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903613410 LL3375 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903613500-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 114 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903613500 LJ4073 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903613504-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2671 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613504 JE6419 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903613540-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 4449 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613540 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903613548-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 101 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903613548 LJ4075 | 46337 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903613575-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613575 JE6417 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903613612-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 551 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613612 JE6414 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903613665-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 1700 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613665 KA5088 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903613678-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 497 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903613678 JC5282 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M L SLIDE PKT T |  | SS27
ADIDAS | 0903613692-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 329 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613692 KA5090 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903613721-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1098 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613721 KD4872 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903613777-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 8900 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613777 KD4872 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903614230-1 HK7309 | BLACK | 45D | F2225M402 | 2400 | 46214 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614230 HK7309 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903614355-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 210 | 46215 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614355 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903614477-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 101 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614477 KB5961 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903614507-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 116 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903614507 LJ4073 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903614548-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 172 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903614548 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903614550-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 148 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903614550 JE6419 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903614552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 301 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614552 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903614583-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 247 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614583 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903614597-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903614597 KA5088 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903614654-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 300 | 15/12/2026 |  | AN | AN11/09/2026 |  | T-SHIRT |  |  |  | 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903614654 LC8884 |  | KAHATEX CIJERAH | CANADA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903614843-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 200 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614843 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903615339-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 285 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615339 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903615648-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1700 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615648 JE6417 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903615680-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 330 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615680 JE6419 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903615732-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 101 | 15/12/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903615732 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903615872-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 120 | 46214 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903615872 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903616174-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 308 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516342 | HT SUB PROCESS_V1 | 0903616174 IT1467 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903617338-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 124 | 15/12/2026 |  | AN | AN11/09/2026 |  | SHORTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903617338 KW2924 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903617380-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 299 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617380 LJ4073 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903617441-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 201 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617441 LJ4075 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903617477-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 206 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617477 LJ4074 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903624240-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 580 | 46215 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516342 | PRINT L3 SUB PROCESS_V3 | 0903624240 IU0217 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903626403-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 751 | 15/11/2026 |  | SI | SI11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626403 LJ2754 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903626428-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 751 | 15/11/2026 |  | SA | SA11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626428 LE4570 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903627485-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 3037 | 15/12/2026 |  | SI | SI11/09/2026 |  | PANTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903627485 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903627519-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 348 | 15/12/2026 |  | SI | SI11/09/2026 |  | PANTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903627519 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903637773-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 567 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L3 SUB PROCESS_V3 | 0903637773 LZ9161 | 46337 | KAHATEX CIJERAH | GERMANY | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 4501928388-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 14/11/2026 |  | ID | ID29/05/2026 |  | SKIRT |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928388 LG9668 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 4502065732-2 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 14/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) |  | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066730-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 30 | 21/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502066730 KX7716 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066730-2 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 14/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 28-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502066730 KX7716 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066741-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 926 | 46215 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066741 KX3655 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 4502066741-2 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1135 | 14/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066741 KX3655 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 4502066831-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 171 | 14/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502066831 LF0729 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 4502066844-2 KB5965 | BLACK | 120D | S2608MR0900A | 100 | 14/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066844-3 KB5965 | BLACK | 120D | S2608MR0900A | 100 | 46215 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066850-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 327 | 14/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066850 KX3654 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 4502066871-2 KE8424 | BLACK | 120D | S2608MR0906A | 100 | 14/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 4502066873-2 KB5960 | WHITE | 120D | S2608MR0900A | 72 | 46214 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066873-3 KB5960 | WHITE | 120D | S2608MR0900A | 385 | 21/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502069351-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502069351 LI2667 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 4502070211-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 193 | 14/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070211 LF0721 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 4502070409-2 LF0718 | BLACK | 105D | S2754MAS512B | 50 | 14/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 4502070657-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070657 LI2670 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 4502070658-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070658 LI2671 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 4502070659-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070659 LI2645 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 4502070898-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070898 LI2669 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 4502070899-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070899 LI2646 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 4502070901-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070901 LI2647 | 46303 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 4502075076-1 KT4840 | ONIX | 90D | S2408MR1600 | 859 | 21/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075076 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 4502075079-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 46214 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075079 KR3066 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502075080-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 260 | 21/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502075080 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 4502075930-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 140 | 14/11/2026 |  | AN | AN30/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? ZA30 | PRINT L2+HT SUB PROCESS_V3 | 4502075930 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 4502076909-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 46214 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502076909-2 JZ7709 | BLACK | 120D | S2608MR0201 | 300 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502077373-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 46214 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077373-2 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 14/11/2026 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077374-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1193 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502077374 KY9384 | 46032 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 4502347325-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 249 | 14/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4502347325 LH3760 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 4502347613-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1094 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347613 JZ7709 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502347613-2 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 46215 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347613 JZ7709 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502347632-1 JZ7711 | BLACK | 120D | S2608MR0202 | 130 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347632 JZ7711 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 4502348815-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 116 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502348815 KR3066 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502349090-1 KD3875 | BLACK | 120D | S2608WR0201 | 142 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502349090 KD3875 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 4502349403-1 KA6229 | BLACK | 120D | S2608WR0202 | 112 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349403 KA6229 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502349501-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 141 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349501 JZ7715 | 46244 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502364155-1 KZ4389 | WHITE | 120D | F2608MR1500 | 15 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. ZA30 | PAD+HT SUB PROCESS_V3 | 4502364155 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 4502364164-1 KZ4388 | BLACK | 120D | F2608MR1500 | 15 | 15/12/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Men Chuen, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502364164 KZ4388 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M BLACK |  | SS27-TRAX
ADIDAS | 4502368096-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 169 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502368096 KY9391 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 4502368741-1 JZ7709 | BLACK | 120D | S2608MR0201 | 208 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502368741 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 4502369618-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 15 | 14/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue ZA30 | PAD+HT SUB PROCESS_V3 | 4502369618 KV0333 | 46367 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 4502369661-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 14/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4502369661 LH3759 |  | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 4502369662-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 251 | 21/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | ZA30 | PRINT L1 SUB PROCESS_V3 | 4502369662 LE1843 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 4502369990-1 KA6229 | BLACK | 120D | S2608WR0202 | 1 | 14/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502369990 KA6229 | 46367 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502370031-1 JZ7711 | BLACK | 120D | S2608MR0202 | 56 | 14/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 1st Art (TC 10 pcs) ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502370031 JZ7711 | 46367 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 4502374523-1 KA6229 | BLACK | 120D | S2608WR0202 | 867 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502374523 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502374524-1 KA6229 | BLACK | 120D | S2608WR0202 | 2969 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502374524 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502375402-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2 | 14/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | ZA30 | PRINT L1 SUB PROCESS_V3 | 4502375402 LE1843 | 46337 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | OFC-07092026-013 | MULTI COLOR | 45D | F2225M402 | 465 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-013 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-017 | MULTI COLOR | 90D | F2225M403 | 400 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-017 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-021 | MULTI COLOR | 90D | F2325M414 | 11 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-021 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-025 | MULTI COLOR | 75D | F2325M421 | 360 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPS SUB PROCESS_V3 | OFC-07092026-025 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-026 | MULTI COLOR | 105D | F2408MR1606 | 709 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-026 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-033 | MULTI COLOR | 45D | F24KLKGFX003 | 2546 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-033 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-034 | MULTI COLOR | 45D | F24KLKGFX003 | 5 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-034 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-035 | MULTI COLOR | 60D | F2525M432 | 594 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-035 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-036 | MULTI COLOR | 60D | F2550WTR422 | 4 | 15/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L3+PAD+HT SUB PROCESS_V3 | OFC-07092026-036 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-037 | MULTI COLOR | 90D | F2554MESS710WV | 90 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-037 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-038 | MULTI COLOR | 90D | F2554MESS710WV | 600 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-038 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-040 | MULTI COLOR | 30D | F25GFXBLANKM | 5909 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-040 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-044 | MULTI COLOR | 60D | F25KIUGFX010 | 1697 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-044 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-045 | MULTI COLOR | 60D | F25KIUGFX010 | 5948 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-045 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-049 | MULTI COLOR | 60D | F25KLKGFX011 | 178 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-049 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-050 | MULTI COLOR | 60D | F25KLKGFX011 | 150 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-050 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-055 | MULTI COLOR | 60D | F25SPRMGFX040 | 1166 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-055 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-056 | MULTI COLOR | 60D | F25SPRMGFX041 | 419 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-056 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-057 | MULTI COLOR | 105D | F25SSW0313 | 5 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-057 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1005 | MULTI COLOR | 90D | S2762LHAMG125 | 503 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1005 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1009 | MULTI COLOR | 90D | S2762LHAMG130 | 301 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1009 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1013-B | MULTI COLOR | 105D | S2762LHAMG135-B | 20 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1013-B |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1013-T | MULTI COLOR | 105D | S2762LHAMG135 | 20 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1013-T |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1016 | MULTI COLOR | 90D | S2762LHAU1410M | 357 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1016 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1075 | MULTI COLOR | 90D | S2762LHME145M | 300 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1075 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1076 | MULTI COLOR | 90D | S2762LHME146M | 300 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1076 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1077 | MULTI COLOR | 90D | S2762LHME150M | 170 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1077 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1078 | MULTI COLOR | 90D | S2762LHME151K | 132 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1078 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1079 | MULTI COLOR | 90D | S2762LHME152M | 300 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1079 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1080 | MULTI COLOR | 90D | S2762LHMEDR103M | 300 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1080 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1083 | MULTI COLOR | 90D | S2762LHMEDR106K | 255 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1083 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1088 | MULTI COLOR | 90D | S2762LHMEDR107M | 300 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1088 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-110 | MULTI COLOR | 90D | F2606LHAF101MF | 144 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-110 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1105 | MULTI COLOR | 90D | S2762LHMEKA201M | 6 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1105 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-111 | MULTI COLOR | 90D | F2606LHAF101YF | 229 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-111 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-112 | MULTI COLOR | 90D | F2606LHBM101MF | 478 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-112 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1130 | MULTI COLOR | 60D | S27FBGFXP101 | 355 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1130 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1131 | MULTI COLOR | 60D | S27FBGFXP102 | 318 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1132 | MULTI COLOR | 60D | S27FBGFXP102 | 181 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1132 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1135 | MULTI COLOR | 60D | S27FBGFXP510 | 171 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1135 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1136 | MULTI COLOR | 60D | S27FBGFXP510 | 1054 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1136 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1137 | MULTI COLOR | 60D | S27FBGFXP510 | 268 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1137 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1139 | MULTI COLOR | 60D | S27FBGFXP600 | 324 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1139 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-114 | MULTI COLOR | 90D | F2606LHLF101FY | 238 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-114 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1142 | MULTI COLOR | 90D | S27SPRMGFXP0600 | 210 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-1142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1143 | MULTI COLOR | 90D | S27SPRMGFXP0800 | 74 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1143 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1144 | MULTI COLOR | 90D | S27SPRMGFXP0900 | 442 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-1144 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-115 | MULTI COLOR | 90D | F2606LHLF101FYL | 244 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-115 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-116 | MULTI COLOR | 90D | F2606LHLF101MFL | 880 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-116 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1176 | MULTI COLOR | 60D | S2762LHAU334 | 564 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1176 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1177 | MULTI COLOR | 60D | S2762LHAU334 | 340 | 15/12/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1177 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-118 | MULTI COLOR | 90D | F2606LHLF101MFN | 112 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-118 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1180 | MULTI COLOR | 60D | S2762LHAU373 | 34 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1180 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1181 | MULTI COLOR | 60D | S2762LHAU373 | 38 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1181 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1182 | MULTI COLOR | 60D | S2762LHAU373 | 230 | 15/12/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1182 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1185 | MULTI COLOR | 60D | S2762LHMR399 | 661 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1185 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1186 | MULTI COLOR | 60D | S27AOCP101 | 1370 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1186 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1187 | MULTI COLOR | 60D | S27AOCP101 | 15361 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1187 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1188 | MULTI COLOR | 60D | S27AOCP102 | 1171 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1188 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1189 | MULTI COLOR | 60D | S27AOCP102 | 9098 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1189 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1190 | MULTI COLOR | 60D | S27AOCP103 | 840 | 15/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1190 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1191 | MULTI COLOR | 60D | S27AOCP103 | 1380 | 30/11/2026 |  |  | 46212 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1191 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-121 | MULTI COLOR | 90D | F2606LHLF102FY | 642 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-121 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-122 | MULTI COLOR | 90D | F2606LHLF102FYL | 241 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-122 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-123 | MULTI COLOR | 90D | F2606LHLF102MFL | 248 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-123 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-124 | MULTI COLOR | 90D | F2606LHLF102MFN | 282 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-124 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-125 | MULTI COLOR | 90D | F2606LHLF103FY | 100 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-125 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-126 | MULTI COLOR | 90D | F2606LHLF103FYL | 318 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-126 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-127 | MULTI COLOR | 90D | F2606LHLF103MFL | 646 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-127 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-128 | MULTI COLOR | 90D | F2606LHMU101FY | 262 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-128 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-129 | MULTI COLOR | 90D | F2606LHMU101MFN | 22 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-129 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-131 | MULTI COLOR | 90D | F2608MR1201BUF | 374 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-132 | MULTI COLOR | 90D | F2608MR1201BUF | 185 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-132 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-143 | MULTI COLOR | 90D | F2625M101 | 594 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-143 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-144 | MULTI COLOR | 90D | F2625M101 | 536 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-144 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-145 | MULTI COLOR | 90D | F2625M101 | 602 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-145 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-150 | MULTI COLOR | 90D | F2625W233 | 54 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-150 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-151 | MULTI COLOR | 90D | F2625W233 | 1 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-151 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-152 | MULTI COLOR | 105D | F2654MESS614WVB | 37 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-152 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-157 | MULTI COLOR | 60D | F26FBGFXP101 | 410 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-157 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-158 | MULTI COLOR | 60D | F26FBGFXP104 | 1800 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-158 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-159 | MULTI COLOR | 60D | F26FBGFXP105 | 451 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-159 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-298 | MULTI COLOR | 60D | PH_F_BKB_A | 185 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-298 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-299 | MULTI COLOR | 60D | PH_F_SPW_A | 100 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-299 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-300 | MULTI COLOR | 60D | PH_F_SPW_A | 308 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-300 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-304 | MULTI COLOR | 60D | PH_F_SWK_A | 283 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-304 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-305 | MULTI COLOR | 60D | PH_F_SWK_A | 260 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-305 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-309 | MULTI COLOR | 60D | PH_F_TRA_A | 254 | 15/11/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-309 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-310 | MULTI COLOR | 60D | PH_F_TRA_A | 376 | 30/11/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-310 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-311 | MULTI COLOR | 90D | PH_MOTORSPR_APP | 233 | 15/12/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-311 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-340 | MULTI COLOR | 90D | PHORIGMEN | 4447 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-340 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-350 | MULTI COLOR | 90D | PHORIGWMN | 25 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-350 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-356 | MULTI COLOR | 90D | PHRUN | 1545 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-356 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-357 | MULTI COLOR | 90D | PHRUN | 6813 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-357 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-367 | MULTI COLOR | 90D | PHRUNWMN | 1445 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-367 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-376 | MULTI COLOR | 90D | PHSPWK | 1223 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-376 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-385 | MULTI COLOR | 90D | PHSPWM | 720 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-385 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-386 | MULTI COLOR | 90D | PHSPWM | 2303 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-386 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-396 | MULTI COLOR | 90D | PHSPWW | 271 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-396 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-404 | MULTI COLOR | 90D | PHSWIM | 2 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-404 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-410 | MULTI COLOR | 90D | PHTRNMEN | 38 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-410 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-411 | MULTI COLOR | 90D | PHTRNMEN | 345 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-411 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-419 | MULTI COLOR | 90D | PHTRNWMN | 30 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-419 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-426 | MULTI COLOR | 60D | S1954WC511 | 336 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-426 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-428 | MULTI COLOR | 60D | S211CSIM120FLTC | 2 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-428 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-436 | MULTI COLOR | 60D | S2307M501 | 2 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT+PPA+PPH SUB PROCESS_V3 | OFC-07092026-436 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-437 | MULTI COLOR | 90D | S23080640 | 462 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-437 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-438 | MULTI COLOR | 90D | S23080640 | 1648 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-438 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-440-B | MULTI COLOR | 90D | S2315KSWLK102-B | 7383 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-440-B |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-440-T | MULTI COLOR | 90D | S2315KSWLK102 | 7383 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-440-T |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-445 | MULTI COLOR | 45D | S2315KSWU324A | 260 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-445 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-447 | MULTI COLOR | 105D | S2408MR1600 | 495 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-447 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-448 | MULTI COLOR | 105D | S2408MR1600 | 103 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-448 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-449 | MULTI COLOR | 105D | S2408MR1600 | 1244 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-449 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-459 | MULTI COLOR | 90D | S2408MR1601 | 405 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-459 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-460 | MULTI COLOR | 90D | S2408MR1601 | 1013 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-460 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-461 | MULTI COLOR | 90D | S2408MR1601 | 1016 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-461 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-476 | MULTI COLOR | 105D | S2408WR1600 | 238 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-476 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-477 | MULTI COLOR | 105D | S2408WR1600 | 203 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-477 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-487 | MULTI COLOR | 105D | S2408WR1601A | 109 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-487 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-488 | MULTI COLOR | 105D | S2408WR1601A | 368 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-488 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-497 | MULTI COLOR | 105D | S2408WR1603 | 87 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-497 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-504 | MULTI COLOR | 60D | S2425M405 | 1295 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-504 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-505 | MULTI COLOR | 60D | S2425M405 | 8325 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-505 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-506 | MULTI COLOR | 60D | S2425M405 | 7642 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-506 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-514 | MULTI COLOR | 90D | S2450WTR803 | 81 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-514 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-518 | MULTI COLOR | 90D | S2506GHTM400M | 218 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-518 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-519 | MULTI COLOR | 90D | S2506GHTM400Y | 1 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-519 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-520 | MULTI COLOR | 90D | S2506GHTM401M | 643 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-520 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-523 | MULTI COLOR | 60D | S2525M200 | 790 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-523 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-524 | MULTI COLOR | 60D | S2525M200 | 8189 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-524 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-530 | MULTI COLOR | 90D | S2554MESS601FT | 1 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-530 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-531 | MULTI COLOR | 90D | S2554MESS601FT | 13842 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-531 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-536 | MULTI COLOR | 90D | S2554MESS605FT | 5 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-536 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-537 | MULTI COLOR | 90D | S2554MESS605FT | 655 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-537 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-541 | MULTI COLOR | 90D | S2554MESS611FT | 91 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-541 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-542 | MULTI COLOR | 90D | S2554MESS611FT | 10 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-542 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-546 | MULTI COLOR | 90D | S2554MESS612FT | 1941 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-546 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-549 | MULTI COLOR | 90D | S2554MESS642WV | 76 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L1+PPH L1 SUB PROCESS_V3 | OFC-07092026-549 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-550 | MULTI COLOR | 90D | S2554MESS663SJ | 1 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-550 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-551 | MULTI COLOR | 90D | S2554MESS663SJ | 279 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-551 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-554 | MULTI COLOR | 90D | S2554MESS675FT | 1158 | 15/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-554 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-555 | MULTI COLOR | 90D | S2554MESS675FT | 29 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-555 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-561 | MULTI COLOR | 90D | S2554WES402FT | 14 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-561 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-562 | MULTI COLOR | 90D | S2554WES402FT | 9710 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-562 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-566 | MULTI COLOR | 90D | S2554WES403FT | 6 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-566 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-567 | MULTI COLOR | 90D | S2554WES403FT | 874 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-567 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-570 | MULTI COLOR | 90D | S2554WES413FTB | 22 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-570 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-571 | MULTI COLOR | 90D | S2554WES413FTB | 2852 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-571 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-574 | MULTI COLOR | 90D | S2554WES421WV | 38 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-574 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-575 | MULTI COLOR | 90D | S2554WES421WV | 3706 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-575 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-584 | MULTI COLOR | 90D | S2554WES428FT | 319 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-584 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-586 | MULTI COLOR | 90D | S2554WES503FT | 102 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-586 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-587 | MULTI COLOR | 90D | S2554WES512FT | 120 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-587 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-588 | MULTI COLOR | 90D | S2554WES512FT | 4034 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-588 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-593 | MULTI COLOR | 60D | S25SPRMGFX230 | 40 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PPH L1+PAD SUB PROCESS_V3 | OFC-07092026-593 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-594 | MULTI COLOR | 60D | S25SPRMGFX233 | 36 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-594 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-595 | MULTI COLOR | 60D | S25SPRMGFX233 | 432 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-595 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-601 | MULTI COLOR | 60D | S25SPRMGFX313 | 957 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-601 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-602 | MULTI COLOR | 90D | S25TEGFX501A | 27 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD+HT SUB PROCESS_V3 | OFC-07092026-602 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-606 | MULTI COLOR | 90D | S2606GHTM302M | 310 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO+HT+PAD SUB PROCESS_V3 | OFC-07092026-606 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-608 | MULTI COLOR | 120D | S2608MR0201 | 173 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-608 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-609 | MULTI COLOR | 120D | S2608MR0201 | 101 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-609 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-610 | MULTI COLOR | 120D | S2608MR0201 | 646 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-610 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-621 | MULTI COLOR | 105D | S2608MR0201B | 375 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-621 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-647 | MULTI COLOR | 120D | S2608MR0900A | 910 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-647 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-648 | MULTI COLOR | 120D | S2608MR0900A | 37 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-648 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-649 | MULTI COLOR | 120D | S2608MR0900A | 1747 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-649 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-660 | MULTI COLOR | 105D | S2608MR0901 | 209 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-660 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-668 | MULTI COLOR | 90D | S2608MR0902 | 1018 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-668 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-669 | MULTI COLOR | 90D | S2608MR0902 | 253 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-669 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-680 | MULTI COLOR | 120D | S2608MR0906A | 1 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-680 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-693 | MULTI COLOR | 120D | S2608WR0201 | 587 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-693 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-708 | MULTI COLOR | 120D | S2608WR0202 | 546 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-708 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-732 | MULTI COLOR | 105D | S2608WR0901 | 30 | 15/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-732 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-733 | MULTI COLOR | 105D | S2608WR0901 | 1844 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-733 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-745 | MULTI COLOR | 105D | S2608WR0902 | 101 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-745 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-746 | MULTI COLOR | 105D | S2608WR0902 | 3685 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-746 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-756 | MULTI COLOR | 90D | S2608WR0910 | 117 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-756 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-759 | MULTI COLOR | 90D | S2615KSWJ751 | 1975 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-759 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-764 | MULTI COLOR | 90D | S2615KSWJ753 | 864 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-764 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-770 | MULTI COLOR | 90D | S2625M018 | 586 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-770 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-771 | MULTI COLOR | 90D | S2625M018 | 923 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-771 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-775 | MULTI COLOR | 90D | S2625M036 | 101 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-775 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-776 | MULTI COLOR | 90D | S2625M036 | 404 | 30/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-776 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-777 | MULTI COLOR | 90D | S2625M036 | 18 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-777 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-783 | MULTI COLOR | 30D | S2625W005 | 239 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-783 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-787 | MULTI COLOR | 90D | S2625W005 | 587 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-787 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-794 | MULTI COLOR | 90D | S2650MTR402 | 13 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-794 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-810 | MULTI COLOR | 105D | S2650MTR436 | 2466 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | HT+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-810 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-817 | MULTI COLOR | 105D | S2650MTR437 | 647 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-817 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-820 | MULTI COLOR | 90D | S2650MTR805A | 40 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-820 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-825 | MULTI COLOR | 105D | S2650WTR339 | 204 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-825 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-834 | MULTI COLOR | 90D | S2654MSERENO742 | 926 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-834 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-839 | MULTI COLOR | 90D | S2654MSERENO743 | 685 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-839 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-843 | MULTI COLOR | 90D | S26AAWVL320 | 2 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-843 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-846 | MULTI COLOR | 60D | S26KJGGFX020 | 145 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-846 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-861 | MULTI COLOR | 60D | S26SPRWGFX005 | 829 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-861 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-862 | MULTI COLOR | 60D | S26SPRWGFX023 | 1 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-862 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-866 | MULTI COLOR | 60D | S26SPRWGFX110 | 1120 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-866 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-867 | MULTI COLOR | 60D | S26SPRWGFX111 | 117 | 15/11/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-867 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-870 | MULTI COLOR | 90D | S2706CHLF022 | 134 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-870 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-871 | MULTI COLOR | 75D | S2706CHRM031 | 1203 | 30/11/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L2+EMBRO SUB PROCESS_V3 | OFC-07092026-871 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-875 | MULTI COLOR | 90D | S2725M920 | 351 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-875 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-876 | MULTI COLOR | 90D | S2725M926A | 1604 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-876 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-878 | MULTI COLOR | 90D | S2725M993 | 758 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-878 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-882 | MULTI COLOR | 105D | S2750MTR041A | 552 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+PAD SUB PROCESS_V3 | OFC-07092026-882 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-885 | MULTI COLOR | 105D | S2750MTR052 | 287 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-885 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-893 | MULTI COLOR | 105D | S2754JKTM534B | 60 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-893 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-907 | MULTI COLOR | 105D | S2754MAS511B | 48 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-907 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-914 | MULTI COLOR | 105D | S2754MAS512B | 44 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-914 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-920 | MULTI COLOR | 105D | S2754MAS513 | 124 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-920 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-933 | MULTI COLOR | 90D | S2754MESS659PQ | 975 | 15/12/2026 |  |  | 46212 |  | POLO SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-933 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-935 | MULTI COLOR | 90D | S2754MESS674DK | 706 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-935 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-937 | MULTI COLOR | 90D | S2754MESS676SJ | 2904 | 15/12/2026 |  |  | 46212 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-937 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-942 | MULTI COLOR | 105D | S2754MESS708WV | 2455 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-942 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-945 | MULTI COLOR | 105D | S2754MESS710WV | 152 | 15/12/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-945 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-963 | MULTI COLOR | 90D | S2754WESS404WV | 4515 | 30/11/2026 |  |  | 46212 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-963 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-973 | MULTI COLOR | 90D | S2754WESS420WV | 132 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-973 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-974 | MULTI COLOR | 90D | S2754WESS420WV | 240 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-974 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-979 | MULTI COLOR | 90D | S2754WESS421WV | 1632 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-979 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-988 | MULTI COLOR | 90D | S2754WESS422WV | 108 | 30/11/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-988 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-989 | MULTI COLOR | 90D | S2754WESS422WV | 722 | 15/12/2026 |  |  | 46212 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-989 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-995 | MULTI COLOR | 90D | S2754WESS501DK | 1342 | 15/12/2026 |  |  | 46212 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-995 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-998 | MULTI COLOR | 90D | S2754WESS703WV | 49 | 30/11/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-998 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-999 | MULTI COLOR | 90D | S2754WESS703WV | 437 | 15/12/2026 |  |  | 46212 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-999 | 46184 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27