## Sheet1
JO Tracking Report
Factory: | KAHATEX CIJERAH | Floor | G1,G2,G3,G4,G5,SPL | JO: |  | Style No: |  | Delivery Date: | 16/08/2026 - 15/10/2026 | JO Status: | Uncompleted, Completed, Export | Printed by: | REYNALDI | Print time: | 15/09/2026 14:34:41
Customer Name | Order No. | Color | Lot No | Factory Style | Qty | Delivery Date | Plan Qty | Merchaniser | PO.NO | Line | Product Type | Floor | Fabrics | Auxiliary | JO Remarks | Process Route Name | Cust_Order_No | Pre-production event finish date | Factory | Ship To | Ship Mode | Sewing Start | Style Description | Plan Remarks | Season | SEWING | [8 empty] | COMPLETE ASSEMBLY | [8 empty] | HEAT TRANSFER
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902369757-1 KC4275 | GREY FIVE F17 | 60D | S2608MR0910A | 110 | 20/08/2026 | 110 | SI | SI24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L2+HT SUB PROCESS_V3 | 0902369757 KC4275 | 2026-03-03 | KAHATEX CIJERAH | URUGUAY | SEA | 23/06/2026 | Run Ess BL T M |  | FW26 | 23/06/2026 | 26/06/2026 | 24/06/2026 | 25/06/2026 | 110 | 110 |  |  |  | 18/06/2026 | 23/06/2026 | 25/05/2026 | 2026-05-06 | 110 | 110 |  |  |  | 17/06/2026 | 22/06/2026 | 21/05/2026 | 2026-03-06 | 110 | 110
ADIDAS | 0902369999-1 JD3669 | BLACK | 90D | SMSURBF24BFRNTM | 1 | 21/08/2026 | 1 | SA | SA24/01/2026 | G2M | T-SHIRT | G2 | ok | (11/02/2026) | 21/08: ex-fty 980004 | PRINT L1+PAD SUB PROCESS_V3 | 0902369999 JD3669 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/07/2026 | BF LOGO TEE M |  | FW26 | 15/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 1 | 1 |  |  |  | 2026-10-07 | 15/07/2026 | 17/07/2026 | 17/07/2026 | 1 | 1
ADIDAS | 0902370337-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 4368 | 21/08/2026 | 4368 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 27-feb, 3S actual receives 26-Mar. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370337 JE1309 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 14/07/2026 | 27/07/2026 | 14/07/2026 | 23/07/2026 | 4368 | 4368 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-11-07 | 23/07/2026 | 4368 | 4368
ADIDAS | 0902370353-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 1404 | 21/08/2026 | 1404 | NT | NT24/01/2026 | G1B | SHORTS | G1 | ok | ok | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370353 JE1310 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 21/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 1404 | 1404 |  |  |  | 16/07/2026 | 21/07/2026 | 2026-10-07 | 16/07/2026 | 1404 | 1404
ADIDAS | 0902370399-1 KF8293 | KHAKI SIX F26/WHITE | 90D | S2554WES421WV | 2028 | 21/08/2026 | 2028 | NT | NT24/01/2026 | G1B | SHORTS | G1 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, material quality issues (body: shading), 3S actual receives 26-Mar, Body actual receives 30-Apr. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370399 KF8293 | 2026-08-04 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 15/07/2026 | 24/07/2026 | 15/07/2026 | 24/07/2026 | 2028 | 2028 |  |  |  | 2026-10-07 | 21/07/2026 | 13/07/2026 | 21/07/2026 | 2028 | 2028
ADIDAS | 0902370407-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 375 | 21/08/2026 | 375 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 27-Feb, 3S actual receives 12-Mar. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370407 JE1309 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 22/07/2026 | 23/07/2026 | 375 | 375 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 375 | 375
ADIDAS | 0902370413-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 135 | 21/08/2026 | 135 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | ok | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370413 JE1310 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 23/07/2026 | 27/07/2026 | 135 | 135 |  |  |  | 17/07/2026 | 22/07/2026 | 13/07/2026 | 13/07/2026 | 135 | 135
ADIDAS | 0902370424-1 KF8293 | KHAKI SIX F26/WHITE | 90D | S2554WES421WV | 240 | 21/08/2026 | 240 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 21/08: ex-fty (COSTCO). T2 Libolon, PI Date 21-Feb, material quality issues (body: shading), 3S actual receives 12-Mar, Body actual receives 30-Apr. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902370424 KF8293 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 22/07/2026 | W 3S WV SHO |  | FW26-COSTCO | 22/07/2026 | 27/07/2026 | 23/07/2026 | 27/07/2026 | 240 | 240 |  |  |  | 17/07/2026 | 22/07/2026 | 13/07/2026 | 13/07/2026 | 240 | 240
ADIDAS | 0902372182-1 JD3663 | BLACK | 90D | SMSURBF24ABTEEY | 900 | 21/08/2026 | 900 | SI | SI24/01/2026 | G2M | T-SHIRT | G2 | ok | (11/02/2026) | 21/08: ex-fty 980004 | PRINT L2+PAD SUB PROCESS_V3 | 0902372182 JD3663 | 2026-08-04 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 20/07/2026 | AB LOGO TEE Y |  | FW26 | 20/07/2026 | 22/07/2026 | 20/07/2026 | 22/07/2026 | 900 | 900 |  |  |  | 15/07/2026 | 17/07/2026 | 2026-10-07 | 21/07/2026 | 900 | 900
ADIDAS | 0902372325-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 590 | 2026-08-09 | 590 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372325 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 590 | 590 |  |  |  | 2026-03-07 | 15/07/2026 | 29/06/2026 | 2026-09-07 | 590 | 590
ADIDAS | 0902372436-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 124 | 31/08/2026 | 124 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372436 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 124 | 124 |  |  |  | 2026-03-07 | 15/07/2026 | 30/06/2026 | 2026-09-07 | 124 | 124
ADIDAS | 0902372459-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 122 | 31/08/2026 | 122 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Libolon, PI Date 23-Feb, actual receives 26-Feb. 800005T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902372459 JE1310 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26 | 14/07/2026 | 22/07/2026 | 14/07/2026 | 17/07/2026 | 122 | 122 |  |  |  | 2026-09-07 | 17/07/2026 | 13/07/2026 | 13/07/2026 | 122 | 122
ADIDAS | 0902372469-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 104 | 31/08/2026 | 104 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372469 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 104 | 104 |  |  |  | 2026-03-07 | 15/07/2026 | 2026-07-07 | 2026-07-07 | 104 | 104
ADIDAS | 0902372479-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 186 | 2026-08-09 | 186 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372479 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 22/07/2026 | 2026-09-07 | 21/07/2026 | 186 | 186 |  |  |  | 2026-03-07 | 17/07/2026 | 2026-02-07 | 18/07/2026 | 186 | 186
ADIDAS | 0902372487-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 134 | 31/08/2026 | 134 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372487 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 16/07/2026 | 2026-09-07 | 14/07/2026 | 134 | 134 |  |  |  | 2026-03-07 | 13/07/2026 | 30/06/2026 | 2026-07-07 | 134 | 134
ADIDAS | 0902372517-1 JE1310 | WHITE/BLACK | 90D | S2554WES421WV | 120 | 31/08/2026 | 120 | NT | NT24/01/2026 | G3J | SHORTS | G3 | ok | (11/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Libolon, PI Date 21-Feb, Body actual receives 12-Feb, 3S actual receives 02-Mar. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902372517 JE1310 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | W 3S WV SHO |  | FW26 | 14/07/2026 | 22/07/2026 | 14/07/2026 | 17/07/2026 | 120 | 120 |  |  |  | 2026-09-07 | 17/07/2026 | 13/07/2026 | 14/07/2026 | 120 | 120
ADIDAS | 0902497405-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 244 | 2026-08-09 | 244 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497405 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-06-08 | 29/07/2026 | 2026-06-08 | 244 | 244 |  |  |  | 24/07/2026 | 2026-03-08 | 27/07/2026 | 2026-07-08 | 244 | 244
ADIDAS | 0902497408-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2L | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497408 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902497412-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 205 | 2026-08-09 | 205 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497412 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 27/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 205 | 205 |  |  |  | 22/07/2026 | 30/07/2026 | 15/07/2026 | 2026-04-08 | 205 | 205
ADIDAS | 0902497414-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497414 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 100 | 100 |  |  |  | 24/07/2026 | 30/07/2026 | 16/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902545290-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 3000 | 2026-05-09 | 3000 | SA | SA06/02/2026 | G1D,G1K,G3I | PANTS | G1,G3 | ok | ok | 04/09: ex-fty 823016 | EMBRO SUB PROCESS_V1 | 0902545290 GK9267 | 2026-11-03 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 21/07/2026 | M 3S FL O PT |  | FW26 | 21/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 3000 | 3000 |  |  |  | 16/07/2026 | 22/07/2026 | 2026-07-07 | 22/07/2026 | 3000 | 3000
ADIDAS | 0902556131-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1862 | 21/08/2026 | 1862 | SA | SA06/02/2026 | G3C | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, PI Date 02-Mar, actual receives 27-Feb. 960026 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0902556131 JE9016 | 2026-05-05 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/07/2026 | M LIN CHELSEA |  | FW26 | 15/07/2026 | 28/07/2026 | 14/07/2026 | 23/07/2026 | 1862 | 1862 |  |  |  | 2026-10-07 | 23/07/2026 | 2026-08-07 | 20/07/2026 | 1862 | 1862
ADIDAS | 0902557430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 112 | 31/08/2026 | 112 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, PI Date 17-Mar, actual receives 04-Jul (FOC 2147 yd) (switch with fabric from Libolon). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557430 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 20/07/2026 | 23/07/2026 | 112 | 112 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 14/07/2026 | 112 | 112 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 14/07/2026 | 112 | 112
ADIDAS | 0902557495-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 824 | 2026-08-09 | 824 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, using fabric stock (FOC 2147 yd) (switch with fabric from Far Eastern.). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557495 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 15/07/2026 | 23/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824
ADIDAS | 0902557554-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 100 | 31/08/2026 | 100 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, actual receives 04-Jul (FOC 2147 yd) (switch with fabric from Libolon). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557554 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 16/07/2026 | 24/07/2026 | 13/07/2026 | 15/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 15/07/2026 | 100 | 100
ADIDAS | 0902622148-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 4220 | 2026-12-09 | 4220 | AT | AT27/02/2026 | G3J,G3K | PANTS | G3 | ok | (19/03/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902622148 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 27/07/2026 | M 3S FT TC PT |  | FW26 | 27/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 4220 | 4220 |  |  |  | 22/07/2026 | 30/07/2026 | 2026-10-07 | 25/07/2026 | 4220 | 4220
ADIDAS | 0902622190-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 780 | 21/08/2026 | 780 | AT | AT27/02/2026 | G3D | PANTS | G3 | ok | (19/03/2026) | 21/08: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902622190 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 29/07/2026 | 23/07/2026 | 28/07/2026 | 780 | 780 |  |  |  | 16/07/2026 | 24/07/2026 | 2026-04-07 | 13/07/2026 | 780 | 780
ADIDAS | 0902635931-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 602 | 2026-08-09 | 602 | SA | SA27/02/2026 | G2S | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635931 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 20/07/2026 | 602 | 602 |  |  |  | 2026-03-07 | 15/07/2026 | 26/06/2026 | 2026-02-07 | 602 | 602
ADIDAS | 0902635960-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 204 | 31/08/2026 | 204 | SA | SA27/02/2026 | G2E,G2L | T-SHIRT | G2 | ok | (18/03/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635960 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 17/07/2026 | 204 | 204 |  |  |  | 2026-03-07 | 15/07/2026 | 30/06/2026 | 2026-08-07 | 204 | 204
ADIDAS | 0902636875-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2720 | 15/09/2026 | 2720 | AT | AT04/03/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (28/03/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902636875 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-09-09 | 29/08/2026 | 2026-09-09 | 2720 | 2720 |  |  |  | 24/08/2026 | 2026-05-09 | 28/07/2026 | 2026-09-09 | 2720 | 2720
ADIDAS | 0902652229-1 KD5830 | BLACK | 105D | F2525M009 | 154 | 2026-08-09 | 154 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2-SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652229 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 154 | 154 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-01-07 | 2026-10-07 | 154 | 154
ADIDAS | 0902652258-1 KD5830 | BLACK | 105D | F2525M009 | 1514 | 31/08/2026 | 1514 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2 SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652258 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 22/07/2026 | 15/07/2026 | 21/07/2026 | 1514 | 1514 |  |  |  | 2026-10-07 | 17/07/2026 | 2026-01-07 | 17/07/2026 | 1514 | 1514
ADIDAS | 0902652411-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652411 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 24/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652437-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652437 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652462-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 205 | 30/09/2026 | 205 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652462 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 15/07/2026 | 205 | 205
ADIDAS | 0902652495-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 241 | 30/09/2026 | 241 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652495 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 30/07/2026 | 20/07/2026 | 29/07/2026 | 241 | 241 |  |  |  | 15/07/2026 | 27/07/2026 | 15/07/2026 | 23/07/2026 | 241 | 241
ADIDAS | 0902685475-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 780 | 21/08/2026 | 780 | AT | AT04/03/2026 | G2P | SWEATSHIRT | G2 | ok | (28/03/2026) | 21/08: ex-fty 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902685475 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 16/07/2026 | M 3S FT SWT |  | FW26 | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 780 | 780 |  |  |  | 13/07/2026 | 21/07/2026 | 15/07/2026 | 22/07/2026 | 780 | 780
ADIDAS | 0902757486-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1201 | 21/08/2026 | 1201 | SA | SA27/03/2026 | G3D | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 30-Jun, actual receives 31-May. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902757486 JM1775 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M SL WV PT 2 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 1201 | 1201 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-11-07 | 17/07/2026 | 1201 | 1201
ADIDAS | 0902758851-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 370 | 28/08/2026 | 370 | AT | AT27/03/2026 | G3C | PANTS | G3 | ok | (20/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902758851 JD5302 | 16/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S FT CF PT |  | FW26 | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 370 | 370 |  |  |  | 23/07/2026 | 30/07/2026 | 22/07/2026 | 30/07/2026 | 370 | 370
ADIDAS | 0902760350-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 1199 | 21/08/2026 | 1199 | AT | AT27/03/2026 | G1C | JACKET | G1 | ok | (20/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 27-Jun, actual receives 29-Apr. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902760350 JM1772 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M SL WV TT |  | FW26 | 14/07/2026 | 20/07/2026 | 15/07/2026 | 20/07/2026 | 1199 | 1199 |  |  |  | 2026-09-07 | 15/07/2026 | 13/07/2026 | 17/07/2026 | 1199 | 1199
ADIDAS | 0902760456-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 800 | 21/08/2026 | 800 | SA | SA27/03/2026 | G3D | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty. T2 Libolon, LLT material, PI Date 30-Jun, actual receives 03-Jun. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902760456 JM1776 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M SL WV PT 2 |  | FW26 | 21/07/2026 | 24/07/2026 | 20/07/2026 | 22/07/2026 | 800 | 800 |  |  |  | 16/07/2026 | 21/07/2026 | 2026-11-07 | 22/07/2026 | 800 | 800
ADIDAS | 0902760499-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1205 | 21/08/2026 | 1205 | SA | SA27/03/2026 | G3F | PANTS | G3 | ok | (18/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902760499 IN6163 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 23/07/2026 | 20/07/2026 | 22/07/2026 | 1205 | 1205 |  |  |  | 15/07/2026 | 20/07/2026 | 2026-06-07 | 14/07/2026 | 1205 | 1205
ADIDAS | 0902763183-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 480 | 21/08/2026 | 480 | SI | SI27/03/2026 | G2T | SWEATSHIRT | G2 | ok | (16/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902763183 JE8949 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M BL FT SWT |  | FW26 | 21/07/2026 | 28/07/2026 | 22/07/2026 | 24/07/2026 | 480 | 480 |  |  |  | 16/07/2026 | 23/07/2026 | 21/07/2026 | 22/07/2026 | 480 | 480
ADIDAS | 0902763228-1 JM1773 | DARK BLUE/WHITE | 90D | F2554MESS712WV-MTF | 799 | 21/08/2026 | 799 | NT | NT27/03/2026 | G1C | JACKET | G1 | ok | (15/04/2026) | 21/08: ex-fty. T2 Libolon, using fabric stock. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902763228 JM1773 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 28/07/2026 | 17/07/2026 | 27/07/2026 | 799 | 799 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 24/07/2026 | 799 | 799
ADIDAS | 0902763261-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 804 | 21/08/2026 | 804 | SA | SA27/03/2026 | G3F | PANTS | G3 | ok | (16/04/2026) | 21/08: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902763261 JE8969 | 16/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 15/07/2026 | M BL FT PT |  | FW26 | 15/07/2026 | 20/07/2026 | 16/07/2026 | 20/07/2026 | 804 | 804 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-02-07 | 2026-11-07 | 804 | 804
ADIDAS | 0902764900-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1G,G1I,G1K | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902764900 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/07/2026 | LFC A F JSY SE |  | FW26-FJ | 23/07/2026 | 21/08/2026 | 23/07/2026 | 14/08/2026 | 15000 | 15000 |  |  |  | 20/07/2026 | 18/08/2026 | 13/07/2026 | 13/08/2026 | 15000 | 15000
ADIDAS | 0902765031-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1O,G1P,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902765031 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/07/2026 | LFC A F JSY SE |  | FW26-FJ | 23/07/2026 | 2026-07-08 | 23/07/2026 | 2026-06-08 | 15000 | 15000 |  |  |  | 20/07/2026 | 2026-04-08 | 18/07/2026 | 13/08/2026 | 15000 | 15000
ADIDAS | 0902767490-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1O,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767490 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/07/2026 | LFC A F JSY SE |  | FW26-FJ | 29/07/2026 | 20/08/2026 | 29/07/2026 | 14/08/2026 | 15000 | 15000 |  |  |  | 24/07/2026 | 14/08/2026 | 20/07/2026 | 14/08/2026 | 15000 | 15000
ADIDAS | 0902767515-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1N,G1O,G1P,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767515 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | LFC A F JSY SE |  | FW26-FJ | 2026-03-08 | 19/08/2026 | 2026-03-08 | 18/08/2026 | 15000 | 15000 |  |  |  | 29/07/2026 | 13/08/2026 | 25/07/2026 | 18/08/2026 | 15000 | 15000
ADIDAS | 0902767538-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 28/08/2026 | 15000 | AT | AT27/03/2026 | G1M,G1O,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767538 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | LFC A F JSY SE |  | FW26-FJ | 2026-03-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 15000 | 15000 |  |  |  | 29/07/2026 | 13/08/2026 | 25/07/2026 | 19/08/2026 | 15000 | 15000
ADIDAS | 0902767561-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 12788 | 28/08/2026 | 12788 | AT | AT27/03/2026 | G1A,G1E,G1G,G1K,G1M | T-SHIRT | G1 | ok | (17/04/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902767561 LE8199 | 16/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/07/2026 | LFC A F JSY SE |  | FW26-FJ | 28/07/2026 | 18/08/2026 | 24/07/2026 | 18/08/2026 | 12788 | 12788 |  |  |  | 23/07/2026 | 2026-12-08 | 13/07/2026 | 13/08/2026 | 12788 | 12788
ADIDAS | 0902769872-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 4240 | 2026-05-09 | 4240 | AT | AT27/03/2026 | G1P,G1Q,G1R | T-SHIRT | G1 | ok | ok | 04/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902769872 LE8199 | 16/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-08 | LFC A F JSY SE |  | FW26-FJ | 2026-05-08 | 19/08/2026 | 2026-10-08 | 18/08/2026 | 4240 | 4240 |  |  |  | 31/07/2026 | 13/08/2026 | 31/07/2026 | 18/08/2026 | 4240 | 4240
ADIDAS | 0902803294-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV-MTF | 233 | 2026-05-09 | 233 | NT | NT10/04/2026 | G3D | PANTS | G3 | ok | (08/05/2026) | 05/09: ex-fty. T2 Libolon, PI Date 21-Jun, actual receives 22-May. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902803294 JM1778 | 30/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | M SL WV PT 1 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 17/07/2026 | 233 | 233 |  |  |  | 2026-09-07 | 16/07/2026 | 13/07/2026 | 17/07/2026 | 233 | 233
ADIDAS | 0902803647-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 30/09/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual reiceves 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803647 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 15/09/2026 | 2026-07-08 | 15/09/2026 | 100 | 100 |  |  | 7 | 2026-03-08 | 2026-11-09 | 22/07/2026 | 2026-05-08 | 100 | 100
ADIDAS | 0902803818-1 KF9922 | TEAM COLL BURGUNDY 2 | 90D | F2606CHMU042 | 377 | 2026-08-09 | 377 | AN | AN10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 08/09: ex-fty (NYK warehouse). T2 Kahatex, material quality issues (creasemark), PI Date 09-May, actual receives 17-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L2+EMBRO SUB PROCESS_V3 | 0902803818 KF9922 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | MUFC LF TEE |  | FW26 | 27/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 377 | 377 |  |  |  | 22/07/2026 | 30/07/2026 | 21/07/2026 | 28/07/2026 | 377 | 377
ADIDAS | 0902803854-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 15/10/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803854 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-04-08 | LFC LF TEE |  | FW26 | 2026-04-08 | 2026-01-09 | 2026-05-08 | 2026-02-09 | 100 | 100 |  |  |  | 30/07/2026 | 28/08/2026 | 22/07/2026 | 2026-02-09 | 100 | 100
ADIDAS | 0902803922-1 KG2924 | BLACK | 90D | F2606CHLF041 | 200 | 15/10/2026 | 200 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803922 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 2026-04-09 | 2026-06-08 | 2026-03-09 | 200 | 200 |  |  |  | 2026-03-08 | 2026-01-09 | 23/07/2026 | 2026-05-08 | 200 | 200
ADIDAS | 0902804254-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 4267 | 2026-05-09 | 4267 | SA | SA10/04/2026 | G2L,G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 04/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804254 LE8211 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 29/08/2026 | 2026-04-09 | 4267 | 4267 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-04-09 | 4267 | 4267
ADIDAS | 0902804280-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 5861 | 28/08/2026 | 5861 | SI | SI10/04/2026 | G2O | T-SHIRT | G2 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804280 LE8190 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 22/07/2026 | 2026-10-08 | 22/07/2026 | 2026-05-08 | 5861 | 5861 |  |  |  | 17/07/2026 | 2026-05-08 | 2026-11-07 | 24/07/2026 | 5861 | 5861
ADIDAS | 0902804314-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 15000 | 28/08/2026 | 15000 | SI | SI10/04/2026 | G2K,G2M,G2O | T-SHIRT | G2 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804314 LE8190 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 22/07/2026 | 13/08/2026 | 22/07/2026 | 2026-12-08 | 15000 | 15000 |  |  |  | 17/07/2026 | 2026-10-08 | 18/07/2026 | 2026-10-08 | 15000 | 15000
ADIDAS | 0902804368-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 12412 | 2026-05-09 | 12412 | AT | AT10/04/2026 | G1Q,G2K,G2L,G2M,G2O | T-SHIRT | G1,G2 | ok | ok | 05/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804368 LE5779 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSY SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 12412 | 12412 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-01-09 | 2026-05-09 | 12412 | 12412
ADIDAS | 0902804483-1 KG2924 | BLACK | 90D | F2606CHLF041 | 1015 | 21/08/2026 | 1015 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 814006 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902804483 KG2924 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 22/07/2026 | LFC LF TEE |  | FW26 | 22/07/2026 | 29/07/2026 | 22/07/2026 | 29/07/2026 | 1015 | 1015 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 29/07/2026 | 1015 | 1015
ADIDAS | 0902806140-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 739 | 21/08/2026 | 739 | AT | AT10/04/2026 | G3D | PANTS | G3 | ok | (29/04/2026) | 21/08: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902806140 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 29/07/2026 | 22/07/2026 | 27/07/2026 | 739 | 739 |  |  |  | 16/07/2026 | 24/07/2026 | 2026-07-07 | 18/07/2026 | 739 | 739
ADIDAS | 0902806727-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 150 | 21/08/2026 | 150 | AT | AT10/04/2026 | G2P | SWEATSHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902806727 KG2925 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 20/07/2026 | LFC LF HD |  | FW26 | 20/07/2026 | 28/07/2026 | 23/07/2026 | 27/07/2026 | 150 | 150 |  |  |  | 15/07/2026 | 23/07/2026 | 20/07/2026 | 27/07/2026 | 150 | 150
ADIDAS | 0902807370-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1F,G1P,G1Q | T-SHIRT | G1 | ok | ok | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902807370 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC H F JSY SE |  | FW26-FJ | 14/07/2026 | 30/07/2026 | 15/07/2026 | 29/07/2026 | 15000 | 15000 |  |  |  | 2026-09-07 | 27/07/2026 | 14/07/2026 | 29/07/2026 | 15000 | 15000
ADIDAS | 0902807414-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 6387 | 21/08/2026 | 6387 | AT | AT10/04/2026 | G2M | T-SHIRT | G2 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902807414 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 31/07/2026 | LFC H F JSY SE |  | FW26-FJ | 31/07/2026 | 20/08/2026 | 31/07/2026 | 14/08/2026 | 6387 | 6387 |  |  |  | 28/07/2026 | 14/08/2026 | 28/07/2026 | 20/08/2026 | 6387 | 6387
ADIDAS | 0902808177-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 3220 | 2026-12-09 | 3220 | AT | AT10/04/2026 | G3C,G3D,G3E | PANTS | G3 | ok | (29/04/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902808177 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 3220 | 3220 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 2026-01-08 | 3220 | 3217 | 3
ADIDAS | 0902808402-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1A,G1G,G1I,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808402 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 30/07/2026 | LFC H F JSY SE |  | FW26-FJ | 30/07/2026 | 21/08/2026 | 2026-06-08 | 21/08/2026 | 15000 | 15000 |  |  |  | 27/07/2026 | 18/08/2026 | 31/07/2026 | 20/08/2026 | 15000 | 15000
ADIDAS | 0902808430-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 11421 | 21/08/2026 | 11421 | AN | AN10/04/2026 | G1F,G1P,G1Q,G1R | T-SHIRT | G1 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808430 LE8192 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-07 | AFC H F JSY SE |  | FW26-FJ | 2026-10-07 | 27/07/2026 | 2026-09-07 | 27/07/2026 | 11421 | 11421 |  |  |  | 2026-07-07 | 22/07/2026 | 2026-06-07 | 24/07/2026 | 11421 | 11421
ADIDAS | 0902808466-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 15000 | 21/08/2026 | 15000 | SI | SI10/04/2026 | G2G,G2K,G2N,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808466 LE8190 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 13/07/2026 | MUFC H F JSY SE |  | FW26-FJ | 13/07/2026 | 2026-03-08 | 2026-10-07 | 29/07/2026 | 15000 | 15000 |  |  |  | 2026-08-07 | 29/07/2026 | 2026-06-07 | 24/07/2026 | 15000 | 15000
ADIDAS | 0902808499-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 6436 | 21/08/2026 | 6436 | SI | SI10/04/2026 | G1A | T-SHIRT | G1 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808499 LE8190 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-07 | MUFC H F JSY SE |  | FW26-FJ | 2026-07-07 | 28/07/2026 | 2026-09-07 | 24/07/2026 | 6436 | 6436 |  |  |  | 2026-02-07 | 23/07/2026 | 2026-03-07 | 17/07/2026 | 6436 | 6436
ADIDAS | 0902808529-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 5899 | 21/08/2026 | 5899 | SA | SA10/04/2026 | G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808529 LE8211 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 31/07/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/07/2026 | 21/08/2026 | 31/07/2026 | 18/08/2026 | 5899 | 5899 |  |  |  | 28/07/2026 | 18/08/2026 | 29/07/2026 | 18/08/2026 | 5899 | 5899
ADIDAS | 0902808575-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 7472 | 21/08/2026 | 7472 | AT | AT10/04/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808575 LE8199 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC A F JSY SE |  | FW26-FJ | 14/07/2026 | 2026-03-08 | 16/07/2026 | 29/07/2026 | 7472 | 7472 |  |  |  | 2026-09-07 | 29/07/2026 | 2026-09-07 | 29/07/2026 | 7472 | 7472
ADIDAS | 0902808623-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 15000 | 21/08/2026 | 15000 | AT | AT10/04/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | (09/05/2026) | (08/05/2026) | 21/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902808623 LE8199 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 14/07/2026 | LFC A F JSY SE |  | FW26-FJ | 14/07/2026 | 2026-03-08 | 14/07/2026 | 27/07/2026 | 15000 | 15000 |  |  |  | 2026-09-07 | 29/07/2026 | 2026-07-07 | 29/07/2026 | 15000 | 15000
ADIDAS | 0902808893-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 11609 | 28/08/2026 | 11609 | AN | AN10/04/2026 | G1A,G1F,G1I,G1Q | T-SHIRT | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902808893 LE8192 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 27/07/2026 | AFC H F JSY SE |  | FW26-FJ | 27/07/2026 | 14/08/2026 | 21/07/2026 | 14/08/2026 | 11609 | 11609 |  |  |  | 22/07/2026 | 2026-11-08 | 14/07/2026 | 2026-05-08 | 11609 | 11609
ADIDAS | 0902810670-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 15000 | 28/08/2026 | 15000 | AT | AT10/04/2026 | G2K,G2L,G2M,G2O | T-SHIRT | G2 | ok | (08/05/2026) | 28/08: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902810670 LE5779 | 30/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-08 | LFC H F JSY SE |  | FW26-FJ | 2026-07-08 | 28/08/2026 | 2026-10-08 | 29/08/2026 | 15000 | 15000 |  |  |  | 2026-04-08 | 24/08/2026 | 2026-06-08 | 28/08/2026 | 15000 | 15000
ADIDAS | 0902847822-1 JE3837 | BLACK/WHITE | 90D | S2554MESS682FT | 1348 | 2026-05-09 | 1348 | AT | AT24/04/2026 | G2T | SWEATSHIRT | G2 | ok | (14/05/2026) | 05/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847822 JE3837 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M FEELCOZY SWT |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 21/07/2026 | 1348 | 1348 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-10-07 | 15/07/2026 | 1348 | 1348
ADIDAS | 0902847867-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 1491 | 2026-05-09 | 1491 | AT | AT24/04/2026 | G1D | PANTS | G1 | ok | ok | 04/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847867 JE3854 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M FEELCOZY PANT |  | FW26 | 21/07/2026 | 2026-05-08 | 23/07/2026 | 31/07/2026 | 1491 | 1491 |  |  |  | 16/07/2026 | 31/07/2026 | 18/07/2026 | 23/07/2026 | 1491 | 1491
ADIDAS | 0902850291-1 KF5291 | MAGIC LILAC S22 | 60D | S2608WR0910 | 144 | 20/08/2026 | 144 | SA | SA24/04/2026 | G2K | T-SHIRT | G2 | ok | ok | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L2+HT SUB PROCESS_V3 | 0902850291 KF5291 | 2026-12-06 | KAHATEX CIJERAH | URUGUAY | SEA | 26/06/2026 | Run Ess BL T W |  | FW26 | 26/06/2026 | 29/06/2026 | 26/06/2026 | 26/06/2026 | 144 | 144 |  |  |  | 23/06/2026 | 24/06/2026 | 2026-11-06 | 24/06/2026 | 144 | 144 |  |  |  | 22/06/2026 | 23/06/2026 | 2026-11-06 | 23/06/2026 | 144 | 144
ADIDAS | 0902853719-1 LE8209 | ACTIVE MAROON F19 | 90D | F2606LHLF101FYL | 5200 | 28/08/2026 | 5200 | SI | SI24/04/2026 | G1A,G1F | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902853719 LE8209 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | LFC HFY JSYL SE |  | FW26-FJ | 20/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 5200 | 5200 |  |  |  | 15/07/2026 | 27/07/2026 | 17/07/2026 | 30/07/2026 | 5200 | 5200
ADIDAS | 0902853964-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 81 | 15/10/2026 | 81 | AT | AT24/04/2026 | G2P | SWEATSHIRT | G2 | (22/05/2026) | (18/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902853964 KG2925 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-09 | LFC LF HD |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 81 | 81 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-11-08 | 2026-10-09 | 81 | 81
ADIDAS | 0902854036-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 29-May, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902854036 KA8777 | 28/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | TIRO26L SHO M |  | FW26-L2L | 14/07/2026 | 17/07/2026 | 14/07/2026 | 17/07/2026 | 132 | 132 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 16/07/2026 | 132 | 132 |  |  |  | 2026-07-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 132 | 132
ADIDAS | 0902854145-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 430 | 2026-05-09 | 430 | SI | SI24/04/2026 | G1D | JACKET | G1 | ok | ok | 04/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902854145 JE0052 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | W 3S FT FZ HD |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-06-08 | 2026-07-08 | 430 | 430 |  |  |  | 31/07/2026 | 2026-04-08 | 31/07/2026 | 2026-06-08 | 430 | 430
ADIDAS | 0902854237-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 481 | 23/09/2026 | 481 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/09: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854237 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 21/07/2026 | 2026-03-08 | 21/07/2026 | 31/07/2026 | 481 | 481 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 30/07/2026 | 481 | 481 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 23/07/2026 | 481 | 481
ADIDAS | 0902854269-1 KS0014 | WHITE | 90D | F26BMGFX210 | 102 | 20/08/2026 | 102 | SI | SI24/04/2026 | G2R | T-SHIRT | G2 | ok | (14/05/2026) | 20/08: ex-fty (Airowes). DRC 0047-hold shipment customer. 650034 | PRINT L3+PAD SUB PROCESS_V3 | 0902854269 KS0014 | 14/07/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-10-07 | WWH UNITED T |  | FW26 | 2026-10-07 | 14/07/2026 | 13/07/2026 | 13/07/2026 | 102 | 102 |  |  |  | 2026-07-07 | 2026-09-07 | 2026-08-07 | 13/07/2026 | 102 | 102
ADIDAS | 0902854292-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 300 | 21/08/2026 | 300 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/08: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854292 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 15/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 300 | 300 |  |  |  | 2026-10-07 | 16/07/2026 | 2026-09-07 | 14/07/2026 | 300 | 300 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-09-07 | 14/07/2026 | 300 | 300
ADIDAS | 0902855664-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 12218 | 28/08/2026 | 12218 | AN | AN24/04/2026 | G1I | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902855664 LE5780 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-07 | LFC H FY JSY SE |  | FW26-FJ | 2026-10-07 | 30/07/2026 | 2026-10-07 | 30/07/2026 | 12218 | 12218 |  |  |  | 2026-07-07 | 27/07/2026 | 2026-10-07 | 30/07/2026 | 12218 | 12218
ADIDAS | 0902856132-1 KE8425 | WHITE | 60D | S2608MR0906A | 264 | 21/08/2026 | 264 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 21/08: ex-fty 516394 | HT+PAD SUB PROCESS_V3 | 0902856132 KE8425 | 2026-12-06 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/07/2026 | Run Ess LS M |  | FW26 | 16/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 264 | 264 |  |  |  | 13/07/2026 | 24/07/2026 | 2026-09-07 | 16/07/2026 | 264 | 264 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-09-07 | 16/07/2026 | 264 | 264
ADIDAS | 0902856344-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 301 | 28/08/2026 | 301 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516343 | EMBRO+HT+PPH L1 SUB PROCESS_V3 | 0902856344 IA7637 | 14/07/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | AFC LF HD |  | FW26 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 301 | 301 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-07-08 | 13/08/2026 | 301 | 301 |  |  |  | 29/07/2026 | 2026-05-08 | 2026-06-08 | 2026-12-08 | 301 | 301
ADIDAS | 0902856437-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 160 | 31/08/2026 | 160 | NT | NT24/04/2026 | G1E | T-SHIRT | G1 | ok | (11/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516443 | HT SUB PROCESS_V1 | 0902856437 IT1824 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 23/07/2026 | 160 | 160 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 20/07/2026 | 160 | 160 |  |  |  | 15/07/2026 | 23/07/2026 | 2026-10-07 | 20/07/2026 | 160 | 160
ADIDAS | 0902857447-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 11170 | 28/08/2026 | 11170 | AN | AN24/04/2026 | G1G,G1I | T-SHIRT | G1 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902857447 LE8191 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/07/2026 | AFC H FY JSY SE |  | FW26-FJ | 30/07/2026 | 18/08/2026 | 30/07/2026 | 18/08/2026 | 11170 | 11170 |  |  |  | 27/07/2026 | 2026-12-08 | 28/07/2026 | 14/08/2026 | 11170 | 11170
ADIDAS | 0902857603-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 402 | 31/08/2026 | 402 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | EMBRO+HT+PPH L1+PPA SUB PROCESS_V3 | 0902857603 IA7637 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | AFC LF HD |  | FW26 | 24/07/2026 | 2026-07-08 | 24/07/2026 | 2026-04-08 | 402 | 402 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 2026-05-08 | 402 | 402 |  |  |  | 13/07/2026 | 27/07/2026 | 20/07/2026 | 31/07/2026 | 402 | 402
ADIDAS | 0902857630-1 IA7637 | PRELOVED RUBY S25 | 90D | F2606CHAFC029N | 818 | 31/08/2026 | 818 | SI | SI24/04/2026 | G2P | SWEATSHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | EMBRO+HT+PPH L1 SUB PROCESS_V3 | 0902857630 IA7637 | 14/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-08 | AFC LF HD |  | FW26 | 2026-07-08 | 18/08/2026 | 2026-10-08 | 18/08/2026 | 818 | 818 |  |  |  | 2026-04-08 | 2026-12-08 | 2026-07-08 | 15/08/2026 | 818 | 818 |  |  |  | 29/07/2026 | 2026-06-08 | 2026-07-08 | 15/08/2026 | 818 | 818
ADIDAS | 0902857874-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 12666 | 28/08/2026 | 12666 | SI | SI24/04/2026 | G1A,G2K,G2O | T-SHIRT | G1,G2 | (22/05/2026) | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902857874 LE8189 | 14/07/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-08 | MUFC HFY JSY SE |  | FW26-FJ | 2026-03-08 | 21/08/2026 | 2026-03-08 | 18/08/2026 | 12666 | 12666 |  |  |  | 29/07/2026 | 18/08/2026 | 28/07/2026 | 15/08/2026 | 12666 | 12666
ADIDAS | 0902857895-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 728 | 31/08/2026 | 728 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Gistex, PI Date 15-Jun, actual receives 24-Jul. T2 Formosa, PI Date 24-May, actual receives 20-Jun. T2 Kahatex, PI Date 22-May, actual receives 12-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902857895 KY4155 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 728 | 728 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-11-08 | 2026-02-09 | 728 | 727 | 1
ADIDAS | 0902857969-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1590 | 31/08/2026 | 1590 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Gistex, PI Date 15-Jun, actual receives 15-Jul. T2 Kahatex, PI Date 22-May, actual receives 02-Jul. T2 Formosa, PI Date 24-May, actual receives 20-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902857969 KY6510 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-08 | M 3S CHELSEA B7 |  | SS27 | 2026-12-08 | 29/08/2026 | 2026-12-08 | 29/08/2026 | 1590 | 1590 |  |  |  | 2026-07-08 | 26/08/2026 | 2026-07-08 | 2026-09-09 | 1590 | 1580 | 10
ADIDAS | 0902858585-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 114 | 2026-08-09 | 114 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858585 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 31/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 31/07/2026 | 2026-07-08 | 31/07/2026 | 2026-03-08 | 114 | 114 |  |  |  | 28/07/2026 | 2026-04-08 | 17/07/2026 | 28/07/2026 | 114 | 114
ADIDAS | 0902858612-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 777 | 30/09/2026 | 777 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858612 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 22/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 22/07/2026 | 2026-07-08 | 22/07/2026 | 2026-03-08 | 777 | 777 |  |  |  | 17/07/2026 | 2026-04-08 | 16/07/2026 | 21/07/2026 | 777 | 777
ADIDAS | 0902858673-1 KE8425 | WHITE | 60D | S2608MR0906A | 458 | 21/08/2026 | 458 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 21/08: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902858673 KE8425 | 2026-12-06 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess LS M |  | FW26 | 22/07/2026 | 29/07/2026 | 20/07/2026 | 27/07/2026 | 458 | 458 |  |  |  | 17/07/2026 | 24/07/2026 | 2026-10-07 | 24/07/2026 | 458 | 458 |  |  |  | 15/07/2026 | 22/07/2026 | 2026-10-07 | 24/07/2026 | 458 | 458
ADIDAS | 0902858704-1 KE8425 | WHITE | 60D | S2608MR0906A | 302 | 31/08/2026 | 302 | SI | SI24/04/2026 | G1M | T-SHIRT | G1 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | HT+PAD SUB PROCESS_V3 | 0902858704 KE8425 | 2026-12-06 | KAHATEX CIJERAH | ITALY | SEA | 16/07/2026 | Run Ess LS M |  | FW26 | 16/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 302 | 302 |  |  |  | 13/07/2026 | 24/07/2026 | 2026-09-07 | 22/07/2026 | 302 | 302 |  |  |  | 2026-09-07 | 22/07/2026 | 2026-09-07 | 22/07/2026 | 302 | 302
ADIDAS | 0902860131-1 JZ7808 | BLACK | 60D | S2608WR0900 | 341 | 31/08/2026 | 341 | AT | AT24/04/2026 | G2J | T-SHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | HT+PAD SUB PROCESS_V3 | 0902860131 JZ7808 | 2026-12-06 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | Run Ess Tee W |  | FW26 | 20/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 341 | 341 |  |  |  | 15/07/2026 | 22/07/2026 | 14/07/2026 | 22/07/2026 | 341 | 341 |  |  |  | 13/07/2026 | 20/07/2026 | 14/07/2026 | 22/07/2026 | 341 | 341
ADIDAS | 0902860651-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 169 | 28/08/2026 | 169 | SI | SI24/04/2026 | G1L,G3C | SHORTS | G1,G3 | ok | (04/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, PI Date 07-Jun, actual receives 23-Jun. 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902860651 LD5435 | 28/07/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 169 | 169 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 169 | 169
ADIDAS | 0902860692-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 101 | 2026-08-09 | 101 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860692 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 101 | 101 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-10-07 | 14/07/2026 | 101 | 101
ADIDAS | 0902860750-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 486 | 30/09/2026 | 486 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860750 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 486 | 486 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-09-07 | 14/07/2026 | 486 | 486
ADIDAS | 0902860782-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 205 | 2026-08-09 | 205 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860782 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 31/07/2026 | 21/07/2026 | 31/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 28/07/2026 | 17/07/2026 | 21/07/2026 | 205 | 205
ADIDAS | 0902860813-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 104 | 31/08/2026 | 104 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 31/08: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860813 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 22/07/2026 | 20/07/2026 | 21/07/2026 | 104 | 104 |  |  |  | 15/07/2026 | 17/07/2026 | 16/07/2026 | 17/07/2026 | 104 | 104
ADIDAS | 0902861800-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 274 | 31/08/2026 | 274 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok | (04/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902861800 LD5435 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 29/07/2026 | 2026-06-08 | 31/07/2026 | 2026-06-08 | 274 | 274 |  |  |  | 24/07/2026 | 2026-03-08 | 24/07/2026 | 2026-04-08 | 274 | 274
ADIDAS | 0902862442-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 318 | 28/08/2026 | 318 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok | (04/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862442 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-03-08 | 2026-07-08 | 31/07/2026 | 2026-12-08 | 318 | 318 |  |  |  | 29/07/2026 | 2026-04-08 | 23/07/2026 | 2026-11-08 | 318 | 318
ADIDAS | 0902882925-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 317 | 21/08/2026 | 317 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902882925 KD0677 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 317 | 317 |  |  |  | 2026-10-07 | 16/07/2026 | 14/07/2026 | 15/07/2026 | 317 | 317 |  |  |  | 2026-03-07 | 2026-09-07 | 13/07/2026 | 15/07/2026 | 317 | 317
ADIDAS | 0902887724-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 359 | 2026-05-09 | 359 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 28-May, using fabric stock. 516400 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887724 KD0677 | 22/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 359 | 359 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 29/07/2026 | 359 | 359 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 25/07/2026 | 359 | 359
ADIDAS | 0902899919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 502 | 2026-05-09 | 502 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899919 LD0288 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 31/07/2026 | 502 | 502 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502
ADIDAS | 0902899965-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899965 LD0287 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 369 | 369 |  |  |  | 2026-06-08 | 28/08/2026 | 2026-01-08 | 2026-08-08 | 369 | 369 |  |  |  | 2026-04-08 | 26/08/2026 | 27/07/2026 | 2026-07-08 | 369 | 369
ADIDAS | 0902900004-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 2400 | 21/08/2026 | 2400 | AN | AN15/05/2026 | G1H | JACKET | G1 | ok | (05/06/2026) | 21/08: ex-fty. T2 Kahatex, PI Date 13-Jun, actua receives 04-Aug. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902900004 KV8005 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/07/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 30/07/2026 | 19/08/2026 | 30/07/2026 | 20/08/2026 | 2400 | 2400 |  |  |  | 27/07/2026 | 13/08/2026 | 27/07/2026 | 20/08/2026 | 2400 | 2400
ADIDAS | 0902900128-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1800 | 31/08/2026 | 1800 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902900128 LE5390 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/07/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 1800 | 1800 |  |  |  | 13/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 1800 | 1800
ADIDAS | 0902900771-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 327 | 2026-05-09 | 327 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900771 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 327 | 327 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-02-09 | 327 | 327 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-02-09 | 327 | 327
ADIDAS | 0902900873-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 347 | 2026-05-09 | 347 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902900873 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 31/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-05-08 | 347 | 347
ADIDAS | 0902900896-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 326 | 21/08/2026 | 326 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0902900896 LD0285 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 22/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 326 | 326 |  |  |  | 17/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 326 | 326 |  |  |  | 15/07/2026 | 22/07/2026 | 16/07/2026 | 24/07/2026 | 326 | 326
ADIDAS | 0902900910-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 337 | 2026-07-10 | 337 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900910 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 337 |  | 337 |  |  | 25/09/2026 | 26/09/2026 | 2026-04-08 | 2026-10-08 | 337 | 337 |  |  |  | 23/09/2026 | 24/09/2026 | 2026-01-08 | 2026-10-08 | 337 | 337
ADIDAS | 0902900938-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 358 | 30/09/2026 | 358 | AN | AN15/05/2026 | G2E | T-SHIRT | G2 | ok | (05/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900938 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 358 |  | 358 |  |  | 14/09/2026 | 15/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358 |  |  |  | 2026-11-09 | 2026-12-09 | 28/08/2026 | 2026-08-09 | 358 | 358
ADIDAS | 0902900970-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 2026-05-09 | 306 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902900970 KG3225 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-06-08 | 306 | 306 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 306 | 306 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 306 | 306
ADIDAS | 0902900989-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 741 | 2026-05-09 | 741 | AN | AN15/05/2026 | G2H | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900989 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 741 | 741 |  |  |  | 31/08/2026 | 2026-02-09 | 28/08/2026 | 2026-04-09 | 741 | 741 |  |  |  | 28/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 741 | 741
ADIDAS | 0902901030-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 309 | 31/08/2026 | 309 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0902901030 KX3650 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 309 | 309 |  |  |  | 16/07/2026 | 23/07/2026 | 16/07/2026 | 27/07/2026 | 309 | 309 |  |  |  | 14/07/2026 | 21/07/2026 | 16/07/2026 | 27/07/2026 | 309 | 309
ADIDAS | 0902901306-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 306 | 26/08/2026 | 306 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 18-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. T2 Libolon, PI Date 19-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901306 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 24/08/2026 | 2026-03-08 | 20/08/2026 | 306 | 306 |  |  |  | 29/07/2026 | 19/08/2026 | 28/07/2026 | 20/08/2026 | 306 | 306
ADIDAS | 0902901357-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 410 | 2026-09-09 | 410 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901357 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-07-08 | 2026-03-09 | 410 | 410 |  |  |  | 2026-03-08 | 2026-04-09 | 2026-04-08 | 2026-03-09 | 410 | 410
ADIDAS | 0902901389-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 377 | 2026-09-09 | 377 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901389 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-06-08 | 2026-03-09 | 377 | 377 |  |  |  | 2026-03-08 | 2026-04-09 | 30/07/2026 | 2026-05-09 | 377 | 377
ADIDAS | 0902901486-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 383 | 26/08/2026 | 383 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901486 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/07/2026 | M 3S WV WB LND |  | FW26 | 30/07/2026 | 24/08/2026 | 30/07/2026 | 20/08/2026 | 383 | 383 |  |  |  | 27/07/2026 | 19/08/2026 | 27/07/2026 | 21/08/2026 | 383 | 383
ADIDAS | 0902901531-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 312 | 2026-09-09 | 312 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | ok | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901531 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 2026-08-09 | 2026-10-08 | 2026-07-09 | 312 | 312 |  |  |  | 2026-05-08 | 2026-04-09 | 2026-05-08 | 2026-01-09 | 312 | 312
ADIDAS | 0902901569-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 507 | 2026-09-09 | 507 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901569 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-08-09 | 507 | 507 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 2026-02-09 | 507 | 507
ADIDAS | 0902901687-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4200 | 21/08/2026 | 4200 | AN | AN15/05/2026 | G3A | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901687 LE7510 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 21/07/2026 | 2026-04-08 | 20/07/2026 | 28/07/2026 | 4200 | 4200 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 28/07/2026 | 4200 | 4200
ADIDAS | 0902901795-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3000 | 21/08/2026 | 3000 | AN | AN15/05/2026 | G3A | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901795 LE7508 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/07/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 27/07/2026 | 14/08/2026 | 24/07/2026 | 2026-12-08 | 3000 | 3000 |  |  |  | 22/07/2026 | 2026-11-08 | 23/07/2026 | 2026-11-08 | 3000 | 3000
ADIDAS | 0902901874-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 6443 | 30/09/2026 | 6443 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 24/09: ex-fty. T2 Libolon, PI Date 09-Jun, actual receives 09-Jul. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901874 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 13/08/2026 | 17/09/2026 | 2026-12-08 | 15/09/2026 | 6443 | 5075 | 1368 |  | 426 | 2026-10-08 | 14/09/2026 | 31/07/2026 | 2026-11-09 | 6443 | 5827 | 616
ADIDAS | 0902901925-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 791 | 31/08/2026 | 791 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 29/08: ex-fty. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 29-May. T2 Libolon, PI Date 09-Jun, actual receives 18-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901925 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 28/07/2026 | 13/08/2026 | 28/07/2026 | 14/08/2026 | 791 | 791 |  |  |  | 23/07/2026 | 2026-10-08 | 25/07/2026 | 15/08/2026 | 791 | 791
ADIDAS | 0902902811-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 317 | 15/09/2026 | 317 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902811 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 317 | 317 |  |  |  | 2026-06-08 | 28/08/2026 | 23/07/2026 | 2026-05-08 | 317 | 317 |  |  |  | 2026-04-08 | 26/08/2026 | 22/07/2026 | 2026-04-08 | 317 | 317
ADIDAS | 0902902836-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 595 | 15/09/2026 | 595 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902836 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 595 | 592 | 3 |  | 9 | 2026-02-09 | 2026-11-09 | 24/08/2026 | 2026-08-09 | 595 | 595 |  |  |  | 31/08/2026 | 2026-09-09 | 24/08/2026 | 2026-08-09 | 595 | 595
ADIDAS | 0902902865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902902865 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 2026-04-08 | 22/07/2026 | 31/07/2026 | 369 | 369 |  |  |  | 16/07/2026 | 30/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369 |  |  |  | 14/07/2026 | 28/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369
ADIDAS | 0902902891-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 15/09/2026 | 322 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902891 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-10-08 | 2026-01-09 | 322 | 322 |  |  |  | 2026-06-08 | 29/08/2026 | 22/07/2026 | 2026-07-08 | 322 | 322 |  |  |  | 2026-04-08 | 27/08/2026 | 22/07/2026 | 2026-06-08 | 322 | 322
ADIDAS | 0902902948-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1044 | 2026-05-09 | 1044 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902902948 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 1044 | 1044 |  |  |  | 27/08/2026 | 2026-02-09 | 21/08/2026 | 2026-01-09 | 1044 | 1044 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 1044 | 1044
ADIDAS | 0902902967-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 455 | 31/08/2026 | 455 | SI | SI15/05/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902902967 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 455 | 455 |  |  |  | 20/08/2026 | 27/08/2026 | 2026-04-08 | 31/08/2026 | 455 | 455
ADIDAS | 0902902973-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 30/09/2026 | 880 | SA | SA15/05/2026 | G2M | T-SHIRT | G2 | ok | (08/06/2026) | 23/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902902973 KX3655 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 880 |  | 880 |  |  | 19/09/2026 | 21/09/2026 | 26/08/2026 | 14/09/2026 | 880 | 581 | 299 |  | 2 | 17/09/2026 | 18/09/2026 | 21/08/2026 | 14/09/2026 | 880 | 581 | 299 |  | 2
ADIDAS | 0902903099-1 KE8425 | WHITE | 120D | S2608MR0906A | 305 | 2026-07-10 | 305 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516333 | HT+PAD SUB PROCESS_V3 | 0902903099 KE8425 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess LS M WHITE |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 305 |  | 305 |  |  | 29/09/2026 | 30/09/2026 | 13/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 26/09/2026 | 28/09/2026 | 2026-11-08 | 27/08/2026 | 305 | 305
ADIDAS | 0902904399-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 172 | 31/08/2026 | 172 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 26-Jun, actual receives 18-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. T2 Libolon, PI Date 19-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902904399 KY4221 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 31/08/2026 | 2026-11-08 | 31/08/2026 | 172 | 172 |  |  |  | 2026-05-08 | 27/08/2026 | 2026-06-08 | 31/08/2026 | 172 | 172
ADIDAS | 0902904515-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 339 | 2026-05-09 | 339 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904515 LD0287 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 339 | 339 |  |  |  | 2026-06-08 | 29/08/2026 | 2026-01-08 | 31/08/2026 | 339 | 339 |  |  |  | 2026-04-08 | 27/08/2026 | 27/07/2026 | 31/08/2026 | 339 | 339
ADIDAS | 0902904537-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 329 | 15/09/2026 | 329 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904537 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 329 | 329 |  |  |  | 2026-06-08 | 29/08/2026 | 31/07/2026 | 2026-10-08 | 329 | 329 |  |  |  | 2026-04-08 | 27/08/2026 | 30/07/2026 | 2026-10-08 | 329 | 329
ADIDAS | 0902904602-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 696 | 2026-05-09 | 696 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904602 LD0284 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 696 | 696 |  |  |  | 28/07/2026 | 28/08/2026 | 27/07/2026 | 2026-01-08 | 696 | 696 |  |  |  | 24/07/2026 | 26/08/2026 | 25/07/2026 | 2026-01-08 | 696 | 696
ADIDAS | 0902904645-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 309 | 2026-05-09 | 309 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902904645 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 309 | 309 |  |  |  | 28/07/2026 | 28/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309 |  |  |  | 24/07/2026 | 26/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309
ADIDAS | 0902905667-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 530 | 23/09/2026 | 530 | SA | SA15/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902905667 LD0285 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 27/07/2026 | 21/08/2026 | 27/07/2026 | 20/08/2026 | 530 | 530 |  |  |  | 22/07/2026 | 18/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530 |  |  |  | 20/07/2026 | 13/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530
ADIDAS | 0902905691-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 336 | 2026-12-09 | 336 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902905691 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 24/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 336 | 336 |  |  |  | 21/07/2026 | 24/07/2026 | 16/07/2026 | 23/07/2026 | 336 | 336 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 336 | 336
ADIDAS | 0902906172-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 45 | 28/08/2026 | 45 | AT | AT15/05/2026 | G2P | SWEATSHIRT | G2 | (13/06/2026) | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 839055 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902906172 KG2925 | 31/07/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-08 | LFC LF HD |  | FW26 | 2026-07-08 | 2026-12-08 | 2026-10-08 | 2026-10-08 | 45 | 45 |  |  |  | 2026-04-08 | 2026-07-08 | 2026-08-08 | 2026-10-08 | 45 | 45
ADIDAS | 0902906579-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 15 | 23/09/2026 | 15 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902906579 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15 |  |  |  | 21/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15
ADIDAS | 0902906608-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 1321 | 15/09/2026 | 1321 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿) , PI Date 30-Jun, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902906608 LG9669 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-04-09 | W SL WV SK BLACK |  | SS27 | 2026-04-09 | 16/09/2026 | 2026-04-09 | 2026-07-09 | 1321 | 1136 | 185 |  |  | 2026-01-09 | 2026-12-09 | 22/08/2026 | 15/09/2026 | 1321 | 1306 | 15
ADIDAS | 0902906662-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 324 | 2026-05-09 | 324 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906662 LD0288 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 30/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 30/07/2026 | 20/07/2026 | 31/07/2026 | 324 | 324 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 324 | 324
ADIDAS | 0902906685-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 961 | 30/09/2026 | 961 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906685 LD0287 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 15/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 961 | 545 | 416 |  | 472 | 2026-11-09 | 15/09/2026 | 31/07/2026 | 2026-06-08 | 961 | 961 |  |  |  | 2026-09-09 | 2026-12-09 | 30/07/2026 | 2026-06-08 | 961 | 961
ADIDAS | 0902906698-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 3281 | 2026-05-09 | 3281 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0902906698 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 21/08/2026 | 2026-05-09 | 21/08/2026 | 2026-04-09 | 3281 | 3281 |  |  |  | 18/08/2026 | 2026-02-09 | 13/08/2026 | 2026-01-09 | 3281 | 3281 |  |  |  | 13/08/2026 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 3281 | 3281
ADIDAS | 0902906708-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 360 | 15/09/2026 | 360 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902906708 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 360 | 347 | 13 |  | 96 | 2026-02-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 360 | 360 |  |  |  | 31/08/2026 | 2026-09-09 | 31/07/2026 | 2026-04-08 | 360 | 360
ADIDAS | 0902906721-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 797 | 2026-05-09 | 797 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906721 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 797 | 797 |  |  |  | 2026-12-08 | 29/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797
ADIDAS | 0902906734-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 328 | 2026-05-09 | 328 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902906734 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 328 | 328 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 328 | 328 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 31/07/2026 | 328 | 328
ADIDAS | 0902906748-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 319 | 30/09/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906748 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 17/09/2026 | 14/09/2026 | 15/09/2026 | 319 | 287 | 32 |  | 108 | 2026-10-09 | 14/09/2026 | 26/08/2026 | 2026-02-09 | 319 | 319 |  |  |  | 2026-08-09 | 2026-11-09 | 24/08/2026 | 2026-02-09 | 319 | 319
ADIDAS | 0902906766-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 322 | 28/08/2026 | 322 | AN | AN15/05/2026 | G1E | T-SHIRT | G1 | ok | (05/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, actual receives 29-Apr (PO booking 25063167). T2 Fu Hsun, actual receives 23-Apr (PO booking 25063168). 516342 | HT SUB PROCESS_V1 | 0902906766 IT1824 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 20/07/2026 | 322 | 322 |  |  |  | 14/07/2026 | 16/07/2026 | 14/07/2026 | 17/07/2026 | 322 | 322 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 16/07/2026 | 322 | 322
ADIDAS | 0902906789-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 779 | 2026-05-09 | 779 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906789 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-06-08 | 2026-01-09 | 779 | 779 |  |  |  | 2026-03-08 | 29/08/2026 | 25/07/2026 | 31/08/2026 | 779 | 779 |  |  |  | 30/07/2026 | 27/08/2026 | 22/07/2026 | 31/08/2026 | 779 | 779
ADIDAS | 0902907417-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907417 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 308 | 308 |  |  |  | 23/07/2026 | 30/07/2026 | 18/07/2026 | 24/07/2026 | 308 | 308 |  |  |  | 21/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 308 | 308
ADIDAS | 0902907437-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 332 | 15/09/2026 | 332 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907437 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 29/07/2026 | 2026-03-08 | 332 | 332 |  |  |  | 23/07/2026 | 30/07/2026 | 21/07/2026 | 27/07/2026 | 332 | 332 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 24/07/2026 | 332 | 332
ADIDAS | 0902907453-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 443 | 15/09/2026 | 443 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907453 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-07-09 | 15/09/2026 | 443 | 443 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 14/09/2026 | 443 | 443 |  |  | 7
ADIDAS | 0902907472-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 812 | 23/09/2026 | 812 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902907472 KX3651 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 812 | 812 |  |  |  | 21/07/2026 | 30/07/2026 | 17/07/2026 | 30/07/2026 | 812 | 812 |  |  |  | 17/07/2026 | 28/07/2026 | 17/07/2026 | 28/07/2026 | 812 | 812
ADIDAS | 0902907504-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 652 | 2026-05-09 | 652 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902907504 KX3654 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-01-09 | 2026-07-08 | 2026-01-09 | 652 | 652 |  |  |  | 2026-03-08 | 28/08/2026 | 25/07/2026 | 2026-05-08 | 652 | 652 |  |  |  | 30/07/2026 | 26/08/2026 | 23/07/2026 | 28/07/2026 | 652 | 652
ADIDAS | 0902907522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 648 | 2026-05-09 | 648 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907522 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/07/2026 | 2026-11-08 | 29/07/2026 | 2026-07-08 | 648 | 648 |  |  |  | 23/07/2026 | 2026-06-08 | 25/07/2026 | 2026-01-08 | 648 | 648 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 28/07/2026 | 648 | 648
ADIDAS | 0902907548-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 671 | 2026-05-09 | 671 | SA | SA15/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907548 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 22/07/2026 | 30/07/2026 | 22/07/2026 | 29/07/2026 | 671 | 671 |  |  |  | 17/07/2026 | 27/07/2026 | 17/07/2026 | 22/07/2026 | 671 | 671 |  |  |  | 15/07/2026 | 23/07/2026 | 17/07/2026 | 28/07/2026 | 671 | 671
ADIDAS | 0902907571-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 12/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907571 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 308 | 308 |  |  | 25 | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-12-09 | 308 | 308 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-12-09 | 308 | 308
ADIDAS | 0902907642-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 376 | 21/08/2026 | 376 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 21/08: ex-fty (KN GLT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 28-May, actual receives 03-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 25-May (PO NT-351). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902907642 LG9660 | 31/07/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 376 | 376 |  |  |  | 27/07/2026 | 2026-11-08 | 22/07/2026 | 14/08/2026 | 376 | 371 | 5
ADIDAS | 0902908675-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 516 | 21/08/2026 | 516 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | ok | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902908675 LG9660 | 31/07/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 516 | 516 |  |  |  | 27/07/2026 | 2026-11-08 | 24/07/2026 | 30/07/2026 | 516 | 516
ADIDAS | 0902908709-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 684 | 15/09/2026 | 684 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 14-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902908709 LF0726 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 684 | 618 | 66 |  | 5 | 2026-04-09 | 14/09/2026 | 28/08/2026 | 14/09/2026 | 684 | 610 | 74 |  | 4
ADIDAS | 0902908777-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT15/05/2026 | G3E | SHORTS | G3 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 12-Jun, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902908777 KA8777 | 14/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/07/2026 | TIRO26L SHO M |  | SS27-L2L | 30/07/2026 | 2026-07-08 | 31/07/2026 | 2026-05-08 | 132 | 132 |  |  |  | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 132 | 132 |  |  |  | 23/07/2026 | 31/07/2026 | 13/07/2026 | 13/07/2026 | 132 | 132
ADIDAS | 0902909669-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 30/09/2026 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Jun, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902909669 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 144 | 144 |  |  |  | 29/08/2026 | 2026-04-09 | 26/08/2026 | 2026-07-09 | 144 | 142 | 2
ADIDAS | 0902909771-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902909771 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 13/08/2026 | 14/08/2026 | 8 | 8 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 2026-05-08 | 8 | 8
ADIDAS | 0902909794-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902909794 LG9660 | 31/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 8 | 8 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-11-08 | 18/08/2026 | 8 | 8
ADIDAS | 0902909815-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902909815 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 27/08/2026 | 29/08/2026 | 14/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902910585-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 858 | 2026-05-09 | 858 | SA | SA15/05/2026 | G2G,G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902910585 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 858 | 858 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 2026-03-09 | 858 | 858 |  |  |  | 27/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 858 | 858
ADIDAS | 0902910626-1 KX3712 | LIME TINT S27 | 120D | S2608MR0906A | 420 | 2026-05-09 | 420 | SI | SI15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902910626 KX3712 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess LS M LIME TINT S27 |  | SS27-TI-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 420 | 420 |  |  |  | 27/07/2026 | 2026-11-08 | 17/07/2026 | 24/07/2026 | 420 | 420 |  |  |  | 23/07/2026 | 2026-07-08 | 17/07/2026 | 24/07/2026 | 420 | 420
ADIDAS | 0902911467-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1312 | 23/09/2026 | 1312 | SA | SA15/05/2026 | G2G,G2I,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 834012 | HT+PAD SUB PROCESS_V3 | 0902911467 KF5311 | 14/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-03-08 | 2026-02-09 | 2026-03-08 | 2026-01-09 | 1312 | 1312 |  |  |  | 29/07/2026 | 29/08/2026 | 28/07/2026 | 2026-10-08 | 1312 | 1312 |  |  |  | 27/07/2026 | 27/08/2026 | 25/07/2026 | 2026-10-08 | 1312 | 1312
ADIDAS | 0902911942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 15 | 2026-05-09 | 15 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902911942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI-SPOMA | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 15 | 15 |  |  |  | 27/07/2026 | 30/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15 |  |  |  | 23/07/2026 | 28/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15
ADIDAS | 0902911985-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 351 | 2026-09-09 | 351 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902911985 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 351 | 351 |  |  |  | 29/08/2026 | 2026-01-09 | 13/08/2026 | 2026-07-09 | 351 | 351
ADIDAS | 0902912004-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 652 | 2026-05-09 | 652 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912004 LF0726 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 652 | 652 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 652 | 652
ADIDAS | 0902912022-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 335 | 2026-05-09 | 335 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902912022 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 335 | 335 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 20/08/2026 | 335 | 335
ADIDAS | 0902912038-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1761 | 2026-05-09 | 1761 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912038 LF0727 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 19/08/2026 | 1761 | 1761 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 1761 | 1761
ADIDAS | 0902912063-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 339 | 2026-05-09 | 339 | AN | AN15/05/2026 | G1E | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912063 LF0729 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 18/08/2026 | 339 | 339 |  |  |  | 2026-03-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 339 | 339
ADIDAS | 0902912066-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 544 | 2026-05-09 | 544 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912066 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-07-08 | 2026-12-08 | 544 | 544 |  |  |  | 2026-03-08 | 2026-10-08 | 31/07/2026 | 19/08/2026 | 544 | 544
ADIDAS | 0902912087-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 2026-05-09 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902912087 LG9669 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 144 | 144 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 19/08/2026 | 144 | 144
ADIDAS | 0902912093-1 LG9669 | BLACK | 120D | S2754WAS514C | 789 | 2026-09-09 | 789 | ID | ID15/05/2026 | G3B | SKIRT | G3 | ok | (04/06/2026) | 09/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 659018 | PRINT L3+PPA SUB PROCESS_V3 | 0902912093 LG9669 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 789 | 789 |  |  |  | 27/08/2026 | 2026-04-09 | 13/08/2026 | 2026-07-09 | 789 | 789
ADIDAS | 0902912125-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1399 | 2026-05-09 | 1399 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912125 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 1399 | 1399 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 19/08/2026 | 1399 | 1399
ADIDAS | 0902913684-1 KE8424 | BLACK | 60D | S2608MR0906A-MTF | 304 | 2026-05-09 | 304 | AN | AN15/05/2026 | G2G | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902913684 KE8424 | 2026-02-07 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-09 | Run Ess LS M BLACK |  | FW26 | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 304 | 304 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 304 | 304 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 304 | 304
ADIDAS | 0902913763-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2000 | 2026-12-09 | 2000 | AT | AT15/05/2026 | G3D,G3K | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913763 JD1881 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-08 | M 3S FT TC PT |  | FW26 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 2026-12-08 | 2000 | 2000 |  |  |  | 29/07/2026 | 2026-11-08 | 20/07/2026 | 2026-08-08 | 2000 | 2000
ADIDAS | 0902913788-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 720 | 2026-12-09 | 720 | AT | AT15/05/2026 | G3D | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913788 JE6346 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 720 | 720 |  |  |  | 21/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 720 | 720
ADIDAS | 0902913850-1 KY5990 | OLIVE FOUR S27/SEMI LUCID RED S25 | 105D | S2650MTR436 | 271 | 21/08/2026 | 271 | SA | SA15/05/2026 | G3E | PANTS | G3 | ok | (08/06/2026) | 21/08: ex-fty 516029 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902913850 KY5990 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | WE ALLSET 3S PT OLIVE FOUR S27/SEMI LUCID RED S25 |  | SS27-TI-SPOMA | 2026-12-08 | 14/08/2026 | 14/08/2026 | 14/08/2026 | 271 | 271 |  |  |  | 2026-07-08 | 2026-11-08 | 2026-12-08 | 14/08/2026 | 271 | 271 |  |  |  | 31/07/2026 | 2026-04-08 | 2026-11-08 | 14/08/2026 | 271 | 271
ADIDAS | 0902915780-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 60 | 15/09/2026 | 60 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902915780 LF0729 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-09-09 | 2026-10-09 | 60 | 58 | 2 |  |  | 2026-04-09 | 14/09/2026 | 21/08/2026 | 2026-01-09 | 60 | 60
ADIDAS | 0902915810-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 230 | 2026-05-09 | 230 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902915810 KX3713 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 230 | 230 |  |  |  | 29/08/2026 | 2026-02-09 | 30/07/2026 | 2026-06-08 | 230 | 230 |  |  |  | 27/08/2026 | 31/08/2026 | 27/07/2026 | 2026-04-08 | 230 | 230
ADIDAS | 0902915970-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 105 | 2026-05-09 | 105 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902915970 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI-SPOMA | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 21/07/2026 | 30/07/2026 | 22/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 17/07/2026 | 28/07/2026 | 21/07/2026 | 2026-03-08 | 105 | 105
ADIDAS | 0902916014-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 975 | 2026-05-09 | 975 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902916014 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI-SPOMA | 21/07/2026 | 2026-04-08 | 22/07/2026 | 2026-04-08 | 975 | 975 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 22/07/2026 | 975 | 975 |  |  |  | 14/07/2026 | 28/07/2026 | 15/07/2026 | 21/07/2026 | 975 | 975
ADIDAS | 0902916052-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 588 | 2026-05-09 | 588 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902916052 LD0930 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 588 | 588 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-04-09 | 588 | 588 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 588 | 588
ADIDAS | 0902916115-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 311 | 21/08/2026 | 311 | AN | AN15/05/2026 | G1E | T-SHIRT | G1 | ok | (05/06/2026) | 21/08: ex-fty. T2 Libolon, actual receives 29-Apr (PO booking 25063167). T2 Fu Hsun, actual receives 23-Apr (PO booking 25063168). 516029 | HT SUB PROCESS_V1 | 0902916115 IT1824 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | ADIZERO E TEE |  | FW26-SPOMA | 14/07/2026 | 16/07/2026 | 14/07/2026 | 15/07/2026 | 311 | 311 |  |  |  | 2026-10-07 | 14/07/2026 | 2026-09-07 | 13/07/2026 | 311 | 311 |  |  |  | 2026-09-07 | 13/07/2026 | 2026-09-07 | 2026-10-07 | 311 | 311
ADIDAS | 0902917391-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 327 | 15/09/2026 | 327 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902917391 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 327 | 327 |  |  |  | 2026-03-08 | 29/08/2026 | 30/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 30/07/2026 | 27/08/2026 | 29/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902917424-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 673 | 2026-05-09 | 673 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902917424 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 24/07/2026 | 2026-11-08 | 24/07/2026 | 2026-06-08 | 673 | 673 |  |  |  | 21/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 673 | 673 |  |  |  | 17/07/2026 | 2026-04-08 | 21/07/2026 | 2026-04-08 | 673 | 673
ADIDAS | 0902918914-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2400 | 21/08/2026 | 2400 | AN | AN15/05/2026 | G3G | PANTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902918914 KV7863 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/07/2026 | 24/07/2026 | 15/07/2026 | 24/07/2026 | 2400 | 2400 |  |  |  | 2026-08-07 | 21/07/2026 | 2026-10-07 | 27/07/2026 | 2400 | 2400
ADIDAS | 0902919030-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 5346 | 15/09/2026 | 5346 | AN | AN15/05/2026 | G3A,G3B,G3F,G3H | PANTS | G3 | ok | (13/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902919030 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 15/09/2026 | 14/08/2026 | 14/09/2026 | 5346 | 5240 | 106 |  | 5 | 2026-11-08 | 2026-11-09 | 2026-06-08 | 2026-10-09 | 5346 | 5273 | 73
ADIDAS | 0902926321-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 321 | 2026-05-09 | 321 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926321 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-11-08 | 321 | 321 |  |  |  | 2026-03-08 | 2026-10-08 | 30/07/2026 | 19/08/2026 | 321 | 321
ADIDAS | 0902926382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 200 | 30/09/2026 | 200 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 23/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926382 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 2026-08-09 | 29/08/2026 | 2026-07-09 | 200 | 200 |  |  |  | 21/08/2026 | 2026-04-09 | 26/08/2026 | 2026-09-09 | 200 | 200
ADIDAS | 0902930255-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 600 | 31/08/2026 | 600 | SI | SI21/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902930255 KX3713 | 21/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 600 | 600 |  |  |  | 30/07/2026 | 2026-11-08 | 28/07/2026 | 2026-07-08 | 600 | 600 |  |  |  | 28/07/2026 | 2026-07-08 | 28/07/2026 | 2026-08-08 | 600 | 600
ADIDAS | 0902930259-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 324 | 2026-07-10 | 324 | SA | SA21/05/2026 | G2Q | T-SHIRT | G2 | ok | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902930259 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 324 |  | 324 |  |  | 26/09/2026 | 26/09/2026 | 14/08/2026 | 2026-08-09 | 324 | 298 | 26 |  |  | 24/09/2026 | 24/09/2026 | 13/08/2026 | 2026-08-09 | 324 | 297 | 27
ADIDAS | 0902931107-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 449 | 31/08/2026 | 449 | SA | SA21/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 29/08: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902931107 LD0285 | 21/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/07/2026 | 29/07/2026 | 21/07/2026 | 28/07/2026 | 449 | 449 |  |  |  | 15/07/2026 | 24/07/2026 | 15/07/2026 | 22/07/2026 | 449 | 449 |  |  |  | 13/07/2026 | 22/07/2026 | 14/07/2026 | 22/07/2026 | 449 | 449
ADIDAS | 0902931109-1 KD0683 | OLIVE STRATA S23/BLACK | 90D | S2650MTR434 | 301 | 21/08/2026 | 301 | SI | SI21/05/2026 | G3E | SHORTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Libolon, PI Date 11-Jun, actual receives 23-Jun. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902931109 KD0683 | 2026-06-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 301 | 301 |  |  |  | 16/07/2026 | 21/07/2026 | 14/07/2026 | 22/07/2026 | 301 | 301 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 22/07/2026 | 301 | 301
ADIDAS | 0902932095-1 KY4154 | OLIVE FOUR S27/BLACK | 105D | F2654MESS608WVB | 113 | 21/08/2026 | 113 | SI | SI24/04/2026 | G1L | SHORTS | G1 | ok |  | 21/08: ex-fty. T2 Gistex, PI Date 07-Jun, actual receives 13-Jun. T2 Formosa, PI Date 07-Jun, using fabric stock. T2 Kahatex, PI Date 10-Jun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902932095 KY4154 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | M 3S CHELSEA B7 |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-03-08 | 2026-12-08 | 113 | 113 |  |  |  | 29/07/2026 | 2026-04-08 | 23/07/2026 | 2026-10-08 | 113 | 113
ADIDAS | 0902933082-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 315 | 28/08/2026 | 315 | AN | AN15/05/2026 | G3H | PANTS | G3 | ok |  | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933082 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/07/2026 | 2026-06-08 | 31/07/2026 | 2026-06-08 | 315 | 315 |  |  |  | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 315 | 315
ADIDAS | 0902933083-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 320 | 28/08/2026 | 320 | SI | SI15/05/2026 | G1H | JACKET | G1 | ok |  | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933083 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 320 | 320 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 320 | 320
ADIDAS | 0902940286-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 30 | 15/09/2026 | 30 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940286 LE0357 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 30 |  | 30 |  |  | 16/09/2026 | 16/09/2026 | 26/08/2026 | 2026-04-09 | 30 | 21 | 9
ADIDAS | 0902940338-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 499 | 15/10/2026 | 499 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 31-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940338 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 499 |  | 499 |  |  | 14/10/2026 | 15/10/2026 |  |  | 499 |  | 499
ADIDAS | 0902941400-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941400 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 4800 |  | 4800 |  |  | 21/09/2026 | 24/09/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902941469-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 3000 | 2026-07-10 | 3000 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902941469 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 3000 |  | 3000 |  |  | 18/09/2026 | 21/09/2026 |  |  | 3000 |  | 3000
ADIDAS | 0902942438-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 360 | 15/09/2026 | 360 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942438 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | M 3S CHELSEA B7 |  | FW26 | 15/09/2026 | 19/09/2026 |  |  | 360 |  | 360 |  |  | 2026-11-09 | 16/09/2026 | 2026-10-09 | 2026-11-09 | 360 | 351 | 9
ADIDAS | 0902942448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 05/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942448 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 29/08/2026 | 18/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-10-08 | 2026-04-09 | 450 | 450
ADIDAS | 0902942463-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 465 | 2026-09-09 | 465 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516419 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942463 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-07-09 | 465 | 465 |  |  |  | 2026-11-08 | 2026-03-09 | 2026-11-08 | 2026-07-09 | 465 | 465
ADIDAS | 0902942481-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5600 | 15/09/2026 | 5600 | SI | SI29/05/2026 | G3C,G3E | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942481 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | M 3S CHELSEA B7 |  | FW26 | 2026-07-09 | 16/09/2026 | 2026-04-09 | 14/09/2026 | 5600 | 5600 |  |  | 1730 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 14/09/2026 | 5600 | 5557 | 43 |  | 9
ADIDAS | 0902942491-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942491 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-11-09 | 315 | 315
ADIDAS | 0902942496-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942496 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 27/08/2026 | 2026-03-09 | 315 | 315 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-02-09 | 315 | 315
ADIDAS | 0902942511-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942511 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-04-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 400 | 400
ADIDAS | 0902942519-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 390 | 15/09/2026 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942519 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 390 | 251 | 139 |  |  | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 390 | 303 | 87
ADIDAS | 0902942533-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 2026-09-09 | 900 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942533 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-07-09 | 900 | 900 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-05-09 | 900 | 900
ADIDAS | 0902942573-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 125 | 21/08/2026 | 125 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 830009 | PRINT L3 SUB PROCESS_V3 | 0902942573 IU0217 | 13/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 20/07/2026 | 14/07/2026 | 20/07/2026 | 125 | 125 |  |  |  | 2026-09-07 | 15/07/2026 | 2026-06-07 | 15/07/2026 | 125 | 125
ADIDAS | 0902945010-1 LE8187 | BLACK | 105D | S2754MAS513 | 331 | 15/09/2026 | 331 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945010 LE8187 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 17/09/2026 | 2026-08-09 | 2026-09-09 | 331 | 286 | 45 |  |  | 2026-02-09 | 14/09/2026 | 27/08/2026 | 2026-04-09 | 331 | 292 | 39
ADIDAS | 0902945087-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 401 | 30/09/2026 | 401 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945087 LE8188 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 401 |  | 401 |  |  | 2026-12-09 | 15/09/2026 |  |  | 401 |  | 401
ADIDAS | 0902946696-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 856 | 15/09/2026 | 856 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946696 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 15/09/2026 |  |  | 856 |  | 856 |  |  | 2026-11-09 | 2026-11-09 | 20/08/2026 | 2026-09-09 | 856 | 834 | 22
ADIDAS | 0902946778-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 341 | 21/08/2026 | 341 | SI | SI29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946778 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 29/07/2026 | 29/07/2026 | 29/07/2026 | 29/07/2026 | 341 | 341 |  |  |  | 24/07/2026 | 24/07/2026 | 27/07/2026 | 29/07/2026 | 341 | 341
ADIDAS | 0902946844-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 357 | 15/09/2026 | 357 | SI | SI29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946844 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 15/09/2026 | 15/09/2026 |  |  | 357 |  | 357 |  |  | 2026-11-09 | 2026-11-09 | 2026-01-08 | 2026-10-09 | 357 | 352 | 5
ADIDAS | 0902946897-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 510 | 21/08/2026 | 510 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 10-Jun. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946897 KW2924 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 510 | 510 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 510 | 510
ADIDAS | 0902946950-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 400 | 2026-12-09 | 400 | SI | SI29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946950 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/08/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-11-09 | 400 | 400 |  |  |  | 26/08/2026 | 2026-09-09 | 2026-05-08 | 2026-11-09 | 400 | 400
ADIDAS | 0902947001-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 324 | 21/08/2026 | 324 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902947001 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 28/07/2026 | 2026-06-08 | 28/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 2026-03-08 | 25/07/2026 | 2026-05-08 | 324 | 324
ADIDAS | 0902947050-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1120 | 15/10/2026 | 1120 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902947050 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-11 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 1120 |  | 1120 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902947104-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 1030 | 21/08/2026 | 1030 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902947104 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-05-08 | 1030 | 1030 |  |  |  | 22/07/2026 | 2026-03-08 | 23/07/2026 | 2026-11-08 | 1030 | 1030
ADIDAS | 0902948665-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 219 | 21/08/2026 | 219 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 800187 | PRINT L3 SUB PROCESS_V3 | 0902948665 IU0217 | 13/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 20/07/2026 | 13/07/2026 | 17/07/2026 | 219 | 219 |  |  |  | 2026-09-07 | 15/07/2026 | 2026-06-07 | 17/07/2026 | 219 | 219
ADIDAS | 0902948698-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 561 | 2026-07-10 | 561 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948698 LG9668 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 561 |  | 561 |  |  | 2026-08-10 | 2026-10-10 |  |  | 561 |  | 561
ADIDAS | 0902948720-1 LG9669 | BLACK | 120D | S2754WAS514C | 283 | 30/09/2026 | 283 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902948720 LG9669 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | W SL WV SK BLACK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 283 |  | 283 |  |  | 28/09/2026 | 29/09/2026 | 24/08/2026 | 2026-05-09 | 283 | 240 | 43
ADIDAS | 0902948739-1 LG9669 | BLACK | 120D | S2754WAS514C | 316 | 30/09/2026 | 316 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948739 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W SL WV SK BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 316 |  | 316 |  |  | 14/09/2026 | 15/09/2026 | 28/08/2026 | 2026-05-09 | 316 | 307 | 9
ADIDAS | 0902948754-1 LG9669 | BLACK | 120D | S2754WAS514C | 416 | 2026-07-10 | 416 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948754 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W SL WV SK BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 416 |  | 416 |  |  | 2026-08-10 | 2026-10-10 |  |  | 416 |  | 416
ADIDAS | 0902948775-1 LG9669 | BLACK | 120D | S2754WAS514C | 497 | 30/09/2026 | 497 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948775 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W SL WV SK BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 497 |  | 497 |  |  | 26/09/2026 | 28/09/2026 | 26/08/2026 | 2026-12-09 | 497 | 460 | 37
ADIDAS | 0902949162-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 377 | 15/09/2026 | 377 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949162 LF0725 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 16/09/2026 | 2026-10-09 | 2026-12-09 | 377 | 372 | 5 |  |  | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 377 | 374 | 3
ADIDAS | 0902949302-1 LF0723 | BLACK | 105D | S2754MAS511B | 402 | 30/09/2026 | 402 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949302 LF0723 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | M SL WV SHO BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 402 |  | 402 |  |  | 19/09/2026 | 21/09/2026 |  |  | 402 |  | 402
ADIDAS | 0902950353-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 300 | 28/08/2026 | 300 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902950353 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV WB |  | SS27 | 2026-03-08 | 24/08/2026 | 2026-03-08 | 24/08/2026 | 300 | 300 |  |  |  | 29/07/2026 | 19/08/2026 | 23/07/2026 | 31/08/2026 | 300 | 300
ADIDAS | 0902951279-1 LH3758 | BLACK | 120D | S2754WAS518B | 500 | 15/10/2026 | 500 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951279 LH3758 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | W SL WV BR PT BLACK |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 500 |  | 500 |  |  | 2026-12-10 | 13/10/2026 |  |  | 500 |  | 500
ADIDAS | 0902951331-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 500 | 30/09/2026 | 500 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951331 LD5446 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 26/09/2026 |  |  | 500 |  | 500
ADIDAS | 0902951411-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 302 | 26/08/2026 | 302 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951411 LE4307 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/07/2026 | 14/08/2026 | 28/07/2026 | 18/08/2026 | 302 | 302 |  |  |  | 23/07/2026 | 2026-11-08 | 22/07/2026 | 21/08/2026 | 302 | 302
ADIDAS | 0902951455-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 598 | 21/08/2026 | 598 | AN | AN29/05/2026 | G2I,G2J | T-SHIRT | G2 | ok | (27/06/2026) | 21/08: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0902951455 KX0126 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 29/07/2026 | 31/07/2026 | 28/07/2026 | 30/07/2026 | 598 | 598 |  |  |  | 24/07/2026 | 28/07/2026 | 21/07/2026 | 29/07/2026 | 598 | 598
ADIDAS | 0902951458-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 136 | 31/08/2026 | 136 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty (S4EU). T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951458 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 14/08/2026 | 21/08/2026 | 136 | 136 |  |  |  | 2026-11-08 | 20/08/2026 | 31/07/2026 | 2026-10-08 | 136 | 136
ADIDAS | 0902951503-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 922 | 31/08/2026 | 922 | SI | SI29/05/2026 | G1H,G1L | JACKET | G1 | ok | ok | 29/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902951503 LE4307 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 21/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 922 | 922 |  |  |  | 18/08/2026 | 27/08/2026 | 20/08/2026 | 29/08/2026 | 922 | 922
ADIDAS | 0902951560-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 302 | 15/10/2026 | 302 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951560 LG9665 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 302 |  | 302 |  |  | 25/09/2026 | 28/09/2026 |  |  | 302 |  | 302
ADIDAS | 0902951622-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 498 | 15/10/2026 | 498 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951622 LG9661 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 498 |  | 498 |  |  | 28/09/2026 | 2026-01-10 |  |  | 498 |  | 498
ADIDAS | 0902952735-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 318 | 26/08/2026 | 318 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul. T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902952735 KW2909 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | W 3S WV WB |  | SS27 | 24/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 318 | 318 |  |  |  | 21/07/2026 | 2026-03-08 | 20/07/2026 | 28/07/2026 | 318 | 318
ADIDAS | 0902952799-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 598 | 21/08/2026 | 598 | AN | AN29/05/2026 | G2I,G2J | T-SHIRT | G2 | ok | (27/06/2026) | 21/08: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0902952799 LC8884 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | M RESORT T BLACK |  | SS27 | 29/07/2026 | 31/07/2026 | 28/07/2026 | 30/07/2026 | 598 | 598 |  |  |  | 24/07/2026 | 28/07/2026 | 24/07/2026 | 30/07/2026 | 598 | 598
ADIDAS | 0902953067-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 327 | 2026-07-10 | 327 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953067 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 327 |  | 327 |  |  | 2026-05-10 | 2026-06-10 |  |  | 327 |  | 327
ADIDAS | 0902953119-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 139 | 31/08/2026 | 139 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953119 LE8181 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 139 | 139 |  |  |  | 21/08/2026 | 27/08/2026 | 13/08/2026 | 20/08/2026 | 139 | 139
ADIDAS | 0902953315-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 307 | 23/09/2026 | 307 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953315 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 14/08/2026 | 2026-01-09 | 307 | 307 |  |  |  | 2026-11-08 | 29/08/2026 | 28/07/2026 | 2026-11-08 | 307 | 307 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 28/07/2026 | 307 | 307
ADIDAS | 0902953364-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 472 | 23/09/2026 | 472 | SA | SA29/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953364 LD0288 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 21/08/2026 | 31/07/2026 | 20/08/2026 | 472 | 472 |  |  |  | 27/07/2026 | 18/08/2026 | 25/07/2026 | 30/07/2026 | 472 | 472 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 29/07/2026 | 472 | 472
ADIDAS | 0902953400-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 312 | 23/09/2026 | 312 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 18/09: ex-fty 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902953400 KY5988 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 312 | 312 |  |  |  | 27/07/2026 | 2026-11-08 | 30/07/2026 | 2026-08-08 | 312 | 312 |  |  |  | 20/07/2026 | 2026-04-08 | 30/07/2026 | 2026-06-08 | 312 | 312
ADIDAS | 0902953446-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 542 | 23/09/2026 | 542 | SA | SA29/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953446 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 542 | 542 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 31/07/2026 | 542 | 542 |  |  |  | 28/07/2026 | 2026-04-08 | 24/07/2026 | 30/07/2026 | 542 | 542
ADIDAS | 0902953533-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 327 | 30/09/2026 | 327 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902953533 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 327 |  | 327 |  |  | 15/09/2026 | 16/09/2026 | 27/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 2026-12-09 | 14/09/2026 | 25/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902953571-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 479 | 30/09/2026 | 479 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 23/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953571 KX3651 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 479 |  | 479 |  |  | 23/09/2026 | 23/09/2026 | 31/07/2026 | 2026-08-08 | 479 | 479 |  |  |  | 21/09/2026 | 21/09/2026 | 30/07/2026 | 2026-07-08 | 479 | 479
ADIDAS | 0902953689-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 130 | 21/08/2026 | 130 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953689 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-10-08 | 13/08/2026 | 130 | 130 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 20/08/2026 | 130 | 130
ADIDAS | 0902953736-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 305 | 28/08/2026 | 305 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953736 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-05-08 | 29/08/2026 | 305 | 305
ADIDAS | 0902953783-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 370 | 21/08/2026 | 370 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953783 KV7963 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 370 | 370 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 370 | 370
ADIDAS | 0902953842-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 26/08/2026 | 300 | AN | AN29/05/2026 | G1L | JACKET | G1 | ok | (27/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun (PO NT-353). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953842 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-06-08 | 2026-07-08 | 2026-07-08 | 14/08/2026 | 300 | 300 |  |  |  | 2026-03-08 | 2026-04-08 | 30/07/2026 | 22/08/2026 | 300 | 300
ADIDAS | 0902953974-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 305 | 28/08/2026 | 305 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902953974 KV7963 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 305 | 305 |  |  |  | 22/07/2026 | 2026-03-08 | 23/07/2026 | 2026-05-08 | 305 | 305
ADIDAS | 0902954045-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954045 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 313 |  | 313 |  |  | 25/09/2026 | 25/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902954068-1 KT7552 | BLACK | 60D | F26FBGFXP104 | 1344 | 21/08/2026 | 1344 | SI | SI29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902954068 KT7552 | 15/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/07/2026 | SOC CAT GFX T BLACK |  | SS27 | 31/07/2026 | 2026-06-08 | 30/07/2026 | 2026-05-08 | 1344 | 1344 |  |  |  | 28/07/2026 | 2026-03-08 | 21/07/2026 | 2026-05-08 | 1344 | 1344
ADIDAS | 0902954088-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 246 | 15/09/2026 | 246 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954088 LG9661 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 246 | 202 | 44 |  | 4 | 2026-04-09 | 2026-11-09 | 28/08/2026 | 15/09/2026 | 246 | 222 | 24
ADIDAS | 0902954666-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 2026-07-10 | 200 | SA | SA29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954666 LE8181 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 200 |  | 200 |  |  | 2026-07-10 | 2026-08-10 |  |  | 200 |  | 200
ADIDAS | 0902954719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 162 | 15/09/2026 | 162 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954719 LE8186 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 14/09/2026 | 16/09/2026 | 14/09/2026 | 15/09/2026 | 162 | 84 | 78 |  | 3 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 15/09/2026 | 162 | 121 | 41
ADIDAS | 0902954826-1 LE8187 | BLACK | 105D | S2754MAS513 | 152 | 15/09/2026 | 152 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954826 LE8187 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 152 | 64 | 88 |  |  | 2026-10-09 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 152 | 140 | 12
ADIDAS | 0902954882-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 174 | 15/09/2026 | 174 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954882 LE8188 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 16/09/2026 | 14/09/2026 | 15/09/2026 | 174 | 116 | 58 |  | 101 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 15/09/2026 | 174 | 161 | 13
ADIDAS | 0902954999-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 609 | 2026-07-10 | 609 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954999 LF0726 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 609 |  | 609 |  |  | 2026-05-10 | 2026-07-10 |  |  | 609 |  | 609
ADIDAS | 0902955058-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 206 | 23/09/2026 | 206 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955058 LF0727 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 206 | 206 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-07-08 | 31/08/2026 | 206 | 206
ADIDAS | 0902955123-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 356 | 15/09/2026 | 356 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (S4EU). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955123 LF0726 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-04-09 | 2026-12-09 | 356 | 334 | 22 |  |  | 2026-01-09 | 14/09/2026 | 27/08/2026 | 2026-10-09 | 356 | 326 | 30
ADIDAS | 0902955656-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 590 | 30/09/2026 | 590 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955656 KX3655 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 590 | 135 | 455 |  |  | 2026-11-09 | 2026-12-09 | 2026-07-09 | 14/09/2026 | 590 | 568 | 22 |  | 2 | 2026-09-09 | 2026-10-09 | 2026-07-09 | 14/09/2026 | 590 | 567 | 23 |  | 2
ADIDAS | 0902955699-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 441 | 30/09/2026 | 441 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955699 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 441 | 419 | 22 |  | 413 | 2026-08-09 | 2026-11-09 | 2026-10-08 | 26/08/2026 | 441 | 441 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-10-08 | 24/08/2026 | 441 | 441
ADIDAS | 0902955746-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 324 | 30/09/2026 | 324 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902955746 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-09 | 17/09/2026 | 2026-07-09 | 2026-08-09 | 324 | 278 | 46 |  |  | 2026-04-09 | 14/09/2026 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1 |  |  | 2026-02-09 | 2026-11-09 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1
ADIDAS | 0902955843-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 30/09/2026 | 301 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955843 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M SL WV SHO BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 19/09/2026 | 21/09/2026 | 2026-10-09 | 2026-10-09 | 301 | 120 | 181
ADIDAS | 0902955890-1 LF0723 | BLACK | 105D | S2754MAS511B | 137 | 2026-09-09 | 137 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955890 LF0723 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | M SL WV SHO BLACK |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 137 | 137 |  |  |  | 29/08/2026 | 2026-03-09 | 18/08/2026 | 28/08/2026 | 137 | 137
ADIDAS | 0902955942-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 417 | 2026-07-10 | 417 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955942 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 417 |  | 417 |  |  | 19/10/2026 | 20/10/2026 |  |  | 417 |  | 417
ADIDAS | 0902955987-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 322 | 22/09/2026 | 322 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955987 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-08-09 | 2026-10-09 | 322 | 322 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 14/09/2026 | 322 | 322 |  |  | 8
ADIDAS | 0902956072-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 187 | 2026-05-09 | 187 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956072 LD5446 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 187 | 187 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 187 | 187
ADIDAS | 0902956169-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 302 | 15/09/2026 | 302 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956169 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | M SL WV TT BLACK |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 264 | 38 |  | 1 | 2026-04-09 | 14/09/2026 | 2026-06-08 | 14/09/2026 | 302 | 284 | 18 |  | 5
ADIDAS | 0902956226-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 645 | 2026-07-10 | 645 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956226 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TT BLACK |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 645 |  | 645 |  |  | 2026-07-10 | 2026-10-10 |  |  | 645 |  | 645
ADIDAS | 0902956293-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 203 | 23/09/2026 | 203 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956293 LF0729 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 203 | 203 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 203 | 202 | 1
ADIDAS | 0902956352-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 177 | 15/09/2026 | 177 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956352 LF0726 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 17/09/2026 | 2026-04-09 | 14/09/2026 | 177 | 177 |  |  | 23 | 27/08/2026 | 14/09/2026 | 13/08/2026 | 14/09/2026 | 177 | 180 | -3 | 3 | 20
ADIDAS | 0902956415-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 605 | 2026-07-10 | 605 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956415 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 605 |  | 605 |  |  | 2026-03-10 | 2026-05-10 | 2026-04-09 | 2026-11-09 | 605 | 216 | 389
ADIDAS | 0902956471-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 305 | 2026-07-10 | 305 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956471 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 305 |  | 305 |  |  | 2026-05-10 | 2026-06-10 |  |  | 305 |  | 305
ADIDAS | 0902956523-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 301 | 28/08/2026 | 301 | SI | SI29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902956523 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-07-08 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 301 | 301 |  |  |  | 2026-04-08 | 20/08/2026 | 2026-05-08 | 26/08/2026 | 301 | 301
ADIDAS | 0902956639-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 747 | 28/08/2026 | 747 | SI | SI29/05/2026 | G3B,G3E | PANTS | G3 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902956639 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 28/08/2026 | 2026-07-08 | 27/08/2026 | 747 | 747 |  |  |  | 2026-03-08 | 24/08/2026 | 2026-05-08 | 26/08/2026 | 747 | 747
ADIDAS | 0902956678-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 599 | 15/09/2026 | 599 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956678 LG9661 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-09 | 15/09/2026 | 2026-05-09 | 15/09/2026 | 599 | 406 | 193 |  | 1 | 28/08/2026 | 2026-11-09 | 26/08/2026 | 15/09/2026 | 599 | 523 | 76
ADIDAS | 0902956729-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 438 | 2026-07-10 | 438 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956729 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 438 |  | 438 |  |  | 25/09/2026 | 28/09/2026 |  |  | 438 |  | 438
ADIDAS | 0902956767-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 133 | 15/09/2026 | 133 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 24/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956767 LG9664 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 133 |  | 133 |  |  | 16/09/2026 | 18/09/2026 | 2026-10-09 | 2026-10-09 | 133 | 109 | 24
ADIDAS | 0902956798-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 310 | 15/09/2026 | 310 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956798 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 310 |  | 310 |  |  | 15/09/2026 | 16/09/2026 | 2026-01-09 | 2026-08-09 | 310 | 242 | 68
ADIDAS | 0902956842-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 710 | 30/09/2026 | 710 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956842 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W SL WV TT BLACK |  | SS27 | 16/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 710 | 22 | 688 |  |  | 2026-12-09 | 15/09/2026 | 29/08/2026 | 2026-07-09 | 710 | 599 | 111
ADIDAS | 0902956973-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 139 | 30/09/2026 | 139 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956973 LG9666 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 139 |  | 139 |  |  | 15/09/2026 | 15/09/2026 | 31/08/2026 | 2026-04-09 | 139 | 138 | 1
ADIDAS | 0902957021-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 495 | 2026-07-10 | 495 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957021 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 495 |  | 495 |  |  | 2026-05-10 | 2026-06-10 |  |  | 495 |  | 495
ADIDAS | 0902957107-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 334 | 2026-07-10 | 334 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957107 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W SL WV PT LEGEND IVY S19 |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 334 |  | 334 |  |  | 2026-02-10 | 2026-05-10 |  |  | 334 |  | 334
ADIDAS | 0902957145-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 300 | 30/09/2026 | 300 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957145 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 15/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902958225-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 270 | 28/08/2026 | 270 | AN | AN29/05/2026 | G3E | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 05-Jun (PO NT-347). 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958225 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-10-08 | 270 | 270 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 2026-10-08 | 270 | 270
ADIDAS | 0902958280-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 262 | 31/08/2026 | 262 | SI | SI29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958280 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 2026-12-08 | 2026-06-08 | 2026-11-08 | 262 | 262 |  |  |  | 30/07/2026 | 2026-07-08 | 29/07/2026 | 2026-11-08 | 262 | 262
ADIDAS | 0902958335-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 239 | 28/08/2026 | 239 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958335 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-08 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 239 | 239 |  |  |  | 2026-04-08 | 20/08/2026 | 2026-07-08 | 24/08/2026 | 239 | 239
ADIDAS | 0902958409-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 608 | 31/08/2026 | 608 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 29-May (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958409 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-10-08 | 608 | 608 |  |  |  | 29/07/2026 | 2026-07-08 | 27/07/2026 | 2026-05-08 | 608 | 608
ADIDAS | 0902958471-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 747 | 28/08/2026 | 747 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 27-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958471 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-05-08 | 14/08/2026 | 747 | 747 |  |  |  | 29/07/2026 | 2026-10-08 | 31/07/2026 | 2026-05-08 | 747 | 747
ADIDAS | 0902958524-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 28/08/2026 | 313 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958524 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 2026-06-08 | 2026-04-08 | 2026-06-08 | 313 | 313 |  |  |  | 29/07/2026 | 2026-03-08 | 31/07/2026 | 13/08/2026 | 313 | 313
ADIDAS | 0902958584-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 303 | 31/08/2026 | 303 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902958584 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 2026-12-08 | 2026-05-08 | 2026-07-08 | 303 | 303 |  |  |  | 29/07/2026 | 2026-07-08 | 27/07/2026 | 2026-01-08 | 303 | 303
ADIDAS | 0902959184-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 201 | 30/09/2026 | 201 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959184 LG9673 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 201 |  | 201 |  |  | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 201 | 66 | 135
ADIDAS | 0902959230-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 428 | 2026-07-10 | 428 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959230 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 428 |  | 428 |  |  | 2026-05-10 | 2026-06-10 |  |  | 428 |  | 428
ADIDAS | 0902959276-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 205 | 30/09/2026 | 205 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959276 LG9675 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W SL WV PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 205 |  | 205 |  |  | 16/09/2026 | 17/09/2026 |  |  | 205 |  | 205
ADIDAS | 0902959319-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 23/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959319 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | W SL WV PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959364-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 308 | 2026-07-10 | 308 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959364 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W SL WV PT BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 308 |  | 308 |  |  | 2026-02-10 | 2026-05-10 |  |  | 308 |  | 308
ADIDAS | 0902959405-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 356 | 2026-09-09 | 356 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959405 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-02-09 | 356 | 356 |  |  |  | 20/08/2026 | 31/08/2026 | 2026-12-08 | 2026-07-09 | 356 | 356
ADIDAS | 0902959452-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1380 | 30/09/2026 | 1380 | SI | SI29/05/2026 | G3D | SHORTS | G3 | (12/07/2026) | ok | Waiting fabric. DRC 0002-T2 Gistex, material delayed, PI Date 12-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959452 KY4155 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 16/09/2026 | 18/09/2026 |  |  | 1380 |  | 1380 |  |  | 2026-12-09 | 15/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0902959473-1 LH3758 | BLACK | 120D | S2754WAS518B | 182 | 30/09/2026 | 182 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959473 LH3758 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV BR PT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 182 |  | 182 |  |  | 15/09/2026 | 15/09/2026 |  |  | 182 |  | 182
ADIDAS | 0902959508-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 3010 | 15/09/2026 | 3010 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959508 KY6510 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | M 3S CHELSEA B7 |  | FW26 | 15/09/2026 | 19/09/2026 | 15/09/2026 | 15/09/2026 | 3010 | 325 | 2685 |  |  | 2026-11-09 | 16/09/2026 | 2026-10-09 | 15/09/2026 | 3010 | 2744 | 266
ADIDAS | 0902959557-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 419 | 2026-09-09 | 419 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959557 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 |  | FW26 | 29/08/2026 | 2026-07-09 | 29/08/2026 | 2026-07-09 | 419 | 419 |  |  |  | 26/08/2026 | 2026-03-09 | 13/08/2026 | 2026-07-09 | 419 | 419
ADIDAS | 0902959562-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 134 | 30/09/2026 | 134 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959562 LH3761 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 134 |  | 134 |  |  | 17/09/2026 | 19/09/2026 |  |  | 134 |  | 134
ADIDAS | 0902959597-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 799 | 15/09/2026 | 799 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | ok | 15/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959597 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 799 | 265 | 534 |  |  | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 799 | 735 | 64
ADIDAS | 0902959610-1 LH3758 | BLACK | 120D | S2754WAS518B | 640 | 2026-07-10 | 640 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959610 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W SL WV BR PT BLACK |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 640 |  | 640 |  |  | 2026-09-10 | 2026-12-10 |  |  | 640 |  | 640
ADIDAS | 0902959964-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516461 | HT+PAD SUB PROCESS_V3 | 0902959964 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 300 | 300 |  |  | 18 | 2026-05-09 | 2026-11-09 | 2026-10-08 | 15/08/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-10-08 | 14/08/2026 | 300 | 300
ADIDAS | 0902960005-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902960005 KX3655 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 320 |  | 320 |  |  | 29/09/2026 | 29/09/2026 |  |  | 320 |  | 320 |  |  | 26/09/2026 | 26/09/2026 |  |  | 320 |  | 320
ADIDAS | 0902960049-1 LF0723 | BLACK | 105D | S2754MAS511B | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902960049 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 420 |  | 420 |  |  | 20/10/2026 | 22/10/2026 |  |  | 420 |  | 420
ADIDAS | 0902960084-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 2026-03-09 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960084 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 29/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-04-08 | 2026-12-08 | 300 | 300
ADIDAS | 0902960126-1 JZ7808 | BLACK | 120D | S2608WR0900 | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902960126 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 22/09/2026 | 22/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 18/09/2026 | 2026-07-08 | 15/08/2026 | 313 | 312 | 1 |  |  | 16/09/2026 | 16/09/2026 | 2026-07-08 | 14/08/2026 | 313 | 313
ADIDAS | 0902960651-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 480 | 2026-05-09 | 480 | SI | SI29/05/2026 | G3A,G3C | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960651 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 480 | 480 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-04-08 | 13/08/2026 | 480 | 480
ADIDAS | 0902960711-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 500 | 15/09/2026 | 500 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960711 LH4535 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 17/09/2026 | 2026-10-09 | 15/09/2026 | 500 | 465 | 35 |  |  | 2026-05-09 | 14/09/2026 | 13/08/2026 | 2026-03-09 | 500 | 497 | 3
ADIDAS | 0902960763-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 244 | 15/09/2026 | 244 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960763 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 17/09/2026 | 2026-10-09 | 2026-11-09 | 244 | 238 | 6 |  |  | 2026-05-09 | 14/09/2026 | 15/08/2026 | 28/08/2026 | 244 | 234 | 10
ADIDAS | 0902960819-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 306 | 28/08/2026 | 306 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | (25/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960819 LH4535 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 2026-03-08 | 2026-07-08 | 306 | 306 |  |  |  | 24/07/2026 | 2026-05-08 | 28/07/2026 | 2026-07-08 | 306 | 306
ADIDAS | 0902961677-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 309 | 2026-07-10 | 309 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961677 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 309 |  | 309 |  |  | 2026-09-10 | 2026-12-10 |  |  | 309 |  | 309
ADIDAS | 0902961728-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 887 | 30/09/2026 | 887 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902961728 LH3759 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 887 |  | 887 |  |  | 16/09/2026 | 17/09/2026 |  |  | 887 |  | 887
ADIDAS | 0902961768-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 313 | 30/09/2026 | 313 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961768 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 313 |  | 313 |  |  | 16/09/2026 | 17/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902961819-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 341 | 2026-07-10 | 341 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961819 LH3761 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 341 |  | 341 |  |  | 2026-09-10 | 2026-12-10 |  |  | 341 |  | 341
ADIDAS | 0902962271-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 3004 | 28/08/2026 | 3004 | SI | SI29/05/2026 | G1H,G1L | JACKET | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 20-Aug. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962271 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-12-08 | 28/08/2026 | 14/08/2026 | 28/08/2026 | 3004 | 3004 |  |  |  | 2026-07-08 | 24/08/2026 | 2026-07-08 | 2026-07-09 | 3004 | 3004
ADIDAS | 0902962301-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 500 | 2026-03-09 | 500 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962301 KV7963 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 500 | 500 |  |  |  | 22/07/2026 | 30/07/2026 | 23/07/2026 | 2026-05-08 | 500 | 500
ADIDAS | 0902962328-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962328 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 15/09/2026 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 300 | 290 | 10
ADIDAS | 0902962445-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962445 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-08-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-02-09 | 2026-08-09 | 400 | 400
ADIDAS | 0902962469-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962469 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-02-09 | 315 | 315 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-02-09 | 315 | 315
ADIDAS | 0902962488-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 390 | 2026-09-09 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962488 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-07-09 | 2026-08-09 | 390 | 390 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 390 | 390
ADIDAS | 0902962541-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962541 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 330 | 330 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-08-09 | 330 | 330
ADIDAS | 0902962571-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516241 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962571 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-08-09 | 330 | 330 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-09-09 | 330 | 330
ADIDAS | 0902962600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962600 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 450 | 450 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0902962624-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 3000 | 2026-12-09 | 3000 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 27-Aug. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962624 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-11-09 | 3000 | 3000 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 3000 | 3000
ADIDAS | 0902962644-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962644 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-02-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 315 | 315
ADIDAS | 0902966036-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966036 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-08-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-07-09 | 14/09/2026 | 65 | 65 |  |  | 2
ADIDAS | 0902966052-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966052 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 27 | 20 | 7
ADIDAS | 0902966064-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966064 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-08-09 | 65 | 65 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-04-09 | 65 | 65
ADIDAS | 0902966089-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966089 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-08-09 | 2026-10-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 2026-10-09 | 22 | 22 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-05-09 | 2026-10-09 | 22 | 22
ADIDAS | 0902966098-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 65 | 30/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966098 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 65 | 65 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 65 | 63 | 2
ADIDAS | 0902966111-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 27 | 30/09/2026 | 27 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902966111 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 16/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902966123-1 KY5991 | PURE BLUE S27/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 20-Aug. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966123 KY5991 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 35SSHO PURE BLUE S27/WHITE |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 2026-07-09 | 22 | 22 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-05-09 | 2026-05-09 | 22 | 22
ADIDAS | 0902966135-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 50 | 21/08/2026 | 50 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902966135 LG9660 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 2026-03-08 | 50 | 50 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 28/07/2026 | 50 | 50
ADIDAS | 0902970651-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 992 | 15/09/2026 | 992 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. T2 Kahatex, PI Date 06-Aug, actual receives 25-Jun. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902970651 KA2571 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 992 | 992 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-07-09 | 2026-11-09 | 992 | 992 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-07-09 | 2026-10-09 | 992 | 992
ADIDAS | 0902970663-1 LG9669 | BLACK | 120D | S2754WAS514C | 27 | 30/09/2026 | 27 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970663 LG9669 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/09/2026 | W SL WV SK BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 27 |  | 27 |  |  | 26/09/2026 | 28/09/2026 | 29/08/2026 | 2026-01-09 | 27 | 17 | 10
ADIDAS | 0902970676-1 LE0355 | BLACK | 105D | S2754MAS514 | 65 | 30/09/2026 | 65 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970676 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | M SL WV CU PT BLACK |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 65 |  | 65 |  |  | 30/09/2026 | 2026-03-10 | 2026-01-09 | 2026-01-09 | 65 | 61 | 4
ADIDAS | 0902970685-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 65 | 22/09/2026 | 65 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970685 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-08-09 | 65 | 65
ADIDAS | 0902970699-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 27 | 15/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970699 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 14/09/2026 | 27 | 23 | 4 |  | 8
ADIDAS | 0902970711-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 27 | 30/09/2026 | 27 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | ok | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970711 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | W SL WV PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 27 |  | 27 |  |  | 16/09/2026 | 17/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902970727-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 54 | 30/09/2026 | 54 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970727 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 54 |  | 54 |  |  | 15/09/2026 | 15/09/2026 | 2026-01-09 | 2026-03-09 | 54 | 46 | 8
ADIDAS | 0902970843-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 23/09/2026 | 322 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970843 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-06-08 | 2026-11-08 | 322 | 322 |  |  |  | 2026-03-08 | 2026-06-08 | 29/07/2026 | 31/07/2026 | 322 | 322 |  |  |  | 30/07/2026 | 2026-04-08 | 24/07/2026 | 28/07/2026 | 322 | 322
ADIDAS | 0902970859-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 462 | 30/09/2026 | 462 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970859 KX3654 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 17/09/2026 | 2026-07-09 | 2026-08-09 | 462 | 416 | 46 |  |  | 2026-02-09 | 14/09/2026 | 2026-08-08 | 15/08/2026 | 462 | 462 |  |  |  | 31/08/2026 | 2026-11-09 | 2026-08-08 | 14/08/2026 | 462 | 462
ADIDAS | 0902970876-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 503 | 15/10/2026 | 503 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970876 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 503 |  | 503 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 24/08/2026 | 503 | 503 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 503 | 503
ADIDAS | 0902970893-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 433 | 15/10/2026 | 433 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970893 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 433 |  | 433 |  |  | 24/09/2026 | 25/09/2026 |  |  | 433 |  | 433 |  |  | 22/09/2026 | 23/09/2026 |  |  | 433 |  | 433
ADIDAS | 0902970931-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 365 | 23/09/2026 | 365 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970931 LD0285 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/08/2026 | 24/08/2026 | 24/08/2026 | 24/08/2026 | 365 | 365 |  |  |  | 14/08/2026 | 19/08/2026 | 29/07/2026 | 2026-01-08 | 365 | 365 |  |  |  | 2026-12-08 | 14/08/2026 | 25/07/2026 | 2026-01-08 | 365 | 365
ADIDAS | 0902970945-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 479 | 2026-05-09 | 479 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty 684009 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902970945 KC8152 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 31/08/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 479 | 479 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-09 | 2026-10-09 | 479 | 479 |  |  |  | 19/08/2026 | 27/08/2026 | 2026-03-09 | 2026-07-09 | 479 | 479
ADIDAS | 0902970957-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 658 | 30/09/2026 | 658 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902970957 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 658 |  | 658 |  |  | 2026-12-09 | 14/09/2026 | 31/07/2026 | 2026-05-08 | 658 | 658 |  |  |  | 2026-10-09 | 2026-11-09 | 30/07/2026 | 2026-05-08 | 658 | 658
ADIDAS | 0902970975-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 322 | 30/09/2026 | 322 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970975 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 322 |  | 322 |  |  | 21/09/2026 | 21/09/2026 | 2026-04-09 | 14/09/2026 | 322 | 322 |  |  | 2 | 18/09/2026 | 18/09/2026 | 2026-03-09 | 14/09/2026 | 322 | 322 |  |  | 2
ADIDAS | 0902970994-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 65 | 15/09/2026 | 65 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970994 LE0357 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 19/09/2026 | 19/09/2026 |  |  | 65 |  | 65 |  |  | 16/09/2026 | 16/09/2026 | 24/08/2026 | 14/09/2026 | 65 | 56 | 9 |  | 9
ADIDAS | 0902971007-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 325 | 30/09/2026 | 325 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902971007 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 325 |  | 325 |  |  | 2026-12-09 | 14/09/2026 | 2026-03-08 | 2026-12-08 | 325 | 325 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-12-08 | 325 | 325
ADIDAS | 0902971009-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 433 | 30/09/2026 | 433 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902971009 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 17/09/2026 |  |  | 433 |  | 433 |  |  | 2026-10-09 | 14/09/2026 | 2026-10-08 | 20/08/2026 | 433 | 433 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-10-08 | 19/08/2026 | 433 | 433
ADIDAS | 0902971034-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902971034 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 24/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 65 | 65 |  |  |  | 19/08/2026 | 27/08/2026 | 31/07/2026 | 26/08/2026 | 65 | 65
ADIDAS | 0902971040-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 674 | 30/09/2026 | 674 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902971040 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 24/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 674 |  | 674 |  |  | 21/09/2026 | 21/09/2026 |  |  | 674 |  | 674 |  |  | 18/09/2026 | 18/09/2026 |  |  | 674 |  | 674
ADIDAS | 0902971044-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 54 | 30/09/2026 | 54 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902971044 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 54 |  | 54 |  |  | 15/09/2026 | 15/09/2026 |  |  | 54 |  | 54
ADIDAS | 0902971059-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 562 | 15/09/2026 | 562 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902971059 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-11-09 | 562 | 562 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-11-09 | 562 | 562 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-08-09 | 2026-11-09 | 562 | 562
ADIDAS | 0902971713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1094 | 23/09/2026 | 1094 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902971713 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-12-08 | 1094 | 1094 |  |  |  | 2026-03-08 | 2026-10-08 | 2026-04-08 | 14/08/2026 | 1094 | 1094
ADIDAS | 0902972065-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 514 | 30/09/2026 | 514 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972065 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 514 |  | 514 |  |  | 24/09/2026 | 26/09/2026 |  |  | 514 |  | 514
ADIDAS | 0902972095-1 LE8187 | BLACK | 105D | S2754MAS513 | 320 | 15/09/2026 | 320 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972095 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-09 | M SL WV TP PT BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-11-09 | 15/09/2026 | 320 | 185 | 135 |  | 17 | 2026-04-09 | 2026-12-09 | 29/08/2026 | 2026-12-09 | 320 | 291 | 29
ADIDAS | 0902972345-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 503 | 28/08/2026 | 503 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516400 | EMBRO SUB PROCESS_V1 | 0902972345 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | M FEELCOZY PANT |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-05-08 | 2026-07-08 | 503 | 503 |  |  |  | 31/07/2026 | 2026-04-08 | 21/07/2026 | 30/07/2026 | 503 | 503
ADIDAS | 0902972376-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 4291 | 2026-05-09 | 4291 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 04/09: ex-fty 516400 | EMBRO SUB PROCESS_V1 | 0902972376 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | M FEELCOZY PANT |  | FW26 | 27/07/2026 | 2026-07-08 | 27/07/2026 | 2026-07-08 | 4291 | 4291 |  |  |  | 22/07/2026 | 2026-04-08 | 18/07/2026 | 2026-05-08 | 4291 | 4291
ADIDAS | 0902972647-1 KY7166 | BLACK | 75D | S2706CHCC008-MTF | 865 | 21/08/2026 | 865 | AN | AN29/05/2026 | G2Q | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902972647 KY7166 | 16/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 21/07/2026 | CC DNA SHO BLACK |  | SS27 | 21/07/2026 | 2026-03-08 | 23/07/2026 | 29/07/2026 | 865 | 865 |  |  |  | 16/07/2026 | 29/07/2026 | 16/07/2026 | 28/07/2026 | 865 | 865
ADIDAS | 0902972659-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1 | 2026-05-09 | 1 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972659 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1 |  |  |  | 24/08/2026 | 27/08/2026 | 14/08/2026 | 14/08/2026 | 1 | 1
ADIDAS | 0902972672-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1 | 23/09/2026 | 1 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972672 LF0726 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1 |  | 1 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1 |  | 1
ADIDAS | 0902972688-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 803 | 21/08/2026 | 803 | ID | ID29/05/2026 | G2Q | SHORTS | G2 | ok | (02/07/2026) | 21/08: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902972688 KY7184 | 16/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 27/07/2026 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 27/07/2026 | 2026-03-08 | 27/07/2026 | 2026-03-08 | 803 | 803 |  |  |  | 22/07/2026 | 29/07/2026 | 18/07/2026 | 2026-03-08 | 803 | 803
ADIDAS | 0902972711-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 56 | 2026-05-09 | 56 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | ok | 04/09: ex-fty 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902972711 KY5988 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-08 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-07-08 | 56 | 56 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 31/07/2026 | 56 | 56 |  |  |  | 22/07/2026 | 31/07/2026 | 30/07/2026 | 30/07/2026 | 56 | 56
ADIDAS | 0902972724-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 349 | 15/10/2026 | 349 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972724 LG9666 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | W SL WV TT BLACK |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 349 |  | 349 |  |  | 2026-01-10 | 2026-01-10 |  |  | 349 |  | 349
ADIDAS | 0902972758-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 330 | 15/10/2026 | 330 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972758 LG9661 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-01-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 330 |  | 330 |  |  | 28/09/2026 | 2026-01-10 |  |  | 330 |  | 330
ADIDAS | 0902972883-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 480 | 15/09/2026 | 480 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972883 LF0727 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 17/09/2026 | 27/08/2026 | 2026-10-09 | 480 | 479 | 1 |  |  | 19/08/2026 | 14/09/2026 | 24/08/2026 | 2026-09-09 | 480 | 480
ADIDAS | 0902972938-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 486 | 23/09/2026 | 486 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902972938 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 486 | 486 |  |  |  | 2026-12-08 | 29/08/2026 | 29/07/2026 | 31/07/2026 | 486 | 486 |  |  |  | 2026-10-08 | 27/08/2026 | 28/07/2026 | 31/07/2026 | 486 | 486
ADIDAS | 0902973524-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1200 | 15/10/2026 | 1200 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 19-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902973524 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 19/10/2026 | 22/10/2026 |  |  | 1200 |  | 1200 |  |  | 15/10/2026 | 19/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902973619-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 1000 | 23/09/2026 | 1000 | AN | AN29/05/2026 | G3G,G3H,G3J | PANTS | G3 | ok | (19/06/2026) | 18/09: ex-fty. T2 Libolon, PI Date 31-May, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973619 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-04-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 1000 | 1000 |  |  |  | 30/07/2026 | 13/08/2026 | 31/07/2026 | 15/08/2026 | 1000 | 1000
ADIDAS | 0902973747-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 356 | 21/08/2026 | 356 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973747 KV7863 | 13/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 20/07/2026 | 24/07/2026 | 356 | 356 |  |  |  | 15/07/2026 | 21/07/2026 | 16/07/2026 | 24/07/2026 | 356 | 356
ADIDAS | 0902973776-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 23/09/2026 | 300 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902973776 KF5311 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 300 | 300 |  |  |  | 2026-03-08 | 29/08/2026 | 29/07/2026 | 30/07/2026 | 300 | 300 |  |  |  | 30/07/2026 | 27/08/2026 | 27/07/2026 | 29/07/2026 | 300 | 300
ADIDAS | 0902973810-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 399 | 2026-05-09 | 399 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902973810 LE5609 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/07/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 31/08/2026 | 31/07/2026 | 31/08/2026 | 399 | 399 |  |  |  | 27/07/2026 | 27/08/2026 | 30/07/2026 | 2026-07-08 | 399 | 399 |  |  |  | 20/07/2026 | 19/08/2026 | 30/07/2026 | 2026-06-08 | 399 | 399
ADIDAS | 0902973847-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (07/07/2026) |  | 07/09: ex-fty. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock, T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973847 LC5741 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902973850-1 LF0723 | BLACK | 105D | S2754MAS511B | 433 | 15/09/2026 | 433 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902973850 LF0723 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | M SL WV SHO BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-05-09 | 2026-11-09 | 433 | 433 |  |  |  | 2026-02-09 | 2026-10-09 | 15/08/2026 | 2026-11-09 | 433 | 433
ADIDAS | 0902973860-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (29/06/2026) | ok | 07/09: ex-fty. T2 Kahatex, using fabric stock. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973860 KY6616 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 3S WV WB LND |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 26/08/2026 | 1 | 1 |  |  |  | 19/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 1 | 1
ADIDAS | 0902973878-1 LC5739 | OLIVE FOUR S27/BLACK | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (10/07/2026) |  | 07/09: ex-fty. T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 01-Jul, actual receives 09-Jul. T2 Kahatex, PI Date 07-Jul, using fabric stock. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973878 LC5739 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 3S WV WB LND OLIVE FOUR S27/BLACK |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902974162-1 LE8187 | BLACK | 105D | S2754MAS513 | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974162 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-11-08 | 2026-11-08 | 8 | 8 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-08-08 | 2026-11-08 | 8 | 8
ADIDAS | 0902974179-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974179 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902974202-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 542 | 2026-05-09 | 542 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974202 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 542 | 542 |  |  |  | 29/08/2026 | 2026-02-09 | 14/08/2026 | 28/08/2026 | 542 | 542
ADIDAS | 0902974244-1 LE8187 | BLACK | 105D | S2754MAS513 | 311 | 2026-05-09 | 311 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974244 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-09 | M SL WV TP PT BLACK |  | SS27 | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 311 | 311 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-05-08 | 2026-04-09 | 311 | 311
ADIDAS | 0902974263-1 LE8187 | BLACK | 105D | S2754MAS513 | 1425 | 2026-05-09 | 1425 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974263 LE8187 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 1425 | 1425 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-06-08 | 2026-11-09 | 1425 | 1405 | 20
ADIDAS | 0902974284-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1436 | 15/09/2026 | 1436 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974284 LD5446 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-07-09 | 16/09/2026 | 2026-07-09 | 14/09/2026 | 1436 | 1436 |  |  | 22 | 2026-03-09 | 2026-12-09 | 2026-12-08 | 14/09/2026 | 1436 | 1441 | -5 | 5 | 9
ADIDAS | 0902974308-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 353 | 2026-09-09 | 353 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974308 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-07-09 | 353 | 353 |  |  |  | 29/08/2026 | 2026-03-09 | 13/08/2026 | 2026-02-09 | 353 | 353
ADIDAS | 0902974332-1 LE8187 | BLACK | 105D | S2754MAS513 | 370 | 2026-05-09 | 370 | SI | SI29/05/2026 | G3D,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974332 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-03-09 | 14/08/2026 | 2026-01-09 | 370 | 370 |  |  |  | 2026-03-08 | 31/08/2026 | 2026-05-08 | 14/09/2026 | 370 | 370 |  |  | 2
ADIDAS | 0902975286-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 29 | 23/09/2026 | 29 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975286 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-10-08 | 2026-10-08 | 29 | 29 |  |  |  | 2026-03-08 | 2026-06-08 | 2026-01-08 | 2026-01-08 | 29 | 29 |  |  |  | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 29 | 29
ADIDAS | 0902975694-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1272 | 30/09/2026 | 1272 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902975694 LD0287 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 18/09/2026 | 21/09/2026 |  |  | 1272 |  | 1272 |  |  | 15/09/2026 | 17/09/2026 | 2026-05-09 | 2026-10-09 | 1272 | 1268 | 4 |  |  | 2026-12-09 | 15/09/2026 | 2026-04-09 | 14/09/2026 | 1272 | 1269 | 3 |  | 1
ADIDAS | 0902975717-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1200 | 2026-07-10 | 1200 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 600000 | EMBRO SUB PROCESS_V1 | 0902975717 LE5390 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 1200 |  | 1200 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0902975773-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-10 | 4800 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902975773 LE5391 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 4800 |  | 4800 |  |  | 25/09/2026 | 29/09/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902975811-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 80 | 30/09/2026 | 80 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975811 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 16/09/2026 | 17/09/2026 |  |  | 80 |  | 80 |  |  | 2026-12-09 | 14/09/2026 | 2026-04-08 | 2026-04-08 | 80 | 80 |  |  |  | 2026-10-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 80 | 80
ADIDAS | 0902975837-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 20 | 21/08/2026 | 20 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975837 LG9660 | 13/08/2026 | KAHATEX CIJERAH | PERU | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 2026-03-08 | 20 | 20 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 2026-03-08 | 20 | 20
ADIDAS | 0902975855-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 31 | 30/09/2026 | 31 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975855 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 31 | 31 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 31/07/2026 | 31 | 31 |  |  |  | 31/08/2026 | 2026-03-09 | 27/07/2026 | 28/07/2026 | 31 | 31
ADIDAS | 0902975887-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 2400 | 2026-07-10 | 2400 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975887 LE7510 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-09-10 | 13/10/2026 |  |  | 2400 |  | 2400
ADIDAS | 0902975946-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | 23/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Sep. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975946 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 25/09/2026 | 2026-03-10 |  |  | 2400 |  | 2400 |  |  | 22/09/2026 | 30/09/2026 | 26/08/2026 | 2026-07-09 | 2400 | 1864 | 536
ADIDAS | 0902975975-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975975 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-09 | 19/09/2026 | 2026-03-09 | 15/09/2026 | 2400 | 1609 | 791 |  |  | 2026-02-09 | 16/09/2026 | 22/08/2026 | 2026-08-09 | 2400 | 2356 | 44
ADIDAS | 0902976008-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3600 | 2026-07-10 | 3600 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976008 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 19/10/2026 | 23/10/2026 |  |  | 3600 |  | 3600 |  |  | 15/10/2026 | 20/10/2026 |  |  | 3600 |  | 3600
ADIDAS | 0902976049-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 2026-07-10 | 6000 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976049 LE7509 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27 | 2026-06-10 | 14/10/2026 |  |  | 6000 |  | 6000 |  |  | 2026-02-10 | 2026-10-10 |  |  | 6000 |  | 6000
ADIDAS | 0902976088-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 2026-07-10 | 8400 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976088 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 14/10/2026 | 26/10/2026 |  |  | 8400 |  | 8400 |  |  | 2026-10-10 | 22/10/2026 |  |  | 8400 |  | 8400
ADIDAS | 0902976952-1 LG9669 | BLACK | 120D | S2754WAS514C | 8 | 15/10/2026 | 8 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902976952 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 8 |  | 8 |  |  | 2026-10-10 | 13/10/2026 |  |  | 8 |  | 8
ADIDAS | 0902976974-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 8 | 15/10/2026 | 8 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902976974 LF0726 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 18/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 8 |  | 8 |  |  | 15/09/2026 | 17/09/2026 |  |  | 8 |  | 8
ADIDAS | 0902977037-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 508 | 21/08/2026 | 508 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902977037 KV7863 | 13/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 21/07/2026 | 24/07/2026 | 508 | 508 |  |  |  | 15/07/2026 | 21/07/2026 | 17/07/2026 | 28/07/2026 | 508 | 508
ADIDAS | 0902977144-1 LE8187 | BLACK | 105D | S2754MAS513 | 342 | 2026-05-09 | 342 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902977144 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 14/08/2026 | 342 | 342 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-05-08 | 2026-04-09 | 342 | 342
ADIDAS | 0902977685-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1796 | 30/09/2026 | 1796 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 29/09: ex-fty (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902977685 KX3655 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 23/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 1796 |  | 1796 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1796 |  | 1796 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1796 |  | 1796
ADIDAS | 0902977729-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 466 | 15/10/2026 | 466 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | HT+PAD SUB PROCESS_V3 | 0902977729 LD0288 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 466 | 466 |  |  |  | 2026-12-08 | 29/08/2026 | 25/07/2026 | 2026-06-08 | 466 | 466 |  |  |  | 2026-10-08 | 27/08/2026 | 24/07/2026 | 2026-05-08 | 466 | 466
ADIDAS | 0902977769-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 497 | 30/09/2026 | 497 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977769 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 21/09/2026 |  |  | 497 |  | 497 |  |  | 17/09/2026 | 17/09/2026 |  |  | 497 |  | 497 |  |  | 15/09/2026 | 15/09/2026 |  |  | 497 |  | 497
ADIDAS | 0902977806-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 198 | 23/09/2026 | 198 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977806 LD0288 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 198 | 198 |  |  |  | 2026-12-08 | 29/08/2026 | 30/07/2026 | 2026-07-08 | 198 | 198 |  |  |  | 2026-10-08 | 27/08/2026 | 29/07/2026 | 2026-06-08 | 198 | 198
ADIDAS | 0902977843-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 200 | 15/10/2026 | 200 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902977843 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 200 |  | 200 |  |  | 21/09/2026 | 22/09/2026 |  |  | 200 |  | 200 |  |  | 18/09/2026 | 19/09/2026 |  |  | 200 |  | 200
ADIDAS | 0902977919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 154 | 30/09/2026 | 154 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977919 LD0288 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 154 | 154 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 2026-01-08 | 154 | 154 |  |  |  | 31/08/2026 | 2026-03-09 | 30/07/2026 | 2026-01-08 | 154 | 154
ADIDAS | 0902977969-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 879 | 30/09/2026 | 879 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977969 KX3655 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 879 |  | 879 |  |  | 18/09/2026 | 19/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879
ADIDAS | 0902978212-1 LE0355 | BLACK | 105D | S2754MAS514 | 2156 | 30/09/2026 | 2156 | SA | SA29/05/2026 | G3C | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978212 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-10 | M SL WV CU PT BLACK |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 2156 |  | 2156 |  |  | 30/09/2026 | 2026-03-10 | 2026-01-09 | 2026-12-09 | 2156 | 2044 | 112
ADIDAS | 0902978235-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 2398 | 30/09/2026 | 2398 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978235 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 2398 | 471 | 1927 |  |  | 2026-10-09 | 14/09/2026 | 2026-11-08 | 20/08/2026 | 2398 | 2398 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-11-08 | 19/08/2026 | 2398 | 2398
ADIDAS | 0902978263-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1644 | 30/09/2026 | 1644 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978263 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 1644 |  | 1644 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1557 | 87 |  |  | 16/09/2026 | 17/09/2026 | 2026-08-09 | 2026-11-09 | 1644 | 1556 | 88
ADIDAS | 0902978291-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 2268 | 30/09/2026 | 2268 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978291 LD0287 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 2268 |  | 2268 |  |  | 17/09/2026 | 18/09/2026 | 2026-07-09 | 15/09/2026 | 2268 | 2205 | 63 |  |  | 15/09/2026 | 16/09/2026 | 2026-07-09 | 14/09/2026 | 2268 | 2209 | 59 |  | 76
ADIDAS | 0902978328-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1623 | 30/09/2026 | 1623 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978328 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-10 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 1623 |  | 1623 |  |  | 29/09/2026 | 2026-02-10 |  |  | 1623 |  | 1623
ADIDAS | 0902978352-1 LF0718 | BLACK | 105D | S2754MAS512B | 1886 | 15/09/2026 | 1886 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978352 LF0718 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 1886 |  | 1886 |  |  | 16/09/2026 | 19/09/2026 | 15/09/2026 | 15/09/2026 | 1886 | 194 | 1692
ADIDAS | 0902978382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1442 | 15/09/2026 | 1442 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978382 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 17/09/2026 | 2026-02-09 | 2026-11-09 | 1442 | 1423 | 19 |  |  | 27/08/2026 | 14/09/2026 | 28/08/2026 | 15/09/2026 | 1442 | 1438 | 4
ADIDAS | 0902978413-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 1394 | 15/09/2026 | 1394 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978413 LG9670 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | W SL WV PT AURORA COFFEE S26 |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 1394 | 1311 | 83 |  | 365 | 2026-05-09 | 2026-11-09 | 2026-07-09 | 2026-10-09 | 1394 | 1338 | 56
ADIDAS | 0902978440-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 767 | 30/09/2026 | 767 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978440 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 767 | 195 | 572 |  |  | 2026-11-09 | 2026-12-09 | 14/09/2026 | 14/09/2026 | 767 | 261 | 506 |  | 261
ADIDAS | 0902978469-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 491 | 30/09/2026 | 491 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978469 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 491 |  | 491 |  |  | 14/09/2026 | 15/09/2026 |  |  | 491 |  | 491
ADIDAS | 0902978495-1 LE8187 | BLACK | 105D | S2754MAS513 | 1353 | 15/09/2026 | 1353 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978495 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 17/09/2026 | 2026-04-09 | 2026-09-09 | 1353 | 1115 | 238 |  |  | 2026-02-09 | 14/09/2026 | 28/08/2026 | 2026-10-09 | 1353 | 1232 | 121
ADIDAS | 0902978547-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1342 | 15/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 15/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978547 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 17/09/2026 | 26/08/2026 | 14/09/2026 | 1342 | 1140 | 202 |  | 12 | 19/08/2026 | 14/09/2026 | 21/08/2026 | 15/09/2026 | 1342 | 1224 | 118 |  | 2
ADIDAS | 0902978578-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 870 | 30/09/2026 | 870 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 20-Jun, actual receives 06-AUg (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978578 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV TT BLACK |  | SS27 | 22/09/2026 | 26/09/2026 |  |  | 870 |  | 870 |  |  | 18/09/2026 | 23/09/2026 | 28/08/2026 | 2026-03-09 | 870 | 537 | 333
ADIDAS | 0902978593-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 655 | 21/08/2026 | 655 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902978593 JE6372 | 13/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/07/2026 | M 3S FT SWT |  | FW26 | 20/07/2026 | 2026-07-08 | 21/07/2026 | 31/07/2026 | 655 | 655 |  |  |  | 15/07/2026 | 2026-04-08 | 15/07/2026 | 31/07/2026 | 655 | 655
ADIDAS | 0902978632-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2607 | 21/08/2026 | 2607 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902978632 KV7863 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/07/2026 | 13/08/2026 | 23/07/2026 | 2026-12-08 | 2607 | 2607 |  |  |  | 20/07/2026 | 2026-10-08 | 21/07/2026 | 2026-12-08 | 2607 | 2607
ADIDAS | 0902978872-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 339 | 2026-09-09 | 339 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978872 LD5446 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-03-09 | 339 | 339 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 20/08/2026 | 339 | 339
ADIDAS | 0902978908-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 2026-05-09 | 300 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978908 LE8181 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-03-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0902978941-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 23/09/2026 | 300 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978941 LF0729 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 18/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0902978973-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 347 | 15/09/2026 | 347 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual recieves 27-Jun (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978973 LF0726 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-07-09 | 2026-12-09 | 347 | 343 | 4 |  |  | 2026-01-09 | 14/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 347
ADIDAS | 0902978999-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1030 | 2026-12-09 | 1030 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902978999 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 31/08/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1030 | 1030 |  |  |  | 27/08/2026 | 2026-04-09 | 31/07/2026 | 2026-07-08 | 1030 | 1030 |  |  |  | 24/08/2026 | 2026-02-09 | 31/07/2026 | 2026-06-08 | 1030 | 1030
ADIDAS | 0902979020-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 1006 | 2026-12-09 | 1006 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979020 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-05-09 | 2026-08-09 | 1006 | 1006 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-03-08 | 13/08/2026 | 1006 | 1006 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-01-08 | 2026-12-08 | 1006 | 1006
ADIDAS | 0902979047-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 339 | 21/08/2026 | 339 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902979047 KV7863 | 13/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 22/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 22/07/2026 | 28/07/2026 | 339 | 339 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 27/07/2026 | 339 | 339
ADIDAS | 0902979072-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 408 | 31/08/2026 | 408 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979072 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 21/08/2026 | 2026-10-08 | 21/08/2026 | 408 | 408 |  |  |  | 2026-06-08 | 18/08/2026 | 29/07/2026 | 31/07/2026 | 408 | 408 |  |  |  | 2026-04-08 | 13/08/2026 | 24/07/2026 | 28/07/2026 | 408 | 408
ADIDAS | 0902979096-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 495 | 31/08/2026 | 495 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979096 KX3655 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 28/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/08/2026 | 29/08/2026 | 28/08/2026 | 29/08/2026 | 495 | 495 |  |  |  | 24/08/2026 | 26/08/2026 | 21/08/2026 | 29/08/2026 | 495 | 495 |  |  |  | 20/08/2026 | 21/08/2026 | 21/08/2026 | 27/08/2026 | 495 | 495
ADIDAS | 0902979127-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 530 | 31/08/2026 | 530 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979127 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 18/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 530 | 530 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-10-08 | 18/08/2026 | 530 | 530 |  |  |  | 2026-10-08 | 18/08/2026 | 2026-10-08 | 14/08/2026 | 530 | 530
ADIDAS | 0902979825-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 2026-12-09 | 123 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902979825 LD5446 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 123 | 123 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 123 | 123
ADIDAS | 0902980168-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 574 | 30/09/2026 | 574 | SI | SI29/05/2026 | G3F | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980168 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 574 |  | 574 |  |  | 22/09/2026 | 24/09/2026 |  |  | 574 |  | 574
ADIDAS | 0902980203-1 LE8187 | BLACK | 105D | S2754MAS513 | 812 | 15/09/2026 | 812 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980203 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 17/09/2026 |  |  | 812 |  | 812 |  |  | 2026-10-09 | 14/09/2026 | 2026-05-09 | 2026-12-09 | 812 | 462 | 350
ADIDAS | 0902980238-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 521 | 21/08/2026 | 521 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 28-May. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980238 KZ3205 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/07/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 17/07/2026 | 2026-07-08 | 20/07/2026 | 2026-06-08 | 521 | 521 |  |  |  | 14/07/2026 | 2026-04-08 | 15/07/2026 | 19/08/2026 | 521 | 521
ADIDAS | 0902980266-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 612 | 21/08/2026 | 612 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 12-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980266 KZ3198 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 27/07/2026 | 14/08/2026 | 28/07/2026 | 13/08/2026 | 612 | 612 |  |  |  | 22/07/2026 | 2026-11-08 | 24/07/2026 | 14/08/2026 | 612 | 612
ADIDAS | 0902980284-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 356 | 26/08/2026 | 356 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980284 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 2026-10-08 | 21/08/2026 | 356 | 356 |  |  |  | 2026-11-08 | 20/08/2026 | 27/07/2026 | 2026-01-09 | 356 | 356
ADIDAS | 0902980314-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 324 | 21/08/2026 | 324 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980314 KV7963 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 22/07/2026 | 29/07/2026 | 23/07/2026 | 28/07/2026 | 324 | 324 |  |  |  | 17/07/2026 | 24/07/2026 | 17/07/2026 | 29/07/2026 | 324 | 324
ADIDAS | 0902980345-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 334 | 26/08/2026 | 334 | SI | SI29/05/2026 | G1H | JACKET | G1 | (29/06/2026) | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 12-Aug. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980345 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 334 | 334 |  |  |  | 13/08/2026 | 20/08/2026 | 14/08/2026 | 24/08/2026 | 334 | 334
ADIDAS | 0902980371-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 317 | 26/08/2026 | 317 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980371 KV8005 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 2026-12-08 | 24/08/2026 | 317 | 317 |  |  |  | 2026-11-08 | 20/08/2026 | 29/07/2026 | 2026-12-08 | 317 | 317
ADIDAS | 0902980401-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 318 | 26/08/2026 | 318 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980401 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 28/07/2026 | 19/08/2026 | 29/07/2026 | 19/08/2026 | 318 | 318 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 21/08/2026 | 318 | 318
ADIDAS | 0902980431-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 26/08/2026 | 344 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | ok | 24/08: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980431 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 13/08/2026 | 21/08/2026 | 344 | 344 |  |  |  | 2026-11-08 | 20/08/2026 | 22/07/2026 | 21/08/2026 | 344 | 344
ADIDAS | 0902980461-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 895 | 15/09/2026 | 895 | AN | AN29/05/2026 | G3B,G3E,G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902980461 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 15/09/2026 | 895 | 716 | 179 |  | 3 | 20/08/2026 | 2026-11-09 | 2026-06-08 | 26/08/2026 | 895 | 864 | 31
ADIDAS | 0902980492-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1236 | 15/09/2026 | 1236 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980492 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 1236 | 1224 | 12 |  | 57 | 2026-05-09 | 2026-11-09 | 2026-11-08 | 2026-10-09 | 1236 | 1214 | 22
ADIDAS | 0902980497-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1200 | 30/09/2026 | 1200 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902980497 LD0287 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 17/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1200 |  | 1200 |  |  | 14/09/2026 | 15/09/2026 | 2026-03-08 | 14/09/2026 | 1200 | 1200 |  |  | 11 | 2026-11-09 | 2026-12-09 | 2026-01-08 | 14/09/2026 | 1200 | 1200 |  |  | 11
ADIDAS | 0902980530-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 901 | 15/09/2026 | 901 | AN | AN29/05/2026 | G1B,G1J | JACKET | G1 | ok | (19/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980530 LG9666 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-09 | W SL WV TT BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-09-09 | 15/09/2026 | 901 | 737 | 164 |  | 19 | 2026-04-09 | 2026-12-09 | 22/08/2026 | 2026-08-09 | 901 | 805 | 96
ADIDAS | 0902980559-1 LH3758 | BLACK | 120D | S2754WAS518B | 800 | 30/09/2026 | 800 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980559 LH3758 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | W SL WV BR PT BLACK |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 800 |  | 800 |  |  | 15/09/2026 | 16/09/2026 |  |  | 800 |  | 800
ADIDAS | 0902980595-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 1066 | 15/09/2026 | 1066 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980595 LG9664 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 1066 |  | 1066 |  |  | 2026-11-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 1066 | 968 | 98 |  | 148
ADIDAS | 0902980626-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 1094 | 30/09/2026 | 1094 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980626 LH3761 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 21/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 1094 |  | 1094 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1094 |  | 1094
ADIDAS | 0902980662-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1530 | 15/09/2026 | 1530 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980662 LE8181 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 19/09/2026 | 2026-12-09 | 2026-12-09 | 1530 | 105 | 1425 |  |  | 2026-10-09 | 16/09/2026 | 2026-11-09 | 14/09/2026 | 1530 | 585 | 945 |  | 10
ADIDAS | 0902980942-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 2026-07-10 | 300 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980942 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV TT BLACK |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0902980969-1 LE8187 | BLACK | 105D | S2754MAS513 | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980969 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M SL WV TP PT BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 420 |  | 420 |  |  | 2026-08-10 | 2026-10-10 |  |  | 420 |  | 420
ADIDAS | 0902981008-1 LE8187 | BLACK | 105D | S2754MAS513 | 300 | 2026-07-10 | 300 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 08-Jul. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981008 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M SL WV TP PT BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0902981035-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 360 | 2026-07-10 | 360 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981035 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-10-09 | 17/09/2026 | 2026-11-09 | 14/09/2026 | 360 | 214 | 146 |  | 4 | 2026-07-09 | 14/09/2026 | 2026-04-09 | 2026-04-09 | 360 | 293 | 67
ADIDAS | 0902981042-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 120 | 2026-09-09 | 120 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981042 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 120 | 120 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 14/08/2026 | 120 | 120
ADIDAS | 0902981068-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 532 | 2026-05-09 | 532 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 672027 | HT+PAD SUB PROCESS_V3 | 0902981068 KX3650 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 2026-05-08 | 30/07/2026 | 2026-05-08 | 532 | 532 |  |  |  | 27/07/2026 | 31/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532 |  |  |  | 23/07/2026 | 29/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532
ADIDAS | 0902981069-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 300 | 28/08/2026 | 300 | AN | AN29/05/2026 | G3E | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981069 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 300 | 300 |  |  |  | 29/07/2026 | 2026-11-08 | 31/07/2026 | 21/08/2026 | 300 | 300
ADIDAS | 0902981094-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 21/08/2026 | 390 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516406 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981094 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 23/07/2026 | 2026-03-08 | 24/07/2026 | 31/07/2026 | 390 | 390 |  |  |  | 20/07/2026 | 29/07/2026 | 22/07/2026 | 2026-05-08 | 390 | 390
ADIDAS | 0902981100-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 672027 | HT+PAD SUB PROCESS_V3 | 0902981100 KX3655 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 14 | 286 |  |  | 17/09/2026 | 17/09/2026 | 2026-10-09 | 2026-12-09 | 300 | 240 | 60 |  |  | 15/09/2026 | 15/09/2026 | 2026-09-09 | 2026-12-09 | 300 | 240 | 60
ADIDAS | 0902981242-1 LG9669 | BLACK | 120D | S2754WAS514C | 15 | 30/09/2026 | 15 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902981242 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | W SL WV SK BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 15 |  | 15 |  |  | 26/09/2026 | 28/09/2026 | 29/08/2026 | 2026-01-09 | 15 | 15
ADIDAS | 0902981276-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 3 | 21/08/2026 | 3 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (KN GLT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902981276 LG9660 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 30/07/2026 | 2026-03-08 | 30/07/2026 | 30/07/2026 | 3 | 3 |  |  |  | 27/07/2026 | 29/07/2026 | 28/07/2026 | 28/07/2026 | 3 | 3
ADIDAS | 0902981317-1 LD0282 | OLIVE TWO S27 | 120D | S2608WR0900 | 185 | 30/09/2026 | 185 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty (KN GLT). 1st Art (TC 10 pcs) 650010 | HT+PAD SUB PROCESS_V3 | 0902981317 LD0282 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/09/2026 | Run Ess Tee W OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 185 |  | 185 |  |  | 14/09/2026 | 15/09/2026 | 2026-01-08 | 2026-08-08 | 185 | 185 |  |  |  | 2026-11-09 | 2026-12-09 | 31/07/2026 | 2026-07-08 | 185 | 185
ADIDAS | 0902981358-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 10 | 15/10/2026 | 10 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0902981358 LD0285 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10
ADIDAS | 0902981395-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 21 | 30/09/2026 | 21 | SI | SI29/05/2026 | G3A | SHORTS | G3 | (28/07/2026) | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981395 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-10-09 | 2026-09-09 | 2026-09-09 | 21 | 21 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 21 | 21
ADIDAS | 0902981438-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 30/09/2026 | 120 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0902981438 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W SL WV SK BLACK |  | SS27-SPOMA | 30/09/2026 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 26/09/2026 | 28/09/2026 | 28/08/2026 | 2026-05-09 | 120 | 114 | 6
ADIDAS | 0902981654-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 384 | 26/08/2026 | 384 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902981654 LD0287 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 18/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 384 | 384 |  |  |  | 2026-12-08 | 20/08/2026 | 31/07/2026 | 2026-12-08 | 384 | 384 |  |  |  | 2026-10-08 | 18/08/2026 | 29/07/2026 | 2026-12-08 | 384 | 384
ADIDAS | 0902981678-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 553 | 26/08/2026 | 553 | SA | SA29/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902981678 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-04-08 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-04-08 | 21/08/2026 | 2026-04-08 | 20/08/2026 | 553 | 553 |  |  |  | 30/07/2026 | 18/08/2026 | 30/07/2026 | 2026-01-08 | 553 | 553 |  |  |  | 28/07/2026 | 13/08/2026 | 27/07/2026 | 2026-01-08 | 553 | 553
ADIDAS | 0902981755-1 LF0723 | BLACK | 105D | S2754MAS511B | 1697 | 30/09/2026 | 1697 | SI | SI29/05/2026 | G3D | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Kahatex, PI Date 28-Jul, actual 10-Aug. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981755 LF0723 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | M SL WV SHO BLACK |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1697 |  | 1697 |  |  | 17/09/2026 | 21/09/2026 |  |  | 1697 |  | 1697
ADIDAS | 0902981783-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 1824 | 23/09/2026 | 1824 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902981783 LD0288 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 18/08/2026 | 2026-01-09 | 1824 | 1824 |  |  |  | 2026-11-08 | 29/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824
ADIDAS | 0902981811-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 712 | 15/09/2026 | 712 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981811 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 712 |  | 712 |  |  | 16/09/2026 | 18/09/2026 | 2026-11-09 | 15/09/2026 | 712 | 663 | 49
ADIDAS | 0902981835-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 1342 | 30/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981835 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/08/2026 | 2026-10-09 | 20/08/2026 | 2026-10-09 | 1342 | 1342 |  |  |  | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-03-09 | 1342 | 1342
ADIDAS | 0902981856-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 1297 | 15/09/2026 | 1297 | SI | SI29/05/2026 | G3A,G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981856 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-10-09 | 19/09/2026 | 2026-10-09 | 2026-12-09 | 1297 | 1245 | 52 |  |  | 2026-07-09 | 16/09/2026 | 2026-03-09 | 2026-12-09 | 1297 | 1270 | 27
ADIDAS | 0902981919-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 425 | 15/09/2026 | 425 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981919 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 425 | 288 | 137 |  | 158 | 2026-04-09 | 2026-12-09 | 2026-01-09 | 2026-07-09 | 425 | 356 | 69
ADIDAS | 0902981952-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 300 | 30/09/2026 | 300 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902981952 LG9668 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902981983-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 619 | 15/09/2026 | 619 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981983 LG9661 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 619 | 391 | 228 |  | 235 | 2026-09-09 | 2026-11-09 | 26/08/2026 | 2026-10-09 | 619 | 545 | 74
ADIDAS | 0902982011-1 KZ3229 | GREY FIVE F17/WHITE | 90D | S2754WESS703WV-MTF | 744 | 21/08/2026 | 744 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (19/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun (PO NT-351). T2 Libolon, PI Date 28-May, actual receives 28-May. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982011 KZ3229 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/07/2026 | W 13S WV BER SHO GREY FIVE F17/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 30/07/2026 | 14/08/2026 | 744 | 744 |  |  |  | 27/07/2026 | 2026-11-08 | 25/07/2026 | 13/08/2026 | 744 | 744
ADIDAS | 0902982057-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 1502 | 21/08/2026 | 1502 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 12-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 28-May (PO NT-347). 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982057 KZ3198 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 28/07/2026 | 19/08/2026 | 29/07/2026 | 18/08/2026 | 1502 | 1502 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 14/08/2026 | 1502 | 1502
ADIDAS | 0902982085-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 814 | 30/09/2026 | 814 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902982085 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | W SL WV PT BLACK |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 814 |  | 814 |  |  | 17/09/2026 | 19/09/2026 |  |  | 814 |  | 814
ADIDAS | 0902982124-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 577 | 21/08/2026 | 577 | AN | AN29/05/2026 | G1H | JACKET | G1 | ok | (27/06/2026) | 21/08: ex-fty (Mexico). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 28-May. T2 Kahatex, PI Date 13-Jun, actual receives 22-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982124 KZ3205 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/07/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 22/07/2026 | 14/08/2026 | 24/07/2026 | 14/08/2026 | 577 | 577 |  |  |  | 17/07/2026 | 2026-11-08 | 15/07/2026 | 20/08/2026 | 577 | 577
ADIDAS | 0902982159-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 10 | 2026-05-09 | 10 | AN | AN29/05/2026 | G1E | T-SHIRT | G1 | ok | ok | 04/09: ex-fty (KN GLT). T2 Libolon, actual receives 29-Apr (PO 25063167). T2 Fu Hsun, actual receives 23-Apr (PO 25063168). 650010 | HT SUB PROCESS_V1 | 0902982159 IT1824 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 10 | 10 |  |  |  | 14/07/2026 | 16/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10
ADIDAS | 0902982649-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 300 | 21/08/2026 | 300 | AN | AN29/05/2026 | G3B | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 18-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 29-May (PO NT-347). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982649 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/07/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 28/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 300 | 300 |  |  |  | 23/07/2026 | 2026-11-08 | 27/07/2026 | 2026-10-08 | 300 | 300
ADIDAS | 0902982718-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 400 | 2026-03-09 | 400 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | ok | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982718 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-07-08 | 400 | 400 |  |  |  | 24/07/2026 | 2026-05-08 | 27/07/2026 | 29/08/2026 | 400 | 400
ADIDAS | 0902982800-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902982800 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 24/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902982852-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982852 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 320 |  | 320 |  |  | 21/09/2026 | 21/09/2026 | 2026-07-08 | 15/08/2026 | 320 | 320 |  |  |  | 18/09/2026 | 18/09/2026 | 2026-07-08 | 14/08/2026 | 320 | 320
ADIDAS | 0902982880-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982880 LD0287 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 350 |  | 350 |  |  | 19/09/2026 | 19/09/2026 |  |  | 350 |  | 350 |  |  | 17/09/2026 | 17/09/2026 |  |  | 350 |  | 350
ADIDAS | 0902982910-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982910 LD0285 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 19/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902982939-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982939 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 21/09/2026 | 21/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350 |  |  |  | 18/09/2026 | 18/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350
ADIDAS | 0902982968-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 414 | 30/09/2026 | 414 | SA | SA29/05/2026 | G2E | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982968 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 414 |  | 414 |  |  | 15/09/2026 | 16/09/2026 | 25/07/2026 | 2026-01-08 | 414 | 414 |  |  |  | 2026-12-09 | 14/09/2026 | 25/07/2026 | 31/07/2026 | 414 | 414
ADIDAS | 0902983088-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 320 | 30/09/2026 | 320 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516254 | HT+PAD SUB PROCESS_V3 | 0902983088 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 17/09/2026 |  |  | 320 |  | 320 |  |  | 14/09/2026 | 14/09/2026 | 26/08/2026 | 2026-05-09 | 320 | 320 |  |  |  | 2026-11-09 | 2026-11-09 | 26/08/2026 | 2026-05-09 | 320 | 320
ADIDAS | 0902983300-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983300 KX3651 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 108 |  | 108 |  |  | 23/09/2026 | 23/09/2026 | 25/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 21/09/2026 | 21/09/2026 | 24/07/2026 | 31/07/2026 | 108 | 108
ADIDAS | 0902983336-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983336 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 17/09/2026 |  |  | 108 |  | 108 |  |  | 14/09/2026 | 14/09/2026 | 26/08/2026 | 2026-08-09 | 108 | 108 |  |  |  | 2026-11-09 | 2026-11-09 | 26/08/2026 | 2026-08-09 | 108 | 108
ADIDAS | 0902983370-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 108 | 23/09/2026 | 108 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983370 KF5311 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 108 | 108 |  |  |  | 2026-06-08 | 29/08/2026 | 30/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 2026-04-08 | 27/08/2026 | 29/07/2026 | 30/07/2026 | 108 | 108
ADIDAS | 0902983535-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F,G3K | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902983535 JE8969 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 1200 | 1200 |  |  |  | 15/07/2026 | 2026-03-08 | 2026-09-07 | 2026-05-08 | 1200 | 1200
ADIDAS | 0902983568-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902983568 JE6346 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 1201 | 1201 |  |  |  | 16/07/2026 | 29/07/2026 | 18/07/2026 | 22/07/2026 | 1201 | 1201
ADIDAS | 0902983877-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 408 | 2026-05-09 | 408 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983877 LE8181 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 408 | 408 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-05-09 | 408 | 408
ADIDAS | 0902983897-1 LE8187 | BLACK | 105D | S2754MAS513 | 1822 | 2026-05-09 | 1822 | SI | SI29/05/2026 | G3D,G3I,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983897 LE8187 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-05-09 | 2026-12-08 | 2026-04-09 | 1822 | 1822 |  |  |  | 2026-03-08 | 2026-02-09 | 2026-07-08 | 2026-04-09 | 1822 | 1820 | 2
ADIDAS | 0902983913-1 LF0718 | BLACK | 105D | S2754MAS512B | 647 | 2026-05-09 | 647 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983913 LF0718 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT BLACK |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 647 | 647 |  |  |  | 27/08/2026 | 2026-02-09 | 14/08/2026 | 2026-04-09 | 647 | 647
ADIDAS | 0902983933-1 LF0723 | BLACK | 105D | S2754MAS511B | 471 | 2026-12-09 | 471 | SI | SI29/05/2026 | G3D,G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983933 LF0723 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO BLACK |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 471 | 471 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-09-09 | 471 | 471
ADIDAS | 0902983951-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 15/09/2026 | 100 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983951 LG9664 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 100 |  | 100 |  |  | 16/09/2026 | 18/09/2026 | 2026-11-09 | 2026-11-09 | 100 | 40 | 60
ADIDAS | 0902983960-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 100 | 2026-12-09 | 100 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983960 LF0725 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-12-08 | 2026-03-09 | 100 | 100
ADIDAS | 0902983978-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983978 LG9673 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 16/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902983990-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983990 LG9674 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 15/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902984005-1 LH3758 | BLACK | 120D | S2754WAS518B | 400 | 30/09/2026 | 400 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902984005 LH3758 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | W SL WV BR PT BLACK |  | SS27 | 18/09/2026 | 18/09/2026 |  |  | 400 |  | 400 |  |  | 15/09/2026 | 15/09/2026 |  |  | 400 |  | 400
ADIDAS | 0902984019-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902984019 LG9666 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | W SL WV TT BLACK |  | SS27 | 22/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 23/09/2026 | 31/08/2026 | 2026-03-09 | 300 | 267 | 33
ADIDAS | 0902985687-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985687 JE6374 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 29/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 2026-06-08 | 2026-02-09 | 1201 | 1201
ADIDAS | 0902985715-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 1200 | 15/09/2026 | 1200 | SI | SI29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902985715 JE8949 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-01-09 | M BL FT SWT |  | FW26 | 2026-01-09 | 2026-12-09 | 2026-01-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 28/08/2026 | 2026-09-09 | 29/07/2026 | 2026-03-09 | 1200 | 1200
ADIDAS | 0902985747-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902985747 IN6163 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 23/07/2026 | M BL FT PT |  | FW26 | 23/07/2026 | 2026-03-08 | 22/07/2026 | 30/07/2026 | 1200 | 1200 |  |  |  | 20/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 1200 | 1200
ADIDAS | 0902985818-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1201 | 2026-12-09 | 1201 | AT | AT29/05/2026 | G3C,G3D | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902985818 JD1881 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/07/2026 | M 3S FT TC PT |  | FW26 | 28/07/2026 | 2026-12-08 | 29/07/2026 | 2026-10-08 | 1201 | 1201 |  |  |  | 23/07/2026 | 2026-07-08 | 20/07/2026 | 2026-01-08 | 1201 | 1201
ADIDAS | 0902985896-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 1970 | 21/08/2026 | 1970 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0902985896 IU0217 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-10-07 | IN RANGE |  | FW26 | 2026-10-07 | 23/07/2026 | 2026-09-07 | 22/07/2026 | 1970 | 1970 |  |  |  | 2026-07-07 | 20/07/2026 | 2026-03-07 | 21/07/2026 | 1970 | 1970
ADIDAS | 0902985931-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985931 JE6372 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 15/07/2026 | 18/08/2026 | 1201 | 1201
ADIDAS | 0902986122-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 112 | 2026-07-10 | 112 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902986122 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 112 |  | 112 |  |  | 29/09/2026 | 29/09/2026 |  |  | 112 |  | 112 |  |  | 26/09/2026 | 26/09/2026 |  |  | 112 |  | 112
ADIDAS | 0902987661-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 615 | 21/08/2026 | 615 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 838103 | PRINT L3 SUB PROCESS_V3 | 0902987661 IU0217 | 13/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 23/07/2026 | 13/07/2026 | 22/07/2026 | 615 | 615 |  |  |  | 2026-09-07 | 20/07/2026 | 2026-03-07 | 20/07/2026 | 615 | 615
ADIDAS | 0902987761-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 540 | 15/10/2026 | 540 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987761 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 540 |  | 540 |  |  | 24/09/2026 | 24/09/2026 |  |  | 540 |  | 540 |  |  | 22/09/2026 | 22/09/2026 |  |  | 540 |  | 540
ADIDAS | 0902987861-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 529 | 15/10/2026 | 529 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987861 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 529 |  | 529 |  |  | 24/09/2026 | 24/09/2026 |  |  | 529 |  | 529 |  |  | 22/09/2026 | 22/09/2026 |  |  | 529 |  | 529
ADIDAS | 0902987900-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902987900 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 15/09/2026 | 2026-12-08 | 13/08/2026 | 300 | 244 | 56 |  |  | 2026-05-08 | 2026-11-09 | 2026-10-08 | 31/08/2026 | 300 | 266 | 34
ADIDAS | 0902987944-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 28/08/2026 | 300 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902987944 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 13/08/2026 | 2026-10-08 | 14/08/2026 | 300 | 300 |  |  |  | 2026-05-08 | 2026-10-08 | 2026-01-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902988860-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 231 | 2026-07-10 | 231 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988860 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 231 |  | 231 |  |  | 20/10/2026 | 21/10/2026 |  |  | 231 |  | 231 |  |  | 14/10/2026 | 15/10/2026 |  |  | 231 |  | 231
ADIDAS | 0902988896-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 481 | 15/09/2026 | 481 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD) 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988896 KC8152 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 481 | 481 |  |  | 44 | 2026-02-09 | 2026-10-09 | 2026-04-09 | 2026-11-09 | 481 | 481 |  |  |  | 27/08/2026 | 2026-04-09 | 2026-04-09 | 2026-09-09 | 481 | 481
ADIDAS | 0902990795-1 IU0217 | WONDER WHITE F21 | 90D | S2425M405 | 302 | 21/08/2026 | 302 | SI | SI29/05/2026 | G2S | T-SHIRT | G2 | ok | (22/06/2026) | 21/08: ex-fty 839055 | PRINT L3 SUB PROCESS_V3 | 0902990795 IU0217 | 13/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 14/07/2026 | IN RANGE |  | FW26 | 14/07/2026 | 23/07/2026 | 14/07/2026 | 22/07/2026 | 302 | 302 |  |  |  | 2026-09-07 | 20/07/2026 | 2026-04-07 | 20/07/2026 | 302 | 302
ADIDAS | 0902990885-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 110 | 15/10/2026 | 110 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990885 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 26/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 110 |  | 110 |  |  | 23/09/2026 | 24/09/2026 |  |  | 110 |  | 110 |  |  | 21/09/2026 | 22/09/2026 |  |  | 110 |  | 110
ADIDAS | 0902993705-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 2026-12-09 | 368 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (19/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993705 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-06-08 | 368 | 368 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 19/08/2026 | 368 | 368
ADIDAS | 0902993733-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 371 | 28/08/2026 | 371 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516240 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993733 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 371 | 371 |  |  |  | 24/07/2026 | 2026-11-08 | 29/07/2026 | 13/08/2026 | 371 | 371
ADIDAS | 0902993759-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 405 | 15/09/2026 | 405 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902993759 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 2026-12-09 | 405 | 391 | 14 |  |  | 2026-01-09 | 2026-11-09 | 2026-10-08 | 2026-10-09 | 405 | 405
ADIDAS | 0902993780-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 600 | 2026-05-09 | 600 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993780 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-03-08 | 2026-11-08 | 600 | 600 |  |  |  | 29/07/2026 | 2026-10-08 | 28/07/2026 | 2026-10-08 | 600 | 600
ADIDAS | 0902997572-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 621 | 28/08/2026 | 621 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902997572 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 14/08/2026 | 2026-10-08 | 14/08/2026 | 621 | 621 |  |  |  | 2026-05-08 | 2026-11-08 | 27/07/2026 | 24/08/2026 | 621 | 621
ADIDAS | 0902997625-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 28/08/2026 | 368 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902997625 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 2026-07-08 | 31/07/2026 | 2026-07-08 | 368 | 368 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-07-08 | 368 | 368
ADIDAS | 0902997868-1 KB5960 | WHITE | 120D | S2608MR0900A | 524 | 15/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902997868 KB5960 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 524 |  | 524 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 27/08/2026 | 524 | 524 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 26/08/2026 | 524 | 524
ADIDAS | 0902999653-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 330 | 21/08/2026 | 330 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999653 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 20/07/2026 | 24/07/2026 | 20/07/2026 | 24/07/2026 | 330 | 330 |  |  |  | 15/07/2026 | 21/07/2026 | 16/07/2026 | 29/07/2026 | 330 | 330
ADIDAS | 0902999704-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 563 | 28/08/2026 | 563 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999704 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 14/08/2026 | 563 | 563 |  |  |  | 29/07/2026 | 2026-11-08 | 27/07/2026 | 14/08/2026 | 563 | 563
ADIDAS | 0902999743-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 255 | 31/08/2026 | 255 | AN | AN29/05/2026 | G3C | PANTS | G3 | ok | (19/06/2026) | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902999743 KV7863 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 255 | 255 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-01-08 | 31/08/2026 | 255 | 255
ADIDAS | 0903014150-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 120 | 21/08/2026 | 120 | AN | AN29/05/2026 | G2S | SHORTS | G2 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 25-May (PO NT-351). T2 Libolon, PI Date 23-Jun, actual receives 23-Jun. 516029 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903014150 LG9660 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 120 | 120 |  |  |  | 27/07/2026 | 2026-11-08 | 27/07/2026 | 14/08/2026 | 120 | 120
ADIDAS | 0903014154-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 778 | 21/08/2026 | 778 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | 21/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 31-May, actual receives 03-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 03-Jun. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903014154 KV7863 | 13/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/07/2026 | 2026-06-08 | 24/07/2026 | 2026-05-08 | 778 | 778 |  |  |  | 21/07/2026 | 2026-03-08 | 20/07/2026 | 2026-05-08 | 778 | 778
ADIDAS | 0903017607-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 1100 | 2026-05-09 | 1100 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok |  | 05/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903017607 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV WB |  | SS27 | 29/07/2026 | 31/08/2026 | 29/07/2026 | 31/08/2026 | 1100 | 1100 |  |  |  | 24/07/2026 | 27/08/2026 | 22/07/2026 | 2026-01-09 | 1100 | 1100
ADIDAS | 0903031703-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 2026-05-09 | 313 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031703 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 313 | 313 |  |  |  | 29/07/2026 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 313 | 313
ADIDAS | 0903031747-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 352 | 2026-05-09 | 352 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031747 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 352 | 352 |  |  |  | 24/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 352 | 352
ADIDAS | 0903031828-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 1176 | 30/09/2026 | 1176 | AN | AN12/06/2026 | G1E | T-SHIRT | G1 | ok | (02/07/2026) | 22/09: ex-fty. T2 Libolon, PI Date 29-Aug, actual receives 30-Jul. T2 Fu Hsun, actual receives 14-Jan (PO 25063168). 600000 | HT SUB PROCESS_V1 | 0903031828 IT1824 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 23/09/2026 |  |  | 1176 |  | 1176 |  |  | 18/09/2026 | 21/09/2026 | 2026-09-09 | 15/09/2026 | 1176 | 1150 | 26 |  | 2 | 17/09/2026 | 19/09/2026 | 2026-09-09 | 15/09/2026 | 1176 | 1162 | 14 |  | 17
ADIDAS | 0903031894-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 7560 | 2026-05-09 | 7560 | AN | AN12/06/2026 | G3A,G3B,G3C,G3E,G3F,G3G,G3H,G3J | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jul. T2 Libolon, PI Date 06-Jul, actual receives 22-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031894 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-04-08 | 19/08/2026 | 7560 | 7560 |  |  |  | 29/07/2026 | 18/08/2026 | 30/07/2026 | 20/08/2026 | 7560 | 7560
ADIDAS | 0903031957-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 540 | 2026-12-09 | 540 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903031957 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 540 | 540 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 18/08/2026 | 540 | 540
ADIDAS | 0903032010-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | ok | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 17-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903032010 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-10-08 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 332 | 332 |  |  |  | 2026-05-08 | 13/08/2026 | 2026-11-08 | 18/08/2026 | 332 | 332
ADIDAS | 0903042722-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 2026-09-09 | 344 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903042722 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 344 | 344 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 344 | 344
ADIDAS | 0903042749-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 300 | 30/09/2026 | 300 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903042749 LE5389 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 18/09/2026 | 2026-11-08 | 26/08/2026 | 300 | 300
ADIDAS | 0903043439-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 15/10/2026 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903043439 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 4002 |  | 4002 |  |  | 2026-02-10 | 2026-05-10 |  |  | 4002 |  | 4002
ADIDAS | 0903043644-1 KB5965 | BLACK | 120D | S2608MR0900A | 1380 | 30/09/2026 | 1380 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 23/09: ex-fty. DRC 0090-early shipment customer (BTP_23_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903043644 KB5965 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 1380 |  | 1380 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1380 |  | 1380 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903045739-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 984 | 2026-12-09 | 984 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903045739 KB5960 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | Run Ess Tee M |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-08-09 | 2026-10-09 | 984 | 984
ADIDAS | 0903045869-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 2026-07-10 | 12000 | AN | AN12/06/2026 | G3A,G3B,G3C | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045869 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 2026-05-10 | 22/10/2026 |  |  | 12000 |  | 12000 |  |  | 2026-01-10 | 19/10/2026 | 28/07/2026 | 28/07/2026 | 12000 | 1 | 11999
ADIDAS | 0903045909-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 2026-07-10 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045909 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 4002 |  | 4002 |  |  | 29/09/2026 | 2026-02-10 |  |  | 4002 |  | 4002
ADIDAS | 0903046028-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 15/10/2026 | 12000 | AN | AN12/06/2026 | G3D,G3E,G3F | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046028 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 28/10/2026 | 2026-10-11 |  |  | 12000 |  | 12000 |  |  | 24/10/2026 | 2026-06-11 |  |  | 12000 |  | 12000
ADIDAS | 0903046531-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 301 | 30/09/2026 | 301 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046531 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-02-10 | 2026-02-10 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903046557-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 121 | 2026-12-09 | 121 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046557 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 121 | 121 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 31/08/2026 | 121 | 121
ADIDAS | 0903046577-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 414 | 2026-12-09 | 414 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046577 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 414 | 414 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 2026-10-09 | 414 | 414
ADIDAS | 0903046607-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 360 | 2026-09-09 | 360 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046607 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 360 | 360 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 360 | 360
ADIDAS | 0903046624-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 2083 | 15/09/2026 | 2083 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046624 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 17/09/2026 | 2026-10-08 | 27/08/2026 | 2083 | 1632 | 451 |  |  | 2026-04-08 | 14/09/2026 | 28/07/2026 | 2026-12-09 | 2083 | 2071 | 12
ADIDAS | 0903046936-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 200 | 23/09/2026 | 200 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route. DRC 0010-hold shipment customer (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 1st Art (TC 10 pcs) 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046936 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 15/08/2026 | 200 | 200
ADIDAS | 0903046982-1 KB5965 | BLACK | 120D | S2608MR0900A | 1010 | 30/09/2026 | 1010 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903046982 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 1010 |  | 1010 |  |  | 22/09/2026 | 22/09/2026 |  |  | 1010 |  | 1010 |  |  | 19/09/2026 | 19/09/2026 |  |  | 1010 |  | 1010
ADIDAS | 0903047029-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3E,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_02_07_2026 EARLY HOLD SHIPMENT). 516240 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903047029 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-09 | 16/09/2026 | 14/09/2026 | 15/09/2026 | 300 | 300 |  |  | 290 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 15/09/2026 | 300 | 300 |  |  | 164 | 2026-03-09 | 2026-07-09 | 2026-11-09 | 14/09/2026 | 300 | 300 |  |  | 101
ADIDAS | 0903047077-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 350 | 2026-07-10 | 350 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516461 | HT+PAD SUB PROCESS_V3 | 0903047077 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 350 |  | 350 |  |  | 19/09/2026 | 21/09/2026 |  |  | 350 |  | 350 |  |  | 17/09/2026 | 18/09/2026 |  |  | 350 |  | 350
ADIDAS | 0903047104-1 KB5960 | WHITE | 120D | S2608MR0900A | 634 | 30/09/2026 | 634 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903047104 KB5960 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 634 |  | 634 |  |  | 22/09/2026 | 23/09/2026 | 2026-05-08 | 2026-10-09 | 634 | 614 | 20 |  |  | 19/09/2026 | 21/09/2026 | 2026-01-08 | 2026-10-09 | 634 | 615 | 19
ADIDAS | 0903047150-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516433 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047150 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 | 28/08/2026 | 2026-04-09 | 301 | 14 | 287
ADIDAS | 0903047185-1 JZ7808 | BLACK | 120D | S2608WR0900 | 803 | 15/10/2026 | 803 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047185 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 803 |  | 803 |  |  | 26/09/2026 | 26/09/2026 |  |  | 803 |  | 803 |  |  | 24/09/2026 | 24/09/2026 |  |  | 803 |  | 803
ADIDAS | 0903047214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 2411 | 15/10/2026 | 2411 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047214 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 29/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 29/09/2026 | 2026-01-10 |  |  | 2411 |  | 2411 |  |  | 25/09/2026 | 28/09/2026 |  |  | 2411 |  | 2411 |  |  | 23/09/2026 | 25/09/2026 |  |  | 2411 |  | 2411
ADIDAS | 0903047216-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 431 | 30/09/2026 | 431 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047216 KY6616 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 431 |  | 431 |  |  | 18/09/2026 | 19/09/2026 |  |  | 431 |  | 431
ADIDAS | 0903047241-1 KB5965 | BLACK | 120D | S2608MR0900A | 4136 | 15/10/2026 | 4136 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047241 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-08-10 | Run Ess Tee M |  | SS27-TI | 2026-08-10 | 13/10/2026 |  |  | 4136 |  | 4136 |  |  | 2026-05-10 | 2026-09-10 |  |  | 4136 |  | 4136 |  |  | 2026-02-10 | 2026-07-10 |  |  | 4136 |  | 4136
ADIDAS | 0903047261-1 LG9675 | BLACK | 120D | S2754WAS513C | 301 | 15/10/2026 | 301 | SI | SI12/06/2026 | G3G | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047261 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | W SL WV PT BLACK |  | SS27 | 27/10/2026 | 27/10/2026 |  |  | 301 |  | 301 |  |  | 23/10/2026 | 23/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903047275-1 LE8201 | BLACK | 90D | F2606LHLF103FY-MTF | 14000 | 15/09/2026 | 14000 | AN | AN12/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047275 LE8201 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 14000 | 14000 |  |  | 1909 | 2026-02-09 | 2026-11-09 | 2026-01-09 | 14/09/2026 | 14000 | 13952 | 48 |  | 137
ADIDAS | 0903047299-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2O | T-SHIRT | G2 | ok | (02/07/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047299 LE8208 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 F JSYL SE BLACK |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-05-09 | 14/09/2026 | 3500 | 3500 |  |  | 44 | 2026-02-09 | 2026-11-09 | 2026-02-09 | 14/09/2026 | 3500 | 3500 |  |  | 64
ADIDAS | 0903047330-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1R | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 20 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047330 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-01-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-01-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 15000 | 15000 |  |  | 1686 | 28/08/2026 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 15000 | 15000 |  |  | 183
ADIDAS | 0903047342-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2L,G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047342 LE8210 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3500 | 3500 |  |  | 333 | 2026-05-09 | 2026-11-09 | 2026-05-09 | 14/09/2026 | 3500 | 3480 | 20 |  | 63
ADIDAS | 0903047363-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 3678 | 2026-12-09 | 3678 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 11/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047363 LE8194 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL HFY JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 3678 | 3678 |  |  |  | 27/08/2026 | 2026-05-09 | 20/08/2026 | 2026-04-09 | 3678 | 3678
ADIDAS | 0903047388-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1O,G1Q,G1R,G2M | T-SHIRT | G1,G2 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047388 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-01-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-01-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 15000 | 15000 |  |  | 5182 | 28/08/2026 | 2026-11-09 | 2026-05-09 | 14/09/2026 | 15000 | 14832 | 168 |  | 394
ADIDAS | 0903047414-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 5500 | 15/09/2026 | 5500 | SA | SA12/06/2026 | G1G | T-SHIRT | G1 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047414 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 5500 | 5500 |  |  | 521 | 2026-05-09 | 2026-11-09 | 31/08/2026 | 2026-12-09 | 5500 | 5483 | 17
ADIDAS | 0903047417-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 121 | 15/10/2026 | 121 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047417 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 121 |  | 121 |  |  | 2026-01-10 | 2026-02-10 |  |  | 121 |  | 121
ADIDAS | 0903047441-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 249 | 15/09/2026 | 249 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903047441 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 249 | 249 |  |  | 8 | 2026-09-09 | 2026-11-09 | 2026-11-08 | 26/08/2026 | 249 | 249
ADIDAS | 0903047468-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 150 | 15/09/2026 | 150 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047468 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 150 | 110 | 40 |  | 3 | 2026-09-09 | 2026-11-09 | 22/08/2026 | 14/09/2026 | 150 | 140 | 10 |  | 22
ADIDAS | 0903047497-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 15/09/2026 | 101 | AN | AN12/06/2026 | G1L | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047497 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 101 |  | 101 |  |  | 14/09/2026 | 14/09/2026 | 26/08/2026 | 2026-05-09 | 101 | 101
ADIDAS | 0903047521-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047521 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-01-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903048420-1 KB5965 | BLACK | 120D | S2608MR0900A | 456 | 30/09/2026 | 456 | SA | SA12/06/2026 | G2K | T-SHIRT | G2 | ok | (04/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048420 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | Run Ess Tee M |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 456 |  | 456 |  |  | 21/09/2026 | 22/09/2026 |  |  | 456 |  | 456 |  |  | 18/09/2026 | 19/09/2026 |  |  | 456 |  | 456
ADIDAS | 0903048444-1 JZ7808 | BLACK | 120D | S2608WR0900 | 420 | 15/10/2026 | 420 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516461 | HT+PAD SUB PROCESS_V3 | 0903048444 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 420 |  | 420 |  |  | 22/09/2026 | 22/09/2026 |  |  | 420 |  | 420 |  |  | 19/09/2026 | 19/09/2026 |  |  | 420 |  | 420
ADIDAS | 0903048469-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1100 | 15/10/2026 | 1100 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903048469 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 1100 |  | 1100 |  |  | 22/09/2026 | 23/09/2026 |  |  | 1100 |  | 1100 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1100 |  | 1100
ADIDAS | 0903048502-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1004 | 2026-07-10 | 1004 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048502 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 1004 |  | 1004 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1004 |  | 1004 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1004 |  | 1004
ADIDAS | 0903048576-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 112 | 15/09/2026 | 112 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048576 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 |  |  | 112 |  | 112 |  |  | 2026-09-09 | 2026-11-09 | 14/09/2026 | 14/09/2026 | 112 | 5 | 107 |  | 5
ADIDAS | 0903048604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 15/09/2026 | 300 | AN | AN12/06/2026 | G3F,G3G | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903048604 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-05-09 | 14/09/2026 | 300 | 292 | 8 |  | 17 | 2026-01-09 | 2026-11-09 | 2026-10-08 | 13/08/2026 | 300 | 300
ADIDAS | 0903048647-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 434 | 2026-09-09 | 434 | AN | AN12/06/2026 | G1H,G1L | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 14-Aug. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048647 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/08/2026 | 2026-08-09 | 24/08/2026 | 2026-05-09 | 434 | 434 |  |  |  | 18/08/2026 | 2026-04-09 | 18/08/2026 | 2026-07-09 | 434 | 434
ADIDAS | 0903049187-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 376 | 15/10/2026 | 376 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903049187 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 376 |  | 376 |  |  | 2026-03-10 | 2026-05-10 |  |  | 376 |  | 376 |  |  | 2026-01-10 | 2026-02-10 |  |  | 376 |  | 376
ADIDAS | 0903049270-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 450 | 21/08/2026 | 450 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049270 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 21/08/2026 | 2026-06-08 | 20/08/2026 | 450 | 450 |  |  |  | 2026-04-08 | 18/08/2026 | 30/07/2026 | 2026-06-08 | 450 | 450
ADIDAS | 0903049350-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 414 | 21/08/2026 | 414 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (02/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049350 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | LA PALMS TEE |  | SS27 | 14/08/2026 | 21/08/2026 | 14/08/2026 | 21/08/2026 | 414 | 414 |  |  |  | 2026-11-08 | 18/08/2026 | 2026-06-08 | 20/08/2026 | 414 | 414
ADIDAS | 0903049383-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049383 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | PIZZA TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-08-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-07-08 | 2026-07-09 | 450 | 450
ADIDAS | 0903049419-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 341 | 2026-09-09 | 341 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 08/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049419 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M TATTOO SPRT T BLACK |  | SS27 | 2026-03-09 | 2026-09-09 | 2026-04-09 | 2026-08-09 | 341 | 341 |  |  |  | 31/08/2026 | 2026-05-09 | 24/08/2026 | 2026-07-09 | 341 | 341
ADIDAS | 0903049448-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 301 | 30/09/2026 | 301 | AN | AN12/06/2026 | G2N | T-SHIRT | G2 | ok | (02/07/2026) | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049448 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | LA PALMS TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 301 |  | 301 |  |  | 15/09/2026 | 16/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903049516-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 301 | 23/09/2026 | 301 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049516 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 301 | 301 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903049556-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 141 | 21/08/2026 | 141 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049556 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 21/08/2026 | 2026-06-08 | 20/08/2026 | 141 | 141 |  |  |  | 2026-04-08 | 18/08/2026 | 31/07/2026 | 31/07/2026 | 141 | 141
ADIDAS | 0903049584-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049584 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PIZZA TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 301 |  | 301 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 19/08/2026 | 301 | 293 | 8
ADIDAS | 0903049615-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 24/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049615 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | HOU COLL TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 301 |  | 301 |  |  | 2026-01-10 | 2026-01-10 | 2026-10-08 | 2026-07-09 | 301 | 301
ADIDAS | 0903050997-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 558 | 30/09/2026 | 558 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 1st Art (TC 12 pcs) 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903050997 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 558 |  | 558 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-09 | 2026-08-09 | 558 | 195 | 363
ADIDAS | 0903051027-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 236 | 30/09/2026 | 236 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903051027 LE0358 | 2026-11-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 236 |  | 236 |  |  | 29/09/2026 | 30/09/2026 | 2026-04-09 | 2026-11-09 | 236 | 123 | 113
ADIDAS | 0903051147-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 230 | 21/08/2026 | 230 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (02/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903051147 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | LA PALMS TEE |  | SS27 | 14/08/2026 | 21/08/2026 | 14/08/2026 | 21/08/2026 | 230 | 230 |  |  |  | 2026-11-08 | 18/08/2026 | 2026-06-08 | 19/08/2026 | 230 | 230
ADIDAS | 0903051176-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903051176 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | HOU COLL TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-08-08 | 2026-12-09 | 450 | 450
ADIDAS | 0903051217-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 417 | 26/08/2026 | 417 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 24/08: ex-fty 600000 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903051217 KY1361 | 29/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 417 | 417 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 22/08/2026 | 417 | 417
ADIDAS | 0903051428-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/09/2026 | 18 | SA | SA12/06/2026 | G3J | SHORTS | G3 | ok |  | 14/09: ex-fty. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. T2 Formosa, PI Date 20-Jul, actual receives 07-Jul. 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903051428 KZ0925 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 18 | 18 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 18 | 18
ADIDAS | 0903051498-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 40 | 15/10/2026 | 40 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051498 LD0283 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 40 |  | 40 |  |  | 26/09/2026 | 26/09/2026 |  |  | 40 |  | 40 |  |  | 24/09/2026 | 24/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903051523-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051523 KX3651 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 50 |  | 50 |  |  | 24/09/2026 | 24/09/2026 | 2026-04-08 | 2026-08-08 | 50 | 50 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-01-08 | 2026-07-08 | 50 | 50
ADIDAS | 0903051563-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 40 | 15/10/2026 | 40 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051563 LD0284 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 40 |  | 40 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40
ADIDAS | 0903051592-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 18 | 30/09/2026 | 18 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903051592 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 18 |  | 18 |  |  | 14/09/2026 | 15/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903051620-1 KA0227 | MEDIUM GREY HEATHER | 120D | S2608WR0900 | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0903051620 KA0227 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | Run Ess Tee W MEDIUM GREY HEATHER |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-08 | 2026-12-08 | 50 | 50 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-08-08 | 2026-11-08 | 50 | 50
ADIDAS | 0903052489-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 379 | 2026-09-09 | 379 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052489 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-07-09 | 379 | 379 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 31/08/2026 | 379 | 379
ADIDAS | 0903052531-1 LE5038 | BLACK | 105D | S2750MTR104A | 387 | 15/10/2026 | 387 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | (NYK warehouse). T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 1st Art (TC 10 pcs) 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903052531 LE5038 | 2026-11-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-10 | D4T AOP GFX T BLACK |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 387 |  | 387 |  |  | 2026-05-10 | 2026-05-10 |  |  | 387 |  | 387 |  |  | 2026-03-10 | 2026-03-10 |  |  | 387 |  | 387
ADIDAS | 0903052564-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 414 | 21/08/2026 | 414 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (04/07/2026) | 21/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052564 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 20/08/2026 | 414 | 414 |  |  |  | 29/07/2026 | 18/08/2026 | 31/07/2026 | 19/08/2026 | 414 | 414
ADIDAS | 0903052598-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 135 | 2026-05-09 | 135 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 05/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052598 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-05-08 | 2026-06-08 | 135 | 135 |  |  |  | 29/07/2026 | 2026-04-08 | 28/07/2026 | 31/07/2026 | 135 | 135
ADIDAS | 0903052654-1 KB5960 | WHITE | 120D | S2608MR0900A | 459 | 15/10/2026 | 459 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0903052654 KB5960 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 459 |  | 459 |  |  | 24/09/2026 | 25/09/2026 | 2026-05-08 | 2026-07-08 | 459 | 459 |  |  |  | 22/09/2026 | 23/09/2026 | 2026-01-08 | 2026-07-08 | 459 | 459
ADIDAS | 0903052671-1 KB5965 | BLACK | 120D | S2608MR0900A | 282 | 15/10/2026 | 282 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903052671 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 282 |  | 282 |  |  | 2026-02-10 | 2026-03-10 |  |  | 282 |  | 282 |  |  | 30/09/2026 | 2026-01-10 |  |  | 282 |  | 282
ADIDAS | 0903052708-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 365 | 22/09/2026 | 365 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052708 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 365 | 365 |  |  |  | 2026-03-09 | 2026-09-09 | 20/08/2026 | 2026-10-09 | 365 | 365
ADIDAS | 0903052721-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 459 | 15/09/2026 | 459 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903052721 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 459 | 459 |  |  |  | 27/08/2026 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 459 | 459
ADIDAS | 0903052745-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 305 | 2026-05-09 | 305 | AN | AN12/06/2026 | G3A,G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052745 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 18/08/2026 | 305 | 305 |  |  |  | 29/07/2026 | 18/08/2026 | 2026-03-08 | 14/08/2026 | 305 | 305
ADIDAS | 0903052755-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 633 | 15/09/2026 | 633 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052755 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 633 | 608 | 25 |  | 1 | 2026-03-09 | 2026-11-09 | 20/08/2026 | 2026-01-09 | 633 | 609 | 24
ADIDAS | 0903052784-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 15/09/2026 | 390 | AN | AN12/06/2026 | G3C,G3F | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052784 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 26/08/2026 | 15/09/2026 | 27/08/2026 | 15/09/2026 | 390 | 365 | 25 |  | 150 | 20/08/2026 | 2026-11-09 | 2026-06-08 | 2026-12-09 | 390 | 380 | 10
ADIDAS | 0903052813-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903052813 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 23/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903053034-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 1170 | 15/09/2026 | 1170 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903053034 KD4899 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 2026-01-09 | 2026-12-09 | 1170 | 1170 |  |  |  | 27/08/2026 | 2026-10-09 | 2026-01-09 | 2026-05-09 | 1170 | 1170
ADIDAS | 0903053050-1 KH0396 | DARK BLUE | 90D | F26SPRMGFX910-MTF | 641 | 2026-12-09 | 641 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty 516318 | PRINT L2+PAD+PPH L1 SUB PROCESS_V3 | 0903053050 KH0396 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | M HIGHLITE T1 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-10-09 | 641 | 641 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 641 | 641
ADIDAS | 0903053086-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 912 | 2026-12-09 | 912 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 10/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053086 KF2398 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV TT |  | FW26 | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-02-09 | 912 | 912 |  |  |  | 27/08/2026 | 2026-04-09 | 22/08/2026 | 2026-09-09 | 912 | 912
ADIDAS | 0903053111-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 5386 | 2026-12-09 | 5386 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053111 JN1956 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT QZ HD |  | SS27 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-10-09 | 5386 | 5386 |  |  |  | 24/08/2026 | 2026-09-09 | 24/08/2026 | 2026-09-09 | 5386 | 5386
ADIDAS | 0903053136-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 780 | 15/09/2026 | 780 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903053136 KD4899 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 31/08/2026 | 2026-12-09 | 780 | 780 |  |  |  | 27/08/2026 | 2026-10-09 | 23/07/2026 | 2026-03-09 | 780 | 780
ADIDAS | 0903053424-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 493 | 31/08/2026 | 493 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053424 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 493 | 493 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 24/08/2026 | 493 | 493
ADIDAS | 0903053462-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 603 | 2026-05-09 | 603 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053462 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 603 | 603 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-07-09 | 603 | 603
ADIDAS | 0903053919-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 782 | 2026-09-09 | 782 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 08/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0903053919 KE8424 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-09 | Run Ess LS M BLACK |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 782 | 782 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-05-09 | 2026-08-09 | 782 | 782 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-04-09 | 2026-08-09 | 782 | 782
ADIDAS | 0903054030-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 468 | 2026-05-09 | 468 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903054030 KX0123 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 468 | 468 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-01-08 | 2026-02-09 | 468 | 468
ADIDAS | 0903054066-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 410 | 2026-05-09 | 410 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 05/09: ex-fty 980004 | PRINT L3+PAD SUB PROCESS_V3 | 0903054066 LC8882 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/08/2026 | M ADI RETRO T BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 410 | 410 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 410 | 410
ADIDAS | 0903054127-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 408 | 2026-07-10 | 408 | SA | SA12/06/2026 | G3K | SHORTS | G3 | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-Jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054127 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | W 3S WV SHO 74 WHITE/BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 408 |  | 408 |  |  | 2026-10-10 | 2026-12-10 |  |  | 408 |  | 408
ADIDAS | 0903054613-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1450 | 15/09/2026 | 1450 | SA | SA12/06/2026 | G1A | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903054613 LE8202 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1450 | 1450 |  |  | 255 | 2026-09-09 | 2026-11-09 | 2026-04-09 | 14/09/2026 | 1450 | 1441 | 9 |  | 12
ADIDAS | 0903054711-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 508 | 15/10/2026 | 508 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054711 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 508 |  | 508 |  |  | 24/09/2026 | 25/09/2026 |  |  | 508 |  | 508 |  |  | 22/09/2026 | 23/09/2026 |  |  | 508 |  | 508
ADIDAS | 0903054732-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 127 | 30/09/2026 | 127 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903054732 LE0358 | 2026-11-09 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 127 |  | 127 |  |  | 29/09/2026 | 30/09/2026 |  |  | 127 |  | 127
ADIDAS | 0903054737-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 426 | 26/08/2026 | 426 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 26/08: ex-fty (Mexico). 652001 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903054737 KY1361 | 29/07/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 426 | 426 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 21/08/2026 | 426 | 426
ADIDAS | 0903054739-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 132 | 15/10/2026 | 132 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054739 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 132 |  | 132 |  |  | 23/09/2026 | 24/09/2026 |  |  | 132 |  | 132 |  |  | 21/09/2026 | 22/09/2026 |  |  | 132 |  | 132
ADIDAS | 0903054752-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 290 | 2026-12-09 | 290 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054752 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 290 | 290 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-09-09 | 290 | 290
ADIDAS | 0903054814-1 JZ7808 | BLACK | 120D | S2608WR0900 | 151 | 15/10/2026 | 151 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 857010 | HT+PAD SUB PROCESS_V3 | 0903054814 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 25/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 151 |  | 151 |  |  | 22/09/2026 | 22/09/2026 |  |  | 151 |  | 151 |  |  | 19/09/2026 | 19/09/2026 |  |  | 151 |  | 151
ADIDAS | 0903054871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2292 | 30/09/2026 | 2292 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty 857010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903054871 KC8152 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 22/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 22/09/2026 | 25/09/2026 |  |  | 2292 |  | 2292 |  |  | 18/09/2026 | 22/09/2026 | 15/09/2026 | 15/09/2026 | 2292 | 13 | 2279 |  |  | 2026-12-09 | 16/09/2026 | 2026-08-09 | 14/09/2026 | 2292 | 1235 | 1057 |  | 83
ADIDAS | 0903055171-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 607 | 15/09/2026 | 607 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 14/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055171 KF2398 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 13/08/2026 | 22/07/2026 | 14/08/2026 | 607 | 607 |  |  |  | 15/07/2026 | 2026-10-08 | 21/07/2026 | 29/07/2026 | 607 | 607
ADIDAS | 0903055195-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 371 | 15/09/2026 | 371 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055195 KV7963 | 28/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 371 | 371 |  |  |  | 22/07/2026 | 2026-03-08 | 22/07/2026 | 2026-05-08 | 371 | 371
ADIDAS | 0903055207-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 3592 | 15/09/2026 | 3592 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 14/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055207 JN1956 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W 3S FT QZ HD |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 3592 | 3592 |  |  | 92 | 2026-04-09 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 3592 | 3577 | 15 |  | 37
ADIDAS | 0903055240-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 879 | 23/09/2026 | 879 | AN | AN12/06/2026 | G3J,G3K | SHORTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055240 KV7963 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-10-08 | 879 | 879 |  |  |  | 24/07/2026 | 2026-05-08 | 25/07/2026 | 2026-07-08 | 879 | 879
ADIDAS | 0903056002-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 472 | 15/10/2026 | 472 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903056002 LD0287 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 24/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 472 |  | 472 |  |  | 21/09/2026 | 22/09/2026 | 2026-05-08 | 29/08/2026 | 472 | 472 |  |  |  | 18/09/2026 | 19/09/2026 | 2026-05-08 | 28/08/2026 | 472 | 472
ADIDAS | 0903056023-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 797 | 23/09/2026 | 797 | SA | SA12/06/2026 | G2T | JACKET | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056023 JE6338 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 3S FT FZ HD |  | SS27 | 28/07/2026 | 28/08/2026 | 29/07/2026 | 31/08/2026 | 797 | 797 |  |  |  | 23/07/2026 | 24/08/2026 | 23/07/2026 | 15/08/2026 | 797 | 797
ADIDAS | 0903056094-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 161 | 15/10/2026 | 161 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (02/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056094 KX3653 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 161 |  | 161 |  |  | 2026-05-10 | 2026-06-10 | 2026-10-09 | 2026-10-09 | 161 | 138 | 23 |  |  | 2026-02-10 | 2026-03-10 | 2026-09-09 | 2026-09-09 | 161 | 138 | 23
ADIDAS | 0903056095-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1009 | 30/09/2026 | 1009 | SA | SA12/06/2026 | G2B | JACKET | G2 | ok | (03/07/2026) | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056095 JD1877 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 1009 |  | 1009 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903056120-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 427 | 30/09/2026 | 427 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (03/07/2026) | 24/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903056120 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 17/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 427 |  | 427 |  |  | 14/09/2026 | 14/09/2026 | 2026-01-08 | 13/08/2026 | 427 | 421 | 6
ADIDAS | 0903056133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 939 | 15/10/2026 | 939 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903056133 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 939 |  | 939 |  |  | 2026-03-10 | 2026-05-10 |  |  | 939 |  | 939 |  |  | 2026-01-10 | 2026-02-10 |  |  | 939 |  | 939
ADIDAS | 0903056160-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 521 | 2026-05-09 | 521 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903056160 LC8882 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T BLACK |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 521 | 521 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-05-08 | 26/08/2026 | 521 | 521
ADIDAS | 0903056304-1 KX8877 | WHITE | 90D | S27GMGFX100 | 376 | 30/09/2026 | 376 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903056304 KX8877 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M CHIP T WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 376 |  | 376 |  |  | 18/09/2026 | 19/09/2026 | 22/08/2026 | 24/08/2026 | 376 | 45 | 331
ADIDAS | 0903056585-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 110 | 30/09/2026 | 110 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056585 KY5988 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 15/09/2026 | 17/09/2026 |  |  | 110 |  | 110 |  |  | 2026-11-09 | 14/09/2026 |  |  | 110 |  | 110 |  |  | 2026-05-09 | 2026-08-09 |  |  | 110 |  | 110
ADIDAS | 0903056609-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 320 | 2026-07-10 | 320 | SA | SA12/06/2026 | G3E | PANTS | G3 | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056609 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 320 |  | 320 |  |  | 2026-09-10 | 2026-10-10 |  |  | 320 |  | 320 |  |  | 2026-03-10 | 2026-05-10 |  |  | 320 |  | 320
ADIDAS | 0903056658-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 208 | 30/09/2026 | 208 | SA | SA12/06/2026 | G3C | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903056658 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-02-10 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 208 |  | 208 |  |  | 29/09/2026 | 30/09/2026 | 2026-05-09 | 2026-11-09 | 208 | 186 | 22
ADIDAS | 0903056767-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 311 | 15/10/2026 | 311 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056767 KX3654 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 311 |  | 311 |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102 |  |  | 30/09/2026 | 2026-01-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102
ADIDAS | 0903056781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 444 | 30/09/2026 | 444 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 21/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056781 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S CHELSEA B7 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 444 |  | 444 |  |  | 17/09/2026 | 18/09/2026 |  |  | 444 |  | 444
ADIDAS | 0903056795-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 402 | 15/10/2026 | 402 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516343 | HT+PAD SUB PROCESS_V3 | 0903056795 KX3654 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 402 |  | 402 |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 2026-10-09 | 402 | 371 | 31 |  |  | 30/09/2026 | 2026-01-10 | 27/08/2026 | 2026-09-09 | 402 | 371 | 31
ADIDAS | 0903056811-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1919 | 30/09/2026 | 1919 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 23/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056811 KY6510 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 3S CHELSEA B7 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1919 |  | 1919 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1919 |  | 1919
ADIDAS | 0903056816-1 KE8424 | BLACK | 120D | S2608MR0906A | 321 | 15/10/2026 | 321 | SI | SI12/06/2026 | G2N | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056816 KE8424 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 321 |  | 321 |  |  | 2026-05-10 | 2026-07-10 |  |  | 321 |  | 321 |  |  | 2026-02-10 | 2026-05-10 |  |  | 321 |  | 321
ADIDAS | 0903056835-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 351 | 30/09/2026 | 351 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056835 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 351 |  | 351 |  |  | 15/09/2026 | 16/09/2026 |  |  | 351 |  | 351 |  |  | 2026-09-09 | 2026-10-09 |  |  | 351 |  | 351
ADIDAS | 0903056841-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 119 | 30/09/2026 | 119 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056841 KC8152 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 119 |  | 119 |  |  | 15/09/2026 | 16/09/2026 |  |  | 119 |  | 119 |  |  | 2026-09-09 | 2026-10-09 |  |  | 119 |  | 119
ADIDAS | 0903056853-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1356 | 2026-05-09 | 1356 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056853 KV7863 | 28/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 21/08/2026 | 30/07/2026 | 18/08/2026 | 1356 | 1356 |  |  |  | 23/07/2026 | 18/08/2026 | 27/07/2026 | 20/08/2026 | 1356 | 1356
ADIDAS | 0903056865-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 443 | 23/09/2026 | 443 | SA | SA12/06/2026 | G3F | PANTS | G3 | ok | (04/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056865 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 18/09/2026 | 19/09/2026 |  |  | 443 |  | 443 |  |  | 15/09/2026 | 16/09/2026 |  |  | 443 |  | 443 |  |  | 2026-09-09 | 2026-10-09 |  |  | 443 |  | 443
ADIDAS | 0903056887-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 30/09/2026 | 300 | AN | AN12/06/2026 | G1H | JACKET | G1 | (13/07/2026) | (03/07/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056887 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 29/09/2026 | 2026-05-09 | 2026-05-09 | 300 | 97 | 203
ADIDAS | 0903056914-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 314 | 2026-12-09 | 314 | AN | AN12/06/2026 | G1G,G1H | JACKET | G1 | ok | (03/07/2026) | 10/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056914 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-10-09 | 314 | 314 |  |  |  | 27/08/2026 | 2026-05-09 | 27/08/2026 | 2026-07-09 | 314 | 314
ADIDAS | 0903056942-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 304 | 2026-09-09 | 304 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056942 KV8005 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 304 | 304 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-09-09 | 304 | 304
ADIDAS | 0903056963-1 JZ7808 | BLACK | 120D | S2608WR0900 | 312 | 15/10/2026 | 312 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056963 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 312 |  | 312 |  |  | 26/09/2026 | 28/09/2026 |  |  | 312 |  | 312 |  |  | 24/09/2026 | 25/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903057469-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 323 | 15/10/2026 | 323 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903057469 LD0285 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 22/09/2026 | 23/09/2026 |  |  | 323 |  | 323 |  |  | 18/09/2026 | 19/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323 |  |  |  | 16/09/2026 | 17/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323
ADIDAS | 0903057500-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 30/09/2026 | 123 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 24/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 19-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057500 LD5446 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 123 |  | 123 |  |  | 22/09/2026 | 24/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903057529-1 LE8187 | BLACK | 105D | S2754MAS513 | 385 | 30/09/2026 | 385 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 13-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057529 LE8187 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 16/09/2026 | M SL WV TP PT BLACK |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 385 |  | 385 |  |  | 2026-12-09 | 15/09/2026 |  |  | 385 |  | 385
ADIDAS | 0903057535-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 30/09/2026 | 512 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057535 LF0718 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 512 |  | 512 |  |  | 16/09/2026 | 17/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903057574-1 LF0723 | BLACK | 105D | S2754MAS511B | 221 | 30/09/2026 | 221 | SI | SI12/06/2026 | G3F | SHORTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057574 LF0723 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | M SL WV SHO BLACK |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 221 |  | 221 |  |  | 22/09/2026 | 22/09/2026 |  |  | 221 |  | 221
ADIDAS | 0903057608-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 379 | 15/10/2026 | 379 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057608 LF0726 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 379 |  | 379 |  |  | 15/09/2026 | 17/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903057614-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 653 | 15/10/2026 | 653 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057614 LH3759 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 653 |  | 653 |  |  | 2026-12-10 | 2026-12-10 |  |  | 653 |  | 653
ADIDAS | 0903057632-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 309 | 15/10/2026 | 309 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057632 LH3761 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 309 |  | 309 |  |  | 2026-12-10 | 13/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903058035-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 292 | 2026-12-09 | 292 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903058035 LE8194 | 28/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-01-09 | 2026-12-09 | 2026-07-09 | 2026-10-09 | 292 | 292 |  |  |  | 28/08/2026 | 2026-09-09 | 24/08/2026 | 2026-12-09 | 292 | 292
ADIDAS | 0903058049-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 320 | 31/08/2026 | 320 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 29/08: ex-fty. DRC 0090-early shipment customer (BTP_08_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058049 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 24/08/2026 | 31/08/2026 | 24/08/2026 | 29/08/2026 | 320 | 320 |  |  |  | 19/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 320 | 320
ADIDAS | 0903058072-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 402 | 30/09/2026 | 402 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058072 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 402 |  | 402 |  |  | 14/09/2026 | 15/09/2026 |  |  | 402 |  | 402
ADIDAS | 0903058091-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 597 | 15/10/2026 | 597 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058091 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 597 |  | 597 |  |  | 19/09/2026 | 22/09/2026 | 2026-04-08 | 20/08/2026 | 597 | 399 | 198
ADIDAS | 0903058157-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 900 | 15/10/2026 | 900 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058157 KX3650 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 900 |  | 900 |  |  | 2026-05-10 | 2026-06-10 | 31/08/2026 | 2026-04-09 | 900 | 360 | 540 |  |  | 2026-02-10 | 2026-03-10 | 29/08/2026 | 2026-04-09 | 900 | 360 | 540
ADIDAS | 0903058652-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 216 | 26/08/2026 | 216 | AN | AN12/06/2026 | G2P | SWEATSHIRT | G2 | ok | (17/07/2026) | 24/08: ex-fty 1st Art (TC 10 pcs) 516333 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903058652 KY1361 | 29/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | REAL HER CR BLACK/BLACK |  | SS27 | 18/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 216 | 216 |  |  |  | 2026-12-08 | 20/08/2026 | 14/08/2026 | 21/08/2026 | 216 | 216
ADIDAS | 0903058691-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 415 | 15/10/2026 | 415 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903058691 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 415 |  | 415 |  |  | 23/09/2026 | 24/09/2026 |  |  | 415 |  | 415 |  |  | 21/09/2026 | 22/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903058943-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 331 | 2026-07-10 | 331 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058943 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 21/08/2026 | 331 | 331 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-05-08 | 20/08/2026 | 331 | 331
ADIDAS | 0903058963-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 539 | 30/09/2026 | 539 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058963 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 539 | 539 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-03-08 | 2026-06-08 | 539 | 539
ADIDAS | 0903058992-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jul (PO NT-351). T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058992 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 332 | 332 |  |  |  | 27/07/2026 | 2026-11-08 | 28/07/2026 | 2026-04-08 | 332 | 332
ADIDAS | 0903059036-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 355 | 2026-05-09 | 355 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059036 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 19/08/2026 | 31/07/2026 | 18/08/2026 | 355 | 355 |  |  |  | 24/07/2026 | 13/08/2026 | 29/07/2026 | 2026-11-08 | 355 | 355
ADIDAS | 0903059059-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 306 | 2026-05-09 | 306 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059059 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 306 | 306 |  |  |  | 2026-04-08 | 2026-11-08 | 29/07/2026 | 2026-11-08 | 306 | 306
ADIDAS | 0903059081-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 519 | 15/10/2026 | 519 | SI | SI12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059081 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 519 |  | 519 |  |  | 2026-03-10 | 2026-06-10 |  |  | 519 |  | 519
ADIDAS | 0903059085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/09/2026 | 300 | AN | AN12/06/2026 | G3A | PANTS | G3 | ok | (03/07/2026) | 21/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059085 KV7863 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 300 | 300 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-01-08 | 14/08/2026 | 300 | 300
ADIDAS | 0903059107-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 253 | 2026-07-10 | 253 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059107 LE4307 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 253 |  | 253 |  |  | 29/09/2026 | 2026-01-10 | 2026-04-09 | 2026-07-09 | 253 | 27 | 226
ADIDAS | 0903059113-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 1150 | 15/09/2026 | 1150 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903059113 LE8210 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-11-09 | 2026-12-09 | 1150 | 1150 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-07-09 | 14/09/2026 | 1150 | 1147 | 3 |  | 8
ADIDAS | 0903059133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059133 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 27/08/2026 | 29/08/2026 | 300 | 295 | 5
ADIDAS | 0903059183-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3J,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516403 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903059183 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 300 |  |  | 300 | 2026-09-09 | 2026-11-09 | 13/09/2026 | 14/09/2026 | 300 | 300 |  |  | 104 | 2026-03-09 | 2026-05-09 | 2026-12-09 | 14/09/2026 | 300 | 300 |  |  | 104
ADIDAS | 0903059345-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 147 | 15/09/2026 | 147 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (02/07/2026) | 14/09: ex-fty. T2 Libolon, using PO 26000011, body actual receives 11-Feb, 3S actual receives 10-Feb. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059345 JE1309 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | W 3S WV SHO |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-09-09 | 2026-11-09 | 147 | 147 |  |  |  | 2026-02-09 | 2026-09-09 | 24/07/2026 | 2026-10-09 | 147 | 147
ADIDAS | 0903059367-1 KB5965 | BLACK | 120D | S2608MR0900A | 360 | 15/10/2026 | 360 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903059367 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 360 |  | 360 |  |  | 2026-02-10 | 2026-03-10 |  |  | 360 |  | 360 |  |  | 30/09/2026 | 2026-01-10 |  |  | 360 |  | 360
ADIDAS | 0903059372-1 LE8187 | BLACK | 105D | S2754MAS513 | 170 | 2026-07-10 | 170 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059372 LE8187 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M SL WV TP PT BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 170 |  | 170 |  |  | 2026-08-10 | 2026-10-10 |  |  | 170 |  | 170
ADIDAS | 0903059402-1 LE8187 | BLACK | 105D | S2754MAS513 | 494 | 2026-07-10 | 494 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059402 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV TP PT BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 494 |  | 494 |  |  | 2026-06-10 | 2026-08-10 |  |  | 494 |  | 494
ADIDAS | 0903059416-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 111 | 15/10/2026 | 111 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059416 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 23/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 111 |  | 111 |  |  | 20/10/2026 | 20/10/2026 |  |  | 111 |  | 111
ADIDAS | 0903059460-1 LE8187 | BLACK | 105D | S2754MAS513 | 465 | 2026-07-10 | 465 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059460 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV TP PT BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 465 |  | 465 |  |  | 2026-06-10 | 2026-08-10 |  |  | 465 |  | 465
ADIDAS | 0903059491-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 362 | 15/10/2026 | 362 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059491 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 23/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 362 |  | 362 |  |  | 20/10/2026 | 20/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903059522-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 218 | 15/10/2026 | 218 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059522 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 23/10/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 218 |  | 218 |  |  | 20/10/2026 | 20/10/2026 |  |  | 218 |  | 218
ADIDAS | 0903059553-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059553 LF0718 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | M SL WV OH PT BLACK |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 100 |  | 100 |  |  | 16/09/2026 | 17/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903059578-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (13/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059578 LG9669 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903059583-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 309 | 15/10/2026 | 309 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059583 LF0726 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 309 |  | 309 |  |  | 15/09/2026 | 17/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903059626-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 299 | 15/10/2026 | 299 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059626 LF0726 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 299 |  | 299 |  |  | 13/10/2026 | 16/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903059656-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 457 | 15/10/2026 | 457 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059656 LF0727 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M SL WV TT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 457 |  | 457 |  |  | 2026-10-10 | 13/10/2026 |  |  | 457 |  | 457
ADIDAS | 0903059680-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 283 | 15/10/2026 | 283 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059680 LF0729 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 20/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 283 |  | 283 |  |  | 16/10/2026 | 17/10/2026 | 2026-07-09 | 2026-07-09 | 283 | 200 | 83
ADIDAS | 0903059710-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/10/2026 | 100 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059710 LH3759 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 0903059734-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/10/2026 | 200 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059734 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200 |  |  | 30/09/2026 | 2026-01-10 |  |  | 200 |  | 200
ADIDAS | 0903059757-1 JZ7808 | BLACK | 120D | S2608WR0900 | 811 | 15/10/2026 | 811 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059757 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 811 |  | 811 |  |  | 26/09/2026 | 28/09/2026 |  |  | 811 |  | 811 |  |  | 24/09/2026 | 25/09/2026 |  |  | 811 |  | 811
ADIDAS | 0903059786-1 KB5965 | BLACK | 120D | S2608MR0900A | 1790 | 15/10/2026 | 1790 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059786 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-10 | Run Ess Tee M |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 1790 |  | 1790 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1790 |  | 1790 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1790 |  | 1790
ADIDAS | 0903060200-1 LF0723 | BLACK | 105D | S2754MAS511B | 552 | 15/10/2026 | 552 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060200 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 552 |  | 552 |  |  | 22/10/2026 | 24/10/2026 |  |  | 552 |  | 552
ADIDAS | 0903060220-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 309 | 2026-07-10 | 309 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 30/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060220 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 19/09/2026 | 2026-04-08 | 20/08/2026 | 309 | 198 | 111
ADIDAS | 0903060841-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 455 | 2026-07-10 | 455 | AN | AN12/06/2026 | G3K | SHORTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903060841 KV7963 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 455 |  | 455 |  |  | 2026-10-10 | 2026-12-10 |  |  | 455 |  | 455
ADIDAS | 0903060907-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 819 | 30/09/2026 | 819 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 1st Art (TC 10 pcs) 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060907 LD6542 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 819 |  | 819 |  |  | 15/09/2026 | 18/09/2026 |  |  | 819 |  | 819
ADIDAS | 0903060936-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060936 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV OH PT BLACK |  | SS27-SPOMA | 2026-01-10 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 28/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903060943-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 200 | 30/09/2026 | 200 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060943 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 200 |  | 200 |  |  | 14/09/2026 | 15/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903060967-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 77 | 15/10/2026 | 77 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903060967 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | W SL WV PT BLACK |  | SS27-SPOMA | 27/10/2026 | 27/10/2026 |  |  | 77 |  | 77 |  |  | 23/10/2026 | 23/10/2026 |  |  | 77 |  | 77
ADIDAS | 0903060981-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 117 | 30/09/2026 | 117 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060981 LD6542 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 117 |  | 117 |  |  | 14/09/2026 | 15/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903061148-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 100 | 15/09/2026 | 100 | SI | SI12/06/2026 | G1G | T-SHIRT | G1 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903061148 LE8194 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-05-09 | 21/08/2026 | 2026-03-09 | 100 | 100
ADIDAS | 0903061664-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 303 | 15/10/2026 | 303 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061664 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M SL WV TT BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-10-10 | 13/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903061878-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 816 | 15/10/2026 | 816 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (01/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061878 LF0726 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 16/10/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 816 |  | 816 |  |  | 13/10/2026 | 16/10/2026 |  |  | 816 |  | 816
ADIDAS | 0903061908-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1613 | 30/09/2026 | 1613 | SI | SI12/06/2026 | G3F | SHORTS | G3 |  |  | 25/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 20-Aug. 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061908 LD5446 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 30/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1613 |  | 1613 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903061936-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 559 | 30/09/2026 | 559 | SA | SA12/06/2026 | G3E | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903061936 LE0358 | 2026-11-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 24/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 559 |  | 559 |  |  | 21/09/2026 | 22/09/2026 | 2026-05-09 | 2026-11-09 | 559 | 451 | 108
ADIDAS | 0903062303-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5037 | 30/09/2026 | 5037 | SI | SI12/06/2026 | G1Q | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062303 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | M 3S CHELSEA B7 |  | SS27 | 16/09/2026 | 25/09/2026 |  |  | 5037 |  | 5037 |  |  | 2026-12-09 | 22/09/2026 |  |  | 5037 |  | 5037
ADIDAS | 0903062323-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 857 | 2026-09-09 | 857 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (03/07/2026) | 09/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903062323 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 857 | 857 |  |  |  | 2026-01-09 | 2026-05-09 | 30/07/2026 | 2026-04-09 | 857 | 857
ADIDAS | 0903062337-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 6000 | 30/09/2026 | 6000 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. Waiting fabric. T2 Gistex, PI Date 25-Jul, ETD ?? T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062337 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | M 3S CHELSEA B7 |  | SS27 | 24/09/2026 | 2026-03-10 |  |  | 6000 |  | 6000 |  |  | 21/09/2026 | 30/09/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903063242-1 KX8877 | WHITE | 90D | S27GMGFX100 | 191 | 2026-12-09 | 191 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903063242 KX8877 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | M CHIP T WHITE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 191 | 191 |  |  |  | 2026-05-09 | 2026-09-09 | 22/08/2026 | 2026-10-09 | 191 | 191
ADIDAS | 0903063361-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 301 | 15/10/2026 | 301 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063361 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | W SL WV SK BLACK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 301 |  | 301 |  |  | 13/10/2026 | 14/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903063503-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 310 | 15/10/2026 | 310 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063503 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | W SL WV SK BLACK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 310 |  | 310 |  |  | 13/10/2026 | 14/10/2026 |  |  | 310 |  | 310
ADIDAS | 0903086049-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 752 | 15/09/2026 | 752 | SA | SA17/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903086049 LE8193 | 2026-01-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-08-09 | 752 | 752 |  |  |  | 27/08/2026 | 2026-04-09 | 26/08/2026 | 2026-08-09 | 752 | 752
ADIDAS | 0903086050-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 459 | 15/09/2026 | 459 | SA | SA17/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903086050 LE8193 | 2026-01-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-09 | REAL H F JSY SE WHITE |  | FW26-FJ | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-11-09 | 459 | 459 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-01-09 | 2026-10-09 | 459 | 459
ADIDAS | 0903089629-1 LF0718 | BLACK | 105D | S2754MAS512B | 301 | 2026-07-10 | 301 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089629 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV OH PT BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 301 |  | 301 |  |  | 2026-07-10 | 2026-08-10 |  |  | 301 |  | 301
ADIDAS | 0903089630-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 2026-07-10 | 301 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089630 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 301 |  | 301 |  |  | 20/10/2026 | 22/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903089631-1 LF0723 | BLACK | 105D | S2754MAS511B | 17 | 2026-07-10 | 17 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089631 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV SHO BLACK |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 17 |  | 17 |  |  | 20/10/2026 | 22/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903089632-1 LF0718 | BLACK | 105D | S2754MAS512B | 59 | 2026-07-10 | 59 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089632 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M SL WV OH PT BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 59 |  | 59 |  |  | 2026-07-10 | 2026-08-10 |  |  | 59 |  | 59
ADIDAS | 0903091452-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 808 | 23/09/2026 | 808 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903091452 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 21/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 808 |  | 808 |  |  | 17/09/2026 | 18/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903093104-1 JZ7711 | BLACK | 120D | S2608MR0202 | 149 | 2026-07-10 | 149 | SA | SA23/06/2026 | G3E | SHORTS | G3 | ok | (04/08/2026) | T2 Hua Feng, PI Date 31-Jul, actual receives 04-Sep. T2 Far Easten, PI Date 14-Aug, actual receives 03-Sep. 1st Art (TC 10 pcs) 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093104 JZ7711 | 21/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 2026-05-10 | 2026-06-10 |  |  | 149 |  | 149 |  |  | 2026-01-10 | 2026-02-10 |  |  | 149 |  | 149 |  |  | 28/09/2026 | 29/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903093145-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 392 | 15/10/2026 | 392 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903093145 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 392 |  | 392 |  |  | 2026-05-10 | 2026-06-10 |  |  | 392 |  | 392 |  |  | 2026-03-10 | 2026-05-10 |  |  | 392 |  | 392
ADIDAS | 0903093460-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 481 | 15/10/2026 | 481 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093460 KY9384 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 481 |  | 481 |  |  | 19/10/2026 | 21/10/2026 |  |  | 481 |  | 481 |  |  | 15/10/2026 | 17/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903093463-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 600 | 15/10/2026 | 600 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093463 KY9384 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 600 |  | 600 |  |  | 19/10/2026 | 21/10/2026 |  |  | 600 |  | 600 |  |  | 15/10/2026 | 17/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903093466-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 300 | 15/10/2026 | 300 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093466 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 17/10/2026 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903093469-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 579 | 15/10/2026 | 579 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093469 KD3854 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 19/10/2026 | 20/10/2026 |  |  | 579 |  | 579 |  |  | 15/10/2026 | 16/10/2026 |  |  | 579 |  | 579 |  |  | 2026-12-10 | 13/10/2026 |  |  | 579 |  | 579
ADIDAS | 0903093480-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 350 | 15/10/2026 | 350 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 24-Jul, ETD ?? 516241 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093480 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 350 |  | 350 |  |  | 14/10/2026 | 15/10/2026 |  |  | 350 |  | 350 |  |  | 2026-10-10 | 2026-12-10 |  |  | 350 |  | 350
ADIDAS | 0903093503-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 5119 | 15/10/2026 | 5119 | SI | SI23/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | 28/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093503 KC9082 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 14/10/2026 | 24/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-10-10 | 21/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-07-10 | 17/10/2026 |  |  | 5119 |  | 5119
ADIDAS | 0903093882-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1600 | 30/09/2026 | 1600 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903093882 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 1600 |  | 1600 |  |  | 17/09/2026 | 18/09/2026 |  |  | 1600 |  | 1600 |  |  | 16/09/2026 | 17/09/2026 |  |  | 1600 |  | 1600
ADIDAS | 0903093883-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 500 | 30/09/2026 | 500 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 839055 | PRINT L2+HT SUB PROCESS_V3 | 0903093883 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 23/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 19/09/2026 |  |  | 500 |  | 500 |  |  | 18/09/2026 | 18/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903093884-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 250 | 23/09/2026 | 250 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093884 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 21/09/2026 |  |  | 250 |  | 250 |  |  | 17/09/2026 | 17/09/2026 |  |  | 250 |  | 250 |  |  | 16/09/2026 | 16/09/2026 |  |  | 250 |  | 250
ADIDAS | 0903093889-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 157 | 23/09/2026 | 157 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093889 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 157 |  | 157 |  |  | 15/09/2026 | 17/09/2026 |  |  | 157 |  | 157 |  |  | 14/09/2026 | 16/09/2026 |  |  | 157 |  | 157
ADIDAS | 0903093890-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 403 | 23/09/2026 | 403 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093890 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 21/09/2026 |  |  | 403 |  | 403 |  |  | 17/09/2026 | 17/09/2026 |  |  | 403 |  | 403 |  |  | 16/09/2026 | 16/09/2026 |  |  | 403 |  | 403
ADIDAS | 0903093891-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 533 | 23/09/2026 | 533 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093891 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 533 |  | 533 |  |  | 15/09/2026 | 17/09/2026 |  |  | 533 |  | 533 |  |  | 14/09/2026 | 16/09/2026 |  |  | 533 |  | 533
ADIDAS | 0903093893-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 107 | 22/09/2026 | 107 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 08-Sep. 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093893 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 107 |  | 107 |  |  | 15/09/2026 | 17/09/2026 |  |  | 107 |  | 107 |  |  | 14/09/2026 | 16/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903093895-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 583 | 15/10/2026 | 583 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093895 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 583 |  | 583 |  |  | 14/10/2026 | 14/10/2026 |  |  | 583 |  | 583 |  |  | 13/10/2026 | 13/10/2026 |  |  | 583 |  | 583
ADIDAS | 0903093906-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 559 | 15/10/2026 | 559 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093906 KV0333 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 559 |  | 559 |  |  | 21/09/2026 | 22/09/2026 |  |  | 559 |  | 559 |  |  | 19/09/2026 | 21/09/2026 |  |  | 559 |  | 559
ADIDAS | 0903093907-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 309 | 15/10/2026 | 309 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093907 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 309 |  | 309 |  |  | 21/09/2026 | 22/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903093908-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 345 | 15/10/2026 | 345 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903093908 LG1784 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 345 |  | 345 |  |  | 22/09/2026 | 23/09/2026 |  |  | 345 |  | 345 |  |  | 21/09/2026 | 22/09/2026 |  |  | 345 |  | 345
ADIDAS | 0903093909-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 158 | 15/10/2026 | 158 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093909 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 158 |  | 158 |  |  | 22/09/2026 | 23/09/2026 |  |  | 158 |  | 158 |  |  | 21/09/2026 | 22/09/2026 |  |  | 158 |  | 158
ADIDAS | 0903093910-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 425 | 15/10/2026 | 425 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093910 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 425 |  | 425 |  |  | 23/09/2026 | 24/09/2026 |  |  | 425 |  | 425 |  |  | 22/09/2026 | 23/09/2026 |  |  | 425 |  | 425
ADIDAS | 0903093911-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 354 | 15/10/2026 | 354 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093911 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 354 |  | 354 |  |  | 23/09/2026 | 24/09/2026 |  |  | 354 |  | 354 |  |  | 22/09/2026 | 23/09/2026 |  |  | 354 |  | 354
ADIDAS | 0903093912-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 105 | 15/10/2026 | 105 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093912 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 25/09/2026 | 26/09/2026 |  |  | 105 |  | 105 |  |  | 22/09/2026 | 23/09/2026 |  |  | 105 |  | 105 |  |  | 21/09/2026 | 22/09/2026 |  |  | 105 |  | 105
ADIDAS | 0903095162-1 KE9656 | BLACK | 105D | S2608WR0201A | 7 | 15/10/2026 | 7 | SI | SI23/06/2026 | G3D | SHORTS | G3 | ok |  | 23/09: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 22-Aug, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 10-Sep. T2 Y.R.C, PI Date 15-Aug, actual receives 03-Sep (using fabric from TRAX). T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095162 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 7 |  | 7 |  |  | 13/10/2026 | 13/10/2026 |  |  | 7 |  | 7 |  |  | 2026-12-10 | 2026-12-10 |  |  | 7 |  | 7
ADIDAS | 0903095174-1 KE9656 | BLACK | 105D | S2608WR0201A | 5411 | 15/10/2026 | 5411 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (15/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | PAD+HT SUB PROCESS_V3 | 0903095174 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 29/10/2026 |  |  | 5411 |  | 5411 |  |  | 13/10/2026 | 26/10/2026 |  |  | 5411 |  | 5411 |  |  | 2026-12-10 | 24/10/2026 |  |  | 5411 |  | 5411
ADIDAS | 0903095176-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 503 | 15/10/2026 | 503 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095176 LC6791 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX | 23/10/2026 | 24/10/2026 |  |  | 503 |  | 503 |  |  | 20/10/2026 | 21/10/2026 |  |  | 503 |  | 503 |  |  | 16/10/2026 | 17/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903095186-1 KA6229 | BLACK | 120D | S2608WR0202 | 448 | 23/09/2026 | 448 | SA | SA23/06/2026 | G1N | SHORTS | G1 | ok | ok | 21/09: ex-fty. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095186 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 448 |  | 448 |  |  | 17/09/2026 | 18/09/2026 |  |  | 448 |  | 448 |  |  | 14/09/2026 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 448 | 287 | 161 |  | 287
ADIDAS | 0903095189-1 KA6229 | BLACK | 120D | S2608WR0202 | 301 | 22/09/2026 | 301 | SA | SA23/06/2026 | G1P | SHORTS | G1 | ok | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual recieves 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Aug (switch fabric from TREX). 1st Art (TC 10 pcs) 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095189 KA6229 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 15/09/2026 | 18/09/2026 |  |  | 301 |  | 301 |  |  | 2026-11-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 301 | 269 | 32 |  | 40
ADIDAS | 0903095193-1 KA6229 | BLACK | 120D | S2608WR0202 | 339 | 15/10/2026 | 339 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 07-Sep, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095193 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 339 |  | 339 |  |  | 2026-06-10 | 2026-08-10 |  |  | 339 |  | 339 |  |  | 2026-02-10 | 2026-05-10 | 2026-09-09 | 2026-09-09 | 339 | 322 | 17
ADIDAS | 0903095197-1 KA6229 | BLACK | 120D | S2608WR0202 | 765 | 22/09/2026 | 765 | SA | SA23/06/2026 | G1P | SHORTS | G1 | (14/08/2026) | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095197 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 22/09/2026 |  |  | 765 |  | 765 |  |  | 15/09/2026 | 18/09/2026 |  |  | 765 |  | 765 |  |  | 2026-11-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 765 | 558 | 207 |  | 558
ADIDAS | 0903095199-1 KA6229 | BLACK | 120D | S2608WR0202 | 277 | 15/10/2026 | 277 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095199 KA6229 | 21/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-10 | 2026-12-10 |  |  | 277 |  | 277 |  |  | 2026-06-10 | 2026-08-10 |  |  | 277 |  | 277 |  |  | 2026-02-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903095204-1 KC4947 | BLACK | 105D | S2608WR0216 | 523 | 15/10/2026 | 523 | SA | SA23/06/2026 | G3G | PANTS | G3 | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903095204 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 13/10/2026 | adi365 Astro W |  | SS27-TRAX | 13/10/2026 | 16/10/2026 |  |  | 523 |  | 523 |  |  | 2026-09-10 | 13/10/2026 |  |  | 523 |  | 523 |  |  | 2026-08-10 | 2026-12-10 |  |  | 523 |  | 523
ADIDAS | 0903110856-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1103 | 26/09/2026 | 1103 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 22-Jul, ETD ?? Waiting fabric. T2 Formosa, PI Date 26-Jul, ETD 03-Aug, ETA-Kaha 14-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110856 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 19/09/2026 | 24/09/2026 |  |  | 1103 |  | 1103 |  |  | 16/09/2026 | 21/09/2026 |  |  | 1103 |  | 1103
ADIDAS | 0903110887-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 5118 | 15/10/2026 | 5118 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110887 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-09-10 | 29/10/2026 |  |  | 5118 |  | 5118 |  |  | 2026-06-10 | 26/10/2026 |  |  | 5118 |  | 5118
ADIDAS | 0903128588-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903128588 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-09-09 | 420 | 420
ADIDAS | 0903129093-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 792 | 15/09/2026 | 792 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129093 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 16/09/2026 | 2026-02-09 | 15/09/2026 | 792 | 792 |  |  |  | 27/08/2026 | 2026-12-09 | 2026-05-08 | 22/08/2026 | 792 | 792
ADIDAS | 0903129353-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 497 | 26/08/2026 | 497 | SI | SI26/06/2026 | G2L,G2O | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129353 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 497 | 497 |  |  |  | 18/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 497 | 497
ADIDAS | 0903129376-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 550 | 15/10/2026 | 550 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129376 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 550 |  | 550 |  |  | 2026-07-10 | 2026-08-10 |  |  | 550 |  | 550
ADIDAS | 0903129505-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 303 | 15/10/2026 | 303 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129505 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303 |  |  | 2026-10-10 | 13/10/2026 | 2026-02-09 | 2026-02-09 | 303 | 19 | 284
ADIDAS | 0903129548-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 350 | 28/08/2026 | 350 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3 SUB PROCESS_V3 | 0903129548 LI2667 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 350 | 350 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-12-08 | 350 | 350
ADIDAS | 0903129731-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 471 | 26/08/2026 | 471 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129731 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 471 | 471 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 29/08/2026 | 471 | 471
ADIDAS | 0903129796-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 432 | 28/08/2026 | 432 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129796 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 432 | 432 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 29/08/2026 | 432 | 432
ADIDAS | 0903129828-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 458 | 28/08/2026 | 458 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129828 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 458 | 458 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 458 | 458
ADIDAS | 0903129915-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 350 | 28/08/2026 | 350 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129915 LI2668 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-04-08 | 2026-10-08 | 350 | 350 |  |  |  | 30/07/2026 | 2026-06-08 | 2026-03-08 | 2026-07-08 | 350 | 350
ADIDAS | 0903129964-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 4 | 28/08/2026 | 4 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 857010 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129964 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 4 | 4 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 18/08/2026 | 4 | 4
ADIDAS | 0903130488-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 2026-07-10 | 103 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130488 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 103 |  | 103 |  |  | 29/09/2026 | 30/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903130527-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130527 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 500 |  | 500 |  |  | 2026-05-10 | 2026-07-10 |  |  | 500 |  | 500
ADIDAS | 0903130582-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 106 | 2026-07-10 | 106 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130582 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 106 |  | 106 |  |  | 2026-02-10 | 2026-03-10 | 20/08/2026 | 29/08/2026 | 106 | 34 | 72
ADIDAS | 0903130615-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130615 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903130649-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 234 | 31/08/2026 | 234 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903130649 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 234 | 234 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-10-08 | 234 | 234
ADIDAS | 0903130700-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 680 | 28/08/2026 | 680 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903130700 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 27/08/2026 | 21/08/2026 | 27/08/2026 | 680 | 680 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-03-08 | 2026-10-08 | 680 | 680
ADIDAS | 0903130740-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 325 | 30/09/2026 | 325 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130740 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 3S FT OH PT |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 325 |  | 325 |  |  | 2026-02-10 | 2026-03-10 | 14/08/2026 | 2026-07-09 | 325 | 294 | 31
ADIDAS | 0903130742-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 208 | 15/09/2026 | 208 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130742 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 2026-03-09 | 24/08/2026 | 2026-03-09 | 208 | 208 |  |  |  | 19/08/2026 | 31/08/2026 | 2026-07-08 | 2026-11-08 | 208 | 208
ADIDAS | 0903130761-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 550 | 15/10/2026 | 550 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130761 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 550 |  | 550 |  |  | 20/10/2026 | 21/10/2026 | 2026-03-09 | 2026-09-09 | 550 | 85 | 465
ADIDAS | 0903130786-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 101 | 2026-07-10 | 101 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130786 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 101 |  | 101 |  |  | 14/09/2026 | 15/09/2026 | 2026-02-09 | 2026-02-09 | 101 | 101
ADIDAS | 0903130838-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 358 | 31/08/2026 | 358 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130838 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 358 | 358 |  |  |  | 14/08/2026 | 27/08/2026 | 2026-04-08 | 2026-07-08 | 358 | 358
ADIDAS | 0903130929-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 15/10/2026 | 103 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130929 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 103 |  | 103 |  |  | 2026-07-10 | 2026-07-10 |  |  | 103 |  | 103
ADIDAS | 0903130982-1 LF0723 | BLACK | 105D | S2754MAS511B | 308 | 15/10/2026 | 308 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130982 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 308 |  | 308 |  |  | 22/10/2026 | 24/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903130983-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 147 | 31/08/2026 | 147 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903130983 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 147 | 147 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-04-08 | 2026-08-08 | 147 | 147
ADIDAS | 0903131013-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 120 | 31/08/2026 | 120 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131013 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 120 | 120 |  |  |  | 18/08/2026 | 20/08/2026 | 2026-05-08 | 2026-08-08 | 120 | 120
ADIDAS | 0903131041-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 343 | 23/09/2026 | 343 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131041 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 343 |  | 343 |  |  | 14/09/2026 | 15/09/2026 | 31/08/2026 | 2026-03-09 | 343 | 292 | 51
ADIDAS | 0903131046-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 103 | 15/10/2026 | 103 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131046 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 103 |  | 103 |  |  | 20/10/2026 | 21/10/2026 | 2026-02-09 | 2026-10-09 | 103 | 103
ADIDAS | 0903131085-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 31/08/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131085 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 31/08/2026 | 249 | 249 |  |  |  | 18/08/2026 | 27/08/2026 | 2026-04-08 | 2026-07-08 | 249 | 249
ADIDAS | 0903131111-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 254 | 30/09/2026 | 254 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903131111 LE4307 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 254 |  | 254 |  |  | 23/09/2026 | 25/09/2026 |  |  | 254 |  | 254
ADIDAS | 0903131134-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 115 | 31/08/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903131134 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 115 | 115 |  |  |  | 24/08/2026 | 27/08/2026 | 2026-06-08 | 24/08/2026 | 115 | 115
ADIDAS | 0903131303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 221 | 28/08/2026 | 221 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903131303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 221 | 221 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-01-09 | 221 | 221
ADIDAS | 0903131630-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 236 | 28/08/2026 | 236 | AN | AN26/06/2026 | G1G,G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131630 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 236 | 236 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-04-08 | 2026-06-08 | 236 | 236
ADIDAS | 0903131716-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131716 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 303 |  | 303 |  |  | 2026-09-10 | 2026-10-10 |  |  | 303 |  | 303
ADIDAS | 0903131801-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 744 | 15/10/2026 | 744 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131801 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 744 |  | 744 |  |  | 15/10/2026 | 17/10/2026 |  |  | 744 |  | 744
ADIDAS | 0903131901-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131901 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 18/08/2026 | 2026-07-08 | 14/08/2026 | 150 | 150 |  |  |  | 30/07/2026 | 2026-12-08 | 2026-04-08 | 2026-12-08 | 150 | 150
ADIDAS | 0903132014-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 225 | 28/08/2026 | 225 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132014 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 225 | 225 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-07-08 | 19/08/2026 | 225 | 225
ADIDAS | 0903132049-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 270 | 15/10/2026 | 270 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132049 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 270 |  | 270 |  |  | 17/10/2026 | 19/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903132063-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 28/08/2026 | 150 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132063 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 150 | 150 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 29/08/2026 | 150 | 150
ADIDAS | 0903132086-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 250 | 28/08/2026 | 250 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132086 LI2646 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 250 | 250 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 20/08/2026 | 250 | 250
ADIDAS | 0903132121-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 190 | 28/08/2026 | 190 | SA | SA26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132121 LI2671 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 27/08/2026 | 26/08/2026 | 26/08/2026 | 190 | 190 |  |  |  | 20/08/2026 | 21/08/2026 | 20/08/2026 | 2026-01-09 | 190 | 190
ADIDAS | 0903132226-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 225 | 28/08/2026 | 225 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903132226 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 225 | 225 |  |  |  | 2026-12-08 | 19/08/2026 | 2026-06-08 | 2026-12-08 | 225 | 225
ADIDAS | 0903132278-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 315 | 28/08/2026 | 315 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 547012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132278 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UKRAINE | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 315 | 315 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 28/08/2026 | 315 | 315
ADIDAS | 0903132419-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 106 | 2026-07-10 | 106 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132419 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 106 |  | 106 |  |  | 2026-05-10 | 2026-07-10 |  |  | 106 |  | 106
ADIDAS | 0903132455-1 LD5424 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS614WVB | 331 | 15/10/2026 | 331 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Formosa, PI Date 12-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 12-Aug, actual receives 28-Aug. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132455 LD5424 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | M 95S WV WB LND OLIVE FOUR S27/OFF WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 331 |  | 331 |  |  | 13/10/2026 | 15/10/2026 |  |  | 331 |  | 331
ADIDAS | 0903132482-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 150 | 2026-12-09 | 150 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132482 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-03-09 | 150 | 150 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-03-09 | 150 | 150
ADIDAS | 0903132526-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 250 | 28/08/2026 | 250 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 1st Art (TC 10 pcs) 512106 | PRINT L3 SUB PROCESS_V3 | 0903132526 LI2667 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 14/08/2026 | 2026-12-08 | 2026-12-08 | 250 | 250 |  |  |  | 2026-07-08 | 2026-11-08 | 2026-04-08 | 2026-06-08 | 250 | 250
ADIDAS | 0903132534-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 255 | 15/09/2026 | 255 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132534 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 2026-04-09 | 255 | 255 |  |  |  | 29/08/2026 | 31/08/2026 | 15/08/2026 | 24/08/2026 | 255 | 255
ADIDAS | 0903132553-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132553 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 200 | 200 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 22/08/2026 | 200 | 200
ADIDAS | 0903132567-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 350 | 28/08/2026 | 350 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132567 LI2645 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 26/08/2026 | 350 | 350 |  |  |  | 19/08/2026 | 24/08/2026 | 14/08/2026 | 21/08/2026 | 350 | 350
ADIDAS | 0903132571-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 704 | 30/09/2026 | 704 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132571 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 3S FT FZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 704 |  | 704 |  |  | 14/09/2026 | 15/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903132573-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132573 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 20/08/2026 | 27/08/2026 | 200 | 200
ADIDAS | 0903132592-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 170 | 2026-12-09 | 170 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132592 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 170 | 170 |  |  |  | 29/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 170 | 170
ADIDAS | 0903132602-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 100 | 31/08/2026 | 100 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132602 LI2668 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-10-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-10-08 | 2026-12-08 | 2026-10-08 | 2026-11-08 | 100 | 100 |  |  |  | 2026-05-08 | 2026-07-08 | 2026-03-08 | 2026-04-08 | 100 | 100
ADIDAS | 0903132697-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 691 | 15/09/2026 | 691 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132697 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 2026-03-09 | 24/08/2026 | 2026-01-09 | 691 | 691 |  |  |  | 18/08/2026 | 31/08/2026 | 2026-04-08 | 2026-07-08 | 691 | 691
ADIDAS | 0903132705-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 170 | 30/09/2026 | 170 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 22/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132705 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 170 |  | 170 |  |  | 23/09/2026 | 25/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903132709-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 15/10/2026 | 600 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132709 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 14/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 600 |  | 600 |  |  | 2026-10-10 | 13/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903132743-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 226 | 31/08/2026 | 226 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903132743 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 226 | 226 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-03-08 | 2026-07-08 | 226 | 226
ADIDAS | 0903132754-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 278 | 15/10/2026 | 278 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132754 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 278 |  | 278 |  |  | 2026-09-10 | 2026-10-10 |  |  | 278 |  | 278
ADIDAS | 0903132786-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 369 | 15/10/2026 | 369 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132786 KY6510 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 369 |  | 369 |  |  | 2026-02-10 | 2026-03-10 |  |  | 369 |  | 369
ADIDAS | 0903132803-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132803 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 266 |  | 266 |  |  | 2026-07-10 | 2026-07-10 |  |  | 266 |  | 266
ADIDAS | 0903132827-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132827 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 271 |  | 271 |  |  | 2026-05-10 | 2026-06-10 | 28/08/2026 | 2026-03-09 | 271 | 268 | 3
ADIDAS | 0903132837-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 143 | 2026-07-10 | 143 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132837 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 | 2026-01-09 | 2026-04-09 | 143 | 36 | 107
ADIDAS | 0903132864-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 15/10/2026 | 316 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132864 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 19/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 316 |  | 316 |  |  | 15/10/2026 | 17/10/2026 |  |  | 316 |  | 316
ADIDAS | 0903132871-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 358 | 15/10/2026 | 358 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Kahatex, PI Date 12-Aug, actual receives 05-Sep. T2 Formosa, PI Date 12-Aug, actual receives 03-Sep. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132871 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 358 |  | 358 |  |  | 15/10/2026 | 16/10/2026 |  |  | 358 |  | 358
ADIDAS | 0903132881-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 180 | 28/08/2026 | 180 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132881 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 21/08/2026 | 20/08/2026 | 21/08/2026 | 180 | 180 |  |  |  | 14/08/2026 | 18/08/2026 | 2026-04-08 | 2026-07-08 | 180 | 180
ADIDAS | 0903132916-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 900 | 15/10/2026 | 900 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132916 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 900 |  | 900 |  |  | 19/10/2026 | 20/10/2026 |  |  | 900 |  | 900
ADIDAS | 0903132931-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 308 | 2026-07-10 | 308 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132931 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 308 |  | 308 |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 29/08/2026 | 308 | 308
ADIDAS | 0903132955-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132955 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 266 |  | 266 |  |  | 2026-09-10 | 2026-10-10 |  |  | 266 |  | 266
ADIDAS | 0903132969-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132969 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-12-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 1000 |  | 1000 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1000 |  | 1000
ADIDAS | 0903132997-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132997 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-01-09 | 2026-10-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-09-09 | 2026-04-08 | 26/08/2026 | 420 | 420
ADIDAS | 0903133002-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1375 | 2026-07-10 | 1375 | SI | SI26/06/2026 | G1H | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133002 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 1375 |  | 1375 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 24/08/2026 | 1375 | 1293 | 82
ADIDAS | 0903133009-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133009 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 15/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 1000 |  | 1000 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903133055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1218 | 2026-07-10 | 1218 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1218 |  | 1218 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1218 |  | 1218
ADIDAS | 0903133059-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 367 | 15/10/2026 | 367 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133059 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 367 |  | 367 |  |  | 13/10/2026 | 14/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903133104-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 2450 | 2026-07-10 | 2450 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133104 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 2450 |  | 2450 |  |  | 2026-03-10 | 2026-06-10 | 26/08/2026 | 28/08/2026 | 2450 | 2432 | 18
ADIDAS | 0903133114-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 282 | 15/09/2026 | 282 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133114 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 2026-07-09 | 282 | 277 | 5 |  |  | 29/08/2026 | 2026-11-09 | 20/08/2026 | 24/08/2026 | 282 | 282
ADIDAS | 0903133128-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 500 | 15/10/2026 | 500 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133128 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 13/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 500 |  | 500 |  |  | 2026-09-10 | 2026-09-10 |  |  | 500 |  | 500
ADIDAS | 0903133146-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133146 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903133194-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 103 | 2026-07-10 | 103 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133194 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 103 |  | 103 |  |  | 2026-02-10 | 2026-03-10 | 31/08/2026 | 2026-05-09 | 103 | 101 | 2
ADIDAS | 0903133260-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 194 | 2026-07-10 | 194 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133260 LI2646 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 194 |  | 194 |  |  | 28/09/2026 | 29/09/2026 | 28/08/2026 | 28/08/2026 | 194 | 181 | 13
ADIDAS | 0903133331-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 500 | 2026-07-10 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133331 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 500 |  | 500 |  |  | 2026-02-10 | 2026-03-10 | 31/08/2026 | 2026-04-09 | 500 | 484 | 16
ADIDAS | 0903133357-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 675 | 2026-02-09 | 675 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133357 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 675 | 675 |  |  |  | 27/08/2026 | 28/08/2026 | 21/08/2026 | 2026-03-09 | 675 | 675
ADIDAS | 0903133374-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 143 | 2026-07-10 | 143 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133374 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 143 |  | 143 |  |  | 29/09/2026 | 30/09/2026 |  |  | 143 |  | 143
ADIDAS | 0903133397-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 115 | 2026-02-09 | 115 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133397 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 115 | 115 |  |  |  | 27/08/2026 | 28/08/2026 | 26/08/2026 | 2026-01-09 | 115 | 115
ADIDAS | 0903133440-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 347 | 31/08/2026 | 347 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133440 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 347 | 347 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 2026-02-09 | 347 | 346 | 1
ADIDAS | 0903133475-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133475 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100
ADIDAS | 0903133506-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E,G2R | ACCESSORIES | G1,G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133506 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-03-09 | 24/08/2026 | 31/08/2026 | 420 | 420
ADIDAS | 0903133517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133517 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 19/08/2026 | 26/08/2026 | 220 | 220
ADIDAS | 0903133575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 220 | 220 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 220 | 220
ADIDAS | 0903133589-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 586 | 23/09/2026 | 586 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133589 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 586 |  | 586 |  |  | 14/09/2026 | 15/09/2026 | 2026-01-09 | 2026-04-09 | 586 | 393 | 193
ADIDAS | 0903133603-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 84 | 15/10/2026 | 84 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133603 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 84 | 84 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 84 | 84
ADIDAS | 0903133644-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133644 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 28/08/2026 | 2026-03-09 | 27/08/2026 | 2026-02-09 | 295 | 295
ADIDAS | 0903133706-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 251 | 15/10/2026 | 251 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133706 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 251 |  | 251 |  |  | 2026-07-10 | 2026-07-10 |  |  | 251 |  | 251
ADIDAS | 0903133759-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 15/09/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133759 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-01-09 | 249 | 249 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-04-08 | 2026-05-08 | 249 | 249
ADIDAS | 0903133823-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1008 | 28/08/2026 | 1008 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133823 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 1008 | 1008 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-04-08 | 26/08/2026 | 1008 | 1008
ADIDAS | 0903133849-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 423 | 2026-07-10 | 423 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133849 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 423 |  | 423 |  |  | 30/09/2026 | 2026-02-10 |  |  | 423 |  | 423
ADIDAS | 0903133851-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 2026-07-10 | 156 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133851 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 156 |  | 156 |  |  | 14/09/2026 | 15/09/2026 | 31/08/2026 | 31/08/2026 | 156 | 150 | 6
ADIDAS | 0903133871-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133871 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 234 | 234 |  |  |  | 28/08/2026 | 31/08/2026 | 26/08/2026 | 2026-03-09 | 234 | 234
ADIDAS | 0903133936-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 358 | 2026-07-10 | 358 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133936 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 358 |  | 358 |  |  | 28/09/2026 | 29/09/2026 | 15/08/2026 | 2026-10-09 | 358 | 349 | 9
ADIDAS | 0903133965-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133965 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-08 | 2026-10-08 | 420 | 420
ADIDAS | 0903134033-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 284 | 15/09/2026 | 284 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134033 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 2026-05-09 | 284 | 284 |  |  |  | 29/08/2026 | 2026-11-09 | 19/08/2026 | 2026-09-09 | 284 | 284
ADIDAS | 0903134047-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2000 | 2026-07-10 | 2000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134047 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-12-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 2000 |  | 2000 |  |  | 2026-08-10 | 2026-12-10 |  |  | 2000 |  | 2000
ADIDAS | 0903134049-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 980 | 15/10/2026 | 980 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134049 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 980 |  | 980 |  |  | 14/10/2026 | 15/10/2026 |  |  | 980 |  | 980
ADIDAS | 0903134052-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 119 | 31/08/2026 | 119 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134052 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 119 | 119 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 119 | 119
ADIDAS | 0903134065-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 31/08/2026 | 160 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134065 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 160 | 160 |  |  |  | 24/08/2026 | 27/08/2026 | 15/08/2026 | 28/08/2026 | 160 | 160
ADIDAS | 0903134093-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 204 | 31/08/2026 | 204 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903134093 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 204 | 204 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 204 | 202 | 2
ADIDAS | 0903134104-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 142 | 2026-02-09 | 142 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134104 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 142 | 142 |  |  |  | 27/08/2026 | 29/08/2026 | 18/08/2026 | 27/08/2026 | 142 | 142
ADIDAS | 0903134120-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1000 | 2026-07-10 | 1000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134120 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 1000 |  | 1000 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1000 |  | 1000
ADIDAS | 0903134126-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 203 | 15/10/2026 | 203 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134126 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 203 |  | 203 |  |  | 2026-05-10 | 2026-06-10 | 19/08/2026 | 31/08/2026 | 203 | 203
ADIDAS | 0903134127-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 912 | 26/08/2026 | 912 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134127 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 13/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 13/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 912 | 912 |  |  |  | 2026-10-08 | 20/08/2026 | 2026-06-08 | 19/08/2026 | 912 | 912
ADIDAS | 0903134177-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 190 | 28/08/2026 | 190 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 1st Art (TC 10 pcs) 512106 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134177 LI2668 | 2026-10-08 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 190 | 190 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-03-08 | 2026-05-08 | 190 | 190
ADIDAS | 0903134200-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 225 | 15/09/2026 | 225 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134200 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 225 | 225 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-07-09 | 225 | 225
ADIDAS | 0903134339-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 210 | 2026-12-09 | 210 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134339 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 210 | 210 |  |  |  | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-10-09 | 210 | 210
ADIDAS | 0903134348-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 150 | 31/08/2026 | 150 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3 SUB PROCESS_V3 | 0903134348 LI2667 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 150 | 150 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 2026-05-08 | 150 | 150
ADIDAS | 0903134404-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134404 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 100 | 100 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-04-09 | 100 | 100
ADIDAS | 0903134412-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 150 | 31/08/2026 | 150 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134412 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 150 | 150 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-10-08 | 29/08/2026 | 150 | 150
ADIDAS | 0903134448-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134448 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 28/08/2026 | 31/08/2026 | 27/08/2026 | 2026-07-09 | 100 | 100
ADIDAS | 0903134454-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 31/08/2026 | 100 | SA | SA26/06/2026 | G1M,G1O | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134454 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 100 | 100 |  |  |  | 21/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 100 | 100
ADIDAS | 0903134486-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134486 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 29/08/2026 | 2026-02-09 | 28/08/2026 | 2026-12-09 | 295 | 295
ADIDAS | 0903134488-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 425 | 26/08/2026 | 425 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 848012 | PRINT L3 SUB PROCESS_V3 | 0903134488 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 425 | 425 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-04-08 | 2026-11-08 | 425 | 425
ADIDAS | 0903134529-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134529 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-03-09 | 2026-04-09 | 220 | 220 |  |  |  | 28/08/2026 | 2026-03-09 | 2026-02-09 | 2026-10-09 | 220 | 220
ADIDAS | 0903134584-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 690 | 28/08/2026 | 690 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134584 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 690 | 690 |  |  |  | 19/08/2026 | 20/08/2026 | 13/08/2026 | 26/08/2026 | 690 | 690
ADIDAS | 0903134690-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 150 | 2026-12-09 | 150 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134690 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 150 | 150 |  |  |  | 29/08/2026 | 31/08/2026 | 31/08/2026 | 2026-02-09 | 150 | 150
ADIDAS | 0903134709-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 2191 | 15/10/2026 | 2191 | AN | AN26/06/2026 | G1B | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. T2 Formosa, PI Date 26-Jul, actual receives 27-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134709 KW2909 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 2191 |  | 2191 |  |  | 22/09/2026 | 26/09/2026 |  |  | 2191 |  | 2191
ADIDAS | 0903134753-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 265 | 15/09/2026 | 265 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134753 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-07-09 | 265 | 265 |  |  |  | 29/08/2026 | 2026-02-09 | 22/08/2026 | 27/08/2026 | 265 | 265
ADIDAS | 0903134766-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 355 | 28/08/2026 | 355 | SA | SA26/06/2026 | G1C | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134766 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 355 | 355 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 31/08/2026 | 355 | 355
ADIDAS | 0903134783-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 225 | 15/09/2026 | 225 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134783 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-09 | 15/09/2026 | 2026-05-09 | 2026-07-09 | 225 | 148 | 77 |  |  | 31/08/2026 | 2026-11-09 | 2026-03-09 | 2026-04-09 | 225 | 216 | 9
ADIDAS | 0903134821-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134821 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 15/08/2026 | 29/08/2026 | 220 | 220
ADIDAS | 0903134827-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2H,G2L | T-SHIRT | G2 | ok | (15/08/2026(10)) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134827 KS1804 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 28/09/2026 | 2026-07-08 | 20/08/2026 | 1072 | 334 | 738 |  |  | 2026-04-08 | 24/09/2026 | 2026-01-08 | 2026-07-09 | 1072 | 1056 | 16
ADIDAS | 0903134852-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 355 | 26/08/2026 | 355 | AN | AN26/06/2026 | G1G,G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134852 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 26/08/2026 | 18/08/2026 | 24/08/2026 | 355 | 355 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-03-08 | 28/08/2026 | 355 | 355
ADIDAS | 0903134857-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 67 | 15/10/2026 | 67 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134857 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 67 | 67 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-08-09 | 67 | 67
ADIDAS | 0903134891-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 490 | 28/08/2026 | 490 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134891 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 490 | 490 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 29/08/2026 | 490 | 490
ADIDAS | 0903134905-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 56 | 15/10/2026 | 56 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134905 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 56 | 56 |  |  |  | 29/08/2026 | 2026-03-09 | 31/08/2026 | 13/09/2026 | 56 | 55 | 1
ADIDAS | 0903134982-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 105 | 30/09/2026 | 105 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134982 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 105 |  | 105 |  |  | 2026-02-10 | 2026-02-10 |  |  | 105 |  | 105
ADIDAS | 0903135001-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1500 | 26/08/2026 | 1500 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135001 LI2668 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 1500 | 1500 |  |  |  | 30/07/2026 | 2026-06-08 | 2026-03-08 | 27/08/2026 | 1500 | 1500
ADIDAS | 0903135003-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 634 | 2026-08-09 | 634 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135003 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 634 | 634 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 634 | 634
ADIDAS | 0903135049-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 744 | 2026-08-09 | 744 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135049 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 744 | 744 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 744 | 744
ADIDAS | 0903135083-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 26/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135083 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ARCH SEAL TEE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1072 |  | 1072 |  |  | 2026-02-10 | 2026-03-10 | 26/08/2026 | 2026-02-09 | 1072 | 1067 | 5
ADIDAS | 0903135108-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 642 | 2026-08-09 | 642 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135108 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 642 | 642 |  |  |  | 2026-10-08 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 642 | 642
ADIDAS | 0903135135-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 2000 | 29/08/2026 | 2000 | SA | SA26/06/2026 | G2R | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135135 LI2670 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 2000 | 2000 |  |  |  | 18/08/2026 | 24/08/2026 | 19/08/2026 | 2026-03-09 | 2000 | 2000
ADIDAS | 0903135147-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 270 | 15/09/2026 | 270 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135147 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 270 | 270 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-08 | 2026-12-08 | 270 | 270
ADIDAS | 0903135149-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 168 | 31/08/2026 | 168 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135149 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 168 | 168 |  |  |  | 20/08/2026 | 27/08/2026 | 21/08/2026 | 2026-02-09 | 168 | 168
ADIDAS | 0903135150-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 125 | 2026-07-10 | 125 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135150 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 125 |  | 125 |  |  | 28/09/2026 | 29/09/2026 | 28/08/2026 | 29/08/2026 | 125 | 125
ADIDAS | 0903135184-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135184 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/08/2026 | 2026-12-09 | 29/08/2026 | 2026-10-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-09-09 | 20/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135185-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 15/10/2026 | 259 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135185 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 30/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 30/10/2026 | 30/10/2026 |  |  | 259 |  | 259 |  |  | 27/10/2026 | 27/10/2026 | 2026-02-09 | 2026-12-09 | 259 | 228 | 31
ADIDAS | 0903135215-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 258 | 15/10/2026 | 258 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135215 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 258 |  | 258 |  |  | 2026-05-10 | 2026-06-10 | 15/08/2026 | 2026-01-09 | 258 | 252 | 6
ADIDAS | 0903135238-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 112 | 31/08/2026 | 112 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135238 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 112 | 112 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 26/08/2026 | 112 | 112
ADIDAS | 0903135251-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 233 | 15/10/2026 | 233 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135251 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 16/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 233 |  | 233 |  |  | 13/10/2026 | 14/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903135255-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 301 | 28/08/2026 | 301 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903135255 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-05-08 | 301 | 301
ADIDAS | 0903135286-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135286 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 230 |  | 230 |  |  | 30/09/2026 | 2026-01-10 |  |  | 230 |  | 230
ADIDAS | 0903135308-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 101 | 28/08/2026 | 101 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903135308 LI2669 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 101 | 101 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-04-08 | 2026-08-08 | 101 | 101
ADIDAS | 0903135352-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 310 | 2026-07-10 | 310 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135352 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 310 |  | 310 |  |  | 30/09/2026 | 2026-01-10 |  |  | 310 |  | 310
ADIDAS | 0903135416-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 241 | 31/08/2026 | 241 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135416 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 241 | 241 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 28/08/2026 | 241 | 241
ADIDAS | 0903135464-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 160 | 31/08/2026 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135464 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 19/08/2026 | 20/08/2026 | 160 | 160 |  |  |  | 2026-11-08 | 13/08/2026 | 14/08/2026 | 14/08/2026 | 160 | 160
ADIDAS | 0903135472-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 115 | 15/09/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135472 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 115 | 115 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-10-08 | 115 | 115
ADIDAS | 0903135480-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 148 | 15/10/2026 | 148 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135480 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 30/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 30/10/2026 | 30/10/2026 |  |  | 148 |  | 148 |  |  | 27/10/2026 | 27/10/2026 | 31/08/2026 | 2026-09-09 | 148 | 148
ADIDAS | 0903135497-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 496 | 31/08/2026 | 496 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135497 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 496 | 496 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 28/08/2026 | 496 | 496
ADIDAS | 0903135498-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 980 | 15/10/2026 | 980 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135498 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 14/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 980 |  | 980 |  |  | 2026-10-10 | 2026-12-10 |  |  | 980 |  | 980
ADIDAS | 0903135520-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 493 | 26/08/2026 | 493 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135520 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 493 | 493 |  |  |  | 14/08/2026 | 19/08/2026 | 15/08/2026 | 26/08/2026 | 493 | 493
ADIDAS | 0903135538-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 165 | 31/08/2026 | 165 | SI | SI26/06/2026 | G2K | ACCESSORIES | G2 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135538 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 165 | 165 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 165 | 165
ADIDAS | 0903135544-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 169 | 2026-07-10 | 169 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135544 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 169 |  | 169 |  |  | 2026-05-10 | 2026-07-10 | 31/08/2026 | 2026-07-09 | 169 | 169
ADIDAS | 0903135569-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 189 | 2026-07-10 | 189 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135569 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 189 |  | 189 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-07-09 | 189 | 188 | 1
ADIDAS | 0903135588-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135588 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 29/08/2026 | 420 | 420
ADIDAS | 0903135590-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 811 | 15/10/2026 | 811 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135590 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 811 |  | 811 |  |  | 2026-06-10 | 2026-07-10 | 28/08/2026 | 2026-09-09 | 811 | 779 | 32
ADIDAS | 0903135591-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 688 | 28/08/2026 | 688 | SA | SA26/06/2026 | G1B,G1C | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135591 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 24/08/2026 | 28/08/2026 | 28/08/2026 | 28/08/2026 | 688 | 688 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 31/08/2026 | 688 | 688
ADIDAS | 0903135621-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2439 | 28/08/2026 | 2439 | SA | SA26/06/2026 | G1B,G1E,G1G,G1I,G1J,G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135621 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 2439 | 2439 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 2026-01-09 | 2439 | 2439
ADIDAS | 0903135624-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 263 | 31/08/2026 | 263 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135624 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 263 | 263 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 24/08/2026 | 263 | 263
ADIDAS | 0903135646-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 84 | 15/10/2026 | 84 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135646 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 84 | 84 |  |  |  | 29/08/2026 | 31/08/2026 | 19/08/2026 | 26/08/2026 | 84 | 84
ADIDAS | 0903135659-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135659 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135683-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 67 | 15/10/2026 | 67 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135683 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 67 | 67 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 28/08/2026 | 67 | 67
ADIDAS | 0903135694-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 160 | 31/08/2026 | 160 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135694 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 160 | 160 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 2026-01-09 | 160 | 160
ADIDAS | 0903135743-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 282 | 15/09/2026 | 282 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135743 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 282 | 282 |  |  |  | 27/08/2026 | 31/08/2026 | 24/08/2026 | 2026-03-09 | 282 | 282
ADIDAS | 0903135819-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 122 | 2026-02-09 | 122 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135819 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 122 | 122 |  |  |  | 27/08/2026 | 29/08/2026 | 26/08/2026 | 2026-04-09 | 122 | 122
ADIDAS | 0903135839-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135839 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 19/08/2026 | 24/08/2026 | 18/08/2026 | 2026-07-09 | 660 | 660
ADIDAS | 0903135961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 292 | 15/09/2026 | 292 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 292 | 292 |  |  |  | 29/08/2026 | 2026-01-09 | 21/08/2026 | 31/08/2026 | 292 | 292
ADIDAS | 0903136044-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136044 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 660 | 660
ADIDAS | 0903136117-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 778 | 2026-08-09 | 778 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136117 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 778 | 778 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 28/08/2026 | 778 | 778
ADIDAS | 0903136141-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 119 | 2026-02-09 | 119 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136141 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 119 | 119 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-03-09 | 119 | 119
ADIDAS | 0903136170-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 225 | 31/08/2026 | 225 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 848024 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136170 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 225 | 225 |  |  |  | 20/08/2026 | 24/08/2026 | 2026-12-08 | 28/08/2026 | 225 | 225
ADIDAS | 0903136217-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1700 | 28/08/2026 | 1700 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136217 LI2645 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 19/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1700 | 1700 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 1700 | 1700
ADIDAS | 0903136285-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1500 | 28/08/2026 | 1500 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 630001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136285 LI2647 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1500 | 1500 |  |  |  | 20/08/2026 | 24/08/2026 | 26/08/2026 | 31/08/2026 | 1500 | 1500
ADIDAS | 0903136324-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2100 | 31/08/2026 | 2100 | SA | SA26/06/2026 | G1G,G1I,G1K | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136324 LI2671 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 2100 | 2100 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 2100 | 2100
ADIDAS | 0903136369-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 2000 | 26/08/2026 | 2000 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903136369 LI2667 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 20/08/2026 | 2000 | 2000 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-01-08 | 26/08/2026 | 2000 | 2000
ADIDAS | 0903136429-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1200 | 29/08/2026 | 1200 | SA | SA26/06/2026 | G1B,G1C,G2I,G2M,G2R | ACCESSORIES | G1,G2 | ok | ok | 29/08: ex-fty 630001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136429 LI2672 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 1200 | 1200 |  |  |  | 14/08/2026 | 26/08/2026 | 21/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903136661-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 800 | 2026-07-10 | 800 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136661 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 800 |  | 800 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-12-09 | 800 | 791 | 9
ADIDAS | 0903136678-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 536 | 31/08/2026 | 536 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136678 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 536 | 536 |  |  |  | 24/08/2026 | 27/08/2026 | 22/08/2026 | 2026-03-09 | 536 | 536
ADIDAS | 0903136726-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 308 | 2026-07-10 | 308 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136726 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 308 |  | 308 |  |  | 30/09/2026 | 2026-02-10 |  |  | 308 |  | 308
ADIDAS | 0903136772-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1540 | 31/08/2026 | 1540 | SA | SA26/06/2026 | G1J,G1K,G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136772 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 1540 | 1540 |  |  |  | 21/08/2026 | 27/08/2026 | 21/08/2026 | 2026-01-09 | 1540 | 1540
ADIDAS | 0903136816-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 278 | 31/08/2026 | 278 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136816 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 278 | 278 |  |  |  | 24/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 278 | 278
ADIDAS | 0903136925-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 104 | 2026-07-10 | 104 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136925 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 104 |  | 104 |  |  | 2026-07-10 | 2026-08-10 |  |  | 104 |  | 104
ADIDAS | 0903136927-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 666 | 31/08/2026 | 666 | SA | SA26/06/2026 | G1M,G1O | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136927 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 666 | 666 |  |  |  | 21/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 666 | 666
ADIDAS | 0903136961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 422 | 2026-07-10 | 422 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 422 |  | 422 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-07-09 | 422 | 419 | 3
ADIDAS | 0903136977-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 620 | 26/08/2026 | 620 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136977 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 19/08/2026 | 24/08/2026 | 620 | 620 |  |  |  | 2026-11-08 | 19/08/2026 | 15/08/2026 | 26/08/2026 | 620 | 620
ADIDAS | 0903136996-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 277 | 15/09/2026 | 277 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136996 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 277 | 277 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 26/08/2026 | 277 | 277
ADIDAS | 0903137012-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 478 | 26/08/2026 | 478 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137012 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 478 | 478 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 28/08/2026 | 478 | 478
ADIDAS | 0903137023-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 201 | 31/08/2026 | 201 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137023 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 201 | 201 |  |  |  | 2026-11-08 | 24/08/2026 | 15/08/2026 | 28/08/2026 | 201 | 201
ADIDAS | 0903137027-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137027 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903137031-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 772 | 28/08/2026 | 772 | SI | SI26/06/2026 | G2L,G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137031 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 772 | 772 |  |  |  | 19/08/2026 | 24/08/2026 | 14/08/2026 | 31/08/2026 | 772 | 772
ADIDAS | 0903137049-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 117 | 15/09/2026 | 117 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137049 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 117 | 117 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-12-09 | 117 | 117
ADIDAS | 0903137055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 235 | 26/08/2026 | 235 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 235 | 235 |  |  |  | 18/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 235 | 235
ADIDAS | 0903137069-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1245 | 31/08/2026 | 1245 | SA | SA26/06/2026 | G1G,G1J,G1K,G1Q,G2I,G2M,G2R | ACCESSORIES | G1,G2 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137069 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 31/08/2026 | 29/08/2026 | 29/08/2026 | 1245 | 1245 |  |  |  | 19/08/2026 | 27/08/2026 | 28/08/2026 | 2026-01-09 | 1245 | 1245
ADIDAS | 0903137098-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1416 | 28/08/2026 | 1416 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137098 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1416 | 1416 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 1416 | 1416
ADIDAS | 0903137102-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 638 | 28/08/2026 | 638 | SA | SA26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137102 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 638 | 638 |  |  |  | 18/08/2026 | 24/08/2026 | 14/08/2026 | 31/08/2026 | 638 | 638
ADIDAS | 0903137111-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 194 | 15/09/2026 | 194 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137111 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 194 | 105 | 89 |  |  | 2026-09-09 | 2026-11-09 | 2026-03-09 | 2026-10-09 | 194 | 163 | 31
ADIDAS | 0903137134-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 358 | 15/09/2026 | 358 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137134 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 16/09/2026 | 2026-03-09 | 2026-07-09 | 358 | 349 | 9 |  |  | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-07-09 | 358 | 358
ADIDAS | 0903137137-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1735 | 31/08/2026 | 1735 | SA | SA26/06/2026 | G1I,G1J,G1K,G1M,G1O,G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137137 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 27/08/2026 | 31/08/2026 | 29/08/2026 | 29/08/2026 | 1735 | 1735 |  |  |  | 21/08/2026 | 27/08/2026 | 28/08/2026 | 2026-03-09 | 1735 | 1741 | -6 | 6
ADIDAS | 0903137299-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1152 | 26/08/2026 | 1152 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137299 LI2668 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-07-08 | 20/08/2026 | 1152 | 1152 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-03-08 | 24/08/2026 | 1152 | 1152
ADIDAS | 0903137310-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 382 | 30/09/2026 | 382 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137310 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 382 |  | 382 |  |  | 15/09/2026 | 16/09/2026 |  |  | 382 |  | 382
ADIDAS | 0903137336-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 784 | 28/08/2026 | 784 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137336 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 784 | 784 |  |  |  | 13/08/2026 | 20/08/2026 | 18/08/2026 | 2026-03-09 | 784 | 784
ADIDAS | 0903137376-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1488 | 28/08/2026 | 1488 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137376 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1488 | 1488 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 29/08/2026 | 1488 | 1488
ADIDAS | 0903137413-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1458 | 28/08/2026 | 1458 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137413 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 2026-12-08 | 20/08/2026 | 1458 | 1458 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-10-08 | 21/08/2026 | 1458 | 1458
ADIDAS | 0903137434-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 4525 | 15/10/2026 | 4525 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137434 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/10/2026 | 2026-04-11 |  |  | 4525 |  | 4525 |  |  | 17/10/2026 | 31/10/2026 |  |  | 4525 |  | 4525
ADIDAS | 0903137493-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 1143 | 26/08/2026 | 1143 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 1st Art (TC 10 pcs) 652001 | PRINT L3 SUB PROCESS_V3 | 0903137493 LI2669 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-10-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 1143 | 1143 |  |  |  | 2026-05-08 | 14/08/2026 | 2026-01-08 | 2026-12-08 | 1143 | 1143
ADIDAS | 0903137501-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 320 | 30/09/2026 | 320 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137501 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 320 |  | 320 |  |  | 25/09/2026 | 29/09/2026 | 28/08/2026 | 2026-01-09 | 320 | 51 | 269
ADIDAS | 0903137531-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 656 | 28/08/2026 | 656 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137531 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 21/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 656 | 656 |  |  |  | 18/08/2026 | 20/08/2026 | 20/08/2026 | 28/08/2026 | 656 | 656
ADIDAS | 0903137540-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 401 | 15/10/2026 | 401 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137540 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 401 |  | 401 |  |  | 2026-02-10 | 2026-03-10 |  |  | 401 |  | 401
ADIDAS | 0903137570-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 592 | 26/08/2026 | 592 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty (Mexico). 652001 | PRINT L3 SUB PROCESS_V3 | 0903137570 LI2667 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 592 | 592 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-04-08 | 2026-12-08 | 592 | 592
ADIDAS | 0903137595-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 290 | 28/08/2026 | 290 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137595 LI2645 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 290 | 290 |  |  |  | 19/08/2026 | 20/08/2026 | 13/08/2026 | 26/08/2026 | 290 | 290
ADIDAS | 0903137631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 370 | 28/08/2026 | 370 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3 SUB PROCESS_V3 | 0903137631 LI2667 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 18/08/2026 | 18/08/2026 | 370 | 370 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-01-08 | 2026-07-08 | 370 | 370
ADIDAS | 0903137651-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 153 | 28/08/2026 | 153 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137651 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 153 | 153 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 15/08/2026 | 153 | 153
ADIDAS | 0903137665-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 2268 | 28/08/2026 | 2268 | SA | SA26/06/2026 | G1O,G1Q | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137665 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 2268 | 2268 |  |  |  | 20/08/2026 | 24/08/2026 | 18/08/2026 | 29/08/2026 | 2268 | 2268
ADIDAS | 0903137727-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 132 | 2026-07-10 | 132 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137727 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 132 |  | 132 |  |  | 28/09/2026 | 29/09/2026 | 27/08/2026 | 2026-07-09 | 132 | 132
ADIDAS | 0903137746-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1612 | 28/08/2026 | 1612 | SA | SA26/06/2026 | G2I | ACCESSORIES | G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137746 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 1612 | 1612 |  |  |  | 19/08/2026 | 24/08/2026 | 20/08/2026 | 29/08/2026 | 1612 | 1612
ADIDAS | 0903137792-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 168 | 31/08/2026 | 168 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137792 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 168 | 168 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 168 | 168
ADIDAS | 0903137840-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 851 | 31/08/2026 | 851 | SA | SA26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137840 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 851 | 851 |  |  |  | 24/08/2026 | 27/08/2026 | 26/08/2026 | 31/08/2026 | 851 | 851
ADIDAS | 0903137916-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 268 | 31/08/2026 | 268 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137916 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 268 | 268 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 31/08/2026 | 268 | 268
ADIDAS | 0903137964-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 326 | 31/08/2026 | 326 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137964 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 21/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 326 | 326 |  |  |  | 18/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 326 | 326
ADIDAS | 0903137967-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1104 | 28/08/2026 | 1104 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137967 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 1104 | 1104 |  |  |  | 14/08/2026 | 24/08/2026 | 15/08/2026 | 28/08/2026 | 1104 | 1104
ADIDAS | 0903138012-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 1750 | 31/08/2026 | 1750 | SA | SA26/06/2026 | G1B,G1C,G1E,G1O,G1Q | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138012 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 1750 | 1750 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 2026-08-09 | 1750 | 1728 | 22
ADIDAS | 0903138028-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138028 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 420 | 420 |  |  |  | 29/08/2026 | 2026-09-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903138055-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1430 | 28/08/2026 | 1430 | SA | SA26/06/2026 | G1B,G1E,G1G,G1I,G1Q,G2R | ACCESSORIES | G1,G2 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138055 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 29/08/2026 | 28/08/2026 | 28/08/2026 | 1430 | 1430 |  |  |  | 20/08/2026 | 26/08/2026 | 15/08/2026 | 31/08/2026 | 1430 | 1430
ADIDAS | 0903138063-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 137 | 2026-07-10 | 137 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138063 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 137 |  | 137 |  |  | 30/09/2026 | 2026-01-10 |  |  | 137 |  | 137
ADIDAS | 0903138090-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1318 | 28/08/2026 | 1318 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903138090 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 1318 | 1318 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-01-08 | 2026-11-08 | 1318 | 1318
ADIDAS | 0903138123-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1750 | 26/08/2026 | 1750 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138123 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-11-08 | 18/08/2026 | 2026-11-08 | 18/08/2026 | 1750 | 1750 |  |  |  | 2026-06-08 | 2026-12-08 | 2026-04-08 | 24/08/2026 | 1750 | 1750
ADIDAS | 0903138138-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 156 | 31/08/2026 | 156 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138138 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 156 | 156 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 156 | 156
ADIDAS | 0903138177-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 760 | 31/08/2026 | 760 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138177 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 29/08/2026 | 760 | 760 |  |  |  | 20/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 760 | 760
ADIDAS | 0903138297-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 266 | 2026-02-09 | 266 | SA | SA26/06/2026 | G1B,G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138297 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 266 | 266 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 266 | 266
ADIDAS | 0903138373-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 542 | 26/08/2026 | 542 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138373 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 542 | 542 |  |  |  | 13/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 542 | 542
ADIDAS | 0903138385-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 174 | 31/08/2026 | 174 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138385 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 174 | 174 |  |  |  | 24/08/2026 | 27/08/2026 | 28/08/2026 | 2026-01-09 | 174 | 174
ADIDAS | 0903138432-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 158 | 2026-02-09 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138432 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 158 | 158 |  |  |  | 27/08/2026 | 28/08/2026 | 22/08/2026 | 29/08/2026 | 158 | 158
ADIDAS | 0903138434-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 650 | 28/08/2026 | 650 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138434 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 28/08/2026 | 18/08/2026 | 27/08/2026 | 650 | 650 |  |  |  | 2026-10-08 | 24/08/2026 | 13/08/2026 | 2026-02-09 | 650 | 650
ADIDAS | 0903138439-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1991 | 29/08/2026 | 1991 | SI | SI26/06/2026 | G2K,G2L,G2N | ACCESSORIES | G2 | ok | ok | 29/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138439 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 29/08/2026 | 27/08/2026 | 29/08/2026 | 1991 | 1991 |  |  |  | 19/08/2026 | 26/08/2026 | 15/08/2026 | 31/08/2026 | 1991 | 1991
ADIDAS | 0903138477-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 545 | 26/08/2026 | 545 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138477 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 545 | 545 |  |  |  | 14/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 545 | 545
ADIDAS | 0903138483-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 296 | 28/08/2026 | 296 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty (Mexico). 652001 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138483 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 296 | 296 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 296 | 296
ADIDAS | 0903138496-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 129 | 26/08/2026 | 129 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138496 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 129 | 129 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 26/08/2026 | 129 | 129
ADIDAS | 0903138514-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1366 | 28/08/2026 | 1366 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138514 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1366 | 1366 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1366 | 1366
ADIDAS | 0903138552-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 526 | 28/08/2026 | 526 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138552 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 526 | 526 |  |  |  | 13/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 526 | 526
ADIDAS | 0903138575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 276 | 15/10/2026 | 276 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 21/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 276 |  | 276 |  |  | 17/10/2026 | 19/10/2026 |  |  | 276 |  | 276
ADIDAS | 0903138583-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 562 | 26/08/2026 | 562 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138583 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 562 | 562 |  |  |  | 19/08/2026 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 562 | 562
ADIDAS | 0903138590-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 189 | 26/08/2026 | 189 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138590 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 189 | 189 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 24/08/2026 | 189 | 189
ADIDAS | 0903138615-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 158 | 2026-07-10 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138615 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 158 |  | 158 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-07-09 | 158 | 155 | 3
ADIDAS | 0903138621-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 851 | 26/08/2026 | 851 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138621 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 851 | 851 |  |  |  | 18/08/2026 | 20/08/2026 | 20/08/2026 | 29/08/2026 | 851 | 851
ADIDAS | 0903139152-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 124 | 31/08/2026 | 124 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139152 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 124 | 124 |  |  |  | 13/08/2026 | 24/08/2026 | 18/08/2026 | 19/08/2026 | 124 | 124
ADIDAS | 0903139189-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 188 | 31/08/2026 | 188 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139189 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 188 | 188 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 29/08/2026 | 188 | 188
ADIDAS | 0903139269-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 563 | 2026-07-10 | 563 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139269 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 563 |  | 563 |  |  | 28/09/2026 | 29/09/2026 | 15/08/2026 | 2026-07-09 | 563 | 550 | 13
ADIDAS | 0903139272-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 181 | 31/08/2026 | 181 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139272 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 181 | 181 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 2026-01-09 | 181 | 181
ADIDAS | 0903139328-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 707 | 23/09/2026 | 707 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139328 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 707 |  | 707 |  |  | 21/09/2026 | 22/09/2026 | 27/08/2026 | 31/08/2026 | 707 | 706 | 1
ADIDAS | 0903139350-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1855 | 26/08/2026 | 1855 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139350 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 18/08/2026 | 1855 | 1855 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-11-08 | 1855 | 1855
ADIDAS | 0903139367-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 851 | 26/08/2026 | 851 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903139367 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 851 | 851 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-05-08 | 2026-12-08 | 851 | 851
ADIDAS | 0903139370-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 437 | 31/08/2026 | 437 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139370 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 29/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 29/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 437 | 437 |  |  |  | 26/08/2026 | 27/08/2026 | 22/08/2026 | 29/08/2026 | 437 | 437
ADIDAS | 0903139403-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 112 | 2026-02-09 | 112 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139403 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 112 | 112 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-03-09 | 112 | 112
ADIDAS | 0903139409-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 493 | 26/08/2026 | 493 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139409 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 493 | 493 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-05-08 | 493 | 493
ADIDAS | 0903139439-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 584 | 23/09/2026 | 584 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139439 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 584 |  | 584 |  |  | 2026-12-09 | 14/09/2026 | 31/08/2026 | 2026-04-09 | 584 | 580 | 4
ADIDAS | 0903139469-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 105 | 2026-07-10 | 105 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139469 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 105 |  | 105 |  |  | 2026-12-10 | 14/10/2026 | 31/08/2026 | 2026-07-09 | 105 | 105
ADIDAS | 0903139495-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 28/08/2026 | 156 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139495 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 19/08/2026 | 21/08/2026 | 156 | 156 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-04-08 | 26/08/2026 | 156 | 156
ADIDAS | 0903139498-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 478 | 26/08/2026 | 478 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139498 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 18/08/2026 | 13/08/2026 | 18/08/2026 | 478 | 478 |  |  |  | 2026-07-08 | 2026-12-08 | 2026-03-08 | 28/08/2026 | 478 | 478
ADIDAS | 0903139533-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1104 | 26/08/2026 | 1104 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139533 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-12-08 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 1104 | 1104 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 2026-07-08 | 1104 | 1104
ADIDAS | 0903139570-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 523 | 26/08/2026 | 523 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903139570 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 14/08/2026 | 20/08/2026 | 14/08/2026 | 18/08/2026 | 523 | 523 |  |  |  | 2026-11-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 523 | 523
ADIDAS | 0903139649-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1921 | 29/08/2026 | 1921 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139649 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 29/08/2026 | 1921 | 1921 |  |  |  | 20/08/2026 | 24/08/2026 | 26/08/2026 | 2026-03-09 | 1921 | 1921
ADIDAS | 0903139660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139660 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-04-09 | 2026-01-09 | 2026-04-09 | 234 | 234 |  |  |  | 27/08/2026 | 2026-01-09 | 29/08/2026 | 2026-02-09 | 234 | 234
ADIDAS | 0903139688-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 485 | 26/08/2026 | 485 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139688 LI2645 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 485 | 485 |  |  |  | 18/08/2026 | 19/08/2026 | 14/08/2026 | 28/08/2026 | 485 | 485
ADIDAS | 0903139741-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1214 | 28/08/2026 | 1214 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 28/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139741 LI2647 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1214 | 1214 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1214 | 1214
ADIDAS | 0903139767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 136 | 2026-02-09 | 136 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 136 | 136 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 136 | 136
ADIDAS | 0903139780-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 336 | 26/08/2026 | 336 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3 SUB PROCESS_V3 | 0903139780 LI2669 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 20/08/2026 | 336 | 336 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 19/08/2026 | 336 | 336
ADIDAS | 0903139907-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 432 | 26/08/2026 | 432 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139907 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 20/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 20/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 432 | 432 |  |  |  | 14/08/2026 | 20/08/2026 | 13/08/2026 | 27/08/2026 | 432 | 432
ADIDAS | 0903139930-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 307 | 26/08/2026 | 307 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139930 LI2668 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 307 | 307 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-05-08 | 2026-05-08 | 307 | 307
ADIDAS | 0903139936-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 236 | 28/08/2026 | 236 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903139936 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 236 | 236 |  |  |  | 14/08/2026 | 19/08/2026 | 2026-03-08 | 26/08/2026 | 236 | 236
ADIDAS | 0903139968-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 404 | 26/08/2026 | 404 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139968 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 24/08/2026 | 404 | 404 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-10-08 | 19/08/2026 | 404 | 404
ADIDAS | 0903140000-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 405 | 26/08/2026 | 405 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 684009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140000 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 405 | 405 |  |  |  | 14/08/2026 | 20/08/2026 | 14/08/2026 | 29/08/2026 | 405 | 405
ADIDAS | 0903140004-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 432 | 26/08/2026 | 432 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 834012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140004 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 432 | 432 |  |  |  | 19/08/2026 | 20/08/2026 | 20/08/2026 | 2026-03-09 | 432 | 432
ADIDAS | 0903140046-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 156 | 28/08/2026 | 156 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903140046 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 19/08/2026 | 156 | 156 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-03-08 | 2026-10-08 | 156 | 156
ADIDAS | 0903140069-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 28/08/2026 | 316 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 684009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140069 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 316 | 316 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 28/08/2026 | 316 | 316
ADIDAS | 0903140106-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 340 | 28/08/2026 | 340 | SA | SA26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140106 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 27/08/2026 | 26/08/2026 | 27/08/2026 | 340 | 340 |  |  |  | 20/08/2026 | 21/08/2026 | 20/08/2026 | 2026-01-09 | 340 | 340
ADIDAS | 0903140109-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 320 | 26/08/2026 | 320 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140109 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 19/08/2026 | 19/08/2026 | 20/08/2026 | 320 | 320 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-07-08 | 21/08/2026 | 320 | 320
ADIDAS | 0903140137-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 28/08/2026 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140137 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 24/08/2026 | 100 | 100 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 100 | 100
ADIDAS | 0903140150-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1245 | 26/08/2026 | 1245 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140150 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-05-08 | 21/08/2026 | 1245 | 1245 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-01-08 | 24/08/2026 | 1245 | 1245
ADIDAS | 0903140177-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 267 | 31/08/2026 | 267 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443e | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140177 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 267 | 267 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 31/08/2026 | 267 | 267
ADIDAS | 0903140270-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 506 | 26/08/2026 | 506 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903140270 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-08 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 14/08/2026 | 19/08/2026 | 506 | 506 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 506 | 506
ADIDAS | 0903140301-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1170 | 28/08/2026 | 1170 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 600000 | PRINT L3 SUB PROCESS_V3 | 0903140301 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 1170 | 1170 |  |  |  | 14/08/2026 | 24/08/2026 | 2026-04-08 | 28/08/2026 | 1170 | 1170
ADIDAS | 0903140693-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 409 | 28/08/2026 | 409 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 684009 | PRINT L3 SUB PROCESS_V3 | 0903140693 LI2667 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 409 | 409 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-03-08 | 27/08/2026 | 409 | 409
ADIDAS | 0903140729-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 26/08/2026 | 420 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140729 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 420 | 420 |  |  |  | 19/08/2026 | 20/08/2026 | 14/08/2026 | 26/08/2026 | 420 | 420
ADIDAS | 0903140767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 28/08/2026 | 259 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 27/08/2026 | 26/08/2026 | 26/08/2026 | 259 | 259 |  |  |  | 19/08/2026 | 21/08/2026 | 18/08/2026 | 28/08/2026 | 259 | 259
ADIDAS | 0903140818-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 300 | 28/08/2026 | 300 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140818 LI2670 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 20/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/08/2026 | 28/08/2026 | 21/08/2026 | 27/08/2026 | 300 | 300 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 27/08/2026 | 300 | 300
ADIDAS | 0903140868-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 371 | 26/08/2026 | 371 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 684009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140868 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PERU | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 371 | 371 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 371 | 371
ADIDAS | 0903141670-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 292 | 28/08/2026 | 292 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 834012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141670 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ISRAEL | SEA | 21/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 292 | 292 |  |  |  | 18/08/2026 | 20/08/2026 | 14/08/2026 | 26/08/2026 | 292 | 292
ADIDAS | 0903141841-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 455 | 28/08/2026 | 455 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141841 LI2645 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 24/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 455 | 455 |  |  |  | 19/08/2026 | 24/08/2026 | 13/08/2026 | 27/08/2026 | 455 | 455
ADIDAS | 0903141927-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 421 | 26/08/2026 | 421 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141927 LI2647 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 421 | 421 |  |  |  | 18/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 421 | 421
ADIDAS | 0903141933-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141933 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 200 | 200
ADIDAS | 0903141960-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 472 | 26/08/2026 | 472 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903141960 LI2667 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 21/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 21/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 472 | 472 |  |  |  | 18/08/2026 | 20/08/2026 | 2026-01-08 | 2026-11-08 | 472 | 472
ADIDAS | 0903141964-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141964 LI2668 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 21/08/2026 | 21/08/2026 | 21/08/2026 | 150 | 150 |  |  |  | 14/08/2026 | 18/08/2026 | 2026-05-08 | 2026-07-08 | 150 | 150
ADIDAS | 0903142009-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 363 | 26/08/2026 | 363 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142009 LI2670 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 20/08/2026 | 14/08/2026 | 20/08/2026 | 363 | 363 |  |  |  | 2026-10-08 | 14/08/2026 | 2026-12-08 | 27/08/2026 | 363 | 363
ADIDAS | 0903142071-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 280 | 26/08/2026 | 280 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 26/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142071 LI2672 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 26/08/2026 | 26/08/2026 | 26/08/2026 | 280 | 280 |  |  |  | 19/08/2026 | 20/08/2026 | 18/08/2026 | 2026-03-09 | 280 | 280
ADIDAS | 0903142076-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 150 | 28/08/2026 | 150 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). 960006 | PRINT L3 SUB PROCESS_V3 | 0903142076 LI2669 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 150 | 150 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-04-08 | 2026-10-08 | 150 | 150
ADIDAS | 0903142132-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 250 | 2026-12-09 | 250 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142132 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 250 | 250 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 250 | 250
ADIDAS | 0903142187-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 344 | 28/08/2026 | 344 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142187 LI2671 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 344 | 344 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 344 | 344
ADIDAS | 0903142240-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 305 | 28/08/2026 | 305 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142240 LI2647 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 305 | 305 |  |  |  | 19/08/2026 | 20/08/2026 | 19/08/2026 | 28/08/2026 | 305 | 305
ADIDAS | 0903142291-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 349 | 26/08/2026 | 349 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142291 LI2668 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 20/08/2026 | 349 | 349 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-07-08 | 349 | 349
ADIDAS | 0903142317-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 360 | 26/08/2026 | 360 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 24/08: ex-fty 672027 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142317 LI2646 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 24/08/2026 | 360 | 360 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-06-08 | 19/08/2026 | 360 | 360
ADIDAS | 0903142327-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 100 | 28/08/2026 | 100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142327 LI2668 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 20/08/2026 | 19/08/2026 | 20/08/2026 | 100 | 100 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-07-08 | 100 | 100
ADIDAS | 0903142410-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 380 | 26/08/2026 | 380 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 24/08: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903142410 LI2669 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 18/08/2026 | 2026-12-08 | 14/08/2026 | 380 | 380 |  |  |  | 2026-07-08 | 2026-12-08 | 2026-01-08 | 2026-05-08 | 380 | 379 | 1
ADIDAS | 0903142438-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142438 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 28/08/2026 | 24/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142461-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142461 LI2647 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 24/08/2026 | 19/08/2026 | 28/08/2026 | 200 | 200
ADIDAS | 0903142489-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 200 | 28/08/2026 | 200 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960006 | PRINT L3 SUB PROCESS_V3 | 0903142489 LI2667 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 27/08/2026 | 24/08/2026 | 24/08/2026 | 200 | 200 |  |  |  | 19/08/2026 | 21/08/2026 | 2026-03-08 | 2026-11-08 | 200 | 200
ADIDAS | 0903142499-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 895 | 28/08/2026 | 895 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3 SUB PROCESS_V3 | 0903142499 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 895 | 895 |  |  |  | 2026-12-08 | 19/08/2026 | 2026-04-08 | 2026-10-08 | 895 | 895
ADIDAS | 0903142507-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 100 | 26/09/2026 | 100 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142507 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 100 | 100 |  |  | 34 | 2026-05-09 | 2026-10-09 | 13/08/2026 | 13/08/2026 | 100 | 100
ADIDAS | 0903142516-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142516 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 21/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142526-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142526 LI2645 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 15/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 15/09/2026 | 23/09/2026 |  |  | 8900 |  | 8900 |  |  | 2026-11-09 | 19/09/2026 |  |  | 8900 |  | 8900
ADIDAS | 0903142529-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 926 | 28/08/2026 | 926 | SI | SI26/06/2026 | G2K | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142529 LI2645 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 926 | 926 |  |  |  | 20/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 926 | 926
ADIDAS | 0903142537-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 24/09: ex-fty. Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142537 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 150 |  | 150 |  |  | 25/09/2026 | 29/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903142557-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 507 | 28/08/2026 | 507 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3 SUB PROCESS_V3 | 0903142557 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 13/08/2026 | 20/08/2026 | 507 | 507 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 28/08/2026 | 507 | 507
ADIDAS | 0903142558-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142558 LI2646 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 21/08/2026 | 28/08/2026 | 20/08/2026 | 28/08/2026 | 200 | 200 |  |  |  | 18/08/2026 | 24/08/2026 | 18/08/2026 | 20/08/2026 | 200 | 200
ADIDAS | 0903142574-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142574 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903142580-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 2026-12-09 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142580 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 160 | 160 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 2026-04-09 | 160 | 160
ADIDAS | 0903142585-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 855 | 28/08/2026 | 855 | SA | SA26/06/2026 | G1I,G1O,G1Q | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142585 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 855 | 855 |  |  |  | 20/08/2026 | 24/08/2026 | 15/08/2026 | 29/08/2026 | 855 | 855
ADIDAS | 0903142605-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 2026-07-10 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142605 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-02-10 | 2026-02-09 | 2026-02-09 | 100 | 2 | 98
ADIDAS | 0903142609-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 566 | 28/08/2026 | 566 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142609 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 21/08/2026 | 26/08/2026 | 566 | 566 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-10-08 | 19/08/2026 | 566 | 566
ADIDAS | 0903142628-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 170 | 28/08/2026 | 170 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142628 LI2668 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 20/08/2026 | 27/08/2026 | 21/08/2026 | 27/08/2026 | 170 | 170 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-04-08 | 2026-05-08 | 170 | 170
ADIDAS | 0903142631-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 2950 | 30/09/2026 | 2950 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 24/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142631 LI2647 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 26/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 26/09/2026 | 30/09/2026 |  |  | 2950 |  | 2950 |  |  | 23/09/2026 | 26/09/2026 |  |  | 2950 |  | 2950
ADIDAS | 0903142639-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 560 | 28/08/2026 | 560 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142639 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 18/08/2026 | 21/08/2026 | 18/08/2026 | 21/08/2026 | 560 | 560 |  |  |  | 2026-12-08 | 18/08/2026 | 2026-03-08 | 2026-05-08 | 560 | 560
ADIDAS | 0903142841-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903142841 JD1877 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 25/09/2026 |  |  | 1759 |  | 1759 |  |  | 18/09/2026 | 22/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903142873-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 30/09/2026 | 1079 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142873 JD5302 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | W 3S FT CF PT |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 1079 |  | 1079 |  |  | 16/09/2026 | 17/09/2026 | 27/08/2026 | 15/09/2026 | 1079 | 529 | 550 |  | 320
ADIDAS | 0903142903-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142903 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S FT FZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 400 |  | 400 |  |  | 14/09/2026 | 15/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903142926-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 399 | 30/09/2026 | 399 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142926 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 399 | 111 | 288 |  |  | 27/08/2026 | 15/09/2026 | 22/08/2026 | 2026-09-09 | 399 | 399
ADIDAS | 0903142998-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 718 | 30/09/2026 | 718 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516204 | EMBRO SUB PROCESS_V1 | 0903142998 JE6419 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-05-09 | 2026-08-09 | 718 | 718 |  |  |  | 31/08/2026 | 2026-04-09 | 15/08/2026 | 2026-07-09 | 718 | 718
ADIDAS | 0903143026-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 899 | 2026-02-09 | 899 | SA | SA26/06/2026 | G2D,G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903143026 GK8824 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 29/08/2026 | 2026-01-09 | 899 | 899 |  |  |  | 24/08/2026 | 28/08/2026 | 21/08/2026 | 31/08/2026 | 899 | 899
ADIDAS | 0903143086-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 719 | 30/09/2026 | 719 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143086 JE1309 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | W 3S WV SHO |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 719 |  | 719 |  |  | 14/09/2026 | 16/09/2026 |  |  | 719 |  | 719
ADIDAS | 0903143118-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903143118 JE6419 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 1318 | 1318 |  |  |  | 31/08/2026 | 2026-04-09 | 29/08/2026 | 31/08/2026 | 1318 | 1318
ADIDAS | 0903143145-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Libolon, PI Date 26-Jul, actual receives 17-Jul. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903143145 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S WV SHO |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 300 |  | 300 |  |  | 14/09/2026 | 16/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903143171-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 300 | 28/08/2026 | 300 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3 SUB PROCESS_V3 | 0903143171 LI2669 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-08 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-12-08 | 20/08/2026 | 2026-12-08 | 20/08/2026 | 300 | 300 |  |  |  | 2026-07-08 | 14/08/2026 | 2026-01-08 | 2026-04-08 | 300 | 300
ADIDAS | 0903143196-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 28/08/2026 | 300 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143196 LI2647 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 300 | 300 |  |  |  | 13/08/2026 | 19/08/2026 | 19/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0903143227-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 320 | 28/08/2026 | 320 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143227 LI2671 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 27/08/2026 | 320 | 320 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 28/08/2026 | 320 | 320
ADIDAS | 0903143256-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 28/08/2026 | 300 | SI | SI26/06/2026 | G2J | ACCESSORIES | G2 | ok | ok | 27/08: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143256 LI2645 | 2026-10-08 | KAHATEX CIJERAH | CHILE | SEA | 21/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/08/2026 | 24/08/2026 | 21/08/2026 | 24/08/2026 | 300 | 300 |  |  |  | 18/08/2026 | 19/08/2026 | 13/08/2026 | 20/08/2026 | 300 | 300
ADIDAS | 0903143278-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 370 | 28/08/2026 | 370 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143278 LI2646 | 2026-10-08 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 24/08/2026 | 370 | 370 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 21/08/2026 | 370 | 370
ADIDAS | 0903143303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 600 | 23/09/2026 | 600 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 600 | 600 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 600 | 600
ADIDAS | 0903143351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143351 LI2669 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 800 | 800 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 800 | 800
ADIDAS | 0903143380-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 23/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143380 LI2646 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-03-09 | 22/09/2026 | 2026-04-09 | 15/09/2026 | 8900 | 2040 | 6860 |  |  | 31/08/2026 | 18/09/2026 | 15/08/2026 | 2026-08-09 | 8900 | 8886 | 14
ADIDAS | 0903143435-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1100 | 30/09/2026 | 1100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143435 LI2668 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-09 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-05-09 | 18/09/2026 | 2026-05-09 | 2026-08-09 | 1100 | 1085 | 15 |  |  | 2026-02-09 | 15/09/2026 | 19/08/2026 | 2026-03-09 | 1100 | 1091 | 9
ADIDAS | 0903143462-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3900 | 30/09/2026 | 3900 | SA | SA26/06/2026 | G1E,G1I,G1O | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143462 LI2670 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-09 | 22/09/2026 | 2026-03-09 | 2026-07-09 | 3900 | 2209 | 1691 |  |  | 29/08/2026 | 18/09/2026 | 24/08/2026 | 2026-10-09 | 3900 | 2354 | 1546
ADIDAS | 0903143489-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 5100 | 30/09/2026 | 5100 | SA | SA26/06/2026 | G1E,G1I | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143489 LI2671 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-09 | 2026-02-10 | 2026-07-09 | 15/09/2026 | 5100 | 371 | 4729 |  |  | 2026-03-09 | 29/09/2026 | 24/08/2026 | 14/09/2026 | 5100 | 5101 | -1 | 1 | 1
ADIDAS | 0903144181-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-02-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144181 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 28/08/2026 | 20/08/2026 | 2026-01-09 | 220 | 220
ADIDAS | 0903144227-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 375 | 31/08/2026 | 375 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144227 LI2646 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 20/08/2026 | 29/08/2026 | 375 | 375 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 19/08/2026 | 375 | 375
ADIDAS | 0903144303-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144303 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 200 | 195 | 5
ADIDAS | 0903144665-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 244 | 31/08/2026 | 244 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 672027 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144665 LI2671 | 2026-10-08 | KAHATEX CIJERAH | BRAZIL | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 244 | 244 |  |  |  | 20/08/2026 | 27/08/2026 | 20/08/2026 | 29/08/2026 | 244 | 244
ADIDAS | 0903144673-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 31/08/2026 | 200 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144673 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 29/08/2026 | 200 | 200 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 26/08/2026 | 200 | 200
ADIDAS | 0903144697-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 456 | 28/08/2026 | 456 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 27/08: ex-fty 678002 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144697 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 27/08/2026 | 456 | 456 |  |  |  | 20/08/2026 | 24/08/2026 | 18/08/2026 | 27/08/2026 | 456 | 456
ADIDAS | 0903144719-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 230 | 28/08/2026 | 230 | AN | AN26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3 SUB PROCESS_V3 | 0903144719 LI2667 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 230 | 230 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-03-08 | 2026-05-08 | 230 | 230
ADIDAS | 0903144744-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 180 | 28/08/2026 | 180 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 28/08: ex-fty 960026 | PRINT L3 SUB PROCESS_V3 | 0903144744 LI2669 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 18/08/2026 | 20/08/2026 | 18/08/2026 | 19/08/2026 | 180 | 180 |  |  |  | 2026-12-08 | 14/08/2026 | 2026-03-08 | 2026-03-08 | 180 | 180
ADIDAS | 0903144771-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 250 | 31/08/2026 | 250 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 29/08: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903144771 LI2647 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 28/08/2026 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 250 | 250 |  |  |  | 24/08/2026 | 24/08/2026 | 29/08/2026 | 29/08/2026 | 250 | 250
ADIDAS | 0903144813-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 260 | 2026-02-09 | 260 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144813 LI2672 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 260 | 260 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-05-09 | 260 | 260
ADIDAS | 0903145175-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO SUB PROCESS_V1 | 0903145175 JE6414 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1319 |  | 1319 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1319 |  | 1319
ADIDAS | 0903145234-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 1050 | 2026-12-09 | 1050 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 12/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145234 IM0081 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | U FI LOGO PT |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050
ADIDAS | 0903145265-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 480 | 30/09/2026 | 480 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145265 JE6341 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 480 |  | 480 |  |  | 21/09/2026 | 22/09/2026 |  |  | 480 |  | 480
ADIDAS | 0903145293-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903145293 JE6419 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-08-09 | 16/09/2026 | 2026-08-09 | 2026-10-09 | 1318 | 1082 | 236 |  |  | 2026-04-09 | 2026-12-09 | 29/08/2026 | 2026-02-09 | 1318 | 1294 | 24
ADIDAS | 0903145318-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 499 | 30/09/2026 | 499 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145318 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 499 |  | 499 |  |  | 17/09/2026 | 19/09/2026 |  |  | 499 |  | 499
ADIDAS | 0903145343-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 451 | 2026-09-09 | 451 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145343 IM0081 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | U FI LOGO PT |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 451 | 451 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-07-09 | 451 | 451
ADIDAS | 0903145368-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 450 | 2026-09-09 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145368 IS4395 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 450 | 450
ADIDAS | 0903145380-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 15/10/2026 | 315 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145380 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S CHELSEA B7 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 315 |  | 315 |  |  | 2026-02-10 | 2026-03-10 |  |  | 315 |  | 315
ADIDAS | 0903145392-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145392 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-05-10 |  |  | 330 |  | 330
ADIDAS | 0903145395-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 09/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145395 IS4395 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-09-09 | 1051 | 1051 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-03-09 | 1051 | 1051
ADIDAS | 0903145433-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 15/10/2026 | 450 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145433 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S CHELSEA B7 |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 450 |  | 450 |  |  | 2026-03-10 | 2026-05-10 |  |  | 450 |  | 450
ADIDAS | 0903145448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145448 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 420 |  | 420 |  |  | 2026-05-10 | 2026-07-10 |  |  | 420 |  | 420
ADIDAS | 0903145462-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145462 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 3S CHELSEA B7 |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 345 |  | 345 |  |  | 2026-05-10 | 2026-07-10 |  |  | 345 |  | 345
ADIDAS | 0903145473-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145473 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | M 3S CHELSEA B7 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 420 |  | 420 |  |  | 2026-07-10 | 2026-08-10 |  |  | 420 |  | 420
ADIDAS | 0903145504-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 960 | 30/09/2026 | 960 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145504 JD1877 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 960 |  | 960 |  |  | 16/09/2026 | 18/09/2026 |  |  | 960 |  | 960
ADIDAS | 0903145534-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 401 | 30/09/2026 | 401 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145534 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S FT FZ HD |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 401 |  | 401 |  |  | 25/09/2026 | 26/09/2026 | 28/08/2026 | 2026-11-09 | 401 | 386 | 15
ADIDAS | 0903145568-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145568 JE6340 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 14/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903145571-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145571 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | M 3S CHELSEA B7 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 435 |  | 435 |  |  | 2026-07-10 | 2026-08-10 |  |  | 435 |  | 435
ADIDAS | 0903145627-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 30/09/2026 | 359 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145627 JE6340 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 359 |  | 359 |  |  | 16/09/2026 | 18/09/2026 |  |  | 359 |  | 359
ADIDAS | 0903146197-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 30/09/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903146197 LC8884 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | M RESORT T BLACK |  | SS27 | 17/09/2026 | 17/09/2026 |  |  | 128 |  | 128 |  |  | 14/09/2026 | 14/09/2026 | 28/07/2026 | 2026-11-08 | 128 | 99 | 29
ADIDAS | 0903146288-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 222 | 30/09/2026 | 222 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (07/08/2026) | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146288 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 222 |  | 222 |  |  | 18/09/2026 | 18/09/2026 |  |  | 222 |  | 222
ADIDAS | 0903146309-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Cargoport). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146309 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 23/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 150 |  | 150 |  |  | 19/09/2026 | 21/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903146354-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 215 | 23/09/2026 | 215 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903146354 KX0126 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 215 |  | 215 |  |  | 2026-11-09 | 14/09/2026 | 2026-05-08 | 2026-12-08 | 215 | 205 | 10
ADIDAS | 0903146398-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Cargoport). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146398 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 24/10/2026 |  |  | 174 |  | 174 |  |  | 19/10/2026 | 21/10/2026 |  |  | 174 |  | 174 |  |  | 13/10/2026 | 15/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146484-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 308 | 15/10/2026 | 308 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146484 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 308 |  | 308 |  |  | 19/10/2026 | 20/10/2026 |  |  | 308 |  | 308
ADIDAS | 0903146520-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 274 | 15/10/2026 | 274 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146520 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 274 |  | 274 |  |  | 24/10/2026 | 26/10/2026 |  |  | 274 |  | 274
ADIDAS | 0903146532-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146532 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 174 |  | 174 |  |  | 29/10/2026 | 30/10/2026 |  |  | 174 |  | 174 |  |  | 23/10/2026 | 24/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146599-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 895 | 15/10/2026 | 895 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903146599 KY5988 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 895 |  | 895 |  |  | 2026-10-10 | 2026-12-10 |  |  | 895 |  | 895 |  |  | 2026-05-10 | 2026-06-10 |  |  | 895 |  | 895
ADIDAS | 0903146738-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 126 | 30/09/2026 | 126 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903146738 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 126 |  | 126 |  |  | 18/09/2026 | 19/09/2026 |  |  | 126 |  | 126 |  |  | 17/09/2026 | 18/09/2026 |  |  | 126 |  | 126
ADIDAS | 0903146791-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 15/10/2026 | 100 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 512108 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903146791 KX7715 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 21/09/2026 | 24/09/2026 |  |  | 100 |  | 100 |  |  | 17/09/2026 | 21/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903146836-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 174 | 30/09/2026 | 174 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Damco offline). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 688010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146836 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 174 |  | 174 |  |  | 19/09/2026 | 21/09/2026 | 26/08/2026 | 31/08/2026 | 174 | 151 | 23
ADIDAS | 0903147020-1 KT4840 | ONIX | 90D | S2408MR1600 | 386 | 15/10/2026 | 386 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903147020 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 386 |  | 386 |  |  | 13/10/2026 | 14/10/2026 |  |  | 386 |  | 386 |  |  | 2026-12-10 | 13/10/2026 |  |  | 386 |  | 386
ADIDAS | 0903147025-1 KE6712 | BLACK | 105D | S2608MR0601A | 448 | 15/10/2026 | 448 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147025 KE6712 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 23/10/2026 | 24/10/2026 |  |  | 448 |  | 448 |  |  | 20/10/2026 | 21/10/2026 |  |  | 448 |  | 448 |  |  | 19/10/2026 | 20/10/2026 |  |  | 448 |  | 448
ADIDAS | 0903147045-1 JD0957 | BLACK | 60D | S25ORISW311 | 800 | 15/10/2026 | 800 | ID | ID26/06/2026 | G3J | SHORTS | G3 | ok | ok | T2 Fu Hsun, PI Date 29-Jul, actual receives 14-Aug. T2 Libolon, PI Date 29-Jul, actual receives 09-Jul. 960006 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903147045 JD0957 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIC SWIMSH 5IN |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 800 |  | 800 |  |  | 2026-06-10 | 2026-07-10 |  |  | 800 |  | 800
ADIDAS | 0903147053-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 382 | 15/10/2026 | 382 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147053 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 382 |  | 382 |  |  | 17/10/2026 | 20/10/2026 |  |  | 382 |  | 382 |  |  | 16/10/2026 | 19/10/2026 |  |  | 382 |  | 382
ADIDAS | 0903147253-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147253 KD3911 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | RELEASED |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 881 |  | 881 |  |  | 2026-12-09 | 14/09/2026 | 13/09/2026 | 15/09/2026 | 881 | 874 | 7
ADIDAS | 0903147280-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1560 | 30/09/2026 | 1560 | SI | SI26/06/2026 | G3E | PANTS | G3 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903147280 HK7317 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | ESS SWTP |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1560 |  | 1560 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1560 |  | 1560
ADIDAS | 0903147309-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147309 JW7177 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | W 3S FT OH PT |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1541 |  | 1541 |  |  | 24/09/2026 | 26/09/2026 | 2026-07-09 | 14/09/2026 | 1541 | 1340 | 201 |  | 329
ADIDAS | 0903147338-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903147338 HK7319 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | ESS SWTP |  | SS27 | 25/09/2026 | 2026-01-10 |  |  | 2641 |  | 2641 |  |  | 22/09/2026 | 28/09/2026 |  |  | 2641 |  | 2641
ADIDAS | 0903147369-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 599 | 2026-02-09 | 599 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147369 HL2270 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | IN RANGE |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 599 | 599 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 599 | 599
ADIDAS | 0903147397-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 2101 | 28/08/2026 | 2101 | SA | SA26/06/2026 | G2D,G2F,G2S | PANTS | G2 | (29/07/2026) | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903147397 GK8824 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | M 3S FL TC PT |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 2101 | 2101 |  |  |  | 19/08/2026 | 24/08/2026 | 2026-12-08 | 19/08/2026 | 2101 | 2101
ADIDAS | 0903147489-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 597 | 2026-02-09 | 597 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147489 H57046 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 2026-01-09 | 26/08/2026 | 29/08/2026 | 597 | 597 |  |  |  | 20/08/2026 | 28/08/2026 | 22/08/2026 | 27/08/2026 | 597 | 597
ADIDAS | 0903147513-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903147513 KD3911 | 2026-10-08 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | RELEASED |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 881 |  | 881 |  |  | 14/09/2026 | 15/09/2026 | 13/09/2026 | 15/09/2026 | 881 | 866 | 15 |  | 278
ADIDAS | 0903147547-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 1400 | 28/08/2026 | 1400 | SA | SA26/06/2026 | G2D,G2F,G2S | PANTS | G2 | (29/07/2026) | ok | 28/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903147547 GK8823 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 24/08/2026 | M 3S FL TC PT |  | SS27 | 24/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1400 | 1400 |  |  |  | 19/08/2026 | 24/08/2026 | 26/08/2026 | 28/08/2026 | 1400 | 1400
ADIDAS | 0903147569-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 601 | 2026-02-09 | 601 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147569 GK8823 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 601 | 601 |  |  |  | 24/08/2026 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 601 | 601
ADIDAS | 0903147631-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3E | PANTS | G3 | (29/07/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903147631 HK7317 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-05-10 |  |  | 2860 |  | 2860 |  |  | 25/09/2026 | 2026-01-10 |  |  | 2860 |  | 2860
ADIDAS | 0903147665-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516442 | EMBRO SUB PROCESS_V1 | 0903147665 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 1320 |  | 1320 |  |  | 16/09/2026 | 18/09/2026 | 2026-11-08 | 31/08/2026 | 1320 | 1320
ADIDAS | 0903147675-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 895 | 30/09/2026 | 895 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903147675 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 895 |  | 895 |  |  | 19/09/2026 | 21/09/2026 |  |  | 895 |  | 895 |  |  | 18/09/2026 | 19/09/2026 |  |  | 895 |  | 895
ADIDAS | 0903147741-1 GV5295 | BLACK/WHITE | 45D | F213CSIM109FL | 899 | 31/08/2026 | 899 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 |  |  | 31/08: ex-fty (S4EU). DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903147741 GV5295 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/07/2026 | M FEELCOZY SWT |  | SS27 | 23/07/2026 | 28/07/2026 | 23/07/2026 | 28/07/2026 | 899 | 899 |  |  |  | 20/07/2026 | 23/07/2026 | 20/07/2026 | 24/07/2026 | 899 | 899
ADIDAS | 0903147765-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 900 | 30/09/2026 | 900 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147765 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 900 |  | 900 |  |  | 15/09/2026 | 17/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903147789-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 30/09/2026 | 720 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903147789 JE6414 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 720 |  | 720 |  |  | 2026-11-09 | 15/09/2026 | 29/08/2026 | 2026-01-09 | 720 | 634 | 86
ADIDAS | 0903147800-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 838 | 15/10/2026 | 838 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147800 KX7716 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 16/10/2026 | 20/10/2026 |  |  | 838 |  | 838 |  |  | 13/10/2026 | 16/10/2026 |  |  | 838 |  | 838
ADIDAS | 0903147835-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 675 | 15/10/2026 | 675 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516443 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147835 KX7716 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 29/09/2026 | 2026-03-10 |  |  | 675 |  | 675 |  |  | 25/09/2026 | 30/09/2026 |  |  | 675 |  | 675
ADIDAS | 0903147850-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903147850 JE6340 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 660 |  | 660 |  |  | 14/09/2026 | 16/09/2026 |  |  | 660 |  | 660
ADIDAS | 0903147881-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147881 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1319 |  | 1319 |  |  | 17/09/2026 | 21/09/2026 | 2026-11-08 | 2026-01-09 | 1319 | 493 | 826
ADIDAS | 0903147929-1 GN4054 | BLACK/WHITE | 60D | S211CSIG213 | 901 | 31/08/2026 | 901 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | HT SUB PROCESS_V1 | 0903147929 GN4054 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | IN RANGE |  | SS27 | 26/08/2026 | 28/08/2026 | 21/08/2026 | 28/08/2026 | 901 | 901 |  |  |  | 21/08/2026 | 26/08/2026 | 2026-07-08 | 26/08/2026 | 901 | 901 |  |  |  | 20/08/2026 | 24/08/2026 | 2026-07-08 | 26/08/2026 | 901 | 901
ADIDAS | 0903147940-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 241 | 15/09/2026 | 241 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903147940 LE8193 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 241 | 241 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-07-09 | 241 | 241
ADIDAS | 0903147956-1 GN4054 | BLACK/WHITE | 60D | S211CSIG213 | 2100 | 26/08/2026 | 2100 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 26/08: ex-fty 516318 | HT SUB PROCESS_V1 | 0903147956 GN4054 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | IN RANGE |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 2100 | 2100 |  |  |  | 14/08/2026 | 21/08/2026 | 2026-05-08 | 2026-11-08 | 2100 | 2100 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-05-08 | 2026-10-08 | 2100 | 2100
ADIDAS | 0903147997-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 335 | 23/09/2026 | 335 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903147997 LC8884 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | M RESORT T BLACK |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 335 |  | 335 |  |  | 2026-11-09 | 14/09/2026 | 28/07/2026 | 2026-11-08 | 335 | 335
ADIDAS | 0903148037-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 1321 | 30/09/2026 | 1321 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148037 JE1309 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV SHO |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 1321 |  | 1321 |  |  | 16/09/2026 | 18/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903148066-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903148066 JE6338 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 1760 |  | 1760 |  |  | 24/09/2026 | 28/09/2026 | 2026-03-09 | 2026-05-09 | 1760 | 486 | 1274
ADIDAS | 0903148083-1 LC6583 | GREY | 105D | S2750MTR051 | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 830009 | HT SUB PROCESS_V1 | 0903148083 LC6583 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D4T ESS T GREY |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 110 |  | 110 |  |  | 2026-03-10 | 2026-05-10 |  |  | 110 |  | 110 |  |  | 2026-02-10 | 2026-03-10 |  |  | 110 |  | 110
ADIDAS | 0903148089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 719 | 30/09/2026 | 719 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903148089 JE6417 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 719 |  | 719 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-08 | 2026-01-09 | 719 | 715 | 4
ADIDAS | 0903148210-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 15/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516471 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148210 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 17/09/2026 | 2026-11-09 | 15/09/2026 | 300 | 300 |  |  |  | 2026-05-09 | 14/09/2026 | 26/08/2026 | 2026-11-09 | 300 | 300
ADIDAS | 0903148776-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 561 | 15/10/2026 | 561 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148776 KY5988 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 561 |  | 561 |  |  | 2026-09-10 | 2026-10-10 |  |  | 561 |  | 561 |  |  | 2026-03-10 | 2026-05-10 |  |  | 561 |  | 561
ADIDAS | 0903148797-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 603 | 30/09/2026 | 603 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903148797 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 17/09/2026 | 14/08/2026 | 2026-03-09 | 603 | 603 |  |  |  | 2026-11-08 | 15/09/2026 | 30/07/2026 | 2026-06-08 | 603 | 603 |  |  |  | 2026-10-08 | 14/09/2026 | 29/07/2026 | 13/08/2026 | 603 | 603
ADIDAS | 0903148818-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 318 | 23/09/2026 | 318 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148818 LE8181 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 318 |  | 318 |  |  | 2026-12-09 | 14/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903148821-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 443 | 15/09/2026 | 443 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903148821 LE8193 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-02-09 | 443 | 443
ADIDAS | 0903148878-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148878 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 16/10/2026 | W 3S FT OH PT |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 437 |  | 437 |  |  | 13/10/2026 | 14/10/2026 |  |  | 437 |  | 437
ADIDAS | 0903148893-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 312 | 23/09/2026 | 312 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148893 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 312 |  | 312 |  |  | 2026-12-09 | 2026-12-09 |  |  | 312 |  | 312
ADIDAS | 0903148948-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 142 | 15/10/2026 | 142 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903148948 LD6542 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 142 |  | 142 |  |  | 13/10/2026 | 15/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903148963-1 LE8187 | BLACK | 105D | S2754MAS513 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148963 LE8187 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 174 |  | 174 |  |  | 17/10/2026 | 20/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903148974-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 948 | 2026-02-10 | 948 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903148974 LD0930 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 30/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 948 |  | 948 |  |  | 26/09/2026 | 28/09/2026 |  |  | 948 |  | 948 |  |  | 24/09/2026 | 25/09/2026 |  |  | 948 |  | 948
ADIDAS | 0903148990-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 455 | 15/10/2026 | 455 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148990 LF0718 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-12-10 | M SL WV OH PT BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 455 |  | 455 |  |  | 2026-08-10 | 2026-09-10 |  |  | 455 |  | 455
ADIDAS | 0903148994-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903148994 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 13/10/2026 | M 3S FT TC PT |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 437 |  | 437 |  |  | 2026-09-10 | 2026-10-10 |  |  | 437 |  | 437
ADIDAS | 0903149007-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 101 | 30/09/2026 | 101 | SA | SA26/06/2026 | G2J | T-SHIRT | G2 | (28/08/2026) | ok | 23/09: ex-fty 838103 | PAD+HT SUB PROCESS_V3 | 0903149007 JG5832 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/09/2026 | SQUA133 JSY M BLACK/WHITE |  | SS27-TI | 26/09/2026 | 26/09/2026 |  |  | 101 |  | 101 |  |  | 23/09/2026 | 23/09/2026 |  |  | 101 |  | 101 |  |  | 22/09/2026 | 22/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903149019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Aug. T2 Libolon, PI Date 22-Jul, actual receives 25-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149019 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 |  |  | 1 |  | 1
ADIDAS | 0903149036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 660 | 15/10/2026 | 660 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903149036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 26/10/2026 | 27/10/2026 |  |  | 660 |  | 660 |  |  | 22/10/2026 | 23/10/2026 |  |  | 660 |  | 660 |  |  | 16/10/2026 | 17/10/2026 |  |  | 660 |  | 660
ADIDAS | 0903149043-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149043 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 1 |  | 1 |  |  | 23/09/2026 | 25/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149056-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 1 | 30/09/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149056 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 1 |  | 1 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1 |  | 1
ADIDAS | 0903149090-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3H | PANTS | G3 | ok | (07/08/2026(3)) | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149090 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 | 2026-07-08 | 2026-07-08 | 1 | 1
ADIDAS | 0903149104-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1 | 30/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149104 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 19/09/2026 | 24/09/2026 |  |  | 1 |  | 1 |  |  | 16/09/2026 | 21/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149132-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 387 | 29/09/2026 | 387 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149132 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 24/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 387 |  | 387 |  |  | 21/09/2026 | 22/09/2026 | 26/08/2026 | 2026-03-09 | 387 | 369 | 18
ADIDAS | 0903149247-1 KT4840 | ONIX | 90D | S2408MR1600 | 150 | 15/10/2026 | 150 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903149247 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 150 |  | 150 |  |  | 13/10/2026 | 14/10/2026 | 2026-12-09 | 2026-12-09 | 150 | 2 | 148 |  |  | 2026-12-10 | 13/10/2026 | 2026-05-09 | 2026-05-09 | 150 | 2 | 148
ADIDAS | 0903149419-1 KT4840 | ONIX | 90D | S2408MR1600 | 2315 | 23/09/2026 | 2315 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903149419 KT4840 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 21/09/2026 |  |  | 2315 |  | 2315 |  |  | 15/09/2026 | 18/09/2026 | 2026-08-09 | 2026-11-09 | 2315 | 1946 | 369 |  |  | 14/09/2026 | 17/09/2026 | 2026-07-09 | 14/09/2026 | 2315 | 1961 | 354 |  | 15
ADIDAS | 0903149526-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 399 | 31/08/2026 | 399 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L2+PAD SUB PROCESS_V3 | 0903149526 KU2430 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/08/2026 | M FB NOVELTY T WHITE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 399 | 399 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-11-08 | 22/08/2026 | 399 | 399
ADIDAS | 0903149560-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 329 | 26/08/2026 | 329 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903149560 KU2430 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/08/2026 | M FB NOVELTY T WHITE |  | SS27 | 18/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 329 | 329 |  |  |  | 2026-12-08 | 20/08/2026 | 2026-11-08 | 21/08/2026 | 329 | 329
ADIDAS | 0903149656-1 HK7319 | BLACK | 90D | F2225M403 | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149656 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 400 |  | 400 |  |  | 21/09/2026 | 22/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903149744-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149744 HK7319 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | ESS SWTP |  | SS27 | 2026-01-10 | 2026-07-10 |  |  | 2641 |  | 2641 |  |  | 28/09/2026 | 2026-03-10 | 15/09/2026 | 15/09/2026 | 2641 | 183 | 2458
ADIDAS | 0903149771-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 600 | 30/09/2026 | 600 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149771 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 600 |  | 600 |  |  | 21/09/2026 | 24/09/2026 |  |  | 600 |  | 600
ADIDAS | 0903149799-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 601 | 31/08/2026 | 601 | SA | SA26/06/2026 | G3I | PANTS | G3 | (29/07/2026(9)) |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903149799 GK9267 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/07/2026 | M 3S FL O PT |  | SS27 | 22/07/2026 | 30/07/2026 | 24/07/2026 | 28/07/2026 | 601 | 601 |  |  |  | 17/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 601 | 601
ADIDAS | 0903149833-1 HZ0747 | BLACK | 90D | F2325M414 | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903149833 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 399 |  | 399 |  |  | 2026-11-09 | 2026-12-09 | 31/08/2026 | 2026-02-09 | 399 | 398 | 1
ADIDAS | 0903149866-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3A | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149866 HR8583 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | ESS SWTP |  | SS27 | 2026-07-10 | 13/10/2026 |  |  | 3300 |  | 3300 |  |  | 2026-03-10 | 2026-09-10 |  |  | 3300 |  | 3300
ADIDAS | 0903149894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 25/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149894 IB8686 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | ESS TEE |  | SS27 | 16/09/2026 | 18/09/2026 |  |  | 2200 |  | 2200 |  |  | 2026-12-09 | 15/09/2026 | 2026-12-08 | 2026-12-09 | 2200 | 2187 | 13
ADIDAS | 0903149921-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 1398 | 28/08/2026 | 1398 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903149921 HL2270 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | IN RANGE |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1398 | 1398 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 24/08/2026 | 1398 | 1398
ADIDAS | 0903149953-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903149953 IB8686 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | ESS TEE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 1200 |  | 1200 |  |  | 2026-11-09 | 2026-12-09 | 26/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903149971-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 820 | 15/10/2026 | 820 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903149971 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 820 |  | 820 |  |  | 27/10/2026 | 28/10/2026 |  |  | 820 |  | 820 |  |  | 26/10/2026 | 27/10/2026 |  |  | 820 |  | 820
ADIDAS | 0903149978-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2A | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149978 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 22/09/2026 |  |  | 4543 |  | 4543 |  |  | 2026-12-09 | 18/09/2026 |  |  | 4543 |  | 4543
ADIDAS | 0903150021-1 KA0246 | BLACK | 90D | S2608WR0902 | 399 | 2026-07-10 | 399 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903150021 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 22/09/2026 | 24/09/2026 |  |  | 399 |  | 399 |  |  | 21/09/2026 | 23/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903150041-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 900 | 2026-02-09 | 900 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903150041 GK8821 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 900 | 900 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 2026-02-09 | 900 | 900
ADIDAS | 0903150068-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150068 IB8686 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | ESS TEE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 2200 |  | 2200 |  |  | 15/09/2026 | 17/09/2026 | 2026-11-08 | 31/08/2026 | 2200 | 2200
ADIDAS | 0903150072-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 1200 | 2026-07-10 | 1200 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516260 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903150072 KY5988 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-10-10 | 13/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1200 |  | 1200 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1200 |  | 1200
ADIDAS | 0903150101-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 360 | 30/09/2026 | 360 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903150101 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 360 |  | 360 |  |  | 25/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 360 | 332 | 28
ADIDAS | 0903150103-1 HZ0747 | BLACK | 90D | F2325M414 | 2478 | 30/09/2026 | 2478 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903150103 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 2478 | 36 | 2442 |  |  | 2026-11-09 | 15/09/2026 | 2026-01-09 | 13/09/2026 | 2478 | 2472 | 6
ADIDAS | 0903150130-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1800 | 30/09/2026 | 1800 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 21/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903150130 HR8583 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | ESS SWTP |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 1800 |  | 1800 |  |  | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 1800 | 102 | 1698
ADIDAS | 0903150152-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 26/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150152 JE6341 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 881 |  | 881 |  |  | 22/09/2026 | 24/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150214-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2B | JACKET | G2 | (08/08/2026) | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150214 JD1877 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1759 |  | 1759 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903150242-1 IY9082 | ALUMINA S20 | 45D | F213CSIM109FL | 449 | 31/08/2026 | 449 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903150242 IY9082 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/07/2026 | M FEELCOZY SWT |  | SS27 | 17/07/2026 | 23/07/2026 | 20/07/2026 | 23/07/2026 | 449 | 449 |  |  |  | 14/07/2026 | 20/07/2026 | 17/07/2026 | 20/07/2026 | 449 | 449
ADIDAS | 0903150279-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 901 | 30/09/2026 | 901 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150279 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | W 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 901 |  | 901 |  |  | 26/09/2026 | 28/09/2026 | 28/08/2026 | 2026-11-09 | 901 | 862 | 39
ADIDAS | 0903150304-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150304 JE6338 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1760 |  | 1760 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903150340-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150340 JE6341 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 881 |  | 881 |  |  | 18/09/2026 | 21/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150366-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 959 | 30/09/2026 | 959 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150366 JE6338 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 959 |  | 959 |  |  | 16/09/2026 | 18/09/2026 |  |  | 959 |  | 959
ADIDAS | 0903150392-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1321 | 30/09/2026 | 1321 | SI | SI26/06/2026 | G3J | SHORTS | G3 | (10/08/2026) | ok | 26/09: ex-fty. Waiting fabric. T2 Gistex, (3S) PI Date 10-Aug, ETD ?? T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150392 JE1309 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | W 3S WV SHO |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1321 |  | 1321 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903150471-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 28/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150471 JE6417 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1320 |  | 1320 |  |  | 19/09/2026 | 22/09/2026 | 2026-11-08 | 2026-01-09 | 1320 | 1320
ADIDAS | 0903150495-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150495 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 500 |  | 500 |  |  | 14/09/2026 | 16/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903150517-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 372 | 29/09/2026 | 372 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | ok | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150517 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 21/09/2026 |  |  | 372 |  | 372 |  |  | 17/09/2026 | 17/09/2026 |  |  | 372 |  | 372 |  |  | 15/09/2026 | 15/09/2026 |  |  | 372 |  | 372
ADIDAS | 0903150541-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1148 | 14/10/2026 | 1148 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150541 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-10 | 2026-06-10 |  |  | 1148 |  | 1148 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1148 |  | 1148 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1148 |  | 1148
ADIDAS | 0903150629-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1235 | 14/10/2026 | 1235 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150629 LD0283 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 1235 |  | 1235 |  |  | 26/09/2026 | 28/09/2026 |  |  | 1235 |  | 1235 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1235 |  | 1235
ADIDAS | 0903150630-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 648 | 15/09/2026 | 648 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903150630 LE8210 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 648 | 312 | 336 |  | 90 | 2026-09-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 648 | 561 | 87 |  | 26
ADIDAS | 0903150635-1 IS1413 | BLACK | 60D | S2425M405 | 1042 | 26/08/2026 | 1042 | SI | SI26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903150635 IS1413 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 20/08/2026 | IN RANGE |  | SS27 | 20/08/2026 | 26/08/2026 | 20/08/2026 | 24/08/2026 | 1042 | 1042 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-04-08 | 24/08/2026 | 1042 | 1042
ADIDAS | 0903150899-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 181 | 30/09/2026 | 181 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903150899 LC6339 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 181 |  | 181 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 181 | 157 | 24
ADIDAS | 0903150944-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 345 | 30/09/2026 | 345 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150944 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 345 |  | 345 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 345 | 335 | 10
ADIDAS | 0903150972-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 126 | 15/10/2026 | 126 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150972 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 126 |  | 126 |  |  | 17/10/2026 | 20/10/2026 |  |  | 126 |  | 126
ADIDAS | 0903151028-1 IS1413 | BLACK | 60D | S2425M405 | 378 | 2026-12-09 | 378 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903151028 IS1413 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 378 | 378 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-11-08 | 2026-03-09 | 378 | 378
ADIDAS | 0903151088-1 KC4947 | BLACK | 105D | S2608WR0216 | 566 | 15/10/2026 | 566 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 806020 | PAD+HT SUB PROCESS_V3 | 0903151088 KC4947 | 24/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA | 13/10/2026 | adi365 Astro W |  | SS27-TRAX | 13/10/2026 | 16/10/2026 |  |  | 566 |  | 566 |  |  | 2026-09-10 | 13/10/2026 |  |  | 566 |  | 566 |  |  | 2026-08-10 | 2026-12-10 |  |  | 566 |  | 566
ADIDAS | 0903151096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903151096 IZ0443 | 28/07/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-02-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903151127-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2C | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903151127 JE6419 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 25/09/2026 | 26/09/2026 | 18/08/2026 | 29/08/2026 | 540 | 540
ADIDAS | 0903151171-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151171 LC8884 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-08-10 | 2026-11-08 | 2026-11-08 | 100 | 96 | 4
ADIDAS | 0903151219-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 327 | 15/10/2026 | 327 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903151219 LE5609 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/10/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 327 |  | 327 |  |  | 16/10/2026 | 17/10/2026 |  |  | 327 |  | 327 |  |  | 2026-10-10 | 2026-12-10 |  |  | 327 |  | 327
ADIDAS | 0903151248-1 LF0723 | BLACK | 105D | S2754MAS511B | 373 | 15/10/2026 | 373 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151248 LF0723 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | M SL WV SHO BLACK |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 373 |  | 373 |  |  | 22/10/2026 | 24/10/2026 |  |  | 373 |  | 373
ADIDAS | 0903151295-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151295 KX0126 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-07-10 | 2026-05-08 | 20/08/2026 | 100 | 94 | 6
ADIDAS | 0903151313-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151313 JN1958 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | W 3S FT QZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 1540 |  | 1540 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151330-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 26/09: ex-fty 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151330 JN1958 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 18/09/2026 | W 3S FT QZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1540 |  | 1540 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151405-1 H12221 | MEDIUM GREY HEATHER/BLACK | 45D | F213CSIM109FL | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903151405 H12221 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/07/2026 | M FEELCOZY SWT |  | SS27 | 23/07/2026 | 28/07/2026 | 24/07/2026 | 29/07/2026 | 450 | 450 |  |  |  | 20/07/2026 | 23/07/2026 | 24/07/2026 | 27/07/2026 | 450 | 450
ADIDAS | 0903151431-1 H12258 | DARK GREY HEATHER/BLACK | 45D | S211CSIM117FLRO | 598 | 31/08/2026 | 598 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903151431 H12258 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-07 | M 3S FL O PT |  | SS27 | 2026-10-07 | 27/07/2026 | 2026-10-07 | 27/07/2026 | 598 | 598 |  |  |  | 2026-07-07 | 22/07/2026 | 18/07/2026 | 22/07/2026 | 598 | 598
ADIDAS | 0903151460-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 2100 | 28/08/2026 | 2100 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 27/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903151460 GK8821 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S FL TC PT |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 2100 | 2100 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-12-08 | 19/08/2026 | 2100 | 2100
ADIDAS | 0903151539-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151539 JN1958 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | W 3S FT QZ HD |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 840 | 674 | 166 |  | 427 | 2026-09-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 840 | 764 | 76
ADIDAS | 0903151579-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151579 JW7177 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | W 3S FT OH PT |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 1541 |  | 1541 |  |  | 26/09/2026 | 28/09/2026 | 31/08/2026 | 2026-08-09 | 1541 | 1533 | 8
ADIDAS | 0903151624-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151624 JW7178 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-10 | W 3S FT OH PT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 1431 |  | 1431 |  |  | 2026-05-10 | 2026-06-10 | 2026-12-09 | 15/09/2026 | 1431 | 1312 | 119
ADIDAS | 0903151645-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 355 | 15/10/2026 | 355 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903151645 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 355 |  | 355 |  |  | 29/10/2026 | 30/10/2026 |  |  | 355 |  | 355 |  |  | 23/10/2026 | 24/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903152156-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1054 | 29/09/2026 | 1054 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152156 KX3650 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 1054 |  | 1054 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1054 |  | 1054 |  |  | 2026-11-09 | 2026-12-09 |  |  | 1054 |  | 1054
ADIDAS | 0903152165-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 752 | 30/09/2026 | 752 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152165 LE8201 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 14/09/2026 | 2026-07-09 | 14/09/2026 | 752 | 485 | 267 |  | 98 | 2026-02-09 | 2026-10-09 | 2026-03-09 | 13/09/2026 | 752 | 752
ADIDAS | 0903152177-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 370 | 29/09/2026 | 370 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152177 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 17/09/2026 |  |  | 370 |  | 370 |  |  | 14/09/2026 | 14/09/2026 |  |  | 370 |  | 370 |  |  | 2026-11-09 | 2026-11-09 |  |  | 370 |  | 370
ADIDAS | 0903152204-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 4012 | 15/09/2026 | 4012 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152204 LE8202 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 4012 | 3717 | 295 |  | 424 | 2026-02-09 | 2026-11-09 | 21/08/2026 | 15/09/2026 | 4012 | 3864 | 148 |  | 95
ADIDAS | 0903152214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 756 | 29/09/2026 | 756 | AN | AN26/06/2026 | G2M | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152214 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 756 |  | 756 |  |  | 17/09/2026 | 18/09/2026 |  |  | 756 |  | 756 |  |  | 15/09/2026 | 16/09/2026 |  |  | 756 |  | 756
ADIDAS | 0903152235-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 351 | 15/09/2026 | 351 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152235 LE8208 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 351 | 224 | 127 |  | 224 | 2026-05-09 | 2026-11-09 | 2026-12-09 | 15/09/2026 | 351 | 348 | 3 |  | 334
ADIDAS | 0903152275-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 1600 | 30/09/2026 | 1600 | SI | SI26/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152275 LE8194 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | REAL HFY JSY SE WHITE |  | SS27-FJ | 2026-01-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 1600 | 1600 |  |  |  | 28/08/2026 | 2026-09-09 | 2026-03-09 | 2026-10-09 | 1600 | 1600
ADIDAS | 0903152279-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 875 | 15/09/2026 | 875 | AN | AN26/06/2026 | G3J,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152279 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  | 574 | 2026-05-09 | 2026-10-09 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  | 25 | 31/08/2026 | 2026-04-09 | 2026-08-09 | 14/09/2026 | 875 | 875 |  |  | 25
ADIDAS | 0903152318-1 KE6712 | BLACK | 105D | S2608MR0601A | 1026 | 15/10/2026 | 1026 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 678002 | PAD+HT SUB PROCESS_V3 | 0903152318 KE6712 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 24/10/2026 | 28/10/2026 |  |  | 1026 |  | 1026 |  |  | 21/10/2026 | 24/10/2026 |  |  | 1026 |  | 1026 |  |  | 20/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903152321-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 4210 | 15/09/2026 | 4210 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152321 LE8193 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL H F JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 4210 | 4065 | 145 |  |  | 29/08/2026 | 2026-11-09 | 18/08/2026 | 14/09/2026 | 4210 | 4210 |  |  | 47
ADIDAS | 0903152351-1 KE6899 | BLACK | 105D | S2608WR0601B | 661 | 15/10/2026 | 661 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903152351 KE6899 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 661 |  | 661 |  |  | 29/10/2026 | 31/10/2026 |  |  | 661 |  | 661 |  |  | 28/10/2026 | 30/10/2026 |  |  | 661 |  | 661
ADIDAS | 0903152382-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 828 | 29/09/2026 | 828 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152382 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 16/09/2026 | 16/09/2026 |  |  | 828 |  | 828 |  |  | 2026-12-09 | 2026-12-09 |  |  | 828 |  | 828 |  |  | 2026-10-09 | 2026-10-09 |  |  | 828 |  | 828
ADIDAS | 0903152458-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 396 | 29/09/2026 | 396 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152458 LD0930 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 18/09/2026 | 18/09/2026 |  |  | 396 |  | 396 |  |  | 15/09/2026 | 15/09/2026 |  |  | 396 |  | 396 |  |  | 2026-12-09 | 2026-12-09 |  |  | 396 |  | 396
ADIDAS | 0903152502-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 300 | 29/09/2026 | 300 | SA | SA26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152502 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/09/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 2026-10-09 | 2026-11-09 |  |  | 300 |  | 300
ADIDAS | 0903152532-1 LG9669 | BLACK | 120D | S2754WAS514C | 319 | 29/09/2026 | 319 | ID | ID26/06/2026 | G3C | SKIRT | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 12-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152532 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 30/09/2026 | W SL WV SK BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 26/09/2026 | 28/09/2026 | 29/08/2026 | 2026-02-09 | 319 | 236 | 83
ADIDAS | 0903152551-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 2026-09-09 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903152551 IS1413 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | IN RANGE |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 300 | 300 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-05-08 | 2026-03-09 | 300 | 300
ADIDAS | 0903152558-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 324 | 29/09/2026 | 324 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152558 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 324 |  | 324 |  |  | 14/09/2026 | 15/09/2026 |  |  | 324 |  | 324
ADIDAS | 0903152588-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 731 | 30/09/2026 | 731 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 21/09: ex-fty 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152588 HK7317 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 731 |  | 731 |  |  | 21/09/2026 | 24/09/2026 |  |  | 731 |  | 731
ADIDAS | 0903152648-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152648 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152660-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G3B | PANTS | G3 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152660 HR8583 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | ESS SWTP |  | SS27 | 22/09/2026 | 28/09/2026 |  |  | 3300 |  | 3300 |  |  | 18/09/2026 | 24/09/2026 |  |  | 3300 |  | 3300
ADIDAS | 0903152687-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 2112 | 15/10/2026 | 2112 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152687 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 20/10/2026 | 26/10/2026 |  |  | 2112 |  | 2112 |  |  | 16/10/2026 | 22/10/2026 |  |  | 2112 |  | 2112
ADIDAS | 0903152692-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152692 HK7317 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-02-10 |  |  | 2860 |  | 2860 |  |  | 24/09/2026 | 29/09/2026 |  |  | 2860 |  | 2860
ADIDAS | 0903152712-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 300 | 2026-07-10 | 300 | AN | AN26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152712 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152716-1 HK7319 | BLACK | 90D | F2225M403 | 1439 | 30/09/2026 | 1439 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 26/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903152716 HK7319 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | ESS SWTP |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 1439 |  | 1439 |  |  | 21/09/2026 | 24/09/2026 |  |  | 1439 |  | 1439
ADIDAS | 0903152733-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152733 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152759-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152759 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 330 |  | 330 |  |  | 2026-08-10 | 2026-09-10 |  |  | 330 |  | 330
ADIDAS | 0903152773-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152773 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903152781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152781 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903152787-1 GK9270 | MEDIUM GREY HEATHER | 45D | S211CSIM117FLRO | 600 | 31/08/2026 | 600 | SA | SA26/06/2026 | G3I | PANTS | G3 |  |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903152787 GK9270 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | M 3S FL O PT |  | SS27 | 27/07/2026 | 30/07/2026 | 27/07/2026 | 28/07/2026 | 600 | 600 |  |  |  | 22/07/2026 | 27/07/2026 | 25/07/2026 | 27/07/2026 | 600 | 600
ADIDAS | 0903152816-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 1750 | 26/08/2026 | 1750 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/08: ex-fty 516318 | HT SUB PROCESS_V1 | 0903152816 HU1551 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | IN RANGE |  | SS27 | 2026-06-08 | 26/08/2026 | 2026-06-08 | 20/08/2026 | 1750 | 1750 |  |  |  | 2026-04-08 | 21/08/2026 | 2026-03-08 | 2026-08-08 | 1750 | 1750 |  |  |  | 2026-03-08 | 20/08/2026 | 31/07/2026 | 2026-07-08 | 1750 | 1750
ADIDAS | 0903152843-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 750 | 30/09/2026 | 750 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | HT SUB PROCESS_V1 | 0903152843 HU1551 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 750 | 79 | 671 |  |  | 2026-12-09 | 15/09/2026 | 26/08/2026 | 14/09/2026 | 750 | 747 | 3 |  | 8 | 2026-11-09 | 14/09/2026 | 24/08/2026 | 14/09/2026 | 750 | 747 | 3 |  | 8
ADIDAS | 0903152870-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903152870 HR6286 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | U FI LOGO PT |  | SS27 | 28/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 1051 | 1051 |  |  |  | 24/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 1051 | 1051
ADIDAS | 0903152901-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | PRINT L3 SUB PROCESS_V3 | 0903152901 HR6286 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | U FI LOGO PT |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 20/08/2026 | 24/08/2026 | 14/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0903152957-1 GK9269 | LEGEND INK F17 | 45D | S211CSIM117FLRO | 599 | 31/08/2026 | 599 | SA | SA26/06/2026 | G3I | PANTS | G3 | (29/07/2026(4)) |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903152957 GK9269 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | M 3S FL O PT |  | SS27 | 27/07/2026 | 30/07/2026 | 29/07/2026 | 29/07/2026 | 599 | 599 |  |  |  | 22/07/2026 | 27/07/2026 | 28/07/2026 | 29/07/2026 | 599 | 599
ADIDAS | 0903152983-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903152983 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | PL TEE |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 4543 |  | 4543 |  |  | 21/09/2026 | 26/09/2026 | 2026-12-09 | 15/09/2026 | 4543 | 3193 | 1350 |  | 1423
ADIDAS | 0903153088-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 389 | 30/09/2026 | 389 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153088 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 389 |  | 389 |  |  | 2026-05-10 | 2026-06-10 |  |  | 389 |  | 389
ADIDAS | 0903153111-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 550 | 30/09/2026 | 550 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | ok | 23/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 28-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153111 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 550 |  | 550 |  |  | 30/09/2026 | 2026-02-10 | 28/08/2026 | 2026-08-09 | 550 | 538 | 12
ADIDAS | 0903153147-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153147 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 25/09/2026 | 26/09/2026 | 2026-01-08 | 2026-03-09 | 540 | 540
ADIDAS | 0903153178-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 576 | 30/09/2026 | 576 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153178 JE6414 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 |  |  | 576 |  | 576 |  |  | 2026-11-09 | 15/09/2026 | 2026-01-08 | 31/08/2026 | 576 | 555 | 21
ADIDAS | 0903153208-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 414 | 30/09/2026 | 414 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153208 LC6339 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 414 |  | 414 |  |  | 19/09/2026 | 19/09/2026 | 2026-08-09 | 2026-09-09 | 414 | 405 | 9
ADIDAS | 0903153249-1 LC6341 | BLACK | 90D | S27GMGFX130 | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153249 LC6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 468 |  | 468 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 14/09/2026 | 468 | 386 | 82 |  | 24
ADIDAS | 0903153273-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153273 JE0052 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 16/09/2026 | W 3S FT FZ HD |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 308 |  | 308 |  |  | 2026-12-09 | 14/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153303-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153303 JE6338 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 468 |  | 468 |  |  | 17/09/2026 | 19/09/2026 |  |  | 468 |  | 468
ADIDAS | 0903153333-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 504 | 30/09/2026 | 504 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153333 JE6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 504 |  | 504 |  |  | 22/09/2026 | 24/09/2026 |  |  | 504 |  | 504
ADIDAS | 0903153362-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 378 | 23/09/2026 | 378 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153362 JD5302 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 378 | 378 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 378 | 378
ADIDAS | 0903153392-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153392 JE0055 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | W 3S FT FZ HD |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 308 |  | 308 |  |  | 25/09/2026 | 26/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903153425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153425 JD1877 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 |  |  | 540 |  | 540 |  |  | 14/09/2026 | 16/09/2026 |  |  | 540 |  | 540
ADIDAS | 0903153431-1 KC4947 | BLACK | 105D | S2608WR0216 | 1524 | 15/10/2026 | 1524 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 823016 | PAD+HT SUB PROCESS_V3 | 0903153431 KC4947 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 16/10/2026 | adi365 Astro W |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 1524 |  | 1524 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1524 |  | 1524 |  |  | 2026-12-10 | 15/10/2026 |  |  | 1524 |  | 1524
ADIDAS | 0903153447-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153447 KA5089 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 2026-04-09 | 2026-12-09 | 266 | 266
ADIDAS | 0903153486-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153486 KA5090 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 26/08/2026 | 2026-12-09 | 266 | 266
ADIDAS | 0903153557-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 17 | 15/10/2026 | 17 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153557 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 28/10/2026 | 29/10/2026 |  |  | 17 |  | 17 |  |  | 24/10/2026 | 26/10/2026 |  |  | 17 |  | 17
ADIDAS | 0903153563-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 844 | 2026-12-09 | 844 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 688010 | HT+PAD SUB PROCESS_V3 | 0903153563 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 844 | 844 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 844 | 844 |  |  |  | 28/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 844 | 844
ADIDAS | 0903153653-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 780 | 30/09/2026 | 780 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153653 JW7178 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | W 3S FT OH PT |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 780 |  | 780 |  |  | 2026-03-10 | 2026-05-10 | 2026-12-09 | 2026-12-09 | 780 | 698 | 82
ADIDAS | 0903153676-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153676 JW7177 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 840 |  | 840 |  |  | 18/09/2026 | 19/09/2026 | 31/08/2026 | 2026-09-09 | 840 | 798 | 42
ADIDAS | 0903153692-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903153692 KC8152 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 300 |  | 300 |  |  | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903153702-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153702 JW7178 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-10 | W 3S FT OH PT |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 1431 |  | 1431 |  |  | 2026-06-10 | 2026-08-10 | 2026-01-09 | 2026-02-09 | 1431 | 1427 | 4
ADIDAS | 0903153713-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 207 | 2026-05-09 | 207 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 04/09: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153713 IN1172 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 207 | 207 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 23/07/2026 | 207 | 207 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 23/07/2026 | 207 | 207
ADIDAS | 0903153722-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 355 | 15/10/2026 | 355 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153722 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 24/10/2026 |  |  | 355 |  | 355 |  |  | 19/10/2026 | 21/10/2026 |  |  | 355 |  | 355 |  |  | 13/10/2026 | 15/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903153754-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 201 | 2026-09-09 | 201 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153754 IN1157 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-04-09 | 201 | 201 |  |  |  | 27/08/2026 | 31/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201 |  |  |  | 26/08/2026 | 29/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201
ADIDAS | 0903153757-1 KA2965 | OFF WHITE | 60D | S26KLKGFX011-MTF | 1200 | 26/08/2026 | 1200 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 24/08: ex-fty 516204 | PRINT L2+PAD SUB PROCESS_V3 | 0903153757 KA2965 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/07/2026 | LK TIRONS T |  | SS27 | 29/07/2026 | 21/08/2026 | 29/07/2026 | 20/08/2026 | 1200 | 1200 |  |  |  | 24/07/2026 | 18/08/2026 | 25/07/2026 | 20/08/2026 | 1200 | 1200
ADIDAS | 0903153806-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 |  | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903153806 JP1528 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/07/2026 | M L G ENG TEE |  | SS27 | 22/07/2026 | 30/07/2026 | 23/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 17/07/2026 | 27/07/2026 | 21/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903153843-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 480 | 30/09/2026 | 480 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903153843 KD3911 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | RELEASED |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 480 |  | 480 |  |  | 14/09/2026 | 15/09/2026 | 31/08/2026 | 15/09/2026 | 480 | 435 | 45
ADIDAS | 0903153852-1 KE6899 | BLACK | 105D | S2608WR0601B | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903153852 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300 |  |  | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903153861-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 906 | 30/09/2026 | 906 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153861 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 906 |  | 906 |  |  | 25/09/2026 | 29/09/2026 | 29/08/2026 | 2026-03-09 | 906 | 360 | 546
ADIDAS | 0903153888-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 364 | 30/09/2026 | 364 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153888 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 364 |  | 364 |  |  | 23/09/2026 | 25/09/2026 | 31/08/2026 | 2026-03-09 | 364 | 255 | 109
ADIDAS | 0903153890-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 1504 | 15/10/2026 | 1504 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153890 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-03-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-03-11 | 2026-05-11 |  |  | 1504 |  | 1504 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1504 |  | 1504 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1504 |  | 1504
ADIDAS | 0903153893-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 481 | 15/10/2026 | 481 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 650010 | PAD+HT SUB PROCESS_V3 | 0903153893 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 481 |  | 481 |  |  | 14/10/2026 | 17/10/2026 |  |  | 481 |  | 481 |  |  | 13/10/2026 | 16/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903153906-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153906 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S FT QZ HD |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 399 |  | 399 |  |  | 14/09/2026 | 15/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903153934-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 |  | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903153934 JP1528 | 28/07/2026 | KAHATEX CIJERAH | SPAIN | SEA | 24/07/2026 | M L G ENG TEE |  | SS27 | 24/07/2026 | 30/07/2026 | 24/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 21/07/2026 | 27/07/2026 | 22/07/2026 | 28/07/2026 | 1321 | 1321
ADIDAS | 0903153996-1 H42002 | LEGEND INK F17/WHITE | 45D | F213CSIM109FL | 899 | 31/08/2026 | 899 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903153996 H42002 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/07/2026 | M FEELCOZY SWT |  | SS27 | 17/07/2026 | 23/07/2026 | 20/07/2026 | 22/07/2026 | 899 | 899 |  |  |  | 14/07/2026 | 20/07/2026 | 16/07/2026 | 20/07/2026 | 899 | 899
ADIDAS | 0903154027-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 23/09/2026 | 400 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154027 JE0052 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | W 3S FT FZ HD |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 400 |  | 400 |  |  | 2026-12-09 | 14/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903154028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 393 | 30/09/2026 | 393 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154028 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 393 |  | 393 |  |  | 19/09/2026 | 21/09/2026 | 26/08/2026 | 2026-12-09 | 393 | 324 | 69
ADIDAS | 0903154066-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 1951 | 15/10/2026 | 1951 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903154066 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 24/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 27/10/2026 |  |  | 1951 |  | 1951 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1951 |  | 1951 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1951 |  | 1951
ADIDAS | 0903154068-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903154068 JP1527 | 28/07/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/07/2026 | M L G ENG TEE |  | SS27 | 28/07/2026 | 30/07/2026 | 29/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 23/07/2026 | 27/07/2026 | 24/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903154077-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154077 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 435 |  | 435 |  |  | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435
ADIDAS | 0903154087-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 510 | 15/10/2026 | 510 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154087 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 510 |  | 510 |  |  | 2026-12-10 | 13/10/2026 |  |  | 510 |  | 510
ADIDAS | 0903154094-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 1321 | 31/08/2026 | 1321 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903154094 JP1527 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | M L G ENG TEE |  | SS27 | 28/07/2026 | 30/07/2026 | 27/07/2026 | 30/07/2026 | 1321 | 1321 |  |  |  | 23/07/2026 | 27/07/2026 | 23/07/2026 | 30/07/2026 | 1321 | 1321
ADIDAS | 0903154119-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154119 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 2026-12-09 | 14/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903154124-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 533 | 23/09/2026 | 533 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154124 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 533 | 468 | 65 |  | 255 | 2026-09-09 | 2026-11-09 | 2026-11-09 | 13/09/2026 | 533 | 516 | 17
ADIDAS | 0903154136-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154136 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | W 3S FT OH PT |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 399 |  | 399 |  |  | 2026-03-10 | 2026-05-10 | 2026-01-09 | 2026-01-09 | 399 | 351 | 48
ADIDAS | 0903154672-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 28/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154672 JE0055 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 30/09/2026 | W 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903154711-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 1265 | 30/09/2026 | 1265 | AN | AN26/06/2026 | G3K | SHORTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154711 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 1265 |  | 1265 |  |  | 19/09/2026 | 21/09/2026 | 14/09/2026 | 15/09/2026 | 1265 | 1263 | 2 |  | 931
ADIDAS | 0903154744-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA26/06/2026 | G1G,G1I,G1O,G1Q | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154744 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | LFC 3 F JSY SE |  | SS27-FJ | 31/08/2026 | 15/09/2026 | 31/08/2026 | 15/09/2026 | 15000 | 15000 |  |  | 1408 | 27/08/2026 | 2026-11-09 | 21/08/2026 | 14/09/2026 | 15000 | 14760 | 240 |  | 270
ADIDAS | 0903154788-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 2110 | 2026-12-09 | 2110 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 12/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154788 LE8201 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 2026-12-09 | 2026-07-09 | 2026-12-09 | 2110 | 2110 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-03-09 | 14/09/2026 | 2110 | 2110 |  |  | 16
ADIDAS | 0903154833-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 6345 | 15/09/2026 | 6345 | SA | SA26/06/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154833 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 6345 | 6345 |  |  | 669 | 2026-03-09 | 2026-11-09 | 2026-04-09 | 15/09/2026 | 6345 | 6283 | 62 |  | 101
ADIDAS | 0903154839-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 924 | 15/10/2026 | 924 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903154839 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 27/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 924 |  | 924 |  |  | 23/10/2026 | 24/10/2026 |  |  | 924 |  | 924 |  |  | 17/10/2026 | 19/10/2026 |  |  | 924 |  | 924
ADIDAS | 0903154867-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3701 | 15/09/2026 | 3701 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154867 LE8208 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3701 | 3701 |  |  | 505 | 2026-05-09 | 2026-11-09 | 2026-07-09 | 15/09/2026 | 3701 | 3715 | -14 | 14 | 75
ADIDAS | 0903154898-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 760 | 15/09/2026 | 760 | SA | SA26/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154898 LE8210 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 760 | 760 |  |  | 734 | 2026-02-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 760 | 760 |  |  | 66
ADIDAS | 0903154925-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 200 | 2026-12-09 | 200 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903154925 LE8193 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-02-09 | 2026-10-09 | 200 | 200 |  |  |  | 27/08/2026 | 2026-07-09 | 21/08/2026 | 2026-10-09 | 200 | 200
ADIDAS | 0903154950-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 1096 | 2026-12-09 | 1096 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903154950 LE8193 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1096 | 1096 |  |  |  | 27/08/2026 | 2026-07-09 | 20/08/2026 | 2026-10-09 | 1096 | 1096
ADIDAS | 0903154953-1 KA0235 | BLACK | 90D | S2608WR0901 | 1036 | 2026-07-10 | 1036 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 28-Aug. 516276 | PAD+HT SUB PROCESS_V3 | 0903154953 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-02-10 | 2026-05-10 |  |  | 1036 |  | 1036 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1036 |  | 1036 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903154980-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 14142 | 2026-12-09 | 14142 | SA | SA26/06/2026 | G1I,G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 12/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903154980 LE8193 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-12-09 | 2026-02-09 | 2026-12-09 | 14142 | 14142 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-11-09 | 14142 | 14142
ADIDAS | 0903155196-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G3E | PANTS | G3 | ok | ok | 834012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155196 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903155361-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 992 | 28/08/2026 | 992 | AN | AN26/06/2026 | G3B,G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155361 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 21/08/2026 | 28/08/2026 | 992 | 992 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-06-08 | 2026-05-09 | 992 | 992
ADIDAS | 0903155389-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 380 | 15/09/2026 | 380 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155389 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-10-09 | 380 | 380 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 380 | 380
ADIDAS | 0903155457-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1114 | 30/09/2026 | 1114 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 25/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 678002 | PRINT L2+HT SUB PROCESS_V3 | 0903155457 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 1114 |  | 1114 |  |  | 21/09/2026 | 22/09/2026 |  |  | 1114 |  | 1114 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1114 |  | 1114
ADIDAS | 0903155494-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 14 | 15/10/2026 | 14 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155494 LE8187 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 14 |  | 14 |  |  | 17/10/2026 | 17/10/2026 |  |  | 14 |  | 14
ADIDAS | 0903155496-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 407 | 30/09/2026 | 407 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155496 LG9660 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 407 |  | 407 |  |  | 2026-11-09 | 2026-12-09 |  |  | 407 |  | 407
ADIDAS | 0903155525-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 24 | 15/10/2026 | 24 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155525 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 24 |  | 24 |  |  | 24/10/2026 | 26/10/2026 |  |  | 24 |  | 24
ADIDAS | 0903155581-1 KB5960 | WHITE | 120D | S2608MR0900A | 3741 | 29/09/2026 | 3741 | SA | SA26/06/2026 | G2M | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155581 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/09/2026 | Run Ess Tee M |  | SS27-TI | 16/09/2026 | 21/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-12-09 | 17/09/2026 |  |  | 3741 |  | 3741 |  |  | 2026-10-09 | 15/09/2026 |  |  | 3741 |  | 3741
ADIDAS | 0903155606-1 KB5965 | BLACK | 120D | S2608MR0900A | 989 | 29/09/2026 | 989 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155606 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | Run Ess Tee M |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 989 |  | 989 |  |  | 21/09/2026 | 22/09/2026 |  |  | 989 |  | 989 |  |  | 18/09/2026 | 19/09/2026 |  |  | 989 |  | 989
ADIDAS | 0903155643-1 KB5965 | BLACK | 120D | S2608MR0900A | 5978 | 29/09/2026 | 5978 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155643 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/09/2026 | Run Ess Tee M |  | SS27-TI | 18/09/2026 | 24/09/2026 |  |  | 5978 |  | 5978 |  |  | 15/09/2026 | 21/09/2026 |  |  | 5978 |  | 5978 |  |  | 2026-12-09 | 18/09/2026 |  |  | 5978 |  | 5978
ADIDAS | 0903155916-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155916 KW9039 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 24/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 224 |  | 224 |  |  | 21/09/2026 | 22/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903155960-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903155960 JD1877 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 19/09/2026 | M 3S FT FZ HD |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 16/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903155978-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 1218 | 2026-09-09 | 1218 | ID | ID26/06/2026 | G2S | SHORTS | G2 | ok | ok | 08/09: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155978 KY7184 | 2026-11-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-09 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 2026-01-09 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1218 | 1218 |  |  |  | 28/08/2026 | 2026-04-09 | 31/08/2026 | 2026-08-09 | 1218 | 1218
ADIDAS | 0903155986-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903155986 KY3734 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 29/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903156009-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903156009 JE6341 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903156065-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 344 | 30/09/2026 | 344 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO SUB PROCESS_V1 | 0903156065 JD1881 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | M 3S FT TC PT |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 344 |  | 344 |  |  | 2026-05-10 | 2026-05-10 |  |  | 344 |  | 344
ADIDAS | 0903156157-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 401 | 30/09/2026 | 401 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156157 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 401 |  | 401 |  |  | 18/09/2026 | 19/09/2026 | 14/08/2026 | 2026-08-09 | 401 | 394 | 7
ADIDAS | 0903156162-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156162 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 435 |  | 435 |  |  | 2026-09-10 | 2026-12-10 |  |  | 435 |  | 435
ADIDAS | 0903156174-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 938 | 2026-07-10 | 938 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156174 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 938 |  | 938 |  |  | 2026-07-10 | 2026-08-10 |  |  | 938 |  | 938
ADIDAS | 0903156181-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 375 | 15/10/2026 | 375 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156181 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 375 |  | 375 |  |  | 2026-12-10 | 13/10/2026 |  |  | 375 |  | 375
ADIDAS | 0903156184-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 23/09/2026 | 610 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156184 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 14/09/2026 | 15/09/2026 | 610 | 484 | 126 |  | 285 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 2026-12-09 | 610 | 610
ADIDAS | 0903156205-1 H12226 | DARK GREY HEATHER/BLACK | 45D | F213CSIM109FL | 450 | 31/08/2026 | 450 | SI | SI26/06/2026 | G2T | SWEATSHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. DRC 0064-other customer related delay reason. 516442 | EMBRO SUB PROCESS_V1 | 0903156205 H12226 | 28/07/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/07/2026 | M FEELCOZY SWT |  | SS27 | 21/07/2026 | 23/07/2026 | 21/07/2026 | 23/07/2026 | 450 | 450 |  |  |  | 16/07/2026 | 20/07/2026 | 20/07/2026 | 23/07/2026 | 450 | 450
ADIDAS | 0903156224-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1251 | 2026-07-10 | 1251 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156224 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1251 |  | 1251 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1251 |  | 1251
ADIDAS | 0903156225-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 360 | 15/10/2026 | 360 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156225 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 360 |  | 360 |  |  | 13/10/2026 | 14/10/2026 |  |  | 360 |  | 360
ADIDAS | 0903156247-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156247 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 345 |  | 345 |  |  | 13/10/2026 | 14/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156271-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 1398 | 26/08/2026 | 1398 | SA | SA26/06/2026 | G2F | PANTS | G2 | (29/07/2026) | ok | 24/08: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903156271 H57046 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | M 3S FL TC PT |  | SS27 | 20/08/2026 | 26/08/2026 | 21/08/2026 | 24/08/2026 | 1398 | 1398 |  |  |  | 14/08/2026 | 20/08/2026 | 2026-10-08 | 15/08/2026 | 1398 | 1398
ADIDAS | 0903156282-1 KA4331 | BLACK | 90D | S2608MR0902 | 399 | 2026-07-10 | 399 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903156282 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 22/09/2026 | 24/09/2026 |  |  | 399 |  | 399 |  |  | 21/09/2026 | 23/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903156297-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156297 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 345 |  | 345 |  |  | 14/10/2026 | 16/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156313-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 525 | 15/10/2026 | 525 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156313 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 525 |  | 525 |  |  | 14/10/2026 | 16/10/2026 |  |  | 525 |  | 525
ADIDAS | 0903156320-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1051 | 30/09/2026 | 1051 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156320 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 1051 |  | 1051 |  |  | 23/09/2026 | 25/09/2026 | 2026-11-09 | 2026-12-09 | 1051 | 822 | 229
ADIDAS | 0903156341-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 624 | 30/09/2026 | 624 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156341 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 624 |  | 624 |  |  | 22/09/2026 | 23/09/2026 | 2026-10-09 | 2026-12-09 | 624 | 623 | 1
ADIDAS | 0903156375-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 349 | 30/09/2026 | 349 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156375 KW2924 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 349 |  | 349 |  |  | 16/09/2026 | 18/09/2026 |  |  | 349 |  | 349
ADIDAS | 0903156407-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 741 | 30/09/2026 | 741 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156407 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 15/09/2026 | 16/09/2026 |  |  | 741 |  | 741 |  |  | 2026-11-09 | 2026-12-09 |  |  | 741 |  | 741
ADIDAS | 0903156431-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 1249 | 30/09/2026 | 1249 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156431 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 17/09/2026 | 17/09/2026 |  |  | 1249 |  | 1249 |  |  | 14/09/2026 | 14/09/2026 |  |  | 1249 |  | 1249
ADIDAS | 0903156487-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156487 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 110 |  | 110 |  |  | 30/09/2026 | 30/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903156511-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903156511 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 29/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 26/09/2026 | 2026-01-09 | 2026-01-09 | 100 | 100
ADIDAS | 0903156518-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 122 | 2026-07-10 | 122 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156518 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 122 |  | 122 |  |  | 24/09/2026 | 24/09/2026 |  |  | 122 |  | 122
ADIDAS | 0903156528-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 451 | 26/08/2026 | 451 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 1st Art (TC 10 pcs) 659018 | HT SUB PROCESS_V1 | 0903156528 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 14/08/2026 | 13/08/2026 | 20/08/2026 | 451 | 451 |  |  |  | 2026-11-08 | 2026-12-08 | 28/07/2026 | 29/07/2026 | 451 | 451 |  |  |  | 2026-10-08 | 2026-11-08 | 28/07/2026 | 29/07/2026 | 451 | 451
ADIDAS | 0903156531-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903156531 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300
ADIDAS | 0903156547-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 800 | 15/10/2026 | 800 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903156547 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 800 |  | 800 |  |  | 26/10/2026 | 27/10/2026 |  |  | 800 |  | 800 |  |  | 24/10/2026 | 26/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903156570-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 500 | 26/08/2026 | 500 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903156570 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 26/08/2026 | 13/08/2026 | 20/08/2026 | 500 | 500 |  |  |  | 2026-11-08 | 21/08/2026 | 28/07/2026 | 30/07/2026 | 500 | 500 |  |  |  | 2026-10-08 | 20/08/2026 | 28/07/2026 | 30/07/2026 | 500 | 500
ADIDAS | 0903156595-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 150 | 30/09/2026 | 150 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156595 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | W 3S FT OH PT |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 150 |  | 150 |  |  | 2026-02-10 | 2026-03-10 | 20/08/2026 | 28/08/2026 | 150 | 140 | 10
ADIDAS | 0903156613-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 540 | 15/10/2026 | 540 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Mexico). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903156613 KE6716 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 540 |  | 540 |  |  | 14/10/2026 | 17/10/2026 |  |  | 540 |  | 540 |  |  | 13/10/2026 | 16/10/2026 |  |  | 540 |  | 540
ADIDAS | 0903156885-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 416 | 30/09/2026 | 416 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Airowes). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156885 KV7863 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 24/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 416 |  | 416 |  |  | 21/09/2026 | 22/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903157062-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 124 | 15/10/2026 | 124 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157062 KU8797 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 124 |  | 124 |  |  | 2026-01-10 | 2026-01-10 |  |  | 124 |  | 124
ADIDAS | 0903157093-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 148 | 15/10/2026 | 148 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157093 KW8934 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 148 |  | 148 |  |  | 30/09/2026 | 30/09/2026 |  |  | 148 |  | 148
ADIDAS | 0903157098-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903157098 KX0126 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-10-10 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 128 |  | 128 |  |  | 2026-07-10 | 2026-07-10 | 2026-10-08 | 2026-11-08 | 128 | 84 | 44
ADIDAS | 0903157127-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 273 | 30/09/2026 | 273 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | (04/08/2026) | 29/09: ex-fty (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157127 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 22/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 273 |  | 273 |  |  | 18/09/2026 | 18/09/2026 |  |  | 273 |  | 273
ADIDAS | 0903157647-1 KE8424 | BLACK | 120D | S2608MR0906A | 890 | 2026-02-10 | 890 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903157647 KE8424 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 890 |  | 890 |  |  | 28/09/2026 | 29/09/2026 |  |  | 890 |  | 890 |  |  | 25/09/2026 | 26/09/2026 |  |  | 890 |  | 890
ADIDAS | 0903157667-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 1500 | 2026-12-09 | 1500 | SA | SA26/06/2026 | G2Q,G2S,G2T | SHORTS | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 678002 | PRINT L1 SUB PROCESS_V3 | 0903157667 JC9346 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-09 | M LIN SJ SHO |  | SS27 | 2026-02-09 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1500 | 1500 |  |  |  | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-10-09 | 1500 | 1500
ADIDAS | 0903157692-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1000 | 26/08/2026 | 1000 | SA | SA26/06/2026 | G2S | SHORTS | G2 | (08/08/2026) | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157692 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 20/08/2026 | 26/08/2026 | 1000 | 1000 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-01-08 | 2026-08-08 | 1000 | 1000
ADIDAS | 0903157724-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 800 | 26/08/2026 | 800 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157724 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/08/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 24/08/2026 | 26/08/2026 | 24/08/2026 | 26/08/2026 | 800 | 800 |  |  |  | 19/08/2026 | 20/08/2026 | 2026-01-08 | 19/08/2026 | 800 | 800
ADIDAS | 0903157733-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 198 | 15/10/2026 | 198 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903157733 KD0738 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 22/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 24/10/2026 |  |  | 198 |  | 198 |  |  | 19/10/2026 | 21/10/2026 |  |  | 198 |  | 198 |  |  | 13/10/2026 | 15/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903157738-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 306 | 23/09/2026 | 306 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157738 JD5302 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 306 | 306 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 27/08/2026 | 306 | 306
ADIDAS | 0903157745-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | SHORTS | G3 | ok | ok | 23/09: ex-fty. T2 Gistex, PI Date 10-Aug, actual receives 22-Aug. 1st Art (TC 10 pcs) 678002 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0903157745 JE9016 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-06-10 | M LIN CHELSEA |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1500 |  | 1500 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1500 |  | 1500
ADIDAS | 0903157768-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157768 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 303 |  | 303 |  |  | 14/10/2026 | 16/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903157773-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 2500 | 26/08/2026 | 2500 | AN | AN26/06/2026 | G2E | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | PRINT L1 SUB PROCESS_V3 | 0903157773 JG8639 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W LIN FT SHO |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 26/08/2026 | 2500 | 2500 |  |  |  | 13/08/2026 | 20/08/2026 | 2026-12-08 | 31/08/2026 | 2500 | 2500
ADIDAS | 0903157804-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 118 | 30/09/2026 | 118 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903157804 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 19/09/2026 | 24/09/2026 |  |  | 118 |  | 118 |  |  | 16/09/2026 | 21/09/2026 | 31/08/2026 | 2026-05-09 | 118 | 104 | 14
ADIDAS | 0903157810-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157810 JE0052 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 18/09/2026 | W 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 17/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903157899-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 108 | 15/10/2026 | 108 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | (Airowes). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157899 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 108 |  | 108 |  |  | 17/10/2026 | 17/10/2026 |  |  | 108 |  | 108
ADIDAS | 0903157953-1 KE8424 | BLACK | 120D | S2608MR0906A | 489 | 29/09/2026 | 489 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903157953 KE8424 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess LS M BLACK |  | SS27-TI | 17/09/2026 | 18/09/2026 |  |  | 489 |  | 489 |  |  | 14/09/2026 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 489 | 246 | 243 |  | 246 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 15/09/2026 | 489 | 432 | 57 |  | 428
ADIDAS | 0903158261-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903158261 JG8639 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 134 | 166 |  |  | 2026-11-09 | 2026-11-09 | 2026-03-08 | 24/08/2026 | 300 | 300
ADIDAS | 0903158265-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 11222 | 30/09/2026 | 11222 | AT | AT26/06/2026 | G2C | T-SHIRT | G2 | ok | (30/07/2026) | 25/09: ex-fty 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903158265 KA5089 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | MINI EMB T |  | SS27 | 21/09/2026 | 29/09/2026 |  |  | 11222 |  | 11222 |  |  | 17/09/2026 | 25/09/2026 | 2026-11-09 | 2026-11-09 | 11222 | 123 | 11099 |  |  | 15/09/2026 | 23/09/2026 | 2026-07-09 | 14/09/2026 | 11222 | 142 | 11080 |  | 11
ADIDAS | 0903158297-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 482 | 15/10/2026 | 482 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158297 JE0052 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | W 3S FT FZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 482 |  | 482 |  |  | 27/10/2026 | 28/10/2026 |  |  | 482 |  | 482
ADIDAS | 0903158492-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 332 | 15/10/2026 | 332 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158492 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 332 |  | 332 |  |  | 17/10/2026 | 20/10/2026 |  |  | 332 |  | 332
ADIDAS | 0903158495-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158495 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 2026-09-10 | 29/10/2026 |  |  | 101 |  | 101 |  |  | 2026-06-10 | 26/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903158663-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 107 | 2026-07-10 | 107 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158663 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 107 |  | 107 |  |  | 19/09/2026 | 21/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903158691-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 118 | 2026-07-10 | 118 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158691 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 26/09/2026 | 26/09/2026 |  |  | 118 |  | 118 |  |  | 23/09/2026 | 23/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903158714-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 300 | 29/09/2026 | 300 | AN | AN26/06/2026 | G2R | SHORTS | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158714 LG9660 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 15/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 |  |  | 300 |  | 300
ADIDAS | 0903158739-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 332 | 15/10/2026 | 332 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158739 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 13/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 332 |  | 332 |  |  | 2026-09-10 | 2026-12-10 |  |  | 332 |  | 332
ADIDAS | 0903158761-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 239 | 23/09/2026 | 239 | SA | SA26/06/2026 | G3C | PANTS | G3 | (08/08/2026(13)) |  | 18/09: ex-fty 806020 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158761 JW7177 | 2026-10-09 | KAHATEX CIJERAH | HONGKONG | SEA | 28/07/2026 | W 3S FT OH PT |  | SS27 | 28/07/2026 | 2026-04-08 | 29/07/2026 | 29/07/2026 | 239 | 239 |  |  |  | 23/07/2026 | 30/07/2026 | 28/07/2026 | 29/07/2026 | 239 | 239
ADIDAS | 0903158798-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 229 | 15/10/2026 | 229 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158798 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 13/10/2026 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 229 |  | 229 |  |  | 2026-09-10 | 2026-12-10 |  |  | 229 |  | 229
ADIDAS | 0903158825-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 451 | 15/10/2026 | 451 | SA | SA26/06/2026 | G3B | PANTS | G3 | (28/08/2026) | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158825 LE8181 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 451 |  | 451 |  |  | 2026-12-10 | 13/10/2026 |  |  | 451 |  | 451
ADIDAS | 0903158829-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | (17/07/2026) | 25/09: ex-fty 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158829 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | DICE TEE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 415 |  | 415 |  |  | 16/09/2026 | 17/09/2026 |  |  | 415 |  | 415 |  |  | 14/09/2026 | 15/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903158907-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 245 | 30/09/2026 | 245 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158907 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PDX HBR TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 245 |  | 245 |  |  | 17/09/2026 | 18/09/2026 | 2026-11-08 | 2026-11-08 | 245 | 244 | 1
ADIDAS | 0903158935-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158935 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PIZZA TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 415 |  | 415 |  |  | 30/09/2026 | 2026-01-10 | 2026-07-08 | 19/08/2026 | 415 | 414 | 1
ADIDAS | 0903158955-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 187 | 30/09/2026 | 187 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158955 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PDX HBR TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 187 |  | 187 |  |  | 17/09/2026 | 18/09/2026 | 2026-11-08 | 15/08/2026 | 187 | 187
ADIDAS | 0903158980-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 1203 | 30/09/2026 | 1203 | AN | AN26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158980 KS2152 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | LA PALMS TEE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 1203 |  | 1203 |  |  | 15/09/2026 | 16/09/2026 | 2026-08-09 | 2026-12-09 | 1203 | 1020 | 183
ADIDAS | 0903159040-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 862 | 30/09/2026 | 862 | ID | ID26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 22/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159040 KR2006 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | SPORT GOODS T |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 862 |  | 862 |  |  | 17/09/2026 | 17/09/2026 | 2026-08-09 | 2026-11-09 | 862 | 838 | 24
ADIDAS | 0903159157-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159157 KW8932 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 30/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903159180-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 274 | 15/10/2026 | 274 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159180 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 274 |  | 274 |  |  | 2026-01-10 | 2026-02-10 |  |  | 274 |  | 274
ADIDAS | 0903159200-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 346 | 15/10/2026 | 346 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159200 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 346 |  | 346 |  |  | 2026-01-10 | 2026-01-10 |  |  | 346 |  | 346
ADIDAS | 0903159205-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159205 LC8884 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 128 |  | 128 |  |  | 2026-07-10 | 2026-08-10 | 2026-11-08 | 2026-11-08 | 128 | 126 | 2
ADIDAS | 0903159207-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 257 | 15/10/2026 | 257 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Airowes). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903159207 KA2571 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-02-11 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 257 |  | 257 |  |  | 29/10/2026 | 30/10/2026 |  |  | 257 |  | 257 |  |  | 23/10/2026 | 24/10/2026 |  |  | 257 |  | 257
ADIDAS | 0903159219-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 1058 | 26/08/2026 | 1058 | AN | AN26/06/2026 | G1H | JACKET | G1 | (29/07/2026) | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159219 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 14/08/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 26/08/2026 | 1058 | 1058 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-12-08 | 2026-05-09 | 1058 | 1058
ADIDAS | 0903159239-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 238 | 15/10/2026 | 238 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159239 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 238 |  | 238 |  |  | 2026-01-10 | 2026-02-10 |  |  | 238 |  | 238
ADIDAS | 0903159248-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 640 | 28/08/2026 | 640 | AN | AN26/06/2026 | G3A,G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159248 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-08 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-11-08 | 19/08/2026 | 2026-11-08 | 20/08/2026 | 640 | 640 |  |  |  | 2026-06-08 | 13/08/2026 | 2026-04-08 | 20/08/2026 | 640 | 640
ADIDAS | 0903159269-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 1861 | 28/08/2026 | 1861 | AN | AN26/06/2026 | G3H | PANTS | G3 | ok | ok | 28/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159269 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 19/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 1861 | 1861 |  |  |  | 13/08/2026 | 20/08/2026 | 15/08/2026 | 24/08/2026 | 1861 | 1861
ADIDAS | 0903159282-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 132 | 15/10/2026 | 132 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159282 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 132 |  | 132 |  |  | 24/10/2026 | 26/10/2026 |  |  | 132 |  | 132
ADIDAS | 0903159299-1 KZ3229 | GREY FIVE F17/WHITE | 90D | S2754WESS703WV-MTF | 597 | 26/08/2026 | 597 | AN | AN26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/08: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, actual receives 28-May (PO 26022031). T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159299 KZ3229 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/08/2026 | W 13S WV BER SHO GREY FIVE F17/WHITE |  | SS27 | 19/08/2026 | 24/08/2026 | 19/08/2026 | 21/08/2026 | 597 | 597 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-10-08 | 21/08/2026 | 597 | 597
ADIDAS | 0903159308-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 102 | 15/10/2026 | 102 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (Cargoport). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159308 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 15/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 102 |  | 102 |  |  | 2026-12-10 | 13/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903159320-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 222 | 30/09/2026 | 222 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650036 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159320 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-02-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 222 |  | 222 |  |  | 29/09/2026 | 30/09/2026 | 28/08/2026 | 28/08/2026 | 222 | 221 | 1
ADIDAS | 0903159340-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 313 | 30/09/2026 | 313 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 838103 | PRINT L1 SUB PROCESS_V3 | 0903159340 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 22/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 22/09/2026 | 22/09/2026 |  |  | 313 |  | 313 |  |  | 18/09/2026 | 18/09/2026 |  |  | 313 |  | 313
ADIDAS | 0903159374-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 100 | 15/10/2026 | 100 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903159374 KW8932 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903159551-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159551 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 | 2026-02-09 | 2026-10-09 | 300 | 92 | 208
ADIDAS | 0903159571-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 2026-12-09 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159571 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 2026-05-09 | 29/08/2026 | 31/08/2026 | 522 | 522 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-08-09 | 522 | 522
ADIDAS | 0903159587-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 30/09/2026 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159587 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 18/09/2026 | 31/08/2026 | 31/08/2026 | 522 | 215 | 307 |  |  | 27/08/2026 | 15/09/2026 | 27/08/2026 | 2026-09-09 | 522 | 518 | 4
ADIDAS | 0903159856-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 606 | 30/09/2026 | 606 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 630001 | PAD+HT SUB PROCESS_V3 | 0903159856 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 21/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 606 |  | 606 |  |  | 17/09/2026 | 18/09/2026 |  |  | 606 |  | 606 |  |  | 16/09/2026 | 17/09/2026 |  |  | 606 |  | 606
ADIDAS | 0903159964-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 607 | 15/10/2026 | 607 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903159964 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 607 |  | 607 |  |  | 29/09/2026 | 30/09/2026 |  |  | 607 |  | 607 |  |  | 28/09/2026 | 29/09/2026 |  |  | 607 |  | 607
ADIDAS | 0903159994-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 328 | 15/10/2026 | 328 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159994 KX7716 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 29/09/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 29/09/2026 | 2026-03-10 |  |  | 328 |  | 328 |  |  | 25/09/2026 | 30/09/2026 |  |  | 328 |  | 328
ADIDAS | 0903160003-1 KA3530 | BLACK | 105D | S2650MTR402 | 237 | 15/10/2026 | 237 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903160003 KA3530 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | WE FR T BLACK |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 237 |  | 237 |  |  | 28/09/2026 | 29/09/2026 |  |  | 237 |  | 237 |  |  | 26/09/2026 | 28/09/2026 |  |  | 237 |  | 237
ADIDAS | 0903160021-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 328 | 15/10/2026 | 328 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160021 KX7715 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 24/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 24/09/2026 | 29/09/2026 |  |  | 328 |  | 328 |  |  | 21/09/2026 | 25/09/2026 |  |  | 328 |  | 328
ADIDAS | 0903160371-1 KA0246 | BLACK | 90D | S2608WR0902 | 1181 | 15/10/2026 | 1181 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516267 | PAD+HT SUB PROCESS_V3 | 0903160371 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 1181 |  | 1181 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1181 |  | 1181 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1181 |  | 1181
ADIDAS | 0903160415-1 KA0246 | BLACK | 90D | S2608WR0902 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516404 | PAD+HT SUB PROCESS_V3 | 0903160415 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903160834-1 LE8187 | BLACK | 105D | S2754MAS513 | 217 | 15/10/2026 | 217 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160834 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 21/10/2026 | M SL WV TP PT BLACK |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 217 |  | 217 |  |  | 17/10/2026 | 17/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903161081-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (KN GLT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903161081 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903161114-1 KS0802 | TECH INDIGO S20/WHITE | 105D | S2608WR0601B | 7 | 15/10/2026 | 7 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903161114 KS0802 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | adi365 Short W TECH INDIGO S20/WHITE |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 7 |  | 7 |  |  | 29/10/2026 | 31/10/2026 |  |  | 7 |  | 7 |  |  | 28/10/2026 | 30/10/2026 |  |  | 7 |  | 7
ADIDAS | 0903161148-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 5352 | 15/10/2026 | 5352 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Libolon, PI Date 22-Jul. actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 29-Jul. T2 Formosa, PI Date 09-Jun, actual receives 22-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161148 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 23/10/2026 | 2026-02-11 |  |  | 5352 |  | 5352 |  |  | 20/10/2026 | 29/10/2026 |  |  | 5352 |  | 5352
ADIDAS | 0903161212-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 8768 | 30/09/2026 | 8768 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161212 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 23/09/2026 | 2026-05-10 |  |  | 8768 |  | 8768 |  |  | 19/09/2026 | 2026-01-10 |  |  | 8768 |  | 8768
ADIDAS | 0903161277-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 141 | 30/09/2026 | 141 | AN | AN26/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 21/09: ex-fty 516342 | PRINT L3+PAD SUB PROCESS_V3 | 0903161277 LC8882 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T BLACK |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 141 |  | 141 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-08 | 13/08/2026 | 141 | 141
ADIDAS | 0903162196-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 313 | 23/09/2026 | 313 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 23/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162196 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 313 | 313 |  |  | 24 | 2026-05-09 | 2026-10-09 | 14/08/2026 | 31/08/2026 | 313 | 297 | 16
ADIDAS | 0903162215-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 846 | 30/09/2026 | 846 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162215 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 19/09/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 19/09/2026 | 22/09/2026 |  |  | 846 |  | 846 |  |  | 16/09/2026 | 18/09/2026 |  |  | 846 |  | 846
ADIDAS | 0903162243-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 321 | 15/10/2026 | 321 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162243 LE8188 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 16/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 321 |  | 321 |  |  | 13/10/2026 | 14/10/2026 |  |  | 321 |  | 321
ADIDAS | 0903162307-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162307 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-05-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-05-11 | 2026-06-11 |  |  | 153 |  | 153 |  |  | 2026-02-11 | 2026-03-11 |  |  | 153 |  | 153 |  |  | 31/10/2026 | 2026-02-11 |  |  | 153 |  | 153
ADIDAS | 0903162341-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 205 | 15/10/2026 | 205 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162341 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 205 |  | 205 |  |  | 29/09/2026 | 30/09/2026 |  |  | 205 |  | 205 |  |  | 28/09/2026 | 29/09/2026 |  |  | 205 |  | 205
ADIDAS | 0903162369-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 1229 | 30/09/2026 | 1229 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 23/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162369 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 19/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 1229 |  | 1229 |  |  | 16/09/2026 | 19/09/2026 |  |  | 1229 |  | 1229
ADIDAS | 0903162420-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 100 | 15/10/2026 | 100 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162420 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903162500-1 LC6341 | BLACK | 90D | S27GMGFX130 | 246 | 30/09/2026 | 246 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 630001 | PRINT L3+PAD SUB PROCESS_V3 | 0903162500 LC6341 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 246 |  | 246 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 2026-09-09 | 246 | 226 | 20
ADIDAS | 0903162572-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162572 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 153 |  | 153 |  |  | 23/09/2026 | 24/09/2026 |  |  | 153 |  | 153 |  |  | 22/09/2026 | 23/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903162593-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 624 | 15/10/2026 | 624 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162593 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-05-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-05-11 | 2026-06-11 |  |  | 624 |  | 624 |  |  | 2026-02-11 | 2026-03-11 |  |  | 624 |  | 624 |  |  | 31/10/2026 | 2026-02-11 |  |  | 624 |  | 624
ADIDAS | 0903162621-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 512 | 15/10/2026 | 512 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162621 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M SERENO SHO WHITE |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 512 |  | 512 |  |  | 23/09/2026 | 24/09/2026 |  |  | 512 |  | 512 |  |  | 22/09/2026 | 23/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903162642-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 195 | 30/09/2026 | 195 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 814006 | PRINT L1 SUB PROCESS_V3 | 0903162642 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 22/09/2026 | LFC GR TEE1 BLACK |  | SS27-STX | 22/09/2026 | 22/09/2026 |  |  | 195 |  | 195 |  |  | 18/09/2026 | 18/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903163142-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 344 | 15/10/2026 | 344 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903163142 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 30/09/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 344 |  | 344 |  |  | 26/09/2026 | 26/09/2026 |  |  | 344 |  | 344
ADIDAS | 0903163156-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 8 | 15/10/2026 | 8 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163156 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 8 |  | 8 |  |  | 14/10/2026 | 17/10/2026 |  |  | 8 |  | 8 |  |  | 13/10/2026 | 16/10/2026 |  |  | 8 |  | 8
ADIDAS | 0903163494-1 KE6899 | BLACK | 105D | S2608WR0601B | 1139 | 15/10/2026 | 1139 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163494 KE6899 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-11 | adi365 Short W BLACK |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 1139 |  | 1139 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1139 |  | 1139 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1139 |  | 1139
ADIDAS | 0903163534-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 688 | 15/10/2026 | 688 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163534 KE6716 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 688 |  | 688 |  |  | 17/10/2026 | 20/10/2026 |  |  | 688 |  | 688 |  |  | 16/10/2026 | 19/10/2026 |  |  | 688 |  | 688
ADIDAS | 0903163589-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 336 | 30/09/2026 | 336 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 22/09: ex-fty. Waiting fabric (KN GLT). T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 650010 | PRINT L2+HT SUB PROCESS_V3 | 0903163589 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 336 |  | 336 |  |  | 19/09/2026 | 21/09/2026 |  |  | 336 |  | 336 |  |  | 18/09/2026 | 19/09/2026 |  |  | 336 |  | 336
ADIDAS | 0903163782-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 1st Art (TC 10 pcs) 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903163782 JM1772 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903164418-1 KW5050 | MAROON | 90D | F2625M101 | 230 | 15/10/2026 | 230 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164418 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | ESS REG |  | SS27-STX | 2026-09-10 | 2026-09-10 |  |  | 230 |  | 230 |  |  | 2026-06-10 | 2026-06-10 |  |  | 230 |  | 230
ADIDAS | 0903164544-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 214 | 15/10/2026 | 214 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164544 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/09/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 214 |  | 214 |  |  | 26/09/2026 | 26/09/2026 |  |  | 214 |  | 214
ADIDAS | 0903164569-1 KW5050 | MAROON | 90D | F2625M101 | 170 | 2026-07-10 | 170 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164569 KW5050 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | ESS REG |  | SS27-STX | 2026-01-10 | 2026-01-10 |  |  | 170 |  | 170 |  |  | 28/09/2026 | 28/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903164595-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 416 | 2026-07-10 | 416 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903164595 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 416 |  | 416 |  |  | 19/09/2026 | 21/09/2026 |  |  | 416 |  | 416 |  |  | 18/09/2026 | 19/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903164629-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 808 | 2026-07-10 | 808 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164629 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 29/09/2026 |  |  | 808 |  | 808 |  |  | 24/09/2026 | 25/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903164697-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 133 | 2026-07-10 | 133 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164697 IN1172 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 133 | 133 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 133 | 133 |  |  |  | 2026-11-08 | 26/08/2026 | 15/07/2026 | 23/07/2026 | 133 | 133
ADIDAS | 0903164732-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 264 | 2026-07-10 | 264 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164732 IN1156 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 264 | 264 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 264 | 264 |  |  |  | 2026-11-08 | 26/08/2026 | 13/07/2026 | 27/07/2026 | 264 | 264
ADIDAS | 0903164830-1 KT4840 | ONIX | 90D | S2408MR1600 | 102 | 30/09/2026 | 102 | SA | SA26/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 830009 | HT SUB PROCESS_V1 | 0903164830 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 102 |  | 102 |  |  | 26/09/2026 | 28/09/2026 |  |  | 102 |  | 102 |  |  | 25/09/2026 | 26/09/2026 | 14/09/2026 | 14/09/2026 | 102 | 24 | 78 |  | 24
ADIDAS | 0903164987-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 110 | 2026-07-10 | 110 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 800187 | EMBRO SUB PROCESS_V1 | 0903164987 KT7396 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 110 |  | 110 |  |  | 26/09/2026 | 26/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903165005-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 135 | 15/10/2026 | 135 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165005 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | M SL WV TP PT BLACK |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 135 |  | 135 |  |  | 15/10/2026 | 17/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903165033-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 408 | 2026-07-10 | 408 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903165033 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 408 |  | 408 |  |  | 22/09/2026 | 23/09/2026 |  |  | 408 |  | 408 |  |  | 21/09/2026 | 22/09/2026 |  |  | 408 |  | 408
ADIDAS | 0903165054-1 KW5050 | MAROON | 90D | F2625M101 | 447 | 15/10/2026 | 447 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903165054 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | ESS REG |  | SS27-STX | 2026-01-10 | 2026-01-10 |  |  | 447 |  | 447 |  |  | 28/09/2026 | 28/09/2026 |  |  | 447 |  | 447
ADIDAS | 0903165070-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 309 | 30/09/2026 | 309 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903165070 LD0908 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309 |  |  | 18/09/2026 | 19/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903165109-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 495 | 15/10/2026 | 495 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165109 LE8187 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M SL WV TP PT BLACK |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 495 |  | 495 |  |  | 15/10/2026 | 17/10/2026 |  |  | 495 |  | 495
ADIDAS | 0903165167-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 900 | 30/09/2026 | 900 | SA | SA26/06/2026 | G1C | JACKET | G1 | (29/07/2026) | ok | 21/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903165167 JM1772 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M SL WV TT |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 19/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903165226-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 999 | 30/09/2026 | 999 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165226 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 999 |  | 999 |  |  | 2026-06-10 | 2026-07-10 |  |  | 999 |  | 999
ADIDAS | 0903165306-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 168 | 2026-07-10 | 168 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165306 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 168 |  | 168 |  |  | 2026-08-10 | 2026-09-10 |  |  | 168 |  | 168
ADIDAS | 0903165362-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165362 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903165425-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 315 | 30/09/2026 | 315 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165425 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 315 |  | 315 |  |  | 2026-01-10 | 2026-02-10 |  |  | 315 |  | 315
ADIDAS | 0903165470-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 1248 | 30/09/2026 | 1248 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165470 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 16/09/2026 | 17/09/2026 |  |  | 1248 |  | 1248 |  |  | 2026-12-09 | 14/09/2026 |  |  | 1248 |  | 1248
ADIDAS | 0903165506-1 LC7300 | WHITE | 90D | S2725M926A | 318 | 2026-07-10 | 318 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903165506 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL WHITE |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 318 |  | 318 |  |  | 26/09/2026 | 28/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903165542-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 517 | 2026-07-10 | 517 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903165542 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 517 |  | 517 |  |  | 19/09/2026 | 21/09/2026 |  |  | 517 |  | 517
ADIDAS | 0903165585-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 1245 | 30/09/2026 | 1245 | SI | SI26/06/2026 | G1K | POLO SHIRT | G1 | (12/08/2026) | ok | 25/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165585 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 25/09/2026 |  |  | 1245 |  | 1245 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1245 |  | 1245
ADIDAS | 0903165644-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 243 | 23/09/2026 | 243 | AN | AN26/06/2026 | G1Q | T-SHIRT | G1 | (28/07/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903165644 KX0123 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T WHITE |  | SS27 | 15/09/2026 | 16/09/2026 | 15/09/2026 | 15/09/2026 | 243 | 172 | 71 |  |  | 2026-11-09 | 2026-12-09 | 31/07/2026 | 2026-08-08 | 243 | 243
ADIDAS | 0903166391-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903166391 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-12-09 | 17/09/2026 | 2026-12-09 | 15/09/2026 | 300 | 253 | 47 |  |  | 2026-09-09 | 14/09/2026 | 29/08/2026 | 2026-10-09 | 300 | 296 | 4
ADIDAS | 0903166456-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 704 | 2026-07-10 | 704 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903166456 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 704 |  | 704 |  |  | 22/09/2026 | 23/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903166659-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 319 | 2026-07-10 | 319 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | PRINT L1 SUB PROCESS_V3 | 0903166659 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 319 |  | 319 |  |  | 26/09/2026 | 28/09/2026 |  |  | 319 |  | 319
ADIDAS | 0903167086-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 523 | 15/10/2026 | 523 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 516199 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167086 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 523 |  | 523 |  |  | 21/10/2026 | 22/10/2026 |  |  | 523 |  | 523 |  |  | 15/10/2026 | 16/10/2026 |  |  | 523 |  | 523
ADIDAS | 0903167126-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 1460 | 15/10/2026 | 1460 | AN | AN26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167126 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 21/10/2026 | 23/10/2026 |  |  | 1460 |  | 1460 |  |  | 17/10/2026 | 20/10/2026 |  |  | 1460 |  | 1460 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1460 |  | 1460
ADIDAS | 0903167166-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167166 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-01-10 |  |  | 271 |  | 271
ADIDAS | 0903167196-1 KZ2456 | SILVER BLUE S27/HALO SILVER S21 | 105D | S2650MTR804C | 182 | 15/10/2026 | 182 | AN | AN26/06/2026 | G1M | T-SHIRT | G1 |  | ok | Waiting fabric. T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903167196 KZ2456 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 29/10/2026 | TECHESS TEE SILVER BLUE S27/HALO SILVER S21 |  | SS27-TI | 29/10/2026 | 29/10/2026 |  |  | 182 |  | 182 |  |  | 27/10/2026 | 27/10/2026 |  |  | 182 |  | 182 |  |  | 26/10/2026 | 26/10/2026 |  |  | 182 |  | 182
ADIDAS | 0903167198-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 116 | 15/10/2026 | 116 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167198 LF0718 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M SL WV OH PT BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 116 |  | 116 |  |  | 2026-08-10 | 2026-09-10 |  |  | 116 |  | 116
ADIDAS | 0903167226-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 331 | 21/08/2026 | 331 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 21/08: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 600000 | HT SUB PROCESS_V1 | 0903167226 IN1172 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 16/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 331 | 331 |  |  |  | 14/07/2026 | 24/07/2026 | 14/07/2026 | 20/07/2026 | 331 | 331 |  |  |  | 13/07/2026 | 23/07/2026 | 14/07/2026 | 20/07/2026 | 331 | 331
ADIDAS | 0903167227-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 410 | 2026-07-10 | 410 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903167227 KT7396 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 410 |  | 410 |  |  | 26/09/2026 | 28/09/2026 |  |  | 410 |  | 410
ADIDAS | 0903167268-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 415 | 30/09/2026 | 415 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167268 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | LV COLLEGIATE T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 415 |  | 415 |  |  | 2026-01-10 | 2026-02-10 | 2026-10-09 | 2026-10-09 | 415 | 394 | 21
ADIDAS | 0903167275-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 267 | 2026-07-10 | 267 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167275 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 267 |  | 267 |  |  | 23/09/2026 | 24/09/2026 |  |  | 267 |  | 267
ADIDAS | 0903167287-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 319 | 21/08/2026 | 319 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | (18/04/2026) |  | 21/08: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 600000 | HT SUB PROCESS_V1 | 0903167287 IN1156 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 22/07/2026 | 20/07/2026 | 21/07/2026 | 319 | 319 |  |  |  | 16/07/2026 | 20/07/2026 | 14/07/2026 | 16/07/2026 | 319 | 319 |  |  |  | 15/07/2026 | 17/07/2026 | 13/07/2026 | 16/07/2026 | 319 | 319
ADIDAS | 0903167316-1 KY5866 | BLACK | 90D | S2750MTR052 | 139 | 15/10/2026 | 139 | SI | SI26/06/2026 | G2C | SHORTS | G2 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903167316 KY5866 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D18T ESS SHORTS BLACK |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 139 |  | 139 |  |  | 2026-03-10 | 2026-05-10 |  |  | 139 |  | 139 |  |  | 2026-02-10 | 2026-03-10 |  |  | 139 |  | 139
ADIDAS | 0903167324-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 255 | 15/10/2026 | 255 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903167324 KD0738 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 22/10/2026 | 24/10/2026 |  |  | 255 |  | 255 |  |  | 19/10/2026 | 21/10/2026 |  |  | 255 |  | 255 |  |  | 13/10/2026 | 15/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903167339-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 673 | 2026-07-10 | 673 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167339 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 28/09/2026 | 28/09/2026 |  |  | 673 |  | 673 |  |  | 24/09/2026 | 24/09/2026 |  |  | 673 |  | 673
ADIDAS | 0903167346-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 1269 | 26/08/2026 | 1269 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 24/08: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). (received qty more than MCAF qty). 600000 | HT SUB PROCESS_V1 | 0903167346 IN1157 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 22/07/2026 | 28/07/2026 | 22/07/2026 | 24/07/2026 | 1269 | 1269 |  |  |  | 20/07/2026 | 24/07/2026 | 21/07/2026 | 22/07/2026 | 1269 | 1269 |  |  |  | 17/07/2026 | 23/07/2026 | 15/07/2026 | 21/07/2026 | 1269 | 1269
ADIDAS | 0903167370-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 210 | 15/10/2026 | 210 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903167370 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 210 |  | 210 |  |  | 2026-01-10 | 2026-02-10 |  |  | 210 |  | 210
ADIDAS | 0903167433-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 501 | 2026-07-10 | 501 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167433 KW8934 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 26/09/2026 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 26/09/2026 | 26/09/2026 |  |  | 501 |  | 501 |  |  | 23/09/2026 | 23/09/2026 |  |  | 501 |  | 501
ADIDAS | 0903167457-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 405 | 2026-07-10 | 405 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167457 KW8932 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 26/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 26/09/2026 | 28/09/2026 |  |  | 405 |  | 405 |  |  | 23/09/2026 | 24/09/2026 |  |  | 405 |  | 405
ADIDAS | 0903167485-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 130 | 2026-07-10 | 130 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167485 KW9039 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 23/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 130 |  | 130 |  |  | 19/09/2026 | 21/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903167564-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 652 | 15/10/2026 | 652 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167564 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 652 |  | 652 |  |  | 22/09/2026 | 23/09/2026 |  |  | 652 |  | 652 |  |  | 21/09/2026 | 22/09/2026 |  |  | 652 |  | 652
ADIDAS | 0903167589-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 554 | 15/10/2026 | 554 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167589 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 554 |  | 554 |  |  | 29/09/2026 | 30/09/2026 |  |  | 554 |  | 554
ADIDAS | 0903167678-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167678 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903167694-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 362 | 15/10/2026 | 362 | SI | SI26/06/2026 | G3I | PANTS | G3 | (28/08/2026) | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 04-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167694 LE8188 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 362 |  | 362 |  |  | 13/10/2026 | 14/10/2026 |  |  | 362 |  | 362
ADIDAS | 0903167696-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/09/2026 | 500 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167696 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 500 |  | 500 |  |  | 21/09/2026 | 22/09/2026 | 2026-12-09 | 2026-12-09 | 500 | 122 | 378
ADIDAS | 0903167722-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 754 | 15/10/2026 | 754 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167722 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 23/09/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 23/09/2026 | 24/09/2026 |  |  | 754 |  | 754 |  |  | 19/09/2026 | 21/09/2026 |  |  | 754 |  | 754 |  |  | 18/09/2026 | 19/09/2026 |  |  | 754 |  | 754
ADIDAS | 0903167723-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 517 | 15/10/2026 | 517 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167723 LE8188 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 517 |  | 517 |  |  | 14/10/2026 | 15/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903167736-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 356 | 2026-07-10 | 356 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877)., ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167736 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 356 |  | 356 |  |  | 2026-08-10 | 2026-09-10 |  |  | 356 |  | 356
ADIDAS | 0903167751-1 KW5050 | MAROON | 90D | F2625M101 | 2163 | 15/09/2026 | 2163 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 15/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO SUB PROCESS_V1 | 0903167751 KW5050 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-09 | ESS REG |  | SS27-STX | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 2163 | 1975 | 188 |  | 1226 | 2026-09-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 2163 | 2141 | 22 |  | 7
ADIDAS | 0903167776-1 KA4331 | BLACK | 90D | S2608MR0902 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 22/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 1st Art (TC 10 pcs) 516267 | PAD+HT SUB PROCESS_V3 | 0903167776 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 23/09/2026 | 25/09/2026 |  |  | 1200 |  | 1200 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1200 |  | 1200 |  |  | 18/09/2026 | 21/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903167792-1 KA4331 | BLACK | 90D | S2608MR0902 | 335 | 2026-07-10 | 335 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516400 | PAD+HT SUB PROCESS_V3 | 0903167792 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 335 |  | 335 |  |  | 22/09/2026 | 24/09/2026 |  |  | 335 |  | 335 |  |  | 21/09/2026 | 23/09/2026 |  |  | 335 |  | 335
ADIDAS | 0903167804-1 KW5050 | MAROON | 90D | F2625M101 | 334 | 15/10/2026 | 334 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903167804 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-10 | ESS REG |  | SS27-STX | 2026-09-10 | 2026-09-10 |  |  | 334 |  | 334 |  |  | 2026-06-10 | 2026-06-10 |  |  | 334 |  | 334
ADIDAS | 0903167883-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 262 | 15/10/2026 | 262 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167883 LD6542 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 262 |  | 262 |  |  | 13/10/2026 | 15/10/2026 |  |  | 262 |  | 262
ADIDAS | 0903167908-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 627 | 15/10/2026 | 627 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167908 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | W SL WV TT BLACK |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 627 |  | 627 |  |  | 23/10/2026 | 26/10/2026 |  |  | 627 |  | 627
ADIDAS | 0903167943-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 555 | 15/10/2026 | 555 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167943 KX7715 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 24/09/2026 | 29/09/2026 |  |  | 555 |  | 555 |  |  | 21/09/2026 | 25/09/2026 |  |  | 555 |  | 555
ADIDAS | 0903168109-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 26/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168109 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 400 | 400 |  |  | 22 | 2026-05-09 | 2026-10-09 | 2026-11-08 | 2026-07-09 | 400 | 368 | 32
ADIDAS | 0903168275-1 KA0246 | BLACK | 90D | S2608WR0902 | 339 | 2026-07-10 | 339 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 15-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903168275 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 339 |  | 339 |  |  | 22/09/2026 | 24/09/2026 |  |  | 339 |  | 339 |  |  | 21/09/2026 | 23/09/2026 |  |  | 339 |  | 339
ADIDAS | 0903168299-1 KA0246 | BLACK | 90D | S2608WR0902 | 608 | 15/10/2026 | 608 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903168299 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 608 |  | 608 |  |  | 2026-03-10 | 2026-06-10 |  |  | 608 |  | 608 |  |  | 2026-02-10 | 2026-05-10 |  |  | 608 |  | 608
ADIDAS | 0903168302-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 21/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168302 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903168327-1 KA0246 | BLACK | 90D | S2608WR0902 | 301 | 30/09/2026 | 301 | SI | SI26/06/2026 | G2S | SHORTS | G2 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168327 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 19/09/2026 | 21/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 19/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903168356-1 KA0246 | BLACK | 90D | S2608WR0902 | 314 | 2026-07-10 | 314 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168356 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 314 |  | 314 |  |  | 24/09/2026 | 25/09/2026 |  |  | 314 |  | 314 |  |  | 23/09/2026 | 24/09/2026 |  |  | 314 |  | 314
ADIDAS | 0903168388-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 186 | 30/09/2026 | 186 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168388 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 | 15/09/2026 | 15/09/2026 | 186 | 15 | 171 |  |  | 22/09/2026 | 23/09/2026 | 27/08/2026 | 2026-07-09 | 186 | 168 | 18
ADIDAS | 0903168468-1 KA4331 | BLACK | 90D | S2608MR0902 | 364 | 2026-07-10 | 364 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168468 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 364 |  | 364 |  |  | 24/09/2026 | 25/09/2026 |  |  | 364 |  | 364 |  |  | 23/09/2026 | 24/09/2026 |  |  | 364 |  | 364
ADIDAS | 0903169170-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 204 | 15/10/2026 | 204 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516443 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169170 KU8975 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 24/10/2026 | 27/10/2026 |  |  | 204 |  | 204 |  |  | 21/10/2026 | 23/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903169256-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 701 | 15/10/2026 | 701 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169256 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 24/10/2026 | 27/10/2026 |  |  | 701 |  | 701 |  |  | 21/10/2026 | 23/10/2026 |  |  | 701 |  | 701
ADIDAS | 0903169715-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 328 | 15/10/2026 | 328 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169715 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 328 |  | 328 |  |  | 30/09/2026 | 2026-01-10 |  |  | 328 |  | 328
ADIDAS | 0903169772-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169772 KY3734 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903169855-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 150 | 15/10/2026 | 150 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169855 KW9039 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 24/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 24/09/2026 | 25/09/2026 |  |  | 150 |  | 150 |  |  | 21/09/2026 | 22/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903169976-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 259 | 15/10/2026 | 259 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903169976 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 259 |  | 259 |  |  | 30/09/2026 | 2026-01-10 |  |  | 259 |  | 259
ADIDAS | 0903170085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 538 | 15/09/2026 | 538 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 14-Jul. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170085 LD5446 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-09-09 | 14/09/2026 | 538 | 538 |  |  | 33 | 2026-02-09 | 2026-10-09 | 2026-05-09 | 14/09/2026 | 538 | 527 | 11 |  | 8
ADIDAS | 0903170105-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 1240 | 15/09/2026 | 1240 | SA | SA26/06/2026 | G3E,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903170105 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-09 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-09 | 16/09/2026 | 2026-11-09 | 15/09/2026 | 1240 | 1240 |  |  | 295 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 1240 | 1240 |  |  | 151 | 2026-02-09 | 2026-07-09 | 2026-09-09 | 14/09/2026 | 1240 | 1240 |  |  | 140
ADIDAS | 0903170139-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 574 | 15/09/2026 | 574 | AN | AN26/06/2026 | G3A | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170139 LE8181 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 14/09/2026 | 2026-10-09 | 2026-11-09 | 574 | 574 |  |  |  | 2026-07-09 | 2026-10-09 | 2026-07-09 | 2026-11-09 | 574 | 574
ADIDAS | 0903170160-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 15/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170160 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 17/09/2026 | 2026-11-09 | 15/09/2026 | 400 | 385 | 15 |  |  | 2026-05-09 | 14/09/2026 | 2026-10-09 | 2026-11-09 | 400 | 280 | 120
ADIDAS | 0903170289-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170289 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 17/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 300 | 120 | 180 |  |  | 14/09/2026 | 14/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 299 | 1 |  | 299
ADIDAS | 0903170946-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 260 | 15/10/2026 | 260 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903170946 KD5507 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | WE FR T GREY FIVE F17 |  | SS27-TI | 2026-01-10 | 2026-02-10 |  |  | 260 |  | 260 |  |  | 28/09/2026 | 29/09/2026 |  |  | 260 |  | 260 |  |  | 26/09/2026 | 28/09/2026 |  |  | 260 |  | 260
ADIDAS | 0903170993-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 327 | 2026-07-10 | 327 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903170993 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 25/09/2026 | 26/09/2026 |  |  | 327 |  | 327 |  |  | 22/09/2026 | 23/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903171021-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 500 | 15/10/2026 | 500 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903171021 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 30/09/2026 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 500 |  | 500 |  |  | 26/09/2026 | 28/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903172164-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 1591 | 15/09/2026 | 1591 | AN | AN26/06/2026 | G3B,G3J | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 13-Aug. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 13-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903172164 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1591 | 1591 |  |  | 345 | 2026-02-09 | 2026-10-09 | 2026-03-09 | 15/09/2026 | 1591 | 1578 | 13 |  | 162
ADIDAS | 0903173197-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 1686 | 30/09/2026 | 1686 | SI | SI26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903173197 KW8932 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/09/2026 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 17/09/2026 | 19/09/2026 |  |  | 1686 |  | 1686 |  |  | 14/09/2026 | 16/09/2026 |  |  | 1686 |  | 1686
ADIDAS | 0903173246-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1225 | 30/09/2026 | 1225 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173246 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1225 |  | 1225 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1225 |  | 1225
ADIDAS | 0903173302-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 410 | 30/09/2026 | 410 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516461 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173302 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 410 |  | 410 |  |  | 22/09/2026 | 23/09/2026 | 2026-12-09 | 14/09/2026 | 410 | 400 | 10 |  | 134
ADIDAS | 0903173331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2400 | 2026-07-10 | 2400 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 24-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173331 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/10/2026 | 19/10/2026 |  |  | 2400 |  | 2400 |  |  | 2026-12-10 | 15/10/2026 |  |  | 2400 |  | 2400
ADIDAS | 0903173353-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173353 KV7863 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 15/09/2026 | 1500 | 72 | 1428 |  |  | 2026-11-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 1500 | 1224 | 276
ADIDAS | 0903173473-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173473 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903173515-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173515 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903173545-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173545 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 800 |  | 800 |  |  | 2026-01-10 | 2026-02-10 | 15/09/2026 | 15/09/2026 | 800 | 792 | 8
ADIDAS | 0903173563-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-12-09 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173563 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 300 | 300 |  |  |  | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 300 | 300
ADIDAS | 0903174134-1 KA4331 | BLACK | 90D | S2608MR0902 | 303 | 30/09/2026 | 303 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903174134 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 303 |  | 303 |  |  | 18/09/2026 | 19/09/2026 |  |  | 303 |  | 303 |  |  | 17/09/2026 | 18/09/2026 |  |  | 303 |  | 303
ADIDAS | 0903174475-1 IN1173 | WHITE | 90D | S2408WR1600-SLT | 729 | 26/08/2026 | 729 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 24/08: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 03-Aug, actual receives 03-Aug (using fabric from Y.T.I). T2 Fu Hsun, PI Date 24-Jul, actual receives 03 Aug (using fabric from Y.T.I). (received qty more than MCAF qty). 600000 | HT SUB PROCESS_V1 | 0903174475 IN1173 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 13/08/2026 | 26/08/2026 | 18/08/2026 | 24/08/2026 | 729 | 729 |  |  |  | 2026-11-08 | 21/08/2026 | 2026-10-08 | 24/08/2026 | 729 | 729 |  |  |  | 2026-10-08 | 20/08/2026 | 2026-07-08 | 22/08/2026 | 729 | 729
ADIDAS | 0903176681-1 KA4331 | BLACK | 90D | S2608MR0902 | 371 | 2026-07-10 | 371 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | 30/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516394 | PAD+HT SUB PROCESS_V3 | 0903176681 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 371 |  | 371 |  |  | 24/09/2026 | 25/09/2026 |  |  | 371 |  | 371 |  |  | 23/09/2026 | 24/09/2026 |  |  | 371 |  | 371
ADIDAS | 0903176702-1 KA4331 | BLACK | 90D | S2608MR0902 | 700 | 30/09/2026 | 700 | SA | SA26/06/2026 | G1D | SHORTS | G1 | (25/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903176702 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 700 |  | 700 |  |  | 18/09/2026 | 19/09/2026 |  |  | 700 |  | 700 |  |  | 17/09/2026 | 18/09/2026 |  |  | 700 |  | 700
ADIDAS | 0903176748-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 309 | 15/10/2026 | 309 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176748 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 309 |  | 309 |  |  | 13/10/2026 | 14/10/2026 |  |  | 309 |  | 309 |  |  | 2026-07-10 | 2026-08-10 |  |  | 309 |  | 309
ADIDAS | 0903176770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2305 | 15/10/2026 | 2305 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 23/10/2026 | 27/10/2026 |  |  | 2305 |  | 2305 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2305 |  | 2305 |  |  | 14/10/2026 | 17/10/2026 |  |  | 2305 |  | 2305
ADIDAS | 0903176795-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 459 | 15/10/2026 | 459 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176795 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 459 |  | 459 |  |  | 2026-12-10 | 13/10/2026 |  |  | 459 |  | 459 |  |  | 2026-06-10 | 2026-07-10 |  |  | 459 |  | 459
ADIDAS | 0903176840-1 IN1159 | BLACK | 90D | S2408MR1601 | 223 | 2026-07-10 | 223 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516443 | HT SUB PROCESS_V1 | 0903176840 IN1159 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 223 |  | 223 |  |  | 19/09/2026 | 21/09/2026 |  |  | 223 |  | 223 |  |  | 18/09/2026 | 19/09/2026 |  |  | 223 |  | 223
ADIDAS | 0903176865-1 KA0246 | BLACK | 90D | S2608WR0902 | 450 | 2026-07-10 | 450 | SI | SI26/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand Tex, PI Date 30-Jul, actual receives 26-Aug. 516244 | PAD+HT SUB PROCESS_V3 | 0903176865 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 28/09/2026 | 29/09/2026 |  |  | 450 |  | 450 |  |  | 24/09/2026 | 25/09/2026 |  |  | 450 |  | 450 |  |  | 23/09/2026 | 24/09/2026 |  |  | 450 |  | 450
ADIDAS | 0903194305-1 IN1156 | BLACK | 90D | S2408MR1600 | 180 | 15/10/2026 | 180 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194305 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 180 |  | 180 |  |  | 24/09/2026 | 25/09/2026 | 2026-09-09 | 2026-12-09 | 180 | 16 | 164 |  |  | 23/09/2026 | 24/09/2026 | 31/08/2026 | 2026-10-09 | 180 | 179 | 1
ADIDAS | 0903194307-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194307 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 28/09/2026 | 29/09/2026 | 2026-09-09 | 2026-11-09 | 120 | 119 | 1 |  |  | 26/09/2026 | 28/09/2026 | 2026-03-09 | 2026-10-09 | 120 | 119 | 1
ADIDAS | 0903194308-1 IN1172 | BLACK | 90D | S2408WR1600 | 120 | 15/10/2026 | 120 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194308 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 | 2026-05-09 | 2026-05-09 | 120 | 117 | 3
ADIDAS | 0903194309-1 IN1156 | BLACK | 90D | S2408MR1600 | 1308 | 15/10/2026 | 1308 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194309 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 1308 |  | 1308 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1308 |  | 1308 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1308 |  | 1308
ADIDAS | 0903194311-1 IN1172 | BLACK | 90D | S2408WR1600 | 1174 | 15/10/2026 | 1174 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903194311 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 1174 |  | 1174 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1174 |  | 1174 |  |  | 20/10/2026 | 21/10/2026 | 2026-03-09 | 2026-12-09 | 1174 | 1146 | 28
ADIDAS | 0903194312-1 IN1157 | WHITE | 90D | S2408MR1600 | 1525 | 15/10/2026 | 1525 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194312 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 1525 |  | 1525 |  |  | 30/09/2026 | 2026-02-10 | 2026-09-09 | 2026-12-09 | 1525 | 696 | 829 |  |  | 29/09/2026 | 2026-01-10 | 2026-02-09 | 2026-10-09 | 1525 | 696 | 829
ADIDAS | 0903194314-1 IN1173 | WHITE | 90D | S2408WR1600 | 1776 | 30/09/2026 | 1776 | SI | SI30/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 28/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. 672027 | HT SUB PROCESS_V1 | 0903194314 IN1173 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 26/09/2026 |  |  | 1776 |  | 1776 |  |  | 22/09/2026 | 24/09/2026 | 2026-10-08 | 24/08/2026 | 1776 | 1776 |  |  |  | 21/09/2026 | 23/09/2026 | 2026-08-08 | 24/08/2026 | 1776 | 1776
ADIDAS | 0903194315-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 1508 | 15/10/2026 | 1508 | SA | SA30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903194315 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 1508 |  | 1508 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1508 |  | 1508 |  |  | 30/09/2026 | 2026-03-10 |  |  | 1508 |  | 1508
ADIDAS | 0903194317-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1167 | 15/10/2026 | 1167 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903194317 IT1828 | 14/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 1167 |  | 1167 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1167 |  | 1167 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1167 |  | 1167
ADIDAS | 0903194318-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 443 | 15/10/2026 | 443 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 672027 | PAD+HT SUB PROCESS_V3 | 0903194318 KA0248 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 443 |  | 443 |  |  | 2026-08-10 | 2026-09-10 |  |  | 443 |  | 443 |  |  | 2026-07-10 | 2026-08-10 |  |  | 443 |  | 443
ADIDAS | 0903194321-1 KA4331 | BLACK | 90D | S2608MR0902 | 239 | 15/10/2026 | 239 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194321 KA4331 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 239 |  | 239 |  |  | 2026-05-10 | 2026-06-10 |  |  | 239 |  | 239 |  |  | 2026-03-10 | 2026-05-10 |  |  | 239 |  | 239
ADIDAS | 0903194323-1 IN8707 | BLACK | 90D | S2408WR1601A | 194 | 15/10/2026 | 194 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 960026 | HT SUB PROCESS_V1 | 0903194323 IN8707 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 194 |  | 194 |  |  | 13/10/2026 | 15/10/2026 |  |  | 194 |  | 194 |  |  | 2026-12-10 | 14/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903194325-1 IN1156 | BLACK | 90D | S2408MR1600 | 566 | 15/10/2026 | 566 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903194325 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 566 |  | 566 |  |  | 28/09/2026 | 29/09/2026 |  |  | 566 |  | 566 |  |  | 26/09/2026 | 28/09/2026 |  |  | 566 |  | 566
ADIDAS | 0903194326-1 KA0246 | BLACK | 90D | S2608WR0902 | 377 | 15/10/2026 | 377 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | PAD+HT SUB PROCESS_V3 | 0903194326 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-02-10 |  |  | 377 |  | 377 |  |  | 26/09/2026 | 29/09/2026 |  |  | 377 |  | 377 |  |  | 25/09/2026 | 28/09/2026 |  |  | 377 |  | 377
ADIDAS | 0903194330-1 KA0235 | BLACK | 90D | S2608WR0901 | 348 | 15/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194330 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 348 |  | 348 |  |  | 22/10/2026 | 24/10/2026 |  |  | 348 |  | 348 |  |  | 21/10/2026 | 23/10/2026 |  |  | 348 |  | 348
ADIDAS | 0903194331-1 IN1156 | BLACK | 90D | S2408MR1600 | 231 | 15/10/2026 | 231 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516343 | HT SUB PROCESS_V1 | 0903194331 IN1156 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 231 |  | 231 |  |  | 24/09/2026 | 25/09/2026 | 2026-08-09 | 2026-11-09 | 231 | 198 | 33 |  |  | 23/09/2026 | 24/09/2026 | 31/08/2026 | 2026-11-09 | 231 | 198 | 33
ADIDAS | 0903194333-1 IN1172 | BLACK | 90D | S2408WR1600 | 423 | 15/10/2026 | 423 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 516443 | HT SUB PROCESS_V1 | 0903194333 IN1172 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 423 |  | 423 |  |  | 20/10/2026 | 21/10/2026 |  |  | 423 |  | 423 |  |  | 19/10/2026 | 20/10/2026 | 2026-07-09 | 2026-12-09 | 423 | 414 | 9
ADIDAS | 0903194340-1 IN1157 | WHITE | 90D | S2408MR1600 | 375 | 15/10/2026 | 375 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 06-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903194340 IN1157 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 375 |  | 375 |  |  | 28/09/2026 | 29/09/2026 | 2026-10-09 | 2026-11-09 | 375 | 373 | 2 |  |  | 26/09/2026 | 28/09/2026 | 2026-07-09 | 2026-10-09 | 375 | 374 | 1
ADIDAS | 0903194361-1 IN1156 | BLACK | 90D | S2408MR1600 | 4002 | 15/10/2026 | 4002 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516438 | HT SUB PROCESS_V1 | 0903194361 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-07-10 |  |  | 4002 |  | 4002 |  |  | 30/09/2026 | 2026-05-10 | 2026-08-09 | 2026-12-09 | 4002 | 3250 | 752 |  |  | 29/09/2026 | 2026-03-10 | 29/08/2026 | 2026-11-09 | 4002 | 3259 | 743
ADIDAS | 0903194364-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516404 | HT SUB PROCESS_V1 | 0903194364 IN1172 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 300 |  | 300 |  |  | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 20/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903194475-1 KA6229 | BLACK | 120D | S2608WR0202 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194475 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 631 |  | 631 |  |  | 2026-08-10 | 2026-12-10 |  |  | 631 |  | 631 |  |  | 2026-05-10 | 2026-08-10 |  |  | 631 |  | 631
ADIDAS | 0903194486-1 KA6229 | BLACK | 120D | S2608WR0202 | 526 | 15/10/2026 | 526 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194486 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 526 |  | 526 |  |  | 2026-08-10 | 2026-12-10 |  |  | 526 |  | 526 |  |  | 2026-05-10 | 2026-08-10 |  |  | 526 |  | 526
ADIDAS | 0903194488-1 KA6229 | BLACK | 120D | S2608WR0202 | 310 | 15/10/2026 | 310 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194488 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 310 |  | 310 |  |  | 2026-12-10 | 13/10/2026 |  |  | 310 |  | 310 |  |  | 2026-08-10 | 2026-09-10 |  |  | 310 |  | 310
ADIDAS | 0903194490-1 KA6229 | BLACK | 120D | S2608WR0202 | 369 | 15/10/2026 | 369 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194490 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 369 |  | 369 |  |  | 2026-12-10 | 13/10/2026 |  |  | 369 |  | 369 |  |  | 2026-08-10 | 2026-09-10 | 14/09/2026 | 14/09/2026 | 369 | 147 | 222 |  | 147
ADIDAS | 0903194492-1 KA6229 | BLACK | 120D | S2608WR0202 | 926 | 2026-07-10 | 926 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194492 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/09/2026 | 18/09/2026 |  |  | 926 |  | 926 |  |  | 2026-11-09 | 15/09/2026 |  |  | 926 |  | 926 |  |  | 2026-08-09 | 2026-11-09 |  |  | 926 |  | 926
ADIDAS | 0903194495-1 KA6229 | BLACK | 120D | S2608WR0202 | 321 | 2026-07-10 | 321 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194495 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 321 |  | 321 |  |  | 15/09/2026 | 17/09/2026 |  |  | 321 |  | 321 |  |  | 2026-11-09 | 14/09/2026 |  |  | 321 |  | 321
ADIDAS | 0903194496-1 KA6229 | BLACK | 120D | S2608WR0202 | 779 | 15/10/2026 | 779 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194496 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 779 |  | 779 |  |  | 13/10/2026 | 16/10/2026 |  |  | 779 |  | 779 |  |  | 2026-09-10 | 13/10/2026 | 14/09/2026 | 15/09/2026 | 779 | 398 | 381 |  | 397
ADIDAS | 0903194499-1 KA6229 | BLACK | 120D | S2608WR0202 | 346 | 2026-07-10 | 346 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194499 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 346 |  | 346 |  |  | 15/09/2026 | 17/09/2026 |  |  | 346 |  | 346 |  |  | 2026-11-09 | 14/09/2026 |  |  | 346 |  | 346
ADIDAS | 0903194663-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1069 | 29/09/2026 | 1069 | AN | AN26/06/2026 | G1D | JACKET | G1 | ok | (07/08/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194663 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 1069 | 284 | 785 |  | 71 | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 1069 | 383 | 686
ADIDAS | 0903194835-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 623 | 30/09/2026 | 623 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903194835 KV7863 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 623 |  | 623 |  |  | 25/09/2026 | 26/09/2026 | 2026-10-09 | 14/09/2026 | 623 | 609 | 14 |  | 103
ADIDAS | 0903195508-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 471 | 30/09/2026 | 471 | AN | AN30/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 21/09: ex-fty. Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903195508 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 471 |  | 471 |  |  | 18/09/2026 | 19/09/2026 |  |  | 471 |  | 471 |  |  | 17/09/2026 | 18/09/2026 |  |  | 471 |  | 471
ADIDAS | 0903196020-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 891 | 15/10/2026 | 891 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196020 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 891 |  | 891 |  |  | 26/09/2026 | 28/09/2026 |  |  | 891 |  | 891 |  |  | 25/09/2026 | 26/09/2026 |  |  | 891 |  | 891
ADIDAS | 0903196021-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 12 | 15/10/2026 | 12 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196021 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 12 |  | 12 |  |  | 26/09/2026 | 28/09/2026 |  |  | 12 |  | 12 |  |  | 25/09/2026 | 26/09/2026 |  |  | 12 |  | 12
ADIDAS | 0903196022-1 IN1172 | BLACK | 90D | S2408WR1600 | 2616 | 15/10/2026 | 2616 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 823016 | HT SUB PROCESS_V1 | 0903196022 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 28/10/2026 |  |  | 2616 |  | 2616 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2616 |  | 2616 |  |  | 21/10/2026 | 24/10/2026 | 2026-04-09 | 15/09/2026 | 2616 | 2550 | 66
ADIDAS | 0903196023-1 IN1156 | BLACK | 90D | S2408MR1600 | 3287 | 15/10/2026 | 3287 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 823016 | HT SUB PROCESS_V1 | 0903196023 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 2026-02-10 |  |  | 3287 |  | 3287 |  |  | 25/09/2026 | 30/09/2026 |  |  | 3287 |  | 3287 |  |  | 24/09/2026 | 29/09/2026 |  |  | 3287 |  | 3287
ADIDAS | 0903196024-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960006 | HT SUB PROCESS_V1 | 0903196024 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 | 2026-05-09 | 2026-05-09 | 100 | 97 | 3
ADIDAS | 0903196025-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960006 | HT SUB PROCESS_V1 | 0903196025 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 200 |  | 200 |  |  | 24/09/2026 | 25/09/2026 | 2026-09-09 | 2026-11-09 | 200 | 199 | 1 |  |  | 23/09/2026 | 24/09/2026 | 31/08/2026 | 2026-10-09 | 200 | 199 | 1
ADIDAS | 0903196026-1 IN1172 | BLACK | 90D | S2408WR1600 | 134 | 15/10/2026 | 134 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960026 | HT SUB PROCESS_V1 | 0903196026 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 134 |  | 134 |  |  | 19/10/2026 | 20/10/2026 |  |  | 134 |  | 134 |  |  | 17/10/2026 | 19/10/2026 | 2026-05-09 | 2026-12-09 | 134 | 134
ADIDAS | 0903196027-1 IN1156 | BLACK | 90D | S2408MR1600 | 143 | 15/10/2026 | 143 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960026 | HT SUB PROCESS_V1 | 0903196027 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 143 |  | 143 |  |  | 28/09/2026 | 29/09/2026 | 2026-08-09 | 2026-10-09 | 143 | 142 | 1 |  |  | 26/09/2026 | 28/09/2026 | 29/08/2026 | 2026-10-09 | 143 | 142 | 1
ADIDAS | 0903196028-1 IN1156 | BLACK | 90D | S2408MR1600 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 980004 | HT SUB PROCESS_V1 | 0903196028 IN1156 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-01-10 |  |  | 631 |  | 631 |  |  | 29/09/2026 | 29/09/2026 |  |  | 631 |  | 631 |  |  | 28/09/2026 | 28/09/2026 |  |  | 631 |  | 631
ADIDAS | 0903196030-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1200 | 15/10/2026 | 1200 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196030 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 1200 |  | 1200 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1200 |  | 1200 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1200 |  | 1200
ADIDAS | 0903196031-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 1200 | 15/10/2026 | 1200 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196031 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 16/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903196032-1 IN1157 | WHITE | 90D | S2408MR1600 | 290 | 15/10/2026 | 290 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | (Damco offline). T2 Y.T.I, body & mesh actual receives 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196032 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 290 |  | 290 |  |  | 29/09/2026 | 30/09/2026 | 2026-09-09 | 2026-12-09 | 290 | 288 | 2 |  |  | 28/09/2026 | 29/09/2026 | 2026-02-09 | 2026-10-09 | 290 | 288 | 2
ADIDAS | 0903196033-1 IN1156 | BLACK | 90D | S2408MR1600 | 236 | 15/10/2026 | 236 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196033 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 236 |  | 236 |  |  | 28/09/2026 | 29/09/2026 |  |  | 236 |  | 236 |  |  | 26/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 236 | 197 | 39
ADIDAS | 0903196034-1 IN1173 | WHITE | 90D | S2408WR1600 | 114 | 15/10/2026 | 114 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 01-Aug. 688010 | HT SUB PROCESS_V1 | 0903196034 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 114 |  | 114 |  |  | 2026-07-10 | 2026-08-10 | 13/08/2026 | 26/08/2026 | 114 | 114 |  |  |  | 2026-06-10 | 2026-07-10 | 13/08/2026 | 22/08/2026 | 114 | 114
ADIDAS | 0903196035-1 IN1172 | BLACK | 90D | S2408WR1600 | 528 | 15/10/2026 | 528 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196035 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 528 |  | 528 |  |  | 2026-03-10 | 2026-05-10 |  |  | 528 |  | 528 |  |  | 2026-02-10 | 2026-03-10 | 2026-05-09 | 14/09/2026 | 528 | 516 | 12 |  | 42
ADIDAS | 0903196036-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 144 | 15/10/2026 | 144 | SI | SI30/06/2026 | G1H | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196036 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 144 |  | 144 |  |  | 15/10/2026 | 16/10/2026 |  |  | 144 |  | 144 |  |  | 14/10/2026 | 15/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903196037-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196037 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 248 |  | 248 |  |  | 25/09/2026 | 26/09/2026 |  |  | 248 |  | 248 |  |  | 24/09/2026 | 25/09/2026 |  |  | 248 |  | 248
ADIDAS | 0903197425-1 IN8707 | BLACK | 90D | S2408WR1601A | 156 | 15/10/2026 | 156 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197425 IN8707 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 156 |  | 156 |  |  | 13/10/2026 | 15/10/2026 |  |  | 156 |  | 156 |  |  | 2026-12-10 | 14/10/2026 |  |  | 156 |  | 156
ADIDAS | 0903197427-1 KA0235 | BLACK | 90D | S2608WR0901 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197427 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 24/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903197429-1 KA0246 | BLACK | 90D | S2608WR0902 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197429 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-02-10 |  |  | 200 |  | 200 |  |  | 26/09/2026 | 29/09/2026 |  |  | 200 |  | 200 |  |  | 25/09/2026 | 28/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903197431-1 IN8707 | BLACK | 90D | S2408WR1601A | 361 | 15/10/2026 | 361 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903197431 IN8707 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 15/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 361 |  | 361 |  |  | 13/10/2026 | 15/10/2026 |  |  | 361 |  | 361 |  |  | 2026-12-10 | 14/10/2026 |  |  | 361 |  | 361
ADIDAS | 0903197433-1 KA0246 | BLACK | 90D | S2608WR0902 | 264 | 15/10/2026 | 264 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 688010 | PAD+HT SUB PROCESS_V3 | 0903197433 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-02-10 |  |  | 264 |  | 264 |  |  | 26/09/2026 | 29/09/2026 |  |  | 264 |  | 264 |  |  | 25/09/2026 | 28/09/2026 |  |  | 264 |  | 264
ADIDAS | 0903197435-1 KA0235 | BLACK | 90D | S2608WR0901 | 708 | 15/10/2026 | 708 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197435 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-02-11 | 2026-04-11 |  |  | 708 |  | 708 |  |  | 29/10/2026 | 31/10/2026 |  |  | 708 |  | 708 |  |  | 28/10/2026 | 30/10/2026 |  |  | 708 |  | 708
ADIDAS | 0903197436-1 KA0246 | BLACK | 90D | S2608WR0902 | 268 | 15/10/2026 | 268 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | PAD+HT SUB PROCESS_V3 | 0903197436 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 268 |  | 268 |  |  | 29/09/2026 | 30/09/2026 |  |  | 268 |  | 268 |  |  | 28/09/2026 | 29/09/2026 |  |  | 268 |  | 268
ADIDAS | 0903197439-1 KA0235 | BLACK | 90D | S2608WR0901 | 155 | 15/10/2026 | 155 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197439 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 155 |  | 155 |  |  | 22/10/2026 | 24/10/2026 |  |  | 155 |  | 155 |  |  | 21/10/2026 | 23/10/2026 |  |  | 155 |  | 155
ADIDAS | 0903197440-1 KA4331 | BLACK | 90D | S2608MR0902 | 277 | 15/10/2026 | 277 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 826010 | PAD+HT SUB PROCESS_V3 | 0903197440 KA4331 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 277 |  | 277 |  |  | 2026-05-10 | 2026-06-10 |  |  | 277 |  | 277 |  |  | 2026-03-10 | 2026-05-10 |  |  | 277 |  | 277
ADIDAS | 0903197442-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 335 | 15/10/2026 | 335 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197442 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 335 |  | 335 |  |  | 2026-08-10 | 2026-09-10 |  |  | 335 |  | 335 |  |  | 2026-07-10 | 2026-08-10 |  |  | 335 |  | 335
ADIDAS | 0903197444-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 520 | 15/10/2026 | 520 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 680015 | PAD+HT SUB PROCESS_V3 | 0903197444 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 26/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 26/09/2026 | 29/09/2026 |  |  | 520 |  | 520 |  |  | 23/09/2026 | 25/09/2026 |  |  | 520 |  | 520 |  |  | 22/09/2026 | 24/09/2026 |  |  | 520 |  | 520
ADIDAS | 0903197446-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 630 | 15/10/2026 | 630 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197446 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-10 | 13/10/2026 |  |  | 630 |  | 630 |  |  | 2026-08-10 | 2026-09-10 |  |  | 630 |  | 630 |  |  | 2026-07-10 | 2026-08-10 |  |  | 630 |  | 630
ADIDAS | 0903197448-1 KA0235 | BLACK | 90D | S2608WR0901 | 675 | 15/10/2026 | 675 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197448 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 675 |  | 675 |  |  | 27/10/2026 | 29/10/2026 |  |  | 675 |  | 675 |  |  | 26/10/2026 | 28/10/2026 |  |  | 675 |  | 675
ADIDAS | 0903197449-1 KA0246 | BLACK | 90D | S2608WR0902 | 547 | 15/10/2026 | 547 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197449 KA0246 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 547 |  | 547 |  |  | 29/09/2026 | 30/09/2026 |  |  | 547 |  | 547 |  |  | 28/09/2026 | 29/09/2026 |  |  | 547 |  | 547
ADIDAS | 0903197451-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197451 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903197453-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 681 | 15/10/2026 | 681 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197453 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 26/09/2026 | 29/09/2026 |  |  | 681 |  | 681 |  |  | 23/09/2026 | 25/09/2026 |  |  | 681 |  | 681 |  |  | 22/09/2026 | 24/09/2026 |  |  | 681 |  | 681
ADIDAS | 0903197455-1 KA4331 | BLACK | 90D | S2608MR0902 | 346 | 15/10/2026 | 346 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903197455 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 346 |  | 346 |  |  | 2026-05-10 | 2026-06-10 |  |  | 346 |  | 346 |  |  | 2026-03-10 | 2026-05-10 |  |  | 346 |  | 346
ADIDAS | 0903197456-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 822 | 15/10/2026 | 822 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 659018 | HT SUB PROCESS_V1 | 0903197456 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 20/10/2026 | 21/10/2026 |  |  | 822 |  | 822 |  |  | 17/10/2026 | 19/10/2026 |  |  | 822 |  | 822 |  |  | 16/10/2026 | 17/10/2026 |  |  | 822 |  | 822
ADIDAS | 0903197458-1 KA0235 | BLACK | 90D | S2608WR0901 | 999 | 15/10/2026 | 999 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903197458 KA0235 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-04-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 999 |  | 999 |  |  | 31/10/2026 | 2026-03-11 |  |  | 999 |  | 999 |  |  | 30/10/2026 | 2026-02-11 |  |  | 999 |  | 999
ADIDAS | 0903197459-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 102 | 15/10/2026 | 102 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903197459 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 102 |  | 102 |  |  | 20/10/2026 | 21/10/2026 |  |  | 102 |  | 102 |  |  | 19/10/2026 | 20/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903197461-1 KA0235 | BLACK | 90D | S2608WR0901 | 420 | 15/10/2026 | 420 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903197461 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 30/10/2026 |  |  | 420 |  | 420 |  |  | 24/10/2026 | 27/10/2026 |  |  | 420 |  | 420 |  |  | 23/10/2026 | 26/10/2026 |  |  | 420 |  | 420
ADIDAS | 0903197465-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 307 | 15/10/2026 | 307 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | PAD+HT SUB PROCESS_V3 | 0903197465 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-10 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 2026-12-10 | 2026-12-10 |  |  | 307 |  | 307 |  |  | 2026-08-10 | 2026-08-10 |  |  | 307 |  | 307 |  |  | 2026-07-10 | 2026-07-10 |  |  | 307 |  | 307
ADIDAS | 0903197467-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 478 | 15/10/2026 | 478 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 659018 | PAD+HT SUB PROCESS_V3 | 0903197467 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 22/09/2026 | 24/09/2026 |  |  | 478 |  | 478 |  |  | 18/09/2026 | 21/09/2026 |  |  | 478 |  | 478 |  |  | 17/09/2026 | 19/09/2026 |  |  | 478 |  | 478
ADIDAS | 0903197472-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 408 | 15/10/2026 | 408 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903197472 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 408 |  | 408 |  |  | 20/10/2026 | 21/10/2026 |  |  | 408 |  | 408 |  |  | 19/10/2026 | 20/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903197475-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 498 | 15/10/2026 | 498 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903197475 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-10-10 |  |  | 498 |  | 498 |  |  | 2026-03-10 | 2026-07-10 |  |  | 498 |  | 498 |  |  | 2026-02-10 | 2026-06-10 |  |  | 498 |  | 498
ADIDAS | 0903197478-1 KA4331 | BLACK | 90D | S2608MR0902 | 18 | 15/10/2026 | 18 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197478 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 18 |  | 18 |  |  | 21/09/2026 | 23/09/2026 |  |  | 18 |  | 18 |  |  | 19/09/2026 | 22/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903197480-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 530 | 15/10/2026 | 530 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197480 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 530 |  | 530 |  |  | 2026-07-10 | 2026-08-10 |  |  | 530 |  | 530 |  |  | 2026-06-10 | 2026-07-10 |  |  | 530 |  | 530
ADIDAS | 0903197482-1 KA0235 | BLACK | 90D | S2608WR0901 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903197482 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 26/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197484-1 KA0246 | BLACK | 90D | S2608WR0902 | 611 | 15/10/2026 | 611 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650010 | PAD+HT SUB PROCESS_V3 | 0903197484 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 611 |  | 611 |  |  | 2026-03-10 | 2026-06-10 |  |  | 611 |  | 611 |  |  | 2026-02-10 | 2026-05-10 |  |  | 611 |  | 611
ADIDAS | 0903197486-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 544 | 15/10/2026 | 544 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903197486 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-10-10 |  |  | 544 |  | 544 |  |  | 2026-03-10 | 2026-07-10 |  |  | 544 |  | 544 |  |  | 2026-02-10 | 2026-06-10 |  |  | 544 |  | 544
ADIDAS | 0903197487-1 KA0235 | BLACK | 90D | S2608WR0901 | 106 | 15/10/2026 | 106 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197487 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 30/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 106 |  | 106 |  |  | 27/10/2026 | 29/10/2026 |  |  | 106 |  | 106 |  |  | 26/10/2026 | 28/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903197489-1 KA0246 | BLACK | 90D | S2608WR0902 | 204 | 15/10/2026 | 204 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 834012 | PAD+HT SUB PROCESS_V3 | 0903197489 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 204 |  | 204 |  |  | 30/09/2026 | 2026-02-10 |  |  | 204 |  | 204 |  |  | 29/09/2026 | 2026-01-10 |  |  | 204 |  | 204
ADIDAS | 0903197490-1 KA4331 | BLACK | 90D | S2608MR0902 | 790 | 15/10/2026 | 790 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197490 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 790 |  | 790 |  |  | 21/09/2026 | 23/09/2026 |  |  | 790 |  | 790 |  |  | 19/09/2026 | 22/09/2026 |  |  | 790 |  | 790
ADIDAS | 0903197491-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 118 | 15/10/2026 | 118 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903197491 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 22/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 22/09/2026 | 24/09/2026 |  |  | 118 |  | 118 |  |  | 18/09/2026 | 21/09/2026 |  |  | 118 |  | 118 |  |  | 17/09/2026 | 19/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903197494-1 KA0246 | BLACK | 90D | S2608WR0902 | 772 | 15/10/2026 | 772 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197494 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-03-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 772 |  | 772 |  |  | 30/09/2026 | 2026-02-10 |  |  | 772 |  | 772 |  |  | 29/09/2026 | 2026-01-10 |  |  | 772 |  | 772
ADIDAS | 0903197496-1 KA0235 | BLACK | 90D | S2608WR0901 | 6000 | 15/10/2026 | 6000 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197496 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 2026-05-11 |  |  | 6000 |  | 6000 |  |  | 22/10/2026 | 2026-02-11 |  |  | 6000 |  | 6000 |  |  | 21/10/2026 | 31/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903197498-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 636 | 15/10/2026 | 636 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197498 KA0238 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 636 |  | 636 |  |  | 2026-09-10 | 2026-10-10 |  |  | 636 |  | 636 |  |  | 2026-08-10 | 2026-09-10 |  |  | 636 |  | 636
ADIDAS | 0903197499-1 KA0235 | BLACK | 90D | S2608WR0901 | 1428 | 15/10/2026 | 1428 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197499 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 1428 |  | 1428 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1428 |  | 1428 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1428 |  | 1428
ADIDAS | 0903197500-1 KA4331 | BLACK | 90D | S2608MR0902 | 1450 | 15/10/2026 | 1450 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197500 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 1450 |  | 1450 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1450 |  | 1450 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1450 |  | 1450
ADIDAS | 0903197502-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 653 | 15/10/2026 | 653 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197502 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/09/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 22/09/2026 | 24/09/2026 |  |  | 653 |  | 653 |  |  | 18/09/2026 | 21/09/2026 |  |  | 653 |  | 653 |  |  | 17/09/2026 | 19/09/2026 |  |  | 653 |  | 653
ADIDAS | 0903197760-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 600 | 15/10/2026 | 600 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903197760 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-09-10 | 13/10/2026 |  |  | 600 |  | 600 |  |  | 2026-06-10 | 2026-09-10 |  |  | 600 |  | 600 |  |  | 2026-05-10 | 2026-08-10 |  |  | 600 |  | 600
ADIDAS | 0903197762-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 778 | 15/10/2026 | 778 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (25/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197762 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-09-10 | 13/10/2026 |  |  | 778 |  | 778 |  |  | 2026-06-10 | 2026-09-10 |  |  | 778 |  | 778 |  |  | 2026-05-10 | 2026-08-10 |  |  | 778 |  | 778
ADIDAS | 0903197769-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 1700 | 15/10/2026 | 1700 | SI | SI30/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197769 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-10-10 | 14/10/2026 |  |  | 1700 |  | 1700 |  |  | 2026-07-10 | 2026-10-10 |  |  | 1700 |  | 1700 |  |  | 2026-03-10 | 2026-07-10 |  |  | 1700 |  | 1700
ADIDAS | 0903197775-1 KE9656 | BLACK | 105D | S2608WR0201A | 322 | 15/10/2026 | 322 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 27-Jul. 600000 | PAD+HT SUB PROCESS_V3 | 0903197775 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADI365 SHO W BLACK |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 322 |  | 322 |  |  | 13/10/2026 | 13/10/2026 |  |  | 322 |  | 322 |  |  | 2026-12-10 | 2026-12-10 |  |  | 322 |  | 322
ADIDAS | 0903203166-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 301 | 26/08/2026 | 301 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 22-Jun. T2 Libolon, PI Date 31-May, actual receives 05-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203166 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 22/07/2026 | 27/07/2026 | 24/07/2026 | 29/07/2026 | 301 | 301 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 27/07/2026 | 301 | 301
ADIDAS | 0903203167-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 447 | 26/08/2026 | 447 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (19/06/2026) | 24/08: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). T2 Libolon, PI Date 31-May, actual receives 28-May. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203167 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 13/08/2026 | 28/07/2026 | 14/08/2026 | 447 | 447 |  |  |  | 23/07/2026 | 2026-10-08 | 23/07/2026 | 21/08/2026 | 447 | 447
ADIDAS | 0903203168-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 186 | 2026-05-09 | 186 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203168 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 186 | 186 |  |  |  | 2026-03-08 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 186 | 186
ADIDAS | 0903203169-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 425 | 30/09/2026 | 425 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok |  | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903203169 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 425 |  | 425 |  |  | 25/09/2026 | 26/09/2026 |  |  | 425 |  | 425
ADIDAS | 0903203170-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 240 | 15/09/2026 | 240 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203170 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-07-09 | 2026-10-09 | 240 | 240 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 14/09/2026 | 240 | 240 |  |  | 9 | 27/08/2026 | 2026-02-09 | 28/07/2026 | 15/09/2026 | 240 | 240
ADIDAS | 0903203171-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 347 | 15/10/2026 | 347 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203171 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 347 |  | 347 |  |  | 2026-12-10 | 13/10/2026 |  |  | 347 |  | 347 |  |  | 2026-06-10 | 2026-07-10 |  |  | 347 |  | 347
ADIDAS | 0903205276-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516403 | HT SUB PROCESS_V1 | 0903205276 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 19/09/2026 | 21/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 | 13/08/2026 | 26/08/2026 | 300 | 300 |  |  |  | 16/09/2026 | 17/09/2026 | 13/08/2026 | 24/08/2026 | 300 | 300
ADIDAS | 0903208394-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 152 | 2026-12-09 | 152 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 10/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516342 | HT SUB PROCESS_V1 | 0903208394 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-01-09 | 2026-07-09 | 2026-04-09 | 2026-10-09 | 152 | 152 |  |  |  | 29/08/2026 | 2026-04-09 | 13/08/2026 | 21/08/2026 | 152 | 152 |  |  |  | 28/08/2026 | 2026-03-09 | 13/08/2026 | 20/08/2026 | 152 | 152
ADIDAS | 0903208396-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 459 | 23/09/2026 | 459 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208396 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 16/09/2026 | 17/09/2026 |  |  | 459 |  | 459 |  |  | 14/09/2026 | 15/09/2026 | 19/08/2026 | 2026-01-09 | 459 | 458 | 1 |  |  | 2026-12-09 | 14/09/2026 | 18/08/2026 | 2026-01-09 | 459 | 458 | 1
ADIDAS | 0903208397-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 494 | 15/10/2026 | 494 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903208397 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 494 |  | 494 |  |  | 23/10/2026 | 24/10/2026 | 19/08/2026 | 2026-12-09 | 494 | 490 | 4 |  |  | 22/10/2026 | 23/10/2026 | 18/08/2026 | 2026-02-09 | 494 | 490 | 4
ADIDAS | 0903208398-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 13 | 2026-02-10 | 13 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208398 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-05-10 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-05-10 | 2026-05-10 |  |  | 13 |  | 13 |  |  | 2026-02-10 | 2026-02-10 |  |  | 13 |  | 13 |  |  | 2026-01-10 | 2026-01-10 |  |  | 13 |  | 13
ADIDAS | 0903208407-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 302 | 30/09/2026 | 302 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903208407 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 302 |  | 302 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 15/09/2026 | 302 | 296 | 6 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 296 | 6 |  | 28
ADIDAS | 0903208408-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 597 | 30/09/2026 | 597 | SA | SA03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903208408 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 597 |  | 597 |  |  | 25/09/2026 | 26/09/2026 | 2026-08-09 | 15/09/2026 | 597 | 595 | 2 |  |  | 24/09/2026 | 25/09/2026 | 2026-08-09 | 14/09/2026 | 597 | 596 | 1 |  | 7
ADIDAS | 0903208410-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 361 | 2026-07-10 | 361 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516443 | HT SUB PROCESS_V1 | 0903208410 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 23/09/2026 |  |  | 361 |  | 361 |  |  | 19/09/2026 | 21/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 356 | 5 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-12-09 | 361 | 358 | 3
ADIDAS | 0903208411-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1107 | 15/10/2026 | 1107 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 678002 | HT SUB PROCESS_V1 | 0903208411 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 1107 |  | 1107 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1107 |  | 1107 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1107 |  | 1107
ADIDAS | 0903208412-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1026 | 15/10/2026 | 1026 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug.. 834012 | HT SUB PROCESS_V1 | 0903208412 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 1026 |  | 1026 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1026 |  | 1026 |  |  | 22/10/2026 | 23/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903208413-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 266 | 15/10/2026 | 266 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, body & mesh actual receives 12-Aug. 688010 | HT SUB PROCESS_V1 | 0903208413 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 266 |  | 266 |  |  | 2026-08-10 | 2026-09-10 |  |  | 266 |  | 266 |  |  | 2026-07-10 | 2026-08-10 |  |  | 266 |  | 266
ADIDAS | 0903208414-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 415 | 14/10/2026 | 415 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903208414 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 415 |  | 415 |  |  | 25/09/2026 | 26/09/2026 |  |  | 415 |  | 415 |  |  | 24/09/2026 | 25/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903208419-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903208419 KG8548 | 17/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/08/2026 | ADIZERO E TEE |  | SS27-YTI | 27/08/2026 | 2026-01-09 | 27/08/2026 | 2026-01-09 | 300 | 300 |  |  |  | 24/08/2026 | 29/08/2026 | 2026-12-08 | 21/08/2026 | 300 | 300 |  |  |  | 21/08/2026 | 28/08/2026 | 2026-11-08 | 21/08/2026 | 300 | 300
ADIDAS | 0903208420-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 301 | 2026-09-09 | 301 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208420 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-12-08 | 2026-12-08 | 301 | 301 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-11-08 | 20/08/2026 | 301 | 301
ADIDAS | 0903208421-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208421 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-01-09 | 31/08/2026 | 2026-04-09 | 300 | 300 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-10-08 | 2026-12-08 | 300 | 300 |  |  |  | 26/08/2026 | 28/08/2026 | 2026-08-08 | 2026-11-08 | 300 | 300
ADIDAS | 0903208423-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 244 | 30/09/2026 | 244 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 516342 | HT SUB PROCESS_V1 | 0903208423 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 17/09/2026 | 2026-01-09 | 2026-07-09 | 244 | 239 | 5 |  |  | 27/08/2026 | 15/09/2026 | 2026-10-08 | 2026-12-08 | 244 | 244 |  |  |  | 26/08/2026 | 14/09/2026 | 2026-08-08 | 2026-11-08 | 244 | 244
ADIDAS | 0903208424-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 176 | 2026-07-10 | 176 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 814006 | HT SUB PROCESS_V1 | 0903208424 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 17/10/2026 |  |  | 176 |  | 176 |  |  | 15/10/2026 | 15/10/2026 | 2026-12-08 | 26/08/2026 | 176 | 176 |  |  |  | 14/10/2026 | 14/10/2026 | 2026-11-08 | 24/08/2026 | 176 | 176
ADIDAS | 0903208425-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 220 | 2026-07-10 | 220 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 838103 | HT SUB PROCESS_V1 | 0903208425 KG8548 | 17/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 17/10/2026 |  |  | 220 |  | 220 |  |  | 15/10/2026 | 15/10/2026 | 2026-11-08 | 2026-01-09 | 220 | 220 |  |  |  | 14/10/2026 | 14/10/2026 | 2026-10-08 | 31/08/2026 | 220 | 220
ADIDAS | 0903208426-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 616 | 15/10/2026 | 616 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 800187 | HT SUB PROCESS_V1 | 0903208426 KG8548 | 17/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 616 |  | 616 |  |  | 2026-08-10 | 2026-10-10 | 14/08/2026 | 2026-02-09 | 616 | 616 |  |  |  | 2026-07-10 | 2026-09-10 | 13/08/2026 | 2026-02-09 | 616 | 616
ADIDAS | 0903208427-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 839055 | HT SUB PROCESS_V1 | 0903208427 KG8548 | 17/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 248 |  | 248 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 26/08/2026 | 248 | 248 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 24/08/2026 | 248 | 248
ADIDAS | 0903208428-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 2070 | 15/10/2026 | 2070 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 678002 | HT SUB PROCESS_V1 | 0903208428 KG8548 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 30/10/2026 |  |  | 2070 |  | 2070 |  |  | 24/10/2026 | 28/10/2026 |  |  | 2070 |  | 2070 |  |  | 23/10/2026 | 27/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903208429-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 466 | 23/09/2026 | 466 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 680015 | HT SUB PROCESS_V1 | 0903208429 KG8548 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 17/09/2026 |  |  | 466 |  | 466 |  |  | 15/09/2026 | 15/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 465 | 1 |  |  | 14/09/2026 | 14/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 466
ADIDAS | 0903208430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 648 | 15/10/2026 | 648 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208430 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 648 |  | 648 |  |  | 2026-08-10 | 2026-10-10 | 13/08/2026 | 14/09/2026 | 648 | 648 |  |  | 1 | 2026-07-10 | 2026-09-10 | 13/08/2026 | 2026-03-09 | 648 | 648
ADIDAS | 0903208431-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 424 | 15/10/2026 | 424 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, Body & mesh actual receives 05-Aug. s650010 | HT SUB PROCESS_V1 | 0903208431 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 424 |  | 424 |  |  | 15/10/2026 | 16/10/2026 | 2026-12-08 | 27/08/2026 | 424 | 424 |  |  |  | 14/10/2026 | 15/10/2026 | 2026-12-08 | 26/08/2026 | 424 | 424
ADIDAS | 0903208432-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 550 | 2026-12-09 | 550 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (PODD Improvement Request). T2 Y.T.I, body & mesh actual receives 18-Aug. 688010 | HT SUB PROCESS_V1 | 0903208432 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/08/2026 | ADIZERO E TEE |  | SS27-YTI | 26/08/2026 | 29/08/2026 | 26/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 21/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 20/08/2026 | 26/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903208433-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 240 | 15/10/2026 | 240 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 05-Aug. 688010 | HT SUB PROCESS_V1 | 0903208433 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 240 |  | 240 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 22/08/2026 | 240 | 240 |  |  |  | 2026-07-10 | 2026-09-10 | 15/08/2026 | 22/08/2026 | 240 | 240
ADIDAS | 0903208434-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 472 | 14/10/2026 | 472 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208434 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 472 |  | 472 |  |  | 2026-12-10 | 13/10/2026 | 18/08/2026 | 29/08/2026 | 472 | 470 | 2 |  |  | 2026-10-10 | 2026-12-10 | 15/08/2026 | 28/08/2026 | 472 | 472
ADIDAS | 0903208435-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1324 | 15/10/2026 | 1324 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 814006 | HT SUB PROCESS_V1 | 0903208435 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 1324 |  | 1324 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1324 |  | 1324 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1324 |  | 1324
ADIDAS | 0903208440-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 456 | 15/10/2026 | 456 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 678002 | HT SUB PROCESS_V1 | 0903208440 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 456 |  | 456 |  |  | 2026-05-10 | 2026-06-10 | 24/08/2026 | 2026-04-09 | 456 | 456 |  |  |  | 2026-03-10 | 2026-05-10 | 24/08/2026 | 2026-04-09 | 456 | 456
ADIDAS | 0903208441-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 459 | 15/10/2026 | 459 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 07-Aug. 650010 | HT SUB PROCESS_V1 | 0903208441 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 459 |  | 459 |  |  | 2026-03-10 | 2026-05-10 | 28/08/2026 | 13/09/2026 | 459 | 459 |  |  |  | 2026-02-10 | 2026-03-10 | 26/08/2026 | 2026-03-09 | 459 | 459
ADIDAS | 0903208442-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 518 | 15/10/2026 | 518 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 688010 | HT SUB PROCESS_V1 | 0903208442 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 518 |  | 518 |  |  | 2026-05-10 | 2026-06-10 |  |  | 518 |  | 518 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 14/09/2026 | 518 | 517 | 1 |  | 4
ADIDAS | 0903208443-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 653 | 14/10/2026 | 653 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 684009 | HT SUB PROCESS_V1 | 0903208443 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 653 |  | 653 |  |  | 2026-02-10 | 2026-03-10 |  |  | 653 |  | 653 |  |  | 2026-01-10 | 2026-02-10 | 28/08/2026 | 2026-03-09 | 653 | 653
ADIDAS | 0903209735-1 KT4840 | ONIX | 90D | S2408MR1600 | 1046 | 14/10/2026 | 1046 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 684009 | HT SUB PROCESS_V1 | 0903209735 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 1046 |  | 1046 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1046 |  | 1046 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1046 |  | 1046
ADIDAS | 0903209736-1 KT4840 | ONIX | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug. 650010 | HT SUB PROCESS_V1 | 0903209736 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903209737-1 KT4840 | ONIX | 90D | S2408MR1600 | 2722 | 15/10/2026 | 2722 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Far Eastern, Body: PI Date 21-Sep (2380 yd). Waiting fabric. T2 Fu Hsun, Mesh: PI Date 03-Aug, ETD ?? Waiting fabric. T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug (480 yd). 678002 | HT SUB PROCESS_V1 | 0903209737 KT4840 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 22/10/2026 |  |  | 2722 |  | 2722 |  |  | 16/10/2026 | 20/10/2026 |  |  | 2722 |  | 2722 |  |  | 15/10/2026 | 19/10/2026 |  |  | 2722 |  | 2722
ADIDAS | 0903209739-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 15/09/2026 | 324 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903209739 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-03-09 | 15/09/2026 | 324 | 324 |  |  |  | 29/08/2026 | 2026-12-09 | 22/08/2026 | 2026-02-09 | 324 | 324 |  |  |  | 28/08/2026 | 2026-11-09 | 22/08/2026 | 2026-11-09 | 324 | 324
ADIDAS | 0903209741-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 30/09/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209741 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 17/09/2026 | 2026-05-09 | 15/09/2026 | 300 | 221 | 79 |  |  | 29/08/2026 | 15/09/2026 | 24/08/2026 | 2026-03-09 | 300 | 300 |  |  |  | 28/08/2026 | 14/09/2026 | 22/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0903209742-1 IN1156 | BLACK | 90D | S2408MR1600 | 319 | 30/09/2026 | 319 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516443 | HT SUB PROCESS_V1 | 0903209742 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 17/09/2026 | 2026-05-09 | 15/09/2026 | 319 | 319 |  |  |  | 29/08/2026 | 15/09/2026 | 24/08/2026 | 2026-03-09 | 319 | 319 |  |  |  | 28/08/2026 | 14/09/2026 | 22/08/2026 | 2026-08-09 | 319 | 319
ADIDAS | 0903209744-1 IN1156 | BLACK | 90D | S2408MR1600 | 3278 | 15/10/2026 | 3278 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209744 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 26/10/2026 |  |  | 3278 |  | 3278 |  |  | 20/10/2026 | 23/10/2026 |  |  | 3278 |  | 3278 |  |  | 19/10/2026 | 22/10/2026 |  |  | 3278 |  | 3278
ADIDAS | 0903209745-1 IN1156 | BLACK | 90D | S2408MR1600 | 145 | 23/09/2026 | 145 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209745 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 17/09/2026 |  |  | 145 |  | 145 |  |  | 2026-12-09 | 15/09/2026 |  |  | 145 |  | 145 |  |  | 2026-11-09 | 14/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903209746-1 IN1156 | BLACK | 90D | S2408MR1600 | 726 | 15/10/2026 | 726 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209746 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 726 |  | 726 |  |  | 29/09/2026 | 30/09/2026 |  |  | 726 |  | 726 |  |  | 28/09/2026 | 29/09/2026 |  |  | 726 |  | 726
ADIDAS | 0903209747-1 IN1156 | BLACK | 90D | S2408MR1600 | 6000 | 15/10/2026 | 6000 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209747 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 23/10/2026 |  |  | 6000 |  | 6000 |  |  | 14/10/2026 | 21/10/2026 |  |  | 6000 |  | 6000 |  |  | 13/10/2026 | 20/10/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903209748-1 IN1156 | BLACK | 90D | S2408MR1600 | 1095 | 15/10/2026 | 1095 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903209748 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 1095 |  | 1095 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1095 |  | 1095 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1095 |  | 1095
ADIDAS | 0903209749-1 IN1156 | BLACK | 90D | S2408MR1600 | 1353 | 15/10/2026 | 1353 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903209749 IN1156 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-09-10 |  |  | 1353 |  | 1353 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1353 |  | 1353 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1353 |  | 1353
ADIDAS | 0903209750-1 IN1156 | BLACK | 90D | S2408MR1600 | 1119 | 15/10/2026 | 1119 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209750 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 1119 |  | 1119 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1119 |  | 1119 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1119 |  | 1119
ADIDAS | 0903209751-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903209751 IN1156 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903209755-1 IN1157 | WHITE | 90D | S2408MR1600 | 2425 | 15/10/2026 | 2425 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209755 IN1157 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-08-10 |  |  | 2425 |  | 2425 |  |  | 2026-02-10 | 2026-06-10 |  |  | 2425 |  | 2425 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2425 |  | 2425
ADIDAS | 0903209756-1 IN1157 | WHITE | 90D | S2408MR1600 | 310 | 15/10/2026 | 310 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Far Eastern, PI Date 21-Sep, actual recieves 06-Aug (using fabric from Y.T.I.) T2 Y.T.I, Mesh: ETD 10-Jul, actual recieves 06-Aug. 650010 | HT SUB PROCESS_V1 | 0903209756 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 310 |  | 310 |  |  | 29/09/2026 | 30/09/2026 | 2026-10-09 | 2026-12-09 | 310 | 302 | 8 |  |  | 28/09/2026 | 29/09/2026 | 2026-03-09 | 2026-08-09 | 310 | 302 | 8
ADIDAS | 0903209757-1 IN1157 | WHITE | 90D | S2408MR1600 | 8000 | 30/09/2026 | 8000 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). Waiting fabric (Damco offline). T2 Far Eastern, Body: PI Date 21-Sep (1389 yd). Waiting fabric. T2 Y.T.I, body&mesh ETD 10-Jul, ETA-Kaha 08-Aug (body: 6202yd). 688010 | HT SUB PROCESS_V1 | 0903209757 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 2026-01-10 |  |  | 8000 |  | 8000 |  |  | 19/09/2026 | 29/09/2026 |  |  | 8000 |  | 8000 |  |  | 18/09/2026 | 28/09/2026 |  |  | 8000 |  | 8000
ADIDAS | 0903209758-1 IN1157 | WHITE | 90D | S2408MR1600 | 1268 | 14/10/2026 | 1268 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903209758 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 1268 |  | 1268 |  |  | 26/09/2026 | 28/09/2026 |  |  | 1268 |  | 1268 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903209760-1 IN1172 | BLACK | 90D | S2408WR1600 | 302 | 15/09/2026 | 302 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516406 | HT SUB PROCESS_V1 | 0903209760 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 2026-07-09 | 302 | 302 |  |  |  | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-09-09 | 302 | 302 |  |  |  | 28/08/2026 | 29/08/2026 | 29/08/2026 | 2026-05-09 | 302 | 302
ADIDAS | 0903209762-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209762 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 17/09/2026 |  |  | 300 |  | 300 |  |  | 15/09/2026 | 15/09/2026 | 27/08/2026 | 28/08/2026 | 300 | 300 |  |  |  | 14/09/2026 | 14/09/2026 | 26/08/2026 | 28/08/2026 | 300 | 300
ADIDAS | 0903209764-1 IN1172 | BLACK | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516254 | HT SUB PROCESS_V1 | 0903209764 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 349 |  | 349 |  |  | 19/10/2026 | 20/10/2026 |  |  | 349 |  | 349 |  |  | 17/10/2026 | 19/10/2026 |  |  | 349 |  | 349
ADIDAS | 0903209765-1 IN1172 | BLACK | 90D | S2408WR1600 | 2646 | 15/10/2026 | 2646 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209765 IN1172 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 27/10/2026 |  |  | 2646 |  | 2646 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2646 |  | 2646 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2646 |  | 2646
ADIDAS | 0903209766-1 IN1172 | BLACK | 90D | S2408WR1600 | 428 | 15/10/2026 | 428 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 672027 | HT SUB PROCESS_V1 | 0903209766 IN1172 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 428 |  | 428 |  |  | 19/10/2026 | 20/10/2026 |  |  | 428 |  | 428 |  |  | 17/10/2026 | 19/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903209767-1 IN1172 | BLACK | 90D | S2408WR1600 | 945 | 15/10/2026 | 945 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | 680015 | HT SUB PROCESS_V1 | 0903209767 IN1172 |  | KAHATEX CIJERAH | CHILE | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 945 |  | 945 |  |  | 20/10/2026 | 21/10/2026 |  |  | 945 |  | 945 |  |  | 19/10/2026 | 20/10/2026 |  |  | 945 |  | 945
ADIDAS | 0903209768-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 15/10/2026 | 760 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209768 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 760 |  | 760 |  |  | 17/10/2026 | 19/10/2026 |  |  | 760 |  | 760 |  |  | 16/10/2026 | 17/10/2026 |  |  | 760 |  | 760
ADIDAS | 0903209769-1 IN1172 | BLACK | 90D | S2408WR1600 | 677 | 14/10/2026 | 677 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT SUB PROCESS_V1 | 0903209769 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 677 |  | 677 |  |  | 17/10/2026 | 19/10/2026 |  |  | 677 |  | 677 |  |  | 16/10/2026 | 17/10/2026 |  |  | 677 |  | 677
ADIDAS | 0903209780-1 KG8547 | ONIX | 90D | S2408WR1600 | 278 | 15/10/2026 | 278 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (Damco offline). 688010 | HT SUB PROCESS_V1 | 0903209780 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 278 |  | 278 |  |  | 17/10/2026 | 19/10/2026 |  |  | 278 |  | 278 |  |  | 16/10/2026 | 17/10/2026 |  |  | 278 |  | 278
ADIDAS | 0903209781-1 KG8547 | ONIX | 90D | S2408WR1600 | 532 | 15/10/2026 | 532 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209781 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 532 |  | 532 |  |  | 17/10/2026 | 19/10/2026 |  |  | 532 |  | 532 |  |  | 16/10/2026 | 17/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903209782-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903209782 KG8547 | 21/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903209783-1 KG8547 | ONIX | 90D | S2408WR1600 | 382 | 15/10/2026 | 382 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 960026 | HT SUB PROCESS_V1 | 0903209783 KG8547 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 382 |  | 382 |  |  | 2026-10-10 | 2026-12-10 |  |  | 382 |  | 382 |  |  | 2026-09-10 | 2026-10-10 |  |  | 382 |  | 382
ADIDAS | 0903209784-1 KG8547 | ONIX | 90D | S2408WR1600 | 902 | 15/10/2026 | 902 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | 678002 | HT SUB PROCESS_V1 | 0903209784 KG8547 |  | KAHATEX CIJERAH | ARGENTINA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 902 |  | 902 |  |  | 19/10/2026 | 20/10/2026 |  |  | 902 |  | 902 |  |  | 17/10/2026 | 19/10/2026 |  |  | 902 |  | 902
ADIDAS | 0903209785-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 104 | 30/09/2026 | 104 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903209785 KX9838 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 104 |  | 104 |  |  | 25/09/2026 | 26/09/2026 | 21/08/2026 | 27/08/2026 | 104 | 104 |  |  |  | 24/09/2026 | 25/09/2026 | 15/08/2026 | 26/08/2026 | 104 | 104
ADIDAS | 0903209786-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 3723 | 31/08/2026 | 3723 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209786 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 14/08/2026 | 27/08/2026 | 19/08/2026 | 27/08/2026 | 3723 | 3723 |  |  |  | 2026-12-08 | 24/08/2026 | 18/08/2026 | 26/08/2026 | 3723 | 3723 |  |  |  | 2026-11-08 | 21/08/2026 | 18/08/2026 | 27/08/2026 | 3723 | 3723
ADIDAS | 0903209787-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 512 | 15/10/2026 | 512 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903209787 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 512 |  | 512 |  |  | 24/10/2026 | 26/10/2026 | 21/08/2026 | 31/08/2026 | 512 | 512 |  |  |  | 23/10/2026 | 24/10/2026 | 21/08/2026 | 29/08/2026 | 512 | 512
ADIDAS | 0903209788-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 628 | 15/10/2026 | 628 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903209788 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 628 |  | 628 |  |  | 2026-05-10 | 2026-06-10 | 21/08/2026 | 31/08/2026 | 628 | 628 |  |  |  | 2026-03-10 | 2026-05-10 | 21/08/2026 | 29/08/2026 | 628 | 628
ADIDAS | 0903209789-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 80 | 31/08/2026 | 80 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209789 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 26/08/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 26/08/2026 | 27/08/2026 | 26/08/2026 | 27/08/2026 | 80 | 80 |  |  |  | 21/08/2026 | 24/08/2026 | 22/08/2026 | 22/08/2026 | 80 | 80 |  |  |  | 20/08/2026 | 21/08/2026 | 22/08/2026 | 22/08/2026 | 80 | 80
ADIDAS | 0903209799-1 KG8547 | ONIX | 90D | S2408WR1600 | 1750 | 30/09/2026 | 1750 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 08-Aug. 672027 | HT SUB PROCESS_V1 | 0903209799 KG8547 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 19/09/2026 |  |  | 1750 |  | 1750 |  |  | 15/09/2026 | 17/09/2026 | 2026-09-09 | 14/09/2026 | 1750 | 1496 | 254 |  | 1 | 14/09/2026 | 16/09/2026 | 2026-09-09 | 14/09/2026 | 1750 | 1533 | 217 |  | 38
ADIDAS | 0903209801-1 IN1173 | WHITE | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516254 | HT SUB PROCESS_V1 | 0903209801 IN1173 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 349 |  | 349 |  |  | 2026-07-10 | 2026-08-10 | 14/08/2026 | 2026-01-09 | 349 | 349 |  |  |  | 2026-06-10 | 2026-07-10 | 13/08/2026 | 31/08/2026 | 349 | 349
ADIDAS | 0903209802-1 IN1173 | WHITE | 90D | S2408WR1600 | 1288 | 15/10/2026 | 1288 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 678002 | HT SUB PROCESS_V1 | 0903209802 IN1173 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 1288 |  | 1288 |  |  | 2026-09-10 | 2026-12-10 | 15/08/2026 | 2026-04-09 | 1288 | 1288 |  |  |  | 2026-08-10 | 2026-10-10 | 14/08/2026 | 31/08/2026 | 1288 | 1288
ADIDAS | 0903209803-1 IN1173 | WHITE | 90D | S2408WR1600 | 550 | 14/10/2026 | 550 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 680015 | HT SUB PROCESS_V1 | 0903209803 IN1173 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 14/10/2026 |  |  | 550 |  | 550 |  |  | 2026-09-10 | 2026-12-10 | 15/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 2026-08-10 | 2026-10-10 | 14/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903209804-1 IN1173 | WHITE | 90D | S2408WR1600 | 1445 | 15/10/2026 | 1445 | SI | SI07/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 659018 | HT SUB PROCESS_V1 | 0903209804 IN1173 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 1445 |  | 1445 |  |  | 24/09/2026 | 25/09/2026 | 19/08/2026 | 2026-02-09 | 1445 | 1445 |  |  |  | 23/09/2026 | 24/09/2026 | 15/08/2026 | 2026-02-09 | 1445 | 1445
ADIDAS | 0903209805-1 IN1173 | WHITE | 90D | S2408WR1600 | 555 | 15/10/2026 | 555 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650010 | HT SUB PROCESS_V1 | 0903209805 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-03-10 |  |  | 555 |  | 555 |  |  | 2026-01-10 | 2026-01-10 |  |  | 555 |  | 555 |  |  | 30/09/2026 | 30/09/2026 |  |  | 555 |  | 555
ADIDAS | 0903209806-1 IN1173 | WHITE | 90D | S2408WR1600 | 892 | 14/10/2026 | 892 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 684009 | HT SUB PROCESS_V1 | 0903209806 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 892 |  | 892 |  |  | 2026-08-10 | 2026-09-10 | 19/08/2026 | 27/08/2026 | 892 | 890 | 2 |  |  | 2026-07-10 | 2026-08-10 | 15/08/2026 | 27/08/2026 | 892 | 890 | 2
ADIDAS | 0903209808-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 1211 | 30/09/2026 | 1211 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903209808 IT1462 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | ADIZERO E TEE |  | SS27-YTI | 23/09/2026 | 24/09/2026 |  |  | 1211 |  | 1211 |  |  | 21/09/2026 | 22/09/2026 | 2026-07-09 | 15/09/2026 | 1211 | 1192 | 19 |  |  | 19/09/2026 | 21/09/2026 | 2026-07-09 | 14/09/2026 | 1211 | 1198 | 13 |  | 18
ADIDAS | 0903209809-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 451 | 15/10/2026 | 451 | SI | SI07/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903209809 IT1462 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 451 |  | 451 |  |  | 15/10/2026 | 16/10/2026 | 2026-09-09 | 15/09/2026 | 451 | 439 | 12 |  |  | 14/10/2026 | 15/10/2026 | 2026-09-09 | 14/09/2026 | 451 | 439 | 12 |  | 4
ADIDAS | 0903245395-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903245395 KA4331 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903245423-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 680015 | HT SUB PROCESS_V1 | 0903245423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-08-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-08-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-05-10 |  |  | 300 |  | 300
ADIDAS | 0903247791-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 501 | 15/10/2026 | 501 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247791 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 501 |  | 501 |  |  | 29/09/2026 | 2026-01-10 |  |  | 501 |  | 501
ADIDAS | 0903247818-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 118 | 15/10/2026 | 118 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 630001 | PRINT L1 SUB PROCESS_V3 | 0903247818 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 118 |  | 118 |  |  | 2026-02-10 | 2026-03-10 |  |  | 118 |  | 118
ADIDAS | 0903247851-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247851 LG8052 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-10 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-07-10 |  |  | 100 |  | 100
ADIDAS | 0903247873-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247873 LI7657 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903247906-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 630001 | PRINT L3 SUB PROCESS_V3 | 0903247906 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903247928-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 210 | 15/10/2026 | 210 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247928 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 210 |  | 210 |  |  | 29/09/2026 | 30/09/2026 |  |  | 210 |  | 210
ADIDAS | 0903247950-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 377 | 15/10/2026 | 377 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247950 LI7659 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 377 |  | 377 |  |  | 2026-01-10 | 2026-02-10 |  |  | 377 |  | 377
ADIDAS | 0903247975-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 15/10/2026 | 65 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247975 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-08-10 | 2026-08-10 |  |  | 65 |  | 65 |  |  | 2026-06-10 | 2026-06-10 |  |  | 65 |  | 65 |  |  | 2026-05-10 | 2026-05-10 |  |  | 65 |  | 65
ADIDAS | 0903247991-1 IN1159 | BLACK | 90D | S2408MR1601 | 15 | 15/10/2026 | 15 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | 29/09: ex-fty. Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903247991 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-08-10 | 2026-08-10 |  |  | 15 |  | 15 |  |  | 2026-06-10 | 2026-06-10 |  |  | 15 |  | 15 |  |  | 2026-05-10 | 2026-05-10 |  |  | 15 |  | 15
ADIDAS | 0903248016-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 14 | 30/09/2026 | 14 | AN | AN10/07/2026 | G1H | JACKET | G1 | (10/08/2026) | ok | 29/09: ex-fty. T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248016 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 14 |  | 14 |  |  | 21/09/2026 | 22/09/2026 |  |  | 14 |  | 14
ADIDAS | 0903248122-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4486 | 31/08/2026 | 4486 | SA | SA10/07/2026 | G3A,G3G | SWEATSHIRT | G3 | ok | ok | 29/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248122 IB8688 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | ESS HDY |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 28/08/2026 | 4486 | 4486 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 4486 | 4486
ADIDAS | 0903248578-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 485 | 15/10/2026 | 485 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903248578 KV7863 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-07-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 485 |  | 485 |  |  | 2026-04-11 | 2026-05-11 |  |  | 485 |  | 485
ADIDAS | 0903248979-1 IN1160 | WHITE | 90D | S2408MR1601 | 1173 | 15/10/2026 | 1173 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT SUB PROCESS_V1 | 0903248979 IN1160 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-08-10 | 2026-12-10 |  |  | 1173 |  | 1173
ADIDAS | 0903249675-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249675 JE6338 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 1150 |  | 1150 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1150 |  | 1150
ADIDAS | 0903249702-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516442 | PAD+HT SUB PROCESS_V3 | 0903249702 IT3474 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 29/10/2026 | 31/10/2026 |  |  | 1795 |  | 1795 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1795 |  | 1795 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249724-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516318 | PAD+HT SUB PROCESS_V3 | 0903249724 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 26/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 24/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903249752-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249752 JD1877 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 1610 |  | 1610 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1610 |  | 1610
ADIDAS | 0903249777-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249777 JE6341 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 432 |  | 432 |  |  | 29/09/2026 | 2026-02-10 |  |  | 432 |  | 432
ADIDAS | 0903249802-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 600 | 15/10/2026 | 600 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249802 JE6338 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 600 |  | 600 |  |  | 2026-02-10 | 2026-05-10 |  |  | 600 |  | 600
ADIDAS | 0903249832-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 299 | 15/10/2026 | 299 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249832 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 299 |  | 299 |  |  | 26/10/2026 | 27/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903249858-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249858 JM1776 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | M SL WV PT 2 |  | SS27 | 30/10/2026 | 2026-03-11 |  |  | 575 |  | 575 |  |  | 27/10/2026 | 30/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903249889-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516205 | PAD+HT SUB PROCESS_V3 | 0903249889 IT3474 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 31/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 31/10/2026 | 2026-03-11 |  |  | 1795 |  | 1795 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1795 |  | 1795 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249911-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4300 | 31/08/2026 | 4300 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903249911 IB8688 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 19/08/2026 | 29/08/2026 | 4300 | 4300 |  |  |  | 18/08/2026 | 27/08/2026 | 15/08/2026 | 31/08/2026 | 4300 | 4291 | 9
ADIDAS | 0903249935-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 4300 | 31/08/2026 | 4300 | SA | SA10/07/2026 | G3A,G3G | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903249935 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 19/08/2026 | ESS HDY |  | SS27 | 19/08/2026 | 31/08/2026 | 21/08/2026 | 29/08/2026 | 4300 | 4300 |  |  |  | 13/08/2026 | 27/08/2026 | 19/08/2026 | 29/08/2026 | 4300 | 4300
ADIDAS | 0903249963-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/10/2026 | 300 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249963 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903250004-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 23/09/2026 | 300 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903250004 JG8642 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 300 | 162 | 138
ADIDAS | 0903250015-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250015 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 30/10/2026 | M SL WV PT 2 |  | SS27 | 30/10/2026 | 2026-03-11 |  |  | 575 |  | 575 |  |  | 27/10/2026 | 30/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903250038-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 326 | 2026-12-09 | 326 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250038 KA0544 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 326 | 326 |  |  |  | 31/08/2026 | 2026-09-09 | 31/08/2026 | 31/08/2026 | 326 | 326
ADIDAS | 0903250043-1 HK7309 | BLACK | 45D | F2225M402 | 1200 | 26/08/2026 | 1200 | SA | SA10/07/2026 | G1N | SWEATSHIRT | G1 | ok |  | 24/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903250043 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 13/08/2026 | ESS HDY |  | SS27 | 13/08/2026 | 21/08/2026 | 13/08/2026 | 21/08/2026 | 1200 | 1200 |  |  |  | 2026-10-08 | 18/08/2026 | 2026-12-08 | 22/08/2026 | 1200 | 1200
ADIDAS | 0903250069-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 304 | 2026-12-09 | 304 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250069 KA0546 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-03-09 | 304 | 304
ADIDAS | 0903250091-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 840 | 15/10/2026 | 840 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250091 JD1877 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 840 |  | 840 |  |  | 25/09/2026 | 28/09/2026 |  |  | 840 |  | 840
ADIDAS | 0903250102-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 378 | 15/10/2026 | 378 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250102 JM1775 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 378 |  | 378 |  |  | 13/10/2026 | 15/10/2026 |  |  | 378 |  | 378
ADIDAS | 0903250117-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250117 JE6341 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-10 | M 3S FT FZ HD |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 828 |  | 828 |  |  | 29/09/2026 | 2026-02-10 |  |  | 828 |  | 828
ADIDAS | 0903250128-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250128 JM1776 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 342 |  | 342 |  |  | 26/10/2026 | 27/10/2026 |  |  | 342 |  | 342
ADIDAS | 0903250411-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 116 | 15/10/2026 | 116 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903250411 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 116 |  | 116 |  |  | 2026-03-10 | 2026-03-10 |  |  | 116 |  | 116
ADIDAS | 0903250503-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903250503 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 107 |  | 107 |  |  | 24/09/2026 | 25/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903250530-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250530 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 107 |  | 107 |  |  | 2026-03-10 | 2026-05-10 |  |  | 107 |  | 107
ADIDAS | 0903250563-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 449 | 15/10/2026 | 449 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (03/08/2026) | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250563 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 449 |  | 449 |  |  | 23/09/2026 | 24/09/2026 |  |  | 449 |  | 449
ADIDAS | 0903250949-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L1 SUB PROCESS_V3 | 0903250949 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 28/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250973-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903250973 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903250977-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250977 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 372 |  | 372 |  |  | 2026-06-10 | 2026-08-10 |  |  | 372 |  | 372
ADIDAS | 0903251020-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251020 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | W 3S FT FZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 230 |  | 230 |  |  | 27/10/2026 | 28/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903251026-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251026 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/09/2026 | MINI EMB T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 590 |  | 590 |  |  | 25/09/2026 | 26/09/2026 |  |  | 590 |  | 590 |  |  | 23/09/2026 | 24/09/2026 |  |  | 590 |  | 590
ADIDAS | 0903251047-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903251047 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 396 |  | 396 |  |  | 24/09/2026 | 25/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903251051-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G3D | SHORTS | G3 | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 848012 | PAD+HT SUB PROCESS_V3 | 0903251051 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | RUN IT SHORT BLACK |  | SS27-TI | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903251082-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1720 | 15/10/2026 | 1720 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903251082 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 1720 |  | 1720 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1720 |  | 1720
ADIDAS | 0903251111-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1136 | 15/10/2026 | 1136 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251111 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/10/2026 | W 3S FT CF PT |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 1136 |  | 1136 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1136 |  | 1136
ADIDAS | 0903251135-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251135 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1610 |  | 1610 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1610 |  | 1610
ADIDAS | 0903251695-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 714 | 15/10/2026 | 714 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251695 JE0052 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 31/10/2026 | W 3S FT FZ HD |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 714 |  | 714 |  |  | 28/10/2026 | 29/10/2026 |  |  | 714 |  | 714
ADIDAS | 0903251728-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251728 KA5089 | 26/08/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/09/2026 | MINI EMB T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 602 |  | 602 |  |  | 25/09/2026 | 26/09/2026 |  |  | 602 |  | 602 |  |  | 23/09/2026 | 24/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903251751-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 124 | 15/10/2026 | 124 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903251751 IU0217 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 124 |  | 124 |  |  | 21/09/2026 | 21/09/2026 | 2026-10-09 | 2026-11-09 | 124 | 20 | 104
ADIDAS | 0903251769-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 890 | 15/10/2026 | 890 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251769 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S FT FZ HD |  | SS27 | 28/10/2026 | 30/10/2026 |  |  | 890 |  | 890 |  |  | 24/10/2026 | 27/10/2026 |  |  | 890 |  | 890
ADIDAS | 0903251842-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1686 | 15/10/2026 | 1686 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251842 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 1686 |  | 1686 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1686 |  | 1686
ADIDAS | 0903251958-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 469 | 15/10/2026 | 469 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 826010 | PRINT L2+PAD SUB PROCESS_V3 | 0903251958 LC8884 |  | KAHATEX CIJERAH | TURKEY | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 469 |  | 469 |  |  | 2026-07-10 | 2026-08-10 | 26/08/2026 | 2026-03-09 | 469 | 314 | 155
ADIDAS | 0903252061-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 481 | 15/10/2026 | 481 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252061 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-06-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-06-11 | 2026-07-11 |  |  | 481 |  | 481 |  |  | 2026-03-11 | 2026-04-11 |  |  | 481 |  | 481
ADIDAS | 0903252085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 354 | 15/10/2026 | 354 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252085 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 354 |  | 354 |  |  | 2026-04-11 | 2026-05-11 |  |  | 354 |  | 354
ADIDAS | 0903252116-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 128 | 15/10/2026 | 128 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903252116 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M ADI RETRO T WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 128 |  | 128 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-09 | 2026-11-09 | 128 | 110 | 18
ADIDAS | 0903252150-1 HK7309 | BLACK | 45D | F2225M402 | 4488 | 28/08/2026 | 4488 | SA | SA10/07/2026 | G1E,G1F,G1N,G1P | SWEATSHIRT | G1 | ok | ok | 28/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo-capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903252150 HK7309 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/08/2026 | ESS HDY |  | SS27 | 13/08/2026 | 28/08/2026 | 18/08/2026 | 28/08/2026 | 4488 | 4488 |  |  |  | 2026-10-08 | 24/08/2026 | 13/08/2026 | 2026-09-09 | 4488 | 4488
ADIDAS | 0903252175-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252175 JM1775 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | M SL WV PT 2 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 576 |  | 576 |  |  | 16/10/2026 | 17/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903252182-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 360 | 15/10/2026 | 360 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903252182 KX8875 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-12-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 360 |  | 360 |  |  | 2026-08-10 | 2026-08-10 |  |  | 360 |  | 360
ADIDAS | 0903252230-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 826010 | HT SUB PROCESS_V1 | 0903252230 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 200 |  | 200 |  |  | 23/09/2026 | 24/09/2026 |  |  | 200 |  | 200 |  |  | 22/09/2026 | 23/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903252254-1 IN1156 | BLACK | 90D | S2408MR1600 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903252254 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-05-10 |  |  | 590 |  | 590 |  |  | 30/09/2026 | 2026-02-10 |  |  | 590 |  | 590 |  |  | 29/09/2026 | 2026-01-10 |  |  | 590 |  | 590
ADIDAS | 0903252439-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252439 LI7657 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 101 |  | 101 |  |  | 2026-05-10 | 2026-06-10 |  |  | 101 |  | 101
ADIDAS | 0903252473-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252473 LI7658 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 117 |  | 117 |  |  | 28/09/2026 | 29/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903252503-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252503 LI7656 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 101 |  | 101 |  |  | 28/09/2026 | 29/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903252539-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252539 LI7659 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 117 |  | 117 |  |  | 2026-01-10 | 2026-02-10 |  |  | 117 |  | 117
ADIDAS | 0903252570-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 230 | 2026-12-09 | 230 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 1st Art (TC 10 pcs) 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903252570 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-04-09 | 2026-09-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-10-09 | 230 | 230
ADIDAS | 0903252644-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/10/2026 | 140 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252644 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 140 |  | 140 |  |  | 26/10/2026 | 27/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903253096-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 201 | 15/10/2026 | 201 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903253096 KV0458 |  | KAHATEX CIJERAH | THAILAND | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 201 |  | 201 |  |  | 22/09/2026 | 24/09/2026 |  |  | 201 |  | 201
ADIDAS | 0903253164-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1421 | 15/10/2026 | 1421 | SA | SA10/07/2026 | G2O | JACKET | G2 | ok | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253164 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M 3S FT FZ HD |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1421 |  | 1421 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1421 |  | 1421
ADIDAS | 0903253174-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253174 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | M SL WV PT 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 288 |  | 288 |  |  | 26/10/2026 | 27/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903253193-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1909 | 15/10/2026 | 1909 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903253193 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 1909 |  | 1909 |  |  | 2026-03-10 | 2026-07-10 |  |  | 1909 |  | 1909
ADIDAS | 0903253213-1 HL2236 | BLACK/WHITE | 45D | F224CSIM430 | 14004 | 28/08/2026 | 14004 | AT | AT10/07/2026 | G2E,G2Q,G2T,G3B,G3E | PANTS | G2,G3 | ok | ok | 28/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253213 HL2236 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | IN RANGE |  | SS27 | 14/08/2026 | 28/08/2026 | 2026-12-08 | 28/08/2026 | 14004 | 14004 |  |  |  | 2026-11-08 | 24/08/2026 | 2026-10-08 | 29/08/2026 | 14004 | 14004
ADIDAS | 0903253229-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253229 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-11 | M SL WV PT 2 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 600 |  | 600 |  |  | 30/10/2026 | 31/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253235-1 H12215 | DARK GREY HEATHER/BLACK | 45D | F213CSIM105FL | 1258 | 26/08/2026 | 1258 | AT | AT10/07/2026 | G2T | SWEATSHIRT | G2 | ok |  | 24/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253235 H12215 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | M FEELCOZY HD |  | SS27 | 14/08/2026 | 26/08/2026 | 18/08/2026 | 21/08/2026 | 1258 | 1258 |  |  |  | 2026-11-08 | 20/08/2026 | 2026-11-08 | 21/08/2026 | 1258 | 1258
ADIDAS | 0903253258-1 HL2243 | DARK GREY HEATHER/BLACK | 45D | F224CSIM430 | 11444 | 31/08/2026 | 11444 | AT | AT10/07/2026 | G3F,G3J | PANTS | G3 | ok | ok | 29/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253258 HL2243 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | IN RANGE |  | SS27 | 14/08/2026 | 29/08/2026 | 14/08/2026 | 29/08/2026 | 11444 | 11444 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-08-08 | 2026-07-09 | 11444 | 11444
ADIDAS | 0903253259-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 650 | 15/10/2026 | 650 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253259 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 650 |  | 650 |  |  | 2026-07-10 | 2026-09-10 |  |  | 650 |  | 650
ADIDAS | 0903253275-1 HL2236 | BLACK/WHITE | 45D | F224CSIM430 | 15000 | 31/08/2026 | 15000 | AT | AT10/07/2026 | G3B,G3C,G3E,G3F | PANTS | G3 | ok | ok | 29/08: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903253275 HL2236 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | IN RANGE |  | SS27 | 21/08/2026 | 31/08/2026 | 19/08/2026 | 29/08/2026 | 15000 | 15000 |  |  |  | 18/08/2026 | 27/08/2026 | 13/08/2026 | 29/08/2026 | 15000 | 15000
ADIDAS | 0903253286-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253286 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 27/10/2026 | W 3S FT FZ HD |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 600 |  | 600 |  |  | 23/10/2026 | 24/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253287-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 200 | 15/10/2026 | 200 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903253287 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 200 |  | 200 |  |  | 14/10/2026 | 15/10/2026 |  |  | 200 |  | 200 |  |  | 13/10/2026 | 14/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903253304-1 H12215 | DARK GREY HEATHER/BLACK | 45D | F213CSIM105FL | 15000 | 28/08/2026 | 15000 | AT | AT10/07/2026 | G2P,G2S,G2T | SWEATSHIRT | G2 | ok | ok | 28/08: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253304 H12215 | 2026-11-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | M FEELCOZY HD |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 15000 | 15000 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-11-08 | 28/08/2026 | 15000 | 15000
ADIDAS | 0903253312-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 374 | 15/10/2026 | 374 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253312 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 374 |  | 374 |  |  | 26/10/2026 | 27/10/2026 |  |  | 374 |  | 374
ADIDAS | 0903253327-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253327 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 600 |  | 600 |  |  | 17/10/2026 | 19/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253337-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 105 | 15/10/2026 | 105 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903253337 KX0123 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M ADI RETRO T WHITE |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 105 |  | 105 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-09 | 2026-11-09 | 105 | 91 | 14
ADIDAS | 0903253341-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 582 | 15/10/2026 | 582 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253341 JE6341 |  | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 582 |  | 582 |  |  | 2026-06-10 | 2026-08-10 |  |  | 582 |  | 582
ADIDAS | 0903253374-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253374 JD5302 |  | KAHATEX CIJERAH | UKRAINE | SEA | 30/10/2026 | W 3S FT CF PT |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 1000 |  | 1000 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903253396-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253396 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 26/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 558 |  | 558 |  |  | 23/09/2026 | 24/09/2026 |  |  | 558 |  | 558
ADIDAS | 0903253447-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512110 | PRINT L2+HT SUB PROCESS_V3 | 0903253447 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903253455-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 191 | 15/10/2026 | 191 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903253455 LD0277 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 22/09/2026 | 22/09/2026 |  |  | 191 |  | 191 |  |  | 18/09/2026 | 18/09/2026 |  |  | 191 |  | 191 |  |  | 17/09/2026 | 17/09/2026 |  |  | 191 |  | 191
ADIDAS | 0903253532-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 20 | 15/10/2026 | 20 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903253532 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 17/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 20 |  | 20 |  |  | 14/10/2026 | 14/10/2026 |  |  | 20 |  | 20 |  |  | 13/10/2026 | 13/10/2026 |  |  | 20 |  | 20
ADIDAS | 0903253551-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 637 | 2026-07-10 | 637 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253551 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 637 |  | 637 |  |  | 23/09/2026 | 24/09/2026 | 2026-04-09 | 15/09/2026 | 637 | 570 | 67 |  | 1
ADIDAS | 0903253557-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 268 | 15/10/2026 | 268 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253557 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 268 |  | 268 |  |  | 2026-01-10 | 2026-03-10 |  |  | 268 |  | 268
ADIDAS | 0903253577-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 347 | 2026-07-10 | 347 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253577 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 347 |  | 347 |  |  | 23/09/2026 | 24/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 192 | 155
ADIDAS | 0903253610-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 351 | 30/09/2026 | 351 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253610 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 351 |  | 351 |  |  | 18/09/2026 | 18/09/2026 | 28/08/2026 | 2026-04-09 | 351 | 294 | 57
ADIDAS | 0903253694-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903253694 JC8238 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903253810-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903253810 KX8875 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 368 |  | 368 |  |  | 2026-08-10 | 2026-08-10 |  |  | 368 |  | 368
ADIDAS | 0903253870-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 936 | 15/10/2026 | 936 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516204 | PAD+HT SUB PROCESS_V3 | 0903253870 IT3474 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 27/10/2026 | 29/10/2026 |  |  | 936 |  | 936 |  |  | 23/10/2026 | 26/10/2026 |  |  | 936 |  | 936 |  |  | 22/10/2026 | 24/10/2026 |  |  | 936 |  | 936
ADIDAS | 0903253904-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253904 JE6338 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1150 |  | 1150 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1150 |  | 1150
ADIDAS | 0903253938-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4737 | 31/08/2026 | 4737 | SA | SA10/07/2026 | G1F,G1N,G1P,G3A,G3D | SWEATSHIRT | G1,G3 | ok | ok | 31/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253938 HK7311 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 27/08/2026 | ESS HDY |  | SS27 | 27/08/2026 | 31/08/2026 | 26/08/2026 | 31/08/2026 | 4737 | 4737 |  |  |  | 21/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 4737 | 4737
ADIDAS | 0903253967-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253967 JE6341 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M 3S FT FZ HD |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 828 |  | 828 |  |  | 2026-08-10 | 2026-10-10 |  |  | 828 |  | 828
ADIDAS | 0903253995-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253995 JD1877 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 1610 |  | 1610 |  |  | 2026-02-10 | 2026-06-10 |  |  | 1610 |  | 1610
ADIDAS | 0903254049-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254049 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | W 3S FT FZ HD |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 230 |  | 230 |  |  | 22/10/2026 | 23/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903254053-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 116 | 15/10/2026 | 116 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903254053 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 17/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 17/10/2026 | 19/10/2026 |  |  | 116 |  | 116 |  |  | 14/10/2026 | 15/10/2026 |  |  | 116 |  | 116 |  |  | 13/10/2026 | 14/10/2026 |  |  | 116 |  | 116
ADIDAS | 0903254056-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254056 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | M SL WV PT 2 |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 576 |  | 576 |  |  | 15/10/2026 | 16/10/2026 |  |  | 576 |  | 576
ADIDAS | 0903254089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903254089 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 396 |  | 396 |  |  | 30/09/2026 | 2026-02-10 |  |  | 396 |  | 396
ADIDAS | 0903254113-1 HK7309 | BLACK | 45D | F2225M402 | 4302 | 31/08/2026 | 4302 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254113 HK7309 | 2026-11-08 | KAHATEX CIJERAH | SPAIN | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 20/08/2026 | 31/08/2026 | 4302 | 4302 |  |  |  | 18/08/2026 | 27/08/2026 | 18/08/2026 | 2026-02-09 | 4302 | 4302
ADIDAS | 0903254136-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4583 | 31/08/2026 | 4583 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 29/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 1st Art (TC 20 pcs) 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254136 HK7311 | 2026-11-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 28/08/2026 | 4583 | 4583 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 31/08/2026 | 4583 | 4583
ADIDAS | 0903254175-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1182 | 15/10/2026 | 1182 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877).. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254175 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 1182 |  | 1182 |  |  | 2026-07-11 | 2026-09-11 |  |  | 1182 |  | 1182
ADIDAS | 0903254325-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903254325 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 340 |  | 340 |  |  | 24/09/2026 | 25/09/2026 |  |  | 340 |  | 340
ADIDAS | 0903254356-1 KZ3049 | BLACK | 90D | S2762LHMEDR109W | 330 | 15/10/2026 | 330 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903254356 KZ3049 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER GR GFCTP W BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-03-10 |  |  | 330 |  | 330
ADIDAS | 0903254368-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254368 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | J FOOTBALL T |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-07-10 | 2026-11-09 | 2026-11-09 | 100 | 8 | 92
ADIDAS | 0903254387-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254387 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 372 |  | 372 |  |  | 2026-03-10 | 2026-05-10 |  |  | 372 |  | 372
ADIDAS | 0903254402-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 130 | 15/10/2026 | 130 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903254402 KV0458 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 130 |  | 130 |  |  | 22/09/2026 | 24/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903254581-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 457 | 15/10/2026 | 457 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254581 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 457 |  | 457 |  |  | 2026-03-10 | 2026-05-10 |  |  | 457 |  | 457
ADIDAS | 0903254614-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 380 | 15/10/2026 | 380 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L3 SUB PROCESS_V3 | 0903254614 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 380 |  | 380 |  |  | 2026-05-10 | 2026-05-10 |  |  | 380 |  | 380
ADIDAS | 0903254741-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903254741 JD1881 |  | KAHATEX CIJERAH | ISRAEL | SEA | 14/10/2026 | M 3S FT TC PT |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1203 |  | 1203 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903254860-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 229 | 15/10/2026 | 229 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254860 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M ADI RETRO T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 229 |  | 229 |  |  | 2026-08-10 | 2026-09-10 | 2026-11-09 | 2026-11-09 | 229 | 201 | 28
ADIDAS | 0903254861-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 312 | 15/10/2026 | 312 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254861 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | W 3S FT FZ HD |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 312 |  | 312 |  |  | 22/10/2026 | 23/10/2026 |  |  | 312 |  | 312
ADIDAS | 0903254872-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2S | SHORTS | G2 | (20/08/2026) | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903254872 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 558 |  | 558 |  |  | 30/09/2026 | 2026-02-10 |  |  | 558 |  | 558
ADIDAS | 0903254887-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 108 | 15/10/2026 | 108 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903254887 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 108 |  | 108 |  |  | 29/09/2026 | 2026-01-10 |  |  | 108 |  | 108
ADIDAS | 0903254914-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 1750 | 15/10/2026 | 1750 | AN | AN10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 09-Jun, ETD 10-Aug, ETA-Kaha 21-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254914 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/10/2026 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 24/10/2026 | 29/10/2026 |  |  | 1750 |  | 1750 |  |  | 21/10/2026 | 26/10/2026 |  |  | 1750 |  | 1750
ADIDAS | 0903254921-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254921 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 288 |  | 288 |  |  | 13/10/2026 | 15/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903254928-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2400 | 31/08/2026 | 2400 | SI | SI10/07/2026 | G2G,G2H,G2L | T-SHIRT | G2 | ok | ok | 31/08: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903254928 KD4066 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | M BLANK TEE BLACK |  | SS27 | 21/08/2026 | 31/08/2026 | 24/08/2026 | 31/08/2026 | 2400 | 2400 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 31/08/2026 | 2400 | 2396 | 4
ADIDAS | 0903254980-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 619 | 15/10/2026 | 619 | SI | SI10/07/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254980 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 619 |  | 619 |  |  | 15/10/2026 | 17/10/2026 |  |  | 619 |  | 619
ADIDAS | 0903255009-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 389 | 15/10/2026 | 389 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255009 LG8051 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 29/09/2026 | 29/09/2026 |  |  | 389 |  | 389 |  |  | 25/09/2026 | 25/09/2026 |  |  | 389 |  | 389
ADIDAS | 0903255022-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 135 | 15/10/2026 | 135 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903255022 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 135 |  | 135 |  |  | 2026-07-10 | 2026-09-10 |  |  | 135 |  | 135
ADIDAS | 0903255023-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1203 | 2026-09-09 | 1203 | SA | SA10/07/2026 | G3G | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255023 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 29/08/2026 | 2026-05-09 | 1203 | 1203 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-04-09 | 1203 | 1203
ADIDAS | 0903255038-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255038 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 169 |  | 169 |  |  | 30/09/2026 | 2026-01-10 |  |  | 169 |  | 169
ADIDAS | 0903255050-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255050 IZ0443 | 2026-11-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-02-09 | 2026-09-09 | 276 | 276
ADIDAS | 0903255078-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 161 | 15/10/2026 | 161 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903255078 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 19/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 161 |  | 161 |  |  | 15/10/2026 | 15/10/2026 |  |  | 161 |  | 161 |  |  | 14/10/2026 | 14/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903255103-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 276 | 2026-12-09 | 276 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255103 KA0546 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 276 | 276 |  |  |  | 28/08/2026 | 2026-09-09 | 13/08/2026 | 2026-03-09 | 276 | 276
ADIDAS | 0903255118-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 344 | 15/10/2026 | 344 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255118 LG8052 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 344 |  | 344 |  |  | 2026-06-10 | 2026-07-10 |  |  | 344 |  | 344
ADIDAS | 0903255151-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903255151 LI7657 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER GR NNTEE M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903255192-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 492 | 15/10/2026 | 492 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | T2 Formosa, PI Date 08-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255192 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 492 |  | 492 |  |  | 30/10/2026 | 31/10/2026 |  |  | 492 |  | 492
ADIDAS | 0903255212-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1894 | 15/10/2026 | 1894 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Formosa, PI Date 08-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255212 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-11 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 1894 |  | 1894 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1894 |  | 1894
ADIDAS | 0903255230-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 287 | 15/10/2026 | 287 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255230 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 287 |  | 287 |  |  | 2026-01-10 | 2026-02-10 |  |  | 287 |  | 287
ADIDAS | 0903255277-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 234 | 15/10/2026 | 234 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255277 LI7658 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 234 |  | 234 |  |  | 29/09/2026 | 30/09/2026 |  |  | 234 |  | 234
ADIDAS | 0903255316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 365 | 15/10/2026 | 365 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 365 |  | 365 |  |  | 29/09/2026 | 30/09/2026 |  |  | 365 |  | 365
ADIDAS | 0903255344-1 IN1173 | WHITE | 90D | S2408WR1600 | 2980 | 15/10/2026 | 2980 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 960006 | HT SUB PROCESS_V1 | 0903255344 IN1173 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-08-10 |  |  | 2980 |  | 2980 |  |  | 2026-01-10 | 2026-06-10 |  |  | 2980 |  | 2980 |  |  | 30/09/2026 | 2026-05-10 |  |  | 2980 |  | 2980
ADIDAS | 0903255352-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 180 | 15/10/2026 | 180 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903255352 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 180 |  | 180 |  |  | 30/09/2026 | 2026-01-10 |  |  | 180 |  | 180
ADIDAS | 0903255377-1 IN1157 | WHITE | 90D | S2408MR1600 | 3100 | 15/10/2026 | 3100 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903255377 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 14/10/2026 |  |  | 3100 |  | 3100 |  |  | 2026-07-10 | 2026-12-10 | 2026-09-09 | 14/09/2026 | 3100 | 565 | 2535 |  | 59 | 2026-06-10 | 2026-10-10 | 2026-04-09 | 15/09/2026 | 3100 | 581 | 2519 |  | 9
ADIDAS | 0903255384-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 204 | 15/10/2026 | 204 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903255384 LI7658 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 204 |  | 204 |  |  | 28/09/2026 | 29/09/2026 |  |  | 204 |  | 204
ADIDAS | 0903255415-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903255415 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903255423-1 IN1159 | BLACK | 90D | S2408MR1601 | 3310 | 15/10/2026 | 3310 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT SUB PROCESS_V1 | 0903255423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 14/10/2026 | 20/10/2026 |  |  | 3310 |  | 3310 |  |  | 2026-12-10 | 17/10/2026 |  |  | 3310 |  | 3310 |  |  | 2026-10-10 | 16/10/2026 |  |  | 3310 |  | 3310
ADIDAS | 0903255441-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 960 | 15/10/2026 | 960 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L3 SUB PROCESS_V3 | 0903255441 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 960 |  | 960 |  |  | 30/09/2026 | 2026-01-10 |  |  | 960 |  | 960
ADIDAS | 0903255467-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 1080 | 15/10/2026 | 1080 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L1 SUB PROCESS_V3 | 0903255467 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 1080 |  | 1080 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1080 |  | 1080
ADIDAS | 0903255589-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903255589 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903255616-1 IN1172 | BLACK | 90D | S2408WR1600 | 4574 | 15/10/2026 | 4574 | SI | SI10/07/2026 | G1I | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255616 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 20/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-12-10 | 17/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-10-10 | 16/10/2026 |  |  | 4574 |  | 4574
ADIDAS | 0903255630-1 KA4331 | BLACK | 90D | S2608MR0902 | 1734 | 15/10/2026 | 1734 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255630 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-01-10 | 2026-05-10 |  |  | 1734 |  | 1734 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1734 |  | 1734 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1734 |  | 1734
ADIDAS | 0903255643-1 IN1173 | WHITE | 90D | S2408WR1600 | 4544 | 15/10/2026 | 4544 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903255643 IN1173 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 14/10/2026 |  |  | 4544 |  | 4544 |  |  | 2026-06-10 | 2026-12-10 |  |  | 4544 |  | 4544 |  |  | 2026-05-10 | 2026-10-10 |  |  | 4544 |  | 4544
ADIDAS | 0903255659-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1202 | 28/08/2026 | 1202 | SA | SA10/07/2026 | G3D | SWEATSHIRT | G3 | ok | ok | 27/08: ex-fty. IMPROVE. DRC 0002-T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255659 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 20/08/2026 | ESS HDY |  | SS27 | 20/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 1202 | 1202 |  |  |  | 14/08/2026 | 24/08/2026 | 14/08/2026 | 28/08/2026 | 1202 | 1202
ADIDAS | 0903255693-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1026 | 15/10/2026 | 1026 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516204 | PAD+HT SUB PROCESS_V3 | 0903255693 KF5295 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 1026 |  | 1026 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1026 |  | 1026 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1026 |  | 1026
ADIDAS | 0903255699-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 509 | 15/10/2026 | 509 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255699 KV7863 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 509 |  | 509 |  |  | 2026-05-11 | 2026-07-11 |  |  | 509 |  | 509
ADIDAS | 0903255776-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1452 | 15/10/2026 | 1452 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255776 JE6414 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-10-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 1452 |  | 1452 |  |  | 2026-07-10 | 2026-10-10 |  |  | 1452 |  | 1452
ADIDAS | 0903255800-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 149 | 15/10/2026 | 149 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512102 | PRINT L2+HT SUB PROCESS_V3 | 0903255800 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 149 |  | 149 |  |  | 15/10/2026 | 15/10/2026 |  |  | 149 |  | 149 |  |  | 14/10/2026 | 14/10/2026 |  |  | 149 |  | 149
ADIDAS | 0903255801-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1140 | 15/10/2026 | 1140 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255801 JE6338 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 1140 |  | 1140 |  |  | 2026-06-10 | 2026-08-10 |  |  | 1140 |  | 1140
ADIDAS | 0903255819-1 HK7309 | BLACK | 45D | F2225M402 | 4302 | 31/08/2026 | 4302 | SA | SA10/07/2026 | G1F,G1N,G1P | SWEATSHIRT | G1 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255819 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 21/08/2026 | ESS HDY |  | SS27 | 21/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 4302 | 4302 |  |  |  | 18/08/2026 | 27/08/2026 | 19/08/2026 | 2026-02-09 | 4302 | 4302
ADIDAS | 0903255833-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 918 | 15/10/2026 | 918 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255833 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 22/10/2026 | M SL WV PT 2 |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 918 |  | 918 |  |  | 19/10/2026 | 20/10/2026 |  |  | 918 |  | 918
ADIDAS | 0903255882-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1546 | 15/10/2026 | 1546 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255882 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-12-10 |  |  | 1546 |  | 1546 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1546 |  | 1546
ADIDAS | 0903255885-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 4737 | 31/08/2026 | 4737 | SA | SA10/07/2026 | G3D,G3G,G3H,G3I | SWEATSHIRT | G3 | ok | ok | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). IMPROVE. T2 Paiho Indo, capacity problem, PI Date 18-Aug, actual receives 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255885 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | ESS HDY |  | SS27 | 26/08/2026 | 31/08/2026 | 26/08/2026 | 31/08/2026 | 4737 | 4737 |  |  |  | 20/08/2026 | 27/08/2026 | 21/08/2026 | 31/08/2026 | 4737 | 4737
ADIDAS | 0903255908-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255908 JE6419 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1278 |  | 1278
ADIDAS | 0903255912-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516205 | PAD+HT SUB PROCESS_V3 | 0903255912 KF5295 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 17/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 1967 |  | 1967 |  |  | 14/10/2026 | 17/10/2026 |  |  | 1967 |  | 1967 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903255968-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516442 | PAD+HT SUB PROCESS_V3 | 0903255968 KF5295 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 14/10/2026 | 17/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-10-10 | 14/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903256022-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256022 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-11 | M SL WV PT 2 |  | SS27 | 2026-05-11 | 2026-07-11 |  |  | 896 |  | 896 |  |  | 2026-02-11 | 2026-04-11 |  |  | 896 |  | 896
ADIDAS | 0903256045-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 181 | 15/10/2026 | 181 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 848024 | PRINT L2+HT SUB PROCESS_V3 | 0903256045 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 19/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 181 |  | 181 |  |  | 15/10/2026 | 15/10/2026 |  |  | 181 |  | 181 |  |  | 14/10/2026 | 14/10/2026 |  |  | 181 |  | 181
ADIDAS | 0903256347-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256347 JD5302 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/10/2026 | W 3S FT CF PT |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 896 |  | 896 |  |  | 26/10/2026 | 27/10/2026 |  |  | 896 |  | 896
ADIDAS | 0903256411-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | (20/08/2026) | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903256411 JE6417 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-02-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1278 |  | 1278 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1278 |  | 1278
ADIDAS | 0903256435-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1230 | 15/10/2026 | 1230 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903256435 JE6341 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 1230 |  | 1230 |  |  | 25/09/2026 | 29/09/2026 |  |  | 1230 |  | 1230
ADIDAS | 0903256461-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 792 | 15/10/2026 | 792 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256461 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-04-11 | M SL WV PT 2 |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 792 |  | 792 |  |  | 31/10/2026 | 2026-02-11 |  |  | 792 |  | 792
ADIDAS | 0903256486-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 113 | 15/10/2026 | 113 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903256486 LC8882 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-12-10 | M ADI RETRO T BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 113 |  | 113 |  |  | 2026-08-10 | 2026-09-10 |  |  | 113 |  | 113
ADIDAS | 0903256510-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1210 | 15/10/2026 | 1210 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256510 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | M SL WV PT 2 |  | SS27 | 26/10/2026 | 29/10/2026 |  |  | 1210 |  | 1210 |  |  | 22/10/2026 | 26/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903256620-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 14/10/2026 | 610 | AN | AN10/07/2026 | G3D | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256620 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 610 |  | 610 |  |  | 26/10/2026 | 26/10/2026 |  |  | 610 |  | 610
ADIDAS | 0903256755-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 209 | 15/10/2026 | 209 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256755 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 209 |  | 209 |  |  | 24/09/2026 | 25/09/2026 |  |  | 209 |  | 209
ADIDAS | 0903256779-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 119 | 15/10/2026 | 119 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903256779 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 119 |  | 119 |  |  | 24/09/2026 | 25/09/2026 |  |  | 119 |  | 119
ADIDAS | 0903256801-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 121 | 15/10/2026 | 121 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256801 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 121 |  | 121 |  |  | 24/09/2026 | 25/09/2026 |  |  | 121 |  | 121
ADIDAS | 0903256821-1 KE3743 | BLACK | 30D | F25ORIGFXBLANKW | 2387 | 28/08/2026 | 2387 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/08: ex-fty 1st Art (TC 10 pcs) 960026 | EMBRO SUB PROCESS_V1 | 0903256821 KE3743 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | W BLANK TEE |  | SS27 | 18/08/2026 | 28/08/2026 | 19/08/2026 | 28/08/2026 | 2387 | 2387 |  |  |  | 2026-12-08 | 24/08/2026 | 14/08/2026 | 21/08/2026 | 2387 | 2387
ADIDAS | 0903256825-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 132 | 15/10/2026 | 132 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903256825 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 132 |  | 132 |  |  | 2026-03-10 | 2026-05-10 |  |  | 132 |  | 132
ADIDAS | 0903256846-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 216 | 15/10/2026 | 216 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256846 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 216 |  | 216 |  |  | 2026-03-10 | 2026-03-10 |  |  | 216 |  | 216
ADIDAS | 0903256847-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 210 | 15/10/2026 | 210 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256847 JE6346 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | M 3S FT TC PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 210 |  | 210 |  |  | 2026-06-10 | 2026-07-10 |  |  | 210 |  | 210
ADIDAS | 0903256851-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256851 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 288 |  | 288 |  |  | 2026-01-10 | 2026-03-10 |  |  | 288 |  | 288
ADIDAS | 0903256871-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 124 | 15/10/2026 | 124 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903256871 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 124 |  | 124 |  |  | 2026-03-10 | 2026-03-10 |  |  | 124 |  | 124
ADIDAS | 0903256878-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 299 | 15/10/2026 | 299 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256878 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | M 3S FT TC PT |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 299 |  | 299 |  |  | 2026-09-10 | 2026-10-10 |  |  | 299 |  | 299
ADIDAS | 0903256884-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256884 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-06-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-06-11 | 2026-07-11 |  |  | 342 |  | 342 |  |  | 2026-03-11 | 2026-04-11 |  |  | 342 |  | 342
ADIDAS | 0903256891-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 269 | 15/10/2026 | 269 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903256891 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 269 |  | 269 |  |  | 2026-03-10 | 2026-05-10 |  |  | 269 |  | 269
ADIDAS | 0903256901-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256901 LF1392 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 107 |  | 107 |  |  | 2026-06-10 | 2026-09-10 |  |  | 107 |  | 107
ADIDAS | 0903256955-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 219 | 15/10/2026 | 219 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256955 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 30/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 219 |  | 219 |  |  | 27/10/2026 | 28/10/2026 |  |  | 219 |  | 219
ADIDAS | 0903256972-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 123 | 15/10/2026 | 123 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512102 | PRINT L2+PAD SUB PROCESS_V3 | 0903256972 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 123 |  | 123 |  |  | 2026-07-10 | 2026-08-10 |  |  | 123 |  | 123
ADIDAS | 0903257022-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257022 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 120 |  | 120 |  |  | 2026-06-10 | 2026-09-10 |  |  | 120 |  | 120
ADIDAS | 0903257161-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 176 | 15/10/2026 | 176 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257161 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 176 |  | 176 |  |  | 24/09/2026 | 25/09/2026 |  |  | 176 |  | 176
ADIDAS | 0903257172-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 119 | 15/10/2026 | 119 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257172 LG8055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 119 |  | 119 |  |  | 2026-02-10 | 2026-02-10 |  |  | 119 |  | 119
ADIDAS | 0903257177-1 IS1413 | BLACK | 60D | S2425M405 | 1203 | 2026-12-09 | 1203 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903257177 IS1413 | 26/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | IN RANGE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 1203 | 1203 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-03-09 | 2026-11-09 | 1203 | 1203
ADIDAS | 0903257182-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 336 | 15/10/2026 | 336 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257182 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 336 |  | 336 |  |  | 2026-02-10 | 2026-05-10 |  |  | 336 |  | 336
ADIDAS | 0903257198-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 404 | 15/10/2026 | 404 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257198 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 404 |  | 404 |  |  | 2026-02-10 | 2026-03-10 |  |  | 404 |  | 404
ADIDAS | 0903257203-1 HK7309 | BLACK | 45D | F2225M402 | 1653 | 2026-09-09 | 1653 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257203 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 31/08/2026 | 2026-07-09 | 1653 | 1653 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-10-09 | 1653 | 1653
ADIDAS | 0903257227-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 101 | 15/10/2026 | 101 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257227 LG8056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-02-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903257252-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 848 | 15/10/2026 | 848 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257252 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 848 |  | 848 |  |  | 2026-01-10 | 2026-02-10 |  |  | 848 |  | 848
ADIDAS | 0903257280-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1098 | 15/10/2026 | 1098 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903257280 IB8686 |  | KAHATEX CIJERAH | ISRAEL | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 1098 |  | 1098 |  |  | 26/09/2026 | 28/09/2026 |  |  | 1098 |  | 1098
ADIDAS | 0903257284-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257284 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 169 |  | 169 |  |  | 29/09/2026 | 29/09/2026 |  |  | 169 |  | 169
ADIDAS | 0903257292-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903257292 JC8238 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 195 |  | 195 |  |  | 25/09/2026 | 26/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903257307-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 177 | 15/10/2026 | 177 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257307 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 177 |  | 177 |  |  | 28/09/2026 | 28/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903257317-1 KD4067 | WHITE | 30D | F25ORIGFXBLANKW | 2398 | 28/08/2026 | 2398 | SA | SA10/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok | ok | 28/08: ex-fty 1st Art (TC 10 pcs) 960026 | EMBRO SUB PROCESS_V1 | 0903257317 KD4067 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 18/08/2026 | W BLANK TEE |  | SS27 | 18/08/2026 | 28/08/2026 | 18/08/2026 | 28/08/2026 | 2398 | 2398 |  |  |  | 2026-12-08 | 24/08/2026 | 2026-12-08 | 31/08/2026 | 2398 | 2398
ADIDAS | 0903257329-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT SUB PROCESS_V1 | 0903257329 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-03-10 |  |  | 100 |  | 100
ADIDAS | 0903257350-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 140 | 15/10/2026 | 140 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257350 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 22/09/2026 | 22/09/2026 |  |  | 140 |  | 140 |  |  | 18/09/2026 | 18/09/2026 |  |  | 140 |  | 140 |  |  | 17/09/2026 | 17/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903257370-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 302 | 15/10/2026 | 302 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257370 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | W 3S WV SHO |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 302 |  | 302 |  |  | 2026-05-10 | 2026-06-10 |  |  | 302 |  | 302
ADIDAS | 0903257378-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 178 | 15/10/2026 | 178 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257378 LF1392 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 178 |  | 178 |  |  | 2026-06-10 | 2026-09-10 |  |  | 178 |  | 178
ADIDAS | 0903257558-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 296 | 2026-12-09 | 296 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903257558 KA0544 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 296 | 296 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-01-09 | 296 | 296
ADIDAS | 0903257658-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 272 | 15/10/2026 | 272 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257658 KY3737 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 25/09/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 25/09/2026 | 25/09/2026 |  |  | 272 |  | 272 |  |  | 22/09/2026 | 22/09/2026 |  |  | 272 |  | 272
ADIDAS | 0903257671-1 IN1159 | BLACK | 90D | S2408MR1601 | 2727 | 15/10/2026 | 2727 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903257671 IN1159 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-08-10 | 14/10/2026 |  |  | 2727 |  | 2727 |  |  | 2026-06-10 | 2026-12-10 |  |  | 2727 |  | 2727 |  |  | 2026-05-10 | 2026-10-10 |  |  | 2727 |  | 2727
ADIDAS | 0903257687-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257687 KV0458 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 224 |  | 224 |  |  | 22/09/2026 | 24/09/2026 |  |  | 224 |  | 224
ADIDAS | 0903257700-1 IN8707 | BLACK | 105D | S2408WR1601A | 2203 | 15/10/2026 | 2203 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903257700 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 17/10/2026 | 22/10/2026 |  |  | 2203 |  | 2203 |  |  | 15/10/2026 | 20/10/2026 |  |  | 2203 |  | 2203 |  |  | 14/10/2026 | 19/10/2026 |  |  | 2203 |  | 2203
ADIDAS | 0903257706-1 IS1413 | BLACK | 60D | S2425M405 | 396 | 2026-07-10 | 396 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903257706 IS1413 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 396 |  | 396 |  |  | 21/09/2026 | 21/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903257728-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903257728 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300
ADIDAS | 0903257736-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 636 | 15/10/2026 | 636 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257736 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 636 |  | 636 |  |  | 29/09/2026 | 30/09/2026 |  |  | 636 |  | 636
ADIDAS | 0903257740-1 KA4331 | BLACK | 90D | S2608MR0902 | 483 | 15/10/2026 | 483 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257740 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 483 |  | 483 |  |  | 2026-06-10 | 2026-07-10 |  |  | 483 |  | 483 |  |  | 2026-05-10 | 2026-06-10 |  |  | 483 |  | 483
ADIDAS | 0903257744-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903257744 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 23/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903257771-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 534 | 15/10/2026 | 534 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257771 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 534 |  | 534 |  |  | 2026-01-10 | 2026-01-10 |  |  | 534 |  | 534
ADIDAS | 0903257785-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 218 | 15/10/2026 | 218 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848024 | PRINT L2+PAD SUB PROCESS_V3 | 0903257785 LC8884 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 218 |  | 218 |  |  | 2026-07-10 | 2026-08-10 | 26/08/2026 | 29/08/2026 | 218 | 199 | 19
ADIDAS | 0903257807-1 KA4331 | BLACK | 90D | S2608MR0902 | 334 | 15/10/2026 | 334 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903257807 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 334 |  | 334 |  |  | 2026-03-10 | 2026-05-10 |  |  | 334 |  | 334 |  |  | 2026-02-10 | 2026-03-10 |  |  | 334 |  | 334
ADIDAS | 0903257817-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 113 | 15/10/2026 | 113 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257817 LE4307 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 113 |  | 113 |  |  | 2026-01-10 | 2026-03-10 |  |  | 113 |  | 113
ADIDAS | 0903257833-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 128 | 15/10/2026 | 128 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 848012 | EMBRO SUB PROCESS_V1 | 0903257833 HK7303 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 128 |  | 128 |  |  | 26/09/2026 | 26/09/2026 |  |  | 128 |  | 128
ADIDAS | 0903257863-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 111 | 15/10/2026 | 111 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903257863 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 111 |  | 111 |  |  | 26/09/2026 | 26/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903257897-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257897 JD1877 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-03-10 | M 3S FT FZ HD |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1278 |  | 1278
ADIDAS | 0903257898-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3008 | 15/10/2026 | 3008 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257898 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 29/09/2026 | 2026-03-10 |  |  | 3008 |  | 3008 |  |  | 25/09/2026 | 30/09/2026 |  |  | 3008 |  | 3008
ADIDAS | 0903257913-1 KA4331 | BLACK | 90D | S2608MR0902 | 306 | 15/10/2026 | 306 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257913 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 306 |  | 306 |  |  | 2026-03-10 | 2026-05-10 |  |  | 306 |  | 306 |  |  | 2026-02-10 | 2026-03-10 |  |  | 306 |  | 306
ADIDAS | 0903258010-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1100 | 15/10/2026 | 1100 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903258010 JG8642 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1100 |  | 1100 |  |  | 29/09/2026 | 2026-01-10 | 2026-09-09 | 2026-11-09 | 1100 | 1056 | 44
ADIDAS | 0903258064-1 KA0527 | PURE RUBY S25 | 60D | S26KJUGFX003 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 1st Art (TC 10 pcs) 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258064 KA0527 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | J SUMMER T |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-10-10 | 15/09/2026 | 15/09/2026 | 100 | 59 | 41
ADIDAS | 0903258118-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903258118 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 368 |  | 368 |  |  | 2026-07-10 | 2026-08-10 | 2026-09-09 | 2026-09-09 | 368 | 349 | 19
ADIDAS | 0903258121-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 117 | 15/10/2026 | 117 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258121 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 117 |  | 117 |  |  | 2026-06-10 | 2026-09-10 |  |  | 117 |  | 117
ADIDAS | 0903258209-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 272 | 15/10/2026 | 272 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903258209 LI7655 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 272 |  | 272 |  |  | 2026-01-10 | 2026-01-10 |  |  | 272 |  | 272
ADIDAS | 0903258233-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1002 | 15/10/2026 | 1002 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903258233 JE6419 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1002 |  | 1002 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1002 |  | 1002
ADIDAS | 0903258257-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1403 | 2026-09-09 | 1403 | SA | SA10/07/2026 | G3H | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258257 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403
ADIDAS | 0903258325-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 111 | 15/10/2026 | 111 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903258325 LI7660 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 111 |  | 111 |  |  | 29/09/2026 | 29/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903258342-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 1448 | 15/10/2026 | 1448 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258342 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 1448 |  | 1448 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1448 |  | 1448
ADIDAS | 0903258375-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903258375 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-01-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903258592-1 KH3706 | WHITE | 60D | S26FBWCGFX410 | 1 | 26/08/2026 | 1 | SI | SI10/07/2026 | G1P | T-SHIRT | G1 |  |  | 24/08: ex-fty 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903258592 KH3706 | 26/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | WC HC T PHILI |  | SS27-WC | 29/07/2026 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 1 | 1 |  |  |  | 24/07/2026 | 31/07/2026 | 2026-05-08 | 2026-05-08 | 1 | 1
ADIDAS | 0903258612-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 2 | 15/10/2026 | 2 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903258612 IT1469 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 2 |  | 2 |  |  | 2026-08-10 | 2026-09-10 |  |  | 2 |  | 2 |  |  | 2026-07-10 | 2026-08-10 |  |  | 2 |  | 2
ADIDAS | 0903258647-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 4605 | 15/10/2026 | 4605 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903258647 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 13/10/2026 |  |  | 4605 |  | 4605 |  |  | 2026-06-10 | 2026-10-10 |  |  | 4605 |  | 4605 |  |  | 2026-05-10 | 2026-09-10 |  |  | 4605 |  | 4605
ADIDAS | 0903258675-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 2130 | 15/10/2026 | 2130 | SI | SI10/07/2026 | G1D | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258675 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 26/10/2026 |  |  | 2130 |  | 2130 |  |  | 19/10/2026 | 23/10/2026 |  |  | 2130 |  | 2130 |  |  | 17/10/2026 | 22/10/2026 |  |  | 2130 |  | 2130
ADIDAS | 0903258696-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 510 | 14/10/2026 | 510 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258696 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 510 |  | 510 |  |  | 2026-03-10 | 2026-06-10 |  |  | 510 |  | 510
ADIDAS | 0903258702-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258702 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 120 |  | 120 |  |  | 2026-07-10 | 2026-08-10 | 2026-11-09 | 2026-11-09 | 120 | 19 | 101
ADIDAS | 0903258720-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1066 | 15/10/2026 | 1066 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903258720 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 1066 |  | 1066 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1066 |  | 1066
ADIDAS | 0903258750-1 IN1157 | WHITE | 90D | S2408MR1600 | 6183 | 15/10/2026 | 6183 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903258750 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 21/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-12-10 | 19/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-10-10 | 17/10/2026 |  |  | 6183 |  | 6183
ADIDAS | 0903258776-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 488 | 15/10/2026 | 488 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258776 LF1392 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 488 |  | 488 |  |  | 2026-06-10 | 2026-09-10 |  |  | 488 |  | 488
ADIDAS | 0903258807-1 IN8707 | BLACK | 105D | S2408WR1601A | 65 | 15/10/2026 | 65 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258807 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 17/10/2026 | 22/10/2026 |  |  | 65 |  | 65 |  |  | 15/10/2026 | 20/10/2026 |  |  | 65 |  | 65 |  |  | 14/10/2026 | 19/10/2026 |  |  | 65 |  | 65
ADIDAS | 0903258822-1 IN1156 | BLACK | 90D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258822 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 1 |  | 1 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1 |  | 1 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903258858-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 672027 | HT SUB PROCESS_V1 | 0903258858 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 250 |  | 250 |  |  | 19/10/2026 | 20/10/2026 |  |  | 250 |  | 250 |  |  | 17/10/2026 | 19/10/2026 | 2026-04-09 | 2026-12-09 | 250 | 81 | 169
ADIDAS | 0903258889-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903258889 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-07-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903258929-1 IN1157 | WHITE | 90D | S2408MR1600 | 145 | 15/10/2026 | 145 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258929 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADIZERO E TEE |  | SS27-YTI | 2026-01-10 | 2026-02-10 |  |  | 145 |  | 145 |  |  | 29/09/2026 | 30/09/2026 |  |  | 145 |  | 145 |  |  | 28/09/2026 | 29/09/2026 |  |  | 145 |  | 145
ADIDAS | 0903258964-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 05-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258964 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 | 20/08/2026 | 29/08/2026 | 100 | 99 | 1 |  |  | 2026-10-10 | 2026-12-10 | 19/08/2026 | 28/08/2026 | 100 | 99 | 1
ADIDAS | 0903258997-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903258997 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 60 |  | 60 |  |  | 2026-05-10 | 2026-06-10 |  |  | 60 |  | 60 |  |  | 2026-03-10 | 2026-05-10 |  |  | 60 |  | 60
ADIDAS | 0903259051-1 KA4331 | BLACK | 90D | S2608MR0902 | 62 | 15/10/2026 | 62 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903259051 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 62 |  | 62 |  |  | 2026-06-10 | 2026-07-10 |  |  | 62 |  | 62 |  |  | 2026-05-10 | 2026-06-10 |  |  | 62 |  | 62
ADIDAS | 0903259083-1 KT4839 | ONIX | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903259083 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 30/09/2026 | 2026-03-10 |  |  | 60 |  | 60 |  |  | 28/09/2026 | 2026-01-10 |  |  | 60 |  | 60 |  |  | 26/09/2026 | 30/09/2026 |  |  | 60 |  | 60
ADIDAS | 0903259087-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259087 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-03-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903259113-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 228 | 15/10/2026 | 228 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903259113 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 228 |  | 228 |  |  | 2026-03-10 | 2026-05-10 |  |  | 228 |  | 228
ADIDAS | 0903259117-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 135 | 15/10/2026 | 135 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903259117 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 17/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 17/10/2026 | 17/10/2026 |  |  | 135 |  | 135 |  |  | 14/10/2026 | 14/10/2026 |  |  | 135 |  | 135 |  |  | 13/10/2026 | 13/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903259145-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I., PI Date 14-Aug, material quality issues body: stain), body&mesh actual receives 18-Aug. 672027 | HT SUB PROCESS_V1 | 0903259145 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-02-10 | 2026-03-10 | 2026-04-09 | 2026-07-09 | 100 | 98 | 2 |  |  | 2026-01-10 | 2026-02-10 | 29/08/2026 | 15/09/2026 | 100 | 100
ADIDAS | 0903259225-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 101 | 15/10/2026 | 101 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903259225 JE6419 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 101 |  | 101 |  |  | 24/09/2026 | 25/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903259421-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 35000 | 30/09/2026 | 35000 | SA | SA10/07/2026 | G2I,G2J,G2L | T-SHIRT | G2 | ok | ok | 29/09: ex-fty (1x20). DRC 0090-early shipment customer (GTS89140-1 Early Shipment Order 0903259421). 834012 | HT+PAD SUB PROCESS_V3 | 0903259421 KB5966 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 17/09/2026 | Run Ess Tee M |  | SS27-TI | 17/09/2026 | 2026-03-10 |  |  | 35000 |  | 35000 |  |  | 14/09/2026 | 30/09/2026 | 2026-10-09 | 15/09/2026 | 35000 | 12441 | 22559 |  | 1601 | 2026-11-09 | 28/09/2026 | 2026-10-09 | 15/09/2026 | 35000 | 16379 | 18621 |  | 4222
ADIDAS | 0903259496-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1820 | 15/10/2026 | 1820 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903259496 JE6346 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-10 | M 3S FT TC PT |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 1820 |  | 1820 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1820 |  | 1820
ADIDAS | 0903259552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 440 | 15/10/2026 | 440 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259552 KV7963 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 16/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 440 |  | 440 |  |  | 13/10/2026 | 13/10/2026 |  |  | 440 |  | 440
ADIDAS | 0903259631-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 425 | 15/10/2026 | 425 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259631 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/10/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 425 |  | 425 |  |  | 13/10/2026 | 13/10/2026 |  |  | 425 |  | 425
ADIDAS | 0903259656-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259656 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 396 |  | 396 |  |  | 25/09/2026 | 28/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903259689-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 270 | 15/10/2026 | 270 | SI | SI10/07/2026 | G3C | PANTS | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259689 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 29/10/2026 | W 3S FT CF PT |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 270 |  | 270 |  |  | 26/10/2026 | 27/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903259717-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903259717 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 432 |  | 432 |  |  | 2026-06-10 | 2026-07-10 |  |  | 432 |  | 432
ADIDAS | 0903259814-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 371 | 15/10/2026 | 371 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259814 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 371 |  | 371 |  |  | 2026-05-11 | 2026-07-11 |  |  | 371 |  | 371
ADIDAS | 0903259865-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259865 JC8239 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 195 |  | 195 |  |  | 24/09/2026 | 25/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903259938-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 200 | 15/10/2026 | 200 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259938 JG8642 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-02-10 | W LIN FT SHO |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 200 |  | 200 |  |  | 29/09/2026 | 2026-01-10 | 2026-11-09 | 2026-11-09 | 200 | 60 | 140
ADIDAS | 0903260199-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903260199 JD1877 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1203 |  | 1203 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903260217-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 703 | 15/10/2026 | 703 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260217 JE0052 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | W 3S FT FZ HD |  | SS27 | 28/10/2026 | 28/10/2026 |  |  | 703 |  | 703 |  |  | 24/10/2026 | 24/10/2026 |  |  | 703 |  | 703
ADIDAS | 0903260239-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2400 | 31/08/2026 | 2400 | SI | SI10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 31/08: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903260239 KE3742 | 29/07/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/08/2026 | M BLANK TEE WHITE |  | SS27 | 21/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 2400 | 2400 |  |  |  | 18/08/2026 | 27/08/2026 | 2026-10-08 | 29/08/2026 | 2400 | 2400
ADIDAS | 0903260282-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 302 | 15/10/2026 | 302 | SA | SA10/07/2026 | G3K | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260282 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 16/10/2026 | W 3S FT OH PT |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 302 |  | 302 |  |  | 13/10/2026 | 14/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903260434-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260434 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 327 |  | 327 |  |  | 18/09/2026 | 19/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 311 | 16 |  |  | 17/09/2026 | 18/09/2026 | 2026-08-09 | 2026-11-09 | 327 | 313 | 14
ADIDAS | 0903260741-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 212 | 15/10/2026 | 212 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903260741 KV0458 |  | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 25/09/2026 | 28/09/2026 |  |  | 212 |  | 212 |  |  | 22/09/2026 | 24/09/2026 |  |  | 212 |  | 212
ADIDAS | 0903261098-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903261098 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER GR GFSWT M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261108-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261108 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER KA NNHD M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261122-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903261122 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 15/09/2026 | MER KA GFSWT M BLACK |  | SS27-MS | 15/09/2026 | 15/09/2026 |  |  | 2 |  | 2 |  |  | 2026-11-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903261168-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 35 | 15/10/2026 | 35 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903261168 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 22/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 22/10/2026 | 23/10/2026 |  |  | 35 |  | 35 |  |  | 20/10/2026 | 21/10/2026 |  |  | 35 |  | 35 |  |  | 19/10/2026 | 20/10/2026 |  |  | 35 |  | 35
ADIDAS | 0903261626-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 349 | 15/10/2026 | 349 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT SUB PROCESS_V1 | 0903261626 KG8553 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 349 |  | 349 |  |  | 2026-05-10 | 2026-06-10 |  |  | 349 |  | 349 |  |  | 2026-03-10 | 2026-05-10 |  |  | 349 |  | 349
ADIDAS | 0903262069-1 IS1413 | BLACK | 60D | S2425M405 | 944 | 2026-09-09 | 944 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903262069 IS1413 | 26/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 944 | 944 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 944 | 944
ADIDAS | 0903262266-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 395 | 15/10/2026 | 395 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903262266 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 395 |  | 395 |  |  | 29/09/2026 | 29/09/2026 |  |  | 395 |  | 395
ADIDAS | 0903262302-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 285 | 15/10/2026 | 285 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903262302 LI7656 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 285 |  | 285 |  |  | 28/09/2026 | 29/09/2026 |  |  | 285 |  | 285
ADIDAS | 0903262703-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 126 | 15/10/2026 | 126 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262703 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 126 |  | 126 |  |  | 2026-05-11 | 2026-07-11 |  |  | 126 |  | 126
ADIDAS | 0903262820-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 190 | 15/10/2026 | 190 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903262820 JE6346 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-09-10 | M 3S FT TC PT |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 190 |  | 190 |  |  | 2026-06-10 | 2026-07-10 |  |  | 190 |  | 190
ADIDAS | 0903262992-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 572 | 30/09/2026 | 572 | SI | SI10/07/2026 | G1E | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). IMPROVE. DRC 0010-T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 652001 | HT SUB PROCESS_V1 | 0903262992 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 21/09/2026 |  |  | 572 |  | 572 |  |  | 18/09/2026 | 18/09/2026 | 29/08/2026 | 2026-04-09 | 572 | 569 | 3 |  |  | 17/09/2026 | 17/09/2026 | 24/08/2026 | 2026-04-09 | 572 | 569 | 3
ADIDAS | 0903263275-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 160 | 15/10/2026 | 160 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903263275 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 19/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 19/10/2026 | 19/10/2026 |  |  | 160 |  | 160 |  |  | 15/10/2026 | 15/10/2026 |  |  | 160 |  | 160 |  |  | 14/10/2026 | 14/10/2026 |  |  | 160 |  | 160
ADIDAS | 0903263698-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2330 | 15/10/2026 | 2330 | AN | AN10/07/2026 | G3B | PANTS | G3 | ok | ok | (Mexico). T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 03-Jul, actual receives 28-Jul. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263698 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-11 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-11 | 16/11/2026 |  |  | 2330 |  | 2330 |  |  | 2026-09-11 | 2026-12-11 |  |  | 2330 |  | 2330
ADIDAS | 0903263747-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903263747 JG8639 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-05-10 | W LIN FT SHO |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 250 |  | 250 |  |  | 2026-01-10 | 2026-03-10 |  |  | 250 |  | 250
ADIDAS | 0903263877-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263877 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 340 |  | 340 |  |  | 2026-12-10 | 13/10/2026 |  |  | 340 |  | 340
ADIDAS | 0903264038-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264038 JC8239 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 1500 |  | 1500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903264065-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 301 | 15/10/2026 | 301 | SA | SA10/07/2026 | G2S | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903264065 JE6414 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | M 3S FT SHO BLACK/WHITE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301 |  |  | 2026-06-10 | 2026-07-10 |  |  | 301 |  | 301
ADIDAS | 0903264129-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903264129 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | MER KA GFCTP W BLACK |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903264137-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264137 JG8639 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-05-10 | W LIN FT SHO |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1000 |  | 1000 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1000 |  | 1000
ADIDAS | 0903265194-1 KA4331 | BLACK | 90D | S2608MR0902 | 5581 | 15/10/2026 | 5581 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903265194 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 30/09/2026 | 2026-07-10 |  |  | 5581 |  | 5581 |  |  | 26/09/2026 | 2026-03-10 |  |  | 5581 |  | 5581 |  |  | 25/09/2026 | 2026-02-10 |  |  | 5581 |  | 5581
ADIDAS | 0903265258-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 831 | 15/10/2026 | 831 | SI | SI10/07/2026 | G3K | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265258 KD3854 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 20/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 20/10/2026 | 22/10/2026 |  |  | 831 |  | 831 |  |  | 16/10/2026 | 19/10/2026 |  |  | 831 |  | 831 |  |  | 13/10/2026 | 15/10/2026 |  |  | 831 |  | 831
ADIDAS | 0903265296-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265296 KF5311 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0903265322-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 572 | 15/10/2026 | 572 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265322 KE8424 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-08-10 | 2026-10-10 |  |  | 572 |  | 572 |  |  | 2026-05-10 | 2026-07-10 |  |  | 572 |  | 572 |  |  | 2026-02-10 | 2026-05-10 |  |  | 572 |  | 572
ADIDAS | 0903265342-1 KG8547 | ONIX | 90D | S2408WR1600 | 3535 | 15/10/2026 | 3535 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | 672027 | HT SUB PROCESS_V1 | 0903265342 KG8547 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 17/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-10-10 | 15/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-09-10 | 14/10/2026 |  |  | 3535 |  | 3535
ADIDAS | 0903265374-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 5948 | 15/10/2026 | 5948 | SA | SA10/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903265374 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 26/10/2026 |  |  | 5948 |  | 5948 |  |  | 16/10/2026 | 23/10/2026 | 2026-12-08 | 14/09/2026 | 5948 | 5867 | 81 |  | 8 | 15/10/2026 | 22/10/2026 | 2026-12-08 | 14/09/2026 | 5948 | 5944 | 4 |  | 88
ADIDAS | 0903265404-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 1408 | 15/10/2026 | 1408 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265404 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 1408 |  | 1408 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1408 |  | 1408 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1408 |  | 1408
ADIDAS | 0903265435-1 KT4840 | ONIX | 90D | S2408MR1600 | 5404 | 15/10/2026 | 5404 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903265435 KT4840 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 16/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-07-10 | 14/10/2026 |  |  | 5404 |  | 5404 |  |  | 2026-06-10 | 13/10/2026 |  |  | 5404 |  | 5404
ADIDAS | 0903265463-1 KT4839 | ONIX | 90D | S2408MR1601 | 1613 | 15/10/2026 | 1613 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT SUB PROCESS_V1 | 0903265463 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 30/09/2026 | 2026-03-10 |  |  | 1613 |  | 1613 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1613 |  | 1613 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903266153-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 309 | 15/10/2026 | 309 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266153 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 309 |  | 309 |  |  | 2026-03-10 | 2026-03-10 |  |  | 309 |  | 309
ADIDAS | 0903266170-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 285 | 15/10/2026 | 285 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | ok | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266170 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA GFTEE K BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 285 |  | 285 |  |  | 2026-03-10 | 2026-03-10 |  |  | 285 |  | 285
ADIDAS | 0903266198-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 177 | 15/10/2026 | 177 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (06/08/2026) | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266198 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 177 |  | 177 |  |  | 23/09/2026 | 24/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903266331-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266331 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903266349-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266349 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 |  |  | 143 |  | 143
ADIDAS | 0903266525-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 310 | 15/10/2026 | 310 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266525 LH4535 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/10/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 310 |  | 310 |  |  | 2026-12-10 | 13/10/2026 |  |  | 310 |  | 310
ADIDAS | 0903266526-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 273 | 15/10/2026 | 273 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266526 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 273 |  | 273 |  |  | 2026-01-10 | 2026-02-10 |  |  | 273 |  | 273
ADIDAS | 0903266548-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266548 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 120 |  | 120 |  |  | 29/09/2026 | 2026-01-10 |  |  | 120 |  | 120
ADIDAS | 0903266578-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266578 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 143 |  | 143 |  |  | 29/09/2026 | 2026-01-10 |  |  | 143 |  | 143
ADIDAS | 0903266599-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266599 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903269490-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269490 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 120 |  | 120 |  |  | 28/09/2026 | 28/09/2026 |  |  | 120 |  | 120
ADIDAS | 0903269545-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903269545 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903269592-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 337 | 15/10/2026 | 337 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269592 LI7656 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 337 |  | 337 |  |  | 28/09/2026 | 29/09/2026 |  |  | 337 |  | 337
ADIDAS | 0903269617-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 103 | 15/10/2026 | 103 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903269617 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 103 |  | 103 |  |  | 28/09/2026 | 28/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903271653-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903271653 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 107 |  | 107 |  |  | 28/09/2026 | 28/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903271675-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 150 | 15/10/2026 | 150 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903271675 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 150 |  | 150 |  |  | 29/09/2026 | 29/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903273743-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 309 | 15/10/2026 | 309 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273743 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 309 |  | 309 |  |  | 27/10/2026 | 28/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903274607-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903274607 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-02-10 | MER GR GFTEE M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 29/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903274622-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2L | T-SHIRT | G2 | (09/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274622 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-08-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-08-10 | 2026-08-10 |  |  | 2 |  | 2 |  |  | 2026-05-10 | 2026-05-10 | 26/08/2026 | 26/08/2026 | 2 | 1 | 1
ADIDAS | 0903274637-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 2 | 2026-07-10 | 2 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274637 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-01-10 | MER KA GFTEE M BLACK |  | SS27-MS | 2026-01-10 | 2026-01-10 |  |  | 2 |  | 2 |  |  | 28/09/2026 | 28/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903276235-1 KY5870 | GREY | 90D | S2750MTR052 | 114 | 15/10/2026 | 114 | SI | SI10/07/2026 | G2C | SHORTS | G2 | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 830009 | HT SUB PROCESS_V1 | 0903276235 KY5870 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | D74T ESS SHORTS GREY |  | SS27-TI | 2026-06-10 | 2026-07-10 |  |  | 114 |  | 114 |  |  | 2026-03-10 | 2026-05-10 |  |  | 114 |  | 114 |  |  | 2026-02-10 | 2026-03-10 |  |  | 114 |  | 114
ADIDAS | 0903305162-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 158 | 15/10/2026 | 158 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848016 | PRINT L2+PAD SUB PROCESS_V3 | 0903305162 LC8884 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 158 |  | 158 |  |  | 2026-07-10 | 2026-08-10 | 15/09/2026 | 15/09/2026 | 158 | 144 | 14
ADIDAS | 0903305163-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 198 | 15/10/2026 | 198 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848012 | PRINT L2+PAD SUB PROCESS_V3 | 0903305163 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M RESORT T BLACK |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 198 |  | 198 |  |  | 2026-07-10 | 2026-08-10 | 26/08/2026 | 26/08/2026 | 198 | 8 | 190
ADIDAS | 0903306652-1 KA6229 | BLACK | 120D | S2608WR0202 | 255 | 15/10/2026 | 255 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306652 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 255 |  | 255 |  |  | 13/10/2026 | 16/10/2026 |  |  | 255 |  | 255 |  |  | 2026-09-10 | 13/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903306653-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 15/10/2026 | 1009 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306653 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 20/10/2026 | 23/10/2026 |  |  | 1009 |  | 1009 |  |  | 16/10/2026 | 20/10/2026 |  |  | 1009 |  | 1009 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1009 |  | 1009
ADIDAS | 0903309141-1 KA4331 | BLACK | 90D | S2608MR0902 | 6720 | 15/10/2026 | 6720 | SA | SA20/07/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. DRC 0064-T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand tex, PI Date 16-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903309141 KA4331 | 2026-02-10 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess 21 S M BLACK |  | SS27 | 28/09/2026 | 2026-08-10 |  |  | 6720 |  | 6720 |  |  | 24/09/2026 | 2026-05-10 |  |  | 6720 |  | 6720 |  |  | 23/09/2026 | 2026-03-10 |  |  | 6720 |  | 6720
ADIDAS | 0903309142-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 3 | 15/10/2026 | 3 | AN | AN20/07/2026 | G2R | SHORTS | G2 |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? Waiting fabroc. T2 Formosa, PI Date ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309142 KZ3231 | 2026-02-10 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 3 |  | 3 |  |  | 2026-09-10 | 2026-09-10 |  |  | 3 |  | 3
ADIDAS | 0903309143-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 28 | 15/10/2026 | 28 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309143 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 28 |  | 28 |  |  | 2026-08-10 | 2026-09-10 |  |  | 28 |  | 28 |  |  | 2026-07-10 | 2026-08-10 |  |  | 28 |  | 28
ADIDAS | 0903309144-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309144 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 1 |  | 1 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1 |  | 1 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1 |  | 1
ADIDAS | 0903309880-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309880 JE6414 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 24/09/2026 | 29/09/2026 |  |  | 2637 |  | 2637 |  |  | 21/09/2026 | 25/09/2026 | 31/08/2026 | 2026-01-09 | 2637 | 2637
ADIDAS | 0903309881-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 6599 | 30/09/2026 | 6599 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309881 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S FT FZ HD |  | SS27 | 21/09/2026 | 29/09/2026 |  |  | 6599 |  | 6599 |  |  | 17/09/2026 | 25/09/2026 |  |  | 6599 |  | 6599
ADIDAS | 0903309882-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 4400 | 30/09/2026 | 4400 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | (28/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309882 IB8686 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | ESS TEE |  | SS27 | 21/09/2026 | 25/09/2026 |  |  | 4400 |  | 4400 |  |  | 17/09/2026 | 22/09/2026 | 2026-02-09 | 2026-10-09 | 4400 | 4395 | 5
ADIDAS | 0903309883-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3522 | 30/09/2026 | 3522 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309883 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 30/09/2026 |  |  | 3522 |  | 3522 |  |  | 21/09/2026 | 26/09/2026 |  |  | 3522 |  | 3522
ADIDAS | 0903309884-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1321 | 30/09/2026 | 1321 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309884 JE6340 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M 3S FT FZ HD |  | SS27 | 15/09/2026 | 17/09/2026 |  |  | 1321 |  | 1321 |  |  | 2026-11-09 | 14/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903309886-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 7920 | 30/09/2026 | 7920 | SI | SI26/06/2026 | G3C | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309886 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S FT CF PT |  | SS27 | 21/09/2026 | 30/09/2026 |  |  | 7920 |  | 7920 |  |  | 17/09/2026 | 26/09/2026 |  |  | 7920 |  | 7920
ADIDAS | 0903309887-1 HZ0747 | BLACK | 90D | F2325M414 | 9088 | 30/09/2026 | 9088 | SA | SA26/06/2026 | G2R | T-SHIRT | G2 | (29/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309887 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PL TEE |  | SS27 | 16/09/2026 | 25/09/2026 |  |  | 9088 |  | 9088 |  |  | 2026-12-09 | 22/09/2026 |  |  | 9088 |  | 9088
ADIDAS | 0903309888-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 3520 | 30/09/2026 | 3520 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309888 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-06-10 |  |  | 3520 |  | 3520 |  |  | 28/09/2026 | 2026-02-10 |  |  | 3520 |  | 3520
ADIDAS | 0903309889-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 6600 | 30/09/2026 | 6600 | SI | SI26/06/2026 | G3G,G3H | JACKET | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309889 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-06-10 |  |  | 6600 |  | 6600 |  |  | 28/09/2026 | 2026-02-10 | 13/08/2026 | 2026-11-09 | 6600 | 5277 | 1323
ADIDAS | 0903309890-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1050 | 15/10/2026 | 1050 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309890 JM1776 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-11 | M SL WV PT 2 |  | SS27 | 2026-07-11 | 2026-10-11 |  |  | 1050 |  | 1050 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1050 |  | 1050
ADIDAS | 0903309891-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1760 | 30/09/2026 | 1760 | SI | SI26/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309891 KD3911 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | RELEASED |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 1760 |  | 1760 |  |  | 15/09/2026 | 17/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903309892-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1761 | 30/09/2026 | 1761 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309892 JE6341 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | M 3S FT FZ HD |  | SS27 | 16/09/2026 | 21/09/2026 |  |  | 1761 |  | 1761 |  |  | 2026-12-09 | 17/09/2026 |  |  | 1761 |  | 1761
ADIDAS | 0903309893-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 6602 | 30/09/2026 | 6602 | SI | SI26/06/2026 | G3E,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309893 HR8583 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | ESS SWTP |  | SS27 | 16/09/2026 | 2026-03-10 |  |  | 6602 |  | 6602 |  |  | 2026-12-09 | 30/09/2026 |  |  | 6602 |  | 6602
ADIDAS | 0903309894-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2A | SHORTS | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309894 JE6417 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 25/09/2026 | 2026-01-10 |  |  | 2637 |  | 2637 |  |  | 22/09/2026 | 28/09/2026 |  |  | 2637 |  | 2637
ADIDAS | 0903309895-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2638 | 30/09/2026 | 2638 | SA | SA26/06/2026 | G2F | SHORTS | G2 | ok | ok | 23/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309895 JE6419 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 2638 |  | 2638 |  |  | 21/09/2026 | 24/09/2026 | 29/08/2026 | 2026-08-09 | 2638 | 2484 | 154
ADIDAS | 0903309897-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 5722 | 30/09/2026 | 5722 | SI | SI26/06/2026 | G3D,G3J | PANTS | G3 | (29/07/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309897 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | ESS SWTP |  | SS27 | 2026-02-10 | 2026-08-10 |  |  | 5722 |  | 5722 |  |  | 29/09/2026 | 2026-05-10 |  |  | 5722 |  | 5722
ADIDAS | 0903309899-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 24312 | 19/09/2026 | 24312 | SA | SA10/07/2026 | G1D, G1E, G1F, G1K, G1L, G1N, G1P, G2A, G2R, G2T, G3A, G3D, G3G, G3H, G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309899 IB8688 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 31/08/2026 | 15/09/2026 | 24312 | 16772 | 7540 |  | 142 | 27/08/2026 | 19/09/2026 | 24/08/2026 | 15/09/2026 | 24312 | 22464 | 1848 |  | 4946
ADIDAS | 0903309900-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2100 | 15/10/2026 | 2100 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309900 JE6338 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M 3S FT FZ HD |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 2100 |  | 2100 |  |  | 2026-07-10 | 2026-10-10 |  |  | 2100 |  | 2100
ADIDAS | 0903309901-1 HK7319 | BLACK | 90D | F2225M403 | 5282 | 30/09/2026 | 5282 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309901 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-08-10 |  |  | 5282 |  | 5282 |  |  | 24/09/2026 | 2026-05-10 |  |  | 5282 |  | 5282
ADIDAS | 0903309902-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2940 | 15/10/2026 | 2940 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309902 JD1877 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 2940 |  | 2940 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2940 |  | 2940
ADIDAS | 0903309903-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1051 | 15/10/2026 | 1051 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309903 JM1775 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M SL WV PT 2 |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1051 |  | 1051 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1051 |  | 1051
ADIDAS | 0903309904-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 24142 | 19/09/2026 | 24142 | SA | SA10/07/2026 | G1E,G1F,G1K,G1N,G1P,G2A,G2R,G2T,G3G,G3H,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309904 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 2026-01-09 | 15/09/2026 | 24142 | 17654 | 6488 |  | 98 | 27/08/2026 | 19/09/2026 | 2026-01-09 | 15/09/2026 | 24142 | 22960 | 1182 |  | 2466
ADIDAS | 0903309905-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2642 | 30/09/2026 | 2642 | SI | SI26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Gistex, (3S) PI Date 10-Aug, actual receives 06-Aug (using fabric stock from libolon). T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309905 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV SHO |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 2642 |  | 2642 |  |  | 21/09/2026 | 24/09/2026 |  |  | 2642 |  | 2642
ADIDAS | 0903309907-1 HK7309 | BLACK | 45D | F2225M402 | 24310 | 19/09/2026 | 24310 | SA | SA10/07/2026 | G1D,G1E,G1F,G1K,G1N,G1P,G2T,G3G,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 16/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309907 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 23/09/2026 | 28/08/2026 | 15/09/2026 | 24310 | 20332 | 3978 |  | 74 | 27/08/2026 | 19/09/2026 | 27/08/2026 | 15/09/2026 | 24310 | 23537 | 773 |  | 1083
ADIDAS | 0903309910-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1512 | 15/10/2026 | 1512 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309910 JE6341 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | M 3S FT FZ HD |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 1512 |  | 1512 |  |  | 2026-02-10 | 2026-05-10 |  |  | 1512 |  | 1512
ADIDAS | 0903316928-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) |  | 29/09: ex-fty (NYK warehouse). T2 Y.T.I, Body & mesh actual receives 05-Aug. 800005 | HT SUB PROCESS_V1 | 0903316928 KG8548 | 17/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 17/09/2026 | 2026-05-09 | 15/09/2026 | 327 | 325 | 2 |  |  | 29/08/2026 | 15/09/2026 | 2026-11-08 | 22/08/2026 | 327 | 327 |  |  |  | 28/08/2026 | 14/09/2026 | 2026-11-08 | 21/08/2026 | 327 | 327
ADIDAS | 0903316929-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 585 | 30/09/2026 | 585 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) |  | Waiting fabric (NYK warehouse). DRC 0064-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 800005 | PRINT L2+HT SUB PROCESS_V3 | 0903316929 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | INDONESIA | SEA | 18/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 18/09/2026 | 21/09/2026 |  |  | 585 |  | 585 |  |  | 15/09/2026 | 17/09/2026 |  |  | 585 |  | 585 |  |  | 14/09/2026 | 16/09/2026 |  |  | 585 |  | 585
ADIDAS | 0903316930-1 KG8547 | ONIX | 90D | S2408WR1600 | 107 | 15/10/2026 | 107 | SI | SI30/06/2026 | G1I | T-SHIRT | G1 | ok |  | (NYK warehouse). T2 Y.T.I, body & mesh actual receives 08-Aug. 800005 | HT SUB PROCESS_V1 | 0903316930 KG8547 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 107 |  | 107 |  |  | 2026-10-10 | 2026-12-10 |  |  | 107 |  | 107 |  |  | 2026-09-10 | 2026-10-10 |  |  | 107 |  | 107
ADIDAS | 0903322460-1 IN1159 | BLACK | 90D | S2408MR1601 | 331 | 2026-07-10 | 331 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | 22/09: ex-fty. Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT SUB PROCESS_V1 | 0903322460 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 331 |  | 331 |  |  | 19/09/2026 | 21/09/2026 |  |  | 331 |  | 331 |  |  | 18/09/2026 | 19/09/2026 |  |  | 331 |  | 331
ADIDAS | 0903322461-1 IN1157 | WHITE | 90D | S2408MR1600 | 335 | 15/10/2026 | 335 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 06-Aug. 516471 | HT SUB PROCESS_V1 | 0903322461 IN1157 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | ADIZERO E TEE |  | SS27-YTI | 30/09/2026 | 2026-01-10 |  |  | 335 |  | 335 |  |  | 28/09/2026 | 29/09/2026 | 2026-09-09 | 2026-12-09 | 335 | 308 | 27 |  |  | 26/09/2026 | 28/09/2026 | 2026-02-09 | 2026-10-09 | 335 | 308 | 27
ADIDAS | 0903322476-1 IN1157 | WHITE | 90D | S2408MR1600 | 845 | 2026-07-10 | 845 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, actual receives 06-Aug. T2 Fu Hsun, Mesh PI Date 03-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322476 IN1157 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 845 |  | 845 |  |  | 25/09/2026 | 26/09/2026 | 2026-10-09 | 14/09/2026 | 845 | 808 | 37 |  | 26 | 24/09/2026 | 25/09/2026 | 2026-03-09 | 14/09/2026 | 845 | 831 | 14 |  | 29
ADIDAS | 0903322477-1 IN1156 | BLACK | 90D | S2408MR1600 | 553 | 18/09/2026 | 553 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322477 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-02-09 | 2026-05-09 | 553 | 553 |  |  |  | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553
ADIDAS | 0903322478-1 IN1173 | WHITE | 90D | S2408WR1600 | 304 | 15/09/2026 | 304 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516471 | HT SUB PROCESS_V1 | 0903322478 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 304 | 303 | 1 |  |  | 29/08/2026 | 2026-12-09 | 15/08/2026 | 15/08/2026 | 304 | 304 |  |  |  | 28/08/2026 | 2026-11-09 | 2026-11-08 | 2026-11-08 | 304 | 304
ADIDAS | 0903322479-1 IN1172 | BLACK | 90D | S2408WR1600 | 807 | 15/09/2026 | 807 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322479 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-03-09 | 15/09/2026 | 807 | 807 |  |  |  | 29/08/2026 | 2026-12-09 | 26/08/2026 | 14/09/2026 | 807 | 806 | 1 |  | 1 | 28/08/2026 | 2026-11-09 | 26/08/2026 | 2026-12-09 | 807 | 807
ADIDAS | 0903322480-1 IN1156 | BLACK | 90D | S2408MR1600 | 924 | 15/09/2026 | 924 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) 516471 | HT SUB PROCESS_V1 | 0903322480 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 15/09/2026 | 2026-01-09 | 15/09/2026 | 924 | 924 |  |  |  | 27/08/2026 | 2026-12-09 | 22/08/2026 | 2026-09-09 | 924 | 924 |  |  |  | 26/08/2026 | 2026-11-09 | 22/08/2026 | 2026-08-09 | 924 | 924
ADIDAS | 0903322484-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 2026-07-10 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322484 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 | 26/08/2026 | 2026-02-09 | 300 | 297 | 3 |  |  | 23/09/2026 | 24/09/2026 | 24/08/2026 | 2026-05-09 | 300 | 300
ADIDAS | 0903322486-1 IN1172 | BLACK | 90D | S2408WR1600 | 265 | 15/10/2026 | 265 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322486 IN1172 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 265 |  | 265 |  |  | 20/10/2026 | 21/10/2026 |  |  | 265 |  | 265 |  |  | 19/10/2026 | 20/10/2026 | 2026-05-09 | 2026-05-09 | 265 | 188 | 77
ADIDAS | 0903322488-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 352 | 2026-07-10 | 352 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516471 | HT SUB PROCESS_V1 | 0903322488 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 23/09/2026 |  |  | 352 |  | 352 |  |  | 19/09/2026 | 21/09/2026 | 2026-07-09 | 14/09/2026 | 352 | 175 | 177 |  | 35 | 18/09/2026 | 19/09/2026 | 2026-07-09 | 2026-12-09 | 352 | 177 | 175
ADIDAS | 0903322491-1 IN1172 | BLACK | 90D | S2408WR1600 | 324 | 30/09/2026 | 324 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322491 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 324 |  | 324 |  |  | 24/09/2026 | 25/09/2026 | 26/08/2026 | 2026-07-09 | 324 | 324 |  |  |  | 23/09/2026 | 24/09/2026 | 26/08/2026 | 2026-04-09 | 324 | 324
ADIDAS | 0903322492-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 254 | 2026-07-10 | 254 | NT | NT24/04/2026 | G1M | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516471 | HT SUB PROCESS_V1 | 0903322492 IT1824 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | ADIZERO E TEE |  | FW26 | 2026-09-10 | 2026-09-10 |  |  | 254 |  | 254 |  |  | 2026-07-10 | 2026-07-10 | 2026-05-08 | 2026-10-08 | 254 | 254 |  |  |  | 2026-06-10 | 2026-06-10 | 2026-05-08 | 2026-10-08 | 254 | 254
ADIDAS | 0903353862-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353862 KC6387 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | K BLANK TEE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 400 |  | 400 |  |  | 28/09/2026 | 29/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903361428-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 369 | 30/09/2026 | 369 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361428 KT7554 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | M CLUB AM TAT |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 369 |  | 369 |  |  | 23/09/2026 | 23/09/2026 | 2026-11-09 | 2026-12-09 | 369 | 341 | 28
ADIDAS | 0903361937-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361937 KD9090 |  | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 400 |  | 400 |  |  | 26/09/2026 | 28/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903362075-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 531 | 15/09/2026 | 531 | ID | ID31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 14/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903362075 KB5965 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee M |  | SS27-TI-SLT | 2026-05-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 531 | 531 |  |  |  | 2026-02-09 | 2026-04-09 | 29/08/2026 | 2026-08-09 | 531 | 531 |  |  |  | 31/08/2026 | 2026-02-09 | 29/08/2026 | 2026-07-09 | 531 | 531
ADIDAS | 0903365289-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 650 | 2026-07-10 | 650 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365289 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-02-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-02-10 | 2026-03-10 |  |  | 650 |  | 650 |  |  | 29/09/2026 | 30/09/2026 |  |  | 650 |  | 650 |  |  | 26/09/2026 | 28/09/2026 |  |  | 650 |  | 650
ADIDAS | 0903365322-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 500 | 2026-07-10 | 500 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365322 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-01-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-01-10 | 2026-02-10 |  |  | 500 |  | 500 |  |  | 28/09/2026 | 29/09/2026 | 27/08/2026 | 31/08/2026 | 500 | 340 | 160 |  |  | 25/09/2026 | 26/09/2026 | 27/08/2026 | 29/08/2026 | 500 | 500
ADIDAS | 0903365354-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 850 | 31/08/2026 | 850 | ID | ID31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 31/08: ex-fty 823016 | HT+PAD SUB PROCESS_V3 | 0903365354 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 29/08/2026 | Run Ess Tee M |  | SS27-TI-SLT | 29/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 850 | 850 |  |  |  | 26/08/2026 | 27/08/2026 | 22/08/2026 | 31/08/2026 | 850 | 850 |  |  |  | 21/08/2026 | 24/08/2026 | 22/08/2026 | 28/08/2026 | 850 | 850
ADIDAS | 0903365391-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 2350 | 31/08/2026 | 2350 | ID | ID31/07/2026 | G2G,G2H,G2J,G2K | T-SHIRT | G2 | ok |  | 31/08: ex-fty 823016 | HT+PAD SUB PROCESS_V3 | 0903365391 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 28/08/2026 | Run Ess Tee M |  | SS27-TI-SLT | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 2350 | 2350 |  |  |  | 24/08/2026 | 27/08/2026 | 29/08/2026 | 2026-03-09 | 2350 | 2318 | 32 |  |  | 20/08/2026 | 24/08/2026 | 29/08/2026 | 31/08/2026 | 2350 | 2350
ADIDAS | 0903366562-1 IS1413 | BLACK | 60D | S2425M405 | 7 | 30/09/2026 | 7 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903366562 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 7 |  | 7 |  |  | 2026-12-09 | 2026-12-09 |  |  | 7 |  | 7
ADIDAS | 0903368552-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2520 | 15/09/2026 | 2520 | SA | SA31/07/2026 | G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368552 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 16/09/2026 | 2026-10-09 | 15/09/2026 | 2520 | 2520 |  |  | 192 | 2026-03-09 | 2026-12-09 | 2026-09-09 | 15/09/2026 | 2520 | 2445 | 75 |  | 63
ADIDAS | 0903368635-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 401 | 15/09/2026 | 401 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368635 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 401 | 401 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 401 | 391 | 10 |  | 76
ADIDAS | 0903369017-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 535 | 30/09/2026 | 535 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 25/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369017 IU0217 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 535 |  | 535 |  |  | 2026-12-09 | 2026-12-09 |  |  | 535 |  | 535
ADIDAS | 0903369058-1 IS1413 | BLACK | 60D | S2425M405 | 374 | 30/09/2026 | 374 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369058 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/09/2026 | IN RANGE |  | SS27 | 16/09/2026 | 16/09/2026 |  |  | 374 |  | 374 |  |  | 2026-12-09 | 2026-12-09 |  |  | 374 |  | 374
ADIDAS | 0903369096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 514 | 30/09/2026 | 514 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 24/09: ex-fty 672027 | PRINT L3+PAD SUB PROCESS_V3 | 0903369096 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | BRAZIL | SEA | 24/09/2026 | POS TABLE LK |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 514 |  | 514 |  |  | 21/09/2026 | 21/09/2026 | 2026-08-09 | 2026-09-09 | 514 | 506 | 8
ADIDAS | 0903370885-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370885 IB8688 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 16/09/2026 | 2026-12-09 | 15/09/2026 | 1840 | 1840 |  |  | 1267 | 2026-03-09 | 2026-12-09 | 2026-12-09 | 15/09/2026 | 1840 | 1716 | 124 |  | 756
ADIDAS | 0903370934-1 HK7309 | BLACK | 45D | F2225M402 | 399 | 15/09/2026 | 399 | SA | SA31/07/2026 | G1K | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370934 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 14/09/2026 | 399 | 399 |  |  | 45 | 2026-04-09 | 2026-07-09 | 2026-09-09 | 14/09/2026 | 399 | 399 |  |  | 10
ADIDAS | 0903370987-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 600 | 15/09/2026 | 600 | SA | SA31/07/2026 | G2A | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370987 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 600 | 600 |  |  | 54 | 2026-04-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 600 | 595 | 5 |  | 32
ADIDAS | 0903371106-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1800 | 15/10/2026 | 1800 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903371106 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | RELEASED |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1800 |  | 1800 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1800 |  | 1800
ADIDAS | 0903371472-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 400 | 2026-02-10 | 400 | SI | SI31/07/2026 | G2P | SWEATSHIRT | G2 | (16/09/2026) |  | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371472 JE6374 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA | 22/09/2026 | M 3S FT SWT |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 400 |  | 400 |  |  | 18/09/2026 | 18/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903371511-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903371511 IW2479 | 2026-03-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903372828-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT-SLT | 149 | 2026-09-09 | 149 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 09/09: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903372828 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27-SLT | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 149 | 149 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 149 | 149
ADIDAS | 0903372885-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372885 HK7309 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-04-09 | ESS HDY |  | SS27 | 2026-04-09 | 17/09/2026 | 2026-09-09 | 15/09/2026 | 1495 | 1495 |  |  | 901 | 2026-01-09 | 14/09/2026 | 2026-08-09 | 15/09/2026 | 1495 | 1466 | 29 |  | 625
ADIDAS | 0903372967-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 296 | 30/09/2026 | 296 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903372967 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 296 |  | 296 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 296 | 247 | 49
ADIDAS | 0903373006-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373006 HK7311 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-09 | ESS HDY |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  | 46 | 29/08/2026 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1379 | 1329 | 50 |  | 30
ADIDAS | 0903373118-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug.. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373118 IB8688 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 1840 | 1840 |  |  | 178 | 2026-03-09 | 14/09/2026 | 2026-09-09 | 15/09/2026 | 1840 | 1808 | 32 |  | 90
ADIDAS | 0903373810-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373810 LI2671 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 10 |  | 10 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 2026-09-09 | 10 | 6 | 4
ADIDAS | 0903373816-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1K,G1P | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373816 HK7309 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 1495 | 1495 |  |  | 251 | 2026-04-09 | 2026-11-09 | 2026-09-09 | 14/09/2026 | 1495 | 1488 | 7 |  | 47
ADIDAS | 0903373846-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373846 LI2645 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 10 |  | 10 |  |  | 18/09/2026 | 18/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373872-1 HK7309 | BLACK | 45D | F2225M402 | 2730 | 15/09/2026 | 2730 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373872 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-10-09 | 15/09/2026 | 2730 | 2730 |  |  | 860 | 2026-03-09 | 14/09/2026 | 2026-10-09 | 15/09/2026 | 2730 | 2621 | 109 |  | 199
ADIDAS | 0903373878-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 10 | 30/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373878 LI2672 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 18/09/2026 | 19/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373912-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373912 LI2647 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 10 |  | 10 |  |  | 28/09/2026 | 28/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 10 | 30/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373945 LI2646 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 10 |  | 10 |  |  | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903374039-1 HK7309 | BLACK | 45D | F2225M402 | 3000 | 15/09/2026 | 3000 | SA | SA31/07/2026 | G1D,G1E,G1F,G1K,G1L,G1N,G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903374039 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 14/09/2026 | 15/09/2026 | 3000 | 3000 |  |  | 2880 | 2026-03-09 | 14/09/2026 | 13/09/2026 | 15/09/2026 | 3000 | 2852 | 148 |  | 2632
ADIDAS | 0903374608-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374608 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 460 |  | 460 |  |  | 19/09/2026 | 21/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903374883-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 103 | 30/09/2026 | 103 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374883 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 103 |  | 103 |  |  | 22/09/2026 | 23/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903374908-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374908 LI2668 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 107 |  | 107 |  |  | 16/09/2026 | 17/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903374971-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 111 | 30/09/2026 | 111 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374971 LI2669 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 111 |  | 111 |  |  | 16/09/2026 | 17/09/2026 | 2026-12-09 | 2026-12-09 | 111 | 29 | 82
ADIDAS | 0903375054-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 519 | 30/09/2026 | 519 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903375054 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 519 |  | 519 |  |  | 2026-03-10 | 2026-05-10 |  |  | 519 |  | 519 |  |  | 2026-01-10 | 2026-02-10 |  |  | 519 |  | 519
ADIDAS | 0903375519-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 413 | 29/08/2026 | 413 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903375519 KC6387 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 413 | 413 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 29/08/2026 | 413 | 413
ADIDAS | 0903375565-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 968 | 29/08/2026 | 968 | SA | SA31/07/2026 | G2G,G2H | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903375565 KC6387 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 968 | 968 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 29/08/2026 | 968 | 968
ADIDAS | 0903375868-1 HK7309 | BLACK | 45D | F2225M402 | 780 | 15/09/2026 | 780 | SA | SA31/07/2026 | G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375868 HK7309 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | ESS HDY |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 14/09/2026 | 780 | 780 |  |  | 292 | 2026-07-09 | 2026-09-09 | 2026-11-09 | 13/09/2026 | 780 | 711 | 69
ADIDAS | 0903376260-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 246 | 30/09/2026 | 246 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903376260 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 246 |  | 246 |  |  | 26/09/2026 | 28/09/2026 |  |  | 246 |  | 246
ADIDAS | 0903377653-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 167 | 30/09/2026 | 167 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377653 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 167 |  | 167 |  |  | 18/09/2026 | 19/09/2026 |  |  | 167 |  | 167
ADIDAS | 0903377680-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 175 | 30/09/2026 | 175 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377680 LI2671 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 175 |  | 175 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 2026-11-09 | 175 | 168 | 7
ADIDAS | 0903378323-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 923 | 23/09/2026 | 923 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378323 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 923 |  | 923 |  |  | 18/09/2026 | 18/09/2026 |  |  | 923 |  | 923
ADIDAS | 0903378381-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 657 | 23/09/2026 | 657 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378381 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 657 |  | 657 |  |  | 18/09/2026 | 19/09/2026 |  |  | 657 |  | 657
ADIDAS | 0903378401-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 140 | 30/09/2026 | 140 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378401 LI2646 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 140 |  | 140 |  |  | 22/09/2026 | 23/09/2026 |  |  | 140 |  | 140
ADIDAS | 0903378433-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 2026-07-10 | 230 | SI | SI31/07/2026 | G1M | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378433 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 230 |  | 230 |  |  | 30/09/2026 | 2026-01-10 |  |  | 230 |  | 230
ADIDAS | 0903378476-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378476 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 113 |  | 113 |  |  | 18/09/2026 | 19/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903378501-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 114 | 30/09/2026 | 114 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378501 LI2667 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 114 |  | 114 |  |  | 15/09/2026 | 16/09/2026 |  |  | 114 |  | 114
ADIDAS | 0903378523-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 121 | 30/09/2026 | 121 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378523 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 121 |  | 121 |  |  | 16/09/2026 | 17/09/2026 | 2026-12-09 | 2026-12-09 | 121 | 109 | 12
ADIDAS | 0903378603-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 351 | 23/09/2026 | 351 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378603 LI2646 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 351 |  | 351 |  |  | 21/09/2026 | 22/09/2026 |  |  | 351 |  | 351
ADIDAS | 0903378692-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 132 | 23/09/2026 | 132 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378692 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/09/2026 | 16/09/2026 |  |  | 132 |  | 132 |  |  | 2026-10-09 | 2026-12-09 |  |  | 132 |  | 132
ADIDAS | 0903378741-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 721 | 15/09/2026 | 721 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378741 HK7311 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 721 | 721 |  |  | 132 | 2026-03-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 721 | 704 | 17 |  | 213
ADIDAS | 0903378980-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 153 | 2026-07-10 | 153 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | (12/09/2026) |  | 30/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378980 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 153 |  | 153 |  |  | 30/09/2026 | 2026-02-10 |  |  | 153 |  | 153
ADIDAS | 0903379027-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 960 | 15/09/2026 | 960 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379027 IB8688 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-09 | ESS HDY |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 960 | 960 |  |  | 8 | 29/08/2026 | 2026-11-09 | 2026-08-09 | 15/09/2026 | 960 | 930 | 30 |  | 11
ADIDAS | 0903379083-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/09/2026 | 2000 | SA | SA31/07/2026 | G2A,G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379083 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 17/09/2026 | 2026-12-09 | 15/09/2026 | 2000 | 2000 |  |  | 1110 | 2026-03-09 | 14/09/2026 | 2026-11-09 | 15/09/2026 | 2000 | 1966 | 34 |  | 433
ADIDAS | 0903379104-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 3360 | 15/09/2026 | 3360 | SA | SA31/07/2026 | G2A,G2R,G2T,G3A,G3H,G3I | SWEATSHIRT | G2,G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379104 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 19/09/2026 | 2026-12-09 | 15/09/2026 | 3360 | 3360 |  |  | 2755 | 2026-03-09 | 16/09/2026 | 2026-12-09 | 15/09/2026 | 3360 | 3257 | 103 |  | 859
ADIDAS | 0903380322-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380322 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 109 |  | 109 |  |  | 28/09/2026 | 28/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380373-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 109 | 30/09/2026 | 109 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380373 LI2672 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 109 |  | 109 |  |  | 18/09/2026 | 19/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380504-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380504 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 460 |  | 460 |  |  | 21/09/2026 | 22/09/2026 |  |  | 460 |  | 460
ADIDAS | 0903380521-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380521 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 32 |  | 32 |  |  | 22/09/2026 | 23/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380549-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 32 | 30/09/2026 | 32 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380549 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 32 |  | 32 |  |  | 18/09/2026 | 19/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380551-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 1254 | 2026-09-09 | 1254 | NT | NT31/07/2026 | G2Q | PANTS | G2 | ok |  | 09/09: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903380551 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-09 | M FEELCOZY PANT |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 1254 | 1254 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 1254 | 1254
ADIDAS | 0903380577-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380577 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 32 |  | 32 |  |  | 26/09/2026 | 28/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380602-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 65 | 30/09/2026 | 65 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380602 LI2645 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 65 |  | 65 |  |  | 18/09/2026 | 18/09/2026 |  |  | 65 |  | 65
ADIDAS | 0903380624-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 442 | 23/09/2026 | 442 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380624 LI2668 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 442 |  | 442 |  |  | 2026-12-09 | 14/09/2026 |  |  | 442 |  | 442
ADIDAS | 0903380631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 50 | 30/09/2026 | 50 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380631 LI2667 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 50 |  | 50 |  |  | 15/09/2026 | 16/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903380648-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380648 HK7311 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  | 329 | 2026-03-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1379 | 1342 | 37 |  | 13
ADIDAS | 0903380684-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 393 | 30/09/2026 | 393 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380684 LI2647 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 393 |  | 393 |  |  | 28/09/2026 | 28/09/2026 |  |  | 393 |  | 393
ADIDAS | 0903380949-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 130 | 30/09/2026 | 130 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380949 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 130 |  | 130 |  |  | 28/09/2026 | 28/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903380973-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 327 | 30/09/2026 | 327 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380973 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 327 |  | 327 |  |  | 26/09/2026 | 28/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903381000-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381000 LI2671 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 113 |  | 113 |  |  | 19/09/2026 | 21/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903381024-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 379 | 30/09/2026 | 379 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381024 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 379 |  | 379 |  |  | 26/09/2026 | 28/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903381048-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 265 | 30/09/2026 | 265 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381048 LI2672 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 265 |  | 265 |  |  | 18/09/2026 | 19/09/2026 |  |  | 265 |  | 265
ADIDAS | 0903381067-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 271 | 15/10/2026 | 271 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381067 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-01-10 |  |  | 271 |  | 271
ADIDAS | 0903381072-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 241 | 2026-07-10 | 241 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 30/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381072 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 17/09/2026 | 18/09/2026 |  |  | 241 |  | 241 |  |  | 14/09/2026 | 15/09/2026 |  |  | 241 |  | 241
ADIDAS | 0903381723-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 130 | 30/09/2026 | 130 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 23/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381723 LI2668 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 130 |  | 130 |  |  | 16/09/2026 | 17/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903381763-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 23/09/2026 | 150 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381763 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 16/09/2026 |  |  | 150 |  | 150 |  |  | 2026-10-09 | 2026-12-09 | 2026-09-09 | 2026-12-09 | 150 | 150
ADIDAS | 0903381803-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 498 | 23/09/2026 | 498 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381803 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 498 |  | 498 |  |  | 2026-12-09 | 14/09/2026 |  |  | 498 |  | 498
ADIDAS | 0903381828-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 568 | 23/09/2026 | 568 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381828 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 568 |  | 568 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 568 | 544 | 24
ADIDAS | 0903381881-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 732 | 30/09/2026 | 732 | SA | SA31/07/2026 | G1F | SWEATSHIRT | G1 | (02/09/2026) |  | 21/09: ex-fty 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381881 HK7311 | 2026-03-09 | KAHATEX CIJERAH | CANADA | SEA | 16/09/2026 | ESS HDY |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 732 |  | 732 |  |  | 2026-12-09 | 14/09/2026 | 15/09/2026 | 15/09/2026 | 732 | 357 | 375
ADIDAS | 0903382128-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 511 | 31/08/2026 | 511 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 31/08: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L1 SUB PROCESS_V3 | 0903382128 JC8238 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | W LIN SJ T |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 511 | 511 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 511 | 511
ADIDAS | 0903382140-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 420 | 2026-09-09 | 420 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903382140 IW2479 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 420 | 420 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 420 | 420
ADIDAS | 0903382660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 40 | 30/09/2026 | 40 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382660 LI2671 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 40 |  | 40 |  |  | 19/09/2026 | 21/09/2026 | 2026-11-09 | 2026-11-09 | 40 | 23 | 17
ADIDAS | 0903382688-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 50 | 30/09/2026 | 50 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382688 LI2646 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 25/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 50 |  | 50 |  |  | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50
ADIDAS | 0903382689-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 149 | 30/09/2026 | 149 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382689 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 149 |  | 149 |  |  | 18/09/2026 | 19/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903382714-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 40 | 30/09/2026 | 40 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382714 LI2668 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 40 |  | 40 |  |  | 16/09/2026 | 17/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903382830-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2D,G2G,G2N,G2O,G2P,G2S | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382830 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M FEELCOZY HD |  | SS27 | 2026-08-09 | 17/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 14223 | 777 |  | 3022 | 2026-04-09 | 14/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 14961 | 39 |  | 3376
ADIDAS | 0903383240-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 23/09/2026 | 234 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903383240 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 14/09/2026 | 16/09/2026 |  |  | 234 |  | 234 |  |  | 2026-10-09 | 2026-12-09 |  |  | 234 |  | 234
ADIDAS | 0903383252-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 292 | 15/10/2026 | 292 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383252 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 292 |  | 292 |  |  | 2026-01-10 | 2026-02-10 |  |  | 292 |  | 292
ADIDAS | 0903384022-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 3923 | 29/08/2026 | 3923 | SA | SA31/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok |  | 29/08: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903384022 KD9094 | 20/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 29/08/2026 | 27/08/2026 | 29/08/2026 | 3923 | 3923 |  |  |  | 20/08/2026 | 26/08/2026 | 24/08/2026 | 29/08/2026 | 3923 | 3923
ADIDAS | 0903384056-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 5972 | 28/08/2026 | 5972 | SA | SA31/07/2026 | G2C,G2G,G2H | T-SHIRT | G2 | ok |  | 28/08: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903384056 KC6386 | 20/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 5972 | 5972 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 31/08/2026 | 5972 | 5963 | 9
ADIDAS | 0903384138-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 104 | 30/09/2026 | 104 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 29/09: ex-fty 839055 | PRINT L2 SUB PROCESS_V3 | 0903384138 KB7172 | 16/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-08-10 | HOT COMMUNITY |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 104 |  | 104 |  |  | 2026-05-10 | 2026-05-10 |  |  | 104 |  | 104
ADIDAS | 0903384150-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT-SLT | 1272 | 28/08/2026 | 1272 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 27/08: ex-fty 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384150 JD5302 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W 3S FT CF PT |  | SS27-SLT | 26/08/2026 | 28/08/2026 | 24/08/2026 | 27/08/2026 | 1272 | 1272 |  |  |  | 20/08/2026 | 24/08/2026 | 22/08/2026 | 31/08/2026 | 1272 | 1272
ADIDAS | 0903384172-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 498 | 28/08/2026 | 498 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 28/08: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903384172 JC8238 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | W LIN SJ T |  | SS27-SLT | 26/08/2026 | 28/08/2026 | 28/08/2026 | 28/08/2026 | 498 | 498 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 31/08/2026 | 498 | 498
ADIDAS | 0903384176-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 480 | 2026-09-09 | 480 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903384176 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 480 | 480 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-04-09 | 2026-08-09 | 480 | 480
ADIDAS | 0903384200-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT-SLT | 765 | 31/08/2026 | 765 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 29/08: ex-fty 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384200 JD5302 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 765 | 765 |  |  |  | 24/08/2026 | 27/08/2026 | 26/08/2026 | 29/08/2026 | 765 | 765
ADIDAS | 0903384236-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ-SLT | 514 | 31/08/2026 | 514 | ID | ID31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 31/08: ex-fty 516342 | PRINT L1 SUB PROCESS_V3 | 0903384236 JC8238 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W LIN SJ T |  | SS27-SLT | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 514 | 514 |  |  |  | 24/08/2026 | 27/08/2026 | 27/08/2026 | 31/08/2026 | 514 | 514
ADIDAS | 0903384949-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 1138 | 2026-07-10 | 1138 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903384949 JC5283 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-10 | M L SLIDE PKT T |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 1138 |  | 1138 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1138 |  | 1138 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1138 |  | 1138
ADIDAS | 0903385022-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 1278 | 2026-07-10 | 1278 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385022 JC5282 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-08-10 | M L SLIDE PKT T |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 1278 |  | 1278 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1278 |  | 1278 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1278 |  | 1278
ADIDAS | 0903385097-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 1076 | 2026-07-10 | 1076 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 1st Art (TC 10 pcs) 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385097 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-10-10 | M L SLIDE PKT T |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 1076 |  | 1076 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1076 |  | 1076 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1076 |  | 1076
ADIDAS | 0903385968-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 100 | 15/10/2026 | 100 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903385968 KD3936 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | RELEASED |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-07-10 |  |  | 100 |  | 100
ADIDAS | 0903386031-1 KY7166 | BLACK | 75D | S2706CHCC008 | 1328 | 15/10/2026 | 1328 | ID | ID31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386031 KY7166 |  | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | CC DNA SHO BLACK |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1328 |  | 1328 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1328 |  | 1328
ADIDAS | 0903386171-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2E,G2F,G2Q,G2S | PANTS | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903386171 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M FEELCOZY PANT |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 14972 | 28 |  | 3360 | 2026-05-09 | 2026-12-09 | 2026-07-09 | 15/09/2026 | 15000 | 15007 | -7 | 7 | 487
ADIDAS | 0903386207-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 248 | 29/08/2026 | 248 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | ok |  | 29/08: ex-fty 839055 | EMBRO SUB PROCESS_V1 | 0903386207 KD9090 | 20/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 248 | 248 |  |  |  | 24/08/2026 | 26/08/2026 | 24/08/2026 | 29/08/2026 | 248 | 248
ADIDAS | 0903386305-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 230 | 30/09/2026 | 230 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 22/09: ex-fty 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903386305 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 230 |  | 230 |  |  | 21/09/2026 | 22/09/2026 |  |  | 230 |  | 230 |  |  | 18/09/2026 | 19/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903387168-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903387168 LI2667 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 18/09/2026 | 19/09/2026 |  |  | 107 |  | 107 |  |  | 15/09/2026 | 16/09/2026 | 2026-11-09 | 2026-11-09 | 107 | 81 | 26
ADIDAS | 0903387206-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 463 | 23/09/2026 | 463 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903387206 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 14/09/2026 | 16/09/2026 |  |  | 463 |  | 463 |  |  | 2026-10-09 | 2026-12-09 |  |  | 463 |  | 463
ADIDAS | 0903388753-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 450 | 31/08/2026 | 450 | SA | SA31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 31/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903388753 KD9090 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | K BLANK TEE |  | SS27 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 450 | 450 |  |  |  | 26/08/2026 | 27/08/2026 | 26/08/2026 | 31/08/2026 | 450 | 450
ADIDAS | 0903388790-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 1096 | 28/08/2026 | 1096 | SA | SA31/07/2026 | G2C,G2G | T-SHIRT | G2 | ok |  | 28/08: ex-fty 516333 | EMBRO SUB PROCESS_V1 | 0903388790 KD9090 | 20/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | K BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 1096 | 1096 |  |  |  | 20/08/2026 | 24/08/2026 | 24/08/2026 | 29/08/2026 | 1096 | 1096
ADIDAS | 0903389129-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903389129 KW1544 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 800 |  | 800 |  |  | 2026-01-10 | 2026-02-10 |  |  | 800 |  | 800
ADIDAS | 0903389678-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 207 | 30/09/2026 | 207 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 29/09: ex-fty (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903389678 KD3911 | 16/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 207 |  | 207 |  |  | 2026-11-09 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 207 | 205 | 2
ADIDAS | 0903389758-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1O | T-SHIRT | G1 | ok |  | 25/09: ex-fty 814006 | EMBRO SUB PROCESS_V1 | 0903389758 KD3911 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 109 |  | 109 |  |  | 2026-11-09 | 2026-12-09 | 14/09/2026 | 15/09/2026 | 109 | 99 | 10 |  | 59
ADIDAS | 0903389769-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 232 | 30/09/2026 | 232 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | (12/09/2026) |  | 23/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903389769 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 232 |  | 232 |  |  | 19/09/2026 | 21/09/2026 |  |  | 232 |  | 232
ADIDAS | 0903389808-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 415 | 23/09/2026 | 415 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903389808 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 15/09/2026 | 16/09/2026 |  |  | 415 |  | 415 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 415 | 354 | 61
ADIDAS | 0903390259-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 500 | 2026-07-10 | 500 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 30/09: ex-fty 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390259 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 24/09/2026 |  |  | 500 |  | 500 |  |  | 22/09/2026 | 22/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903390291-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903390291 IW2479 | 2026-03-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-08-09 | 276 | 276
ADIDAS | 0903390301-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 2062 | 15/10/2026 | 2062 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903390301 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-12-10 | M L SLIDE PKT T |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 2062 |  | 2062 |  |  | 2026-08-10 | 2026-10-10 |  |  | 2062 |  | 2062 |  |  | 2026-06-10 | 2026-08-10 |  |  | 2062 |  | 2062
ADIDAS | 0903391446-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 1098 | 28/08/2026 | 1098 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | ok |  | 28/08: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903391446 KC6386 | 20/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 26/08/2026 | M BLANK TEE |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 1098 | 1098 |  |  |  | 20/08/2026 | 24/08/2026 | 21/08/2026 | 29/08/2026 | 1098 | 1098
ADIDAS | 0903391655-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903391655 KW1543 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M BLANK TEE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 800 |  | 800 |  |  | 2026-01-10 | 2026-01-10 |  |  | 800 |  | 800
ADIDAS | 0903393703-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 1833 | 2026-12-09 | 1833 | NT | NT31/07/2026 | G2P | SWEATSHIRT | G2 | ok |  | 10/09: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393703 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M FEELCOZY HD |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-10-09 | 1833 | 1833 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-04-09 | 2026-11-09 | 1833 | 1833
ADIDAS | 0903394768-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 891 | 30/09/2026 | 891 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394768 KA5090 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 891 |  | 891 |  |  | 21/09/2026 | 22/09/2026 |  |  | 891 |  | 891 |  |  | 18/09/2026 | 19/09/2026 | 2026-09-09 | 2026-09-09 | 891 |  | 891
ADIDAS | 0903394796-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 940 | 30/09/2026 | 940 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394796 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 25/09/2026 | MINI EMB T |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 940 |  | 940 |  |  | 22/09/2026 | 23/09/2026 |  |  | 940 |  | 940 |  |  | 19/09/2026 | 21/09/2026 |  |  | 940 |  | 940
ADIDAS | 0903396292-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 316 | 15/10/2026 | 316 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396292 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-10 | K BLANK TEE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 316 |  | 316 |  |  | 28/09/2026 | 29/09/2026 |  |  | 316 |  | 316
ADIDAS | 0903396384-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 435 | 15/10/2026 | 435 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396384 KD9090 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 435 |  | 435 |  |  | 26/09/2026 | 28/09/2026 |  |  | 435 |  | 435
ADIDAS | 0903396585-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT-SLT | 3823 | 28/08/2026 | 3823 | ID | ID31/07/2026 | G3F | PANTS | G3 | ok |  | 27/08: ex-fty 516471 | EMBRO SUB PROCESS_V1 | 0903396585 JE3854 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/08/2026 | M FEELCOZY PANT |  | SS27-SLT | 19/08/2026 | 28/08/2026 | 20/08/2026 | 27/08/2026 | 3823 | 3823 |  |  |  | 13/08/2026 | 24/08/2026 | 15/08/2026 | 27/08/2026 | 3823 | 3823
ADIDAS | 0903397832-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 356 | 30/09/2026 | 356 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 28/09: ex-fty 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397832 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 356 |  | 356 |  |  | 2026-03-10 | 2026-05-10 |  |  | 356 |  | 356 |  |  | 2026-01-10 | 2026-02-10 | 15/09/2026 | 15/09/2026 | 356 | 312 | 44
ADIDAS | 0903397883-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 258 | 30/09/2026 | 258 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 28/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397883 JC5282 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-10 | M L SLIDE PKT T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 258 |  | 258 |  |  | 2026-03-10 | 2026-05-10 |  |  | 258 |  | 258 |  |  | 2026-01-10 | 2026-02-10 | 2026-04-09 | 2026-04-09 | 258 | 1 | 257
ADIDAS | 0903402737-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 268 | 29/08/2026 | 268 | SA | SA31/07/2026 | G2C | T-SHIRT | G2 | (01/09/2026(6)) |  | 29/08: ex-fty 839055 | EMBRO SUB PROCESS_V1 | 0903402737 KC6387 | 20/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/08/2026 | K BLANK TEE |  | SS27 | 28/08/2026 | 29/08/2026 | 29/08/2026 | 29/08/2026 | 268 | 268 |  |  |  | 24/08/2026 | 26/08/2026 | 28/08/2026 | 28/08/2026 | 268 | 268
ADIDAS | 0903445381-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 2861 | 30/09/2026 | 2861 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445381 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 2861 |  | 2861 |  |  | 15/09/2026 | 18/09/2026 | 2026-02-09 | 14/09/2026 | 2861 | 2509 | 352 |  | 11
ADIDAS | 0903445382-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 24/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445382 LC6339 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 100 |  | 100 |  |  | 19/09/2026 | 19/09/2026 | 2026-09-09 | 2026-09-09 | 100 | 100
ADIDAS | 0903445383-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G2N | T-SHIRT | G2 | (11/07/2026) | (04/07/2026) | 25/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445383 KX8877 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M CHIP T WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 100 |  | 100 |  |  | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903445384-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 3083 | 30/09/2026 | 3083 | SA | SA26/06/2026 | G3B | PANTS | G3 | (08/08/2026) | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445384 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S FT OH PT |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 3083 |  | 3083 |  |  | 28/09/2026 | 2026-01-10 | 15/09/2026 | 15/09/2026 | 3083 | 406 | 2677
ADIDAS | 0903445385-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 3082 | 30/09/2026 | 3082 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903445385 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | W 3S FT QZ HD |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 3082 |  | 3082 |  |  | 19/09/2026 | 23/09/2026 |  |  | 3082 |  | 3082
ADIDAS | 0903450148-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1114 | 2026-05-09 | 1114 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450148 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-04-09 | 1114 | 1114 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-03-09 | 1114 | 1114 |  |  |  | 24/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 1114 | 1114
ADIDAS | 0903450149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 3791 | 2026-05-09 | 3791 | SA | SA15/05/2026 | G2J,G2K | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450149 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-04-09 | 3791 | 3791 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-02-09 | 3791 | 3791 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-02-09 | 3791 | 3791
ADIDAS | 0903450150-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 129 | 23/09/2026 | 129 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 21/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450150 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 129 | 129 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 29/08/2026 | 129 | 129
ADIDAS | 0903450152-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 172 | 23/09/2026 | 172 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 18/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450152 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 2026-12-08 | 2026-06-08 | 2026-07-08 | 172 | 172 |  |  |  | 2026-04-08 | 2026-07-08 | 31/07/2026 | 29/08/2026 | 172 | 168 | 4
ADIDAS | 0903450153-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 942 | 15/10/2026 | 942 | SA | SA24/01/2026 | G1M | T-SHIRT | G1 | ok |  | DRC 0010-hold shipment customer (BTP_24_06_2026 -> Req. PO Cancel & Quantity Change). T2 Far Eastern, PI Date 21-Sep (switch with fabric from Libolon for 500pcs). T2 Fu Hsun, PI Date 18-Aug. 814006 | HT SUB PROCESS_V1 | 0903450153 KG8548 | 2026-08-04 | KAHATEX CIJERAH | THAILAND | SEA | 30/06/2026 | ADIZERO E TEE |  | FW26 | 30/06/2026 | 17/09/2026 | 30/06/2026 | 2026-07-07 | 942 | 273 | 669 |  |  | 26/06/2026 | 15/09/2026 | 20/06/2026 | 20/06/2026 | 942 | 273 | 669 |  |  | 25/06/2026 | 14/09/2026 | 2026-12-08 | 2026-12-08 | 942 | 273 | 669
ADIDAS | 0903467951-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903467951 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 920 |  | 920 |  |  | 2026-08-10 | 2026-10-10 |  |  | 920 |  | 920
ADIDAS | 0903472791-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1P | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472791 IB8688 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | ESS HDY |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 2000 |  | 2000 |  |  | 19/09/2026 | 23/09/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903472864-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472864 IB8688 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 480 |  | 480 |  |  | 2026-08-10 | 2026-10-10 |  |  | 480 |  | 480
ADIDAS | 0903476466-1 JZ7711 | BLACK | 120D | S2608MR0202 | 249 | 23/09/2026 | 249 | SA | SA14/08/2026 | G3G | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903476466 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 249 |  | 249 |  |  | 2026-11-09 | 2026-12-09 |  |  | 249 |  | 249 |  |  | 2026-08-09 | 2026-09-09 |  |  | 249 |  | 249
ADIDAS | 0903478300-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 24/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478300 HK7311 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | ESS HDY |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 2001 |  | 2001 |  |  | 30/09/2026 | 2026-03-10 |  |  | 2001 |  | 2001
ADIDAS | 0903478487-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 202 | 15/09/2026 | 202 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478487 IN1172 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 202 | 202 |  |  | 202 | 2026-04-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 202 | 202 |  |  | 43 | 2026-03-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 202 | 202 |  |  | 5
ADIDAS | 0903478570-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478570 HK7311 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 29/09/2026 | ESS HDY |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 2001 |  | 2001 |  |  | 25/09/2026 | 29/09/2026 |  |  | 2001 |  | 2001
ADIDAS | 0903478582-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 139 | 15/09/2026 | 139 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478582 IN1156 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 139 | 139 |  |  | 121 | 2026-04-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 139 | 139 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 139 | 139
ADIDAS | 0903478609-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 164 | 15/09/2026 | 164 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478609 IN1157 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 164 | 164 |  |  | 164 | 2026-04-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 164 | 164 |  |  | 54 | 2026-03-09 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 164 | 164 |  |  | 7
ADIDAS | 0903478627-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478627 HK7311 |  | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ESS HDY |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 920 |  | 920 |  |  | 13/10/2026 | 15/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903480271-1 IS1413 | BLACK | 60D | S2425M405 | 900 | 15/10/2026 | 900 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848024 | PRINT L3 SUB PROCESS_V3 | 0903480271 IS1413 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/09/2026 | IN RANGE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 21/09/2026 | 22/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903480314-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903480314 KA5090 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 28/09/2026 | MINI EMB T |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 602 |  | 602 |  |  | 24/09/2026 | 24/09/2026 |  |  | 602 |  | 602 |  |  | 22/09/2026 | 22/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903480831-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 335 | 15/10/2026 | 335 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480831 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/10/2026 | W BLANK TEE |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 335 |  | 335 |  |  | 2026-10-10 | 2026-10-10 |  |  | 335 |  | 335
ADIDAS | 0903480958-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1F | SWEATSHIRT | G1 | (15/09/2026) |  | 26/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480958 HK7309 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | ESS HDY |  | SS27 | 17/09/2026 | 22/09/2026 |  |  | 2250 |  | 2250 |  |  | 14/09/2026 | 18/09/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903480993-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1679 | 15/10/2026 | 1679 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480993 HK7311 |  | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | ESS HDY |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1679 |  | 1679 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1679 |  | 1679
ADIDAS | 0903481767-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 5210 | 15/10/2026 | 5210 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903481767 KD9097 |  | KAHATEX CIJERAH | VIETNAM | SEA | 14/10/2026 | W BLANK TEE |  | SS27 | 14/10/2026 | 17/10/2026 |  |  | 5210 |  | 5210 |  |  | 2026-10-10 | 14/10/2026 |  |  | 5210 |  | 5210
ADIDAS | 0903482244-1 HK7309 | BLACK | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482244 HK7309 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 480 |  | 480 |  |  | 2026-01-10 | 2026-03-10 |  |  | 480 |  | 480
ADIDAS | 0903482398-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482398 HK7311 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 920 |  | 920 |  |  | 2026-10-10 | 13/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903482505-1 HK7309 | BLACK | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482505 HK7309 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | ESS HDY |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1680 |  | 1680 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1680 |  | 1680
ADIDAS | 0903483394-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483394 HK7309 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 920 |  | 920 |  |  | 2026-01-10 | 2026-03-10 |  |  | 920 |  | 920
ADIDAS | 0903483669-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483669 IB8688 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | ESS HDY |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 2000 |  | 2000 |  |  | 28/09/2026 | 30/09/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903483726-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483726 IB8688 |  | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1680 |  | 1680 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903484758-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484758 HK7309 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | ESS HDY |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 2250 |  | 2250 |  |  | 24/09/2026 | 28/09/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903484802-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 481 | 15/10/2026 | 481 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484802 HK7311 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ESS HDY |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 481 |  | 481 |  |  | 13/10/2026 | 15/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903484985-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484985 IB8688 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | ESS HDY |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920 |  |  | 2026-07-10 | 2026-08-10 |  |  | 920 |  | 920
ADIDAS | 0903485610-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 23/09/2026 | 100 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485610 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA | 18/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 16/09/2026 |  |  | 100 |  | 100 |  |  | 2026-11-09 | 2026-12-09 |  |  | 100 |  | 100
ADIDAS | 0903486465-1 IS1413 | BLACK | 60D | S2425M405 | 1322 | 15/10/2026 | 1322 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903486465 IS1413 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 25/09/2026 | IN RANGE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1322 |  | 1322 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1322 |  | 1322
ADIDAS | 0903486554-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 207 | 15/09/2026 | 207 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 830009 | HT SUB PROCESS_V1 | 0903486554 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 207 | 207 |  |  | 207 | 2026-04-09 | 2026-12-09 | 2026-08-09 | 14/09/2026 | 207 | 207 |  |  | 9 | 2026-03-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 207 | 207 |  |  | 4
ADIDAS | 0903486586-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 23/09/2026 | 106 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486586 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 15/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 106 |  | 106 |  |  | 2026-11-09 | 2026-12-09 |  |  | 106 |  | 106 |  |  | 2026-08-09 | 2026-09-09 |  |  | 106 |  | 106
ADIDAS | 0903486633-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 103 | 16/09/2026 | 103 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 16/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, PI Date 23-Oct, switch from order 0903443493). T2 Fu Hsun, PI Date 11-Sep, switch from order 903443493). 830009 | HT SUB PROCESS_V1 | 0903486633 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 103 | 103 |  |  | 10 | 2026-04-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 103 | 103 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 103 | 103
ADIDAS | 0903486870-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1164 | 15/10/2026 | 1164 | SI | SI14/08/2026 | G3J | SHORTS | G3 | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486870 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/10/2026 | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX | 24/10/2026 | 28/10/2026 |  |  | 1164 |  | 1164 |  |  | 21/10/2026 | 24/10/2026 |  |  | 1164 |  | 1164 |  |  | 17/10/2026 | 21/10/2026 |  |  | 1164 |  | 1164
ADIDAS | 0903487218-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487218 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | ESS HDY |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 920 |  | 920 |  |  | 30/09/2026 | 2026-01-10 |  |  | 920 |  | 920
ADIDAS | 0903487925-1 JZ7709 | BLACK | 120D | S2608MR0201 | 249 | 23/09/2026 | 249 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487925 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 15/09/2026 | 17/09/2026 |  |  | 249 |  | 249 |  |  | 2026-11-09 | 14/09/2026 |  |  | 249 |  | 249 |  |  | 2026-08-09 | 2026-10-09 |  |  | 249 |  | 249
ADIDAS | 0903488008-1 JZ7709 | BLACK | 120D | S2608MR0201 | 706 | 23/09/2026 | 706 | SI | SI14/08/2026 | G3K | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488008 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 15/09/2026 | 17/09/2026 |  |  | 706 |  | 706 |  |  | 2026-11-09 | 14/09/2026 |  |  | 706 |  | 706 |  |  | 2026-08-09 | 2026-10-09 |  |  | 706 |  | 706
ADIDAS | 0903488538-1 JZ7711 | BLACK | 120D | S2608MR0202 | 690 | 23/09/2026 | 690 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488538 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 690 |  | 690 |  |  | 2026-11-09 | 2026-12-09 |  |  | 690 |  | 690 |  |  | 2026-08-09 | 2026-09-09 |  |  | 690 |  | 690
ADIDAS | 0903488735-1 JZ7709 | BLACK | 120D | S2608MR0201 | 101 | 23/09/2026 | 101 | SI | SI14/08/2026 | G3D | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488735 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 18/09/2026 | 19/09/2026 |  |  | 101 |  | 101 |  |  | 15/09/2026 | 16/09/2026 |  |  | 101 |  | 101 |  |  | 2026-11-09 | 2026-12-09 |  |  | 101 |  | 101
ADIDAS | 0903489269-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 714 | 15/10/2026 | 714 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903489269 KA5090 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | MINI EMB T |  | SS27 | 2026-10-10 | 2026-10-10 |  |  | 714 |  | 714 |  |  | 2026-07-10 | 2026-07-10 |  |  | 714 |  | 714 |  |  | 2026-05-10 | 2026-05-10 |  |  | 714 |  | 714
ADIDAS | 0903490564-1 JZ7711 | BLACK | 120D | S2608MR0202 | 241 | 23/09/2026 | 241 | SA | SA14/08/2026 | G3I | SHORTS | G3 | ok |  | 21/09: ex-fty. IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490564 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 15/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 15/09/2026 | 16/09/2026 |  |  | 241 |  | 241 |  |  | 2026-11-09 | 2026-12-09 |  |  | 241 |  | 241 |  |  | 2026-08-09 | 2026-09-09 |  |  | 241 |  | 241
ADIDAS | 0903492007-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 2604 | 15/10/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903492007 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903492168-1 JM6500 | COLLEGIATE GREEN | 60D | F25SPRMGFX040 | 70 | 15/10/2026 | 70 | NT | NT14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 848012 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903492168 JM6500 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | M DDL SKATE T |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 70 |  | 70 |  |  | 2026-02-10 | 2026-02-10 |  |  | 70 |  | 70
ADIDAS | 0903492638-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 120 | 15/10/2026 | 120 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3+HT SUB PROCESS_V3 | 0903492638 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903492648-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1200 | 2026-12-09 | 1200 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 11/09: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903492648 KX7410 | 2026-04-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-08-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 2026-04-09 | 2026-08-09 | 2026-04-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903492683-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1352 | 15/09/2026 | 1352 | SI | SI14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903492683 KX7410 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1352 | 1352 |  |  | 73 | 2026-08-09 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 1352 | 1352
ADIDAS | 0903493699-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1299 | 15/10/2026 | 1299 | ID | ID14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493699 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | SPORT GOODS T |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 1299 |  | 1299 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1299 |  | 1299
ADIDAS | 0903493969-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 2 | 2026-07-10 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903493969 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 26/09/2026 | MER GR NNHD M BLACK |  | SS27-MS | 26/09/2026 | 26/09/2026 |  |  | 2 |  | 2 |  |  | 23/09/2026 | 23/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494061-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 2 | 2026-07-10 | 2 | AN | AN14/08/2026 | G2C | T-SHIRT | G2 | (14/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903494061 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-01-10 | MER GR NNTEE M WHITE |  | SS27-MS | 2026-01-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 28/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494327-1 LJ9158 | WHITE | 90D | 226205_JZSJ | 8582 | 15/10/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903494327 LJ9158 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494405-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 116 | 15/09/2026 | 116 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494405 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 116 | 116 |  |  | 116 | 2026-04-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 116 | 116 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 116 | 116
ADIDAS | 0903494445-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 126 | 15/09/2026 | 126 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2-Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494445 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-07-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 126 | 126 |  |  | 126 | 2026-04-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 126 | 126 |  |  | 34 | 2026-03-09 | 2026-11-09 | 2026-11-09 | 14/09/2026 | 126 | 126 |  |  | 3
ADIDAS | 0903494678-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 100 | 15/10/2026 | 100 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3 SUB PROCESS_V3 | 0903494678 LE1858 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 24/10/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100 |  |  | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903495174-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 2 | 29/09/2026 | 2 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(33)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495174 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 14/09/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 14/09/2026 | 16/09/2026 |  |  | 2 |  | 2 |  |  | 2026-10-09 | 2026-12-09 |  |  | 2 |  | 2 |  |  | 2026-09-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903495387-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 2 | 29/09/2026 | 2 | SI | SI14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(33)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495387 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 14/09/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 14/09/2026 | 16/09/2026 |  |  | 2 |  | 2 |  |  | 2026-10-09 | 2026-12-09 |  |  | 2 |  | 2 |  |  | 2026-09-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903495400-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 2 | 29/09/2026 | 2 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(33)) |  | 825054 | PRINT L3 SUB PROCESS_V3 | 0903495400 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 14/09/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 14/09/2026 | 16/09/2026 |  |  | 2 |  | 2 |  |  | 2026-10-09 | 2026-12-09 |  |  | 2 |  | 2
ADIDAS | 0903496564-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 29 | 15/10/2026 | 29 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496564 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 29 |  | 29 |  |  | 17/10/2026 | 19/10/2026 |  |  | 29 |  | 29 |  |  | 16/10/2026 | 17/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496599-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 29 | 15/10/2026 | 29 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496599 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 29 |  | 29 |  |  | 20/10/2026 | 21/10/2026 |  |  | 29 |  | 29 |  |  | 19/10/2026 | 20/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496637-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 517 | 15/10/2026 | 517 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903496637 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 517 |  | 517 |  |  | 17/10/2026 | 19/10/2026 |  |  | 517 |  | 517 |  |  | 16/10/2026 | 17/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903497305-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 161 | 15/10/2026 | 161 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903497305 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 161 |  | 161 |  |  | 20/10/2026 | 21/10/2026 |  |  | 161 |  | 161 |  |  | 19/10/2026 | 20/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903497830-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 9287 | 15/10/2026 | 9287 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903497830 KA5089 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | MINI EMB T |  | SS27 | 30/09/2026 | 2026-07-10 |  |  | 9287 |  | 9287 |  |  | 26/09/2026 | 2026-03-10 |  |  | 9287 |  | 9287 |  |  | 24/09/2026 | 2026-01-10 |  |  | 9287 |  | 9287
ADIDAS | 0903500463-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 889 | 15/10/2026 | 889 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903500463 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 24/10/2026 |  |  | 889 |  | 889 |  |  | 19/10/2026 | 21/10/2026 |  |  | 889 |  | 889 |  |  | 17/10/2026 | 20/10/2026 |  |  | 889 |  | 889
ADIDAS | 0903501618-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 122 | 15/10/2026 | 122 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903501618 LE4570 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 122 |  | 122 |  |  | 20/10/2026 | 21/10/2026 |  |  | 122 |  | 122 |  |  | 19/10/2026 | 20/10/2026 |  |  | 122 |  | 122
ADIDAS | 0903502054-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 823 | 15/10/2026 | 823 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903502054 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 22/10/2026 | 23/10/2026 |  |  | 823 |  | 823 |  |  | 19/10/2026 | 20/10/2026 |  |  | 823 |  | 823 |  |  | 17/10/2026 | 19/10/2026 |  |  | 823 |  | 823
ADIDAS | 0903502085-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 166 | 15/10/2026 | 166 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 848012 | PRINT L3+HT SUB PROCESS_V3 | 0903502085 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 166 |  | 166 |  |  | 20/10/2026 | 21/10/2026 |  |  | 166 |  | 166 |  |  | 19/10/2026 | 20/10/2026 |  |  | 166 |  | 166
ADIDAS | 0903502271-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 842 | 2026-12-09 | 842 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903502271 KC6386 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-09 | M BLANK TEE |  | SS27 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 842 | 842 |  |  |  | 2026-05-09 | 2026-08-09 | 31/08/2026 | 2026-09-09 | 842 | 839 | 3
ADIDAS | 0903502599-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 324 | 15/10/2026 | 324 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903502599 KD9094 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M BLANK TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 324 |  | 324 |  |  | 30/09/2026 | 2026-01-10 |  |  | 324 |  | 324
ADIDAS | 0903503153-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 124 | 15/10/2026 | 124 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 1st Art (TC 10 pcs) 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503153 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 124 |  | 124 |  |  | 20/10/2026 | 21/10/2026 |  |  | 124 |  | 124 |  |  | 19/10/2026 | 20/10/2026 |  |  | 124 |  | 124
ADIDAS | 0903503177-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 204 | 15/10/2026 | 204 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503177 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 204 |  | 204 |  |  | 20/10/2026 | 21/10/2026 |  |  | 204 |  | 204 |  |  | 19/10/2026 | 20/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903503204-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 244 | 15/10/2026 | 244 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503204 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 244 |  | 244 |  |  | 17/10/2026 | 19/10/2026 |  |  | 244 |  | 244 |  |  | 16/10/2026 | 17/10/2026 |  |  | 244 |  | 244
ADIDAS | 0903503236-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 226 | 15/10/2026 | 226 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503236 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 24/10/2026 |  |  | 226 |  | 226 |  |  | 19/10/2026 | 21/10/2026 |  |  | 226 |  | 226 |  |  | 17/10/2026 | 20/10/2026 |  |  | 226 |  | 226
ADIDAS | 0903503267-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 127 | 15/10/2026 | 127 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903503267 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 127 |  | 127 |  |  | 17/10/2026 | 19/10/2026 |  |  | 127 |  | 127 |  |  | 16/10/2026 | 17/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903503360-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2004 | 15/09/2026 | 2004 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503360 KD4066 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | M BLANK TEE BLACK |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2004 | 2004 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-01-09 | 2026-08-09 | 2004 | 2004
ADIDAS | 0903503397-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2503 | 15/09/2026 | 2503 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503397 KE3742 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2503 | 2503 |  |  | 1474 | 2026-08-09 | 2026-11-09 | 2026-07-09 | 14/09/2026 | 2503 | 2503 |  |  | 3
ADIDAS | 0903503800-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 300 | 15/10/2026 | 300 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903503800 KC6386 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M BLANK TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903504690-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 1006 | 2026-12-09 | 1006 | SA | SA14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504690 KD9094 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | M BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 1006 | 1006 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-12-09 | 1006 | 1006
ADIDAS | 0903504729-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 2022 | 2026-12-09 | 2022 | SI | SI14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504729 KD9097 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | W BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2022 | 2022 |  |  |  | 2026-07-09 | 2026-09-09 | 31/08/2026 | 2026-08-09 | 2022 | 2022
ADIDAS | 0903535974-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 804028 | PRINT L3 SUB PROCESS_V3 | 0903535974 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | JAPAN | AIR-COLLECT | 14/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 14/09/2026 | 15/09/2026 |  |  | 500 |  | 500 |  |  | 2026-10-09 | 2026-11-09 | 2026-11-09 | 2026-11-09 | 500 | 290 | 210
ADIDAS | 0903535975-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 960026 | PRINT L3 SUB PROCESS_V3 | 0903535975 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | AUSTRALIA | AIR-COLLECT | 15/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 15/09/2026 | 15/09/2026 |  |  | 500 |  | 500 |  |  | 2026-11-09 | 2026-11-09 | 2026-11-09 | 2026-11-09 | 500 | 500
ADIDAS | 0903548414-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 141 | 30/09/2026 | 141 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 29/09: ex-fty 800005 | HT+PAD SUB PROCESS_V3 | 0903548414 KB5961 | 24/11/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 141 |  | 141 |  |  | 17/09/2026 | 18/09/2026 |  |  | 141 |  | 141 |  |  | 15/09/2026 | 16/09/2026 |  |  | 141 |  | 141
ADIDAS | 0903550837-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ-SLT | 898 | 30/09/2026 | 898 | ID | ID28/08/2026 | G2J | T-SHIRT | G2 | ok |  | 23/09: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903550837 JC8239 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W LIN SJ T |  | SS27-SLT | 26/09/2026 | 28/09/2026 |  |  | 898 |  | 898 |  |  | 23/09/2026 | 24/09/2026 | 14/09/2026 | 15/09/2026 | 898 | 848 | 50 |  | 531
ADIDAS | 0903553857-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 123 | 30/09/2026 | 123 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553857 KB5965 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 19/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 19/09/2026 | 21/09/2026 |  |  | 123 |  | 123 |  |  | 16/09/2026 | 17/09/2026 |  |  | 123 |  | 123 |  |  | 14/09/2026 | 15/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903553911-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 134 | 30/09/2026 | 134 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553911 KB5961 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 134 |  | 134 |  |  | 17/09/2026 | 18/09/2026 |  |  | 134 |  | 134 |  |  | 15/09/2026 | 16/09/2026 |  |  | 134 |  | 134
ADIDAS | 0903554010-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 108 | 30/09/2026 | 108 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 814006 | HT+PAD SUB PROCESS_V3 | 0903554010 KB5965 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA | 19/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 19/09/2026 | 21/09/2026 |  |  | 108 |  | 108 |  |  | 16/09/2026 | 17/09/2026 |  |  | 108 |  | 108 |  |  | 14/09/2026 | 15/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903556417-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 107 | 30/09/2026 | 107 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | (06/08/2026) |  | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0903556417 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 21/09/2026 | 22/09/2026 |  |  | 107 |  | 107 |  |  | 17/09/2026 | 18/09/2026 |  |  | 107 |  | 107 |  |  | 15/09/2026 | 16/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903557215-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 19/09/2026 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | Waiting LO (By Air-Collect). DRC 0047-hold shipment customer. 859013 | PRINT L3 SUB PROCESS_V3 | 0903557215 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | TAIWAN | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-11-09 | 300 | 300
ADIDAS | 0903557229-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2 | 30/09/2026 | 2 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 18/09: ex-fty (CMA test) (By Air-Express). DRC 0064-other customer related delay reason. 825054 | PRINT L3 SUB PROCESS_V3 | 0903557229 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | AIR-EXPRESS | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 2 | 2 |  |  | 2 | 2026-08-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 2 | 2
ADIDAS | 0903557263-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2600 | 30/09/2026 | 2600 | SI | SI28/08/2026 | G2K,G2N | T-SHIRT | G2 | (25/09/2026(13)) |  | 18/09: ex-fty (China) (By Air-Collect). DRC 0064-other customer related delay reason. 825066 | PRINT L3 SUB PROCESS_V3 | 0903557263 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | SEA | 14/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 14/09/2026 | 17/09/2026 | 2026-12-09 | 15/09/2026 | 2600 | 1370 | 1230 |  | 143 | 2026-10-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 2600 | 2597 | 3
ADIDAS | 0903565505-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 1473 | 30/09/2026 | 1473 | ID | ID28/08/2026 | G2E | T-SHIRT | G2 | ok |  | 25/09: ex-fty 960026 | HT+PAD SUB PROCESS_V3 | 0903565505 KB5965 | 24/11/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 19/09/2026 | 21/09/2026 |  |  | 1473 |  | 1473 |  |  | 16/09/2026 | 17/09/2026 |  |  | 1473 |  | 1473 |  |  | 14/09/2026 | 15/09/2026 |  |  | 1473 |  | 1473
ADIDAS | 0903566115-1 HL2231 | LEGEND INK F17/WHITE | 45D | F224CSIM430 | 71 | 15/10/2026 | 71 | NT | NT28/08/2026 | G2M | PANTS | G2 | (02/10/2026) |  | 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903566115 HL2231 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | IN RANGE |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 71 |  | 71 |  |  | 2026-05-10 | 2026-05-10 |  |  | 71 |  | 71
ADIDAS | 0903595003-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 4024 | 15/09/2026 | 4024 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595003 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 4024 | 2875 | 1149 |  | 2634 | 2026-08-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 4024 | 4024
ADIDAS | 0903595010-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 5004 | 15/09/2026 | 5004 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595010 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 5004 | 4995 | 9 |  | 719 | 2026-07-09 | 2026-11-09 | 2026-02-09 | 2026-02-09 | 5004 | 5004
ADIDAS | 0903595012-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 890 | 15/09/2026 | 890 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595012 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 17/09/2026 | 2026-10-09 | 14/09/2026 | 890 | 497 | 393 |  | 10 | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-11-09 | 890 | 890
ADIDAS | 0903595017-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 310 | 19/09/2026 | 310 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | Waiting LO. DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595017 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 310 | 310 |  |  | 38 | 2026-07-09 | 2026-11-09 | 2026-02-09 | 2026-04-09 | 310 | 310
ADIDAS | 0903595019-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 2026-12-09 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 12/09: ex-fty (By Air-Collect). 806020 | PRINT L3 SUB PROCESS_V3 | 0903595019 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | HONGKONG | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-11-09 | 2026-12-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-12-09 | 300 | 300
ADIDAS | 0903602357-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 700 | 30/09/2026 | 700 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 800005 | PRINT L3 SUB PROCESS_V3 | 0903602357 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | INDONESIA | AIR-COLLECT | 22/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 22/09/2026 | 23/09/2026 |  |  | 700 |  | 700 |  |  | 18/09/2026 | 19/09/2026 | 2026-10-09 | 2026-10-09 | 700 | 590 | 110
ADIDAS | 0903602358-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1400 | 30/09/2026 | 1400 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 839055 | PRINT L3 SUB PROCESS_V3 | 0903602358 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | SINGAPORE | AIR-COLLECT | 23/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 1400 |  | 1400 |  |  | 19/09/2026 | 21/09/2026 | 2026-10-09 | 2026-10-09 | 1400 | 1119 | 281
ADIDAS | 0903602359-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1880 | 30/09/2026 | 1880 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 814006 | PRINT L3 SUB PROCESS_V3 | 0903602359 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | THAILAND | AIR-COLLECT | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 16/09/2026 | 17/09/2026 |  |  | 1880 |  | 1880 |  |  | 2026-12-09 | 14/09/2026 | 2026-10-09 | 2026-10-09 | 1880 | 1647 | 233
ADIDAS | 0903602360-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2100 | 30/09/2026 | 2100 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 838103 | PRINT L3 SUB PROCESS_V3 | 0903602360 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | MALAYSIA | AIR-COLLECT | 17/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 17/09/2026 | 18/09/2026 |  |  | 2100 |  | 2100 |  |  | 14/09/2026 | 15/09/2026 | 2026-10-09 | 2026-10-09 | 2100 | 1800 | 300
ADIDAS | 0903602828-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1200 | 30/09/2026 | 1200 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | DRC 0064-other customer related delay reason. 600000 | PRINT L3 SUB PROCESS_V3 | 0903602828 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 15/09/2026 | 16/09/2026 |  |  | 1200 |  | 1200 |  |  | 2026-11-09 | 2026-12-09 | 2026-11-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903603199-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 221 | 15/09/2026 | 221 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603199 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 17/09/2026 | 2026-11-09 | 14/09/2026 | 221 | 126 | 95 |  | 29 | 2026-07-09 | 14/09/2026 | 2026-02-09 | 2026-05-09 | 221 | 221
ADIDAS | 0903603200-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 484 | 15/09/2026 | 484 | SI | SI28/08/2026 | G2I | T-SHIRT | G2 | (25/09/2026(17)) |  | 15/09: ex-fty. DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603200 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 484 | 242 | 242 |  | 103 | 2026-07-09 | 2026-11-09 | 2026-03-09 | 2026-03-09 | 484 | 484
ADIDAS | 0903613329-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 301 | 15/10/2026 | 301 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903613329 KA6229 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 301 |  | 301 |  |  | 2026-05-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-01-10 | 2026-02-10 |  |  | 301 |  | 301
ADIDAS | 0903613711-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 345 | 15/10/2026 | 345 | ID | ID11/09/2026 | G2G | T-SHIRT | G2 |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903613711 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-03-10 | 2026-03-10 |  |  | 345 |  | 345 |  |  | 30/09/2026 | 30/09/2026 |  |  | 345 |  | 345 |  |  | 28/09/2026 | 28/09/2026 |  |  | 345 |  | 345
ADIDAS | 0903613739-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 116 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 838103 | PAD+HT SUB PROCESS_V3 | 0903613739 KA0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903614275-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 241 | 15/10/2026 | 241 | ID | ID11/09/2026 | G3D | SHORTS | G3 |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614275 KD3875 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-11 | ADI365/// SHO W BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 241 |  | 241 |  |  | 2026-06-11 | 2026-06-11 |  |  | 241 |  | 241 |  |  | 2026-05-11 | 2026-05-11 |  |  | 241 |  | 241
ADIDAS | 0903614393-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 100 | 15/10/2026 | 100 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614393 KA6229 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-08-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 |  |  | 100 |  | 100
ADIDAS | 0903614427-1 KA0235 | BLACK | 105D | S2608WR0901-SLT | 111 | 15/10/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903614427 KA0235 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903615793-1 KD3875 | BLACK | 120D | S2608WR0201-SLT | 117 | 15/10/2026 | 117 | ID | ID11/09/2026 | G3D | SHORTS | G3 |  |  | 839055 | PAD+HT SUB PROCESS_V3 | 0903615793 KD3875 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-11 | ADI365/// SHO W BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 117 |  | 117 |  |  | 2026-06-11 | 2026-06-11 |  |  | 117 |  | 117 |  |  | 2026-05-11 | 2026-05-11 |  |  | 117 |  | 117
ADIDAS | 4501440021-2 KA3521 | BLACK/WHITE | 60D | S2650MTR434 | 46 | 26/08/2026 | 46 | SI | SI19/12/2025 | G3E | SHORTS | G3 | ok |  | 24/08: ex-fty (By Air-Collect). T2 Libolon, PI Date 12-Jan, actual receives 12-Jan. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501440021 KA3521 | 2026-05-02 | KAHATEX CIJERAH | SOUTH AFRICA | AIR-COLLECT | 17/07/2026 | WE BAS 3SWV SH |  | FW26 | 17/07/2026 | 24/07/2026 | 20/07/2026 | 22/07/2026 | 46 | 46 |  |  |  | 14/07/2026 | 21/07/2026 | 15/07/2026 | 16/07/2026 | 46 | 46 |  |  |  | 2026-07-07 | 14/07/2026 | 14/07/2026 | 14/07/2026 | 46 | 46
ADIDAS | 4501769841-5 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 2026-10-07 | 2026-09-07 | 2026-10-07 | 400 | 400 |  |  |  | 2026-03-07 | 2026-07-07 | 26/06/2026 | 14/07/2026 | 400 | 400
ADIDAS | 4501769841-6 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 383 | 2026-05-09 | 383 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 04/09: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 27/07/2026 | IN RANGE |  | FW26 | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 383 | 383 |  |  |  | 22/07/2026 | 29/07/2026 | 2026-08-07 | 27/07/2026 | 383 | 383
ADIDAS | 4501904766-1 IX3617 | TENT GREEN F16 | 60D | S2315KSWU253 | 400 | 28/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3 SUB PROCESS_V3 | 4501904766 IX3617 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 400 | 400 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-08-07 | 17/07/2026 | 400 | 400
ADIDAS | 4501906112-1 HR6306 | BLACK/BLACK | 60D | S2315KSWU253 | 461 | 28/08/2026 | 461 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 28/08: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906112 HR6306 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 461 | 461 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-08-07 | 20/07/2026 | 461 | 461
ADIDAS | 4501906120-2 HR6306 | BLACK/BLACK | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906120 HR6306 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/07/2026 | U FI LOGO SH |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 17/07/2026 | 400 | 400 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-07-07 | 20/07/2026 | 400 | 400
ADIDAS | 4501906793-2 IX3617 | TENT GREEN F16 | 60D | S2315KSWU253 | 400 | 26/08/2026 | 400 | AN | AN24/04/2026 | G2Q | SHORTS | G2 | ok | (14/05/2026) | 24/08: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501906793 IX3617 | 2026-12-06 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 16/07/2026 | U FI LOGO SH |  | FW26 | 16/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 400 | 400 |  |  |  | 13/07/2026 | 16/07/2026 | 2026-07-07 | 17/07/2026 | 400 | 400
ADIDAS | 4501928501-1 LG9669 | BLACK | 120D | S2754WAS514C | 189 | 14/10/2026 | 189 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928501 LG9669 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 14/10/2026 | W SL WV SK BLACK |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 189 |  | 189 |  |  | 2026-10-10 | 13/10/2026 |  |  | 189 |  | 189
ADIDAS | 4501929295-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 160 | 14/10/2026 | 160 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929295 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 23/09/2026 | 23/09/2026 |  |  | 160 |  | 160 |  |  | 19/09/2026 | 19/09/2026 |  |  | 160 |  | 160 |  |  | 17/09/2026 | 17/09/2026 |  |  | 160 |  | 160
ADIDAS | 4501929321-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 582 | 14/10/2026 | 582 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929321 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-05-10 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 2026-05-10 | 2026-05-10 |  |  | 582 |  | 582 |  |  | 2026-01-10 | 2026-01-10 |  |  | 582 |  | 582 |  |  | 29/09/2026 | 29/09/2026 |  |  | 582 |  | 582
ADIDAS | 4501933525-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 113 | 21/08/2026 | 113 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, using fabric stock. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933525 KA3521 | 22/07/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 16/07/2026 | 21/07/2026 | 113 | 113 |  |  |  | 2026-10-07 | 16/07/2026 | 13/07/2026 | 15/07/2026 | 113 | 113 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-10-07 | 15/07/2026 | 113 | 113
ADIDAS | 4501933526-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 647 | 21/08/2026 | 647 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 21/08: ex-fty. T2 Libolon, PI Date 28-May, actual receives 20-May. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933526 KD0677 | 22/07/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 17/07/2026 | WE BAS 3SWV SH |  | FW26 | 17/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 647 | 647 |  |  |  | 14/07/2026 | 21/07/2026 | 14/07/2026 | 17/07/2026 | 647 | 647 |  |  |  | 2026-07-07 | 14/07/2026 | 13/07/2026 | 17/07/2026 | 647 | 647
ADIDAS | 4501933527-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 347 | 21/08/2026 | 347 | SI | SI21/05/2026 | G3E | SHORTS | G3 | ok | (13/06/2026) | 21/08: ex-fty. T2 Libolon, using fabric stock. ZA30 | HT+PPA+PPH L1 SUB PROCESS_V3 | 4501933527 KA3521 | 2026-06-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/07/2026 | WE BAS 3SWV SH |  | FW26 | 15/07/2026 | 21/07/2026 | 15/07/2026 | 21/07/2026 | 347 | 347 |  |  |  | 2026-10-07 | 16/07/2026 | 2026-09-07 | 13/07/2026 | 347 | 347 |  |  |  | 2026-03-07 | 2026-09-07 | 2026-09-07 | 14/07/2026 | 347 | 347
ADIDAS | 4502065732-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 671 | 14/10/2026 | 671 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 21/09/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 21/09/2026 | 24/09/2026 |  |  | 671 |  | 671 |  |  | 17/09/2026 | 21/09/2026 |  |  | 671 |  | 671
ADIDAS | 4502070409-1 LF0718 | BLACK | 105D | S2754MAS512B | 140 | 14/10/2026 | 140 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-12-10 | M SL WV OH PT BLACK |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 140 |  | 140 |  |  | 2026-08-10 | 2026-09-10 |  |  | 140 |  | 140
ADIDAS | 4502075077-1 IN1173 | WHITE | 90D | S2408WR1600 | 190 | 2026-07-10 | 190 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075077 IN1173 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 190 |  | 190 |  |  | 2026-07-10 | 2026-08-10 | 2026-11-08 | 26/08/2026 | 190 | 190 |  |  |  | 2026-06-10 | 2026-07-10 | 2026-08-08 | 22/08/2026 | 190 | 190
ADIDAS | 4502075081-1 KA0246 | BLACK | 90D | S2608WR0902 | 961 | 14/10/2026 | 961 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075081 KA0246 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 29/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/09/2026 | 30/09/2026 |  |  | 961 |  | 961 |  |  | 25/09/2026 | 26/09/2026 |  |  | 961 |  | 961 |  |  | 24/09/2026 | 25/09/2026 |  |  | 961 |  | 961
ADIDAS | 4502075922-1 KT4840 | ONIX | 90D | S2408MR1600 | 100 | 14/10/2026 | 100 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075922 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 |  |  | 100 |  | 100
ADIDAS | 4502075923-1 IN1156 | BLACK | 90D | S2408MR1600 | 413 | 2026-07-10 | 413 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 26/09/2026 |  |  | 413 |  | 413 |  |  | 23/09/2026 | 24/09/2026 | 26/08/2026 | 2026-12-09 | 413 | 413 |  |  |  | 22/09/2026 | 23/09/2026 | 18/08/2026 | 2026-05-09 | 413 | 413
ADIDAS | 4502075924-1 IN1172 | BLACK | 90D | S2408WR1600 | 212 | 2026-07-10 | 212 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075924 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 212 |  | 212 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-04-09 | 212 | 212 |  |  |  | 2026-02-10 | 2026-03-10 | 27/08/2026 | 2026-04-09 | 212 | 212
ADIDAS | 4502075931-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 179 | 14/10/2026 | 179 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502075931 LD0292 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-07-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-07-10 | 2026-10-10 |  |  | 179 |  | 179 |  |  | 2026-03-10 | 2026-07-10 |  |  | 179 |  | 179 |  |  | 2026-02-10 | 2026-06-10 |  |  | 179 |  | 179
ADIDAS | 4502075932-1 KA0235 | BLACK | 90D | S2608WR0901 | 971 | 14/10/2026 | 971 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075932 KA0235 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 23/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 23/10/2026 | 26/10/2026 |  |  | 971 |  | 971 |  |  | 20/10/2026 | 22/10/2026 |  |  | 971 |  | 971 |  |  | 19/10/2026 | 21/10/2026 |  |  | 971 |  | 971
ADIDAS | 4502076908-1 KA4331 | BLACK | 90D | S2608MR0902 | 1102 | 14/10/2026 | 1102 | SA | SA03/07/2026 | G1C | SHORTS | G1 | (26/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-05-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 1102 |  | 1102 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1102 |  | 1102 |  |  | 30/09/2026 | 2026-02-10 |  |  | 1102 |  | 1102
ADIDAS | 4502077517-1 IN1172 | BLACK | 90D | S2408WR1600 | 292 | 30/09/2026 | 292 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077517 IN1172 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 26/09/2026 | ADIZERO E TEE |  | SS27-YTI | 26/09/2026 | 28/09/2026 |  |  | 292 |  | 292 |  |  | 24/09/2026 | 25/09/2026 | 27/08/2026 | 2026-10-09 | 292 | 292 |  |  |  | 23/09/2026 | 24/09/2026 | 24/08/2026 | 2026-09-09 | 292 | 292
ADIDAS | 4502077518-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 30/09/2026 | 167 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502077518 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 167 |  | 167 |  |  | 26/09/2026 | 28/09/2026 | 24/08/2026 | 2026-07-09 | 167 | 167 |  |  |  | 25/09/2026 | 26/09/2026 | 22/08/2026 | 2026-05-09 | 167 | 167
ADIDAS | 4502077519-1 IN1157 | WHITE | 90D | S2408MR1600 | 706 | 30/09/2026 | 706 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 06-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077519 IN1157 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 29/09/2026 | ADIZERO E TEE |  | SS27-YTI | 29/09/2026 | 30/09/2026 |  |  | 706 |  | 706 |  |  | 26/09/2026 | 28/09/2026 | 2026-09-09 | 2026-11-09 | 706 | 703 | 3 |  |  | 25/09/2026 | 26/09/2026 | 2026-02-09 | 2026-10-09 | 706 | 703 | 3
ADIDAS | 4502080370-1 IN1156 | BLACK | 90D | S2408MR1600 | 527 | 30/09/2026 | 527 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502080370 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 527 | 362 | 165 |  |  | 2026-12-09 | 15/09/2026 | 26/08/2026 | 2026-10-09 | 527 | 527 |  |  |  | 2026-11-09 | 14/09/2026 | 24/08/2026 | 2026-09-09 | 527 | 527
ADIDAS | 4502080372-1 IN1173 | WHITE | 90D | S2408WR1600 | 109 | 30/09/2026 | 109 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. ZA30 | HT SUB PROCESS_V1 | 4502080372 IN1173 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 17/09/2026 | ADIZERO E TEE |  | SS27-YTI | 17/09/2026 | 17/09/2026 |  |  | 109 |  | 109 |  |  | 15/09/2026 | 15/09/2026 | 2026-12-08 | 21/08/2026 | 109 | 109 |  |  |  | 14/09/2026 | 14/09/2026 | 2026-11-08 | 20/08/2026 | 109 | 109
ADIDAS | 4502347774-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 800 | 15/09/2026 | 800 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3+PAD SUB PROCESS_V3 | 4502347774 KA0546 | 26/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 800 | 800 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-09-09 | 800 | 800
ADIDAS | 46075347-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1622 | 30/09/2026 | 1622 | SI | SI22/08/2026 | G2F | T-SHIRT | G2 |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 46075347 LZ9161 | 2026-04-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 16/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27 | 16/09/2026 | 17/09/2026 |  |  | 1622 |  | 1622 |  |  | 2026-12-09 | 14/09/2026 | 29/08/2026 | 2026-11-09 | 1622 | 4200 | -2578 | 2578
Total |  |  |  |  | 2369305 |  | 2357892 | [22 empty] | 2357892 | 1203825 | 1154067 |  | 47084 |  |  |  |  | 2357892 | 1427184 | 930708 | 2614 | 28121 |  |  |  |  | 533627 | 175339 | 358288 |  | 6994