## Sheet1
JO Tracking Report
Factory: | KAHATEX CIJERAH | Floor | G1,G2,G3,G4,G5,SPL | JO: |  | Style No: |  | Delivery Date: | 01/09/2026 - 31/10/2026 | JO Status: | Uncompleted, Completed, Export | Printed by: | REYNALDI | Print time: | 20/09/2026 00:05:18
Customer Name | Order No. | Color | Lot No | Factory Style | Qty | Delivery Date | Plan Qty | Merchaniser | PO.NO | Line | Product Type | Floor | Fabrics | Auxiliary | JO Remarks | Process Route Name | Cust_Order_No | Pre-production event finish date | Factory | Ship To | Ship Mode | Sewing Start | Style Description | Plan Remarks | Season | SEWING | [8 empty] | COMPLETE ASSEMBLY | [8 empty] | HEAT TRANSFER
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902372325-1 KF2349 | KHAKI SIX F26 | 90D | S2554MESS676SJ | 590 | 2026-08-09 | 590 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372325 KF2349 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-09-07 | 20/07/2026 | 590 | 590 |  |  |  | 2026-03-07 | 15/07/2026 | 29/06/2026 | 2026-09-07 | 590 | 590
ADIDAS | 0902372479-1 JC9296 | WHITE/BLACK | 90D | S2554MESS676SJ | 186 | 2026-08-09 | 186 | SA | SA24/01/2026 | G2E,G2L | T-SHIRT | G2 | ok | (12/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902372479 JC9296 | 2026-08-04 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | M SJ T |  | FW26 | 2026-08-07 | 22/07/2026 | 2026-09-07 | 21/07/2026 | 186 | 186 |  |  |  | 2026-03-07 | 17/07/2026 | 2026-02-07 | 18/07/2026 | 186 | 186
ADIDAS | 0902497405-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 244 | 2026-08-09 | 244 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497405 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-06-08 | 29/07/2026 | 2026-06-08 | 244 | 244 |  |  |  | 24/07/2026 | 2026-03-08 | 27/07/2026 | 2026-07-08 | 244 | 244
ADIDAS | 0902497408-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2L | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497408 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 21/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902497412-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 205 | 2026-08-09 | 205 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). 800005 | PRINT L3 SUB PROCESS_V3 | 0902497412 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 27/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 205 | 205 |  |  |  | 22/07/2026 | 30/07/2026 | 15/07/2026 | 2026-04-08 | 205 | 205
ADIDAS | 0902497414-1 IB6941 | NIGHT CARGO F15 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN24/01/2026 | G2J | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902497414 IB6941 | 2026-03-03 | KAHATEX CIJERAH | INDONESIA | SEA | 29/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 29/07/2026 | 2026-04-08 | 29/07/2026 | 2026-04-08 | 100 | 100 |  |  |  | 24/07/2026 | 30/07/2026 | 16/07/2026 | 22/07/2026 | 100 | 100
ADIDAS | 0902545290-1 GK9267 | BLACK | 45D | S211CSIM117FLRO | 3000 | 2026-05-09 | 3000 | SA | SA06/02/2026 | G1D,G1K,G3I | PANTS | G1,G3 | ok | ok | 04/09: ex-fty 823016 | EMBRO SUB PROCESS_V1 | 0902545290 GK9267 | 2026-11-03 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 21/07/2026 | M 3S FL O PT |  | FW26 | 21/07/2026 | 27/07/2026 | 21/07/2026 | 27/07/2026 | 3000 | 3000 |  |  |  | 16/07/2026 | 22/07/2026 | 2026-07-07 | 22/07/2026 | 3000 | 3000
ADIDAS | 0902557495-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600-MTF | 824 | 2026-08-09 | 824 | NT | NT06/02/2026 | G1E | T-SHIRT | G1 | ok | (21/02/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, material qulity issues (Stain, snagging), PI Date 17-Mar, using fabric stock (FOC 2147 yd) (switch with fabric from Far Eastern.). T2 Fu Hsun, PI Date 31-Jan, actual receives 06-Apr. 800005 | HT SUB PROCESS_V1 | 0902557495 KG8548 | 2026-05-05 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | ADIZERO E TEE |  | FW26 | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 16/07/2026 | 24/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824 |  |  |  | 15/07/2026 | 23/07/2026 | 16/07/2026 | 24/07/2026 | 824 | 824
ADIDAS | 0902622148-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 4220 | 2026-12-09 | 4220 | AT | AT27/02/2026 | G3J,G3K | PANTS | G3 | ok | (19/03/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902622148 JD1881 | 26/05/2026 | KAHATEX CIJERAH | JAPAN | SEA | 27/07/2026 | M 3S FT TC PT |  | FW26 | 27/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 4220 | 4220 |  |  |  | 22/07/2026 | 30/07/2026 | 2026-10-07 | 25/07/2026 | 4220 | 4220
ADIDAS | 0902635931-1 KF2350 | MAROON | 90D | S2554MESS676SJ | 602 | 2026-08-09 | 602 | SA | SA27/02/2026 | G2S | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L1 SUB PROCESS_V3 | 0902635931 KF2350 | 26/05/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-08-07 | IN RANGE |  | FW26 | 2026-08-07 | 20/07/2026 | 2026-08-07 | 20/07/2026 | 602 | 602 |  |  |  | 2026-03-07 | 15/07/2026 | 26/06/2026 | 2026-02-07 | 602 | 602
ADIDAS | 0902636875-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2720 | 15/09/2026 | 2720 | AT | AT04/03/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (28/03/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902636875 JE6372 | 2026-02-06 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-09-09 | 29/08/2026 | 2026-09-09 | 2720 | 2720 |  |  |  | 24/08/2026 | 2026-05-09 | 28/07/2026 | 2026-09-09 | 2720 | 2720
ADIDAS | 0902652229-1 KD5830 | BLACK | 105D | F2525M009 | 154 | 2026-08-09 | 154 | AT | AT27/02/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. IMPROVE. T2-SAB, LLT material (CNY), PI Date 10-Mar, actual receives 06-Mar. T2 Fu Hsun PI Date 15-Apr, actual receives 13-Apr. 800005 | PRINT L2 SUB PROCESS_V3 | 0902652229 KD5830 | 2026-11-06 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 154 | 154 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-01-07 | 2026-10-07 | 154 | 154
ADIDAS | 0902652411-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652411 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 24/07/2026 | 20/07/2026 | 23/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 21/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652437-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 100 | 2026-08-09 | 100 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652437 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 100 | 100 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 20/07/2026 | 100 | 100
ADIDAS | 0902652462-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 205 | 30/09/2026 | 205 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652462 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 28/07/2026 | 20/07/2026 | 28/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 23/07/2026 | 15/07/2026 | 15/07/2026 | 205 | 205
ADIDAS | 0902652495-1 KQ8922 | AURORA COFFEE S26 | 60D | S2625M070 | 241 | 30/09/2026 | 241 | AN | AN27/02/2026 | G2L | T-SHIRT | G2 | ok | (18/03/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3 SUB PROCESS_V3 | 0902652495 KQ8922 | 23/04/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | TREFOIL T-SHIRT |  | FW26-L2L | 20/07/2026 | 30/07/2026 | 20/07/2026 | 29/07/2026 | 241 | 241 |  |  |  | 15/07/2026 | 27/07/2026 | 15/07/2026 | 23/07/2026 | 241 | 241
ADIDAS | 0902769872-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 4240 | 2026-05-09 | 4240 | AT | AT27/03/2026 | G1P,G1Q,G1R | T-SHIRT | G1 | ok | ok | 04/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0902769872 LE8199 | 16/06/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-08 | LFC A F JSY SE |  | FW26-FJ | 2026-05-08 | 19/08/2026 | 2026-10-08 | 18/08/2026 | 4240 | 4240 |  |  |  | 31/07/2026 | 13/08/2026 | 31/07/2026 | 18/08/2026 | 4240 | 4240
ADIDAS | 0902803294-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV-MTF | 233 | 2026-05-09 | 233 | NT | NT10/04/2026 | G3D | PANTS | G3 | ok | (08/05/2026) | 05/09: ex-fty. T2 Libolon, PI Date 21-Jun, actual receives 22-May. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902803294 JM1778 | 30/06/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/07/2026 | M SL WV PT 1 |  | FW26 | 14/07/2026 | 21/07/2026 | 15/07/2026 | 17/07/2026 | 233 | 233 |  |  |  | 2026-09-07 | 16/07/2026 | 13/07/2026 | 17/07/2026 | 233 | 233
ADIDAS | 0902803647-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 30/09/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual reiceves 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803647 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 15/09/2026 | 2026-07-08 | 15/09/2026 | 100 | 100 |  |  |  | 2026-03-08 | 2026-11-09 | 22/07/2026 | 2026-05-08 | 100 | 100
ADIDAS | 0902803818-1 KF9922 | TEAM COLL BURGUNDY 2 | 90D | F2606CHMU042 | 377 | 2026-08-09 | 377 | AN | AN10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 08/09: ex-fty (NYK warehouse). T2 Kahatex, material quality issues (creasemark), PI Date 09-May, actual receives 17-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L2+EMBRO SUB PROCESS_V3 | 0902803818 KF9922 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 27/07/2026 | MUFC LF TEE |  | FW26 | 27/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 377 | 377 |  |  |  | 22/07/2026 | 30/07/2026 | 21/07/2026 | 28/07/2026 | 377 | 377
ADIDAS | 0902803854-1 KG2924 | BLACK | 90D | F2606CHLF041 | 100 | 15/10/2026 | 100 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 20-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803854 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-04-08 | LFC LF TEE |  | FW26 | 2026-04-08 | 2026-01-09 | 2026-05-08 | 2026-02-09 | 100 | 100 |  |  |  | 30/07/2026 | 28/08/2026 | 22/07/2026 | 2026-02-09 | 100 | 100
ADIDAS | 0902803922-1 KG2924 | BLACK | 90D | F2606CHLF041 | 200 | 15/10/2026 | 200 | AT | AT10/04/2026 | G2J | T-SHIRT | G2 | ok | (29/04/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Kahatex, PI Date 09-May, actual receives 13-Jul. T2 Sincetech (flatknit), PI Date 11-May, actual receives 06-May. 800005 | PRINT L1+EMBRO SUB PROCESS_V3 | 0902803922 KG2924 | 30/06/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-08 | LFC LF TEE |  | FW26 | 2026-06-08 | 2026-04-09 | 2026-06-08 | 2026-03-09 | 200 | 200 |  |  |  | 2026-03-08 | 2026-01-09 | 23/07/2026 | 2026-05-08 | 200 | 200
ADIDAS | 0902804254-1 LE8211 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFL | 4267 | 2026-05-09 | 4267 | SA | SA10/04/2026 | G2L,G2M,G2O | T-SHIRT | G2 | ok | (29/04/2026) | 04/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804254 LE8211 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSYL SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 29/08/2026 | 2026-04-09 | 4267 | 4267 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-04-09 | 4267 | 4267
ADIDAS | 0902804368-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 12412 | 2026-05-09 | 12412 | AT | AT10/04/2026 | G1Q,G2K,G2L,G2M,G2O | T-SHIRT | G1,G2 | ok | ok | 05/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0902804368 LE5779 | 30/06/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | LFC H F JSY SE |  | FW26-FJ | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 12412 | 12412 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-01-09 | 2026-05-09 | 12412 | 12412
ADIDAS | 0902808177-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 3220 | 2026-12-09 | 3220 | AT | AT10/04/2026 | G3C,G3D,G3E | PANTS | G3 | ok | (29/04/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902808177 JE6346 | 30/06/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 3220 | 3220 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 2026-01-08 | 3220 | 3217 | 3
ADIDAS | 0902847822-1 JE3837 | BLACK/WHITE | 90D | S2554MESS682FT | 1348 | 2026-05-09 | 1348 | AT | AT24/04/2026 | G2T | SWEATSHIRT | G2 | ok | (14/05/2026) | 05/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847822 JE3837 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 14/07/2026 | M FEELCOZY SWT |  | FW26 | 14/07/2026 | 21/07/2026 | 14/07/2026 | 21/07/2026 | 1348 | 1348 |  |  |  | 2026-09-07 | 16/07/2026 | 2026-10-07 | 15/07/2026 | 1348 | 1348
ADIDAS | 0902847867-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 1491 | 2026-05-09 | 1491 | AT | AT24/04/2026 | G1D | PANTS | G1 | ok | ok | 04/09: ex-fty 804028 | EMBRO SUB PROCESS_V1 | 0902847867 JE3854 | 14/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M FEELCOZY PANT |  | FW26 | 21/07/2026 | 2026-05-08 | 23/07/2026 | 31/07/2026 | 1491 | 1491 |  |  |  | 16/07/2026 | 31/07/2026 | 18/07/2026 | 23/07/2026 | 1491 | 1491
ADIDAS | 0902853964-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 81 | 15/10/2026 | 81 | AT | AT24/04/2026 | G2P | SWEATSHIRT | G2 | (22/05/2026) | (18/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902853964 KG2925 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-09 | LFC LF HD |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 81 | 81 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-11-08 | 2026-10-09 | 81 | 81
ADIDAS | 0902854036-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 29-May, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902854036 KA8777 | 28/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/07/2026 | TIRO26L SHO M |  | FW26-L2L | 14/07/2026 | 17/07/2026 | 14/07/2026 | 17/07/2026 | 132 | 132 |  |  |  | 2026-09-07 | 14/07/2026 | 13/07/2026 | 16/07/2026 | 132 | 132 |  |  |  | 2026-07-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 132 | 132
ADIDAS | 0902854145-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 430 | 2026-05-09 | 430 | SI | SI24/04/2026 | G1D | JACKET | G1 | ok | ok | 04/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902854145 JE0052 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-08 | W 3S FT FZ HD |  | FW26 | 2026-05-08 | 2026-07-08 | 2026-06-08 | 2026-07-08 | 430 | 430 |  |  |  | 31/07/2026 | 2026-04-08 | 31/07/2026 | 2026-06-08 | 430 | 430
ADIDAS | 0902854237-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434-SLT | 481 | 23/09/2026 | 481 | NT | NT24/04/2026 | G3E | SHORTS | G3 | ok | (14/05/2026) | 21/09: ex-fty. T2 Libolon, PI Date 15-May, actual receives 09-May. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902854237 KA3521 | 14/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26-SLT | 21/07/2026 | 2026-03-08 | 21/07/2026 | 31/07/2026 | 481 | 481 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 30/07/2026 | 481 | 481 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 23/07/2026 | 481 | 481
ADIDAS | 0902858585-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 114 | 2026-08-09 | 114 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858585 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 31/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 31/07/2026 | 2026-07-08 | 31/07/2026 | 2026-03-08 | 114 | 114 |  |  |  | 28/07/2026 | 2026-04-08 | 17/07/2026 | 28/07/2026 | 114 | 114
ADIDAS | 0902858612-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 777 | 30/09/2026 | 777 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902858612 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 22/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 22/07/2026 | 2026-07-08 | 22/07/2026 | 2026-03-08 | 777 | 777 |  |  |  | 17/07/2026 | 2026-04-08 | 16/07/2026 | 21/07/2026 | 777 | 777
ADIDAS | 0902860692-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 101 | 2026-08-09 | 101 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 1st Art (TC 10 pcs) 800005 | PRINT L2 SUB PROCESS_V3 | 0902860692 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 101 | 101 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-10-07 | 14/07/2026 | 101 | 101
ADIDAS | 0902860750-1 KS7434 | BLACK/DARK FOOTBALL GOLD | 90D | F2525M009 | 486 | 30/09/2026 | 486 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | (14/05/2026) | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 23-May. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860750 KS7434 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 15/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 15/07/2026 | 20/07/2026 | 15/07/2026 | 17/07/2026 | 486 | 486 |  |  |  | 2026-10-07 | 15/07/2026 | 2026-09-07 | 14/07/2026 | 486 | 486
ADIDAS | 0902860782-1 KS7413 | AURORA COFFEE S26 | 90D | F2525M009 | 205 | 2026-08-09 | 205 | AT | AT24/04/2026 | G2M | T-SHIRT | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun, PI Date 18-Jun, actual receives 03-Jul. 800005 | PRINT L2 SUB PROCESS_V3 | 0902860782 KS7413 | 14/07/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 20/07/2026 | JACQUARD JERSEY |  | FW26-L2L | 20/07/2026 | 31/07/2026 | 21/07/2026 | 31/07/2026 | 205 | 205 |  |  |  | 15/07/2026 | 28/07/2026 | 17/07/2026 | 21/07/2026 | 205 | 205
ADIDAS | 0902862481-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 309 | 31/10/2026 | 309 | SI | SI24/04/2026 | G3C | SHORTS | G3 | ok | (04/06/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, PI Date 07-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862481 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-08 | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27 | 2026-12-08 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 309 | 309 |  |  |  | 2026-07-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 309 | 309
ADIDAS | 0902882924-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 306 | 31/10/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902882924 KD0677 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887724-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 359 | 2026-05-09 | 359 | SI | SI05/05/2026 | G3E | SHORTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 28-May, using fabric stock. 516400 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887724 KD0677 | 22/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | WE BAS 3SWV SH |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 359 | 359 |  |  |  | 16/07/2026 | 29/07/2026 | 17/07/2026 | 29/07/2026 | 359 | 359 |  |  |  | 2026-09-07 | 22/07/2026 | 17/07/2026 | 25/07/2026 | 359 | 359
ADIDAS | 0902899919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 502 | 2026-05-09 | 502 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899919 LD0288 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 31/07/2026 | 502 | 502 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 502 | 502
ADIDAS | 0902899965-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902899965 LD0287 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 369 | 369 |  |  |  | 2026-06-08 | 28/08/2026 | 2026-01-08 | 2026-08-08 | 369 | 369 |  |  |  | 2026-04-08 | 26/08/2026 | 27/07/2026 | 2026-07-08 | 369 | 369
ADIDAS | 0902900771-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 327 | 2026-05-09 | 327 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900771 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 327 | 327 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-02-09 | 327 | 327 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-02-09 | 327 | 327
ADIDAS | 0902900873-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 347 | 2026-05-09 | 347 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902900873 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 31/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-06-08 | 347 | 347 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-05-08 | 347 | 347
ADIDAS | 0902900910-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 337 | 2026-07-10 | 337 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900910 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 337 |  | 337 |  |  | 29/09/2026 | 29/09/2026 | 2026-04-08 | 2026-10-08 | 337 | 337 |  |  |  | 26/09/2026 | 26/09/2026 | 2026-01-08 | 2026-10-08 | 337 | 337
ADIDAS | 0902900938-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 358 | 23/09/2026 | 358 | AN | AN15/05/2026 | G2J | T-SHIRT | G2 | ok | (05/06/2026) | 18/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900938 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 23/09/2026 | 15/09/2026 | 18/09/2026 | 358 | 358 |  |  |  | 2026-11-09 | 19/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358 |  |  |  | 2026-09-09 | 17/09/2026 | 28/08/2026 | 2026-08-09 | 358 | 358
ADIDAS | 0902900942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 23/10/2026 | 306 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902900942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 306 |  | 306 |  |  | 29/09/2026 | 29/09/2026 | 2026-04-08 | 28/08/2026 | 306 | 305 | 1 |  |  | 26/09/2026 | 26/09/2026 | 2026-01-08 | 27/08/2026 | 306 | 306
ADIDAS | 0902900970-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 306 | 2026-05-09 | 306 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902900970 KG3225 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-06-08 | 306 | 306 |  |  |  | 27/07/2026 | 2026-06-08 | 27/07/2026 | 2026-04-08 | 306 | 306 |  |  |  | 23/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 306 | 306
ADIDAS | 0902900989-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 741 | 2026-05-09 | 741 | AN | AN15/05/2026 | G2H | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902900989 KX3655 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 741 | 741 |  |  |  | 31/08/2026 | 2026-02-09 | 28/08/2026 | 2026-04-09 | 741 | 741 |  |  |  | 28/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 741 | 741
ADIDAS | 0902901357-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 410 | 2026-09-09 | 410 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901357 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-07-08 | 2026-03-09 | 410 | 410 |  |  |  | 2026-03-08 | 2026-04-09 | 2026-04-08 | 2026-03-09 | 410 | 410
ADIDAS | 0902901389-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 377 | 2026-09-09 | 377 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901389 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | M 3S WV WB LND |  | FW26 | 2026-06-08 | 2026-08-09 | 2026-06-08 | 2026-03-09 | 377 | 377 |  |  |  | 2026-03-08 | 2026-04-09 | 30/07/2026 | 2026-05-09 | 377 | 377
ADIDAS | 0902901531-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 312 | 2026-09-09 | 312 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | ok | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901531 KY4221 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | M 3S WV WB LND |  | FW26 | 2026-10-08 | 2026-08-09 | 2026-10-08 | 2026-07-09 | 312 | 312 |  |  |  | 2026-05-08 | 2026-04-09 | 2026-05-08 | 2026-01-09 | 312 | 312
ADIDAS | 0902901569-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 507 | 2026-09-09 | 507 | SA | SA15/05/2026 | G1C | JACKET | G1 | ok | (08/06/2026) | 08/09: ex-fty. T2 Formosa, PI Date 26-Jun, actual receives 16-Jul. T2 Libolon, PI Date 19-Jun, actual receives 18-Jun. T2 Kahatex, PI Date 24-Jun, actual receives 25-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901569 KY6616 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | M 3S WV WB LND |  | FW26 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-08-09 | 507 | 507 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 2026-02-09 | 507 | 507
ADIDAS | 0902901874-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB-MTF | 6443 | 30/09/2026 | 6443 | AN | AN15/05/2026 | G1C | JACKET | G1 | ok | (04/06/2026) | 24/09: ex-fty. T2 Libolon, PI Date 09-Jun, actual receives 09-Jul. T2 Formosa, PI Date 12-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902901874 LC5741 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 13/08/2026 | 23/09/2026 | 2026-12-08 | 18/09/2026 | 6443 | 5758 | 685 |  |  | 2026-10-08 | 19/09/2026 | 31/07/2026 | 19/09/2026 | 6443 | 5918 | 525 |  | 25
ADIDAS | 0902902811-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 317 | 15/09/2026 | 317 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902811 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-01-09 | 2026-10-08 | 2026-01-09 | 317 | 317 |  |  |  | 2026-06-08 | 28/08/2026 | 23/07/2026 | 2026-05-08 | 317 | 317 |  |  |  | 2026-04-08 | 26/08/2026 | 22/07/2026 | 2026-04-08 | 317 | 317
ADIDAS | 0902902836-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 595 | 15/09/2026 | 595 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902836 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 595 | 595 |  |  |  | 2026-02-09 | 2026-11-09 | 24/08/2026 | 2026-08-09 | 595 | 595 |  |  |  | 31/08/2026 | 2026-09-09 | 24/08/2026 | 2026-08-09 | 595 | 595
ADIDAS | 0902902865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 369 | 2026-05-09 | 369 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902902865 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 21/07/2026 | 2026-04-08 | 22/07/2026 | 31/07/2026 | 369 | 369 |  |  |  | 16/07/2026 | 30/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369 |  |  |  | 14/07/2026 | 28/07/2026 | 17/07/2026 | 22/07/2026 | 369 | 369
ADIDAS | 0902902891-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 15/09/2026 | 322 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902902891 KX3650 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-10-08 | 2026-01-09 | 322 | 322 |  |  |  | 2026-06-08 | 29/08/2026 | 22/07/2026 | 2026-07-08 | 322 | 322 |  |  |  | 2026-04-08 | 27/08/2026 | 22/07/2026 | 2026-06-08 | 322 | 322
ADIDAS | 0902902948-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1044 | 2026-05-09 | 1044 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902902948 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 1044 | 1044 |  |  |  | 27/08/2026 | 2026-02-09 | 21/08/2026 | 2026-01-09 | 1044 | 1044 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 1044 | 1044
ADIDAS | 0902902973-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 30/09/2026 | 880 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 23/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902902973 KX3655 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 23/09/2026 | 16/09/2026 | 18/09/2026 | 880 | 564 | 316 |  |  | 2026-11-09 | 19/09/2026 | 26/08/2026 | 18/09/2026 | 880 | 843 | 37 |  |  | 2026-09-09 | 17/09/2026 | 21/08/2026 | 18/09/2026 | 880 | 861 | 19
ADIDAS | 0902903045-1 KE8425 | WHITE | 120D | S2608MR0906A | 318 | 23/10/2026 | 318 | SI | SI15/05/2026 | G2N | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902903045 KE8425 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | Run Ess LS M WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 318 |  | 318 |  |  | 20/10/2026 | 21/10/2026 |  |  | 318 |  | 318 |  |  | 17/10/2026 | 19/10/2026 |  |  | 318 |  | 318
ADIDAS | 0902903099-1 KE8425 | WHITE | 120D | S2608MR0906A | 305 | 2026-07-10 | 305 | SI | SI15/05/2026 | G2F | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 516333 | HT+PAD SUB PROCESS_V3 | 0902903099 KE8425 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | Run Ess LS M WHITE |  | SS27-TI | 13/10/2026 | 13/10/2026 |  |  | 305 |  | 305 |  |  | 2026-09-10 | 2026-09-10 | 13/08/2026 | 28/08/2026 | 305 | 305 |  |  |  | 2026-07-10 | 2026-07-10 | 2026-11-08 | 27/08/2026 | 305 | 305
ADIDAS | 0902904515-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 339 | 2026-05-09 | 339 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904515 LD0287 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 339 | 339 |  |  |  | 2026-06-08 | 29/08/2026 | 2026-01-08 | 31/08/2026 | 339 | 339 |  |  |  | 2026-04-08 | 27/08/2026 | 27/07/2026 | 31/08/2026 | 339 | 339
ADIDAS | 0902904537-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 329 | 15/09/2026 | 329 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904537 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-08 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 329 | 329 |  |  |  | 2026-06-08 | 29/08/2026 | 31/07/2026 | 2026-10-08 | 329 | 329 |  |  |  | 2026-04-08 | 27/08/2026 | 30/07/2026 | 2026-10-08 | 329 | 329
ADIDAS | 0902904560-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902904560 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 319 |  | 319 |  |  | 2026-07-10 | 2026-08-10 | 2026-10-08 | 2026-12-08 | 319 | 319 |  |  |  | 2026-05-10 | 2026-06-10 | 2026-08-08 | 2026-12-08 | 319 | 319
ADIDAS | 0902904602-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 696 | 2026-05-09 | 696 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902904602 LD0284 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 696 | 696 |  |  |  | 28/07/2026 | 28/08/2026 | 27/07/2026 | 2026-01-08 | 696 | 696 |  |  |  | 24/07/2026 | 26/08/2026 | 25/07/2026 | 2026-01-08 | 696 | 696
ADIDAS | 0902904645-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 309 | 2026-05-09 | 309 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902904645 LD0284 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/07/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 31/07/2026 | 2026-01-09 | 2026-03-08 | 2026-01-09 | 309 | 309 |  |  |  | 28/07/2026 | 28/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309 |  |  |  | 24/07/2026 | 26/08/2026 | 28/07/2026 | 31/07/2026 | 309 | 309
ADIDAS | 0902905667-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 530 | 23/09/2026 | 530 | SA | SA15/05/2026 | G2G,G2J | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902905667 LD0285 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 27/07/2026 | 21/08/2026 | 27/07/2026 | 20/08/2026 | 530 | 530 |  |  |  | 22/07/2026 | 18/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530 |  |  |  | 20/07/2026 | 13/08/2026 | 16/07/2026 | 28/07/2026 | 530 | 530
ADIDAS | 0902905691-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 336 | 2026-12-09 | 336 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902905691 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 24/07/2026 | 29/07/2026 | 24/07/2026 | 28/07/2026 | 336 | 336 |  |  |  | 21/07/2026 | 24/07/2026 | 16/07/2026 | 23/07/2026 | 336 | 336 |  |  |  | 17/07/2026 | 22/07/2026 | 16/07/2026 | 22/07/2026 | 336 | 336
ADIDAS | 0902906579-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 15 | 23/09/2026 | 15 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902906579 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15 |  |  |  | 21/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 15 | 15
ADIDAS | 0902906608-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 1321 | 23/09/2026 | 1321 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿) , PI Date 30-Jun, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902906608 LG9669 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-04-09 | W SL WV SK BLACK |  | SS27 | 2026-04-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 1321 | 1321 |  |  |  | 2026-01-09 | 2026-11-09 | 22/08/2026 | 17/09/2026 | 1321 | 1321
ADIDAS | 0902906662-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 324 | 2026-05-09 | 324 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906662 LD0288 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 30/07/2026 | 2026-04-08 | 324 | 324 |  |  |  | 23/07/2026 | 30/07/2026 | 20/07/2026 | 31/07/2026 | 324 | 324 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 30/07/2026 | 324 | 324
ADIDAS | 0902906685-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 961 | 23/09/2026 | 961 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902906685 LD0287 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 15/09/2026 | 18/09/2026 | 14/09/2026 | 17/09/2026 | 961 | 961 |  |  |  | 2026-11-09 | 15/09/2026 | 31/07/2026 | 2026-06-08 | 961 | 961 |  |  |  | 2026-09-09 | 2026-12-09 | 30/07/2026 | 2026-06-08 | 961 | 961
ADIDAS | 0902906698-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 3281 | 2026-05-09 | 3281 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0902906698 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 21/08/2026 | 2026-05-09 | 21/08/2026 | 2026-04-09 | 3281 | 3281 |  |  |  | 18/08/2026 | 2026-02-09 | 13/08/2026 | 2026-01-09 | 3281 | 3281 |  |  |  | 13/08/2026 | 31/08/2026 | 2026-12-08 | 2026-01-09 | 3281 | 3281
ADIDAS | 0902906708-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 360 | 15/09/2026 | 360 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902906708 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 360 | 360 |  |  |  | 2026-02-09 | 2026-11-09 | 31/07/2026 | 2026-04-08 | 360 | 360 |  |  |  | 31/08/2026 | 2026-09-09 | 31/07/2026 | 2026-04-08 | 360 | 360
ADIDAS | 0902906721-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 797 | 2026-05-09 | 797 | SA | SA15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906721 KX3653 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/08/2026 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 797 | 797 |  |  |  | 2026-12-08 | 29/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-10-08 | 21/08/2026 | 797 | 797
ADIDAS | 0902906734-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 328 | 2026-05-09 | 328 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902906734 LD0288 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 24/07/2026 | 2026-04-08 | 328 | 328 |  |  |  | 21/07/2026 | 30/07/2026 | 20/07/2026 | 30/07/2026 | 328 | 328 |  |  |  | 17/07/2026 | 28/07/2026 | 20/07/2026 | 31/07/2026 | 328 | 328
ADIDAS | 0902906748-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 319 | 23/09/2026 | 319 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906748 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 19/09/2026 | 14/09/2026 | 18/09/2026 | 319 | 319 |  |  |  | 2026-10-09 | 16/09/2026 | 26/08/2026 | 2026-02-09 | 319 | 319 |  |  |  | 2026-08-09 | 14/09/2026 | 24/08/2026 | 2026-02-09 | 319 | 319
ADIDAS | 0902906789-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 779 | 2026-05-09 | 779 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902906789 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-06-08 | 2026-01-09 | 779 | 779 |  |  |  | 2026-03-08 | 29/08/2026 | 25/07/2026 | 31/08/2026 | 779 | 779 |  |  |  | 30/07/2026 | 27/08/2026 | 22/07/2026 | 31/08/2026 | 779 | 779
ADIDAS | 0902907417-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907417 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 28/07/2026 | 2026-03-08 | 308 | 308 |  |  |  | 23/07/2026 | 30/07/2026 | 18/07/2026 | 24/07/2026 | 308 | 308 |  |  |  | 21/07/2026 | 28/07/2026 | 17/07/2026 | 24/07/2026 | 308 | 308
ADIDAS | 0902907437-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 332 | 15/09/2026 | 332 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902907437 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 28/07/2026 | 2026-04-08 | 29/07/2026 | 2026-03-08 | 332 | 332 |  |  |  | 23/07/2026 | 30/07/2026 | 21/07/2026 | 27/07/2026 | 332 | 332 |  |  |  | 21/07/2026 | 28/07/2026 | 20/07/2026 | 24/07/2026 | 332 | 332
ADIDAS | 0902907453-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 443 | 15/09/2026 | 443 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907453 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-07-09 | 15/09/2026 | 443 | 443 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 14/09/2026 | 443 | 443
ADIDAS | 0902907472-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 812 | 23/09/2026 | 812 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902907472 KX3651 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 812 | 812 |  |  |  | 21/07/2026 | 30/07/2026 | 17/07/2026 | 30/07/2026 | 812 | 812 |  |  |  | 17/07/2026 | 28/07/2026 | 17/07/2026 | 28/07/2026 | 812 | 812
ADIDAS | 0902907504-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 652 | 2026-05-09 | 652 | SA | SA15/05/2026 | G2J | T-SHIRT | G2 | ok | (08/06/2026) | 05/09: ex-fty (S4EU). 516443 | HT+PAD SUB PROCESS_V3 | 0902907504 KX3654 | 14/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-08 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-06-08 | 2026-01-09 | 2026-07-08 | 2026-01-09 | 652 | 652 |  |  |  | 2026-03-08 | 28/08/2026 | 25/07/2026 | 2026-05-08 | 652 | 652 |  |  |  | 30/07/2026 | 26/08/2026 | 23/07/2026 | 28/07/2026 | 652 | 652
ADIDAS | 0902907522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 648 | 2026-05-09 | 648 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907522 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/07/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/07/2026 | 2026-11-08 | 29/07/2026 | 2026-07-08 | 648 | 648 |  |  |  | 23/07/2026 | 2026-06-08 | 25/07/2026 | 2026-01-08 | 648 | 648 |  |  |  | 21/07/2026 | 2026-04-08 | 23/07/2026 | 28/07/2026 | 648 | 648
ADIDAS | 0902907548-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 671 | 2026-05-09 | 671 | SA | SA15/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 04/09: ex-fty 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902907548 KX3651 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/07/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 22/07/2026 | 30/07/2026 | 22/07/2026 | 29/07/2026 | 671 | 671 |  |  |  | 17/07/2026 | 27/07/2026 | 17/07/2026 | 22/07/2026 | 671 | 671 |  |  |  | 15/07/2026 | 23/07/2026 | 17/07/2026 | 28/07/2026 | 671 | 671
ADIDAS | 0902907571-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 308 | 15/09/2026 | 308 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902907571 KX3654 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 308 | 308 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-02-09 | 2026-12-09 | 308 | 308 |  |  |  | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-12-09 | 308 | 308
ADIDAS | 0902908709-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 684 | 23/09/2026 | 684 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 14-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902908709 LF0726 | 14/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 19/09/2026 | 2026-08-09 | 19/09/2026 | 684 | 684 |  |  | 7 | 2026-04-09 | 16/09/2026 | 28/08/2026 | 17/09/2026 | 684 | 684
ADIDAS | 0902908777-1 KA8777 | TEAM YELLOW/BLACK | 105D | S2606GHTM305M | 132 | 2026-08-09 | 132 | AT | AT15/05/2026 | G3E | SHORTS | G3 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. T2 Fu Hsun PI Date 12-Jun, actual receives 08-Jun. 800005 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0902908777 KA8777 | 14/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/07/2026 | TIRO26L SHO M |  | SS27-L2L | 30/07/2026 | 2026-07-08 | 31/07/2026 | 2026-05-08 | 132 | 132 |  |  |  | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-04-08 | 132 | 132 |  |  |  | 23/07/2026 | 31/07/2026 | 13/07/2026 | 13/07/2026 | 132 | 132
ADIDAS | 0902909669-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 30/09/2026 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Jun, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902909669 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 144 | 144 |  |  |  | 29/08/2026 | 2026-04-09 | 26/08/2026 | 16/09/2026 | 144 | 144
ADIDAS | 0902909771-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902909771 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 13/08/2026 | 14/08/2026 | 8 | 8 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 2026-05-08 | 8 | 8
ADIDAS | 0902909794-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G2S | SHORTS | G2 | ok | (04/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 03-Jul. T2 Libolon, PI Date 12-Jun, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jun, actual receives 28-May (PO NT-351). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902909794 LG9660 | 31/07/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/08/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 19/08/2026 | 24/08/2026 | 20/08/2026 | 21/08/2026 | 8 | 8 |  |  |  | 13/08/2026 | 19/08/2026 | 2026-11-08 | 18/08/2026 | 8 | 8
ADIDAS | 0902909815-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 8 | 2026-05-09 | 8 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902909815 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 27/08/2026 | 29/08/2026 | 14/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902910585-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 858 | 2026-05-09 | 858 | SA | SA15/05/2026 | G2G,G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902910585 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 858 | 858 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 2026-03-09 | 858 | 858 |  |  |  | 27/08/2026 | 31/08/2026 | 21/08/2026 | 2026-03-09 | 858 | 858
ADIDAS | 0902910626-1 KX3712 | LIME TINT S27 | 120D | S2608MR0906A | 420 | 2026-05-09 | 420 | SI | SI15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902910626 KX3712 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess LS M LIME TINT S27 |  | SS27-TI-SPOMA | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 420 | 420 |  |  |  | 27/07/2026 | 2026-11-08 | 17/07/2026 | 24/07/2026 | 420 | 420 |  |  |  | 23/07/2026 | 2026-07-08 | 17/07/2026 | 24/07/2026 | 420 | 420
ADIDAS | 0902911467-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1312 | 23/09/2026 | 1312 | SA | SA15/05/2026 | G2G,G2I,G2L | T-SHIRT | G2 | ok | (08/06/2026) | 21/09: ex-fty 834012 | HT+PAD SUB PROCESS_V3 | 0902911467 KF5311 | 14/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-03-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-03-08 | 2026-02-09 | 2026-03-08 | 2026-01-09 | 1312 | 1312 |  |  |  | 29/07/2026 | 29/08/2026 | 28/07/2026 | 2026-10-08 | 1312 | 1312 |  |  |  | 27/07/2026 | 27/08/2026 | 25/07/2026 | 2026-10-08 | 1312 | 1312
ADIDAS | 0902911942-1 KG3225 | KHAKI SIX F26 | 120D | S2608WR0900 | 15 | 2026-05-09 | 15 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902911942 KG3225 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | Run Ess Tee W KHAKI SIX F26 |  | SS27-TI-SPOMA | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 15 | 15 |  |  |  | 27/07/2026 | 30/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15 |  |  |  | 23/07/2026 | 28/07/2026 | 27/07/2026 | 27/07/2026 | 15 | 15
ADIDAS | 0902911985-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 351 | 2026-09-09 | 351 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902911985 LG9669 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | W SL WV SK BLACK |  | SS27 | 2026-02-09 | 2026-04-09 | 2026-02-09 | 2026-03-09 | 351 | 351 |  |  |  | 29/08/2026 | 2026-01-09 | 13/08/2026 | 2026-07-09 | 351 | 351
ADIDAS | 0902912004-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 652 | 2026-05-09 | 652 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912004 LF0726 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 20/08/2026 | 2026-10-08 | 19/08/2026 | 652 | 652 |  |  |  | 2026-04-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 652 | 652
ADIDAS | 0902912022-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 335 | 2026-05-09 | 335 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 680015 | PRINT L3+PPA SUB PROCESS_V3 | 0902912022 LG9669 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 335 | 335 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 20/08/2026 | 335 | 335
ADIDAS | 0902912038-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1761 | 2026-05-09 | 1761 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912038 LF0727 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 19/08/2026 | 1761 | 1761 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-04-08 | 19/08/2026 | 1761 | 1761
ADIDAS | 0902912063-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 339 | 2026-05-09 | 339 | AN | AN15/05/2026 | G1E | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912063 LF0729 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 18/08/2026 | 339 | 339 |  |  |  | 2026-03-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 339 | 339
ADIDAS | 0902912066-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 544 | 2026-05-09 | 544 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912066 LF0726 | 14/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-07-08 | 2026-12-08 | 544 | 544 |  |  |  | 2026-03-08 | 2026-10-08 | 31/07/2026 | 19/08/2026 | 544 | 544
ADIDAS | 0902912087-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 144 | 2026-05-09 | 144 | AN | AN15/05/2026 | G3B | SKIRT | G3 | ok | (05/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902912087 LG9669 | 14/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 144 | 144 |  |  |  | 27/08/2026 | 29/08/2026 | 13/08/2026 | 19/08/2026 | 144 | 144
ADIDAS | 0902912093-1 LG9669 | BLACK | 120D | S2754WAS514C | 789 | 2026-09-09 | 789 | ID | ID15/05/2026 | G3B | SKIRT | G3 | ok | (04/06/2026) | 09/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 30-Jun, actual receives 22-Jul (100% QC panel). 659018 | PRINT L3+PPA SUB PROCESS_V3 | 0902912093 LG9669 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/08/2026 | W SL WV SK BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 789 | 789 |  |  |  | 27/08/2026 | 2026-04-09 | 13/08/2026 | 2026-07-09 | 789 | 789
ADIDAS | 0902912125-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1399 | 2026-05-09 | 1399 | AN | AN15/05/2026 | G1D,G1E,G1N | JACKET | G1 | ok | (04/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902912125 LF0726 | 14/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 1399 | 1399 |  |  |  | 2026-04-08 | 2026-11-08 | 2026-05-08 | 19/08/2026 | 1399 | 1399
ADIDAS | 0902913684-1 KE8424 | BLACK | 60D | S2608MR0906A-MTF | 304 | 2026-05-09 | 304 | AN | AN15/05/2026 | G2G | T-SHIRT | G2 | ok | (05/06/2026) | 05/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902913684 KE8424 | 2026-02-07 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-09 | Run Ess LS M BLACK |  | FW26 | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 304 | 304 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 304 | 304 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 304 | 304
ADIDAS | 0902913763-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2000 | 2026-12-09 | 2000 | AT | AT15/05/2026 | G3D,G3K | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913763 JD1881 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-08 | M 3S FT TC PT |  | FW26 | 2026-03-08 | 14/08/2026 | 2026-03-08 | 2026-12-08 | 2000 | 2000 |  |  |  | 29/07/2026 | 2026-11-08 | 20/07/2026 | 2026-08-08 | 2000 | 2000
ADIDAS | 0902913788-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 720 | 2026-12-09 | 720 | AT | AT15/05/2026 | G3D | PANTS | G3 | ok | (08/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902913788 JE6346 | 31/07/2026 | KAHATEX CIJERAH | JAPAN | SEA | 24/07/2026 | M 3S FT TC PT |  | FW26 | 24/07/2026 | 29/07/2026 | 24/07/2026 | 29/07/2026 | 720 | 720 |  |  |  | 21/07/2026 | 24/07/2026 | 17/07/2026 | 22/07/2026 | 720 | 720
ADIDAS | 0902915780-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 60 | 19/09/2026 | 60 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902915780 LF0729 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-08-09 | 19/09/2026 | 2026-09-09 | 17/09/2026 | 60 | 60 |  |  |  | 2026-04-09 | 16/09/2026 | 21/08/2026 | 2026-01-09 | 60 | 60
ADIDAS | 0902915810-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 230 | 2026-05-09 | 230 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902915810 KX3713 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-09 | Run Ess LS M OLIVE TWO S27 |  | SS27-TI | 2026-02-09 | 2026-05-09 | 2026-04-09 | 2026-04-09 | 230 | 230 |  |  |  | 29/08/2026 | 2026-02-09 | 30/07/2026 | 2026-06-08 | 230 | 230 |  |  |  | 27/08/2026 | 31/08/2026 | 27/07/2026 | 2026-04-08 | 230 | 230
ADIDAS | 0902915970-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 105 | 2026-05-09 | 105 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 05/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902915970 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI-SPOMA | 24/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 21/07/2026 | 30/07/2026 | 22/07/2026 | 2026-03-08 | 105 | 105 |  |  |  | 17/07/2026 | 28/07/2026 | 21/07/2026 | 2026-03-08 | 105 | 105
ADIDAS | 0902916014-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 975 | 2026-05-09 | 975 | SA | SA15/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0902916014 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/07/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI-SPOMA | 21/07/2026 | 2026-04-08 | 22/07/2026 | 2026-04-08 | 975 | 975 |  |  |  | 16/07/2026 | 30/07/2026 | 15/07/2026 | 22/07/2026 | 975 | 975 |  |  |  | 14/07/2026 | 28/07/2026 | 15/07/2026 | 21/07/2026 | 975 | 975
ADIDAS | 0902916052-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 588 | 2026-05-09 | 588 | SI | SI15/05/2026 | G2G | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516029 | HT+PAD SUB PROCESS_V3 | 0902916052 LD0930 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI-SPOMA | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 588 | 588 |  |  |  | 29/08/2026 | 2026-02-09 | 29/08/2026 | 2026-04-09 | 588 | 588 |  |  |  | 27/08/2026 | 31/08/2026 | 28/08/2026 | 2026-04-09 | 588 | 588
ADIDAS | 0902917391-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 327 | 15/09/2026 | 327 | SA | SA15/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (08/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | HT+PAD SUB PROCESS_V3 | 0902917391 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 327 | 327 |  |  |  | 2026-03-08 | 29/08/2026 | 30/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 30/07/2026 | 27/08/2026 | 29/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902917424-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 673 | 2026-05-09 | 673 | SA | SA15/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | ok | 04/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902917424 KF5311 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/07/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 24/07/2026 | 2026-11-08 | 24/07/2026 | 2026-06-08 | 673 | 673 |  |  |  | 21/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 673 | 673 |  |  |  | 17/07/2026 | 2026-04-08 | 21/07/2026 | 2026-04-08 | 673 | 673
ADIDAS | 0902919030-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 5346 | 30/09/2026 | 5346 | AN | AN15/05/2026 | G3A,G3B,G3F,G3H | PANTS | G3 | ok | (13/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902919030 KZ3200 | 31/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 14/08/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 23/09/2026 | 14/08/2026 | 17/09/2026 | 5346 | 5266 | 80 |  |  | 2026-11-08 | 19/09/2026 | 2026-06-08 | 17/09/2026 | 5346 | 5329 | 17
ADIDAS | 0902926321-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 321 | 2026-05-09 | 321 | AN | AN15/05/2026 | G1N | JACKET | G1 | ok | ok | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 13-Jul, actual receives 25-May (PO NT-354). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926321 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-11-08 | 321 | 321 |  |  |  | 2026-03-08 | 2026-10-08 | 30/07/2026 | 19/08/2026 | 321 | 321
ADIDAS | 0902926382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 200 | 30/09/2026 | 200 | AN | AN15/05/2026 | G1D | JACKET | G1 | ok | (04/06/2026) | 23/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jun (PO NT-354). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902926382 LF0726 | 14/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 27/08/2026 | 2026-08-09 | 29/08/2026 | 2026-07-09 | 200 | 200 |  |  |  | 21/08/2026 | 2026-04-09 | 26/08/2026 | 2026-09-09 | 200 | 200
ADIDAS | 0902930259-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 324 | 2026-07-10 | 324 | SA | SA21/05/2026 | G2L | T-SHIRT | G2 | ok | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0902930259 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 324 |  | 324 |  |  | 24/09/2026 | 25/09/2026 | 14/08/2026 | 2026-08-09 | 324 | 298 | 26 |  |  | 22/09/2026 | 23/09/2026 | 13/08/2026 | 2026-08-09 | 324 | 297 | 27
ADIDAS | 0902931102-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 319 | 23/10/2026 | 319 | SA | SA21/05/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902931102 LD0285 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-12-10 | 2026-12-10 |  |  | 319 |  | 319 |  |  | 2026-08-10 | 2026-08-10 | 2026-03-08 | 2026-07-08 | 319 | 319 |  |  |  | 2026-06-10 | 2026-06-10 | 2026-03-08 | 2026-05-08 | 319 | 319
ADIDAS | 0902940286-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 30 | 23/09/2026 | 30 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940286 LE0357 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 2026-09-09 | 21/09/2026 | 15/09/2026 | 16/09/2026 | 30 | 21 | 9 |  |  | 2026-05-09 | 17/09/2026 | 26/08/2026 | 2026-04-09 | 30 | 21 | 9
ADIDAS | 0902940338-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 499 | 15/10/2026 | 499 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 31-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902940338 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 499 |  | 499 |  |  | 2026-07-10 | 2026-08-10 |  |  | 499 |  | 499
ADIDAS | 0902941400-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 4800 | 30/09/2026 | 4800 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 600000 | EMBRO SUB PROCESS_V1 | 0902941400 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 4800 |  | 4800 |  |  | 2026-05-10 | 2026-09-10 | 17/09/2026 | 19/09/2026 | 4800 | 3845 | 955 |  | 770
ADIDAS | 0902941469-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 3000 | 30/09/2026 | 3000 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 600000 | EMBRO SUB PROCESS_V1 | 0902941469 KS7770 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W CO BOXY TEE BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 3000 |  | 3000 |  |  | 2026-02-10 | 2026-05-10 |  |  | 3000 |  | 3000
ADIDAS | 0902942438-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 360 | 19/09/2026 | 360 | SI | SI29/05/2026 | G1O | SHORTS | G1 | ok | (22/06/2026) | 18/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942438 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 17/09/2026 | 15/09/2026 | 17/09/2026 | 360 | 360 |  |  |  | 2026-09-09 | 14/09/2026 | 2026-10-09 | 17/09/2026 | 360 | 360
ADIDAS | 0902942448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 05/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942448 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 29/08/2026 | 18/08/2026 | 28/08/2026 | 450 | 450 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-10-08 | 2026-04-09 | 450 | 450
ADIDAS | 0902942463-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 465 | 2026-09-09 | 465 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516419 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902942463 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | M 3S CHELSEA B7 |  | FW26 | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-07-09 | 465 | 465 |  |  |  | 2026-11-08 | 2026-03-09 | 2026-11-08 | 2026-07-09 | 465 | 465
ADIDAS | 0902942481-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5600 | 15/09/2026 | 5600 | SI | SI29/05/2026 | G3C,G3E | SHORTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942481 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | M 3S CHELSEA B7 |  | FW26 | 2026-07-09 | 15/09/2026 | 2026-04-09 | 14/09/2026 | 5600 | 5600 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-03-09 | 18/09/2026 | 5600 | 5604 | -4 | 4
ADIDAS | 0902942491-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942491 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-11-09 | 315 | 315
ADIDAS | 0902942496-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-05-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942496 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 27/08/2026 | 2026-03-09 | 315 | 315 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-02-09 | 315 | 315
ADIDAS | 0902942511-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942511 KY6510 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-04-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 400 | 400
ADIDAS | 0902942519-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 390 | 19/09/2026 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 18/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942519 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | M 3S CHELSEA B7 |  | FW26 | 2026-12-09 | 18/09/2026 | 15/09/2026 | 16/09/2026 | 390 | 390 |  |  |  | 2026-09-09 | 15/09/2026 | 2026-10-09 | 16/09/2026 | 390 | 390
ADIDAS | 0902942533-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 2026-09-09 | 900 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902942533 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-07-09 | 900 | 900 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-05-09 | 900 | 900
ADIDAS | 0902945010-1 LE8187 | BLACK | 105D | S2754MAS513 | 331 | 26/09/2026 | 331 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945010 LE8187 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 21/09/2026 | 2026-08-09 | 2026-09-09 | 331 | 286 | 45 |  |  | 2026-02-09 | 17/09/2026 | 27/08/2026 | 2026-04-09 | 331 | 292 | 39
ADIDAS | 0902945087-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 401 | 30/09/2026 | 401 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945087 LE8188 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 401 |  | 401 |  |  | 19/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 401 | 225 | 176 |  | 4
ADIDAS | 0902945143-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902945143 LE8186 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902946696-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 856 | 30/09/2026 | 856 | SI | SI29/05/2026 | G2A | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946696 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 856 |  | 856 |  |  | 16/09/2026 | 17/09/2026 | 20/08/2026 | 18/09/2026 | 856 | 856
ADIDAS | 0902946844-1 KX0127 | OFF WHITE | 90D | S27SPRMGFXP0900 | 357 | 30/09/2026 | 357 | SI | SI29/05/2026 | G2A | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0902946844 KX0127 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | M TATTOO SPRT T OFF WHITE |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 357 |  | 357 |  |  | 16/09/2026 | 17/09/2026 | 2026-01-08 | 18/09/2026 | 357 | 357
ADIDAS | 0902946950-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 400 | 2026-12-09 | 400 | SI | SI29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902946950 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/08/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 29/08/2026 | 2026-12-09 | 31/08/2026 | 2026-11-09 | 400 | 400 |  |  |  | 26/08/2026 | 2026-09-09 | 2026-05-08 | 2026-11-09 | 400 | 400
ADIDAS | 0902947050-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1120 | 15/10/2026 | 1120 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902947050 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 1120 |  | 1120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 1120 |  | 1120
ADIDAS | 0902948698-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 561 | 2026-07-10 | 561 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948698 LG9668 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 561 |  | 561 |  |  | 2026-02-10 | 2026-05-10 |  |  | 561 |  | 561
ADIDAS | 0902948720-1 LG9669 | BLACK | 120D | S2754WAS514C | 283 | 30/09/2026 | 283 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902948720 LG9669 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV SK BLACK |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 283 | 246 | 37 |  | 3 | 15/09/2026 | 19/09/2026 | 24/08/2026 | 2026-05-09 | 283 | 240 | 43
ADIDAS | 0902948739-1 LG9669 | BLACK | 120D | S2754WAS514C | 316 | 30/09/2026 | 316 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948739 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 316 | 213 | 103 |  | 213 | 21/09/2026 | 22/09/2026 | 28/08/2026 | 2026-05-09 | 316 | 307 | 9
ADIDAS | 0902948754-1 LG9669 | BLACK | 120D | S2754WAS514C | 416 | 2026-07-10 | 416 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948754 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | W SL WV SK BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 416 |  | 416 |  |  | 2026-02-10 | 2026-05-10 |  |  | 416 |  | 416
ADIDAS | 0902948775-1 LG9669 | BLACK | 120D | S2754WAS514C | 497 | 30/09/2026 | 497 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902948775 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV SK BLACK |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 497 | 434 | 63 |  | 127 | 15/09/2026 | 19/09/2026 | 26/08/2026 | 18/09/2026 | 497 | 461 | 36
ADIDAS | 0902949162-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 377 | 23/09/2026 | 377 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949162 LF0725 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-09-09 | 22/09/2026 | 2026-10-09 | 2026-12-09 | 377 | 372 | 5 |  |  | 2026-05-09 | 18/09/2026 | 2026-07-09 | 16/09/2026 | 377 | 377
ADIDAS | 0902949302-1 LF0723 | BLACK | 105D | S2754MAS511B | 402 | 30/09/2026 | 402 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902949302 LF0723 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | M SL WV SHO BLACK |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 402 |  | 402 |  |  | 21/09/2026 | 22/09/2026 |  |  | 402 |  | 402
ADIDAS | 0902951279-1 LH3758 | BLACK | 120D | S2754WAS518B | 500 | 15/10/2026 | 500 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951279 LH3758 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | W SL WV BR PT BLACK |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 500 |  | 500
ADIDAS | 0902951331-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 500 | 30/09/2026 | 500 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951331 LD5446 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 22/09/2026 |  |  | 500 |  | 500
ADIDAS | 0902951389-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 302 | 31/10/2026 | 302 | SA | SA29/05/2026 | G1H | JACKET | G1 | ok | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951389 LG9664 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 302 |  | 302 |  |  | 2026-02-11 | 2026-04-11 |  |  | 302 |  | 302
ADIDAS | 0902951506-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 304 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902951506 LG9673 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902951560-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 302 | 15/10/2026 | 302 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951560 LG9665 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 302 |  | 302 |  |  | 26/09/2026 | 29/09/2026 |  |  | 302 |  | 302
ADIDAS | 0902951622-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 498 | 15/10/2026 | 498 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 1st Art (TC 10 pcs) 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902951622 LG9661 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 498 |  | 498 |  |  | 2026-01-10 | 2026-03-10 |  |  | 498 |  | 498
ADIDAS | 0902952685-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 498 | 31/10/2026 | 498 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 31-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902952685 LG9666 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-11 | W SL WV TT BLACK |  | SS27 | 2026-10-11 | 13/11/2026 |  |  | 498 |  | 498 |  |  | 2026-05-11 | 2026-10-11 |  |  | 498 |  | 498
ADIDAS | 0902953067-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 327 | 2026-07-10 | 327 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902953067 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 327 |  | 327 |  |  | 26/09/2026 | 28/09/2026 |  |  | 327 |  | 327
ADIDAS | 0902953315-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 307 | 23/09/2026 | 307 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953315 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 14/08/2026 | 2026-01-09 | 307 | 307 |  |  |  | 2026-11-08 | 29/08/2026 | 28/07/2026 | 2026-11-08 | 307 | 307 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 28/07/2026 | 307 | 307
ADIDAS | 0902953364-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 472 | 23/09/2026 | 472 | SA | SA29/05/2026 | G2H,G2L | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953364 LD0288 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 30/07/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 21/08/2026 | 31/07/2026 | 20/08/2026 | 472 | 472 |  |  |  | 27/07/2026 | 18/08/2026 | 25/07/2026 | 30/07/2026 | 472 | 472 |  |  |  | 23/07/2026 | 13/08/2026 | 24/07/2026 | 29/07/2026 | 472 | 472
ADIDAS | 0902953400-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 312 | 19/09/2026 | 312 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 18/09: ex-fty 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902953400 KY5988 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 312 | 312 |  |  |  | 27/07/2026 | 2026-11-08 | 30/07/2026 | 2026-08-08 | 312 | 312 |  |  |  | 20/07/2026 | 2026-04-08 | 30/07/2026 | 2026-06-08 | 312 | 312
ADIDAS | 0902953446-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 542 | 19/09/2026 | 542 | SA | SA29/05/2026 | G2H,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953446 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-11-08 | 542 | 542 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 31/07/2026 | 542 | 542 |  |  |  | 28/07/2026 | 2026-04-08 | 24/07/2026 | 30/07/2026 | 542 | 542
ADIDAS | 0902953533-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 327 | 23/09/2026 | 327 | SA | SA29/05/2026 | G2M,G2O | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902953533 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 15/09/2026 | 19/09/2026 | 16/09/2026 | 18/09/2026 | 327 | 327 |  |  |  | 2026-11-09 | 16/09/2026 | 27/07/2026 | 2026-04-08 | 327 | 327 |  |  |  | 2026-09-09 | 14/09/2026 | 25/07/2026 | 2026-04-08 | 327 | 327
ADIDAS | 0902953571-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 479 | 23/09/2026 | 479 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 23/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902953571 KX3651 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 18/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 479 | 469 | 10 |  | 15 | 15/09/2026 | 16/09/2026 | 31/07/2026 | 2026-08-08 | 479 | 479 |  |  |  | 2026-12-09 | 14/09/2026 | 30/07/2026 | 2026-07-08 | 479 | 479
ADIDAS | 0902954045-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 313 | 30/09/2026 | 313 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954045 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 313 |  | 313 |  |  | 25/09/2026 | 26/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902954088-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 246 | 23/09/2026 | 246 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954088 LG9661 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-08-09 | 18/09/2026 | 2026-11-09 | 15/09/2026 | 246 | 246 |  |  |  | 2026-04-09 | 15/09/2026 | 28/08/2026 | 16/09/2026 | 246 | 243 | 3
ADIDAS | 0902954666-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 2026-07-10 | 200 | SA | SA29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954666 LE8181 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 200 |  | 200 |  |  | 2026-01-10 | 2026-02-10 |  |  | 200 |  | 200
ADIDAS | 0902954719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 162 | 15/09/2026 | 162 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954719 LE8186 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT OLIVE ONE S27 |  | SS27 | 14/09/2026 | 15/09/2026 | 14/09/2026 | 16/09/2026 | 162 | 162 |  |  |  | 2026-10-09 | 2026-11-09 | 2026-11-09 | 15/09/2026 | 162 | 162
ADIDAS | 0902954826-1 LE8187 | BLACK | 105D | S2754MAS513 | 152 | 15/09/2026 | 152 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954826 LE8187 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 15/09/2026 | 15/09/2026 | 16/09/2026 | 152 | 152 |  |  |  | 2026-10-09 | 2026-11-09 | 15/09/2026 | 15/09/2026 | 152 | 152
ADIDAS | 0902954882-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 174 | 15/09/2026 | 174 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954882 LE8188 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 14/09/2026 | 15/09/2026 | 14/09/2026 | 16/09/2026 | 174 | 174 |  |  |  | 2026-10-09 | 2026-11-09 | 2026-11-09 | 15/09/2026 | 174 | 174
ADIDAS | 0902954999-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 609 | 2026-07-10 | 609 | SI | SI29/05/2026 | G1K | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954999 LF0726 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 609 |  | 609 |  |  | 30/09/2026 | 2026-02-10 |  |  | 609 |  | 609
ADIDAS | 0902955058-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 206 | 23/09/2026 | 206 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955058 LF0727 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 206 | 206 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-07-08 | 31/08/2026 | 206 | 206
ADIDAS | 0902955123-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 356 | 23/09/2026 | 356 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 22/09: ex-fty (S4EU). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955123 LF0726 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 19/09/2026 | 2026-04-09 | 18/09/2026 | 356 | 356 |  |  |  | 2026-01-09 | 16/09/2026 | 27/08/2026 | 16/09/2026 | 356 | 356
ADIDAS | 0902955656-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 590 | 23/09/2026 | 590 | SA | SA29/05/2026 | G2J | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955656 KX3655 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 23/09/2026 | 15/09/2026 | 18/09/2026 | 590 | 540 | 50 |  |  | 2026-11-09 | 19/09/2026 | 2026-07-09 | 17/09/2026 | 590 | 582 | 8 |  |  | 2026-09-09 | 17/09/2026 | 2026-07-09 | 16/09/2026 | 590 | 581 | 9
ADIDAS | 0902955699-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 441 | 23/09/2026 | 441 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 516342 | HT+PAD SUB PROCESS_V3 | 0902955699 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-11-09 | 18/09/2026 | 14/09/2026 | 18/09/2026 | 441 | 441 |  |  |  | 2026-08-09 | 15/09/2026 | 2026-10-08 | 26/08/2026 | 441 | 441 |  |  |  | 2026-05-09 | 2026-12-09 | 2026-10-08 | 24/08/2026 | 441 | 441
ADIDAS | 0902955746-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 324 | 30/09/2026 | 324 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516443 | HT+PAD SUB PROCESS_V3 | 0902955746 KX3654 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-09 | 19/09/2026 | 2026-07-09 | 17/09/2026 | 324 | 290 | 34 |  |  | 2026-04-09 | 16/09/2026 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1 |  |  | 2026-02-09 | 14/09/2026 | 26/08/2026 | 2026-02-09 | 324 | 323 | 1
ADIDAS | 0902955843-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 30/09/2026 | 301 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955843 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M SL WV SHO BLACK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 18/09/2026 | 18/09/2026 | 2026-10-09 | 19/09/2026 | 301 | 231 | 70 |  | 111
ADIDAS | 0902955890-1 LF0723 | BLACK | 105D | S2754MAS511B | 137 | 2026-09-09 | 137 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955890 LF0723 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | M SL WV SHO BLACK |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 137 | 137 |  |  |  | 29/08/2026 | 2026-03-09 | 18/08/2026 | 28/08/2026 | 137 | 137
ADIDAS | 0902955942-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 417 | 2026-07-10 | 417 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955942 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 417 |  | 417 |  |  | 2026-05-10 | 2026-06-10 |  |  | 417 |  | 417
ADIDAS | 0902955987-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 322 | 22/09/2026 | 322 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 18/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902955987 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 322 | 322 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-05-09 | 14/09/2026 | 322 | 322
ADIDAS | 0902956072-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 187 | 2026-05-09 | 187 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956072 LD5446 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-02-09 | 187 | 187 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 187 | 187
ADIDAS | 0902956169-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 302 | 23/09/2026 | 302 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956169 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | M SL WV TT BLACK |  | SS27 | 2026-08-09 | 19/09/2026 | 2026-08-09 | 18/09/2026 | 302 | 302 |  |  |  | 2026-04-09 | 16/09/2026 | 2026-06-08 | 17/09/2026 | 302 | 302
ADIDAS | 0902956226-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 645 | 2026-07-10 | 645 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956226 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | M SL WV TT BLACK |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 645 |  | 645 |  |  | 2026-02-10 | 2026-06-10 |  |  | 645 |  | 645
ADIDAS | 0902956293-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 203 | 23/09/2026 | 203 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956293 LF0729 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 18/08/2026 | 31/08/2026 | 203 | 203 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-12-08 | 31/08/2026 | 203 | 202 | 1
ADIDAS | 0902956352-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 177 | 15/09/2026 | 177 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956352 LF0726 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-11-09 | 2026-04-09 | 14/09/2026 | 177 | 177 |  |  |  | 27/08/2026 | 2026-08-09 | 13/08/2026 | 14/09/2026 | 177 | 177
ADIDAS | 0902956415-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 605 | 30/09/2026 | 605 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956415 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 605 |  | 605 |  |  | 23/09/2026 | 25/09/2026 | 2026-04-09 | 2026-11-09 | 605 | 216 | 389
ADIDAS | 0902956471-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 305 | 2026-07-10 | 305 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956471 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 305 |  | 305 |  |  | 26/09/2026 | 28/09/2026 |  |  | 305 |  | 305
ADIDAS | 0902956678-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 599 | 23/09/2026 | 599 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956678 LG9661 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-01-09 | 22/09/2026 | 2026-05-09 | 17/09/2026 | 599 | 554 | 45 |  |  | 28/08/2026 | 18/09/2026 | 26/08/2026 | 15/09/2026 | 599 | 596 | 3
ADIDAS | 0902956729-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 438 | 30/09/2026 | 438 | SA | SA29/05/2026 | G1C | JACKET | G1 | ok | (24/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956729 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 438 |  | 438 |  |  | 26/09/2026 | 29/09/2026 |  |  | 438 |  | 438
ADIDAS | 0902956767-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 133 | 26/09/2026 | 133 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956767 LG9664 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 133 |  | 133 |  |  | 18/09/2026 | 21/09/2026 | 2026-10-09 | 2026-10-09 | 133 | 109 | 24
ADIDAS | 0902956798-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 310 | 23/09/2026 | 310 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956798 LG9665 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 22/09/2026 | 17/09/2026 | 18/09/2026 | 310 | 162 | 148 |  |  | 15/09/2026 | 18/09/2026 | 2026-01-09 | 18/09/2026 | 310 | 279 | 31
ADIDAS | 0902956842-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 710 | 30/09/2026 | 710 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956842 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W SL WV TT BLACK |  | SS27 | 15/09/2026 | 22/09/2026 | 15/09/2026 | 19/09/2026 | 710 | 537 | 173 |  | 6 | 2026-11-09 | 18/09/2026 | 29/08/2026 | 18/09/2026 | 710 | 601 | 109
ADIDAS | 0902956889-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 599 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902956889 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956973-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 139 | 30/09/2026 | 139 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956973 LG9666 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 22/09/2026 | 16/09/2026 | 19/09/2026 | 139 | 111 | 28 |  | 10 | 15/09/2026 | 18/09/2026 | 31/08/2026 | 2026-04-09 | 139 | 138 | 1
ADIDAS | 0902957021-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 495 | 2026-07-10 | 495 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957021 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 495 |  | 495 |  |  | 28/09/2026 | 30/09/2026 |  |  | 495 |  | 495
ADIDAS | 0902957107-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 334 | 2026-07-10 | 334 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957107 LG9673 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 334 |  | 334 |  |  | 26/09/2026 | 28/09/2026 | 16/09/2026 | 19/09/2026 | 334 | 257 | 77 |  | 14
ADIDAS | 0902957145-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 300 | 30/09/2026 | 300 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957145 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959184-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 201 | 30/09/2026 | 201 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959184 LG9673 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 201 |  | 201 |  |  | 21/09/2026 | 22/09/2026 | 15/09/2026 | 16/09/2026 | 201 | 118 | 83
ADIDAS | 0902959230-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 428 | 2026-07-10 | 428 | SI | SI29/05/2026 | G3G | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959230 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W SL WV PT KHAKI THREE F26 |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 428 |  | 428 |  |  | 28/09/2026 | 30/09/2026 |  |  | 428 |  | 428
ADIDAS | 0902959276-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 205 | 30/09/2026 | 205 | AN | AN29/05/2026 | G3D | PANTS | G3 | ok | (27/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959276 LG9675 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W SL WV PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 205 |  | 205 |  |  | 22/09/2026 | 23/09/2026 |  |  | 205 |  | 205
ADIDAS | 0902959319-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G3D | PANTS | G3 | ok | (27/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 20-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959319 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W SL WV PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902959364-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 308 | 2026-07-10 | 308 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (27/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959364 LG9675 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | W SL WV PT BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 308 |  | 308 |  |  | 26/09/2026 | 28/09/2026 |  |  | 308 |  | 308
ADIDAS | 0902959405-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 356 | 2026-09-09 | 356 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959405 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-02-09 | 356 | 356 |  |  |  | 20/08/2026 | 31/08/2026 | 2026-12-08 | 2026-07-09 | 356 | 356
ADIDAS | 0902959452-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1380 | 30/09/2026 | 1380 | SI | SI29/05/2026 | G3C | SHORTS | G3 | (12/07/2026) | ok | Waiting fabric. DRC 0002-T2 Gistex, material delayed, PI Date 12-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959452 KY4155 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 21/09/2026 | 23/09/2026 |  |  | 1380 |  | 1380 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0902959473-1 LH3758 | BLACK | 120D | S2754WAS518B | 182 | 30/09/2026 | 182 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959473 LH3758 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W SL WV BR PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 182 |  | 182 |  |  | 22/09/2026 | 23/09/2026 |  |  | 182 |  | 182
ADIDAS | 0902959508-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 3010 | 23/09/2026 | 3010 | SI | SI29/05/2026 | G3C,G3E | SHORTS | G3 | ok | ok | 22/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959508 KY6510 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | M 3S CHELSEA B7 |  | FW26 | 15/09/2026 | 22/09/2026 | 15/09/2026 | 17/09/2026 | 3010 | 2455 | 555 |  |  | 2026-11-09 | 18/09/2026 | 2026-10-09 | 18/09/2026 | 3010 | 2967 | 43
ADIDAS | 0902959557-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 419 | 2026-09-09 | 419 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | ok | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959557 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 |  | FW26 | 29/08/2026 | 2026-07-09 | 29/08/2026 | 2026-07-09 | 419 | 419 |  |  |  | 26/08/2026 | 2026-03-09 | 13/08/2026 | 2026-07-09 | 419 | 419
ADIDAS | 0902959562-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 134 | 30/09/2026 | 134 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902959562 LH3761 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 134 |  | 134 |  |  | 25/09/2026 | 26/09/2026 |  |  | 134 |  | 134
ADIDAS | 0902959597-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 799 | 19/09/2026 | 799 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | ok | 18/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902959597 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-11-09 | M 3S CHELSEA B7 |  | FW26 | 2026-11-09 | 18/09/2026 | 15/09/2026 | 18/09/2026 | 799 | 799 |  |  |  | 2026-08-09 | 15/09/2026 | 2026-10-09 | 17/09/2026 | 799 | 799
ADIDAS | 0902959610-1 LH3758 | BLACK | 120D | S2754WAS518B | 640 | 2026-07-10 | 640 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959610 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W SL WV BR PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 640 |  | 640 |  |  | 22/09/2026 | 23/09/2026 |  |  | 640 |  | 640
ADIDAS | 0902959964-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516461 | HT+PAD SUB PROCESS_V3 | 0902959964 KX3654 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 300 | 300 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-10-08 | 15/08/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-10-08 | 14/08/2026 | 300 | 300
ADIDAS | 0902960005-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902960005 KX3655 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-06-10 | 2026-06-10 |  |  | 320 |  | 320 |  |  | 2026-02-10 | 2026-02-10 |  |  | 320 |  | 320 |  |  | 30/09/2026 | 30/09/2026 |  |  | 320 |  | 320
ADIDAS | 0902960049-1 LF0723 | BLACK | 105D | S2754MAS511B | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902960049 LF0723 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV SHO BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 420 |  | 420 |  |  | 2026-06-10 | 2026-08-10 |  |  | 420 |  | 420
ADIDAS | 0902960084-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 2026-03-09 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Kahatex, PI Date 28-Jun, actual receives 18-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960084 LE4307 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 29/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-04-08 | 2026-12-08 | 300 | 300
ADIDAS | 0902960126-1 JZ7808 | BLACK | 120D | S2608WR0900 | 313 | 2026-07-10 | 313 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902960126 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 313 |  | 313 |  |  | 24/09/2026 | 24/09/2026 | 2026-07-08 | 15/08/2026 | 313 | 312 | 1 |  |  | 22/09/2026 | 22/09/2026 | 2026-07-08 | 14/08/2026 | 313 | 313
ADIDAS | 0902960651-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 480 | 2026-05-09 | 480 | SI | SI29/05/2026 | G3A,G3C | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960651 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 480 | 480 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-04-08 | 13/08/2026 | 480 | 480
ADIDAS | 0902960711-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 500 | 30/09/2026 | 500 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960711 LH4535 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 21/09/2026 | 2026-10-09 | 17/09/2026 | 500 | 497 | 3 |  |  | 2026-05-09 | 17/09/2026 | 13/08/2026 | 18/09/2026 | 500 | 500
ADIDAS | 0902960763-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 244 | 30/09/2026 | 244 | SA | SA29/05/2026 | G3J | SHORTS | G3 | ok | (25/06/2026) | DRC 0090-early shipment customer (Kahatex IPF). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960763 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-09-09 | 21/09/2026 | 2026-10-09 | 2026-11-09 | 244 | 238 | 6 |  |  | 2026-05-09 | 17/09/2026 | 15/08/2026 | 16/09/2026 | 244 | 244
ADIDAS | 0902961677-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 309 | 2026-07-10 | 309 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961677 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 309 |  | 309 |  |  | 22/09/2026 | 23/09/2026 |  |  | 309 |  | 309
ADIDAS | 0902961728-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 887 | 30/09/2026 | 887 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0902961728 LH3759 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 887 |  | 887 |  |  | 24/09/2026 | 25/09/2026 |  |  | 887 |  | 887
ADIDAS | 0902961768-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 313 | 30/09/2026 | 313 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961768 LH3759 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 313 |  | 313 |  |  | 24/09/2026 | 25/09/2026 |  |  | 313 |  | 313
ADIDAS | 0902961819-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 341 | 2026-07-10 | 341 | SI | SI29/05/2026 | G3I | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902961819 LH3761 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 341 |  | 341 |  |  | 22/09/2026 | 23/09/2026 |  |  | 341 |  | 341
ADIDAS | 0902961860-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 592 | 31/10/2026 | 592 | SA | SA29/05/2026 | G2Q | T-SHIRT | G2 | ok | (22/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902961860 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 21/10/2026 | 21/10/2026 |  |  | 592 |  | 592 |  |  | 17/10/2026 | 17/10/2026 | 18/09/2026 | 18/09/2026 | 592 | 416 | 176 |  |  | 15/10/2026 | 15/10/2026 | 18/09/2026 | 18/09/2026 | 592 | 416 | 176
ADIDAS | 0902961984-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 427 | 23/10/2026 | 427 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902961984 LD0287 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 13/10/2026 | 13/10/2026 |  |  | 427 |  | 427 |  |  | 2026-09-10 | 2026-09-10 |  |  | 427 |  | 427 |  |  | 2026-07-10 | 2026-07-10 |  |  | 427 |  | 427
ADIDAS | 0902962301-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 500 | 2026-03-09 | 500 | AN | AN29/05/2026 | G3J | SHORTS | G3 | ok | (27/06/2026) | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Formosa, PI date 09-Jun, actual receives 23-Jun. T2 Libolon, PI Date 09-Jun, actual receives 09-Jun. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962301 KV7963 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-04-08 | 27/07/2026 | 2026-03-08 | 500 | 500 |  |  |  | 22/07/2026 | 30/07/2026 | 23/07/2026 | 2026-05-08 | 500 | 500
ADIDAS | 0902962328-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 27-Jun. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902962328 KV8005 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 15/09/2026 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 15/09/2026 | 300 | 300
ADIDAS | 0902962445-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 400 | 2026-09-09 | 400 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516240 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962445 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-08-09 | 400 | 400 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-02-09 | 2026-08-09 | 400 | 400
ADIDAS | 0902962469-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962469 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-02-09 | 315 | 315 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-02-09 | 315 | 315
ADIDAS | 0902962488-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 390 | 2026-09-09 | 390 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 09/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962488 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-07-09 | 2026-08-09 | 390 | 390 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-03-09 | 2026-09-09 | 390 | 390
ADIDAS | 0902962541-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 24-Jul. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962541 KY4155 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/08/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 29/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 330 | 330 |  |  |  | 26/08/2026 | 27/08/2026 | 2026-12-08 | 2026-08-09 | 330 | 330
ADIDAS | 0902962571-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 2026-12-09 | 330 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 10-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. T2 Formosa, using fabric stock. 516241 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962571 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-08-09 | 330 | 330 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-09-09 | 330 | 330
ADIDAS | 0902962600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 2026-05-09 | 450 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_19_06_2026 EARLY HOLD SHIPMENT). T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962600 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/08/2026 | M 3S CHELSEA B7 |  | FW26 | 26/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 450 | 450 |  |  |  | 20/08/2026 | 31/08/2026 | 18/08/2026 | 2026-04-09 | 450 | 450
ADIDAS | 0902962624-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 3000 | 2026-12-09 | 3000 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 27-Aug. T2 Formosa, using fabric stock. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516199 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962624 KY4155 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | FW26 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-11-09 | 3000 | 3000 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-11-09 | 3000 | 3000
ADIDAS | 0902962644-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 2026-09-09 | 315 | SI | SI29/05/2026 | G3C | SHORTS | G3 | ok | (22/06/2026) | 07/09: ex-fty. T2 Gistex, PI Date 12-Jul, actual receives 28-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 13-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902962644 KY6510 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | M 3S CHELSEA B7 |  | FW26 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-02-09 | 315 | 315 |  |  |  | 27/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 315 | 315
ADIDAS | 0902966036-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 65 | 23/09/2026 | 65 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966036 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 14/09/2026 | 65 | 65
ADIDAS | 0902966052-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 27 | 23/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966052 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT KHAKI THREE F26 |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 18/09/2026 | 2026-11-09 | 18/09/2026 | 27 | 22 | 5
ADIDAS | 0902966064-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966064 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT BLACK |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-08-09 | 65 | 65 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-04-09 | 65 | 65
ADIDAS | 0902966089-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966089 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-08-09 | 2026-10-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 2026-10-09 | 22 | 22 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-05-09 | 2026-10-09 | 22 | 22
ADIDAS | 0902966098-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902966098 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 65 | 65 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-02-09 | 15/09/2026 | 65 | 65
ADIDAS | 0902966111-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 27 | 30/09/2026 | 27 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902966111 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 27 |  | 27 |  |  | 21/09/2026 | 22/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902966123-1 KY5991 | PURE BLUE S27/WHITE | 105D | S2650MTR437 | 22 | 15/09/2026 | 22 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 20-Aug. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902966123 KY5991 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | WE ALLSET 35SSHO PURE BLUE S27/WHITE |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 22 | 22 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 2026-07-09 | 22 | 22 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-05-09 | 2026-05-09 | 22 | 22
ADIDAS | 0902970651-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 992 | 15/09/2026 | 992 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. T2 Kahatex, PI Date 06-Aug, actual receives 25-Jun. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902970651 KA2571 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-08-09 | 2026-12-09 | 992 | 992 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-07-09 | 2026-11-09 | 992 | 992 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-07-09 | 2026-10-09 | 992 | 992
ADIDAS | 0902970663-1 LG9669 | BLACK | 120D | S2754WAS514C | 27 | 30/09/2026 | 27 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970663 LG9669 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 27 | 26 | 1 |  | 26 | 21/09/2026 | 22/09/2026 | 29/08/2026 | 2026-01-09 | 27 | 17 | 10
ADIDAS | 0902970676-1 LE0355 | BLACK | 105D | S2754MAS514 | 65 | 30/09/2026 | 65 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970676 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | M SL WV CU PT BLACK |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 16/09/2026 | 65 | 52 | 13 |  |  | 2026-11-09 | 17/09/2026 | 2026-01-09 | 15/09/2026 | 65 | 62 | 3
ADIDAS | 0902970685-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 65 | 23/09/2026 | 65 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970685 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 65 | 65 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-07-09 | 2026-08-09 | 65 | 65
ADIDAS | 0902970699-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 27 | 23/09/2026 | 27 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970699 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 22/09/2026 |  |  | 27 |  | 27 |  |  | 15/09/2026 | 18/09/2026 | 2026-11-09 | 16/09/2026 | 27 | 24 | 3
ADIDAS | 0902970711-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 27 | 30/09/2026 | 27 | AN | AN29/05/2026 | G3D | PANTS | G3 | ok | ok | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970711 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | W SL WV PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 27 |  | 27 |  |  | 22/09/2026 | 23/09/2026 |  |  | 27 |  | 27
ADIDAS | 0902970727-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 54 | 30/09/2026 | 54 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902970727 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 22/09/2026 | 17/09/2026 | 19/09/2026 | 54 | 46 | 8 |  | 2 | 15/09/2026 | 18/09/2026 | 2026-01-09 | 2026-03-09 | 54 | 46 | 8
ADIDAS | 0902970843-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 322 | 19/09/2026 | 322 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970843 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-06-08 | 2026-11-08 | 322 | 322 |  |  |  | 2026-03-08 | 2026-06-08 | 29/07/2026 | 31/07/2026 | 322 | 322 |  |  |  | 30/07/2026 | 2026-04-08 | 24/07/2026 | 28/07/2026 | 322 | 322
ADIDAS | 0902970859-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 462 | 23/09/2026 | 462 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970859 KX3654 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-05-09 | 19/09/2026 | 2026-07-09 | 18/09/2026 | 462 | 462 |  |  |  | 2026-02-09 | 16/09/2026 | 2026-08-08 | 15/08/2026 | 462 | 462 |  |  |  | 31/08/2026 | 14/09/2026 | 2026-08-08 | 14/08/2026 | 462 | 462
ADIDAS | 0902970876-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 503 | 15/10/2026 | 503 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970876 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-02-10 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 503 |  | 503 |  |  | 29/09/2026 | 30/09/2026 | 2026-04-08 | 24/08/2026 | 503 | 503 |  |  |  | 26/09/2026 | 28/09/2026 | 2026-01-08 | 2026-07-08 | 503 | 503
ADIDAS | 0902970893-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 433 | 15/10/2026 | 433 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0902970893 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 433 |  | 433 |  |  | 30/09/2026 | 2026-01-10 |  |  | 433 |  | 433 |  |  | 28/09/2026 | 29/09/2026 |  |  | 433 |  | 433
ADIDAS | 0902970931-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 365 | 19/09/2026 | 365 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970931 LD0285 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/08/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 20/08/2026 | 24/08/2026 | 24/08/2026 | 24/08/2026 | 365 | 365 |  |  |  | 14/08/2026 | 19/08/2026 | 29/07/2026 | 2026-01-08 | 365 | 365 |  |  |  | 2026-12-08 | 14/08/2026 | 25/07/2026 | 2026-01-08 | 365 | 365
ADIDAS | 0902970945-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 479 | 2026-05-09 | 479 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty 684009 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902970945 KC8152 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 31/08/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 479 | 479 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-09 | 2026-10-09 | 479 | 479 |  |  |  | 19/08/2026 | 27/08/2026 | 2026-03-09 | 2026-07-09 | 479 | 479
ADIDAS | 0902970957-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 658 | 30/09/2026 | 658 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902970957 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 17/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 658 | 627 | 31 |  | 231 | 14/09/2026 | 16/09/2026 | 31/07/2026 | 2026-05-08 | 658 | 658 |  |  |  | 2026-11-09 | 14/09/2026 | 30/07/2026 | 2026-05-08 | 658 | 658
ADIDAS | 0902970975-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 322 | 23/09/2026 | 322 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902970975 KX3655 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 18/09/2026 | 19/09/2026 | 18/09/2026 | 18/09/2026 | 322 | 309 | 13 |  |  | 15/09/2026 | 16/09/2026 | 2026-04-09 | 14/09/2026 | 322 | 322 |  |  |  | 2026-12-09 | 14/09/2026 | 2026-03-09 | 14/09/2026 | 322 | 322
ADIDAS | 0902970994-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 65 | 23/09/2026 | 65 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902970994 LE0357 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | M SL WV CU PT OLIVE ONE S27 |  | SS27 | 2026-09-09 | 21/09/2026 | 15/09/2026 | 16/09/2026 | 65 | 52 | 13 |  |  | 2026-05-09 | 17/09/2026 | 24/08/2026 | 14/09/2026 | 65 | 56 | 9
ADIDAS | 0902971007-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 325 | 30/09/2026 | 325 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902971007 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 325 | 291 | 34 |  | 291 | 16/09/2026 | 17/09/2026 | 2026-03-08 | 2026-12-08 | 325 | 325 |  |  |  | 14/09/2026 | 15/09/2026 | 31/07/2026 | 2026-12-08 | 325 | 325
ADIDAS | 0902971009-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 433 | 30/09/2026 | 433 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902971009 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 16/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 16/09/2026 | 21/09/2026 | 15/09/2026 | 16/09/2026 | 433 | 403 | 30 |  |  | 2026-12-09 | 17/09/2026 | 2026-10-08 | 20/08/2026 | 433 | 433 |  |  |  | 2026-10-09 | 15/09/2026 | 2026-10-08 | 19/08/2026 | 433 | 433
ADIDAS | 0902971034-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 65 | 23/09/2026 | 65 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902971034 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 24/08/2026 | 31/08/2026 | 27/08/2026 | 29/08/2026 | 65 | 65 |  |  |  | 19/08/2026 | 27/08/2026 | 31/07/2026 | 26/08/2026 | 65 | 65
ADIDAS | 0902971040-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 674 | 30/09/2026 | 674 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 29/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902971040 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 25/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 25/09/2026 | 28/09/2026 |  |  | 674 |  | 674 |  |  | 22/09/2026 | 24/09/2026 |  |  | 674 |  | 674 |  |  | 19/09/2026 | 22/09/2026 |  |  | 674 |  | 674
ADIDAS | 0902971044-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 54 | 30/09/2026 | 54 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902971044 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 54 |  | 54 |  |  | 18/09/2026 | 21/09/2026 |  |  | 54 |  | 54
ADIDAS | 0902971059-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 562 | 15/09/2026 | 562 | SI | SI29/05/2026 | G3K | SHORTS | G3 | ok |  | 14/09: ex-fty (Mexico). T2 Kahatex, PI Date 06-Aug, actual receives 16-Jun. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902971059 KD0738 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-11-09 | 562 | 562 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-11-09 | 562 | 562 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-08-09 | 2026-11-09 | 562 | 562
ADIDAS | 0902971713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1094 | 23/09/2026 | 1094 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Libolon, PI Date 23-Jun, actual receives 14-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902971713 KZ3200 | 13/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 13/08/2026 | 2026-06-08 | 2026-12-08 | 1094 | 1094 |  |  |  | 2026-03-08 | 2026-10-08 | 2026-04-08 | 14/08/2026 | 1094 | 1094
ADIDAS | 0902972065-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 514 | 30/09/2026 | 514 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972065 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 514 |  | 514 |  |  | 19/09/2026 | 22/09/2026 |  |  | 514 |  | 514
ADIDAS | 0902972095-1 LE8187 | BLACK | 105D | S2754MAS513 | 320 | 26/09/2026 | 320 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972095 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-09 | M SL WV TP PT BLACK |  | SS27 | 2026-08-09 | 23/09/2026 | 2026-11-09 | 17/09/2026 | 320 | 224 | 96 |  |  | 2026-04-09 | 19/09/2026 | 29/08/2026 | 17/09/2026 | 320 | 310 | 10
ADIDAS | 0902972376-1 JE3854 | BLACK/WHITE | 90D | S2554MESS683FT | 4291 | 2026-05-09 | 4291 | AT | AT29/05/2026 | G1D | PANTS | G1 | ok | (22/06/2026) | 04/09: ex-fty 516400 | EMBRO SUB PROCESS_V1 | 0902972376 JE3854 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/07/2026 | M FEELCOZY PANT |  | FW26 | 27/07/2026 | 2026-07-08 | 27/07/2026 | 2026-07-08 | 4291 | 4291 |  |  |  | 22/07/2026 | 2026-04-08 | 18/07/2026 | 2026-05-08 | 4291 | 4291
ADIDAS | 0902972659-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1 | 2026-05-09 | 1 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972659 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1 |  |  |  | 24/08/2026 | 27/08/2026 | 14/08/2026 | 14/08/2026 | 1 | 1
ADIDAS | 0902972672-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1 | 23/09/2026 | 1 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972672 LF0726 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 1 | 1 |  |  |  | 16/09/2026 | 19/09/2026 | 17/09/2026 | 17/09/2026 | 1 | 1
ADIDAS | 0902972711-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 56 | 2026-05-09 | 56 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | ok | 04/09: ex-fty 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902972711 KY5988 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-08 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-08 | 2026-12-08 | 2026-03-08 | 2026-07-08 | 56 | 56 |  |  |  | 29/07/2026 | 2026-07-08 | 31/07/2026 | 31/07/2026 | 56 | 56 |  |  |  | 22/07/2026 | 31/07/2026 | 30/07/2026 | 30/07/2026 | 56 | 56
ADIDAS | 0902972724-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 349 | 15/10/2026 | 349 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972724 LG9666 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-07-10 | W SL WV TT BLACK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 349 |  | 349 |  |  | 2026-03-10 | 2026-05-10 |  |  | 349 |  | 349
ADIDAS | 0902972758-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 330 | 15/10/2026 | 330 | AN | AN29/05/2026 | G1C | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 27-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972758 LG9661 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 330 |  | 330 |  |  | 2026-01-10 | 2026-03-10 |  |  | 330 |  | 330
ADIDAS | 0902972883-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 480 | 23/09/2026 | 480 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902972883 LF0727 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 19/09/2026 | 27/08/2026 | 2026-10-09 | 480 | 479 | 1 |  |  | 19/08/2026 | 16/09/2026 | 24/08/2026 | 2026-09-09 | 480 | 480
ADIDAS | 0902972938-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 486 | 26/09/2026 | 486 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902972938 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 486 | 486 |  |  |  | 2026-12-08 | 29/08/2026 | 29/07/2026 | 31/07/2026 | 486 | 486 |  |  |  | 2026-10-08 | 27/08/2026 | 28/07/2026 | 31/07/2026 | 486 | 486
ADIDAS | 0902973524-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1200 | 15/10/2026 | 1200 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 19-Aug. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0902973524 LG9668 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | W SL WV SK KHAKI THREE F26 |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-08-10 | 2026-12-10 |  |  | 1200 |  | 1200
ADIDAS | 0902973591-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 894 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973591 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902973619-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 1000 | 19/09/2026 | 1000 | AN | AN29/05/2026 | G3G,G3H,G3J | PANTS | G3 | ok | (19/06/2026) | 18/09: ex-fty. T2 Libolon, PI Date 31-May, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973619 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-04-08 | 19/08/2026 | 2026-05-08 | 18/08/2026 | 1000 | 1000 |  |  |  | 30/07/2026 | 13/08/2026 | 31/07/2026 | 15/08/2026 | 1000 | 1000
ADIDAS | 0902973641-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2142 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902973641 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902973776-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 23/09/2026 | 300 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty 684009 | HT+PAD SUB PROCESS_V3 | 0902973776 KF5311 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-06-08 | 2026-02-09 | 2026-07-08 | 2026-01-09 | 300 | 300 |  |  |  | 2026-03-08 | 29/08/2026 | 29/07/2026 | 30/07/2026 | 300 | 300 |  |  |  | 30/07/2026 | 27/08/2026 | 27/07/2026 | 29/07/2026 | 300 | 300
ADIDAS | 0902973810-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 399 | 2026-05-09 | 399 | SA | SA29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902973810 LE5609 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/07/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 31/08/2026 | 31/07/2026 | 31/08/2026 | 399 | 399 |  |  |  | 27/07/2026 | 27/08/2026 | 30/07/2026 | 2026-07-08 | 399 | 399 |  |  |  | 20/07/2026 | 19/08/2026 | 30/07/2026 | 2026-06-08 | 399 | 399
ADIDAS | 0902973847-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (07/07/2026) |  | 07/09: ex-fty. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock, T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973847 LC5741 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 26S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902973850-1 LF0723 | BLACK | 105D | S2754MAS511B | 433 | 15/09/2026 | 433 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902973850 LF0723 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | M SL WV SHO BLACK |  | SS27 | 2026-05-09 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 433 | 433 |  |  |  | 2026-02-09 | 2026-08-09 | 15/08/2026 | 2026-11-09 | 433 | 433
ADIDAS | 0902973860-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (29/06/2026) | ok | 07/09: ex-fty. T2 Kahatex, using fabric stock. T2 Formosa, using fabric stock. T2 Libolon, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973860 KY6616 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/08/2026 | M 3S WV WB LND |  | SS27 | 24/08/2026 | 28/08/2026 | 26/08/2026 | 26/08/2026 | 1 | 1 |  |  |  | 19/08/2026 | 24/08/2026 | 21/08/2026 | 21/08/2026 | 1 | 1
ADIDAS | 0902973878-1 LC5739 | OLIVE FOUR S27/BLACK | 105D | F2654MESS614WVB | 1 | 2026-09-09 | 1 | SA | SA29/05/2026 | G1C | JACKET | G1 | (10/07/2026) |  | 07/09: ex-fty. T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 01-Jul, actual receives 09-Jul. T2 Kahatex, PI Date 07-Jul, using fabric stock. 1st Art (TC 10 pcs) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902973878 LC5739 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | M 3S WV WB LND OLIVE FOUR S27/BLACK |  | SS27 | 31/08/2026 | 31/08/2026 | 2026-04-09 | 2026-04-09 | 1 | 1 |  |  |  | 27/08/2026 | 27/08/2026 | 31/08/2026 | 31/08/2026 | 1 | 1
ADIDAS | 0902974162-1 LE8187 | BLACK | 105D | S2754MAS513 | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974162 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-11-08 | 2026-11-08 | 8 | 8 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-08-08 | 2026-11-08 | 8 | 8
ADIDAS | 0902974179-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 8 | 2026-05-09 | 8 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974179 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 31/08/2026 | 8 | 8 |  |  |  | 24/08/2026 | 27/08/2026 | 18/08/2026 | 18/08/2026 | 8 | 8
ADIDAS | 0902974202-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 542 | 2026-05-09 | 542 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974202 LD5446 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 542 | 542 |  |  |  | 29/08/2026 | 2026-02-09 | 14/08/2026 | 28/08/2026 | 542 | 542
ADIDAS | 0902974244-1 LE8187 | BLACK | 105D | S2754MAS513 | 311 | 2026-05-09 | 311 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | ok | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974244 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-09 | M SL WV TP PT BLACK |  | SS27 | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 311 | 311 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-05-08 | 2026-04-09 | 311 | 311
ADIDAS | 0902974263-1 LE8187 | BLACK | 105D | S2754MAS513 | 1425 | 2026-05-09 | 1425 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974263 LE8187 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 1425 | 1425 |  |  |  | 2026-03-08 | 19/08/2026 | 2026-06-08 | 2026-11-09 | 1425 | 1405 | 20
ADIDAS | 0902974284-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1436 | 15/09/2026 | 1436 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 14/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974284 LD5446 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 1436 | 1436 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-12-08 | 14/09/2026 | 1436 | 1436
ADIDAS | 0902974308-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 353 | 2026-09-09 | 353 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974308 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-07-09 | 353 | 353 |  |  |  | 29/08/2026 | 2026-03-09 | 13/08/2026 | 2026-02-09 | 353 | 353
ADIDAS | 0902974332-1 LE8187 | BLACK | 105D | S2754MAS513 | 370 | 2026-05-09 | 370 | SI | SI29/05/2026 | G3D,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902974332 LE8187 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-03-09 | 14/08/2026 | 2026-01-09 | 370 | 370 |  |  |  | 2026-03-08 | 31/08/2026 | 2026-05-08 | 14/09/2026 | 370 | 370
ADIDAS | 0902975286-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 29 | 19/09/2026 | 29 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975286 KX3650 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-08 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-06-08 | 2026-11-08 | 2026-10-08 | 2026-10-08 | 29 | 29 |  |  |  | 2026-03-08 | 2026-06-08 | 2026-01-08 | 2026-01-08 | 29 | 29 |  |  |  | 30/07/2026 | 2026-04-08 | 31/07/2026 | 31/07/2026 | 29 | 29
ADIDAS | 0902975671-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1236 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 24-Jun. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902975671 KZ3202 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0902975694-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1272 | 23/09/2026 | 1272 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 600000 | HT+PAD SUB PROCESS_V3 | 0902975694 LD0287 | 31/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 1272 | 1224 | 48 |  | 76 | 14/09/2026 | 16/09/2026 | 2026-05-09 | 16/09/2026 | 1272 | 1270 | 2 |  |  | 2026-11-09 | 14/09/2026 | 2026-04-09 | 16/09/2026 | 1272 | 1270 | 2
ADIDAS | 0902975717-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 1200 | 30/09/2026 | 1200 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 600000 | EMBRO SUB PROCESS_V1 | 0902975717 LE5390 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-09-10 | 2026-09-10 |  |  | 1200 |  | 1200
ADIDAS | 0902975773-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 4800 | 30/09/2026 | 4800 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0902975773 LE5391 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 4800 |  | 4800 |  |  | 2026-09-10 | 13/10/2026 |  |  | 4800 |  | 4800
ADIDAS | 0902975811-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 80 | 30/09/2026 | 80 | SA | SA29/05/2026 | G2D | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975811 LD0287 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 80 |  | 80 |  |  | 21/09/2026 | 22/09/2026 | 2026-04-08 | 2026-04-08 | 80 | 80 |  |  |  | 18/09/2026 | 19/09/2026 | 31/07/2026 | 2026-04-08 | 80 | 80
ADIDAS | 0902975855-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 31 | 30/09/2026 | 31 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 659018 | HT+PAD SUB PROCESS_V3 | 0902975855 LD0288 | 31/08/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-07-09 | 31 | 31 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 31/07/2026 | 31 | 31 |  |  |  | 31/08/2026 | 2026-03-09 | 27/07/2026 | 28/07/2026 | 31 | 31
ADIDAS | 0902975887-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 2400 | 2026-07-10 | 2400 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975887 LE7510 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 2400 |  | 2400 |  |  | 25/09/2026 | 29/09/2026 |  |  | 2400 |  | 2400
ADIDAS | 0902975946-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 2400 | 30/09/2026 | 2400 | SI | SI29/05/2026 | G1C | JACKET | G1 | ok | (22/06/2026) | 29/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Sep. T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975946 KZ3207 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 15/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 2400 | 170 | 2230 |  | 147 | 2026-11-09 | 19/09/2026 | 26/08/2026 | 18/09/2026 | 2400 | 2090 | 310
ADIDAS | 0902975975-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 2400 | 23/09/2026 | 2400 | SI | SI29/05/2026 | G1H | JACKET | G1 | ok | (22/06/2026) | 21/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 22-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Libolon, PI Date 23-Jun, actual receives 09-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902975975 LE4307 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-09 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-09 | 23/09/2026 | 2026-03-09 | 18/09/2026 | 2400 | 2313 | 87 |  |  | 2026-02-09 | 19/09/2026 | 22/08/2026 | 2026-08-09 | 2400 | 2356 | 44
ADIDAS | 0902976008-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 3600 | 2026-07-10 | 3600 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976008 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 2026-08-10 | 13/10/2026 |  |  | 3600 |  | 3600 |  |  | 2026-05-10 | 2026-09-10 |  |  | 3600 |  | 3600
ADIDAS | 0902976049-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 2026-07-10 | 6000 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976049 LE7509 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27 | 30/09/2026 | 2026-08-10 |  |  | 6000 |  | 6000 |  |  | 26/09/2026 | 2026-05-10 |  |  | 6000 |  | 6000
ADIDAS | 0902976088-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 2026-07-10 | 8400 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902976088 LE7508 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | W 3S TRICOT PT BLACK/WHITE |  | SS27 | 2026-08-10 | 19/10/2026 |  |  | 8400 |  | 8400 |  |  | 2026-05-10 | 15/10/2026 |  |  | 8400 |  | 8400
ADIDAS | 0902976602-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1120 | 31/10/2026 | 1120 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902976602 LD0287 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 14/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 1120 |  | 1120 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1120 |  | 1120 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1120 |  | 1120
ADIDAS | 0902976952-1 LG9669 | BLACK | 120D | S2754WAS514C | 8 | 15/10/2026 | 8 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. 684009 | PRINT L3+PPA SUB PROCESS_V3 | 0902976952 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | W SL WV SK BLACK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 8 |  | 8 |  |  | 2026-05-10 | 2026-06-10 |  |  | 8 |  | 8
ADIDAS | 0902976974-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 8 | 15/10/2026 | 8 | SI | SI29/05/2026 | G1D | JACKET | G1 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 24-Jun. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902976974 LF0726 | 31/08/2026 | KAHATEX CIJERAH | PERU | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 8 |  | 8 |  |  | 16/09/2026 | 19/09/2026 |  |  | 8 |  | 8
ADIDAS | 0902977144-1 LE8187 | BLACK | 105D | S2754MAS513 | 342 | 2026-05-09 | 342 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902977144 LE8187 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 20/08/2026 | 2026-07-08 | 14/08/2026 | 342 | 342 |  |  |  | 2026-03-08 | 14/08/2026 | 2026-05-08 | 2026-04-09 | 342 | 342
ADIDAS | 0902977685-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1796 | 30/09/2026 | 1796 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0902977685 KX3655 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 26/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 1796 |  | 1796 |  |  | 23/09/2026 | 24/09/2026 |  |  | 1796 |  | 1796 |  |  | 21/09/2026 | 22/09/2026 |  |  | 1796 |  | 1796
ADIDAS | 0902977729-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 466 | 15/10/2026 | 466 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | HT+PAD SUB PROCESS_V3 | 0902977729 LD0288 | 31/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 19/08/2026 | 2026-01-09 | 466 | 466 |  |  |  | 2026-12-08 | 29/08/2026 | 25/07/2026 | 2026-06-08 | 466 | 466 |  |  |  | 2026-10-08 | 27/08/2026 | 24/07/2026 | 2026-05-08 | 466 | 466
ADIDAS | 0902977769-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 497 | 30/09/2026 | 497 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977769 KX3655 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 25/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 25/09/2026 | 28/09/2026 |  |  | 497 |  | 497 |  |  | 22/09/2026 | 24/09/2026 |  |  | 497 |  | 497 |  |  | 19/09/2026 | 22/09/2026 |  |  | 497 |  | 497
ADIDAS | 0902977806-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 198 | 26/09/2026 | 198 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0902977806 LD0288 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 18/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 18/08/2026 | 2026-02-09 | 20/08/2026 | 2026-01-09 | 198 | 198 |  |  |  | 2026-12-08 | 29/08/2026 | 30/07/2026 | 2026-07-08 | 198 | 198 |  |  |  | 2026-10-08 | 27/08/2026 | 29/07/2026 | 2026-06-08 | 198 | 198
ADIDAS | 0902977843-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 200 | 15/10/2026 | 200 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902977843 LD0287 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 200 |  | 200 |  |  | 26/09/2026 | 26/09/2026 |  |  | 200 |  | 200 |  |  | 24/09/2026 | 24/09/2026 |  |  | 200 |  | 200
ADIDAS | 0902977881-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 504 | 31/10/2026 | 504 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 800187 | HT+PAD SUB PROCESS_V3 | 0902977881 LD0287 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 13/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 504 |  | 504 |  |  | 2026-09-10 | 2026-10-10 |  |  | 504 |  | 504 |  |  | 2026-07-10 | 2026-08-10 |  |  | 504 |  | 504
ADIDAS | 0902977919-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 154 | 30/09/2026 | 154 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 18/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977919 LD0288 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 154 | 154 |  |  |  | 2026-02-09 | 2026-05-09 | 30/07/2026 | 2026-01-08 | 154 | 154 |  |  |  | 31/08/2026 | 2026-03-09 | 30/07/2026 | 2026-01-08 | 154 | 154
ADIDAS | 0902977969-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 879 | 30/09/2026 | 879 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0902977969 KX3655 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 23/09/2026 | 16/09/2026 | 18/09/2026 | 879 | 839 | 40 |  |  | 2026-11-09 | 19/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879 |  |  |  | 2026-09-09 | 17/09/2026 | 2026-03-09 | 2026-09-09 | 879 | 879
ADIDAS | 0902978212-1 LE0355 | BLACK | 105D | S2754MAS514 | 2156 | 30/09/2026 | 2156 | SA | SA29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978212 LE0355 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | M SL WV CU PT BLACK |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 2156 | 2046 | 110 |  | 305 | 2026-11-09 | 17/09/2026 | 2026-01-09 | 17/09/2026 | 2156 | 2065 | 91
ADIDAS | 0902978235-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 2398 | 30/09/2026 | 2398 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978235 KX3654 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 14/09/2026 | 19/09/2026 | 15/09/2026 | 18/09/2026 | 2398 | 2355 | 43 |  |  | 2026-10-09 | 16/09/2026 | 2026-11-08 | 20/08/2026 | 2398 | 2398 |  |  |  | 2026-08-09 | 14/09/2026 | 2026-11-08 | 19/08/2026 | 2398 | 2398
ADIDAS | 0902978263-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1644 | 30/09/2026 | 1644 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978263 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 19/09/2026 | 16/09/2026 | 18/09/2026 | 1644 | 1488 | 156 |  |  | 2026-11-09 | 16/09/2026 | 2026-08-09 | 17/09/2026 | 1644 | 1564 | 80 |  |  | 2026-09-09 | 14/09/2026 | 2026-08-09 | 17/09/2026 | 1644 | 1563 | 81
ADIDAS | 0902978291-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 2268 | 23/09/2026 | 2268 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902978291 LD0287 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 15/09/2026 | 23/09/2026 | 16/09/2026 | 19/09/2026 | 2268 | 2229 | 39 |  | 103 | 2026-11-09 | 19/09/2026 | 2026-07-09 | 18/09/2026 | 2268 | 2234 | 34 |  |  | 2026-09-09 | 17/09/2026 | 2026-07-09 | 18/09/2026 | 2268 | 2234 | 34
ADIDAS | 0902978328-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1623 | 30/09/2026 | 1623 | SI | SI29/05/2026 | G3B | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978328 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1623 |  | 1623 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1623 |  | 1623
ADIDAS | 0902978352-1 LF0718 | BLACK | 105D | S2754MAS512B | 1886 | 23/09/2026 | 1886 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978352 LF0718 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 16/09/2026 | M SL WV OH PT BLACK |  | SS27 | 16/09/2026 | 23/09/2026 | 17/09/2026 | 19/09/2026 | 1886 | 663 | 1223 |  | 264 | 2026-12-09 | 19/09/2026 | 15/09/2026 | 19/09/2026 | 1886 | 1021 | 865 |  | 298
ADIDAS | 0902978382-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1442 | 23/09/2026 | 1442 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 27-Jun (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978382 LF0726 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/08/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 19/09/2026 | 2026-02-09 | 18/09/2026 | 1442 | 1442 |  |  |  | 27/08/2026 | 16/09/2026 | 28/08/2026 | 19/09/2026 | 1442 | 1440 | 2 |  | 1
ADIDAS | 0902978413-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 1394 | 23/09/2026 | 1394 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978413 LG9670 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | W SL WV PT AURORA COFFEE S26 |  | SS27 | 2026-09-09 | 21/09/2026 | 2026-08-09 | 15/09/2026 | 1394 | 1321 | 73 |  |  | 2026-05-09 | 17/09/2026 | 2026-07-09 | 18/09/2026 | 1394 | 1355 | 39
ADIDAS | 0902978440-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 767 | 30/09/2026 | 767 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978440 LG9673 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 15/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 767 | 241 | 526 |  |  | 2026-11-09 | 17/09/2026 | 14/09/2026 | 19/09/2026 | 767 | 730 | 37 |  | 12
ADIDAS | 0902978469-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 491 | 30/09/2026 | 491 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902978469 LG9674 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 491 |  | 491 |  |  | 18/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 491 | 171 | 320 |  | 171
ADIDAS | 0902978495-1 LE8187 | BLACK | 105D | S2754MAS513 | 1353 | 30/09/2026 | 1353 | SI | SI29/05/2026 | G3J | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 12-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 600000 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978495 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 22/09/2026 | 2026-04-09 | 2026-09-09 | 1353 | 1115 | 238 |  |  | 2026-02-09 | 18/09/2026 | 28/08/2026 | 17/09/2026 | 1353 | 1247 | 106
ADIDAS | 0902978547-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 1342 | 23/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978547 LF0727 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/08/2026 | M SL WV TT BLACK |  | SS27 | 24/08/2026 | 19/09/2026 | 26/08/2026 | 19/09/2026 | 1342 | 1274 | 68 |  | 32 | 19/08/2026 | 16/09/2026 | 21/08/2026 | 17/09/2026 | 1342 | 1335 | 7
ADIDAS | 0902978578-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 870 | 30/09/2026 | 870 | AN | AN29/05/2026 | G1J | JACKET | G1 | ok | (19/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (creasemark), PI Date 20-Jun, actual receives 06-AUg (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978578 LG9666 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | W SL WV TT BLACK |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 870 |  | 870 |  |  | 21/09/2026 | 24/09/2026 | 28/08/2026 | 2026-03-09 | 870 | 537 | 333
ADIDAS | 0902978872-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 339 | 2026-09-09 | 339 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978872 LD5446 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-03-09 | 339 | 339 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 20/08/2026 | 339 | 339
ADIDAS | 0902978908-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 2026-05-09 | 300 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978908 LE8181 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-03-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0902978941-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 23/09/2026 | 300 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978941 LF0729 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 14/08/2026 | 31/08/2026 | 19/08/2026 | 31/08/2026 | 300 | 300 |  |  |  | 2026-11-08 | 27/08/2026 | 18/08/2026 | 29/08/2026 | 300 | 300
ADIDAS | 0902978973-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 347 | 23/09/2026 | 347 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual recieves 27-Jun (PO NT-354). 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902978973 LF0726 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-04-09 | 19/09/2026 | 2026-07-09 | 18/09/2026 | 347 | 345 | 2 |  |  | 2026-01-09 | 16/09/2026 | 31/08/2026 | 2026-11-09 | 347 | 347
ADIDAS | 0902978999-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1030 | 2026-12-09 | 1030 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902978999 KX3650 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 31/08/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 31/08/2026 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1030 | 1030 |  |  |  | 27/08/2026 | 2026-04-09 | 31/07/2026 | 2026-07-08 | 1030 | 1030 |  |  |  | 24/08/2026 | 2026-02-09 | 31/07/2026 | 2026-06-08 | 1030 | 1030
ADIDAS | 0902979020-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 1006 | 2026-12-09 | 1006 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0902979020 LD0285 | 31/08/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-05-09 | 2026-08-09 | 1006 | 1006 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-03-08 | 13/08/2026 | 1006 | 1006 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-01-08 | 2026-12-08 | 1006 | 1006
ADIDAS | 0902979825-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 2026-12-09 | 123 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902979825 LD5446 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 123 | 123 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 18/08/2026 | 123 | 123
ADIDAS | 0902980168-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 574 | 30/09/2026 | 574 | SI | SI29/05/2026 | G3H | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980168 LD5446 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 574 |  | 574 |  |  | 18/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 574 | 403 | 171 |  | 20
ADIDAS | 0902980203-1 LE8187 | BLACK | 105D | S2754MAS513 | 812 | 23/09/2026 | 812 | SI | SI29/05/2026 | G3B | PANTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980203 LE8187 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/09/2026 | M SL WV TP PT BLACK |  | SS27 | 14/09/2026 | 23/09/2026 | 15/09/2026 | 17/09/2026 | 812 | 500 | 312 |  |  | 2026-10-09 | 19/09/2026 | 2026-05-09 | 19/09/2026 | 812 | 678 | 134 |  | 22
ADIDAS | 0902980461-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 895 | 23/10/2026 | 895 | AN | AN29/05/2026 | G3B,G3E,G3F | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980461 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 26/08/2026 | 21/09/2026 | 27/08/2026 | 17/09/2026 | 895 | 895 |  |  |  | 20/08/2026 | 17/09/2026 | 2026-06-08 | 18/09/2026 | 895 | 895
ADIDAS | 0902980492-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1236 | 23/10/2026 | 1236 | AN | AN29/05/2026 | G3F | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980492 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-09-09 | 15/09/2026 | 1236 | 1236 |  |  |  | 2026-05-09 | 2026-12-09 | 2026-11-08 | 17/09/2026 | 1236 | 1226 | 10
ADIDAS | 0902980497-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 1200 | 30/09/2026 | 1200 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0902980497 LD0287 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 1200 | 1074 | 126 |  | 635 | 15/09/2026 | 19/09/2026 | 2026-03-08 | 14/09/2026 | 1200 | 1200 |  |  |  | 2026-12-09 | 17/09/2026 | 2026-01-08 | 14/09/2026 | 1200 | 1200
ADIDAS | 0902980516-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2141 | 23/10/2026 | 2141 | AN | AN29/05/2026 | G3F,G3H | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902980516 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/08/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 2026-11-08 | 31/08/2026 | 2141 | 2141 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-08-08 | 21/08/2026 | 2141 | 2125 | 16
ADIDAS | 0902980530-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 901 | 19/09/2026 | 901 | AN | AN29/05/2026 | G1B,G1J | JACKET | G1 | ok | (19/06/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980530 LG9666 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-09 | W SL WV TT BLACK |  | SS27 | 2026-08-09 | 18/09/2026 | 2026-09-09 | 18/09/2026 | 901 | 901 |  |  |  | 2026-04-09 | 15/09/2026 | 22/08/2026 | 18/09/2026 | 901 | 901
ADIDAS | 0902980559-1 LH3758 | BLACK | 120D | S2754WAS518B | 800 | 30/09/2026 | 800 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980559 LH3758 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 26/09/2026 | W SL WV BR PT BLACK |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 800 |  | 800 |  |  | 23/09/2026 | 24/09/2026 |  |  | 800 |  | 800
ADIDAS | 0902980595-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 1066 | 23/09/2026 | 1066 | SA | SA29/05/2026 | G1B,G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980595 LG9664 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 22/09/2026 | 17/09/2026 | 19/09/2026 | 1066 | 742 | 324 |  | 368 | 15/09/2026 | 18/09/2026 | 2026-08-09 | 17/09/2026 | 1066 | 1007 | 59
ADIDAS | 0902980626-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 1094 | 30/09/2026 | 1094 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 630001 | PRINT L3+PPA SUB PROCESS_V3 | 0902980626 LH3761 | 31/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 29/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1094 |  | 1094 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1094 |  | 1094
ADIDAS | 0902980662-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1530 | 23/09/2026 | 1530 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980662 LE8181 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-11-09 | 23/09/2026 | 2026-12-09 | 19/09/2026 | 1530 | 859 | 671 |  | 153 | 2026-08-09 | 19/09/2026 | 2026-11-09 | 19/09/2026 | 1530 | 1231 | 299 |  | 384
ADIDAS | 0902980942-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 2026-07-10 | 300 | AN | AN29/05/2026 | G1K | JACKET | G1 | ok | (19/06/2026) | T2 Teijin Nantong, PI Date 20-Jun, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980942 LF0727 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | M SL WV TT BLACK |  | SS27 | 2026-06-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0902980969-1 LE8187 | BLACK | 105D | S2754MAS513 | 420 | 2026-07-10 | 420 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902980969 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 420 |  | 420 |  |  | 30/09/2026 | 2026-02-10 |  |  | 420 |  | 420
ADIDAS | 0902981008-1 LE8187 | BLACK | 105D | S2754MAS513 | 300 | 2026-07-10 | 300 | SI | SI29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 08-Jul. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981008 LE8187 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 30/09/2026 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0902981035-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 360 | 30/09/2026 | 360 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Teijin Nantong, material quality issues (moir膿), PI Date 20-Jun, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 516243 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981035 LF0729 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-10-09 | 19/09/2026 | 2026-11-09 | 19/09/2026 | 360 | 278 | 82 |  | 64 | 2026-07-09 | 16/09/2026 | 2026-04-09 | 2026-04-09 | 360 | 293 | 67
ADIDAS | 0902981042-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 120 | 2026-09-09 | 120 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 08/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981042 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 120 | 120 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-11-08 | 14/08/2026 | 120 | 120
ADIDAS | 0902981068-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 532 | 2026-05-09 | 532 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 672027 | HT+PAD SUB PROCESS_V3 | 0902981068 KX3650 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 30/07/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 30/07/2026 | 2026-05-08 | 30/07/2026 | 2026-05-08 | 532 | 532 |  |  |  | 27/07/2026 | 31/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532 |  |  |  | 23/07/2026 | 29/07/2026 | 23/07/2026 | 2026-01-08 | 532 | 532
ADIDAS | 0902981100-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/09/2026 | 300 | SA | SA29/05/2026 | G2M | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 672027 | HT+PAD SUB PROCESS_V3 | 0902981100 KX3655 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 15/09/2026 | 18/09/2026 | 15/09/2026 | 18/09/2026 | 300 | 300 |  |  |  | 2026-11-09 | 15/09/2026 | 2026-10-09 | 17/09/2026 | 300 | 279 | 21 |  |  | 2026-09-09 | 2026-12-09 | 2026-09-09 | 17/09/2026 | 300 | 279 | 21
ADIDAS | 0902981242-1 LG9669 | BLACK | 120D | S2754WAS514C | 15 | 30/09/2026 | 15 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty (KN GLT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 650010 | PRINT L3+PPA SUB PROCESS_V3 | 0902981242 LG9669 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/09/2026 | W SL WV SK BLACK |  | SS27 | 24/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 15 | 15 |  |  | 15 | 21/09/2026 | 22/09/2026 | 29/08/2026 | 2026-01-09 | 15 | 15
ADIDAS | 0902981317-1 LD0282 | OLIVE TWO S27 | 120D | S2608WR0900 | 185 | 29/09/2026 | 185 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 29/09: ex-fty (KN GLT). 1st Art (TC 10 pcs) 650010 | HT+PAD SUB PROCESS_V3 | 0902981317 LD0282 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/09/2026 | Run Ess Tee W OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 185 | 185 |  |  |  | 14/09/2026 | 16/09/2026 | 2026-01-08 | 2026-08-08 | 185 | 185 |  |  |  | 2026-11-09 | 14/09/2026 | 31/07/2026 | 2026-07-08 | 185 | 185
ADIDAS | 0902981358-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 10 | 15/10/2026 | 10 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0902981358 LD0285 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 10 |  | 10 |  |  | 24/09/2026 | 24/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-08-08 | 2026-08-08 | 10 | 10
ADIDAS | 0902981395-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 21 | 30/09/2026 | 21 | SI | SI29/05/2026 | G3A | SHORTS | G3 | (28/07/2026) | (22/06/2026) | 18/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI date 15-Jul, actual receives 19-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981395 LD5446 | 31/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 21 | 21 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-07-09 | 2026-07-09 | 21 | 21
ADIDAS | 0902981438-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 30/09/2026 | 120 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 12-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0902981438 LG9669 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W SL WV SK BLACK |  | SS27-SPOMA | 18/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 120 | 113 | 7 |  | 113 | 15/09/2026 | 19/09/2026 | 28/08/2026 | 2026-05-09 | 120 | 114 | 6
ADIDAS | 0902981755-1 LF0723 | BLACK | 105D | S2754MAS511B | 1697 | 30/09/2026 | 1697 | SI | SI29/05/2026 | G3A | SHORTS | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Kahatex, PI Date 28-Jul, actual 10-Aug. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981755 LF0723 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | M SL WV SHO BLACK |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1697 |  | 1697 |  |  | 22/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 1697 | 763 | 934 |  | 763
ADIDAS | 0902981783-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 1824 | 23/09/2026 | 1824 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0902981783 LD0288 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/08/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 14/08/2026 | 2026-02-09 | 18/08/2026 | 2026-01-09 | 1824 | 1824 |  |  |  | 2026-11-08 | 29/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824 |  |  |  | 2026-07-08 | 27/08/2026 | 24/07/2026 | 2026-03-08 | 1824 | 1824
ADIDAS | 0902981811-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 712 | 23/09/2026 | 712 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981811 LG9664 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 712 |  | 712 |  |  | 18/09/2026 | 21/09/2026 | 2026-11-09 | 17/09/2026 | 712 | 683 | 29
ADIDAS | 0902981835-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 1342 | 23/09/2026 | 1342 | AN | AN29/05/2026 | G1D | JACKET | G1 | ok | (19/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 28-May (PO NT-354). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981835 LF0729 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/08/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 20/08/2026 | 2026-10-09 | 20/08/2026 | 2026-10-09 | 1342 | 1342 |  |  |  | 14/08/2026 | 2026-07-09 | 18/08/2026 | 2026-03-09 | 1342 | 1342
ADIDAS | 0902981856-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 1297 | 23/09/2026 | 1297 | SI | SI29/05/2026 | G3A,G3E | SHORTS | G3 | ok | (22/06/2026) | 21/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 06-Aug (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981856 LF0725 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-09-09 | 23/09/2026 | 2026-10-09 | 2026-12-09 | 1297 | 1245 | 52 |  |  | 2026-05-09 | 19/09/2026 | 2026-03-09 | 16/09/2026 | 1297 | 1297
ADIDAS | 0902981919-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 425 | 23/09/2026 | 425 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 23-Jun. 1st Art (TC 10 pcs) 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981919 LG9665 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-09 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-08-09 | 22/09/2026 | 2026-08-09 | 18/09/2026 | 425 | 326 | 99 |  |  | 2026-04-09 | 18/09/2026 | 2026-01-09 | 18/09/2026 | 425 | 379 | 46
ADIDAS | 0902981952-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 300 | 30/09/2026 | 300 | ID | ID29/05/2026 | G3B | SKIRT | G3 | ok | (22/06/2026) | 29/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902981952 LG9668 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 25/09/2026 | W SL WV SK KHAKI THREE F26 |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 22/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0902981983-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C-MTF | 619 | 23/09/2026 | 619 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 22/09: ex-fty (Mexico). T2 Teijin Nantong, material quality issues (cresemark), PI Date 20-Jun, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 22-Jun. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902981983 LG9661 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-12-09 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-09 | 22/09/2026 | 2026-12-09 | 17/09/2026 | 619 | 511 | 108 |  |  | 2026-09-09 | 18/09/2026 | 26/08/2026 | 17/09/2026 | 619 | 555 | 64
ADIDAS | 0902982085-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 814 | 30/09/2026 | 814 | AN | AN29/05/2026 | G3D | PANTS | G3 | ok | (27/06/2026) | 25/09: ex-fty (Mexico). T2 Teijin Nantong, PI date 20-Jun, actual receives 22-Aug. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0902982085 LG9675 | 31/08/2026 | KAHATEX CIJERAH | MEXICO | SEA | 26/09/2026 | W SL WV PT BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 814 |  | 814 |  |  | 23/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 814 | 742 | 72 |  | 742
ADIDAS | 0902982159-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 10 | 2026-05-09 | 10 | AN | AN29/05/2026 | G1E | T-SHIRT | G1 | ok | ok | 04/09: ex-fty (KN GLT). T2 Libolon, actual receives 29-Apr (PO 25063167). T2 Fu Hsun, actual receives 23-Apr (PO 25063168). 650010 | HT SUB PROCESS_V1 | 0902982159 IT1824 | 13/08/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/07/2026 | ADIZERO E TEE |  | FW26 | 16/07/2026 | 20/07/2026 | 17/07/2026 | 17/07/2026 | 10 | 10 |  |  |  | 14/07/2026 | 16/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10 |  |  |  | 13/07/2026 | 15/07/2026 | 13/07/2026 | 13/07/2026 | 10 | 10
ADIDAS | 0902982427-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 363 | 31/10/2026 | 363 | ID | ID29/05/2026 | G2J | T-SHIRT | G2 | (28/07/2026) | (27/06/2026) | DRC 0090-early shipment customer (BTP_12_06_2026 EARLY HOLD SHIPMENT). 800187 | HT+PAD SUB PROCESS_V3 | 0902982427 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-10 | Run Ess Tee W BLACK |  | SS27-SLT-TI | 2026-12-10 | 13/10/2026 |  |  | 363 |  | 363 |  |  | 2026-08-10 | 2026-09-10 |  |  | 363 |  | 363 |  |  | 2026-06-10 | 2026-07-10 |  |  | 363 |  | 363
ADIDAS | 0902982687-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI29/05/2026 |  | PANTS |  | ok | (22/06/2026) | T2 Libolon, PI Date 23-Jun, actual receives 17-Jul. T2 Formosa, PI Date 27-Jun, actual receives 13-Jul. T2 Kahatex, PI Date 28-Jun, actual receives 30-Jun. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902982687 KZ3199 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0902982718-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 400 | 2026-03-09 | 400 | SA | SA29/05/2026 | G3J,G3K | SHORTS | G3 | ok | ok | 03/09: ex-fty (S4EU). DRC 0010-hold shipment customer. T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 1st Art (TC 10 pcs) 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902982718 LH4535 | 13/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/07/2026 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-07-08 | 400 | 400 |  |  |  | 24/07/2026 | 2026-05-08 | 27/07/2026 | 29/08/2026 | 400 | 400
ADIDAS | 0902982774-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 321 | 31/10/2026 | 321 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516254 | HT+PAD SUB PROCESS_V3 | 0902982774 LD0285 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 321 |  | 321 |  |  | 13/10/2026 | 14/10/2026 | 2026-04-08 | 2026-07-08 | 321 | 321 |  |  |  | 2026-10-10 | 2026-12-10 | 2026-01-08 | 2026-06-08 | 321 | 321
ADIDAS | 0902982800-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2L | T-SHIRT | G2 | ok | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902982800 LD0283 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 | 17/09/2026 | 19/09/2026 | 300 | 294 | 6 |  | 6 | 22/09/2026 | 23/09/2026 | 17/09/2026 | 18/09/2026 | 300 | 294 | 6
ADIDAS | 0902982827-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 524 | 31/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902982827 LD0285 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 524 |  | 524 |  |  | 13/10/2026 | 14/10/2026 | 2026-04-08 | 2026-10-08 | 524 | 524 |  |  |  | 2026-10-10 | 2026-12-10 | 2026-01-08 | 2026-10-08 | 524 | 524
ADIDAS | 0902982852-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 320 | 2026-07-10 | 320 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982852 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 320 |  | 320 |  |  | 25/09/2026 | 26/09/2026 | 2026-07-08 | 15/08/2026 | 320 | 320 |  |  |  | 23/09/2026 | 24/09/2026 | 2026-07-08 | 14/08/2026 | 320 | 320
ADIDAS | 0902982880-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982880 LD0287 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 350 |  | 350 |  |  | 24/09/2026 | 25/09/2026 | 16/09/2026 | 16/09/2026 | 350 | 304 | 46 |  |  | 22/09/2026 | 23/09/2026 | 16/09/2026 | 16/09/2026 | 350 | 304 | 46
ADIDAS | 0902982910-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 300 | 2026-07-10 | 300 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982910 LD0285 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 24/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-07-08 | 13/08/2026 | 300 | 300
ADIDAS | 0902982939-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900 | 350 | 2026-07-10 | 350 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | 30/09: ex-fty 516403 | HT+PAD SUB PROCESS_V3 | 0902982939 LD0288 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 350 |  | 350 |  |  | 25/09/2026 | 26/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350 |  |  |  | 23/09/2026 | 24/09/2026 | 27/08/2026 | 2026-07-09 | 350 | 350
ADIDAS | 0902982968-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 414 | 23/09/2026 | 414 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 22/09: ex-fty 516462 | HT+PAD SUB PROCESS_V3 | 0902982968 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 414 | 374 | 40 |  |  | 14/09/2026 | 16/09/2026 | 25/07/2026 | 2026-01-08 | 414 | 414 |  |  |  | 2026-11-09 | 14/09/2026 | 25/07/2026 | 31/07/2026 | 414 | 414
ADIDAS | 0902982993-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 810 | 31/10/2026 | 810 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902982993 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 810 |  | 810 |  |  | 15/10/2026 | 16/10/2026 | 18/09/2026 | 18/09/2026 | 810 | 780 | 30 |  |  | 13/10/2026 | 14/10/2026 | 18/09/2026 | 19/09/2026 | 810 | 794 | 16 |  | 14
ADIDAS | 0902983024-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1000 | 31/10/2026 | 1000 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902983024 KX3651 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 1000 |  | 1000 |  |  | 16/10/2026 | 17/10/2026 | 19/09/2026 | 19/09/2026 | 1000 | 647 | 353 |  | 647 | 14/10/2026 | 15/10/2026 | 18/09/2026 | 19/09/2026 | 1000 | 761 | 239 |  | 114
ADIDAS | 0902983061-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 880 | 31/10/2026 | 880 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0902983061 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 880 |  | 880 |  |  | 15/10/2026 | 16/10/2026 |  |  | 880 |  | 880 |  |  | 13/10/2026 | 14/10/2026 |  |  | 880 |  | 880
ADIDAS | 0902983088-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 320 | 30/09/2026 | 320 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 25/09: ex-fty 516254 | HT+PAD SUB PROCESS_V3 | 0902983088 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 320 | 290 | 30 |  |  | 14/09/2026 | 16/09/2026 | 26/08/2026 | 2026-05-09 | 320 | 320 |  |  |  | 2026-11-09 | 14/09/2026 | 26/08/2026 | 2026-05-09 | 320 | 320
ADIDAS | 0902983300-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983300 KX3651 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/09/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 108 | 108 |  |  | 6 | 14/09/2026 | 16/09/2026 | 25/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 2026-11-09 | 14/09/2026 | 24/07/2026 | 31/07/2026 | 108 | 108
ADIDAS | 0902983336-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 108 | 30/09/2026 | 108 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983336 KX3654 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 108 | 108 |  |  | 7 | 14/09/2026 | 16/09/2026 | 26/08/2026 | 2026-08-09 | 108 | 108 |  |  |  | 2026-11-09 | 14/09/2026 | 26/08/2026 | 2026-08-09 | 108 | 108
ADIDAS | 0902983370-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 108 | 26/09/2026 | 108 | SA | SA29/05/2026 | G2G,G2I | T-SHIRT | G2 | ok | (22/06/2026) | 24/09: ex-fty 848012 | HT+PAD SUB PROCESS_V3 | 0902983370 KF5311 | 31/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-08 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-11-08 | 2026-02-09 | 2026-11-08 | 2026-01-09 | 108 | 108 |  |  |  | 2026-06-08 | 29/08/2026 | 30/07/2026 | 31/07/2026 | 108 | 108 |  |  |  | 2026-04-08 | 27/08/2026 | 29/07/2026 | 30/07/2026 | 108 | 108
ADIDAS | 0902983535-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F,G3K | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902983535 JE8969 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 20/07/2026 | M BL FT PT |  | FW26 | 20/07/2026 | 2026-06-08 | 21/07/2026 | 2026-05-08 | 1200 | 1200 |  |  |  | 15/07/2026 | 2026-03-08 | 2026-09-07 | 2026-05-08 | 1200 | 1200
ADIDAS | 0902983568-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G3E | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902983568 JE6346 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/07/2026 | M 3S FT TC PT |  | FW26 | 21/07/2026 | 2026-03-08 | 22/07/2026 | 31/07/2026 | 1201 | 1201 |  |  |  | 16/07/2026 | 29/07/2026 | 18/07/2026 | 22/07/2026 | 1201 | 1201
ADIDAS | 0902983877-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 408 | 2026-05-09 | 408 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983877 LE8181 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-04-09 | 2026-05-09 | 408 | 408 |  |  |  | 27/08/2026 | 2026-02-09 | 13/08/2026 | 2026-05-09 | 408 | 408
ADIDAS | 0902983897-1 LE8187 | BLACK | 105D | S2754MAS513 | 1822 | 2026-05-09 | 1822 | SI | SI29/05/2026 | G3D,G3I,G3J | PANTS | G3 | ok | (22/06/2026) | 04/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 08-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983897 LE8187 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-08 | M SL WV TP PT BLACK |  | SS27 | 2026-06-08 | 2026-05-09 | 2026-12-08 | 2026-04-09 | 1822 | 1822 |  |  |  | 2026-03-08 | 2026-02-09 | 2026-07-08 | 2026-04-09 | 1822 | 1822
ADIDAS | 0902983913-1 LF0718 | BLACK | 105D | S2754MAS512B | 647 | 2026-05-09 | 647 | SA | SA29/05/2026 | G3A | PANTS | G3 | ok | (22/06/2026) | 05/09: ex-fty. T2 Teijin Nantong, material quality issues (creasemark), PI Date 15-Jul, actual receives 28-Jul (100% QC panel). T2 Kahatex, PI Date 28-Jul, actual receives 10-Jul. 1st Art (TC 10 pcs) 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983913 LF0718 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV OH PT BLACK |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 647 | 647 |  |  |  | 27/08/2026 | 2026-02-09 | 14/08/2026 | 2026-04-09 | 647 | 647
ADIDAS | 0902983933-1 LF0723 | BLACK | 105D | S2754MAS511B | 471 | 2026-12-09 | 471 | SI | SI29/05/2026 | G3D,G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983933 LF0723 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 31/08/2026 | M SL WV SHO BLACK |  | SS27 | 31/08/2026 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 471 | 471 |  |  |  | 27/08/2026 | 2026-08-09 | 18/08/2026 | 2026-09-09 | 471 | 471
ADIDAS | 0902983951-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 23/09/2026 | 100 | SA | SA29/05/2026 | G1J | JACKET | G1 | ok | (24/06/2026) | 22/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983951 LG9664 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | W SL WV TT LEGEND IVY S19 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 100 |  | 100 |  |  | 18/09/2026 | 21/09/2026 | 2026-11-09 | 17/09/2026 | 100 | 88 | 12
ADIDAS | 0902983960-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 100 | 2026-12-09 | 100 | SI | SI29/05/2026 | G3E | SHORTS | G3 | ok | (22/06/2026) | 11/09: ex-fty. T2 Teijin Nantong, material quality issues (cresemark), PI Date 15-Jul, actual receives 22-Jul (100% QC panel). T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902983960 LF0725 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-09 | M SL WV SHO OLIVE ONE S27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-02-09 | 2026-12-08 | 2026-03-09 | 100 | 100
ADIDAS | 0902983978-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 24/09: ex-fty. T2 Teijin Nantong, PI Date 15-Jul, actual receives 19-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983978 LG9673 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 24/09/2026 | W SL WV PT LEGEND IVY S19 |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 21/09/2026 | 22/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902983990-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 100 | 30/09/2026 | 100 | SI | SI29/05/2026 | G3D | PANTS | G3 | ok | (22/06/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 15-Jul, actual receives 20-Aug. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902983990 LG9674 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 100 |  | 100 |  |  | 18/09/2026 | 21/09/2026 |  |  | 100 |  | 100
ADIDAS | 0902984005-1 LH3758 | BLACK | 120D | S2754WAS518B | 400 | 30/09/2026 | 400 | SI | SI29/05/2026 | G3H | PANTS | G3 | ok | (22/06/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI date 15-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0902984005 LH3758 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 25/09/2026 | W SL WV BR PT BLACK |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 400 |  | 400 |  |  | 22/09/2026 | 23/09/2026 |  |  | 400 |  | 400
ADIDAS | 0902984019-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G1B | JACKET | G1 | ok | (19/06/2026) | 28/09: ex-fty. T2 Teijin Nantong, PI Date 20-Jun, actual receives 05-Aug (100% QC panel). T2 Kahatex, PI Date 28-Jun, actual receives 04-Jun (PO NT-356). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902984019 LG9666 | 31/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 18/09/2026 | W SL WV TT BLACK |  | SS27 | 18/09/2026 | 22/09/2026 | 16/09/2026 | 19/09/2026 | 300 | 259 | 41 |  | 20 | 15/09/2026 | 18/09/2026 | 31/08/2026 | 19/09/2026 | 300 | 277 | 23 |  | 10
ADIDAS | 0902985687-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P,G2T | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985687 JE6374 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 29/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 2026-06-08 | 2026-02-09 | 1201 | 1201
ADIDAS | 0902985715-1 JE8949 | BLACK/WHITE | 90D | S2554MESS627FT | 1200 | 15/09/2026 | 1200 | SI | SI29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty 804028 | PRINT L1 SUB PROCESS_V3 | 0902985715 JE8949 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-01-09 | M BL FT SWT |  | FW26 | 2026-01-09 | 2026-12-09 | 2026-01-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 28/08/2026 | 2026-09-09 | 29/07/2026 | 2026-03-09 | 1200 | 1200
ADIDAS | 0902985747-1 IN6163 | BLACK/WHITE | 90D | S2554MESS623FT | 1200 | 2026-12-09 | 1200 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | PRINT L1 SUB PROCESS_V3 | 0902985747 IN6163 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 23/07/2026 | M BL FT PT |  | FW26 | 23/07/2026 | 2026-03-08 | 22/07/2026 | 30/07/2026 | 1200 | 1200 |  |  |  | 20/07/2026 | 29/07/2026 | 16/07/2026 | 22/07/2026 | 1200 | 1200
ADIDAS | 0902985818-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1201 | 2026-12-09 | 1201 | AT | AT29/05/2026 | G3C,G3D | PANTS | G3 | ok | (22/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO SUB PROCESS_V1 | 0902985818 JD1881 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/07/2026 | M 3S FT TC PT |  | FW26 | 28/07/2026 | 2026-12-08 | 29/07/2026 | 2026-10-08 | 1201 | 1201 |  |  |  | 23/07/2026 | 2026-07-08 | 20/07/2026 | 2026-01-08 | 1201 | 1201
ADIDAS | 0902985931-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 1201 | 15/09/2026 | 1201 | AT | AT29/05/2026 | G2P | SWEATSHIRT | G2 | ok | (22/06/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902985931 JE6372 | 13/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 28/08/2026 | M 3S FT SWT |  | FW26 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-09-09 | 1201 | 1201 |  |  |  | 24/08/2026 | 2026-09-09 | 15/07/2026 | 18/08/2026 | 1201 | 1201
ADIDAS | 0902986122-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 112 | 2026-07-10 | 112 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902986122 KX3655 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-06-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-06-10 | 2026-06-10 |  |  | 112 |  | 112 |  |  | 2026-02-10 | 2026-02-10 |  |  | 112 |  | 112 |  |  | 30/09/2026 | 30/09/2026 |  |  | 112 |  | 112
ADIDAS | 0902987761-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 540 | 15/10/2026 | 540 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987761 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 540 |  | 540 |  |  | 29/09/2026 | 30/09/2026 |  |  | 540 |  | 540 |  |  | 26/09/2026 | 28/09/2026 |  |  | 540 |  | 540
ADIDAS | 0902987861-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 529 | 15/10/2026 | 529 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987861 KX3655 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 529 |  | 529 |  |  | 29/09/2026 | 30/09/2026 |  |  | 529 |  | 529 |  |  | 26/09/2026 | 28/09/2026 |  |  | 529 |  | 529
ADIDAS | 0902987900-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 30/09/2026 | 300 | AN | AN29/05/2026 | G3G | PANTS | G3 | ok | (19/06/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902987900 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-10-08 | 21/09/2026 | 2026-12-08 | 18/09/2026 | 300 | 259 | 41 |  |  | 2026-05-08 | 17/09/2026 | 2026-10-08 | 16/09/2026 | 300 | 300
ADIDAS | 0902988860-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 231 | 2026-07-10 | 231 | SA | SA29/05/2026 | G3F | PANTS | G3 | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988860 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 231 |  | 231 |  |  | 2026-09-10 | 2026-10-10 |  |  | 231 |  | 231 |  |  | 2026-03-10 | 2026-05-10 |  |  | 231 |  | 231
ADIDAS | 0902988896-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 481 | 15/09/2026 | 481 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 15/09: ex-fty (STOOD) 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988896 KC8152 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 14/09/2026 | 2026-05-09 | 15/09/2026 | 481 | 481 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-04-09 | 2026-11-09 | 481 | 481 |  |  |  | 27/08/2026 | 2026-04-09 | 2026-04-09 | 2026-09-09 | 481 | 481
ADIDAS | 0902990760-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 144 | 23/10/2026 | 144 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990760 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 16/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 144 |  | 144 |  |  | 13/10/2026 | 14/10/2026 |  |  | 144 |  | 144 |  |  | 2026-10-10 | 2026-12-10 |  |  | 144 |  | 144
ADIDAS | 0902990885-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 110 | 15/10/2026 | 110 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990885 KX3655 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 110 |  | 110 |  |  | 29/09/2026 | 29/09/2026 |  |  | 110 |  | 110 |  |  | 26/09/2026 | 26/09/2026 |  |  | 110 |  | 110
ADIDAS | 0902993705-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 368 | 2026-12-09 | 368 | AN | AN29/05/2026 | G3A | PANTS | G3 | ok | (19/06/2026) | 10/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993705 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 2026-11-08 | 2026-05-08 | 2026-06-08 | 368 | 368 |  |  |  | 30/07/2026 | 2026-06-08 | 27/07/2026 | 19/08/2026 | 368 | 368
ADIDAS | 0902993759-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 405 | 23/10/2026 | 405 | AN | AN29/05/2026 | G3F,G3G | PANTS | G3 | ok | (19/06/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0902993759 KV7863 | 13/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-05-09 | 17/09/2026 | 405 | 405 |  |  |  | 2026-01-09 | 2026-09-09 | 2026-10-08 | 2026-10-09 | 405 | 405
ADIDAS | 0902993780-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 600 | 2026-05-09 | 600 | AN | AN29/05/2026 | G3H | PANTS | G3 | ok | ok | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 31-May, actual receives 09-Jun. T2 Kahatex, PI Date 28-Jun, actual receives 03-Jun (PO NT-347). 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902993780 KV7863 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-03-08 | 13/08/2026 | 2026-03-08 | 2026-11-08 | 600 | 600 |  |  |  | 29/07/2026 | 2026-10-08 | 28/07/2026 | 2026-10-08 | 600 | 600
ADIDAS | 0902997868-1 KB5960 | WHITE | 120D | S2608MR0900A | 524 | 15/10/2026 | 524 | SA | SA29/05/2026 | G2H | T-SHIRT | G2 | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902997868 KB5960 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-03-10 | Run Ess Tee M |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 524 |  | 524 |  |  | 30/09/2026 | 2026-01-10 | 2026-05-08 | 27/08/2026 | 524 | 524 |  |  |  | 28/09/2026 | 29/09/2026 | 2026-01-08 | 26/08/2026 | 524 | 524
ADIDAS | 0902997893-1 KB5960 | WHITE | 120D | S2608MR0900A | 500 | 31/10/2026 | 500 | SA | SA29/05/2026 | G2G | T-SHIRT | G2 | ok | (22/06/2026) | 516260 | HT+PAD SUB PROCESS_V3 | 0902997893 KB5960 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 500 |  | 500 |  |  | 19/10/2026 | 20/10/2026 | 2026-02-09 | 16/09/2026 | 500 | 500 |  |  |  | 16/10/2026 | 17/10/2026 | 2026-02-09 | 2026-12-09 | 500 | 500
ADIDAS | 0903017607-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 1100 | 2026-05-09 | 1100 | SA | SA29/05/2026 | G1B | JACKET | G1 | ok |  | 05/09: ex-fty. T2 Kahatex, PI Date 28-Jun, actual receives 07-Jul (PO NT-353). T2 Formosa, PI Date 27-Jun, actual receives 07-Jul T2 Libolon, PI Date 23-Jun, actual receives 18-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903017607 KW2909 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV WB |  | SS27 | 29/07/2026 | 31/08/2026 | 29/07/2026 | 31/08/2026 | 1100 | 1100 |  |  |  | 24/07/2026 | 27/08/2026 | 22/07/2026 | 2026-01-09 | 1100 | 1100
ADIDAS | 0903031703-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 313 | 2026-05-09 | 313 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031703 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 313 | 313 |  |  |  | 29/07/2026 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 313 | 313
ADIDAS | 0903031747-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 352 | 2026-05-09 | 352 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | ok | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031747 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/07/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 29/07/2026 | 14/08/2026 | 29/07/2026 | 14/08/2026 | 352 | 352 |  |  |  | 24/07/2026 | 2026-11-08 | 27/07/2026 | 13/08/2026 | 352 | 352
ADIDAS | 0903031828-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 1176 | 23/09/2026 | 1176 | AN | AN12/06/2026 | G1E | T-SHIRT | G1 | ok | (02/07/2026) | 22/09: ex-fty. T2 Libolon, PI Date 29-Aug, actual receives 30-Jul. T2 Fu Hsun, actual receives 14-Jan (PO 25063168). 600000 | HT SUB PROCESS_V1 | 0903031828 IT1824 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | ADIZERO E TEE |  | SS27-YTI | 23/09/2026 | 24/09/2026 |  |  | 1176 |  | 1176 |  |  | 21/09/2026 | 22/09/2026 | 2026-09-09 | 19/09/2026 | 1176 | 1167 | 9 |  | 6 | 19/09/2026 | 21/09/2026 | 2026-09-09 | 19/09/2026 | 1176 | 1168 | 8 |  | 6
ADIDAS | 0903031894-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 7560 | 2026-05-09 | 7560 | AN | AN12/06/2026 | G3A,G3B,G3C,G3E,G3F,G3G,G3H,G3J | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jul. T2 Libolon, PI Date 06-Jul, actual receives 22-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903031894 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-04-08 | 19/08/2026 | 7560 | 7560 |  |  |  | 29/07/2026 | 18/08/2026 | 30/07/2026 | 20/08/2026 | 7560 | 7560
ADIDAS | 0903031957-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 540 | 2026-12-09 | 540 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903031957 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 540 | 540 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 18/08/2026 | 540 | 540
ADIDAS | 0903032010-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | ok | 05/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 17-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903032010 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-10-08 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 332 | 332 |  |  |  | 2026-05-08 | 13/08/2026 | 2026-11-08 | 18/08/2026 | 332 | 332
ADIDAS | 0903037254-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037254 LH3761 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903037304-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 500 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903037304 LH3759 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903042722-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 344 | 2026-09-09 | 344 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903042722 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 344 | 344 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-07-09 | 344 | 344
ADIDAS | 0903042749-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 300 | 30/09/2026 | 300 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903042749 LE5389 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-02-10 | 2026-11-08 | 26/08/2026 | 300 | 300
ADIDAS | 0903043064-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903043064 LF0729 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 300 |  | 300 |  |  | 27/10/2026 | 29/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903043439-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 15/10/2026 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903043439 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 4002 |  | 4002 |  |  | 2026-01-10 | 2026-05-10 |  |  | 4002 |  | 4002
ADIDAS | 0903043644-1 KB5965 | BLACK | 120D | S2608MR0900A | 1380 | 30/09/2026 | 1380 | SA | SA12/06/2026 | G2D | T-SHIRT | G2 | ok | (04/07/2026) | 24/09: ex-fty. DRC 0090-early shipment customer (BTP_23_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903043644 KB5965 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | Run Ess Tee M |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 1380 |  | 1380 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1380 |  | 1380 |  |  | 23/09/2026 | 24/09/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903045739-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 984 | 2026-12-09 | 984 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty. DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903045739 KB5960 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | Run Ess Tee M |  | SS27-TI | 2026-09-09 | 2026-11-09 | 2026-09-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-08-09 | 2026-10-09 | 984 | 984 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-08-09 | 2026-10-09 | 984 | 984
ADIDAS | 0903045869-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 2026-07-10 | 12000 | AN | AN12/06/2026 | G3A,G3B,G3C | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045869 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 29/09/2026 | 2026-08-10 |  |  | 12000 |  | 12000 |  |  | 25/09/2026 | 2026-05-10 | 28/07/2026 | 28/07/2026 | 12000 | 1 | 11999
ADIDAS | 0903045909-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4002 | 2026-07-10 | 4002 | SA | SA12/06/2026 | G2E | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045909 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 4002 |  | 4002 |  |  | 29/09/2026 | 2026-01-10 |  |  | 4002 |  | 4002
ADIDAS | 0903046028-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 12000 | 15/10/2026 | 12000 | AN | AN12/06/2026 | G3D,G3E,G3F | PANTS | G3 | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046028 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27 | 19/10/2026 | 30/10/2026 |  |  | 12000 |  | 12000 |  |  | 15/10/2026 | 27/10/2026 |  |  | 12000 |  | 12000
ADIDAS | 0903046531-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 301 | 30/09/2026 | 301 | SI | SI12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046531 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 301 |  | 301 |  |  | 29/09/2026 | 29/09/2026 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903046557-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 121 | 2026-12-09 | 121 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046557 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 121 | 121 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 31/08/2026 | 121 | 121
ADIDAS | 0903046577-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 414 | 2026-12-09 | 414 | SI | SI12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903046577 KS1836 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-04-09 | ARCH SEAL TEE |  | SS27 | 2026-04-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 414 | 414 |  |  |  | 2026-01-09 | 2026-09-09 | 29/07/2026 | 2026-10-09 | 414 | 414
ADIDAS | 0903046607-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 360 | 2026-09-09 | 360 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046607 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-07-08 | 14/08/2026 | 360 | 360 |  |  |  | 2026-04-08 | 2026-11-08 | 31/07/2026 | 14/08/2026 | 360 | 360
ADIDAS | 0903046624-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 2083 | 23/09/2026 | 2083 | AN | AN12/06/2026 | G1H,G1L | JACKET | G1 | ok | (03/07/2026) | 21/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 18-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903046624 KZ3208 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-07-08 | 23/09/2026 | 2026-10-08 | 17/09/2026 | 2083 | 2027 | 56 |  |  | 2026-04-08 | 19/09/2026 | 28/07/2026 | 2026-12-09 | 2083 | 2071 | 12
ADIDAS | 0903046936-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 200 | 30/09/2026 | 200 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route. DRC 0010-hold shipment customer (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 1st Art (TC 10 pcs) 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046936 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 15/08/2026 | 15/08/2026 | 200 | 200
ADIDAS | 0903046980-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 286 | 31/10/2026 | 286 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512110 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903046980 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 2026-07-09 | 2026-05-09 | 2026-10-09 | 286 | 286 |  |  |  | 2026-01-09 | 2026-03-09 | 2026-10-08 | 24/08/2026 | 286 | 286
ADIDAS | 0903046982-1 KB5965 | BLACK | 120D | S2608MR0900A | 1010 | 30/09/2026 | 1010 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903046982 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 1010 |  | 1010 |  |  | 24/09/2026 | 25/09/2026 | 17/09/2026 | 19/09/2026 | 1010 | 752 | 258 |  | 24 | 22/09/2026 | 23/09/2026 | 16/09/2026 | 19/09/2026 | 1010 | 763 | 247 |  | 4
ADIDAS | 0903047029-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3E,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_02_07_2026 EARLY HOLD SHIPMENT). 516240 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903047029 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-11-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 300 | 300 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-12-09 | 15/09/2026 | 300 | 300 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-11-09 | 14/09/2026 | 300 | 300
ADIDAS | 0903047055-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 369 | 31/10/2026 | 369 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903047055 KX3654 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA | 17/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 369 |  | 369 |  |  | 14/10/2026 | 15/10/2026 |  |  | 369 |  | 369 |  |  | 2026-12-10 | 13/10/2026 |  |  | 369 |  | 369
ADIDAS | 0903047077-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 350 | 2026-07-10 | 350 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516461 | HT+PAD SUB PROCESS_V3 | 0903047077 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 29/09/2026 | 29/09/2026 |  |  | 350 |  | 350 |  |  | 25/09/2026 | 25/09/2026 | 18/09/2026 | 18/09/2026 | 350 | 348 | 2 |  |  | 23/09/2026 | 23/09/2026 | 17/09/2026 | 17/09/2026 | 350 | 348 | 2
ADIDAS | 0903047104-1 KB5960 | WHITE | 120D | S2608MR0900A | 634 | 30/09/2026 | 634 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 29/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903047104 KB5960 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee M |  | SS27-TI | 29/09/2026 | 29/09/2026 |  |  | 634 |  | 634 |  |  | 25/09/2026 | 25/09/2026 | 2026-05-08 | 17/09/2026 | 634 | 633 | 1 |  |  | 23/09/2026 | 23/09/2026 | 2026-01-08 | 16/09/2026 | 634 | 634
ADIDAS | 0903047150-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 301 | 23/09/2026 | 301 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 22/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516433 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047150 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 15/09/2026 | 23/09/2026 | 17/09/2026 | 18/09/2026 | 301 | 233 | 68 |  |  | 2026-11-09 | 19/09/2026 | 28/08/2026 | 16/09/2026 | 301 | 232 | 69
ADIDAS | 0903047167-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 468 | 23/10/2026 | 468 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047167 KY6616 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 468 |  | 468 |  |  | 26/10/2026 | 27/10/2026 |  |  | 468 |  | 468
ADIDAS | 0903047185-1 JZ7808 | BLACK | 120D | S2608WR0900 | 803 | 15/10/2026 | 803 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047185 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-08-10 | Run Ess Tee W BLACK |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 803 |  | 803 |  |  | 2026-05-10 | 2026-06-10 |  |  | 803 |  | 803 |  |  | 2026-02-10 | 2026-03-10 |  |  | 803 |  | 803
ADIDAS | 0903047214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 2411 | 15/10/2026 | 2411 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047214 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-05-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-05-10 | 2026-07-10 |  |  | 2411 |  | 2411 |  |  | 2026-01-10 | 2026-03-10 |  |  | 2411 |  | 2411 |  |  | 29/09/2026 | 2026-01-10 |  |  | 2411 |  | 2411
ADIDAS | 0903047216-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 431 | 30/09/2026 | 431 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047216 KY6616 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 431 |  | 431 |  |  | 22/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 431 | 60 | 371
ADIDAS | 0903047241-1 KB5965 | BLACK | 120D | S2608MR0900A | 4136 | 15/10/2026 | 4136 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903047241 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-05-10 | Run Ess Tee M |  | SS27-TI | 2026-05-10 | 2026-08-10 |  |  | 4136 |  | 4136 |  |  | 2026-01-10 | 2026-05-10 |  |  | 4136 |  | 4136 |  |  | 29/09/2026 | 2026-02-10 |  |  | 4136 |  | 4136
ADIDAS | 0903047261-1 LG9675 | BLACK | 120D | S2754WAS513C | 301 | 15/10/2026 | 301 | SI | SI12/06/2026 | G3G | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047261 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | W SL WV PT BLACK |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 301 |  | 301 |  |  | 16/10/2026 | 17/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903047275-1 LE8201 | BLACK | 90D | F2606LHLF103FY-MTF | 14000 | 15/09/2026 | 14000 | AN | AN12/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047275 LE8201 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-07-09 | 15/09/2026 | 14000 | 14000 |  |  |  | 2026-02-09 | 2026-11-09 | 2026-01-09 | 15/09/2026 | 14000 | 14000
ADIDAS | 0903047297-1 LG9675 | BLACK | 120D | S2754WAS513C | 348 | 23/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047297 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047299-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2O | T-SHIRT | G2 | ok | (02/07/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047299 LE8208 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-09 | LFC 3 F JSYL SE BLACK |  | FW26-FJ | 2026-05-09 | 15/09/2026 | 2026-05-09 | 14/09/2026 | 3500 | 3500 |  |  |  | 2026-02-09 | 2026-11-09 | 2026-02-09 | 14/09/2026 | 3500 | 3500
ADIDAS | 0903047330-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1R | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 20 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047330 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-02-09 | 15/09/2026 | 2026-07-09 | 14/09/2026 | 15000 | 15000 |  |  |  | 29/08/2026 | 2026-11-09 | 27/08/2026 | 14/09/2026 | 15000 | 15000
ADIDAS | 0903047342-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 3500 | 15/09/2026 | 3500 | SA | SA12/06/2026 | G2L,G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047342 LE8210 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3500 | 3500 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-05-09 | 15/09/2026 | 3500 | 3500
ADIDAS | 0903047344-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047344 KX0123 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | M ADI RETRO T WHITE |  | SS27 | 2026-06-11 | 2026-06-11 |  |  | 200 |  | 200 |  |  | 2026-03-11 | 2026-03-11 |  |  | 200 |  | 200
ADIDAS | 0903047363-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 3678 | 2026-12-09 | 3678 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 11/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047363 LE8194 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL HFY JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 3678 | 3678 |  |  |  | 27/08/2026 | 2026-05-09 | 20/08/2026 | 2026-04-09 | 3678 | 3678
ADIDAS | 0903047367-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 200 | 23/10/2026 | 200 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). 512107 | PRINT L3+PAD SUB PROCESS_V3 | 0903047367 LC8882 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-11 | M ADI RETRO T BLACK |  | SS27 | 2026-06-11 | 2026-06-11 |  |  | 200 |  | 200 |  |  | 2026-03-11 | 2026-03-11 |  |  | 200 |  | 200
ADIDAS | 0903047388-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA12/06/2026 | G1A,G1G,G1I,G1M,G1O,G1Q,G1R,G2M | T-SHIRT | G1,G2 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047388 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-03-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 15000 | 15000 |  |  |  | 31/08/2026 | 2026-11-09 | 2026-05-09 | 16/09/2026 | 15000 | 15000
ADIDAS | 0903047414-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 5500 | 15/09/2026 | 5500 | SA | SA12/06/2026 | G1G | T-SHIRT | G1 | ok | (04/07/2026) | 14/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903047414 LE8202 | 28/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 5500 | 5500 |  |  |  | 2026-05-09 | 2026-11-09 | 31/08/2026 | 16/09/2026 | 5500 | 5500
ADIDAS | 0903047417-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 121 | 15/10/2026 | 121 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047417 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 121 |  | 121 |  |  | 2026-01-10 | 2026-02-10 |  |  | 121 |  | 121
ADIDAS | 0903047441-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 249 | 30/09/2026 | 249 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 28-May (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903047441 KZ3198 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 2026-12-09 | 16/09/2026 | 2026-12-09 | 15/09/2026 | 249 | 249 |  |  |  | 2026-09-09 | 2026-12-09 | 2026-11-08 | 26/08/2026 | 249 | 249
ADIDAS | 0903047468-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 150 | 30/09/2026 | 150 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047468 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-12-09 | 16/09/2026 | 2026-12-09 | 16/09/2026 | 150 | 150 |  |  |  | 2026-09-09 | 2026-12-09 | 22/08/2026 | 16/09/2026 | 150 | 147 | 3
ADIDAS | 0903047497-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 30/09/2026 | 101 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047497 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 15/09/2026 | 23/09/2026 | 15/09/2026 | 16/09/2026 | 101 | 81 | 20 |  |  | 2026-11-09 | 19/09/2026 | 26/08/2026 | 2026-05-09 | 101 | 85 | 16
ADIDAS | 0903047521-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047521 LE4307 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-01-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903048420-1 KB5965 | BLACK | 120D | S2608MR0900A | 456 | 30/09/2026 | 456 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048420 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | Run Ess Tee M |  | SS27-TI | 26/09/2026 | 28/09/2026 |  |  | 456 |  | 456 |  |  | 23/09/2026 | 24/09/2026 | 17/09/2026 | 18/09/2026 | 456 | 447 | 9 |  |  | 21/09/2026 | 22/09/2026 | 16/09/2026 | 17/09/2026 | 456 | 447 | 9
ADIDAS | 0903048444-1 JZ7808 | BLACK | 120D | S2608WR0900 | 420 | 15/10/2026 | 420 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516461 | HT+PAD SUB PROCESS_V3 | 0903048444 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 420 |  | 420 |  |  | 26/09/2026 | 26/09/2026 |  |  | 420 |  | 420 |  |  | 24/09/2026 | 24/09/2026 |  |  | 420 |  | 420
ADIDAS | 0903048469-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1100 | 15/10/2026 | 1100 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903048469 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 30/09/2026 | 2026-01-10 |  |  | 1100 |  | 1100 |  |  | 26/09/2026 | 28/09/2026 | 17/09/2026 | 19/09/2026 | 1100 | 1063 | 37 |  | 115 | 24/09/2026 | 25/09/2026 | 17/09/2026 | 18/09/2026 | 1100 | 1072 | 28
ADIDAS | 0903048496-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1018 | 23/10/2026 | 1018 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok |  | 804028 | HT+PAD SUB PROCESS_V3 | 0903048496 KX3650 | 2026-11-09 | KAHATEX CIJERAH | JAPAN | SEA | 15/10/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 1018 |  | 1018 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1018 |  | 1018 |  |  | 2026-09-10 | 2026-10-10 | 17/09/2026 | 17/09/2026 | 1018 | 563 | 455
ADIDAS | 0903048502-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1004 | 2026-07-10 | 1004 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516462 | HT+PAD SUB PROCESS_V3 | 0903048502 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-07-10 | 2026-07-10 |  |  | 1004 |  | 1004 |  |  | 2026-03-10 | 2026-03-10 | 19/09/2026 | 19/09/2026 | 1004 | 667 | 337 |  | 667 | 2026-01-10 | 2026-01-10 | 19/09/2026 | 19/09/2026 | 1004 | 667 | 337 |  | 667
ADIDAS | 0903048525-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 395 | 31/10/2026 | 395 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048525 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/10/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 395 |  | 395 |  |  | 24/10/2026 | 26/10/2026 | 20/08/2026 | 20/08/2026 | 395 | 26 | 369
ADIDAS | 0903048540-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 409 | 23/10/2026 | 409 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048540 LD0287 | 2026-11-09 | KAHATEX CIJERAH | JAPAN | SEA | 13/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 13/10/2026 | 13/10/2026 | 19/09/2026 | 19/09/2026 | 409 | 80 | 329 |  | 80 | 2026-09-10 | 2026-09-10 | 2026-08-08 | 29/08/2026 | 409 | 409 |  |  |  | 2026-07-10 | 2026-07-10 | 2026-07-08 | 28/08/2026 | 409 | 409
ADIDAS | 0903048604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/10/2026 | 300 | AN | AN12/06/2026 | G3F,G3G | PANTS | G3 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 512107 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903048604 KV7863 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-09 | 16/09/2026 | 2026-05-09 | 15/09/2026 | 300 | 300 |  |  |  | 2026-01-09 | 2026-12-09 | 2026-10-08 | 13/08/2026 | 300 | 300
ADIDAS | 0903048634-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 151 | 23/10/2026 | 151 | AN | AN12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048634 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 151 |  | 151 |  |  | 2026-05-11 | 2026-11-11 |  |  | 151 |  | 151
ADIDAS | 0903048647-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 434 | 2026-09-09 | 434 | AN | AN12/06/2026 | G1H,G1L | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 14-Aug. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048647 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 21/08/2026 | 2026-08-09 | 24/08/2026 | 2026-05-09 | 434 | 434 |  |  |  | 18/08/2026 | 2026-04-09 | 18/08/2026 | 2026-07-09 | 434 | 434
ADIDAS | 0903049164-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 31/10/2026 | 408 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903049164 KB5965 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | Run Ess Tee M |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 408 |  | 408 |  |  | 15/10/2026 | 16/10/2026 |  |  | 408 |  | 408 |  |  | 13/10/2026 | 14/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903049187-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 376 | 15/10/2026 | 376 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516462 | HT+PAD SUB PROCESS_V3 | 0903049187 KX3654 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 376 |  | 376 |  |  | 2026-07-10 | 2026-08-10 | 18/09/2026 | 18/09/2026 | 376 | 209 | 167 |  |  | 2026-05-10 | 2026-06-10 | 18/09/2026 | 18/09/2026 | 376 | 213 | 163
ADIDAS | 0903049383-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (09/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049383 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | PIZZA TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-01-09 | 2026-08-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-07-08 | 2026-07-09 | 450 | 450
ADIDAS | 0903049419-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 341 | 2026-09-09 | 341 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 08/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049419 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M TATTOO SPRT T BLACK |  | SS27 | 2026-03-09 | 2026-09-09 | 2026-04-09 | 2026-08-09 | 341 | 341 |  |  |  | 31/08/2026 | 2026-05-09 | 24/08/2026 | 2026-07-09 | 341 | 341
ADIDAS | 0903049448-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 301 | 30/09/2026 | 301 | AN | AN12/06/2026 | G2N | T-SHIRT | G2 | ok | (02/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049448 KS2152 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | LA PALMS TEE |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-02-10 | 2026-02-10 |  |  | 301 |  | 301
ADIDAS | 0903049482-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 450 | 31/10/2026 | 450 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049482 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | M TATTOO SPRT T BLACK |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 450 |  | 450 |  |  | 15/10/2026 | 16/10/2026 |  |  | 450 |  | 450
ADIDAS | 0903049516-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 301 | 26/09/2026 | 301 | AN | AN12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049516 KR2020 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | PDX HBR TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 301 | 301 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 2026-10-08 | 301 | 301
ADIDAS | 0903049584-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2B | T-SHIRT | G2 | ok | (09/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049584 KS2145 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PIZZA TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 17/09/2026 | 18/09/2026 | 2026-07-08 | 17/09/2026 | 301 | 301
ADIDAS | 0903049615-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 301 | 30/09/2026 | 301 | SA | SA12/06/2026 | G2B | T-SHIRT | G2 | ok | (04/07/2026) | 24/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903049615 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | HOU COLL TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 301 |  | 301 |  |  | 17/09/2026 | 18/09/2026 | 2026-10-08 | 2026-07-09 | 301 | 301
ADIDAS | 0903050997-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 558 | 30/09/2026 | 558 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 28/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 1st Art (TC 12 pcs) 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903050997 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 558 | 214 | 344 |  | 214 | 17/09/2026 | 18/09/2026 | 2026-04-09 | 18/09/2026 | 558 | 528 | 30
ADIDAS | 0903051027-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 236 | 30/09/2026 | 236 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903051027 LE0358 | 2026-11-09 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 236 | 232 | 4 |  | 232 | 17/09/2026 | 18/09/2026 | 2026-04-09 | 16/09/2026 | 236 | 136 | 100
ADIDAS | 0903051176-1 KS2150 | DARK BLUE | 60D | F26KCHOUGFX100 | 450 | 2026-09-09 | 450 | SA | SA12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 08/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903051176 KS2150 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | HOU COLL TEE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 2026-08-08 | 2026-12-09 | 450 | 450
ADIDAS | 0903051428-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/09/2026 | 18 | SA | SA12/06/2026 | G3J | SHORTS | G3 | ok |  | 14/09: ex-fty. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. T2 Formosa, PI Date 20-Jul, actual receives 07-Jul. 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903051428 KZ0925 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 18 | 18 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-12-09 | 2026-12-09 | 18 | 18
ADIDAS | 0903051498-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 40 | 15/10/2026 | 40 | AN | AN12/06/2026 | G2L | T-SHIRT | G2 | ok | (03/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051498 LD0283 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 40 |  | 40 |  |  | 24/09/2026 | 25/09/2026 |  |  | 40 |  | 40 |  |  | 22/09/2026 | 23/09/2026 |  |  | 40 |  | 40
ADIDAS | 0903051523-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051523 KX3651 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 2026-02-10 | 2026-03-10 |  |  | 50 |  | 50 |  |  | 29/09/2026 | 30/09/2026 | 2026-04-08 | 2026-08-08 | 50 | 50 |  |  |  | 26/09/2026 | 28/09/2026 | 2026-01-08 | 2026-07-08 | 50 | 50
ADIDAS | 0903051563-1 LD0284 | LIME TINT S27 | 120D | S2608WR0900 | 40 | 15/10/2026 | 40 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903051563 LD0284 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee W LIME TINT S27 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 40 |  | 40 |  |  | 24/09/2026 | 24/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-08-08 | 2026-12-08 | 40 | 40
ADIDAS | 0903051592-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 18 | 30/09/2026 | 18 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903051592 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 18 |  | 18 |  |  | 23/09/2026 | 25/09/2026 |  |  | 18 |  | 18
ADIDAS | 0903051620-1 KA0227 | MEDIUM GREY HEATHER | 120D | S2608WR0900 | 50 | 15/10/2026 | 50 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 1st Art (TC 10 pcs) 600000 | HT+PAD SUB PROCESS_V3 | 0903051620 KA0227 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | Run Ess Tee W MEDIUM GREY HEATHER |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 50 |  | 50 |  |  | 24/09/2026 | 24/09/2026 | 2026-08-08 | 2026-12-08 | 50 | 50 |  |  |  | 22/09/2026 | 22/09/2026 | 2026-08-08 | 2026-11-08 | 50 | 50
ADIDAS | 0903052489-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 379 | 2026-09-09 | 379 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052489 KW2909 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | W 3S WV WB BLACK/WHITE |  | SS27 | 2026-03-08 | 2026-08-09 | 2026-04-08 | 2026-07-09 | 379 | 379 |  |  |  | 29/07/2026 | 2026-04-09 | 29/07/2026 | 31/08/2026 | 379 | 379
ADIDAS | 0903052531-1 LE5038 | BLACK | 105D | S2750MTR104A | 387 | 15/10/2026 | 387 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | (NYK warehouse). T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 1st Art (TC 10 pcs) 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903052531 LE5038 | 2026-11-09 | KAHATEX CIJERAH | INDONESIA | SEA | 28/10/2026 | D4T AOP GFX T BLACK |  | SS27-TI | 28/10/2026 | 28/10/2026 |  |  | 387 |  | 387 |  |  | 24/10/2026 | 24/10/2026 |  |  | 387 |  | 387 |  |  | 23/10/2026 | 23/10/2026 |  |  | 387 |  | 387
ADIDAS | 0903052598-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 135 | 2026-05-09 | 135 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 05/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903052598 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-08 | BIG APPLE TEE |  | SS27 | 2026-03-08 | 2026-07-08 | 2026-05-08 | 2026-06-08 | 135 | 135 |  |  |  | 29/07/2026 | 2026-04-08 | 28/07/2026 | 31/07/2026 | 135 | 135
ADIDAS | 0903052654-1 KB5960 | WHITE | 120D | S2608MR0900A | 459 | 15/10/2026 | 459 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | HT+PAD SUB PROCESS_V3 | 0903052654 KB5960 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | Run Ess Tee M |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 459 |  | 459 |  |  | 30/09/2026 | 2026-01-10 | 2026-05-08 | 2026-07-08 | 459 | 459 |  |  |  | 28/09/2026 | 29/09/2026 | 2026-01-08 | 2026-07-08 | 459 | 459
ADIDAS | 0903052671-1 KB5965 | BLACK | 120D | S2608MR0900A | 282 | 15/10/2026 | 282 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903052671 KB5965 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | Run Ess Tee M |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 282 |  | 282 |  |  | 16/10/2026 | 17/10/2026 |  |  | 282 |  | 282 |  |  | 14/10/2026 | 15/10/2026 |  |  | 282 |  | 282
ADIDAS | 0903052708-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 365 | 19/09/2026 | 365 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052708 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-07-09 | 2026-11-09 | 365 | 365 |  |  |  | 2026-03-09 | 2026-09-09 | 20/08/2026 | 2026-10-09 | 365 | 365
ADIDAS | 0903052721-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 459 | 15/09/2026 | 459 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903052721 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 459 | 459 |  |  |  | 27/08/2026 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 459 | 459
ADIDAS | 0903052745-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 305 | 2026-05-09 | 305 | AN | AN12/06/2026 | G3A,G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 02-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052745 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-03-08 | 21/08/2026 | 2026-05-08 | 18/08/2026 | 305 | 305 |  |  |  | 29/07/2026 | 18/08/2026 | 2026-03-08 | 14/08/2026 | 305 | 305
ADIDAS | 0903052755-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 633 | 30/09/2026 | 633 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903052755 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-07-09 | 21/09/2026 | 2026-07-09 | 18/09/2026 | 633 | 633 |  |  |  | 2026-03-09 | 17/09/2026 | 20/08/2026 | 17/09/2026 | 633 | 633
ADIDAS | 0903052784-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 390 | 2026-07-10 | 390 | AN | AN12/06/2026 | G3C,G3F | PANTS | G3 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903052784 KZ3202 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 26/08/2026 | 21/09/2026 | 27/08/2026 | 17/09/2026 | 390 | 390 |  |  |  | 20/08/2026 | 17/09/2026 | 2026-06-08 | 16/09/2026 | 390 | 390
ADIDAS | 0903052813-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G2P | T-SHIRT | G2 | ok | (03/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903052813 LD0288 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 25/09/2026 | 25/09/2026 | 18/09/2026 | 19/09/2026 | 300 | 290 | 10 |  | 232 | 23/09/2026 | 23/09/2026 | 17/09/2026 | 19/09/2026 | 300 | 290 | 10 |  | 232
ADIDAS | 0903053034-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 1170 | 15/09/2026 | 1170 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903053034 KD4899 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 2026-01-09 | 2026-12-09 | 1170 | 1170 |  |  |  | 27/08/2026 | 2026-10-09 | 2026-01-09 | 2026-05-09 | 1170 | 1170
ADIDAS | 0903053050-1 KH0396 | DARK BLUE | 90D | F26SPRMGFX910-MTF | 641 | 2026-12-09 | 641 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (02/07/2026) | 10/09: ex-fty 516318 | PRINT L2+PAD+PPH L1 SUB PROCESS_V3 | 0903053050 KH0396 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | M HIGHLITE T1 |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-09-09 | 2026-10-09 | 641 | 641 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-10-09 | 641 | 641
ADIDAS | 0903053086-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 912 | 2026-12-09 | 912 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 10/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053086 KF2398 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | M SL WV TT |  | FW26 | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-02-09 | 912 | 912 |  |  |  | 27/08/2026 | 2026-04-09 | 22/08/2026 | 2026-09-09 | 912 | 912
ADIDAS | 0903053111-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 5386 | 2026-12-09 | 5386 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053111 JN1956 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | W 3S FT QZ HD |  | SS27 | 28/08/2026 | 2026-12-09 | 31/08/2026 | 2026-10-09 | 5386 | 5386 |  |  |  | 24/08/2026 | 2026-09-09 | 24/08/2026 | 2026-09-09 | 5386 | 5386
ADIDAS | 0903053136-1 KD4899 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS605FT-MTF | 780 | 15/09/2026 | 780 | AN | AN12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 14/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903053136 KD4899 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27 | 31/08/2026 | 14/09/2026 | 31/08/2026 | 2026-12-09 | 780 | 780 |  |  |  | 27/08/2026 | 2026-10-09 | 23/07/2026 | 2026-03-09 | 780 | 780
ADIDAS | 0903053462-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 603 | 2026-05-09 | 603 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 23-Jun. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903053462 KZ3205 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-08 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-04-08 | 14/08/2026 | 603 | 603 |  |  |  | 30/07/2026 | 2026-11-08 | 30/07/2026 | 2026-07-09 | 603 | 603
ADIDAS | 0903053919-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 782 | 2026-09-09 | 782 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (02/07/2026) | 08/09: ex-fty 630001 | HT+PAD SUB PROCESS_V3 | 0903053919 KE8424 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-09 | Run Ess LS M BLACK |  | SS27-TI | 2026-05-09 | 2026-09-09 | 2026-08-09 | 2026-08-09 | 782 | 782 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-05-09 | 2026-08-09 | 782 | 782 |  |  |  | 31/08/2026 | 2026-03-09 | 2026-04-09 | 2026-08-09 | 782 | 782
ADIDAS | 0903054030-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 468 | 2026-05-09 | 468 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903054030 KX0123 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T WHITE |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 468 | 468 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-01-08 | 2026-02-09 | 468 | 468
ADIDAS | 0903054066-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 410 | 2026-05-09 | 410 | AN | AN12/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 05/09: ex-fty 980004 | PRINT L3+PAD SUB PROCESS_V3 | 0903054066 LC8882 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 14/08/2026 | M ADI RETRO T BLACK |  | SS27 | 14/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 410 | 410 |  |  |  | 2026-11-08 | 27/08/2026 | 2026-05-08 | 31/08/2026 | 410 | 410
ADIDAS | 0903054127-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 408 | 2026-07-10 | 408 | SA | SA12/06/2026 | G3K | SHORTS | G3 | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-Jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054127 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-06-10 | W 3S WV SHO 74 WHITE/BLACK |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 408 |  | 408 |  |  | 2026-02-10 | 2026-03-10 |  |  | 408 |  | 408
ADIDAS | 0903054613-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1450 | 15/09/2026 | 1450 | SA | SA12/06/2026 | G1A | T-SHIRT | G1 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903054613 LE8202 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-12-09 | LFC 3 F JSY SE |  | FW26-FJ | 2026-12-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1450 | 1450 |  |  |  | 2026-09-09 | 2026-11-09 | 2026-04-09 | 17/09/2026 | 1450 | 1450
ADIDAS | 0903054711-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 508 | 15/10/2026 | 508 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054711 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 508 |  | 508 |  |  | 30/09/2026 | 2026-01-10 |  |  | 508 |  | 508 |  |  | 28/09/2026 | 29/09/2026 |  |  | 508 |  | 508
ADIDAS | 0903054732-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 127 | 30/09/2026 | 127 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903054732 LE0358 | 2026-11-09 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 21/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 127 |  | 127 |  |  | 17/09/2026 | 18/09/2026 | 17/09/2026 | 17/09/2026 | 127 | 116 | 11
ADIDAS | 0903054739-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 132 | 15/10/2026 | 132 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0903054739 KX3655 | 2026-11-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 132 |  | 132 |  |  | 29/09/2026 | 29/09/2026 |  |  | 132 |  | 132 |  |  | 26/09/2026 | 26/09/2026 |  |  | 132 |  | 132
ADIDAS | 0903054752-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 290 | 2026-12-09 | 290 | SI | SI12/06/2026 | G3F | PANTS | G3 | ok | (03/07/2026) | 10/09: ex-fty. T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903054752 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/08/2026 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-09-09 | 290 | 290 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-09-09 | 290 | 290
ADIDAS | 0903054797-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 217 | 23/10/2026 | 217 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0903054797 KX3655 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 16/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 217 |  | 217 |  |  | 13/10/2026 | 14/10/2026 |  |  | 217 |  | 217 |  |  | 2026-10-10 | 2026-12-10 |  |  | 217 |  | 217
ADIDAS | 0903054814-1 JZ7808 | BLACK | 120D | S2608WR0900 | 151 | 15/10/2026 | 151 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | (11/08/2026) | (03/07/2026) | 857010 | HT+PAD SUB PROCESS_V3 | 0903054814 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 30/09/2026 | Run Ess Tee W BLACK |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 151 |  | 151 |  |  | 26/09/2026 | 26/09/2026 |  |  | 151 |  | 151 |  |  | 24/09/2026 | 24/09/2026 |  |  | 151 |  | 151
ADIDAS | 0903054844-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1405 | 31/10/2026 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903054844 LG9675 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903054871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2292 | 30/09/2026 | 2292 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty 857010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903054871 KC8152 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 22/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 22/09/2026 | 25/09/2026 |  |  | 2292 |  | 2292 |  |  | 18/09/2026 | 22/09/2026 | 15/09/2026 | 19/09/2026 | 2292 | 1812 | 480 |  | 488 | 2026-12-09 | 16/09/2026 | 2026-08-09 | 18/09/2026 | 2292 | 2212 | 80
ADIDAS | 0903055171-1 KF2398 | KHAKI SIX F26/BLACK | 90D | F2554MESS712WV-MTF | 607 | 15/09/2026 | 607 | AN | AN12/06/2026 | G1C | JACKET | G1 | ok | (04/07/2026) | 14/09: ex-fty. T2 Libolon, actual receives 03-Jan (PO 25063151). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055171 KF2398 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/07/2026 | M SL WV TT |  | FW26 | 20/07/2026 | 13/08/2026 | 22/07/2026 | 14/08/2026 | 607 | 607 |  |  |  | 15/07/2026 | 2026-10-08 | 21/07/2026 | 29/07/2026 | 607 | 607
ADIDAS | 0903055195-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 371 | 15/09/2026 | 371 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055195 KV7963 | 28/08/2026 | KAHATEX CIJERAH | SPAIN | SEA | 27/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 27/07/2026 | 2026-06-08 | 28/07/2026 | 2026-05-08 | 371 | 371 |  |  |  | 22/07/2026 | 2026-03-08 | 22/07/2026 | 2026-05-08 | 371 | 371
ADIDAS | 0903055207-1 JN1956 | BLACK/WHITE | 90D | S2554WES413FTB-MTF | 3592 | 15/09/2026 | 3592 | AN | AN12/06/2026 | G1L | SWEATSHIRT | G1 | ok | (02/07/2026) | 14/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055207 JN1956 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-08-09 | W 3S FT QZ HD |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 3592 | 3592 |  |  |  | 2026-04-09 | 2026-11-09 | 27/08/2026 | 15/09/2026 | 3592 | 3592
ADIDAS | 0903055240-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 879 | 19/09/2026 | 879 | AN | AN12/06/2026 | G3J,G3K | SHORTS | G3 | ok | (03/07/2026) | 18/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903055240 KV7963 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 29/07/2026 | 2026-10-08 | 29/07/2026 | 2026-10-08 | 879 | 879 |  |  |  | 24/07/2026 | 2026-05-08 | 25/07/2026 | 2026-07-08 | 879 | 879
ADIDAS | 0903055956-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 629 | 31/10/2026 | 629 | SA | SA12/06/2026 | G2S | JACKET | G2 | ok | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903055956 JE6338 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 629 |  | 629 |  |  | 19/10/2026 | 20/10/2026 |  |  | 629 |  | 629
ADIDAS | 0903055994-1 LG9675 | BLACK | 120D | S2754WAS513C | 498 | 31/10/2026 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903055994 LG9675 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903056002-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 472 | 15/10/2026 | 472 | AN | AN12/06/2026 | G2H | T-SHIRT | G2 | ok | (03/07/2026) | 834012 | HT+PAD SUB PROCESS_V3 | 0903056002 LD0287 | 2026-11-09 | KAHATEX CIJERAH | ISRAEL | SEA | 19/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 472 | 423 | 49 |  | 423 | 16/09/2026 | 17/09/2026 | 2026-05-08 | 29/08/2026 | 472 | 472 |  |  |  | 14/09/2026 | 15/09/2026 | 2026-05-08 | 28/08/2026 | 472 | 472
ADIDAS | 0903056023-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 797 | 23/09/2026 | 797 | SA | SA12/06/2026 | G2T | JACKET | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056023 JE6338 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/07/2026 | M 3S FT FZ HD |  | SS27 | 28/07/2026 | 28/08/2026 | 29/07/2026 | 31/08/2026 | 797 | 797 |  |  |  | 23/07/2026 | 24/08/2026 | 23/07/2026 | 15/08/2026 | 797 | 797
ADIDAS | 0903056060-1 LF0723 | BLACK | 105D | S2754MAS511B | 325 | 31/10/2026 |  | SI | SI12/06/2026 |  | SHORTS |  | ok | (04/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 04-Sep. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903056060 LF0723 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903056094-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 161 | 15/10/2026 | 161 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | ok | (02/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056094 KX3653 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-12-10 | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 161 |  | 161 |  |  | 2026-08-10 | 2026-09-10 | 2026-10-09 | 2026-10-09 | 161 | 138 | 23 |  |  | 2026-06-10 | 2026-07-10 | 2026-09-09 | 2026-09-09 | 161 | 138 | 23
ADIDAS | 0903056095-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1009 | 23/09/2026 | 1009 | SA | SA12/06/2026 | G2T | JACKET | G2 | ok | (03/07/2026) | 21/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056095 JD1877 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | M 3S FT FZ HD |  | SS27 | 18/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 1009 | 798 | 211 |  | 332 | 15/09/2026 | 17/09/2026 | 16/09/2026 | 19/09/2026 | 1009 | 978 | 31 |  | 56
ADIDAS | 0903056120-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 427 | 30/09/2026 | 427 | AN | AN12/06/2026 | G2G | T-SHIRT | G2 | ok | (03/07/2026) | 24/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903056120 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 18/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 427 | 399 | 28 |  | 166 | 15/09/2026 | 19/09/2026 | 2026-01-08 | 13/08/2026 | 427 | 421 | 6
ADIDAS | 0903056133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 939 | 15/10/2026 | 939 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903056133 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-10-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 939 |  | 939 |  |  | 2026-07-10 | 2026-08-10 |  |  | 939 |  | 939 |  |  | 2026-05-10 | 2026-06-10 |  |  | 939 |  | 939
ADIDAS | 0903056140-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1431 | 31/10/2026 | 1431 | SA | SA12/06/2026 | G2Q | JACKET | G2 | (22/07/2026) | (03/07/2026) | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903056140 JD1877 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 26/10/2026 | M 3S FT FZ HD |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 1431 |  | 1431 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1431 |  | 1431
ADIDAS | 0903056160-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 521 | 2026-05-09 | 521 | AN | AN12/06/2026 | G1Q,G1R | T-SHIRT | G1 | ok | (03/07/2026) | 05/09: ex-fty 960026 | PRINT L3+PAD SUB PROCESS_V3 | 0903056160 LC8882 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/08/2026 | M ADI RETRO T BLACK |  | SS27 | 13/08/2026 | 31/08/2026 | 14/08/2026 | 31/08/2026 | 521 | 521 |  |  |  | 2026-10-08 | 27/08/2026 | 2026-05-08 | 26/08/2026 | 521 | 521
ADIDAS | 0903056304-1 KX8877 | WHITE | 90D | S27GMGFX100 | 376 | 30/09/2026 | 376 | SA | SA12/06/2026 | G2F | T-SHIRT | G2 | ok | (04/07/2026) | 25/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903056304 KX8877 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M CHIP T WHITE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 376 |  | 376 |  |  | 2026-01-10 | 2026-01-10 | 22/08/2026 | 17/09/2026 | 376 | 240 | 136
ADIDAS | 0903056585-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 110 | 23/09/2026 | 110 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 23/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056585 KY5988 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 110 |  | 110 |  |  | 16/09/2026 | 17/09/2026 | 19/09/2026 | 19/09/2026 | 110 | 19 | 91 |  | 19 | 2026-10-09 | 2026-11-09 | 18/09/2026 | 18/09/2026 | 110 | 19 | 91
ADIDAS | 0903056609-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 320 | 2026-07-10 | 320 | SA | SA12/06/2026 | G3E | PANTS | G3 | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056609 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 320 |  | 320 |  |  | 30/09/2026 | 2026-01-10 |  |  | 320 |  | 320 |  |  | 24/09/2026 | 25/09/2026 |  |  | 320 |  | 320
ADIDAS | 0903056658-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 208 | 30/09/2026 | 208 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903056658 LE0358 | 2026-11-09 | KAHATEX CIJERAH | UKRAINE | SEA | 15/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 208 | 204 | 4 |  | 37 | 2026-11-09 | 17/09/2026 | 2026-05-09 | 17/09/2026 | 208 | 193 | 15
ADIDAS | 0903056767-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 311 | 15/10/2026 | 311 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056767 KX3654 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 311 |  | 311 |  |  | 2026-06-10 | 2026-07-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-09-09 | 311 | 209 | 102
ADIDAS | 0903056781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 444 | 23/09/2026 | 444 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 23/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056781 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S CHELSEA B7 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 444 |  | 444 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 18/09/2026 | 444 | 95 | 349
ADIDAS | 0903056795-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 402 | 15/10/2026 | 402 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 516343 | HT+PAD SUB PROCESS_V3 | 0903056795 KX3654 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 402 |  | 402 |  |  | 2026-06-10 | 2026-07-10 | 27/08/2026 | 2026-10-09 | 402 | 371 | 31 |  |  | 2026-03-10 | 2026-05-10 | 27/08/2026 | 2026-09-09 | 402 | 371 | 31
ADIDAS | 0903056811-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1919 | 30/09/2026 | 1919 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903056811 KY6510 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | M 3S CHELSEA B7 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1919 |  | 1919 |  |  | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 1919 | 1217 | 702 |  | 158
ADIDAS | 0903056816-1 KE8424 | BLACK | 120D | S2608MR0906A | 321 | 15/10/2026 | 321 | SI | SI12/06/2026 | G2N | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056816 KE8424 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 321 |  | 321 |  |  | 13/10/2026 | 14/10/2026 |  |  | 321 |  | 321 |  |  | 2026-10-10 | 2026-12-10 |  |  | 321 |  | 321
ADIDAS | 0903056835-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 351 | 23/09/2026 | 351 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 23/09: ex-fty 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056835 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 351 | 338 | 13 |  | 338 | 16/09/2026 | 17/09/2026 | 17/09/2026 | 18/09/2026 | 351 | 345 | 6 |  |  | 2026-10-09 | 2026-11-09 | 15/09/2026 | 18/09/2026 | 351 | 346 | 5
ADIDAS | 0903056841-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 119 | 23/09/2026 | 119 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 21/09: ex-fty 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056841 KC8152 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 119 | 76 | 43 |  | 76 | 16/09/2026 | 17/09/2026 | 18/09/2026 | 18/09/2026 | 119 | 107 | 12 |  |  | 2026-10-09 | 2026-11-09 | 17/09/2026 | 18/09/2026 | 119 | 114 | 5
ADIDAS | 0903056853-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1356 | 2026-05-09 | 1356 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 05/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056853 KV7863 | 28/08/2026 | KAHATEX CIJERAH | TURKEY | SEA | 28/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/07/2026 | 21/08/2026 | 30/07/2026 | 18/08/2026 | 1356 | 1356 |  |  |  | 23/07/2026 | 18/08/2026 | 27/07/2026 | 20/08/2026 | 1356 | 1356
ADIDAS | 0903056865-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 443 | 23/09/2026 | 443 | SA | SA12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903056865 KC8152 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 17/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 443 | 431 | 12 |  | 295 | 14/09/2026 | 16/09/2026 | 17/09/2026 | 18/09/2026 | 443 | 443 |  |  |  | 2026-08-09 | 2026-10-09 | 17/09/2026 | 18/09/2026 | 443 | 443
ADIDAS | 0903056887-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 300 | 30/09/2026 | 300 | AN | AN12/06/2026 | G1H | JACKET | G1 | (13/07/2026) | (03/07/2026) | 26/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056887 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 28/09/2026 | 2026-05-09 | 18/09/2026 | 300 | 266 | 34
ADIDAS | 0903056914-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 314 | 2026-12-09 | 314 | AN | AN12/06/2026 | G1G,G1H | JACKET | G1 | ok | (03/07/2026) | 10/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056914 KV8005 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-02-09 | 2026-10-09 | 314 | 314 |  |  |  | 27/08/2026 | 2026-05-09 | 27/08/2026 | 2026-07-09 | 314 | 314
ADIDAS | 0903056942-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 304 | 2026-09-09 | 304 | AN | AN12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 09/09: ex-fty. T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903056942 KV8005 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 304 | 304 |  |  |  | 27/08/2026 | 2026-02-09 | 20/08/2026 | 2026-09-09 | 304 | 304
ADIDAS | 0903056963-1 JZ7808 | BLACK | 120D | S2608WR0900 | 312 | 15/10/2026 | 312 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903056963 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-10 | Run Ess Tee W BLACK |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 312 |  | 312 |  |  | 2026-06-10 | 2026-07-10 |  |  | 312 |  | 312 |  |  | 2026-03-10 | 2026-05-10 |  |  | 312 |  | 312
ADIDAS | 0903057195-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 499 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903057195 LG9669 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903057469-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 323 | 15/10/2026 | 323 | SA | SA12/06/2026 | G2P | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903057469 LD0285 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 28/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 28/09/2026 | 28/09/2026 |  |  | 323 |  | 323 |  |  | 24/09/2026 | 24/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323 |  |  |  | 22/09/2026 | 22/09/2026 | 14/08/2026 | 31/08/2026 | 323 | 323
ADIDAS | 0903057500-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 123 | 30/09/2026 | 123 | SI | SI12/06/2026 | G3H | SHORTS | G3 |  |  | 24/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 04-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 19-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057500 LD5446 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 123 |  | 123 |  |  | 18/09/2026 | 19/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903057529-1 LE8187 | BLACK | 105D | S2754MAS513 | 385 | 30/09/2026 | 385 | SI | SI12/06/2026 | G3B | PANTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 13-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057529 LE8187 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | M SL WV TP PT BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 385 |  | 385 |  |  | 19/09/2026 | 21/09/2026 | 2026-05-09 | 18/09/2026 | 385 | 162 | 223
ADIDAS | 0903057535-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 30/09/2026 | 512 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 29/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057535 LF0718 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 23/09/2026 | M SL WV OH PT BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 512 |  | 512 |  |  | 19/09/2026 | 21/09/2026 | 17/09/2026 | 17/09/2026 | 512 | 79 | 433
ADIDAS | 0903057574-1 LF0723 | BLACK | 105D | S2754MAS511B | 221 | 30/09/2026 | 221 | SI | SI12/06/2026 | G3E | SHORTS | G3 | ok | (04/07/2026) | 25/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057574 LF0723 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 26/09/2026 | M SL WV SHO BLACK |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 221 |  | 221 |  |  | 23/09/2026 | 24/09/2026 |  |  | 221 |  | 221
ADIDAS | 0903057608-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 379 | 15/10/2026 | 379 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903057608 LF0726 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 379 |  | 379 |  |  | 16/09/2026 | 19/09/2026 |  |  | 379 |  | 379
ADIDAS | 0903057614-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 653 | 15/10/2026 | 653 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057614 LH3759 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 653 |  | 653 |  |  | 23/09/2026 | 24/09/2026 |  |  | 653 |  | 653
ADIDAS | 0903057632-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 309 | 15/10/2026 | 309 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 19-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903057632 LH3761 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W SL WV BR PT LEGEND IVY S19 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 309 |  | 309 |  |  | 24/09/2026 | 25/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903058035-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 292 | 2026-12-09 | 292 | SI | SI12/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | (02/07/2026) | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903058035 LE8194 | 28/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-03-09 | 2026-12-09 | 2026-07-09 | 2026-10-09 | 292 | 292 |  |  |  | 31/08/2026 | 2026-09-09 | 24/08/2026 | 2026-12-09 | 292 | 292
ADIDAS | 0903058072-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 402 | 30/09/2026 | 402 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058072 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 26/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 402 |  | 402 |  |  | 23/09/2026 | 25/09/2026 |  |  | 402 |  | 402
ADIDAS | 0903058091-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 597 | 15/10/2026 | 597 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058091 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 597 |  | 597 |  |  | 2026-10-10 | 2026-12-10 | 2026-04-08 | 20/08/2026 | 597 | 399 | 198
ADIDAS | 0903058157-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 900 | 15/10/2026 | 900 | SA | SA12/06/2026 | G2I | T-SHIRT | G2 | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058157 KX3650 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-12-10 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 900 |  | 900 |  |  | 2026-08-10 | 2026-09-10 | 31/08/2026 | 17/09/2026 | 900 | 887 | 13 |  |  | 2026-06-10 | 2026-07-10 | 29/08/2026 | 17/09/2026 | 900 | 886 | 14
ADIDAS | 0903058189-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 541 | 31/10/2026 | 541 | AN | AN12/06/2026 | G2I | T-SHIRT | G2 | (11/07/2026) | (03/07/2026) | 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903058189 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 29/10/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 541 |  | 541 |  |  | 26/10/2026 | 27/10/2026 |  |  | 541 |  | 541
ADIDAS | 0903058216-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 610 | 31/10/2026 | 610 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903058216 KX3654 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA | 29/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 610 |  | 610 |  |  | 26/10/2026 | 27/10/2026 |  |  | 610 |  | 610 |  |  | 23/10/2026 | 24/10/2026 |  |  | 610 |  | 610
ADIDAS | 0903058691-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 415 | 15/10/2026 | 415 | AN | AN12/06/2026 | G2K | T-SHIRT | G2 | (11/08/2026) | (02/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903058691 KX3655 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 415 |  | 415 |  |  | 29/09/2026 | 29/09/2026 |  |  | 415 |  | 415 |  |  | 26/09/2026 | 26/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903058943-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 331 | 2026-07-10 | 331 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058943 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 24/08/2026 | 18/08/2026 | 21/08/2026 | 331 | 331 |  |  |  | 2026-11-08 | 19/08/2026 | 2026-05-08 | 20/08/2026 | 331 | 331
ADIDAS | 0903058963-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 539 | 23/09/2026 | 539 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 21/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-351). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058963 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/08/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 14/08/2026 | 19/08/2026 | 13/08/2026 | 18/08/2026 | 539 | 539 |  |  |  | 2026-11-08 | 13/08/2026 | 2026-03-08 | 2026-06-08 | 539 | 539
ADIDAS | 0903058992-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 332 | 2026-05-09 | 332 | AN | AN12/06/2026 | G2S | SHORTS | G2 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jul (PO NT-351). T2 Libolon, PI Date 05-Jun, actual receives 12-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903058992 KW2924 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/07/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 30/07/2026 | 14/08/2026 | 31/07/2026 | 14/08/2026 | 332 | 332 |  |  |  | 27/07/2026 | 2026-11-08 | 28/07/2026 | 2026-04-08 | 332 | 332
ADIDAS | 0903059036-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 355 | 2026-05-09 | 355 | AN | AN12/06/2026 | G3G,G3H | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059036 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/07/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/07/2026 | 19/08/2026 | 31/07/2026 | 18/08/2026 | 355 | 355 |  |  |  | 24/07/2026 | 13/08/2026 | 29/07/2026 | 2026-11-08 | 355 | 355
ADIDAS | 0903059059-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 306 | 2026-05-09 | 306 | AN | AN12/06/2026 | G3E | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059059 KV7863 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 306 | 306 |  |  |  | 2026-04-08 | 2026-11-08 | 29/07/2026 | 2026-11-08 | 306 | 306
ADIDAS | 0903059081-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 519 | 15/10/2026 | 519 | SI | SI12/06/2026 | G1F | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059081 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 519 |  | 519 |  |  | 16/10/2026 | 19/10/2026 |  |  | 519 |  | 519
ADIDAS | 0903059085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/09/2026 | 300 | AN | AN12/06/2026 | G3A | PANTS | G3 | ok | (03/07/2026) | 21/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 09-Jun. T2 Kahatex, PI Date 13-Jul, actual receives 03-Jun (PO NT-347). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059085 KV7863 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-08 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-04-08 | 14/08/2026 | 2026-05-08 | 14/08/2026 | 300 | 300 |  |  |  | 30/07/2026 | 2026-11-08 | 2026-01-08 | 14/08/2026 | 300 | 300
ADIDAS | 0903059107-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 253 | 2026-07-10 | 253 | SI | SI12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059107 LE4307 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 253 |  | 253 |  |  | 28/09/2026 | 2026-01-10 | 2026-04-09 | 2026-07-09 | 253 | 27 | 226
ADIDAS | 0903059113-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 1150 | 15/09/2026 | 1150 | SA | SA12/06/2026 | G2M | T-SHIRT | G2 | ok | (04/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903059113 LE8210 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-09 | LFC 3FY JSYL SE BLACK |  | FW26-FJ | 2026-09-09 | 14/09/2026 | 2026-11-09 | 2026-12-09 | 1150 | 1150 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-07-09 | 15/09/2026 | 1150 | 1150
ADIDAS | 0903059133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 15/09/2026 | 300 | SI | SI12/06/2026 | G1H | JACKET | G1 | ok | (03/07/2026) | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Kahatex, PI Date 13-Jul, actual receives 18-Jul. T2 Libolon, PI Date 06-Jul, actual receives 18-Jul. T2 Formosa, PI Date 08-Jul, actual receives 16-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059133 LE4307 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-07-09 | 300 | 300 |  |  |  | 27/08/2026 | 2026-02-09 | 27/08/2026 | 15/09/2026 | 300 | 299 | 1
ADIDAS | 0903059183-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 300 | 15/09/2026 | 300 | SA | SA12/06/2026 | G3J,G3K | PANTS | G3 | ok | (04/07/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516403 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903059183 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-12-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 300 |  |  |  | 2026-09-09 | 2026-11-09 | 13/09/2026 | 14/09/2026 | 300 | 300 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-12-09 | 14/09/2026 | 300 | 300
ADIDAS | 0903059345-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 147 | 15/09/2026 | 147 | AN | AN12/06/2026 | G3J | SHORTS | G3 | ok | (02/07/2026) | 14/09: ex-fty. T2 Libolon, using PO 26000011, body actual receives 11-Feb, 3S actual receives 10-Feb. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059345 JE1309 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | W 3S WV SHO |  | SS27 | 2026-05-09 | 2026-12-09 | 2026-09-09 | 2026-11-09 | 147 | 147 |  |  |  | 2026-02-09 | 2026-09-09 | 24/07/2026 | 2026-10-09 | 147 | 147
ADIDAS | 0903059367-1 KB5965 | BLACK | 120D | S2608MR0900A | 360 | 15/10/2026 | 360 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0903059367 KB5965 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | Run Ess Tee M |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 360 |  | 360 |  |  | 16/10/2026 | 17/10/2026 |  |  | 360 |  | 360 |  |  | 14/10/2026 | 15/10/2026 |  |  | 360 |  | 360
ADIDAS | 0903059372-1 LE8187 | BLACK | 105D | S2754MAS513 | 170 | 2026-07-10 | 170 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059372 LE8187 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-06-10 |  |  | 170 |  | 170 |  |  | 30/09/2026 | 2026-02-10 |  |  | 170 |  | 170
ADIDAS | 0903059402-1 LE8187 | BLACK | 105D | S2754MAS513 | 494 | 2026-07-10 | 494 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059402 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV TP PT BLACK |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 494 |  | 494 |  |  | 28/09/2026 | 30/09/2026 |  |  | 494 |  | 494
ADIDAS | 0903059416-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 111 | 15/10/2026 | 111 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059416 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-05-10 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 111 |  | 111 |  |  | 2026-01-10 | 2026-02-10 |  |  | 111 |  | 111
ADIDAS | 0903059460-1 LE8187 | BLACK | 105D | S2754MAS513 | 465 | 2026-07-10 | 465 | SI | SI12/06/2026 | G3K | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059460 LE8187 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV TP PT BLACK |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 465 |  | 465 |  |  | 28/09/2026 | 30/09/2026 |  |  | 465 |  | 465
ADIDAS | 0903059485-1 LF0718 | BLACK | 105D | S2754MAS512B | 170 | 31/10/2026 |  | SA | SA12/06/2026 |  | PANTS |  | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 31-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059485 LF0718 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903059491-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 362 | 15/10/2026 | 362 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059491 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-05-10 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 362 |  | 362 |  |  | 2026-01-10 | 2026-02-10 |  |  | 362 |  | 362
ADIDAS | 0903059517-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 365 | 23/10/2026 | 365 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059517 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M SL WV TT BLACK |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 365 |  | 365 |  |  | 21/10/2026 | 23/10/2026 |  |  | 365 |  | 365
ADIDAS | 0903059522-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 218 | 15/10/2026 | 218 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903059522 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-05-10 | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 218 |  | 218 |  |  | 2026-01-10 | 2026-02-10 |  |  | 218 |  | 218
ADIDAS | 0903059553-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 29/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059553 LF0718 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | M SL WV OH PT BLACK |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 100 |  | 100 |  |  | 19/09/2026 | 21/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903059578-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 15/10/2026 | 300 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (13/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059578 LG9669 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 2026-08-10 | W SL WV SK BLACK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903059583-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 309 | 15/10/2026 | 309 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059583 LF0726 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 19/09/2026 | 23/09/2026 |  |  | 309 |  | 309 |  |  | 16/09/2026 | 19/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903059595-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 161 | 23/10/2026 | 161 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 27-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059595 LF0727 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | M SL WV TT BLACK |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 161 |  | 161 |  |  | 21/10/2026 | 23/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903059626-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 299 | 15/10/2026 | 299 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059626 LF0726 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 299 |  | 299 |  |  | 2026-08-10 | 2026-12-10 |  |  | 299 |  | 299
ADIDAS | 0903059656-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 457 | 15/10/2026 | 457 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059656 LF0727 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | M SL WV TT BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 457 |  | 457 |  |  | 2026-06-10 | 2026-08-10 |  |  | 457 |  | 457
ADIDAS | 0903059680-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 283 | 15/10/2026 | 283 | AN | AN12/06/2026 | G1D | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 18-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903059680 LF0729 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 19/09/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 19/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 283 | 136 | 147 |  | 136 | 16/09/2026 | 19/09/2026 | 2026-07-09 | 2026-07-09 | 283 | 200 | 83
ADIDAS | 0903059710-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/10/2026 | 100 | SI | SI12/06/2026 | G3I | PANTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 13-Jul, actual receives 24-Jun. 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903059710 LH3759 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 26/09/2026 | W SL WV BR PT AURORA COFFEE S26 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 100 |  | 100 |  |  | 23/09/2026 | 24/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903059734-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/10/2026 | 200 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | ok | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059734 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 20/10/2026 | Run Ess Tee M |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 200 |  | 200 |  |  | 16/10/2026 | 17/10/2026 | 17/09/2026 | 17/09/2026 | 200 | 186 | 14 |  |  | 14/10/2026 | 15/10/2026 | 17/09/2026 | 19/09/2026 | 200 | 189 | 11 |  | 3
ADIDAS | 0903059757-1 JZ7808 | BLACK | 120D | S2608WR0900 | 811 | 15/10/2026 | 811 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059757 JZ7808 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | Run Ess Tee W BLACK |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 811 |  | 811 |  |  | 2026-06-10 | 2026-07-10 |  |  | 811 |  | 811 |  |  | 2026-03-10 | 2026-05-10 |  |  | 811 |  | 811
ADIDAS | 0903059786-1 KB5965 | BLACK | 120D | S2608MR0900A | 1790 | 15/10/2026 | 1790 | SA | SA12/06/2026 | G2G | T-SHIRT | G2 | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903059786 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA | 21/10/2026 | Run Ess Tee M |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 1790 |  | 1790 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1790 |  | 1790 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1790 |  | 1790
ADIDAS | 0903059867-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 750 | 31/10/2026 | 750 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 516205 | HT+PAD SUB PROCESS_V3 | 0903059867 LD0285 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-09-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 750 |  | 750 |  |  | 2026-06-10 | 2026-07-10 | 24/08/2026 | 15/09/2026 | 750 | 750 |  |  |  | 2026-03-10 | 2026-05-10 | 24/08/2026 | 2026-12-09 | 750 | 750
ADIDAS | 0903060200-1 LF0723 | BLACK | 105D | S2754MAS511B | 552 | 15/10/2026 | 552 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok | (04/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060200 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | M SL WV SHO BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 552 |  | 552 |  |  | 2026-08-10 | 2026-10-10 |  |  | 552 |  | 552
ADIDAS | 0903060220-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 309 | 30/09/2026 | 309 | AN | AN12/06/2026 | G1B | JACKET | G1 | ok | (03/07/2026) | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, PI Date 03-Jul, actual receives 07-Jul (PO 26021877). T2 Kahatex, PI Date 13-Jul, actual receives 09-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060220 KW2909 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 309 |  | 309 |  |  | 22/09/2026 | 23/09/2026 | 2026-04-08 | 20/08/2026 | 309 | 198 | 111
ADIDAS | 0903060279-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 152 | 31/10/2026 | 152 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060279 LF0729 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 152 |  | 152 |  |  | 27/10/2026 | 29/10/2026 |  |  | 152 |  | 152
ADIDAS | 0903060359-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 315 | 23/10/2026 | 315 | AN | AN12/06/2026 | G1I | JACKET | G1 | ok | (30/06/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060359 LF0729 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | M SL WV TT OLIVE ONE S27 |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 315 |  | 315 |  |  | 27/10/2026 | 29/10/2026 |  |  | 315 |  | 315
ADIDAS | 0903060814-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 325 | 23/10/2026 | 325 | SA | SA12/06/2026 | G2H | T-SHIRT | G2 | ok | (04/07/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0903060814 LD0285 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 325 |  | 325 |  |  | 2026-08-10 | 2026-09-10 | 20/08/2026 | 18/09/2026 | 325 | 325 |  |  |  | 2026-06-10 | 2026-07-10 | 19/08/2026 | 18/09/2026 | 325 | 325
ADIDAS | 0903060841-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 455 | 2026-07-10 | 455 | AN | AN12/06/2026 | G3K | SHORTS | G3 | ok | (03/07/2026) | T2 Formosa, PI Date 09-Jun, actual receives 23-Jun. T2 Libolon, Actual receives 05-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903060841 KV7963 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 455 |  | 455 |  |  | 2026-02-10 | 2026-03-10 |  |  | 455 |  | 455
ADIDAS | 0903060907-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 819 | 30/09/2026 | 819 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Libolon, PI Date 13-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 02-Jul. 1st Art (TC 10 pcs) 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060907 LD6542 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 819 |  | 819 |  |  | 19/09/2026 | 22/09/2026 |  |  | 819 |  | 819
ADIDAS | 0903060936-1 LF0718 | BLACK | 105D | S2754MAS512B | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G3A | PANTS | G3 | ok | (04/07/2026) | 26/09: ex-fty. T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060936 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M SL WV OH PT BLACK |  | SS27-SPOMA | 23/09/2026 | 24/09/2026 |  |  | 100 |  | 100 |  |  | 19/09/2026 | 21/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903060943-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 200 | 30/09/2026 | 200 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060943 LD6542 | 2026-11-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 200 |  | 200 |  |  | 23/09/2026 | 25/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903060967-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 77 | 15/10/2026 | 77 | AN | AN12/06/2026 | G3G | PANTS | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903060967 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | W SL WV PT BLACK |  | SS27-SPOMA | 20/10/2026 | 21/10/2026 |  |  | 77 |  | 77 |  |  | 16/10/2026 | 17/10/2026 |  |  | 77 |  | 77
ADIDAS | 0903060981-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 117 | 30/09/2026 | 117 | SA | SA12/06/2026 | G1C | JACKET | G1 | ok |  | 25/09: ex-fty. T2 Libolon, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 17-Jul, actual receives 22-Jul. T2 Kahatex, PI Date 18-Jul, actual receives 07-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060981 LD6542 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 117 |  | 117 |  |  | 23/09/2026 | 25/09/2026 |  |  | 117 |  | 117
ADIDAS | 0903061148-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 100 | 15/09/2026 | 100 | SI | SI12/06/2026 | G1G | T-SHIRT | G1 | ok | (02/07/2026) | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903061148 LE8194 | 28/08/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-09 | REAL HFY JSY SE WHITE |  | FW26-FJ | 2026-02-09 | 2026-09-09 | 2026-02-09 | 2026-08-09 | 100 | 100 |  |  |  | 29/08/2026 | 2026-05-09 | 21/08/2026 | 2026-03-09 | 100 | 100
ADIDAS | 0903061664-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 303 | 15/10/2026 | 303 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061664 LF0727 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV TT BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 303 |  | 303 |  |  | 2026-06-10 | 2026-08-10 |  |  | 303 |  | 303
ADIDAS | 0903061878-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 816 | 15/10/2026 | 816 | AN | AN12/06/2026 | G1K | JACKET | G1 | ok | (01/07/2026) | T2 Teijin Nantong, PI Date 20-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061878 LF0726 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 2026-12-10 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 816 |  | 816 |  |  | 2026-08-10 | 2026-12-10 |  |  | 816 |  | 816
ADIDAS | 0903061908-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 1613 | 30/09/2026 | 1613 | SI | SI12/06/2026 | G3E | SHORTS | G3 |  |  | 25/09: ex-fty. T2 Kahatex, PI Date 11-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 20-Aug. 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903061908 LD5446 | 2026-11-09 | KAHATEX CIJERAH | INDIA | SEA | 28/09/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 1613 |  | 1613 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903061936-1 LE0358 | LEGEND IVY S19 | 105D | S2754MAS514 | 559 | 30/09/2026 | 559 | SA | SA12/06/2026 | G3D | PANTS | G3 | ok | (04/07/2026) | 24/09: ex-fty. T2 Teijin Nantong, material quality issues (moir膿), PI Date 27-Jul, actual receives 20-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 14-Jul. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903061936 LE0358 | 2026-11-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 15/09/2026 | M SL WV CU PT LEGEND IVY S19 |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 19/09/2026 | 559 | 526 | 33 |  | 15 | 2026-11-09 | 17/09/2026 | 2026-05-09 | 17/09/2026 | 559 | 480 | 79
ADIDAS | 0903062015-1 LE5038 | BLACK | 105D | S2750MTR104A | 141 | 23/10/2026 | 141 | AN | AN12/06/2026 | G1R | T-SHIRT | G1 | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903062015 LE5038 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-12-11 | D4T AOP GFX T BLACK |  | SS27-TI | 2026-12-11 | 2026-12-11 |  |  | 141 |  | 141 |  |  | 2026-09-11 | 2026-09-11 |  |  | 141 |  | 141 |  |  | 2026-06-11 | 2026-06-11 |  |  | 141 |  | 141
ADIDAS | 0903062303-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 5037 | 30/09/2026 | 5037 | SI | SI12/06/2026 | G1Q | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual receives 07-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062303 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | M 3S CHELSEA B7 |  | SS27 | 21/09/2026 | 28/09/2026 |  |  | 5037 |  | 5037 |  |  | 17/09/2026 | 24/09/2026 |  |  | 5037 |  | 5037
ADIDAS | 0903062323-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 857 | 2026-09-09 | 857 | AN | AN12/06/2026 | G2J | T-SHIRT | G2 | ok | (03/07/2026) | 09/09: ex-fty 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903062323 KX0126 | 28/08/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | M RESORT T OLIVE FOUR S27 |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 857 | 857 |  |  |  | 2026-01-09 | 2026-05-09 | 30/07/2026 | 2026-04-09 | 857 | 857
ADIDAS | 0903062337-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 6000 | 30/09/2026 | 6000 | SI | SI12/06/2026 | G1O | SHORTS | G1 | ok | (04/07/2026) | 26/09: ex-fty. T2 Gistex, PI Date 25-Jul, actual recieves 14-Sep. T2 Kahatex, PI Date 13-Jul, actual receives 10-Jul. T2 Formosa, using fabric stock. 516437 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903062337 KY6510 | 2026-11-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | M 3S CHELSEA B7 |  | SS27 | 24/09/2026 | 2026-03-10 |  |  | 6000 |  | 6000 |  |  | 21/09/2026 | 30/09/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903063242-1 KX8877 | WHITE | 90D | S27GMGFX100 | 191 | 2026-12-09 | 191 | SA | SA12/06/2026 | G2J | T-SHIRT | G2 | ok | (04/07/2026) | 10/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903063242 KX8877 | 28/08/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-09 | M CHIP T WHITE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-10-09 | 191 | 191 |  |  |  | 2026-05-09 | 2026-09-09 | 22/08/2026 | 2026-10-09 | 191 | 191
ADIDAS | 0903063361-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 301 | 15/10/2026 | 301 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063361 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W SL WV SK BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 301 |  | 301 |  |  | 2026-06-10 | 2026-07-10 |  |  | 301 |  | 301
ADIDAS | 0903063462-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 347 | 31/10/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | ok | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063462 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903063503-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 310 | 15/10/2026 | 310 | AN | AN12/06/2026 | G3C | SKIRT | G3 | ok | (03/07/2026) | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063503 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | W SL WV SK BLACK |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 310 |  | 310 |  |  | 2026-06-10 | 2026-07-10 |  |  | 310 |  | 310
ADIDAS | 0903086049-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 752 | 30/09/2026 | 752 | SA | SA17/06/2026 | G1R | T-SHIRT | G1 | ok | ok | Waiting FU. DRC 0004-ILA data provided late by customer (CHAIAPP, ETD ??). 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903086049 LE8193 | 2026-01-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | FW26-FJ | 31/08/2026 | 2026-08-09 | 31/08/2026 | 2026-08-09 | 752 | 752 |  |  |  | 27/08/2026 | 2026-04-09 | 26/08/2026 | 2026-08-09 | 752 | 752
ADIDAS | 0903086050-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 459 | 15/09/2026 | 459 | SA | SA17/06/2026 | G1O | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903086050 LE8193 | 2026-01-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-07-09 | REAL H F JSY SE WHITE |  | FW26-FJ | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-11-09 | 459 | 459 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-01-09 | 2026-10-09 | 459 | 459
ADIDAS | 0903089629-1 LF0718 | BLACK | 105D | S2754MAS512B | 301 | 2026-07-10 | 301 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089629 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M SL WV OH PT BLACK |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 301 |  | 301 |  |  | 2026-01-10 | 2026-02-10 |  |  | 301 |  | 301
ADIDAS | 0903089630-1 LF0723 | BLACK | 105D | S2754MAS511B | 301 | 2026-07-10 | 301 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089630 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV SHO BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 301 |  | 301 |  |  | 2026-06-10 | 2026-08-10 |  |  | 301 |  | 301
ADIDAS | 0903089631-1 LF0723 | BLACK | 105D | S2754MAS511B | 17 | 2026-07-10 | 17 | SI | SI12/06/2026 | G3A | SHORTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 22-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089631 LF0723 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M SL WV SHO BLACK |  | SS27 | 2026-09-10 | 2026-12-10 |  |  | 17 |  | 17 |  |  | 2026-06-10 | 2026-08-10 |  |  | 17 |  | 17
ADIDAS | 0903089632-1 LF0718 | BLACK | 105D | S2754MAS512B | 59 | 2026-07-10 | 59 | SA | SA12/06/2026 | G3B | PANTS | G3 | ok |  | T2 Teijin Nantong, PI Date 27-Jul, actual receives 24-Aug. T2 Kahatex, PI Date 11-Aug, actual receives 10-Jul. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903089632 LF0718 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M SL WV OH PT BLACK |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 59 |  | 59 |  |  | 2026-01-10 | 2026-02-10 |  |  | 59 |  | 59
ADIDAS | 0903091452-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 808 | 23/09/2026 | 808 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903091452 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 21/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/09/2026 | 23/09/2026 |  |  | 808 |  | 808 |  |  | 17/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 808 | 273 | 535 |  | 273
ADIDAS | 0903093104-1 JZ7711 | BLACK | 120D | S2608MR0202 | 149 | 2026-07-10 | 149 | SA | SA23/06/2026 | G3E | SHORTS | G3 | ok | (04/08/2026) | T2 Hua Feng, PI Date 31-Jul, actual receives 04-Sep. T2 Far Easten, PI Date 14-Aug, actual receives 03-Sep. 1st Art (TC 10 pcs) 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093104 JZ7711 | 21/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 30/09/2026 | 2026-01-10 |  |  | 149 |  | 149 |  |  | 26/09/2026 | 28/09/2026 |  |  | 149 |  | 149 |  |  | 23/09/2026 | 24/09/2026 |  |  | 149 |  | 149
ADIDAS | 0903093139-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 376 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (25/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093139 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903093140-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 303 | 23/10/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (04/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093140 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903093145-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 392 | 15/10/2026 | 392 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Trax, (ripstop&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093145 KZ1286 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 29/09/2026 | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX | 29/09/2026 | 30/09/2026 |  |  | 392 |  | 392 |  |  | 25/09/2026 | 26/09/2026 |  |  | 392 |  | 392 |  |  | 22/09/2026 | 23/09/2026 |  |  | 392 |  | 392
ADIDAS | 0903093460-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 481 | 15/10/2026 | 481 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 03-Sep. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093460 KY9384 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 481 |  | 481 |  |  | 2026-10-10 | 2026-12-10 |  |  | 481 |  | 481 |  |  | 2026-07-10 | 2026-08-10 |  |  | 481 |  | 481
ADIDAS | 0903093463-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 600 | 15/10/2026 | 600 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 03-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093463 KY9384 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 600 |  | 600 |  |  | 2026-10-10 | 2026-12-10 |  |  | 600 |  | 600 |  |  | 2026-07-10 | 2026-08-10 |  |  | 600 |  | 600
ADIDAS | 0903093466-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 300 | 15/10/2026 | 300 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | T2 Y.R.C, PI Date 31-Jul, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093466 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-10 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903093469-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 579 | 15/10/2026 | 579 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/07/2026) |  | T2 Y.R.C, PI Date 31-Jul, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Jul, actual receives 04-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093469 KD3854 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 579 |  | 579 |  |  | 2026-07-10 | 2026-08-10 |  |  | 579 |  | 579 |  |  | 2026-03-10 | 2026-05-10 |  |  | 579 |  | 579
ADIDAS | 0903093480-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 350 | 15/10/2026 | 350 | SI | SI23/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | T2 Hua Feng, PI Date 31-Aug, actual receives 05-Sep. T2 Y.R.C, PI Date 24-Jul, actual receives 03-Sep. 516241 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093480 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 350 |  | 350 |  |  | 2026-06-10 | 2026-07-10 |  |  | 350 |  | 350 |  |  | 2026-02-10 | 2026-03-10 |  |  | 350 |  | 350
ADIDAS | 0903093503-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 5119 | 15/10/2026 | 5119 | SI | SI23/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | 28/09: ex-fty. T2 Y.R.C, PI Date 5-Aug, actual receives 16-Sep. T2 Grand Tex, PI Date 11-Aug, actual receives 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093503 KC9082 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 2026-07-10 | 17/10/2026 |  |  | 5119 |  | 5119 |  |  | 2026-03-10 | 14/10/2026 |  |  | 5119 |  | 5119 |  |  | 30/09/2026 | 2026-10-10 |  |  | 5119 |  | 5119
ADIDAS | 0903093882-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1600 | 15/10/2026 | 1600 | AN | AN23/06/2026 | G2J | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903093882 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 1600 |  | 1600 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1600 |  | 1600 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1600 |  | 1600
ADIDAS | 0903093883-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 500 | 30/09/2026 | 500 | AN | AN23/06/2026 | G2D | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 16-Sep. 839055 | PRINT L2+HT SUB PROCESS_V3 | 0903093883 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 22/09/2026 |  |  | 500 |  | 500 |  |  | 18/09/2026 | 18/09/2026 |  |  | 500 |  | 500 |  |  | 17/09/2026 | 17/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903093884-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 250 | 15/10/2026 | 250 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093884 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-08-10 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 250 |  | 250 |  |  | 2026-05-10 | 2026-06-10 |  |  | 250 |  | 250 |  |  | 2026-03-10 | 2026-05-10 |  |  | 250 |  | 250
ADIDAS | 0903093889-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 157 | 15/10/2026 | 157 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093889 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-10 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 2026-09-10 | 2026-09-10 |  |  | 157 |  | 157 |  |  | 2026-06-10 | 2026-06-10 |  |  | 157 |  | 157 |  |  | 2026-05-10 | 2026-05-10 |  |  | 157 |  | 157
ADIDAS | 0903093890-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 403 | 15/10/2026 | 403 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093890 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-08-10 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 403 |  | 403 |  |  | 2026-05-10 | 2026-06-10 |  |  | 403 |  | 403 |  |  | 2026-03-10 | 2026-05-10 |  |  | 403 |  | 403
ADIDAS | 0903093891-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 533 | 15/10/2026 | 533 | AN | AN23/06/2026 | G2J | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 814006 | PRINT L2+HT SUB PROCESS_V3 | 0903093891 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | THAILAND | SEA | 25/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 533 |  | 533 |  |  | 22/09/2026 | 24/09/2026 |  |  | 533 |  | 533 |  |  | 21/09/2026 | 23/09/2026 |  |  | 533 |  | 533
ADIDAS | 0903093893-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 107 | 22/09/2026 | 107 | AN | AN23/06/2026 | G2D | T-SHIRT | G2 | ok | ok | 21/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 08-Sep. 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093893 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 107 |  | 107 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 19/09/2026 | 107 | 75 | 32 |  | 56 | 16/09/2026 | 17/09/2026 | 18/09/2026 | 18/09/2026 | 107 | 107
ADIDAS | 0903093894-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 202 | 31/10/2026 | 202 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 516333 | PRINT L2+HT SUB PROCESS_V3 | 0903093894 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 202 |  | 202 |  |  | 2026-12-10 | 13/10/2026 |  |  | 202 |  | 202 |  |  | 2026-10-10 | 2026-12-10 |  |  | 202 |  | 202
ADIDAS | 0903093895-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 583 | 15/10/2026 | 583 | AN | AN23/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 838103 | PRINT L2+HT SUB PROCESS_V3 | 0903093895 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 583 |  | 583 |  |  | 2026-09-10 | 2026-10-10 |  |  | 583 |  | 583 |  |  | 2026-08-10 | 2026-09-10 |  |  | 583 |  | 583
ADIDAS | 0903093898-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 731 | 31/10/2026 | 731 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093898 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/11/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 23/11/2026 | 24/11/2026 |  |  | 731 |  | 731 |  |  | 18/11/2026 | 19/11/2026 |  |  | 731 |  | 731 |  |  | 17/11/2026 | 18/11/2026 |  |  | 731 |  | 731
ADIDAS | 0903093899-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 208 | 24/10/2026 | 208 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | DRC 0090-early shipment customer (ROW - FW: Critical PODD improvement request- RDD Jan availability - LO comm). Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516343 | PAD+HT SUB PROCESS_V3 | 0903093899 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/11/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 23/11/2026 | 24/11/2026 |  |  | 208 |  | 208 |  |  | 18/11/2026 | 19/11/2026 |  |  | 208 |  | 208 |  |  | 17/11/2026 | 18/11/2026 |  |  | 208 |  | 208
ADIDAS | 0903093900-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 300 | 31/10/2026 | 300 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093900 LG1784 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-11 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 300 |  | 300 |  |  | 2026-09-11 | 2026-10-11 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-09-11 |  |  | 300 |  | 300
ADIDAS | 0903093901-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 162 | 23/10/2026 | 162 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093901 LG1784 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-11 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 162 |  | 162 |  |  | 2026-09-11 | 2026-10-11 |  |  | 162 |  | 162 |  |  | 2026-06-11 | 2026-09-11 |  |  | 162 |  | 162
ADIDAS | 0903093906-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 559 | 15/10/2026 | 559 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903093906 KV0333 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 559 |  | 559 |  |  | 2026-10-10 | 2026-12-10 |  |  | 559 |  | 559 |  |  | 2026-09-10 | 2026-10-10 |  |  | 559 |  | 559
ADIDAS | 0903093907-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 309 | 15/10/2026 | 309 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 516342 | PAD+HT SUB PROCESS_V3 | 0903093907 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 309 |  | 309 |  |  | 2026-10-10 | 2026-12-10 |  |  | 309 |  | 309 |  |  | 2026-09-10 | 2026-10-10 |  |  | 309 |  | 309
ADIDAS | 0903093908-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 345 | 15/10/2026 | 345 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903093908 LG1784 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 345 |  | 345 |  |  | 2026-12-10 | 13/10/2026 |  |  | 345 |  | 345 |  |  | 2026-10-10 | 2026-12-10 |  |  | 345 |  | 345
ADIDAS | 0903093909-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 158 | 15/10/2026 | 158 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903093909 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 158 |  | 158 |  |  | 2026-12-10 | 13/10/2026 |  |  | 158 |  | 158 |  |  | 2026-10-10 | 2026-12-10 |  |  | 158 |  | 158
ADIDAS | 0903093910-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 425 | 15/10/2026 | 425 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903093910 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 425 |  | 425 |  |  | 13/10/2026 | 13/10/2026 |  |  | 425 |  | 425 |  |  | 2026-12-10 | 2026-12-10 |  |  | 425 |  | 425
ADIDAS | 0903093911-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 354 | 15/10/2026 | 354 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903093911 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 354 |  | 354 |  |  | 13/10/2026 | 13/10/2026 |  |  | 354 |  | 354 |  |  | 2026-12-10 | 2026-12-10 |  |  | 354 |  | 354
ADIDAS | 0903093912-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 105 | 15/10/2026 | 105 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD 11-Sep, ETA-Kaha 25-Sep. 600000 | PAD+HT SUB PROCESS_V3 | 0903093912 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 105 |  | 105 |  |  | 2026-12-10 | 13/10/2026 |  |  | 105 |  | 105 |  |  | 2026-10-10 | 2026-12-10 |  |  | 105 |  | 105
ADIDAS | 0903095162-1 KE9656 | BLACK | 105D | S2608WR0201A | 7 | 15/10/2026 | 7 | SI | SI23/06/2026 | G3D | SHORTS | G3 | ok |  | 29/09: ex-fty. IMPROVE. DRC 0051-T2 Far Eastern, PI Date 22-Aug, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 10-Sep. T2 Y.R.C, PI Date 15-Aug, actual receives 03-Sep (using fabric from TRAX). T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095162 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ADI365 SHO W BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 7 |  | 7 |  |  | 2026-02-10 | 2026-03-10 |  |  | 7 |  | 7 |  |  | 29/09/2026 | 30/09/2026 |  |  | 7 |  | 7
ADIDAS | 0903095174-1 KE9656 | BLACK | 105D | S2608WR0201A | 5411 | 15/10/2026 | 5411 | SI | SI23/06/2026 | G3D | SHORTS | G3 | (15/08/2026) |  | 29/09: ex-fty. DRC 0051-T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Far Eastern, PI Date 22-Aug, actual receives 15-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 14-Sep. T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095174 KE9656 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | ADI365 SHO W BLACK |  | SS27-TRAX | 2026-07-10 | 19/10/2026 |  |  | 5411 |  | 5411 |  |  | 2026-03-10 | 15/10/2026 |  |  | 5411 |  | 5411 |  |  | 30/09/2026 | 2026-12-10 |  |  | 5411 |  | 5411
ADIDAS | 0903095176-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 503 | 15/10/2026 | 503 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | T2 Trax, PI Date 10-Jul, actual receives 04-Sep. T2 Hua Feng, PI Date 22-Aug, actual receives 05-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (switch fabric from Trax). 1st Art (TC 10 pcs) 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095176 LC6791 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX | 2026-11-11 | 2026-12-11 |  |  | 503 |  | 503 |  |  | 2026-06-11 | 2026-09-11 |  |  | 503 |  | 503 |  |  | 2026-03-11 | 2026-04-11 |  |  | 503 |  | 503
ADIDAS | 0903095186-1 KA6229 | BLACK | 120D | S2608WR0202 | 448 | 23/09/2026 | 448 | SA | SA23/06/2026 | G1N | SHORTS | G1 | ok | ok | 21/09: ex-fty. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095186 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 19/09/2026 | 22/09/2026 |  |  | 448 |  | 448 |  |  | 16/09/2026 | 18/09/2026 |  |  | 448 |  | 448 |  |  | 2026-12-09 | 15/09/2026 | 14/09/2026 | 19/09/2026 | 448 | 376 | 72 |  | 1
ADIDAS | 0903095189-1 KA6229 | BLACK | 120D | S2608WR0202 | 301 | 22/09/2026 | 301 | SA | SA23/06/2026 | G1P | SHORTS | G1 | ok | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual recieves 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Aug (switch fabric from TREX). 1st Art (TC 10 pcs) 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095189 KA6229 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 24/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 24/09/2026 | 28/09/2026 |  |  | 301 |  | 301 |  |  | 21/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 17/09/2026 | 21/09/2026 | 2026-11-09 | 19/09/2026 | 301 | 301 |  |  | 3
ADIDAS | 0903095193-1 KA6229 | BLACK | 120D | S2608WR0202 | 339 | 15/10/2026 | 339 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 07-Sep, ETD 20-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 22-Aug, actual receives 04-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095193 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 339 |  | 339 |  |  | 26/10/2026 | 27/10/2026 |  |  | 339 |  | 339 |  |  | 22/10/2026 | 23/10/2026 | 2026-09-09 | 19/09/2026 | 339 | 339 |  |  | 2
ADIDAS | 0903095197-1 KA6229 | BLACK | 120D | S2608WR0202 | 765 | 22/09/2026 | 765 | SA | SA23/06/2026 | G1P | SHORTS | G1 | (14/08/2026) | ok | 21/09: ex-fty. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Aug, actual receives 04-Sep. T2 Far Easten, PI Date 07-Sep, actual receives 03-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 03-Sep (Switch from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095197 KA6229 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 24/09/2026 | 28/09/2026 |  |  | 765 |  | 765 |  |  | 21/09/2026 | 24/09/2026 | 18/09/2026 | 18/09/2026 | 765 | 152 | 613 |  |  | 17/09/2026 | 21/09/2026 | 14/09/2026 | 19/09/2026 | 765 | 748 | 17 |  | 29
ADIDAS | 0903095199-1 KA6229 | BLACK | 120D | S2608WR0202 | 277 | 15/10/2026 | 277 | SA | SA23/06/2026 | G1B | SHORTS | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095199 KA6229 | 21/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 29/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 277 |  | 277 |  |  | 26/10/2026 | 27/10/2026 |  |  | 277 |  | 277 |  |  | 22/10/2026 | 23/10/2026 |  |  | 277 |  | 277
ADIDAS | 0903095204-1 KC4947 | BLACK | 105D | S2608WR0216 | 523 | 15/10/2026 | 523 | SA | SA23/06/2026 | G3G | PANTS | G3 | (14/08/2026) | ok | Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD 07-Sep, ETA-Kaha 22-Sep. T2 Huge Bamboo, PI Date 29-Aug, actual receives 11-Sep. T2 Grand Tex, PI Date 10-Aug, actual receives 09-Sep. 804028 | PAD+HT SUB PROCESS_V3 | 0903095204 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-10 | adi365 Astro W |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 523 |  | 523 |  |  | 2026-03-10 | 2026-06-10 |  |  | 523 |  | 523 |  |  | 2026-02-10 | 2026-05-10 |  |  | 523 |  | 523
ADIDAS | 0903110773-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 580 | 31/10/2026 | 580 | SI | SI26/06/2026 | G1L | JACKET | G1 | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110773 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-10-11 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-10-11 | 13/11/2026 |  |  | 580 |  | 580 |  |  | 2026-05-11 | 2026-10-11 |  |  | 580 |  | 580
ADIDAS | 0903110856-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1103 | 26/09/2026 | 1103 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | 25/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 17-Sep. T2 Libolon, PI Date 22-Jul, actual receives 15-Aug. T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110856 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 1103 |  | 1103 |  |  | 19/09/2026 | 23/09/2026 |  |  | 1103 |  | 1103
ADIDAS | 0903110887-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 5118 | 15/10/2026 | 5118 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110887 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/10/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 22/10/2026 | 2026-10-11 |  |  | 5118 |  | 5118 |  |  | 19/10/2026 | 2026-05-11 |  |  | 5118 |  | 5118
ADIDAS | 0903128588-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903128588 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-09-09 | 420 | 420
ADIDAS | 0903129024-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 400 | 31/10/2026 | 400 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903129024 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 400 |  | 400 |  |  | 2026-02-11 | 2026-04-11 |  |  | 400 |  | 400
ADIDAS | 0903129074-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 152 | 23/10/2026 | 152 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129074 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 152 |  | 152 |  |  | 24/10/2026 | 26/10/2026 |  |  | 152 |  | 152
ADIDAS | 0903129078-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 399 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903129078 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903129093-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 792 | 15/09/2026 | 792 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129093 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 31/08/2026 | 15/09/2026 | 2026-02-09 | 15/09/2026 | 792 | 792 |  |  |  | 27/08/2026 | 2026-11-09 | 2026-05-08 | 22/08/2026 | 792 | 792
ADIDAS | 0903129376-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 550 | 15/10/2026 | 550 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129376 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 550 |  | 550 |  |  | 26/10/2026 | 27/10/2026 |  |  | 550 |  | 550
ADIDAS | 0903129444-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 750 | 23/10/2026 | 750 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903129444 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 750 |  | 750 |  |  | 26/10/2026 | 27/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903129505-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 303 | 15/10/2026 | 303 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903129505 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 303 |  | 303 |  |  | 24/10/2026 | 26/10/2026 | 2026-02-09 | 2026-02-09 | 303 | 19 | 284
ADIDAS | 0903130488-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 30/09/2026 | 103 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130488 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 103 |  | 103 |  |  | 29/09/2026 | 29/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903130527-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130527 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903130582-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 106 | 30/09/2026 | 106 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130582 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 106 |  | 106 |  |  | 2026-01-10 | 2026-02-10 | 20/08/2026 | 29/08/2026 | 106 | 34 | 72
ADIDAS | 0903130615-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130615 LI2645 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300
ADIDAS | 0903130651-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 698 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903130651 LG9672 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903130696-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 387 | 31/10/2026 | 387 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130696 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-11 | W 3S FT OH PT |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 387 |  | 387 |  |  | 30/10/2026 | 31/10/2026 |  |  | 387 |  | 387
ADIDAS | 0903130740-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 325 | 30/09/2026 | 325 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903130740 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | W 3S FT OH PT |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 325 |  | 325 |  |  | 16/09/2026 | 17/09/2026 | 14/08/2026 | 2026-07-09 | 325 | 294 | 31
ADIDAS | 0903130742-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 208 | 15/09/2026 | 208 | AN | AN26/06/2026 | G1J,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903130742 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/08/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 24/08/2026 | 2026-03-09 | 24/08/2026 | 2026-03-09 | 208 | 208 |  |  |  | 19/08/2026 | 31/08/2026 | 2026-07-08 | 2026-11-08 | 208 | 208
ADIDAS | 0903130761-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 550 | 15/10/2026 | 550 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130761 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-06-11 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-11 | 2026-06-11 |  |  | 550 |  | 550 |  |  | 2026-03-11 | 2026-03-11 | 2026-03-09 | 2026-09-09 | 550 | 85 | 465
ADIDAS | 0903130786-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 101 | 30/09/2026 | 101 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516394 | PRINT L3 SUB PROCESS_V3 | 0903130786 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 101 |  | 101 |  |  | 19/09/2026 | 19/09/2026 | 2026-02-09 | 2026-02-09 | 101 | 101
ADIDAS | 0903130839-1 LF0723 | BLACK | 105D | S2754MAS511B | 358 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130839 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130929-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 103 | 15/10/2026 | 103 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130929 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 103 |  | 103 |  |  | 26/10/2026 | 26/10/2026 |  |  | 103 |  | 103
ADIDAS | 0903130954-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 144 | 23/10/2026 | 144 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903130954 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 144 |  | 144 |  |  | 16/10/2026 | 19/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903130982-1 LF0723 | BLACK | 105D | S2754MAS511B | 308 | 15/10/2026 | 308 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130982 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | M SL WV SHO BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 308 |  | 308 |  |  | 2026-08-10 | 2026-10-10 |  |  | 308 |  | 308
ADIDAS | 0903131041-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 343 | 19/09/2026 | 343 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3 SUB PROCESS_V3 | 0903131041 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 17/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 343 | 343 |  |  |  | 14/09/2026 | 16/09/2026 | 31/08/2026 | 17/09/2026 | 343 | 343
ADIDAS | 0903131046-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 103 | 15/10/2026 | 103 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131046 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 18/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 103 | 79 | 24 |  | 79 | 15/09/2026 | 19/09/2026 | 2026-02-09 | 2026-10-09 | 103 | 103
ADIDAS | 0903131080-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 120 | 23/10/2026 | 120 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131080 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 120 |  | 120 |  |  | 21/10/2026 | 23/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903131111-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 254 | 30/09/2026 | 254 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903131111 LE4307 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 254 |  | 254 |  |  | 21/09/2026 | 24/09/2026 |  |  | 254 |  | 254
ADIDAS | 0903131716-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131716 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 303 |  | 303 |  |  | 28/10/2026 | 29/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903131801-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 744 | 15/10/2026 | 744 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131801 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 744 |  | 744 |  |  | 29/10/2026 | 30/10/2026 |  |  | 744 |  | 744
ADIDAS | 0903131943-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 580 | 23/10/2026 | 580 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903131943 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 580 |  | 580 |  |  | 26/10/2026 | 27/10/2026 |  |  | 580 |  | 580
ADIDAS | 0903132003-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 586 | 23/10/2026 | 586 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132003 LI2647 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-11 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 586 |  | 586 |  |  | 2026-04-11 | 2026-04-11 |  |  | 586 |  | 586
ADIDAS | 0903132049-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 270 | 15/10/2026 | 270 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132049 LI2671 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 270 |  | 270 |  |  | 30/10/2026 | 31/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903132130-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 450 | 23/10/2026 | 450 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132130 LI2672 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 450 |  | 450 |  |  | 21/10/2026 | 23/10/2026 |  |  | 450 |  | 450
ADIDAS | 0903132419-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 106 | 30/09/2026 | 106 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132419 LI2671 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 106 |  | 106 |  |  | 24/09/2026 | 25/09/2026 |  |  | 106 |  | 106
ADIDAS | 0903132455-1 LD5424 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS614WVB | 331 | 15/10/2026 | 331 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Formosa, PI Date 12-Aug, actual receives 04-Sep. T2 Kahatex, PI Date 12-Aug, actual receives 28-Aug. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132455 LD5424 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/10/2026 | M 95S WV WB LND OLIVE FOUR S27/OFF WHITE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 331 |  | 331 |  |  | 16/10/2026 | 17/10/2026 |  |  | 331 |  | 331
ADIDAS | 0903132482-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 150 | 2026-12-09 | 150 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132482 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 150 | 150 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-03-09 | 150 | 150
ADIDAS | 0903132522-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 634 | 31/10/2026 | 634 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903132522 KX3654 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 634 |  | 634 |  |  | 26/10/2026 | 27/10/2026 |  |  | 634 |  | 634 |  |  | 23/10/2026 | 24/10/2026 |  |  | 634 |  | 634
ADIDAS | 0903132534-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 255 | 15/09/2026 | 255 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132534 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 2026-04-09 | 255 | 255 |  |  |  | 29/08/2026 | 31/08/2026 | 15/08/2026 | 24/08/2026 | 255 | 255
ADIDAS | 0903132553-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132553 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 200 | 200 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 22/08/2026 | 200 | 200
ADIDAS | 0903132571-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 704 | 30/09/2026 | 704 | SI | SI26/06/2026 | G2O | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132571 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/09/2026 | W 3S FT FZ HD |  | SS27 | 19/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 704 | 570 | 134 |  | 282 | 16/09/2026 | 17/09/2026 | 18/09/2026 | 18/09/2026 | 704 | 686 | 18
ADIDAS | 0903132573-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 2026-12-09 | 200 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132573 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 200 | 200 |  |  |  | 27/08/2026 | 31/08/2026 | 20/08/2026 | 27/08/2026 | 200 | 200
ADIDAS | 0903132592-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 170 | 2026-12-09 | 170 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132592 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 170 | 170 |  |  |  | 29/08/2026 | 2026-03-09 | 29/08/2026 | 2026-07-09 | 170 | 170
ADIDAS | 0903132607-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 339 | 31/10/2026 | 339 | SI | SI26/06/2026 | G3H | JACKET | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132607 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | W 3S FT FZ HD |  | SS27 | 2026-05-11 | 2026-06-11 |  |  | 339 |  | 339 |  |  | 2026-02-11 | 2026-03-11 |  |  | 339 |  | 339
ADIDAS | 0903132697-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 691 | 15/09/2026 | 691 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132697 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 21/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/08/2026 | 2026-03-09 | 24/08/2026 | 2026-01-09 | 691 | 691 |  |  |  | 18/08/2026 | 31/08/2026 | 2026-04-08 | 2026-07-08 | 691 | 691
ADIDAS | 0903132705-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 170 | 30/09/2026 | 170 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 26/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132705 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 170 |  | 170 |  |  | 21/09/2026 | 24/09/2026 |  |  | 170 |  | 170
ADIDAS | 0903132709-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 15/10/2026 | 600 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132709 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 600 |  | 600 |  |  | 24/10/2026 | 26/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903132754-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 278 | 15/10/2026 | 278 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132754 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 278 |  | 278 |  |  | 28/10/2026 | 29/10/2026 |  |  | 278 |  | 278
ADIDAS | 0903132786-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 369 | 15/10/2026 | 369 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10 Aug, actual receives 14-Sep. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903132786 KY6510 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 369 |  | 369 |  |  | 2026-08-10 | 2026-09-10 |  |  | 369 |  | 369
ADIDAS | 0903132803-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132803 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 29/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 266 |  | 266 |  |  | 26/10/2026 | 26/10/2026 |  |  | 266 |  | 266
ADIDAS | 0903132827-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132827 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 28/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 271 |  | 271 |  |  | 24/10/2026 | 26/10/2026 | 28/08/2026 | 2026-03-09 | 271 | 268 | 3
ADIDAS | 0903132837-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 143 | 30/09/2026 | 143 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132837 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 143 |  | 143 |  |  | 22/09/2026 | 22/09/2026 | 2026-01-09 | 2026-04-09 | 143 | 36 | 107
ADIDAS | 0903132864-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 316 | 15/10/2026 | 316 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132864 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-02-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 316 |  | 316 |  |  | 29/10/2026 | 30/10/2026 |  |  | 316 |  | 316
ADIDAS | 0903132871-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 358 | 15/10/2026 | 358 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Kahatex, PI Date 12-Aug, actual receives 05-Sep. T2 Formosa, PI Date 12-Aug, actual receives 03-Sep. T2 Libolon, PI Date 06-Aug, actual receives 08-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903132871 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 358 |  | 358 |  |  | 17/10/2026 | 19/10/2026 |  |  | 358 |  | 358
ADIDAS | 0903132916-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 900 | 15/10/2026 | 900 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903132916 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 900 |  | 900 |  |  | 31/10/2026 | 2026-03-11 |  |  | 900 |  | 900
ADIDAS | 0903132921-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 615 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903132921 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903132931-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132931 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 308 |  | 308 |  |  | 2026-01-10 | 2026-02-10 | 27/08/2026 | 29/08/2026 | 308 | 308
ADIDAS | 0903132951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 830 | 31/10/2026 | 830 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903132951 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 830 |  | 830 |  |  | 2026-11-11 | 13/11/2026 |  |  | 830 |  | 830
ADIDAS | 0903132955-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 266 | 15/10/2026 | 266 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132955 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 31/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 266 |  | 266 |  |  | 28/10/2026 | 29/10/2026 |  |  | 266 |  | 266
ADIDAS | 0903132969-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132969 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 30/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 1000 |  | 1000 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903132997-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903132997 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-12-09 | 2026-01-09 | 2026-10-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-09-09 | 2026-04-08 | 26/08/2026 | 420 | 420
ADIDAS | 0903133002-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1375 | 30/09/2026 | 1375 | SI | SI26/06/2026 | G1H | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133002 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1375 |  | 1375 |  |  | 28/09/2026 | 30/09/2026 | 2026-07-08 | 24/08/2026 | 1375 | 1293 | 82
ADIDAS | 0903133009-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 1000 | 15/10/2026 | 1000 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133009 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-11 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 1000 |  | 1000 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903133055-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 1218 | 30/09/2026 | 1218 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133055 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 1218 |  | 1218 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1218 |  | 1218
ADIDAS | 0903133059-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 367 | 15/10/2026 | 367 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133059 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 29/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 367 |  | 367 |  |  | 26/10/2026 | 27/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903133068-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 312 | 31/10/2026 | 312 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903133068 LG9661 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-11 | 13/11/2026 |  |  | 312 |  | 312 |  |  | 2026-09-11 | 2026-10-11 |  |  | 312 |  | 312
ADIDAS | 0903133104-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 2450 | 30/09/2026 | 2450 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133104 LI2645 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 2450 |  | 2450 |  |  | 2026-02-10 | 2026-05-10 | 26/08/2026 | 28/08/2026 | 2450 | 2432 | 18
ADIDAS | 0903133114-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 282 | 15/09/2026 | 282 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133114 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 15/09/2026 | 2026-03-09 | 15/09/2026 | 282 | 282 |  |  |  | 29/08/2026 | 2026-11-09 | 20/08/2026 | 24/08/2026 | 282 | 282
ADIDAS | 0903133128-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 500 | 15/10/2026 | 500 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133128 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/10/2026 | 31/10/2026 |  |  | 500 |  | 500 |  |  | 28/10/2026 | 28/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903133146-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133146 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903133194-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 103 | 30/09/2026 | 103 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133194 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 18/09/2026 | 103 | 103 |  |  |  | 2026-11-09 | 17/09/2026 | 31/08/2026 | 2026-05-09 | 103 | 101 | 2
ADIDAS | 0903133260-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 194 | 30/09/2026 | 194 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133260 LI2646 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 194 |  | 194 |  |  | 28/09/2026 | 29/09/2026 | 28/08/2026 | 28/08/2026 | 194 | 181 | 13
ADIDAS | 0903133331-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133331 LI2670 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 19/09/2026 | 500 | 500 |  |  | 6 | 2026-11-09 | 17/09/2026 | 31/08/2026 | 2026-04-09 | 500 | 484 | 16
ADIDAS | 0903133357-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 675 | 2026-02-09 | 675 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133357 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 675 | 675 |  |  |  | 27/08/2026 | 28/08/2026 | 21/08/2026 | 2026-03-09 | 675 | 675
ADIDAS | 0903133374-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 143 | 30/09/2026 | 143 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 800187 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133374 LI2647 | 2026-10-08 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 143 |  | 143 |  |  | 29/09/2026 | 29/09/2026 |  |  | 143 |  | 143
ADIDAS | 0903133397-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 115 | 2026-02-09 | 115 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133397 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 115 | 115 |  |  |  | 27/08/2026 | 28/08/2026 | 26/08/2026 | 2026-01-09 | 115 | 115
ADIDAS | 0903133475-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133475 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 22/09/2026 | 22/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903133506-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E,G2R | ACCESSORIES | G1,G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133506 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-03-09 | 24/08/2026 | 31/08/2026 | 420 | 420
ADIDAS | 0903133517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133517 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 19/08/2026 | 26/08/2026 | 220 | 220
ADIDAS | 0903133575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 220 | 220 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 220 | 220
ADIDAS | 0903133589-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 586 | 23/09/2026 | 586 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 21/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133589 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 17/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 586 | 366 | 220 |  | 14 | 14/09/2026 | 17/09/2026 | 2026-01-09 | 19/09/2026 | 586 | 582 | 4 |  | 189
ADIDAS | 0903133603-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 84 | 15/10/2026 | 84 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133603 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 84 | 84 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 84 | 84
ADIDAS | 0903133644-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133644 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 28/08/2026 | 2026-03-09 | 27/08/2026 | 2026-02-09 | 295 | 295
ADIDAS | 0903133706-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 251 | 15/10/2026 | 251 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133706 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 29/10/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 29/10/2026 | 29/10/2026 |  |  | 251 |  | 251 |  |  | 26/10/2026 | 26/10/2026 |  |  | 251 |  | 251
ADIDAS | 0903133715-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 545 | 23/10/2026 | 545 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133715 LI2667 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 545 |  | 545 |  |  | 31/10/2026 | 2026-02-11 | 2026-03-09 | 2026-03-09 | 545 | 545
ADIDAS | 0903133759-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 249 | 15/09/2026 | 249 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133759 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-01-09 | 249 | 249 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-04-08 | 2026-05-08 | 249 | 249
ADIDAS | 0903133849-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 423 | 30/09/2026 | 423 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133849 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 423 |  | 423 |  |  | 19/09/2026 | 22/09/2026 |  |  | 423 |  | 423
ADIDAS | 0903133851-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 156 | 30/09/2026 | 156 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516394 | PRINT L3 SUB PROCESS_V3 | 0903133851 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 156 |  | 156 |  |  | 19/09/2026 | 19/09/2026 | 31/08/2026 | 19/09/2026 | 156 | 156 |  |  | 6
ADIDAS | 0903133871-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903133871 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 234 | 234 |  |  |  | 28/08/2026 | 31/08/2026 | 26/08/2026 | 2026-03-09 | 234 | 234
ADIDAS | 0903133886-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 888 | 23/10/2026 | 888 | AN | AN26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133886 LI2668 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 888 |  | 888 |  |  | 20/10/2026 | 21/10/2026 | 31/08/2026 | 16/09/2026 | 888 | 883 | 5
ADIDAS | 0903133936-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 358 | 30/09/2026 | 358 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133936 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 358 |  | 358 |  |  | 28/09/2026 | 29/09/2026 | 15/08/2026 | 2026-10-09 | 358 | 349 | 9
ADIDAS | 0903133965-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 420 | 2026-12-09 | 420 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903133965 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 31/08/2026 | 2026-01-08 | 2026-10-08 | 420 | 420
ADIDAS | 0903134033-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 284 | 15/09/2026 | 284 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134033 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 284 | 284 |  |  |  | 29/08/2026 | 2026-02-09 | 19/08/2026 | 2026-09-09 | 284 | 284
ADIDAS | 0903134047-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2000 | 30/09/2026 | 2000 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134047 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 2000 |  | 2000 |  |  | 30/09/2026 | 2026-03-10 |  |  | 2000 |  | 2000
ADIDAS | 0903134049-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 980 | 15/10/2026 | 980 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134049 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 30/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 980 |  | 980 |  |  | 27/10/2026 | 29/10/2026 |  |  | 980 |  | 980
ADIDAS | 0903134104-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 142 | 2026-02-09 | 142 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134104 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 142 | 142 |  |  |  | 27/08/2026 | 29/08/2026 | 18/08/2026 | 27/08/2026 | 142 | 142
ADIDAS | 0903134120-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1000 | 30/09/2026 | 1000 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134120 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 25/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1000 |  | 1000 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903134126-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 203 | 15/10/2026 | 203 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134126 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 28/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 203 |  | 203 |  |  | 24/10/2026 | 26/10/2026 | 19/08/2026 | 31/08/2026 | 203 | 203
ADIDAS | 0903134200-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 225 | 15/09/2026 | 225 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134200 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 225 | 225 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-07-09 | 225 | 225
ADIDAS | 0903134339-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 210 | 2026-12-09 | 210 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134339 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-05-09 | 210 | 210 |  |  |  | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-10-09 | 210 | 210
ADIDAS | 0903134404-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134404 LI2672 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 100 | 100 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-04-09 | 100 | 100
ADIDAS | 0903134448-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 2026-12-09 | 100 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134448 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100 | 100 |  |  |  | 28/08/2026 | 31/08/2026 | 27/08/2026 | 2026-07-09 | 100 | 100
ADIDAS | 0903134486-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 295 | 15/09/2026 | 295 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134486 LI2671 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-02-09 | 2026-04-09 | 295 | 295 |  |  |  | 29/08/2026 | 2026-02-09 | 28/08/2026 | 2026-12-09 | 295 | 295
ADIDAS | 0903134529-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-12-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134529 LI2670 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-07-09 | 2026-03-09 | 2026-04-09 | 220 | 220 |  |  |  | 28/08/2026 | 2026-03-09 | 2026-02-09 | 2026-10-09 | 220 | 220
ADIDAS | 0903134690-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 150 | 2026-12-09 | 150 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134690 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-09 | 150 | 150 |  |  |  | 29/08/2026 | 31/08/2026 | 31/08/2026 | 2026-02-09 | 150 | 150
ADIDAS | 0903134709-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 2191 | 15/10/2026 | 2191 | AN | AN26/06/2026 | G1B | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. T2 Formosa, PI Date 26-Jul, actual receives 27-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134709 KW2909 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 15/10/2026 | 21/10/2026 |  |  | 2191 |  | 2191 |  |  | 2026-12-10 | 17/10/2026 |  |  | 2191 |  | 2191
ADIDAS | 0903134753-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 265 | 15/09/2026 | 265 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134753 LI2645 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-09 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-07-09 | 265 | 265 |  |  |  | 29/08/2026 | 2026-02-09 | 22/08/2026 | 27/08/2026 | 265 | 265
ADIDAS | 0903134783-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 225 | 15/09/2026 | 225 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134783 LI2647 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-03-09 | 15/09/2026 | 2026-05-09 | 15/09/2026 | 225 | 225 |  |  |  | 31/08/2026 | 2026-11-09 | 2026-03-09 | 2026-04-09 | 225 | 216 | 9
ADIDAS | 0903134821-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 220 | 2026-12-09 | 220 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 830009 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903134821 LI2646 | 2026-10-08 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 220 | 220 |  |  |  | 27/08/2026 | 29/08/2026 | 15/08/2026 | 29/08/2026 | 220 | 220
ADIDAS | 0903134827-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2B,G2H,G2L | T-SHIRT | G2 | ok | (15/08/2026(10)) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134827 KS1804 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 26/09/2026 | 2026-07-08 | 20/08/2026 | 1072 | 334 | 738 |  |  | 2026-04-08 | 23/09/2026 | 2026-01-08 | 2026-07-09 | 1072 | 1056 | 16
ADIDAS | 0903134857-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 67 | 15/10/2026 | 67 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134857 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 67 | 67 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-08-09 | 67 | 67
ADIDAS | 0903134876-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 31/10/2026 | 803 | SI | SI26/06/2026 | G2H | T-SHIRT | G2 | ok | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134876 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | BIG APPLE TEE |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 803 |  | 803 |  |  | 14/10/2026 | 14/10/2026 |  |  | 803 |  | 803
ADIDAS | 0903134905-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 56 | 15/10/2026 | 56 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903134905 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-07-09 | 2026-03-09 | 2026-03-09 | 56 | 56 |  |  |  | 29/08/2026 | 2026-03-09 | 31/08/2026 | 18/09/2026 | 56 | 56
ADIDAS | 0903134935-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 31/10/2026 | 804 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134935 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | ARCH SEAL TEE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 804 |  | 804 |  |  | 15/10/2026 | 15/10/2026 | 16/09/2026 | 16/09/2026 | 804 | 660 | 144
ADIDAS | 0903134982-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 105 | 30/09/2026 | 105 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | ok | (05/08/2026) | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134982 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-02-10 |  |  | 105 |  | 105 |  |  | 29/09/2026 | 29/09/2026 |  |  | 105 |  | 105
ADIDAS | 0903135003-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 634 | 2026-08-09 | 634 | SI | SI26/06/2026 | G2N | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135003 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 19/08/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 19/08/2026 | 28/08/2026 | 19/08/2026 | 27/08/2026 | 634 | 634 |  |  |  | 13/08/2026 | 24/08/2026 | 2026-07-08 | 21/08/2026 | 634 | 634
ADIDAS | 0903135049-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 744 | 2026-08-09 | 744 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135049 LI2647 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 21/08/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 21/08/2026 | 26/08/2026 | 21/08/2026 | 26/08/2026 | 744 | 744 |  |  |  | 18/08/2026 | 20/08/2026 | 18/08/2026 | 29/08/2026 | 744 | 744
ADIDAS | 0903135083-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 1072 | 30/09/2026 | 1072 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | ok | (05/08/2026) | 26/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135083 KS1836 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | ARCH SEAL TEE |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 1072 |  | 1072 |  |  | 29/09/2026 | 30/09/2026 | 26/08/2026 | 16/09/2026 | 1072 | 1072
ADIDAS | 0903135108-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 642 | 2026-08-09 | 642 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135108 LI2670 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 13/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 13/08/2026 | 26/08/2026 | 19/08/2026 | 24/08/2026 | 642 | 642 |  |  |  | 2026-10-08 | 20/08/2026 | 15/08/2026 | 28/08/2026 | 642 | 642
ADIDAS | 0903135147-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 270 | 15/09/2026 | 270 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135147 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 270 | 270 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-03-08 | 2026-12-08 | 270 | 270
ADIDAS | 0903135150-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 125 | 30/09/2026 | 125 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135150 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 125 |  | 125 |  |  | 28/09/2026 | 29/09/2026 | 28/08/2026 | 29/08/2026 | 125 | 125
ADIDAS | 0903135182-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 171 | 23/10/2026 | 171 | AN | AN26/06/2026 | G1G | ACCESSORIES | G1 | (04/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135182 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 171 |  | 171 |  |  | 2026-04-11 | 2026-04-11 |  |  | 171 |  | 171
ADIDAS | 0903135184-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G2J,G2K | ACCESSORIES | G2 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135184 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/08/2026 | 2026-12-09 | 29/08/2026 | 2026-10-09 | 420 | 420 |  |  |  | 26/08/2026 | 2026-09-09 | 20/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135185-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 259 | 15/10/2026 | 259 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 839055 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135185 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SINGAPORE | SEA | 18/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 259 | 256 | 3 |  | 17 | 15/09/2026 | 19/09/2026 | 2026-02-09 | 2026-12-09 | 259 | 228 | 31
ADIDAS | 0903135215-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 258 | 15/10/2026 | 258 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135215 LI2646 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 28/10/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 258 |  | 258 |  |  | 24/10/2026 | 26/10/2026 | 15/08/2026 | 2026-01-09 | 258 | 252 | 6
ADIDAS | 0903135229-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 184 | 23/10/2026 | 184 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135229 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 184 |  | 184 |  |  | 26/10/2026 | 27/10/2026 |  |  | 184 |  | 184
ADIDAS | 0903135251-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 233 | 15/10/2026 | 233 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135251 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 29/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 233 |  | 233 |  |  | 26/10/2026 | 27/10/2026 |  |  | 233 |  | 233
ADIDAS | 0903135264-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 596 | 31/10/2026 | 596 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135264 LG9664 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 596 |  | 596 |  |  | 2026-04-11 | 2026-06-11 |  |  | 596 |  | 596
ADIDAS | 0903135286-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 30/09/2026 | 230 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135286 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 230 |  | 230 |  |  | 29/09/2026 | 30/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903135352-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 310 | 30/09/2026 | 310 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135352 LI2647 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 310 |  | 310 |  |  | 29/09/2026 | 30/09/2026 |  |  | 310 |  | 310
ADIDAS | 0903135358-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 750 | 23/10/2026 | 750 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135358 LI2670 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 750 |  | 750 |  |  | 16/10/2026 | 19/10/2026 |  |  | 750 |  | 750
ADIDAS | 0903135402-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 377 | 31/10/2026 | 377 | SA | SA26/06/2026 | G1C | JACKET | G1 | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135402 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-11 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 2026-12-11 | 13/11/2026 |  |  | 377 |  | 377 |  |  | 2026-09-11 | 2026-10-11 |  |  | 377 |  | 377
ADIDAS | 0903135472-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 115 | 15/09/2026 | 115 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135472 LI2669 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 31/08/2026 | 2026-05-09 | 2026-03-09 | 2026-04-09 | 115 | 115 |  |  |  | 27/08/2026 | 2026-02-09 | 2026-04-08 | 2026-10-08 | 115 | 115
ADIDAS | 0903135480-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 148 | 15/10/2026 | 148 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135480 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 20/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 148 |  | 148 |  |  | 16/10/2026 | 16/10/2026 | 31/08/2026 | 2026-09-09 | 148 | 148
ADIDAS | 0903135498-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 980 | 15/10/2026 | 980 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135498 LI2645 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-11 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 980 |  | 980 |  |  | 29/10/2026 | 30/10/2026 |  |  | 980 |  | 980
ADIDAS | 0903135544-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 169 | 30/09/2026 | 169 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135544 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 28/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 169 |  | 169 |  |  | 24/09/2026 | 25/09/2026 | 31/08/2026 | 2026-07-09 | 169 | 169
ADIDAS | 0903135569-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 189 | 30/09/2026 | 189 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135569 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 23/09/2026 | 17/09/2026 | 18/09/2026 | 189 | 173 | 16 |  |  | 2026-10-09 | 19/09/2026 | 29/08/2026 | 2026-07-09 | 189 | 188 | 1
ADIDAS | 0903135588-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135588 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 29/08/2026 | 31/08/2026 | 20/08/2026 | 29/08/2026 | 420 | 420
ADIDAS | 0903135590-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 811 | 15/10/2026 | 811 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135590 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 811 | 586 | 225 |  | 461 | 15/09/2026 | 17/09/2026 | 28/08/2026 | 2026-09-09 | 811 | 779 | 32
ADIDAS | 0903135646-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 84 | 15/10/2026 | 84 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135646 LI2646 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 84 | 84 |  |  |  | 29/08/2026 | 31/08/2026 | 19/08/2026 | 26/08/2026 | 84 | 84
ADIDAS | 0903135659-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135659 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 29/08/2026 | 2026-02-09 | 420 | 420
ADIDAS | 0903135683-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 67 | 15/10/2026 | 67 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135683 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 67 | 67 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 28/08/2026 | 67 | 67
ADIDAS | 0903135743-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 282 | 15/09/2026 | 282 | SA | SA26/06/2026 | G1K,G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135743 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 282 | 282 |  |  |  | 27/08/2026 | 31/08/2026 | 24/08/2026 | 2026-03-09 | 282 | 282
ADIDAS | 0903135819-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 122 | 2026-02-09 | 122 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135819 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 122 | 122 |  |  |  | 27/08/2026 | 29/08/2026 | 26/08/2026 | 2026-04-09 | 122 | 122
ADIDAS | 0903135839-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135839 LI2672 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 24/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/08/2026 | 28/08/2026 | 24/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 19/08/2026 | 24/08/2026 | 18/08/2026 | 2026-07-09 | 660 | 660
ADIDAS | 0903135865-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 247 | 23/10/2026 | 247 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135865 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 247 |  | 247 |  |  | 24/10/2026 | 26/10/2026 |  |  | 247 |  | 247
ADIDAS | 0903135961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 292 | 15/09/2026 | 292 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 292 | 292 |  |  |  | 29/08/2026 | 31/08/2026 | 21/08/2026 | 31/08/2026 | 292 | 292
ADIDAS | 0903136044-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 660 | 2026-08-09 | 660 | SA | SA26/06/2026 | G1B | ACCESSORIES | G1 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136044 LI2671 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/08/2026 | 28/08/2026 | 26/08/2026 | 28/08/2026 | 660 | 660 |  |  |  | 20/08/2026 | 24/08/2026 | 20/08/2026 | 2026-01-09 | 660 | 660
ADIDAS | 0903136117-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 778 | 2026-08-09 | 778 | SI | SI26/06/2026 | G2L | ACCESSORIES | G2 | ok | ok | 08/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136117 LI2645 | 2026-10-08 | KAHATEX CIJERAH | INDONESIA | SEA | 26/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 26/08/2026 | 28/08/2026 | 27/08/2026 | 28/08/2026 | 778 | 778 |  |  |  | 20/08/2026 | 24/08/2026 | 13/08/2026 | 28/08/2026 | 778 | 778
ADIDAS | 0903136141-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 119 | 2026-02-09 | 119 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136141 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 119 | 119 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-03-09 | 119 | 119
ADIDAS | 0903136653-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 136 | 23/10/2026 | 136 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136653 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-04-11 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 136 |  | 136 |  |  | 31/10/2026 | 31/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903136661-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 800 | 2026-07-10 | 800 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136661 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 18/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 18/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 800 | 265 | 535 |  | 265 | 15/09/2026 | 19/09/2026 | 31/08/2026 | 2026-12-09 | 800 | 791 | 9
ADIDAS | 0903136713-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 580 | 23/10/2026 | 580 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 838103 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136713 LI2646 | 2026-10-08 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 580 | 563 | 17 |  | 119 | 15/09/2026 | 17/09/2026 | 22/08/2026 | 2026-09-09 | 580 | 534 | 46
ADIDAS | 0903136726-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 308 | 30/09/2026 | 308 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136726 LI2670 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 23/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 308 |  | 308 |  |  | 19/09/2026 | 22/09/2026 |  |  | 308 |  | 308
ADIDAS | 0903136848-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 249 | 23/10/2026 | 249 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136848 LI2670 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 249 |  | 249 |  |  | 16/10/2026 | 19/10/2026 |  |  | 249 |  | 249
ADIDAS | 0903136900-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 254 | 23/10/2026 | 254 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136900 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 254 |  | 254 |  |  | 31/10/2026 | 31/10/2026 | 27/08/2026 | 2026-01-09 | 254 | 254
ADIDAS | 0903136925-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 104 | 30/09/2026 | 104 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136925 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-03-10 | 2026-03-10 |  |  | 104 |  | 104 |  |  | 30/09/2026 | 30/09/2026 |  |  | 104 |  | 104
ADIDAS | 0903136961-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 422 | 30/09/2026 | 422 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136961 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 18/09/2026 | 17/09/2026 | 18/09/2026 | 422 | 422 |  |  |  | 2026-10-09 | 15/09/2026 | 29/08/2026 | 2026-07-09 | 422 | 419 | 3
ADIDAS | 0903136981-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 417 | 23/10/2026 | 417 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136981 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 417 |  | 417 |  |  | 21/10/2026 | 23/10/2026 |  |  | 417 |  | 417
ADIDAS | 0903136996-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 277 | 15/09/2026 | 277 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | (08/08/2026) | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136996 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-02-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 277 | 277 |  |  |  | 29/08/2026 | 2026-02-09 | 21/08/2026 | 26/08/2026 | 277 | 277
ADIDAS | 0903137027-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 420 | 2026-12-09 | 420 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137027 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-02-09 | 2026-03-09 | 420 | 420 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903137049-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 117 | 15/09/2026 | 117 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137049 LI2672 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-01-09 | 2026-03-09 | 2026-02-09 | 2026-03-09 | 117 | 117 |  |  |  | 28/08/2026 | 31/08/2026 | 31/08/2026 | 2026-12-09 | 117 | 117
ADIDAS | 0903137111-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 194 | 15/09/2026 | 194 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137111 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-12-09 | 15/09/2026 | 15/09/2026 | 15/09/2026 | 194 | 194 |  |  |  | 2026-09-09 | 2026-11-09 | 2026-03-09 | 15/09/2026 | 194 | 194
ADIDAS | 0903137134-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 358 | 15/09/2026 | 358 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903137134 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 2026-02-09 | 2026-11-09 | 2026-03-09 | 15/09/2026 | 358 | 358 |  |  |  | 29/08/2026 | 2026-08-09 | 31/08/2026 | 2026-07-09 | 358 | 358
ADIDAS | 0903137310-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 382 | 30/09/2026 | 382 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 29/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137310 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 382 |  | 382 |  |  | 18/09/2026 | 19/09/2026 |  |  | 382 |  | 382
ADIDAS | 0903137434-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 4525 | 15/10/2026 | 4525 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137434 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 19/10/2026 | 2026-03-11 |  |  | 4525 |  | 4525 |  |  | 15/10/2026 | 30/10/2026 |  |  | 4525 |  | 4525
ADIDAS | 0903137501-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 320 | 30/09/2026 | 320 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137501 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 320 |  | 320 |  |  | 24/09/2026 | 28/09/2026 | 28/08/2026 | 2026-01-09 | 320 | 51 | 269
ADIDAS | 0903137540-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 401 | 15/10/2026 | 401 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137540 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 401 |  | 401 |  |  | 2026-02-10 | 2026-03-10 |  |  | 401 |  | 401
ADIDAS | 0903137727-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 132 | 30/09/2026 | 132 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903137727 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-10 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 132 |  | 132 |  |  | 28/09/2026 | 29/09/2026 | 27/08/2026 | 2026-07-09 | 132 | 132
ADIDAS | 0903138028-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 420 | 2026-12-09 | 420 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138028 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-09 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 420 | 420 |  |  |  | 29/08/2026 | 2026-09-09 | 31/08/2026 | 2026-10-09 | 420 | 420
ADIDAS | 0903138063-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 137 | 30/09/2026 | 137 | SI | SI26/06/2026 | G1M | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138063 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 137 |  | 137 |  |  | 29/09/2026 | 30/09/2026 |  |  | 137 |  | 137
ADIDAS | 0903138297-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 266 | 2026-02-09 | 266 | SA | SA26/06/2026 | G1B,G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138297 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 266 | 266 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 266 | 266
ADIDAS | 0903138432-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 158 | 2026-02-09 | 158 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138432 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 158 | 158 |  |  |  | 27/08/2026 | 28/08/2026 | 22/08/2026 | 29/08/2026 | 158 | 158
ADIDAS | 0903138575-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 276 | 15/10/2026 | 276 | SA | SA26/06/2026 | G1P | ACCESSORIES | G1 | (08/08/2026) | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138575 LI2671 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-11 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 276 |  | 276 |  |  | 30/10/2026 | 31/10/2026 |  |  | 276 |  | 276
ADIDAS | 0903138615-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 158 | 2026-07-10 | 158 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 814006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138615 LI2672 | 2026-10-08 | KAHATEX CIJERAH | THAILAND | SEA | 18/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 158 | 133 | 25 |  | 98 | 15/09/2026 | 19/09/2026 | 31/08/2026 | 2026-07-09 | 158 | 155 | 3
ADIDAS | 0903139177-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 107 | 23/10/2026 | 107 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139177 LI2647 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 107 |  | 107 |  |  | 2026-04-11 | 2026-04-11 |  |  | 107 |  | 107
ADIDAS | 0903139269-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 563 | 2026-07-10 | 563 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139269 LI2646 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 563 | 527 | 36 |  |  | 15/09/2026 | 17/09/2026 | 15/08/2026 | 2026-07-09 | 563 | 550 | 13
ADIDAS | 0903139328-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 707 | 23/09/2026 | 707 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 21/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903139328 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 19/09/2026 | 707 | 707 |  |  | 100 | 2026-11-09 | 17/09/2026 | 27/08/2026 | 31/08/2026 | 707 | 706 | 1
ADIDAS | 0903139403-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 112 | 2026-02-09 | 112 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139403 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 112 | 112 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-03-09 | 112 | 112
ADIDAS | 0903139439-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 584 | 23/09/2026 | 584 | SA | SA26/06/2026 | G1G,G1I | ACCESSORIES | G1 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139439 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 14/09/2026 | 21/09/2026 | 15/09/2026 | 18/09/2026 | 584 | 584 |  |  |  | 2026-10-09 | 17/09/2026 | 31/08/2026 | 18/09/2026 | 584 | 584
ADIDAS | 0903139469-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 105 | 2026-07-10 | 105 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | ok | ok | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139469 LI2672 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 105 | 105 |  |  | 28 | 15/09/2026 | 19/09/2026 | 31/08/2026 | 2026-07-09 | 105 | 105
ADIDAS | 0903139660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 234 | 15/09/2026 | 234 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139660 LI2671 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-04-09 | 234 | 234 |  |  |  | 27/08/2026 | 31/08/2026 | 29/08/2026 | 2026-02-09 | 234 | 234
ADIDAS | 0903139767-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 136 | 2026-02-09 | 136 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139767 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 136 | 136 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-04-09 | 136 | 136
ADIDAS | 0903140620-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 500 | 31/10/2026 | 500 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903140620 KG3190 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 15/10/2026 | Run Ess Tee M CARBON S18 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 500 |  | 500 |  |  | 2026-12-10 | 13/10/2026 |  |  | 500 |  | 500 |  |  | 2026-09-10 | 2026-10-10 |  |  | 500 |  | 500
ADIDAS | 0903140969-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 5996 | 23/10/2026 | 5996 | SI | SI26/06/2026 | G1Q | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903140969 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 30/10/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 30/10/2026 | 2026-06-11 |  |  | 5996 |  | 5996 |  |  | 27/10/2026 | 2026-03-11 |  |  | 5996 |  | 5996
ADIDAS | 0903140992-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 2091 | 23/10/2026 | 2091 | SA | SA26/06/2026 | G1I | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903140992 LI2672 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 27/10/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 27/10/2026 | 30/10/2026 |  |  | 2091 |  | 2091 |  |  | 23/10/2026 | 27/10/2026 |  |  | 2091 |  | 2091
ADIDAS | 0903141018-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903141018 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-04-11 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-04-11 | 2026-07-11 |  |  | 3656 |  | 3656 |  |  | 31/10/2026 | 2026-04-11 |  |  | 3656 |  | 3656
ADIDAS | 0903141059-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 2521 | 23/10/2026 | 2521 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141059 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 30/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 30/10/2026 | 2026-04-11 |  |  | 2521 |  | 2521 |  |  | 27/10/2026 | 31/10/2026 |  |  | 2521 |  | 2521
ADIDAS | 0903141111-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3286 | 23/10/2026 | 3286 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903141111 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 22/10/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 22/10/2026 | 28/10/2026 |  |  | 3286 |  | 3286 |  |  | 19/10/2026 | 24/10/2026 |  |  | 3286 |  | 3286
ADIDAS | 0903142132-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 250 | 2026-12-09 | 250 | SA | SA26/06/2026 | G1K | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142132 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 250 | 250 |  |  |  | 27/08/2026 | 29/08/2026 | 24/08/2026 | 31/08/2026 | 250 | 250
ADIDAS | 0903142255-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 3656 | 23/10/2026 | 3656 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | (08/08/2026) | ok | 823016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142255 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-09-11 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-09-11 | 2026-12-11 |  |  | 3656 |  | 3656 |  |  | 2026-04-11 | 2026-09-11 |  |  | 3656 |  | 3656
ADIDAS | 0903142438-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142438 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 28/08/2026 | 24/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142507-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 100 | 26/09/2026 | 100 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142507 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 100 | 100 |  |  |  | 2026-05-09 | 2026-10-09 | 13/08/2026 | 13/08/2026 | 100 | 100
ADIDAS | 0903142516-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960006 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142516 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 31/08/2026 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 21/08/2026 | 31/08/2026 | 200 | 200
ADIDAS | 0903142526-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1R | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142526 LI2645 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 21/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 29/09/2026 |  |  | 8900 |  | 8900 |  |  | 17/09/2026 | 25/09/2026 |  |  | 8900 |  | 8900
ADIDAS | 0903142537-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 11-Sep. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903142537 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 150 |  | 150 |  |  | 24/09/2026 | 28/09/2026 |  |  | 150 |  | 150
ADIDAS | 0903142574-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10 Aug, actual receives 14-Sep. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142574 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903142580-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 160 | 2026-12-09 | 160 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 10/09: ex-fty 960026 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142580 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-03-09 | 2026-01-09 | 2026-03-09 | 160 | 160 |  |  |  | 27/08/2026 | 31/08/2026 | 26/08/2026 | 2026-04-09 | 160 | 160
ADIDAS | 0903142605-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G1N | ACCESSORIES | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903142605 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 23/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 100 |  | 100 |  |  | 19/09/2026 | 22/09/2026 | 2026-02-09 | 2026-02-09 | 100 | 2 | 98
ADIDAS | 0903142631-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 2950 | 30/09/2026 | 2950 | SI | SI26/06/2026 | G1A | ACCESSORIES | G1 | ok | ok | 24/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903142631 LI2647 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 24/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 2950 |  | 2950 |  |  | 21/09/2026 | 24/09/2026 |  |  | 2950 |  | 2950
ADIDAS | 0903142728-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 680 | 31/10/2026 | 680 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | (07/08/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903142728 LD0288 | 25/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 21/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 680 |  | 680 |  |  | 17/10/2026 | 19/10/2026 |  |  | 680 |  | 680 |  |  | 15/10/2026 | 16/10/2026 |  |  | 680 |  | 680
ADIDAS | 0903142768-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 1350 | 31/10/2026 | 1350 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142768 KB5959 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-11 | Run Ess Tee M |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 1350 |  | 1350 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1350 |  | 1350 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1350 |  | 1350
ADIDAS | 0903142831-1 KB5962 | WONDER CARGO S26 | 120D | S2608MR0900A | 1250 | 31/10/2026 | 1250 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142831 KB5962 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 30/10/2026 | Run Ess Tee M |  | SS27-TI | 30/10/2026 | 31/10/2026 |  |  | 1250 |  | 1250 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1250 |  | 1250 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1250 |  | 1250
ADIDAS | 0903142841-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 23/09/2026 | 1759 | SA | SA26/06/2026 | G2N | JACKET | G2 | ok | ok | 23/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903142841 JD1877 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 25/09/2026 |  |  | 1759 |  | 1759 |  |  | 18/09/2026 | 22/09/2026 | 18/09/2026 | 19/09/2026 | 1759 | 796 | 963 |  | 517
ADIDAS | 0903142873-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 23/09/2026 | 1079 | SI | SI26/06/2026 | G3I,G3K | PANTS | G3 | ok | ok | 22/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142873 JD5302 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | W 3S FT CF PT |  | SS27 | 15/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 1079 | 1016 | 63 |  | 459 | 2026-11-09 | 16/09/2026 | 27/08/2026 | 19/09/2026 | 1079 | 1073 | 6 |  | 14
ADIDAS | 0903142903-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G2O | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142903 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 400 |  | 400 |  |  | 18/09/2026 | 21/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903142926-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 399 | 23/09/2026 | 399 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903142926 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 19/09/2026 | 31/08/2026 | 18/09/2026 | 399 | 398 | 1 |  |  | 27/08/2026 | 16/09/2026 | 22/08/2026 | 2026-09-09 | 399 | 399
ADIDAS | 0903142998-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 718 | 23/09/2026 | 718 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516204 | EMBRO SUB PROCESS_V1 | 0903142998 JE6419 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-05-09 | 2026-08-09 | 718 | 718 |  |  |  | 31/08/2026 | 2026-04-09 | 15/08/2026 | 2026-07-09 | 718 | 718
ADIDAS | 0903143026-1 GK8824 | MEDIUM GREY HEATHER/BLACK | 60D | S211CSIM120FLTC | 899 | 2026-02-09 | 899 | SA | SA26/06/2026 | G2D,G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903143026 GK8824 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 29/08/2026 | 2026-01-09 | 899 | 899 |  |  |  | 24/08/2026 | 28/08/2026 | 21/08/2026 | 31/08/2026 | 899 | 899
ADIDAS | 0903143086-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 719 | 30/09/2026 | 719 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 29/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903143086 JE1309 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | W 3S WV SHO |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 719 |  | 719 |  |  | 18/09/2026 | 19/09/2026 |  |  | 719 |  | 719
ADIDAS | 0903143118-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 30/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 18/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903143118 JE6419 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 1318 | 1318 |  |  |  | 31/08/2026 | 2026-04-09 | 29/08/2026 | 31/08/2026 | 1318 | 1318
ADIDAS | 0903143145-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 300 | 30/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 29/09: ex-fty. T2 Libolon, PI Date 26-Jul, actual receives 17-Jul. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903143145 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S WV SHO |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 19/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903143303-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 600 | 23/09/2026 | 600 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 21/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143303 LI2667 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-03-09 | 2026-07-09 | 600 | 600 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 600 | 600
ADIDAS | 0903143351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 800 | 23/09/2026 | 800 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 21/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143351 LI2669 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-03-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 800 | 800 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-01-08 | 2026-11-08 | 800 | 800
ADIDAS | 0903143380-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 8900 | 30/09/2026 | 8900 | SI | SI26/06/2026 | G1A,G1R | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143380 LI2646 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-09 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-03-09 | 21/09/2026 | 2026-04-09 | 19/09/2026 | 8900 | 8403 | 497 |  | 1127 | 31/08/2026 | 17/09/2026 | 15/08/2026 | 18/09/2026 | 8900 | 8889 | 11
ADIDAS | 0903143435-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 1100 | 23/09/2026 | 1100 | AN | AN26/06/2026 | G1J | ACCESSORIES | G1 | ok | ok | 21/09: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903143435 LI2668 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-09 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-05-09 | 22/09/2026 | 2026-05-09 | 2026-08-09 | 1100 | 1085 | 15 |  |  | 2026-02-09 | 18/09/2026 | 19/08/2026 | 17/09/2026 | 1100 | 1100
ADIDAS | 0903143462-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 3900 | 30/09/2026 | 3900 | SA | SA26/06/2026 | G1E,G1O | ACCESSORIES | G1 | ok | ok | 24/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143462 LI2670 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-09 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 2026-02-09 | 21/09/2026 | 2026-03-09 | 19/09/2026 | 3900 | 2915 | 985 |  | 435 | 29/08/2026 | 17/09/2026 | 24/08/2026 | 19/09/2026 | 3900 | 3929 | -29 | 29 | 792
ADIDAS | 0903143489-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 5100 | 30/09/2026 | 5100 | SA | SA26/06/2026 | G1E,G1G,G1I | ACCESSORIES | G1 | ok | ok | 26/09: ex-fty 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143489 LI2671 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 2026-07-09 | 23/09/2026 | 2026-07-09 | 19/09/2026 | 5100 | 2758 | 2342 |  | 440 | 2026-03-09 | 19/09/2026 | 24/08/2026 | 14/09/2026 | 5100 | 5100
ADIDAS | 0903144181-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 220 | 2026-02-09 | 220 | SA | SA26/06/2026 | G1O | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144181 LI2670 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 31/08/2026 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 220 | 220 |  |  |  | 27/08/2026 | 28/08/2026 | 20/08/2026 | 2026-01-09 | 220 | 220
ADIDAS | 0903144303-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 200 | 2026-02-09 | 200 | SA | SA26/06/2026 | G1G,G1K | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144303 LI2671 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 200 | 200 |  |  |  | 27/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 200 | 195 | 5
ADIDAS | 0903144813-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 260 | 2026-02-09 | 260 | SA | SA26/06/2026 | G1E | ACCESSORIES | G1 | ok | ok | 01/09: ex-fty 960026 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903144813 LI2672 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 31/08/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-01-09 | 260 | 260 |  |  |  | 27/08/2026 | 29/08/2026 | 31/08/2026 | 2026-05-09 | 260 | 260
ADIDAS | 0903144953-1 LG9669 | BLACK | 120D | S2754WAS514C | 756 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903144953 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903145092-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 144 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903145092 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903145124-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 258 | 31/10/2026 | 258 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145124 LF0726 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 23/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 23/11/2026 | 25/11/2026 |  |  | 258 |  | 258 |  |  | 18/11/2026 | 20/11/2026 |  |  | 258 |  | 258
ADIDAS | 0903145175-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 23/09/2026 | 1319 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 22/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO SUB PROCESS_V1 | 0903145175 JE6414 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1319 |  | 1319 |  |  | 19/09/2026 | 22/09/2026 | 18/09/2026 | 19/09/2026 | 1319 | 1039 | 280 |  | 7
ADIDAS | 0903145234-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 1050 | 2026-12-09 | 1050 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 12/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145234 IM0081 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | U FI LOGO PT |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-12-09 | 1050 | 1050
ADIDAS | 0903145265-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 480 | 23/09/2026 | 480 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145265 JE6341 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 480 |  | 480 |  |  | 17/09/2026 | 18/09/2026 | 2026-03-09 | 19/09/2026 | 480 | 371 | 109 |  | 7
ADIDAS | 0903145293-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1318 | 23/09/2026 | 1318 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 21/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903145293 JE6419 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-08-09 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-08-09 | 21/09/2026 | 2026-08-09 | 17/09/2026 | 1318 | 1296 | 22 |  |  | 2026-04-09 | 17/09/2026 | 29/08/2026 | 2026-02-09 | 1318 | 1294 | 24
ADIDAS | 0903145318-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 499 | 30/09/2026 | 499 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145318 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 499 |  | 499 |  |  | 24/09/2026 | 26/09/2026 | 19/09/2026 | 19/09/2026 | 499 | 175 | 324 |  | 175
ADIDAS | 0903145343-1 IM0081 | OLIVE STRATA S23/BLACK | 60D | S2315KSWU257 | 451 | 2026-09-09 | 451 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145343 IM0081 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | U FI LOGO PT |  | SS27 | 31/08/2026 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 451 | 451 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-07-09 | 451 | 451
ADIDAS | 0903145368-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 450 | 2026-09-09 | 450 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516442 | PRINT L3 SUB PROCESS_V3 | 0903145368 IS4395 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-07-09 | 31/08/2026 | 2026-07-09 | 450 | 450 |  |  |  | 27/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 450 | 450
ADIDAS | 0903145380-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 315 | 15/10/2026 | 315 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10 Aug, actual receives 14-Sep. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145380 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M 3S CHELSEA B7 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 315 |  | 315 |  |  | 2026-08-10 | 2026-09-10 |  |  | 315 |  | 315
ADIDAS | 0903145392-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145392 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 330 |  | 330 |  |  | 2026-09-10 | 2026-10-10 |  |  | 330 |  | 330
ADIDAS | 0903145395-1 IS4395 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 09/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903145395 IS4395 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | IN RANGE |  | SS27 | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-09-09 | 1051 | 1051 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-03-09 | 1051 | 1051
ADIDAS | 0903145433-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 450 | 15/10/2026 | 450 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145433 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | M 3S CHELSEA B7 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 450 |  | 450 |  |  | 2026-09-10 | 2026-10-10 |  |  | 450 |  | 450
ADIDAS | 0903145448-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145448 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | M 3S CHELSEA B7 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 420 |  | 420 |  |  | 2026-10-10 | 2026-12-10 |  |  | 420 |  | 420
ADIDAS | 0903145462-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145462 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | M 3S CHELSEA B7 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 345 |  | 345 |  |  | 2026-10-10 | 2026-12-10 |  |  | 345 |  | 345
ADIDAS | 0903145473-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 420 | 15/10/2026 | 420 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145473 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 420 |  | 420 |  |  | 2026-12-10 | 14/10/2026 |  |  | 420 |  | 420
ADIDAS | 0903145504-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 960 | 30/09/2026 | 960 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145504 JD1877 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 960 |  | 960 |  |  | 21/09/2026 | 23/09/2026 |  |  | 960 |  | 960
ADIDAS | 0903145534-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 401 | 30/09/2026 | 401 | SI | SI26/06/2026 | G2A | JACKET | G2 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145534 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | W 3S FT FZ HD |  | SS27 | 17/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 401 | 189 | 212 |  | 134 | 14/09/2026 | 16/09/2026 | 28/08/2026 | 2026-11-09 | 401 | 386 | 15
ADIDAS | 0903145568-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2P | JACKET | G2 | ok | ok | 22/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145568 JE6340 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 22/09/2026 | 18/09/2026 | 19/09/2026 | 660 | 401 | 259 |  | 235 | 14/09/2026 | 18/09/2026 | 16/09/2026 | 17/09/2026 | 660 | 616 | 44
ADIDAS | 0903145571-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145571 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M 3S CHELSEA B7 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 435 |  | 435 |  |  | 2026-12-10 | 14/10/2026 |  |  | 435 |  | 435
ADIDAS | 0903145609-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 23/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145609 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-11 | M 3S CHELSEA B7 |  | SS27 | 2026-05-11 | 2026-06-11 |  |  | 330 |  | 330 |  |  | 2026-02-11 | 2026-03-11 |  |  | 330 |  | 330
ADIDAS | 0903145625-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 23/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903145625 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-11 | M 3S CHELSEA B7 |  | SS27 | 2026-05-11 | 2026-06-11 |  |  | 300 |  | 300 |  |  | 2026-02-11 | 2026-03-11 |  |  | 300 |  | 300
ADIDAS | 0903145627-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 23/09/2026 | 359 | SA | SA26/06/2026 | G2R | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903145627 JE6340 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 359 | 247 | 112 |  | 247 | 14/09/2026 | 19/09/2026 | 16/09/2026 | 18/09/2026 | 359 | 343 | 16
ADIDAS | 0903145643-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 235 | 31/10/2026 | 235 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145643 LF0729 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-11 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 235 |  | 235 |  |  | 29/10/2026 | 31/10/2026 |  |  | 235 |  | 235
ADIDAS | 0903146197-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 23/09/2026 | 128 | AN | AN26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903146197 LC8884 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | M RESORT T BLACK |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 128 | 119 | 9 |  | 19 | 15/09/2026 | 19/09/2026 | 28/07/2026 | 18/09/2026 | 128 | 128
ADIDAS | 0903146288-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 222 | 30/09/2026 | 222 | SI | SI26/06/2026 | G3J | PANTS | G3 | ok | (07/08/2026) | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146288 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 16/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 222 | 206 | 16 |  | 9 | 2026-12-09 | 17/09/2026 | 15/09/2026 | 15/09/2026 | 222 | 220 | 2
ADIDAS | 0903146309-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 150 | 30/09/2026 | 150 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Cargoport). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650036 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146309 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 23/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 150 |  | 150 |  |  | 19/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 150 | 150 |  |  | 150
ADIDAS | 0903146335-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 402 | 31/10/2026 | 402 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146335 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 402 |  | 402 |  |  | 24/10/2026 | 26/10/2026 |  |  | 402 |  | 402 |  |  | 22/10/2026 | 23/10/2026 |  |  | 402 |  | 402
ADIDAS | 0903146354-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 215 | 23/09/2026 | 215 | AN | AN26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903146354 KX0126 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 15/09/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 15/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 215 | 213 | 2 |  | 129 | 2026-11-09 | 16/09/2026 | 2026-05-08 | 18/09/2026 | 215 | 215
ADIDAS | 0903146356-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 414 | 31/10/2026 | 414 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146356 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 19/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 19/10/2026 | 19/10/2026 |  |  | 414 |  | 414 |  |  | 15/10/2026 | 15/10/2026 |  |  | 414 |  | 414 |  |  | 13/10/2026 | 13/10/2026 |  |  | 414 |  | 414
ADIDAS | 0903146377-1 KB5965 | BLACK | 120D | S2608MR0900A | 930 | 31/10/2026 | 930 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146377 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 22/10/2026 |  |  | 930 |  | 930 |  |  | 19/10/2026 | 19/10/2026 |  |  | 930 |  | 930 |  |  | 16/10/2026 | 16/10/2026 |  |  | 930 |  | 930
ADIDAS | 0903146398-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Cargoport). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146398 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 17/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 174 |  | 174 |  |  | 14/10/2026 | 15/10/2026 |  |  | 174 |  | 174 |  |  | 2026-08-10 | 2026-09-10 |  |  | 174 |  | 174
ADIDAS | 0903146415-1 KB5960 | WHITE | 120D | S2608MR0900A | 360 | 31/10/2026 | 360 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146415 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 26/10/2026 |  |  | 360 |  | 360 |  |  | 22/10/2026 | 22/10/2026 |  |  | 360 |  | 360 |  |  | 20/10/2026 | 20/10/2026 |  |  | 360 |  | 360
ADIDAS | 0903146436-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 120 | 31/10/2026 | 120 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | (Cargoport). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650036 | HT+PAD SUB PROCESS_V3 | 0903146436 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 | 19/09/2026 | 19/09/2026 | 120 | 120 |  |  | 120 | 16/10/2026 | 17/10/2026 | 19/09/2026 | 19/09/2026 | 120 | 120 |  |  | 120
ADIDAS | 0903146478-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 31/10/2026 | 102 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | (30/07/2026) | ok | Waiting fabric replacement (Cargoport). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 650036 | HT+PAD SUB PROCESS_V3 | 0903146478 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 30/10/2026 | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI | 30/10/2026 | 30/10/2026 |  |  | 102 |  | 102 |  |  | 27/10/2026 | 27/10/2026 |  |  | 102 |  | 102 |  |  | 24/10/2026 | 24/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903146484-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 308 | 15/10/2026 | 308 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146484 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-08-10 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 308 |  | 308 |  |  | 2026-05-10 | 2026-06-10 |  |  | 308 |  | 308
ADIDAS | 0903146497-1 KE8424 | BLACK | 120D | S2608MR0906A | 438 | 31/10/2026 | 438 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | (Cargoport). 650036 | HT+PAD SUB PROCESS_V3 | 0903146497 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 24/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 24/10/2026 | 27/10/2026 |  |  | 438 |  | 438 |  |  | 21/10/2026 | 23/10/2026 |  |  | 438 |  | 438 |  |  | 19/10/2026 | 21/10/2026 |  |  | 438 |  | 438
ADIDAS | 0903146520-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 274 | 15/10/2026 | 274 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146520 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 14/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 274 |  | 274 |  |  | 2026-10-10 | 2026-12-10 |  |  | 274 |  | 274
ADIDAS | 0903146532-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650036 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903146532 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 174 |  | 174 |  |  | 19/10/2026 | 20/10/2026 |  |  | 174 |  | 174 |  |  | 13/10/2026 | 14/10/2026 |  |  | 174 |  | 174
ADIDAS | 0903146599-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 895 | 15/10/2026 | 895 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903146599 KY5988 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-05-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-05-10 | 2026-06-10 |  |  | 895 |  | 895 |  |  | 2026-01-10 | 2026-02-10 |  |  | 895 |  | 895 |  |  | 25/09/2026 | 26/09/2026 |  |  | 895 |  | 895
ADIDAS | 0903146631-1 KB5960 | WHITE | 120D | S2608MR0900A | 1601 | 31/10/2026 | 1601 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903146631 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 27/10/2026 | Run Ess Tee M |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 1601 |  | 1601 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1601 |  | 1601 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1601 |  | 1601
ADIDAS | 0903146633-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 226 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146633 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903146708-1 LG9669 | BLACK | 120D | S2754WAS514C | 235 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903146708 LG9669 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146738-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 126 | 30/09/2026 | 126 | AN | AN26/06/2026 | G2D | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903146738 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 22/09/2026 |  |  | 126 |  | 126 |  |  | 18/09/2026 | 18/09/2026 |  |  | 126 |  | 126 |  |  | 17/09/2026 | 17/09/2026 |  |  | 126 |  | 126
ADIDAS | 0903146764-1 LG9669 | BLACK | 120D | S2754WAS514C | 333 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903146764 LG9669 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903146791-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 15/10/2026 | 100 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 512108 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903146791 KX7715 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 2026-08-10 | 13/10/2026 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-09-10 |  |  | 100 |  | 100
ADIDAS | 0903146836-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 174 | 30/09/2026 | 174 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Damco offline). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 688010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903146836 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 174 |  | 174 |  |  | 19/09/2026 | 19/09/2026 | 26/08/2026 | 31/08/2026 | 174 | 151 | 23
ADIDAS | 0903146867-1 JZ7711 | BLACK | 120D | S2608MR0202 | 274 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146867 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146909-1 KB5960 | WHITE | 120D | S2608MR0900A | 796 | 31/10/2026 | 796 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903146909 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 27/10/2026 |  |  | 796 |  | 796 |  |  | 22/10/2026 | 23/10/2026 |  |  | 796 |  | 796 |  |  | 20/10/2026 | 21/10/2026 |  |  | 796 |  | 796
ADIDAS | 0903146928-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 956 | 31/10/2026 | 956 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903146928 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | Run Ess Tee M |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 956 |  | 956 |  |  | 20/10/2026 | 21/10/2026 |  |  | 956 |  | 956 |  |  | 17/10/2026 | 19/10/2026 |  |  | 956 |  | 956
ADIDAS | 0903146963-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 220 | 31/10/2026 | 220 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146963 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 220 |  | 220 |  |  | 22/10/2026 | 24/10/2026 |  |  | 220 |  | 220 |  |  | 19/10/2026 | 21/10/2026 |  |  | 220 |  | 220
ADIDAS | 0903147001-1 KB5965 | BLACK | 120D | S2608MR0900A | 922 | 31/10/2026 | 922 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147001 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | Run Ess Tee M |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 922 |  | 922 |  |  | 17/10/2026 | 19/10/2026 |  |  | 922 |  | 922 |  |  | 15/10/2026 | 16/10/2026 |  |  | 922 |  | 922
ADIDAS | 0903147020-1 KT4840 | ONIX | 90D | S2408MR1600 | 386 | 15/10/2026 | 386 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? T2 Fu Hsun, PI Date 25-Jul, actual receives 18-Sep. 960026 | HT SUB PROCESS_V1 | 0903147020 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 386 |  | 386 |  |  | 13/10/2026 | 14/10/2026 |  |  | 386 |  | 386 |  |  | 2026-12-10 | 13/10/2026 |  |  | 386 |  | 386
ADIDAS | 0903147025-1 KE6712 | BLACK | 105D | S2608MR0601A | 448 | 15/10/2026 | 448 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147025 KE6712 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 448 |  | 448 |  |  | 2026-12-10 | 13/10/2026 |  |  | 448 |  | 448 |  |  | 2026-10-10 | 2026-12-10 |  |  | 448 |  | 448
ADIDAS | 0903147045-1 JD0957 | BLACK | 60D | S25ORISW311 | 800 | 15/10/2026 | 800 | ID | ID26/06/2026 | G3J | SHORTS | G3 | ok | ok | T2 Fu Hsun, PI Date 29-Jul, actual receives 14-Aug. T2 Libolon, PI Date 29-Jul, actual receives 09-Jul. 960006 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903147045 JD0957 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | ADIC SWIMSH 5IN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 800 |  | 800 |  |  | 29/09/2026 | 30/09/2026 |  |  | 800 |  | 800
ADIDAS | 0903147053-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 382 | 15/10/2026 | 382 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Damco offline). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | PAD+HT SUB PROCESS_V3 | 0903147053 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-12-10 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 382 |  | 382 |  |  | 2026-08-10 | 2026-12-10 |  |  | 382 |  | 382 |  |  | 2026-07-10 | 2026-10-10 |  |  | 382 |  | 382
ADIDAS | 0903147074-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 304 | 31/10/2026 | 304 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | (30/07/2026) | ok | Waiting fabric replacement (Damco offline). T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 688010 | HT+PAD SUB PROCESS_V3 | 0903147074 KE8420 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/10/2026 | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI | 30/10/2026 | 30/10/2026 |  |  | 304 |  | 304 |  |  | 27/10/2026 | 27/10/2026 |  |  | 304 |  | 304 |  |  | 24/10/2026 | 24/10/2026 |  |  | 304 |  | 304
ADIDAS | 0903147100-1 KE8424 | BLACK | 120D | S2608MR0906A | 306 | 31/10/2026 | 306 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147100 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 24/10/2026 | 27/10/2026 |  |  | 306 |  | 306 |  |  | 21/10/2026 | 23/10/2026 |  |  | 306 |  | 306 |  |  | 19/10/2026 | 21/10/2026 | 19/09/2026 | 19/09/2026 | 306 | 298 | 8 |  | 298
ADIDAS | 0903147122-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 820 | 31/10/2026 | 820 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903147122 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 17/10/2026 | 17/10/2026 |  |  | 820 |  | 820 |  |  | 14/10/2026 | 14/10/2026 |  |  | 820 |  | 820 |  |  | 2026-12-10 | 2026-12-10 |  |  | 820 |  | 820
ADIDAS | 0903147253-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147253 KD3911 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | RELEASED |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 881 | 708 | 173 |  | 207 | 15/09/2026 | 17/09/2026 | 13/09/2026 | 15/09/2026 | 881 | 874 | 7
ADIDAS | 0903147280-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1560 | 30/09/2026 | 1560 | SI | SI26/06/2026 | G1I | PANTS | G1 | ok | ok | 25/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903147280 HK7317 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | ESS SWTP |  | SS27 | 26/09/2026 | 2026-01-10 |  |  | 1560 |  | 1560 |  |  | 23/09/2026 | 28/09/2026 |  |  | 1560 |  | 1560
ADIDAS | 0903147309-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3C | PANTS | G3 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147309 JW7177 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 16/09/2026 | W 3S FT OH PT |  | SS27 | 16/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 1541 | 1300 | 241 |  | 73 | 2026-12-09 | 17/09/2026 | 2026-07-09 | 17/09/2026 | 1541 | 1445 | 96
ADIDAS | 0903147338-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G1Q | PANTS | G1 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903147338 HK7319 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-06-10 |  |  | 2641 |  | 2641 |  |  | 25/09/2026 | 2026-02-10 | 17/09/2026 | 19/09/2026 | 2641 | 1307 | 1334 |  | 514
ADIDAS | 0903147369-1 HL2270 | TEAM ROYAL BLUE/WHITE | 60D | S211CSIM120FLTC | 599 | 2026-02-09 | 599 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147369 HL2270 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | IN RANGE |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 599 | 599 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 599 | 599
ADIDAS | 0903147489-1 H57046 | BLACK/BLACK | 60D | S211CSIM120FLTC | 597 | 2026-02-09 | 597 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147489 H57046 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 2026-01-09 | 26/08/2026 | 29/08/2026 | 597 | 597 |  |  |  | 20/08/2026 | 28/08/2026 | 22/08/2026 | 27/08/2026 | 597 | 597
ADIDAS | 0903147513-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 881 | 30/09/2026 | 881 | SI | SI26/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903147513 KD3911 | 2026-10-08 | KAHATEX CIJERAH | SPAIN | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 881 | 875 | 6 |  | 19 | 2026-11-09 | 17/09/2026 | 13/09/2026 | 18/09/2026 | 881 | 881
ADIDAS | 0903147569-1 GK8823 | LEGEND INK F17/WHITE | 60D | S211CSIM120FLTC | 601 | 2026-02-09 | 601 | SA | SA26/06/2026 | G2S | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903147569 GK8823 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 28/08/2026 | M 3S FL TC PT |  | SS27 | 28/08/2026 | 2026-01-09 | 31/08/2026 | 2026-01-09 | 601 | 601 |  |  |  | 24/08/2026 | 28/08/2026 | 31/08/2026 | 31/08/2026 | 601 | 601
ADIDAS | 0903147631-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G1P | PANTS | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903147631 HK7317 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-05-10 |  |  | 2860 |  | 2860 |  |  | 24/09/2026 | 2026-01-10 |  |  | 2860 |  | 2860
ADIDAS | 0903147665-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516442 | EMBRO SUB PROCESS_V1 | 0903147665 JE6417 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1320 |  | 1320 |  |  | 28/09/2026 | 30/09/2026 | 2026-11-08 | 31/08/2026 | 1320 | 1320
ADIDAS | 0903147675-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 895 | 30/09/2026 | 895 | AN | AN26/06/2026 | G2D | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 16-Sep. 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903147675 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | TURKEY | SEA | 22/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 22/09/2026 | 23/09/2026 |  |  | 895 |  | 895 |  |  | 18/09/2026 | 19/09/2026 |  |  | 895 |  | 895 |  |  | 17/09/2026 | 18/09/2026 |  |  | 895 |  | 895
ADIDAS | 0903147765-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 900 | 30/09/2026 | 900 | SI | SI26/06/2026 | G2J | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903147765 JE0052 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | W 3S FT FZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 900 |  | 900 |  |  | 19/09/2026 | 22/09/2026 | 18/09/2026 | 19/09/2026 | 900 | 767 | 133 |  | 321
ADIDAS | 0903147789-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 23/09/2026 | 720 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903147789 JE6414 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 720 |  | 720 |  |  | 15/09/2026 | 19/09/2026 | 29/08/2026 | 2026-01-09 | 720 | 634 | 86
ADIDAS | 0903147800-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 838 | 15/10/2026 | 838 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147800 KX7716 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 2026-03-11 | 2026-07-11 |  |  | 838 |  | 838 |  |  | 30/10/2026 | 2026-04-11 |  |  | 838 |  | 838
ADIDAS | 0903147835-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 675 | 15/10/2026 | 675 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 516443 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903147835 KX7716 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 16/10/2026 | 21/10/2026 |  |  | 675 |  | 675 |  |  | 13/10/2026 | 17/10/2026 |  |  | 675 |  | 675
ADIDAS | 0903147850-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 660 | 30/09/2026 | 660 | SA | SA26/06/2026 | G2O | JACKET | G2 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903147850 JE6340 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 660 |  | 660 |  |  | 25/09/2026 | 28/09/2026 | 16/09/2026 | 18/09/2026 | 660 | 647 | 13
ADIDAS | 0903147881-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1319 | 30/09/2026 | 1319 | SA | SA26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903147881 JE6414 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-03-10 |  |  | 1319 |  | 1319 |  |  | 26/09/2026 | 30/09/2026 | 2026-11-08 | 2026-01-09 | 1319 | 493 | 826
ADIDAS | 0903147940-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 241 | 15/09/2026 | 241 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903147940 LE8193 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 241 | 241 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-07-09 | 241 | 241
ADIDAS | 0903147997-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 335 | 23/09/2026 | 335 | AN | AN26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 19/09: ex-fty. DRC 0090-early shipment customer (BTP_05_08_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L2+PAD SUB PROCESS_V3 | 0903147997 LC8884 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 18/09/2026 | M RESORT T BLACK |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 335 | 335 |  |  |  | 15/09/2026 | 19/09/2026 | 28/07/2026 | 2026-11-08 | 335 | 335
ADIDAS | 0903148037-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV-MTF | 1321 | 30/09/2026 | 1321 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, using fabric stock (PO 26000011). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903148037 JE1309 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | W 3S WV SHO |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1321 |  | 1321 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903148050-1 KE8424 | BLACK | 120D | S2608MR0906A | 1085 | 31/10/2026 | 1085 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903148050 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 27/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 1085 |  | 1085 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1085 |  | 1085 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1085 |  | 1085
ADIDAS | 0903148066-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2P | JACKET | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903148066 JE6338 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | M 3S FT FZ HD |  | SS27 | 17/09/2026 | 22/09/2026 | 17/09/2026 | 18/09/2026 | 1760 | 279 | 1481 |  |  | 14/09/2026 | 18/09/2026 | 2026-03-09 | 19/09/2026 | 1760 | 1227 | 533 |  | 568
ADIDAS | 0903148083-1 LC6583 | GREY | 105D | S2750MTR051 | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 830009 | HT SUB PROCESS_V1 | 0903148083 LC6583 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | D4T ESS T GREY |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 110 |  | 110 |  |  | 25/09/2026 | 26/09/2026 |  |  | 110 |  | 110 |  |  | 24/09/2026 | 25/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903148089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 719 | 30/09/2026 | 719 | SA | SA26/06/2026 | G2E | SHORTS | G2 | ok | ok | 24/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903148089 JE6417 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 719 |  | 719 |  |  | 19/09/2026 | 22/09/2026 | 2026-11-08 | 2026-01-09 | 719 | 715 | 4
ADIDAS | 0903148210-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 26/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516471 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148210 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-11-09 | 15/09/2026 | 300 | 300 |  |  |  | 2026-05-09 | 2026-12-09 | 26/08/2026 | 2026-11-09 | 300 | 300
ADIDAS | 0903148659-1 LF0727 | BLACK | 120D | S2754MAS510B | 143 | 31/10/2026 | 143 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148659 LF0727 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-03-11 | M SL WV TT BLACK |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 143 |  | 143 |  |  | 30/10/2026 | 2026-02-11 |  |  | 143 |  | 143
ADIDAS | 0903148669-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 150 | 31/10/2026 | 150 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 826010 | HT+PAD SUB PROCESS_V3 | 0903148669 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 150 |  | 150 |  |  | 19/10/2026 | 20/10/2026 | 19/09/2026 | 19/09/2026 | 150 | 149 | 1 |  | 149 | 16/10/2026 | 17/10/2026 | 19/09/2026 | 19/09/2026 | 150 | 149 | 1 |  | 149
ADIDAS | 0903148695-1 KE8424 | BLACK | 120D | S2608MR0906A | 146 | 31/10/2026 | 146 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148695 KE8424 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 24/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 24/10/2026 | 27/10/2026 |  |  | 146 |  | 146 |  |  | 21/10/2026 | 23/10/2026 |  |  | 146 |  | 146 |  |  | 19/10/2026 | 21/10/2026 |  |  | 146 |  | 146
ADIDAS | 0903148707-1 LG9675 | BLACK | 120D | S2754WAS513C | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903148707 LG9675 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903148758-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 393 | 30/10/2026 | 393 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148758 LG9666 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-10-11 | W SL WV TT BLACK |  | SS27 | 2026-10-11 | 13/11/2026 |  |  | 393 |  | 393 |  |  | 2026-05-11 | 2026-10-11 |  |  | 393 |  | 393
ADIDAS | 0903148776-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 561 | 15/10/2026 | 561 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148776 KY5988 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-03-10 | 2026-05-10 |  |  | 561 |  | 561 |  |  | 30/09/2026 | 2026-01-10 |  |  | 561 |  | 561 |  |  | 24/09/2026 | 25/09/2026 |  |  | 561 |  | 561
ADIDAS | 0903148797-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 603 | 23/09/2026 | 603 | SI | SI26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Gistex, PI Date 27-Jul, Body: actual receives 20-Jul, Mesh: actual receives 13-Jul. 659018 | HT SUB PROCESS_V1 | 0903148797 IL4127 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/08/2026 | OWN THE RUN TEE |  | SS27 | 13/08/2026 | 21/09/2026 | 14/08/2026 | 2026-03-09 | 603 | 603 |  |  |  | 2026-11-08 | 18/09/2026 | 30/07/2026 | 2026-06-08 | 603 | 603 |  |  |  | 2026-10-08 | 17/09/2026 | 29/07/2026 | 13/08/2026 | 603 | 603
ADIDAS | 0903148818-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 318 | 23/09/2026 | 318 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148818 LE8181 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 318 |  | 318 |  |  | 15/09/2026 | 19/09/2026 |  |  | 318 |  | 318
ADIDAS | 0903148821-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 443 | 15/09/2026 | 443 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903148821 LE8193 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-08-09 | 2026-02-09 | 2026-09-09 | 443 | 443 |  |  |  | 27/08/2026 | 2026-04-09 | 20/08/2026 | 2026-02-09 | 443 | 443
ADIDAS | 0903148878-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148878 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | W 3S FT OH PT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 437 |  | 437 |  |  | 2026-05-10 | 2026-06-10 |  |  | 437 |  | 437
ADIDAS | 0903148893-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 312 | 23/09/2026 | 312 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903148893 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 23/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 312 |  | 312 |  |  | 19/09/2026 | 19/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903148919-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 383 | 31/10/2026 | 383 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 680015 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148919 LG9661 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 383 |  | 383 |  |  | 2026-10-11 | 2026-11-11 |  |  | 383 |  | 383
ADIDAS | 0903148948-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 142 | 15/10/2026 | 142 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903148948 LD6542 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 20/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 142 |  | 142 |  |  | 16/10/2026 | 17/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903148963-1 LE8187 | BLACK | 105D | S2754MAS513 | 174 | 15/10/2026 | 174 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148963 LE8187 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 174 |  | 174 |  |  | 30/09/2026 | 2026-01-10 |  |  | 174 |  | 174
ADIDAS | 0903148974-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 948 | 2026-02-10 | 948 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | (28/08/2026) | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903148974 LD0930 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-10 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-09-10 | 2026-12-10 |  |  | 948 |  | 948 |  |  | 2026-06-10 | 2026-08-10 |  |  | 948 |  | 948 |  |  | 2026-03-10 | 2026-06-10 |  |  | 948 |  | 948
ADIDAS | 0903148990-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 455 | 15/10/2026 | 455 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148990 LF0718 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-10 | M SL WV OH PT BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 455 |  | 455 |  |  | 2026-02-10 | 2026-05-10 |  |  | 455 |  | 455
ADIDAS | 0903148994-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 437 | 15/10/2026 | 437 | SA | SA26/06/2026 | G3D | PANTS | G3 | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903148994 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-10 | M 3S FT TC PT |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 437 |  | 437 |  |  | 30/09/2026 | 2026-01-10 |  |  | 437 |  | 437
ADIDAS | 0903149007-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 101 | 30/09/2026 | 101 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty 838103 | PAD+HT SUB PROCESS_V3 | 0903149007 JG5832 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 25/09/2026 | SQUA133 JSY M BLACK/WHITE |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 101 |  | 101 |  |  | 22/09/2026 | 22/09/2026 |  |  | 101 |  | 101 |  |  | 21/09/2026 | 21/09/2026 | 17/09/2026 | 17/09/2026 | 101 | 101
ADIDAS | 0903149019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Aug. T2 Libolon, PI Date 22-Jul, actual receives 25-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149019 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 |  |  | 1 |  | 1
ADIDAS | 0903149035-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1 | 23/09/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 10-Sep. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149035 KZ3231 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 17/09/2026 | 23/09/2026 |  |  | 1 |  | 1 |  |  | 14/09/2026 | 19/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 660 | 15/10/2026 | 660 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903149036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 15/10/2026 |  |  | 660 |  | 660 |  |  | 2026-12-10 | 2026-12-10 |  |  | 660 |  | 660 |  |  | 2026-06-10 | 2026-06-10 |  |  | 660 |  | 660
ADIDAS | 0903149043-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149043 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 1 |  | 1 |  |  | 15/09/2026 | 19/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149056-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 1 | 23/09/2026 | 1 | AN | AN26/06/2026 | G2R | SHORTS | G2 |  |  | 23/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149056 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/09/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 17/09/2026 | 23/09/2026 |  |  | 1 |  | 1 |  |  | 14/09/2026 | 19/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149084-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 712 | 31/10/2026 | 712 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 659018 | HT+PAD SUB PROCESS_V3 | 0903149084 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 712 |  | 712 |  |  | 21/10/2026 | 22/10/2026 | 18/09/2026 | 18/09/2026 | 712 | 626 | 86 |  |  | 19/10/2026 | 20/10/2026 | 17/09/2026 | 18/09/2026 | 712 | 626 | 86
ADIDAS | 0903149090-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G3H | PANTS | G3 | ok | (07/08/2026(3)) | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 04-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149090 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-08 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-06-08 | 2026-10-08 | 2026-07-08 | 2026-07-08 | 1 | 1 |  |  |  | 2026-03-08 | 2026-05-08 | 2026-07-08 | 2026-07-08 | 1 | 1
ADIDAS | 0903149104-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 1 | 23/09/2026 | 1 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149104 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 1 |  | 1 |  |  | 15/09/2026 | 19/09/2026 |  |  | 1 |  | 1
ADIDAS | 0903149132-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 387 | 29/09/2026 | 387 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903149132 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 23/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 387 |  | 387 |  |  | 19/09/2026 | 21/09/2026 | 26/08/2026 | 2026-03-09 | 387 | 369 | 18
ADIDAS | 0903149247-1 KT4840 | ONIX | 90D | S2408MR1600 | 150 | 15/10/2026 | 150 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903149247 KT4840 | 2026-10-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 150 |  | 150 |  |  | 13/10/2026 | 14/10/2026 | 2026-12-09 | 2026-12-09 | 150 | 2 | 148 |  |  | 2026-12-10 | 13/10/2026 | 2026-05-09 | 2026-05-09 | 150 | 2 | 148
ADIDAS | 0903149255-1 KT4840 | ONIX | 90D | S2408MR1600 | 352 | 31/10/2026 | 352 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903149255 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 18/11/2026 | ADIZERO E TEE |  | SS27-YTI | 18/11/2026 | 19/11/2026 |  |  | 352 |  | 352 |  |  | 16/11/2026 | 17/11/2026 |  |  | 352 |  | 352 |  |  | 13/11/2026 | 16/11/2026 |  |  | 352 |  | 352
ADIDAS | 0903149303-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/10/2026 | 100 | SI | SI26/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149303 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 100 |  | 100 |  |  | 2026-05-11 | 2026-05-11 |  |  | 100 |  | 100 |  |  | 2026-02-11 | 2026-02-11 |  |  | 100 |  | 100
ADIDAS | 0903149363-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 158 | 31/10/2026 | 158 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149363 KR3066 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-06-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-06-11 | 2026-07-11 |  |  | 158 |  | 158 |  |  | 2026-03-11 | 2026-04-11 |  |  | 158 |  | 158 |  |  | 30/10/2026 | 31/10/2026 |  |  | 158 |  | 158
ADIDAS | 0903149419-1 KT4840 | ONIX | 90D | S2408MR1600 | 2315 | 23/09/2026 | 2315 | SA | SA26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 19/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903149419 KT4840 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 15/09/2026 | 19/09/2026 | 2315 | 2315 |  |  | 156 | 2026-12-09 | 18/09/2026 | 2026-08-09 | 18/09/2026 | 2315 | 2315 |  |  |  | 2026-11-09 | 17/09/2026 | 2026-07-09 | 18/09/2026 | 2315 | 2315
ADIDAS | 0903149656-1 HK7319 | BLACK | 90D | F2225M403 | 400 | 30/09/2026 | 400 | SI | SI26/06/2026 | G1Q | PANTS | G1 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149656 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 400 |  | 400 |  |  | 24/09/2026 | 25/09/2026 | 16/09/2026 | 18/09/2026 | 400 | 331 | 69
ADIDAS | 0903149744-1 HK7319 | BLACK | 90D | F2225M403 | 2641 | 30/09/2026 | 2641 | SI | SI26/06/2026 | G1P | PANTS | G1 | ok | ok | 25/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149744 HK7319 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 17/09/2026 | ESS SWTP |  | SS27 | 17/09/2026 | 24/09/2026 | 18/09/2026 | 19/09/2026 | 2641 | 110 | 2531 |  | 85 | 14/09/2026 | 21/09/2026 | 15/09/2026 | 19/09/2026 | 2641 | 2174 | 467 |  | 9
ADIDAS | 0903149771-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 600 | 30/09/2026 | 600 | SI | SI26/06/2026 | G1F | PANTS | G1 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903149771 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 600 |  | 600 |  |  | 24/09/2026 | 26/09/2026 |  |  | 600 |  | 600
ADIDAS | 0903149833-1 HZ0747 | BLACK | 90D | F2325M414 | 399 | 23/09/2026 | 399 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903149833 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 19/09/2026 | 16/09/2026 | 19/09/2026 | 399 | 387 | 12 |  | 3 | 2026-11-09 | 16/09/2026 | 31/08/2026 | 2026-02-09 | 399 | 398 | 1
ADIDAS | 0903149866-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G1F | PANTS | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903149866 HR8583 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | ESS SWTP |  | SS27 | 19/09/2026 | 28/09/2026 |  |  | 3300 |  | 3300 |  |  | 16/09/2026 | 24/09/2026 | 16/09/2026 | 19/09/2026 | 3300 | 650 | 2650 |  | 226
ADIDAS | 0903149894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | (28/07/2026) | ok | 25/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149894 IB8686 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 2200 |  | 2200 |  |  | 26/09/2026 | 29/09/2026 | 2026-12-08 | 19/09/2026 | 2200 | 2200 |  |  | 3
ADIDAS | 0903149953-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1200 | 23/09/2026 | 1200 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903149953 IB8686 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | ESS TEE |  | SS27 | 16/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 1200 | 1052 | 148 |  | 341 | 2026-12-09 | 16/09/2026 | 26/08/2026 | 2026-01-09 | 1200 | 1200
ADIDAS | 0903149971-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 820 | 15/10/2026 | 820 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 07-Sep, ETD ?? T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903149971 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 820 |  | 820 |  |  | 16/10/2026 | 17/10/2026 |  |  | 820 |  | 820 |  |  | 15/10/2026 | 16/10/2026 |  |  | 820 |  | 820
ADIDAS | 0903149978-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 28/09: ex-fty 516442 | EMBRO SUB PROCESS_V1 | 0903149978 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 19/09/2026 | PL TEE |  | SS27 | 19/09/2026 | 26/09/2026 | 18/09/2026 | 19/09/2026 | 4543 | 313 | 4230 |  | 74 | 16/09/2026 | 23/09/2026 | 16/09/2026 | 19/09/2026 | 4543 | 2293 | 2250 |  | 1237
ADIDAS | 0903150021-1 KA0246 | BLACK | 90D | S2608WR0902 | 399 | 2026-07-10 | 399 | SI | SI26/06/2026 | G2L | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516277 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903150021 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-01-10 |  |  | 399 |  | 399 |  |  | 26/09/2026 | 28/09/2026 |  |  | 399 |  | 399 |  |  | 23/09/2026 | 24/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903150041-1 GK8821 | BLACK/WHITE | 60D | S211CSIM120FLTC | 900 | 2026-02-09 | 900 | SA | SA26/06/2026 | G2F | PANTS | G2 | ok | ok | 01/09: ex-fty (S4EU). DRC 0090-early shipment customer (no need open ticket). 516442 | EMBRO SUB PROCESS_V1 | 0903150041 GK8821 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 26/08/2026 | M 3S FL TC PT |  | SS27 | 26/08/2026 | 31/08/2026 | 27/08/2026 | 31/08/2026 | 900 | 900 |  |  |  | 20/08/2026 | 27/08/2026 | 22/08/2026 | 2026-02-09 | 900 | 900
ADIDAS | 0903150045-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 1980 | 31/10/2026 | 1980 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 516415 | HT+PAD SUB PROCESS_V3 | 0903150045 KX3651 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 21/10/2026 | 22/10/2026 |  |  | 1980 |  | 1980 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1980 |  | 1980 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1980 |  | 1980
ADIDAS | 0903150068-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 2200 | 30/09/2026 | 2200 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 24/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150068 IB8686 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 19/09/2026 | ESS TEE |  | SS27 | 19/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 2200 | 155 | 2045 |  | 155 | 16/09/2026 | 18/09/2026 | 2026-11-08 | 31/08/2026 | 2200 | 2200
ADIDAS | 0903150072-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 1200 | 2026-07-10 | 1200 | SA | SA26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516260 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903150072 KY5988 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI | 2026-01-10 | 2026-03-10 |  |  | 1200 |  | 1200 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1200 |  | 1200 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903150101-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 360 | 30/09/2026 | 360 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903150101 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 360 |  | 360 |  |  | 24/09/2026 | 28/09/2026 | 2026-02-09 | 17/09/2026 | 360 | 341 | 19
ADIDAS | 0903150103-1 HZ0747 | BLACK | 90D | F2325M414 | 2478 | 23/09/2026 | 2478 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903150103 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 19/09/2026 | 15/09/2026 | 19/09/2026 | 2478 | 2416 | 62 |  | 29 | 2026-11-09 | 16/09/2026 | 2026-01-09 | 17/09/2026 | 2478 | 2478
ADIDAS | 0903150130-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1800 | 30/09/2026 | 1800 | SI | SI26/06/2026 | G1J | PANTS | G1 | ok | ok | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903150130 HR8583 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-02-10 |  |  | 1800 |  | 1800 |  |  | 24/09/2026 | 29/09/2026 | 15/09/2026 | 19/09/2026 | 1800 | 1006 | 794 |  | 190
ADIDAS | 0903150152-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | (08/08/2026) | ok | 26/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150152 JE6341 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 881 |  | 881 |  |  | 24/09/2026 | 26/09/2026 |  |  | 881 |  | 881
ADIDAS | 0903150214-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1759 | 30/09/2026 | 1759 | SA | SA26/06/2026 | G2N | JACKET | G2 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150214 JD1877 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 1759 |  | 1759 |  |  | 22/09/2026 | 26/09/2026 |  |  | 1759 |  | 1759
ADIDAS | 0903150279-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 901 | 30/09/2026 | 901 | SI | SI26/06/2026 | G2O | JACKET | G2 | ok | ok | 28/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903150279 JE0055 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | W 3S FT FZ HD |  | SS27 | 15/09/2026 | 19/09/2026 | 16/09/2026 | 19/09/2026 | 901 | 816 | 85 |  | 1 | 2026-11-09 | 16/09/2026 | 28/08/2026 | 17/09/2026 | 901 | 869 | 32
ADIDAS | 0903150285-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 300 | 31/10/2026 |  | AN | AN26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPA SUB PROCESS_V3 | 0903150285 LG9669 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903150304-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1760 | 30/09/2026 | 1760 | SA | SA26/06/2026 | G2O | JACKET | G2 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150304 JE6338 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-06-10 |  |  | 1760 |  | 1760 |  |  | 28/09/2026 | 2026-02-10 | 19/09/2026 | 19/09/2026 | 1760 | 1241 | 519 |  | 1241
ADIDAS | 0903150319-1 LF0727 | BLACK | 120D | S2754MAS510B | 1245 | 31/10/2026 | 1245 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150319 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-10-11 | M SL WV TT BLACK |  | SS27 | 2026-10-11 | 14/11/2026 |  |  | 1245 |  | 1245 |  |  | 2026-05-11 | 2026-11-11 |  |  | 1245 |  | 1245
ADIDAS | 0903150340-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 881 | 30/09/2026 | 881 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150340 JE6341 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 881 |  | 881 |  |  | 23/09/2026 | 24/09/2026 | 18/09/2026 | 18/09/2026 | 881 | 423 | 458
ADIDAS | 0903150366-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 959 | 23/09/2026 | 959 | SA | SA26/06/2026 | G2Q | JACKET | G2 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150366 JE6338 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | M 3S FT FZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 959 |  | 959 |  |  | 19/09/2026 | 22/09/2026 | 2026-03-09 | 19/09/2026 | 959 | 827 | 132 |  | 825
ADIDAS | 0903150392-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1321 | 30/09/2026 | 1321 | SI | SI26/06/2026 | G3J | SHORTS | G3 | (10/08/2026) | ok | 26/09: ex-fty. T2 Gistex, (3S) PI Date 10-Aug, actual receives 15-Sep. T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903150392 JE1309 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | W 3S WV SHO |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1321 |  | 1321 |  |  | 22/09/2026 | 24/09/2026 | 19/09/2026 | 19/09/2026 | 1321 | 975 | 346 |  | 975
ADIDAS | 0903150418-1 KB5960 | WHITE | 120D | S2608MR0900A | 1040 | 31/10/2026 | 1040 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150418 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 27/10/2026 |  |  | 1040 |  | 1040 |  |  | 22/10/2026 | 23/10/2026 |  |  | 1040 |  | 1040 |  |  | 20/10/2026 | 21/10/2026 |  |  | 1040 |  | 1040
ADIDAS | 0903150471-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1320 | 30/09/2026 | 1320 | SA | SA26/06/2026 | G2E | SHORTS | G2 | ok | ok | 28/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903150471 JE6417 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 25/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1320 |  | 1320 |  |  | 22/09/2026 | 24/09/2026 | 2026-11-08 | 2026-01-09 | 1320 | 1320
ADIDAS | 0903150495-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 500 | 30/09/2026 | 500 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903150495 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 500 |  | 500 |  |  | 18/09/2026 | 21/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903150517-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 372 | 29/09/2026 | 372 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150517 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 25/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 25/09/2026 | 28/09/2026 |  |  | 372 |  | 372 |  |  | 22/09/2026 | 24/09/2026 | 18/09/2026 | 19/09/2026 | 372 | 269 | 103 |  | 22 | 19/09/2026 | 22/09/2026 | 17/09/2026 | 19/09/2026 | 372 | 269 | 103 |  | 22
ADIDAS | 0903150541-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1148 | 14/10/2026 | 1148 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150541 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-08-10 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 1148 |  | 1148 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1148 |  | 1148 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1148 |  | 1148
ADIDAS | 0903150606-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 850 | 30/10/2026 | 850 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150606 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-08-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-08-10 | 2026-09-10 |  |  | 850 |  | 850 |  |  | 2026-05-10 | 2026-06-10 |  |  | 850 |  | 850 |  |  | 2026-02-10 | 2026-03-10 |  |  | 850 |  | 850
ADIDAS | 0903150629-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1235 | 14/10/2026 | 1235 | AN | AN29/06/2026 | G2L | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903150629 LD0283 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/09/2026 | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI | 29/09/2026 | 30/09/2026 |  |  | 1235 |  | 1235 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1235 |  | 1235 |  |  | 23/09/2026 | 24/09/2026 |  |  | 1235 |  | 1235
ADIDAS | 0903150630-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 648 | 30/09/2026 | 648 | SA | SA26/06/2026 | G2L,G2M | T-SHIRT | G2 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903150630 LE8210 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-12-09 | 18/09/2026 | 2026-12-09 | 16/09/2026 | 648 | 648 |  |  |  | 2026-09-09 | 15/09/2026 | 2026-08-09 | 14/09/2026 | 648 | 648
ADIDAS | 0903150899-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 181 | 30/09/2026 | 181 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903150899 LC6339 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 181 |  | 181 |  |  | 2026-01-10 | 2026-02-10 | 2026-08-09 | 19/09/2026 | 181 | 172 | 9 |  | 15
ADIDAS | 0903150944-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 345 | 30/09/2026 | 345 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150944 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 345 |  | 345 |  |  | 2026-01-10 | 2026-02-10 | 2026-08-09 | 2026-09-09 | 345 | 335 | 10
ADIDAS | 0903150972-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 126 | 15/10/2026 | 126 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150972 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 126 |  | 126 |  |  | 30/09/2026 | 2026-01-10 |  |  | 126 |  | 126
ADIDAS | 0903150974-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 534 | 31/10/2026 | 534 | SA | SA26/06/2026 | G2N | T-SHIRT | G2 | (28/07/2026) | ok | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903150974 LC6339 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-02-11 | 2026-03-11 |  |  | 534 |  | 534 |  |  | 29/10/2026 | 30/10/2026 | 2026-08-09 | 2026-09-09 | 534 | 467 | 67
ADIDAS | 0903151028-1 IS1413 | BLACK | 60D | S2425M405 | 378 | 2026-12-09 | 378 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903151028 IS1413 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 378 | 378 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-11-08 | 2026-03-09 | 378 | 378
ADIDAS | 0903151067-1 HK7319 | BLACK | 90D | F2225M403 | 378 | 31/10/2026 | 378 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 848016 | EMBRO+PPA SUB PROCESS_V3 | 0903151067 HK7319 |  | KAHATEX CIJERAH | MOROCCO | SEA | 21/10/2026 | ESS SWTP |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 378 |  | 378 |  |  | 17/10/2026 | 19/10/2026 |  |  | 378 |  | 378
ADIDAS | 0903151088-1 KC4947 | BLACK | 105D | S2608WR0216 | 566 | 15/10/2026 | 566 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD 07-Sep, ETA-Kaha 22-Sep. T2 Huge Bamboo, PI Date 29-Aug, actual receives 11-Sep. T2 Grand Tex, PI Date 10-Aug, actual receives 09-Sep. 806020 | PAD+HT SUB PROCESS_V3 | 0903151088 KC4947 | 24/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA | 2026-07-10 | adi365 Astro W |  | SS27-TRAX | 2026-07-10 | 2026-09-10 |  |  | 566 |  | 566 |  |  | 2026-03-10 | 2026-06-10 |  |  | 566 |  | 566 |  |  | 2026-02-10 | 2026-05-10 |  |  | 566 |  | 566
ADIDAS | 0903151096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903151096 IZ0443 | 28/07/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-02-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903151127-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903151127 JE6419 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 15/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 18/09/2026 | 540 | 531 | 9 |  |  | 2026-11-09 | 17/09/2026 | 18/08/2026 | 29/08/2026 | 540 | 540
ADIDAS | 0903151171-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151171 LC8884 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 | 2026-11-08 | 19/09/2026 | 100 | 98 | 2 |  | 2
ADIDAS | 0903151195-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1684 | 31/10/2026 | 1684 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903151195 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 21/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 21/10/2026 | 23/10/2026 |  |  | 1684 |  | 1684 |  |  | 17/10/2026 | 20/10/2026 |  |  | 1684 |  | 1684 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1684 |  | 1684
ADIDAS | 0903151218-1 JZ7766 | MEDIUM GREY HEATHER | 90D | S2608MR0901 | 112 | 31/10/2026 | 112 | AN | AN26/06/2026 | G1E | SHORTS | G1 |  |  | (NYK warehouse). Waiting fabric. T2 Formosa, PI Date 07-Sep. Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 07-Sep. 800005 | PAD+HT SUB PROCESS_V3 | 0903151218 JZ7766 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-11 | Run Ess Shor M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-06-11 | 2026-06-11 |  |  | 112 |  | 112 |  |  | 2026-03-11 | 2026-03-11 |  |  | 112 |  | 112 |  |  | 2026-02-11 | 2026-02-11 |  |  | 112 |  | 112
ADIDAS | 0903151219-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 327 | 15/10/2026 | 327 | SA | SA26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 659018 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903151219 LE5609 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/10/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 14/10/2026 | 14/10/2026 |  |  | 327 |  | 327 |  |  | 2026-10-10 | 2026-10-10 |  |  | 327 |  | 327 |  |  | 2026-05-10 | 2026-05-10 |  |  | 327 |  | 327
ADIDAS | 0903151248-1 LF0723 | BLACK | 105D | S2754MAS511B | 373 | 15/10/2026 | 373 | SI | SI26/06/2026 | G3A | SHORTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, PI Date 11-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 659018 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151248 LF0723 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-12-10 | M SL WV SHO BLACK |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 373 |  | 373 |  |  | 2026-08-10 | 2026-10-10 |  |  | 373 |  | 373
ADIDAS | 0903151275-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 991 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903151275 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903151295-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 839055 | PRINT L2+PAD SUB PROCESS_V3 | 0903151295 KX0126 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 14/10/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-10-10 | 2026-05-08 | 20/08/2026 | 100 | 94 | 6
ADIDAS | 0903151312-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 434 | 31/10/2026 | 434 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903151312 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 434 |  | 434 |  |  | 20/10/2026 | 21/10/2026 | 19/09/2026 | 19/09/2026 | 434 | 273 | 161 |  | 273 | 17/10/2026 | 19/10/2026 | 19/09/2026 | 19/09/2026 | 434 | 273 | 161 |  | 273
ADIDAS | 0903151313-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151313 JN1958 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 25/09/2026 | W 3S FT QZ HD |  | SS27 | 25/09/2026 | 28/09/2026 |  |  | 1540 |  | 1540 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151330-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1540 | 30/09/2026 | 1540 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 26/09: ex-fty 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151330 JN1958 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | W 3S FT QZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1540 |  | 1540 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1540 |  | 1540
ADIDAS | 0903151539-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 840 | 30/09/2026 | 840 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903151539 JN1958 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-09 | W 3S FT QZ HD |  | SS27 | 2026-12-09 | 23/09/2026 | 2026-12-09 | 18/09/2026 | 840 | 764 | 76 |  |  | 2026-09-09 | 19/09/2026 | 2026-09-09 | 15/09/2026 | 840 | 764 | 76
ADIDAS | 0903151579-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 1541 | 30/09/2026 | 1541 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151579 JW7177 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | W 3S FT OH PT |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 1541 |  | 1541 |  |  | 18/09/2026 | 21/09/2026 | 31/08/2026 | 17/09/2026 | 1541 | 1534 | 7
ADIDAS | 0903151624-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 24/09: ex-fty 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903151624 JW7178 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 21/09/2026 | W 3S FT OH PT |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 1431 |  | 1431 |  |  | 17/09/2026 | 18/09/2026 | 2026-12-09 | 19/09/2026 | 1431 | 1426 | 5 |  | 7
ADIDAS | 0903151645-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 355 | 15/10/2026 | 355 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903151645 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 355 |  | 355 |  |  | 19/10/2026 | 20/10/2026 |  |  | 355 |  | 355 |  |  | 13/10/2026 | 14/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903152156-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1054 | 29/09/2026 | 1054 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152156 KX3650 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/09/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 19/09/2026 | 21/09/2026 |  |  | 1054 |  | 1054 |  |  | 16/09/2026 | 17/09/2026 | 17/09/2026 | 19/09/2026 | 1054 | 740 | 314 |  | 4 | 14/09/2026 | 15/09/2026 | 17/09/2026 | 17/09/2026 | 1054 | 740 | 314
ADIDAS | 0903152165-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 752 | 30/09/2026 | 752 | SA | SA26/06/2026 | G2K,G2M | T-SHIRT | G2 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152165 LE8201 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 18/09/2026 | 2026-07-09 | 16/09/2026 | 752 | 752 |  |  |  | 2026-02-09 | 15/09/2026 | 2026-03-09 | 13/09/2026 | 752 | 752
ADIDAS | 0903152177-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 370 | 29/09/2026 | 370 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | (28/07/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152177 KX3654 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 17/09/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/09/2026 | 19/09/2026 |  |  | 370 |  | 370 |  |  | 14/09/2026 | 16/09/2026 |  |  | 370 |  | 370 |  |  | 2026-11-09 | 14/09/2026 |  |  | 370 |  | 370
ADIDAS | 0903152204-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 4012 | 19/09/2026 | 4012 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 14/09: ex-fty (NYK warehouse). DRC 0047-hold shipment customer. 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152204 LE8202 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-05-09 | 19/09/2026 | 2026-07-09 | 16/09/2026 | 4012 | 3614 | 398 |  |  | 2026-02-09 | 16/09/2026 | 21/08/2026 | 15/09/2026 | 4012 | 4012
ADIDAS | 0903152214-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 756 | 29/09/2026 | 756 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152214 KX3655 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 28/09/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 756 |  | 756 |  |  | 24/09/2026 | 25/09/2026 |  |  | 756 |  | 756 |  |  | 22/09/2026 | 23/09/2026 |  |  | 756 |  | 756
ADIDAS | 0903152235-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 351 | 30/09/2026 | 351 | SA | SA26/06/2026 | G2O | T-SHIRT | G2 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152235 LE8208 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 351 | 351 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-12-09 | 15/09/2026 | 351 | 351
ADIDAS | 0903152248-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 870 | 31/10/2026 | 870 | SI | SI26/06/2026 | G3D | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152248 KY9384 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-03-11 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-03-11 | 2026-04-11 |  |  | 870 |  | 870 |  |  | 30/10/2026 | 31/10/2026 |  |  | 870 |  | 870 |  |  | 27/10/2026 | 28/10/2026 |  |  | 870 |  | 870
ADIDAS | 0903152275-1 LE8194 | WHITE | 90D | F2606LHRM101FY | 1600 | 30/09/2026 | 1600 | SI | SI26/06/2026 | G1G,G1I | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152275 LE8194 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-09 | REAL HFY JSY SE WHITE |  | SS27-FJ | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-10-09 | 1600 | 1600 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-10-09 | 1600 | 1600
ADIDAS | 0903152279-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 875 | 15/09/2026 | 875 | AN | AN26/06/2026 | G3J,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152279 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-10-09 | 14/09/2026 | 875 | 875 |  |  |  | 31/08/2026 | 2026-04-09 | 2026-08-09 | 14/09/2026 | 875 | 875
ADIDAS | 0903152318-1 KE6712 | BLACK | 105D | S2608MR0601A | 1026 | 15/10/2026 | 1026 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 678002 | PAD+HT SUB PROCESS_V3 | 0903152318 KE6712 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/10/2026 | adi365 SHORT M BLACK |  | SS27-TRAX | 16/10/2026 | 19/10/2026 |  |  | 1026 |  | 1026 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1026 |  | 1026 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903152321-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 4210 | 30/09/2026 | 4210 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903152321 LE8193 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-02-09 | REAL H F JSY SE WHITE |  | SS27-FJ | 2026-02-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 4210 | 4210 |  |  |  | 29/08/2026 | 2026-11-09 | 18/08/2026 | 14/09/2026 | 4210 | 4210
ADIDAS | 0903152349-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 533 | 31/10/2026 | 533 | SI | SI26/06/2026 | G3C | PANTS | G3 | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152349 HK7317 |  | KAHATEX CIJERAH | CANADA | SEA | 26/10/2026 | ESS SWTP |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 533 |  | 533 |  |  | 22/10/2026 | 24/10/2026 |  |  | 533 |  | 533
ADIDAS | 0903152351-1 KE6899 | BLACK | 105D | S2608WR0601B | 661 | 15/10/2026 | 661 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903152351 KE6899 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/10/2026 | adi365 Short W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 661 |  | 661 |  |  | 22/10/2026 | 24/10/2026 |  |  | 661 |  | 661 |  |  | 21/10/2026 | 23/10/2026 |  |  | 661 |  | 661
ADIDAS | 0903152378-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 731 | 31/10/2026 | 731 | SI | SI26/06/2026 | G3K | PANTS | G3 | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152378 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA | 19/10/2026 | ESS SWTP |  | SS27 | 19/10/2026 | 22/10/2026 |  |  | 731 |  | 731 |  |  | 15/10/2026 | 19/10/2026 |  |  | 731 |  | 731
ADIDAS | 0903152382-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 828 | 29/09/2026 | 828 | AN | AN29/06/2026 | G2D | T-SHIRT | G2 |  | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152382 LD0285 | 25/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/09/2026 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 24/09/2026 | 25/09/2026 |  |  | 828 |  | 828 |  |  | 21/09/2026 | 22/09/2026 |  |  | 828 |  | 828 |  |  | 18/09/2026 | 19/09/2026 |  |  | 828 |  | 828
ADIDAS | 0903152402-1 KB5965 | BLACK | 120D | S2608MR0900A | 551 | 31/10/2026 | 551 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152402 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 20/10/2026 | Run Ess Tee M |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 551 |  | 551 |  |  | 16/10/2026 | 17/10/2026 |  |  | 551 |  | 551 |  |  | 14/10/2026 | 15/10/2026 |  |  | 551 |  | 551
ADIDAS | 0903152458-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 396 | 29/09/2026 | 396 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903152458 LD0930 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 25/09/2026 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 25/09/2026 | 26/09/2026 |  |  | 396 |  | 396 |  |  | 22/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 396 | 246 | 150 |  | 246 | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 396 | 246 | 150 |  | 246
ADIDAS | 0903152475-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 568 | 31/10/2026 | 568 | AN | AN26/06/2026 | G1J | JACKET | G1 | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jul, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152475 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 23/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 23/11/2026 | 25/11/2026 |  |  | 568 |  | 568 |  |  | 18/11/2026 | 20/11/2026 |  |  | 568 |  | 568
ADIDAS | 0903152502-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 300 | 29/09/2026 | 300 | SA | SA26/06/2026 | G3K | PANTS | G3 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903152502 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300 |  |  | 2026-11-09 | 2026-12-09 |  |  | 300 |  | 300
ADIDAS | 0903152519-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 897 | 31/10/2026 | 897 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | DRC 0051-T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152519 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 28/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 28/10/2026 | 31/10/2026 |  |  | 897 |  | 897 |  |  | 24/10/2026 | 28/10/2026 |  |  | 897 |  | 897 |  |  | 21/10/2026 | 24/10/2026 |  |  | 897 |  | 897
ADIDAS | 0903152532-1 LG9669 | BLACK | 120D | S2754WAS514C | 319 | 29/09/2026 | 319 | ID | ID26/06/2026 | G3B | SKIRT | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 11-Aug, actual receives 12-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152532 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 15/09/2026 | W SL WV SK BLACK |  | SS27 | 15/09/2026 | 23/09/2026 | 17/09/2026 | 19/09/2026 | 319 | 221 | 98 |  | 8 | 2026-11-09 | 19/09/2026 | 29/08/2026 | 18/09/2026 | 319 | 237 | 82
ADIDAS | 0903152551-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 2026-09-09 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 630001 | PRINT L3 SUB PROCESS_V3 | 0903152551 IS1413 | 2026-10-08 | KAHATEX CIJERAH | CANADA | SEA | 2026-04-09 | IN RANGE |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 300 | 300 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-05-08 | 2026-03-09 | 300 | 300
ADIDAS | 0903152558-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 324 | 29/09/2026 | 324 | SI | SI26/06/2026 | G3D | PANTS | G3 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPA SUB PROCESS_V3 | 0903152558 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/09/2026 | W SL WV PT KHAKI THREE F26 |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 324 |  | 324 |  |  | 18/09/2026 | 21/09/2026 |  |  | 324 |  | 324
ADIDAS | 0903152588-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 731 | 30/09/2026 | 731 | SI | SI26/06/2026 | G1F | PANTS | G1 | ok | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152588 HK7317 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 30/09/2026 | ESS SWTP |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 731 |  | 731 |  |  | 26/09/2026 | 29/09/2026 |  |  | 731 |  | 731
ADIDAS | 0903152621-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 285 | 23/10/2026 | 285 | SI | SI26/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152621 KR3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 285 |  | 285 |  |  | 2026-05-11 | 2026-05-11 |  |  | 285 |  | 285 |  |  | 2026-02-11 | 2026-02-11 |  |  | 285 |  | 285
ADIDAS | 0903152648-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152648 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152660-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3300 | 30/09/2026 | 3300 | SI | SI26/06/2026 | G1G | PANTS | G1 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152660 HR8583 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 23/09/2026 | ESS SWTP |  | SS27 | 23/09/2026 | 2026-01-10 |  |  | 3300 |  | 3300 |  |  | 19/09/2026 | 28/09/2026 | 16/09/2026 | 19/09/2026 | 3300 | 2512 | 788 |  | 213
ADIDAS | 0903152687-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 2112 | 15/10/2026 | 2112 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | T2 Formosa, PI Date 12-Aug, actual receives 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 10-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 31-Jul. 516277 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152687 KY6616 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 26S WV WB LND BLACK/WHITE |  | SS27 | 22/10/2026 | 29/10/2026 |  |  | 2112 |  | 2112 |  |  | 19/10/2026 | 26/10/2026 |  |  | 2112 |  | 2112
ADIDAS | 0903152692-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2860 | 30/09/2026 | 2860 | SI | SI26/06/2026 | G1G | PANTS | G1 | ok | ok | 25/09: ex-fty 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903152692 HK7317 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-01-10 | ESS SWTP |  | SS27 | 2026-01-10 | 2026-08-10 |  |  | 2860 |  | 2860 |  |  | 28/09/2026 | 2026-05-10 |  |  | 2860 |  | 2860
ADIDAS | 0903152712-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 300 | 2026-07-10 | 300 | AN | AN26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516244 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152712 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903152716-1 HK7319 | BLACK | 90D | F2225M403 | 1439 | 30/09/2026 | 1439 | SI | SI26/06/2026 | G1K | PANTS | G1 | ok | ok | 26/09: ex-fty 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903152716 HK7319 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 1439 |  | 1439 |  |  | 25/09/2026 | 29/09/2026 | 16/09/2026 | 18/09/2026 | 1439 | 472 | 967
ADIDAS | 0903152733-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 26/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 13-Aug. T2 Formosa, PI Date 26-Jul, actual receives 10-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 516461 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903152733 LE4307 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 24/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903152759-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 330 | 15/10/2026 | 330 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152759 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 330 |  | 330 |  |  | 14/10/2026 | 15/10/2026 |  |  | 330 |  | 330
ADIDAS | 0903152760-1 KB5960 | WHITE | 120D | S2608MR0900A | 430 | 31/10/2026 | 430 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903152760 KB5960 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 27/10/2026 |  |  | 430 |  | 430 |  |  | 22/10/2026 | 23/10/2026 |  |  | 430 |  | 430 |  |  | 20/10/2026 | 21/10/2026 |  |  | 430 |  | 430
ADIDAS | 0903152773-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152773 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903152781-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10 Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903152781 KY6510 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 17/10/2026 | M 3S CHELSEA B7 |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903152806-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 1128 | 31/10/2026 | 1128 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152806 KD3854 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 31/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 31/10/2026 | 2026-03-11 |  |  | 1128 |  | 1128 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1128 |  | 1128 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1128 |  | 1128
ADIDAS | 0903152841-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/10/2026 | 150 | SI | SI26/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152841 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-04-11 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 2026-04-11 | 2026-10-11 |  |  | 150 |  | 150 |  |  | 31/10/2026 | 2026-05-11 |  |  | 150 |  | 150 |  |  | 28/10/2026 | 2026-02-11 |  |  | 150 |  | 150
ADIDAS | 0903152843-1 HU1551 | MEDIUM GREY HEATHER/WHITE | 60D | S211CSIG213 | 750 | 30/09/2026 | 750 | AT | AT26/06/2026 | G3K | PANTS | G3 | ok | ok | 24/09: ex-fty 516442 | HT SUB PROCESS_V1 | 0903152843 HU1551 | 2026-10-08 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 19/09/2026 | 15/09/2026 | 16/09/2026 | 750 | 729 | 21 |  |  | 2026-12-09 | 17/09/2026 | 26/08/2026 | 18/09/2026 | 750 | 750 |  |  |  | 2026-11-09 | 16/09/2026 | 24/08/2026 | 18/09/2026 | 750 | 750
ADIDAS | 0903152870-1 HR6286 | BLACK/BLACK | 60D | S2315KSWU257 | 1051 | 2026-09-09 | 1051 | SI | SI26/06/2026 | G2Q | PANTS | G2 | ok | ok | 07/09: ex-fty 516318 | PRINT L3 SUB PROCESS_V3 | 0903152870 HR6286 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 28/08/2026 | U FI LOGO PT |  | SS27 | 28/08/2026 | 2026-03-09 | 28/08/2026 | 2026-03-09 | 1051 | 1051 |  |  |  | 24/08/2026 | 31/08/2026 | 13/08/2026 | 2026-04-09 | 1051 | 1051
ADIDAS | 0903152887-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 435 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152887 KY9391 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152912-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 100 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152912 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152983-1 HZ0747 | BLACK | 90D | F2325M414 | 4543 | 30/09/2026 | 4543 | SA | SA26/06/2026 | G2K,G2L | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 516205 | EMBRO SUB PROCESS_V1 | 0903152983 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | SPAIN | SEA | 15/09/2026 | PL TEE |  | SS27 | 15/09/2026 | 26/09/2026 | 17/09/2026 | 19/09/2026 | 4543 | 2527 | 2016 |  | 1153 | 2026-11-09 | 23/09/2026 | 2026-12-09 | 18/09/2026 | 4543 | 3969 | 574
ADIDAS | 0903153088-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 389 | 30/09/2026 | 389 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 26-Aug. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153088 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 23/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 389 |  | 389 |  |  | 19/09/2026 | 21/09/2026 |  |  | 389 |  | 389
ADIDAS | 0903153111-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 550 | 30/09/2026 | 550 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 28/09: ex-fty (KN GLT). T2 Kahatex, PI Date 29-Jul, actual receives 28-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153111 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 18/09/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 550 | 500 | 50 |  | 404 | 15/09/2026 | 19/09/2026 | 28/08/2026 | 19/09/2026 | 550 | 549 | 1 |  | 11
ADIDAS | 0903153139-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 447 | 31/10/2026 | 447 | SA | SA26/06/2026 | G1O | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 1st Art (TC 10 pcs) 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903153139 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-11-11 | 14/11/2026 |  |  | 447 |  | 447 |  |  | 2026-06-11 | 2026-11-11 |  |  | 447 |  | 447 |  |  | 2026-03-11 | 2026-06-11 |  |  | 447 |  | 447
ADIDAS | 0903153147-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153147 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 30/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 540 |  | 540 |  |  | 26/09/2026 | 28/09/2026 | 2026-01-08 | 2026-03-09 | 540 | 540
ADIDAS | 0903153178-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 576 | 30/09/2026 | 576 | SA | SA26/06/2026 | G2G | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903153178 JE6414 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 576 |  | 576 |  |  | 15/09/2026 | 19/09/2026 | 2026-01-08 | 31/08/2026 | 576 | 555 | 21
ADIDAS | 0903153208-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 414 | 30/09/2026 | 414 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153208 LC6339 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-05-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 414 |  | 414 |  |  | 2026-01-10 | 2026-02-10 | 2026-08-09 | 2026-09-09 | 414 | 405 | 9
ADIDAS | 0903153249-1 LC6341 | BLACK | 90D | S27GMGFX130 | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903153249 LC6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 16/10/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 468 |  | 468 |  |  | 13/10/2026 | 14/10/2026 | 2026-09-09 | 16/09/2026 | 468 | 444 | 24
ADIDAS | 0903153273-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G2O | JACKET | G2 | (08/08/2026) | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153273 JE0052 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | W 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 308 |  | 308 |  |  | 18/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 308 | 106 | 202
ADIDAS | 0903153303-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 468 | 30/09/2026 | 468 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153303 JE6338 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 468 |  | 468 |  |  | 24/09/2026 | 26/09/2026 |  |  | 468 |  | 468
ADIDAS | 0903153333-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 504 | 30/09/2026 | 504 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153333 JE6341 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M 3S FT FZ HD |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 504 |  | 504 |  |  | 24/09/2026 | 26/09/2026 |  |  | 504 |  | 504
ADIDAS | 0903153362-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 378 | 26/09/2026 | 378 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153362 JD5302 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 28/08/2026 | 31/08/2026 | 378 | 378 |  |  |  | 24/08/2026 | 27/08/2026 | 24/08/2026 | 31/08/2026 | 378 | 378
ADIDAS | 0903153392-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 308 | 30/09/2026 | 308 | SI | SI26/06/2026 | G2O | JACKET | G2 | ok | ok | 25/09: ex-fty 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153392 JE0055 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 25/09/2026 | W 3S FT FZ HD |  | SS27 | 25/09/2026 | 25/09/2026 |  |  | 308 |  | 308 |  |  | 22/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 308 | 74 | 234 |  | 74
ADIDAS | 0903153425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 540 | 30/09/2026 | 540 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903153425 JD1877 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | M 3S FT FZ HD |  | SS27 | 22/09/2026 | 24/09/2026 |  |  | 540 |  | 540 |  |  | 18/09/2026 | 21/09/2026 |  |  | 540 |  | 540
ADIDAS | 0903153431-1 KC4947 | BLACK | 105D | S2608WR0216 | 1524 | 15/10/2026 | 1524 | SA | SA26/06/2026 | G3G | PANTS | G3 | (20/08/2026) | ok | Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD 07-Sep, ETA-Kaha 22-Sep. T2 Huge Bamboo, PI Date 29-Aug, actual receives 11-Sep. T2 Grand Tex, PI Date 10-Aug, actual receives 09-Sep. 823016 | PAD+HT SUB PROCESS_V3 | 0903153431 KC4947 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-09-10 | adi365 Astro W |  | SS27-TRAX | 2026-09-10 | 14/10/2026 |  |  | 1524 |  | 1524 |  |  | 2026-06-10 | 2026-10-10 |  |  | 1524 |  | 1524 |  |  | 2026-05-10 | 2026-09-10 |  |  | 1524 |  | 1524
ADIDAS | 0903153447-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153447 KA5089 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 2026-04-09 | 2026-12-09 | 266 | 266
ADIDAS | 0903153486-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 266 | 2026-12-09 | 266 | AT | AT26/06/2026 | G2H | T-SHIRT | G2 | ok | (30/07/2026) | 10/09: ex-fty 848016 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903153486 KA5090 | 2026-10-08 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-04-09 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 266 | 266 |  |  |  | 2026-02-09 | 2026-04-09 | 26/08/2026 | 2026-12-09 | 266 | 266
ADIDAS | 0903153519-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 17 | 31/10/2026 | 17 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153519 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27-SPOMA | 23/11/2026 | 25/11/2026 |  |  | 17 |  | 17 |  |  | 18/11/2026 | 20/11/2026 |  |  | 17 |  | 17
ADIDAS | 0903153557-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 17 | 15/10/2026 | 17 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153557 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27-SPOMA | 14/10/2026 | 15/10/2026 |  |  | 17 |  | 17 |  |  | 2026-10-10 | 2026-12-10 |  |  | 17 |  | 17
ADIDAS | 0903153563-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 844 | 2026-12-09 | 844 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). 688010 | HT+PAD SUB PROCESS_V3 | 0903153563 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-09 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-05-09 | 844 | 844 |  |  |  | 31/08/2026 | 2026-02-09 | 2026-01-09 | 2026-04-09 | 844 | 844 |  |  |  | 28/08/2026 | 31/08/2026 | 2026-01-09 | 2026-04-09 | 844 | 844
ADIDAS | 0903153585-1 LG9675 | BLACK | 120D | S2754WAS513C | 17 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903153585 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27-SPOMA
ADIDAS | 0903153623-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 17 | 31/10/2026 | 17 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153623 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | W SL WV TT KHAKI THREE F26 |  | SS27-SPOMA | 2026-03-11 | 2026-05-11 |  |  | 17 |  | 17 |  |  | 30/10/2026 | 2026-02-11 |  |  | 17 |  | 17
ADIDAS | 0903153653-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 780 | 30/09/2026 | 780 | SA | SA26/06/2026 | G3H | PANTS | G3 | ok | ok | 24/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153653 JW7178 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 780 | 531 | 249 |  | 531 | 15/09/2026 | 18/09/2026 | 2026-12-09 | 16/09/2026 | 780 | 769 | 11
ADIDAS | 0903153676-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 840 | 23/09/2026 | 840 | SA | SA26/06/2026 | G3C | PANTS | G3 | ok | ok | 23/09: ex-fty 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153676 JW7177 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 840 | 459 | 381 |  | 459 | 15/09/2026 | 17/09/2026 | 31/08/2026 | 19/09/2026 | 840 | 841 | -1 | 1 | 13
ADIDAS | 0903153692-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903153692 KC8152 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 13/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300
ADIDAS | 0903153702-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1431 | 30/09/2026 | 1431 | SA | SA26/06/2026 | G3H | PANTS | G3 | ok | ok | 23/09: ex-fty 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903153702 JW7178 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | W 3S FT OH PT |  | SS27 | 15/09/2026 | 22/09/2026 | 17/09/2026 | 19/09/2026 | 1431 | 1431 |  |  | 32 | 2026-11-09 | 18/09/2026 | 2026-01-09 | 17/09/2026 | 1431 | 1431
ADIDAS | 0903153713-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 207 | 2026-05-09 | 207 | ID | ID26/06/2026 | G1E | T-SHIRT | G1 | ok |  | 04/09: ex-fty. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153713 IN1172 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/07/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 20/07/2026 | 28/07/2026 | 21/07/2026 | 24/07/2026 | 207 | 207 |  |  |  | 16/07/2026 | 24/07/2026 | 14/07/2026 | 23/07/2026 | 207 | 207 |  |  |  | 15/07/2026 | 23/07/2026 | 13/07/2026 | 23/07/2026 | 207 | 207
ADIDAS | 0903153721-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 348 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903153721 KE6716 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903153722-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 355 | 15/10/2026 | 355 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (KN GLT). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153722 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 355 |  | 355 |  |  | 14/10/2026 | 15/10/2026 |  |  | 355 |  | 355 |  |  | 2026-08-10 | 2026-09-10 |  |  | 355 |  | 355
ADIDAS | 0903153738-1 JZ5129 | CRYSTAL LINEN S26 | 120D | S2608WR0201 | 300 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Best Pacific, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD 30-Jul, ETA-Kaha 14-Aug. 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903153738 JZ5129 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W CRYSTAL LINEN S26 |  | SS27-TRAX
ADIDAS | 0903153739-1 KE8424 | BLACK | 120D | S2608MR0906A | 463 | 31/10/2026 | 463 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153739 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 28/10/2026 | 30/10/2026 |  |  | 463 |  | 463 |  |  | 24/10/2026 | 27/10/2026 |  |  | 463 |  | 463 |  |  | 22/10/2026 | 24/10/2026 |  |  | 463 |  | 463
ADIDAS | 0903153754-1 IN1157 | WHITE | 90D | S2408MR1600-SLT | 201 | 2026-09-09 | 201 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, using fabric stock (PO 26009343). T2 Fu Hsun, PI Date 24-Jul, using fabric stock (PO 26009344). 838103 | HT SUB PROCESS_V1 | 0903153754 IN1157 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 29/08/2026 | 2026-02-09 | 31/08/2026 | 2026-04-09 | 201 | 201 |  |  |  | 27/08/2026 | 31/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201 |  |  |  | 26/08/2026 | 29/08/2026 | 24/07/2026 | 2026-02-09 | 201 | 201
ADIDAS | 0903153765-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 360 | 31/10/2026 | 360 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153765 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 360 |  | 360 |  |  | 13/10/2026 | 14/10/2026 |  |  | 360 |  | 360 |  |  | 2026-10-10 | 2026-12-10 |  |  | 360 |  | 360
ADIDAS | 0903153773-1 KB5965 | BLACK | 120D | S2608MR0900A | 1585 | 31/10/2026 | 1585 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153773 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 28/10/2026 |  |  | 1585 |  | 1585 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1585 |  | 1585 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1585 |  | 1585
ADIDAS | 0903153793-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 1153 | 31/10/2026 | 1153 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153793 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 1153 |  | 1153 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1153 |  | 1153 |  |  | 14/10/2026 | 15/10/2026 |  |  | 1153 |  | 1153
ADIDAS | 0903153803-1 KE8424 | BLACK | 120D | S2608MR0906A | 580 | 31/10/2026 | 580 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153803 KE8424 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 28/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 28/10/2026 | 30/10/2026 |  |  | 580 |  | 580 |  |  | 24/10/2026 | 27/10/2026 |  |  | 580 |  | 580 |  |  | 22/10/2026 | 24/10/2026 | 19/09/2026 | 19/09/2026 | 580 | 152 | 428 |  | 152
ADIDAS | 0903153815-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1477 | 31/10/2026 | 1477 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153815 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 30/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 30/10/2026 | 31/10/2026 |  |  | 1477 |  | 1477 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1477 |  | 1477 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1477 |  | 1477
ADIDAS | 0903153840-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 540 | 30/10/2026 | 540 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903153840 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 20/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 540 |  | 540 |  |  | 16/10/2026 | 17/10/2026 | 19/09/2026 | 19/09/2026 | 540 | 146 | 394 |  | 146 | 14/10/2026 | 15/10/2026 | 19/09/2026 | 19/09/2026 | 540 | 146 | 394 |  | 146
ADIDAS | 0903153843-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 480 | 23/09/2026 | 480 | SI | SI26/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 22/09: ex-fty 516204 | EMBRO SUB PROCESS_V1 | 0903153843 KD3911 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/09/2026 | RELEASED |  | SS27 | 15/09/2026 | 21/09/2026 | 16/09/2026 | 19/09/2026 | 480 | 480 |  |  | 5 | 2026-11-09 | 17/09/2026 | 31/08/2026 | 18/09/2026 | 480 | 473 | 7
ADIDAS | 0903153852-1 KE6899 | BLACK | 105D | S2608WR0601B | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric (KN GLT). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903153852 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | adi365 Short W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 24/10/2026 |  |  | 300 |  | 300 |  |  | 21/10/2026 | 23/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903153861-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 906 | 30/09/2026 | 906 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153861 KV8005 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 29/09/2026 | 2026-02-10 |  |  | 906 |  | 906 |  |  | 25/09/2026 | 29/09/2026 | 29/08/2026 | 17/09/2026 | 906 | 375 | 531
ADIDAS | 0903153888-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 364 | 30/09/2026 | 364 | SI | SI26/06/2026 | G1H | JACKET | G1 | ok | ok | 23/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153888 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 364 | 352 | 12 |  |  | 15/09/2026 | 19/09/2026 | 31/08/2026 | 17/09/2026 | 364 | 261 | 103
ADIDAS | 0903153890-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437-MTF | 1504 | 15/10/2026 | 1504 | AN | AN26/06/2026 | G3C | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903153890 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 23/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 23/10/2026 | 26/10/2026 |  |  | 1504 |  | 1504 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1504 |  | 1504 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1504 |  | 1504
ADIDAS | 0903153893-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 481 | 15/10/2026 | 481 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 1st Art (TC 10 pcs) 650010 | PAD+HT SUB PROCESS_V3 | 0903153893 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 481 |  | 481 |  |  | 2026-05-10 | 2026-08-10 |  |  | 481 |  | 481 |  |  | 2026-03-10 | 2026-07-10 |  |  | 481 |  | 481
ADIDAS | 0903153906-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 399 | 30/09/2026 | 399 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153906 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT QZ HD |  | SS27 | 18/09/2026 | 23/09/2026 |  |  | 399 |  | 399 |  |  | 15/09/2026 | 19/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903153959-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 609 | 31/10/2026 | 609 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903153959 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/10/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 609 |  | 609 |  |  | 20/10/2026 | 21/10/2026 | 19/09/2026 | 19/09/2026 | 609 | 202 | 407 |  | 202 | 17/10/2026 | 19/10/2026 | 19/09/2026 | 19/09/2026 | 609 | 582 | 27 |  | 582
ADIDAS | 0903153995-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 401 | 31/10/2026 | 401 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903153995 LD0285 | 25/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-09-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-09-10 | 2026-10-10 |  |  | 401 |  | 401 |  |  | 2026-06-10 | 2026-07-10 |  |  | 401 |  | 401 |  |  | 2026-03-10 | 2026-05-10 |  |  | 401 |  | 401
ADIDAS | 0903154027-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 400 | 23/09/2026 | 400 | SI | SI26/06/2026 | G2O | JACKET | G2 | (08/08/2026) | ok | 23/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154027 JE0052 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 21/09/2026 | W 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 400 |  | 400 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 19/09/2026 | 400 | 356 | 44 |  | 7
ADIDAS | 0903154028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 393 | 30/09/2026 | 393 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty (KN GLT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154028 KV7863 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 15/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 18/09/2026 | 393 | 311 | 82 |  |  | 2026-11-09 | 17/09/2026 | 26/08/2026 | 17/09/2026 | 393 | 359 | 34
ADIDAS | 0903154066-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 1951 | 15/10/2026 | 1951 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903154066 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 19/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 19/10/2026 | 21/10/2026 |  |  | 1951 |  | 1951 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1951 |  | 1951 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1951 |  | 1951
ADIDAS | 0903154077-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154077 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 435 |  | 435 |  |  | 15/10/2026 | 17/10/2026 |  |  | 435 |  | 435
ADIDAS | 0903154087-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 510 | 15/10/2026 | 510 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154087 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 510 |  | 510 |  |  | 17/10/2026 | 19/10/2026 |  |  | 510 |  | 510
ADIDAS | 0903154119-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154119 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 300 | 258 | 42 |  | 242 | 2026-12-09 | 17/09/2026 | 18/09/2026 | 18/09/2026 | 300 | 295 | 5
ADIDAS | 0903154124-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 533 | 23/09/2026 | 533 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154124 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-12-09 | 21/09/2026 | 2026-12-09 | 17/09/2026 | 533 | 533 |  |  |  | 2026-09-09 | 17/09/2026 | 2026-11-09 | 13/09/2026 | 533 | 516 | 17
ADIDAS | 0903154136-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 399 | 23/09/2026 | 399 | SA | SA26/06/2026 | G3H | PANTS | G3 | ok | ok | 23/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154136 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 | 18/09/2026 | 19/09/2026 | 399 | 398 | 1 |  | 332 | 15/09/2026 | 18/09/2026 | 2026-01-09 | 19/09/2026 | 399 | 394 | 5 |  | 2
ADIDAS | 0903154672-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G2O | JACKET | G2 | ok | ok | 28/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154672 JE0055 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 24/09/2026 | W 3S FT FZ HD |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 22/09/2026 | 2026-11-09 | 19/09/2026 | 300 | 300 |  |  | 298
ADIDAS | 0903154696-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 68 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903154696 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903154711-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 1265 | 30/09/2026 | 1265 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | DRC 0090-early shipment customer (Kahatex IPF). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903154711 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 16/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 15/09/2026 | 17/09/2026 | 1265 | 1189 | 76 |  |  | 2026-12-09 | 17/09/2026 | 14/09/2026 | 15/09/2026 | 1265 | 1263 | 2
ADIDAS | 0903154728-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 58 | 31/10/2026 | 58 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903154728 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-06-11 | 2026-07-11 |  |  | 58 |  | 58 |  |  | 2026-03-11 | 2026-04-11 |  |  | 58 |  | 58 |  |  | 30/10/2026 | 31/10/2026 |  |  | 58 |  | 58
ADIDAS | 0903154744-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 15000 | 15/09/2026 | 15000 | SA | SA26/06/2026 | G1G,G1I,G1O,G1Q | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154744 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 31/08/2026 | LFC 3 F JSY SE |  | SS27-FJ | 31/08/2026 | 15/09/2026 | 31/08/2026 | 15/09/2026 | 15000 | 15000 |  |  |  | 27/08/2026 | 2026-11-09 | 21/08/2026 | 17/09/2026 | 15000 | 15000
ADIDAS | 0903154754-1 KB5965 | BLACK | 120D | S2608MR0900A | 270 | 31/10/2026 | 270 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903154754 KB5965 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/10/2026 | Run Ess Tee M |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 270 |  | 270 |  |  | 15/10/2026 | 16/10/2026 |  |  | 270 |  | 270 |  |  | 13/10/2026 | 14/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903154788-1 LE8201 | BLACK | 90D | F2606LHLF103FY | 2110 | 2026-12-09 | 2110 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 12/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154788 LE8201 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3 FY JSY SE |  | SS27-FJ | 2026-05-09 | 2026-12-09 | 2026-07-09 | 2026-12-09 | 2110 | 2110 |  |  |  | 2026-02-09 | 2026-09-09 | 2026-03-09 | 14/09/2026 | 2110 | 2110
ADIDAS | 0903154833-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 6345 | 15/09/2026 | 6345 | SA | SA26/06/2026 | G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 14/09: ex-fty 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154833 LE8202 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-09 | LFC 3 F JSY SE |  | SS27-FJ | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 6345 | 6345 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-04-09 | 17/09/2026 | 6345 | 6345
ADIDAS | 0903154839-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 924 | 15/10/2026 | 924 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903154839 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 15/10/2026 | 17/10/2026 |  |  | 924 |  | 924 |  |  | 2026-12-10 | 14/10/2026 |  |  | 924 |  | 924 |  |  | 2026-06-10 | 2026-08-10 |  |  | 924 |  | 924
ADIDAS | 0903154867-1 LE8208 | BLACK | 90D | F2606LHLF103MFL | 3701 | 15/09/2026 | 3701 | SA | SA26/06/2026 | G2M,G2O | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154867 LE8208 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-09-09 | LFC 3 F JSYL SE BLACK |  | SS27-FJ | 2026-09-09 | 15/09/2026 | 2026-09-09 | 15/09/2026 | 3701 | 3701 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-07-09 | 15/09/2026 | 3701 | 3701
ADIDAS | 0903154898-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 760 | 15/09/2026 | 760 | SA | SA26/06/2026 | G2K,G2L,G2M | T-SHIRT | G2 | ok | ok | 15/09: ex-fty (STOOD) 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903154898 LE8210 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-09 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-05-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 760 | 760 |  |  |  | 2026-02-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 760 | 760
ADIDAS | 0903154925-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 200 | 2026-12-09 | 200 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903154925 LE8193 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-02-09 | 2026-10-09 | 200 | 200 |  |  |  | 27/08/2026 | 2026-07-09 | 21/08/2026 | 2026-10-09 | 200 | 200
ADIDAS | 0903154942-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 313 | 30/10/2026 | 313 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903154942 KX3654 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 17/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 313 |  | 313 |  |  | 14/10/2026 | 15/10/2026 |  |  | 313 |  | 313 |  |  | 2026-12-10 | 13/10/2026 |  |  | 313 |  | 313
ADIDAS | 0903154950-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 1096 | 2026-12-09 | 1096 | SA | SA26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 10/09: ex-fty 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903154950 LE8193 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1096 | 1096 |  |  |  | 27/08/2026 | 2026-07-09 | 20/08/2026 | 2026-10-09 | 1096 | 1096
ADIDAS | 0903154953-1 KA0235 | BLACK | 90D | S2608WR0901 | 1036 | 2026-07-10 | 1036 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 28-Aug. 516276 | PAD+HT SUB PROCESS_V3 | 0903154953 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 29/09/2026 | 2026-01-10 |  |  | 1036 |  | 1036 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1036 |  | 1036 |  |  | 24/09/2026 | 26/09/2026 |  |  | 1036 |  | 1036
ADIDAS | 0903154980-1 LE8193 | WHITE | 90D | F2606LHRM101MF | 14142 | 2026-12-09 | 14142 | SA | SA26/06/2026 | G1I,G1O,G1Q,G1R | T-SHIRT | G1 | ok | ok | 12/09: ex-fty 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903154980 LE8193 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | REAL H F JSY SE WHITE |  | SS27-FJ | 31/08/2026 | 2026-12-09 | 2026-02-09 | 2026-12-09 | 14142 | 14142 |  |  |  | 27/08/2026 | 2026-09-09 | 18/08/2026 | 2026-11-09 | 14142 | 14142
ADIDAS | 0903155169-1 KB5960 | WHITE | 120D | S2608MR0900A | 2500 | 31/10/2026 | 2500 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903155169 KB5960 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | Run Ess Tee M |  | SS27-TI | 28/10/2026 | 30/10/2026 |  |  | 2500 |  | 2500 |  |  | 24/10/2026 | 27/10/2026 |  |  | 2500 |  | 2500 |  |  | 22/10/2026 | 24/10/2026 |  |  | 2500 |  | 2500
ADIDAS | 0903155196-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 100 | 15/10/2026 | 100 | AN | AN26/06/2026 | G3E | PANTS | G3 | ok | ok | 834012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155196 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-08-10 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903155209-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 | 100 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 834012 | HT+PAD SUB PROCESS_V3 | 0903155209 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903155389-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 380 | 15/09/2026 | 380 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903155389 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-09 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-07-09 | 2026-12-09 | 2026-08-09 | 2026-10-09 | 380 | 380 |  |  |  | 2026-03-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 380 | 380
ADIDAS | 0903155422-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1482 | 31/10/2026 | 1482 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903155422 KX3654 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/10/2026 | 2026-02-11 |  |  | 1482 |  | 1482 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1482 |  | 1482 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1482 |  | 1482
ADIDAS | 0903155457-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 1114 | 30/09/2026 | 1114 | AN | AN26/06/2026 | G2D | T-SHIRT | G2 | (31/07/2026) | ok | 25/09: ex-fty. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 16-Sep. 678002 | PRINT L2+HT SUB PROCESS_V3 | 0903155457 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 1114 |  | 1114 |  |  | 19/09/2026 | 21/09/2026 |  |  | 1114 |  | 1114 |  |  | 18/09/2026 | 19/09/2026 |  |  | 1114 |  | 1114
ADIDAS | 0903155494-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 14 | 15/10/2026 | 14 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155494 LE8187 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-02-10 | M SL WV TP PT BLACK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 14 |  | 14 |  |  | 29/09/2026 | 30/09/2026 |  |  | 14 |  | 14
ADIDAS | 0903155496-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 407 | 30/09/2026 | 407 | AN | AN26/06/2026 | G2Q | SHORTS | G2 |  |  | 25/09: ex-fty. IMPROVE. DRC 0064-T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. T2 Formosa, PI Date 12-Sep, actual receives 04-Sep. T2 Kahatex, using fabric stock. 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155496 LG9660 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-03-10 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 407 |  | 407 |  |  | 30/09/2026 | 2026-01-10 |  |  | 407 |  | 407
ADIDAS | 0903155525-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 24 | 15/10/2026 | 24 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 684009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903155525 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 24 |  | 24 |  |  | 2026-10-10 | 2026-12-10 |  |  | 24 |  | 24
ADIDAS | 0903155581-1 KB5960 | WHITE | 120D | S2608MR0900A | 3741 | 29/09/2026 | 3741 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155581 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/09/2026 | Run Ess Tee M |  | SS27-TI | 29/09/2026 | 2026-01-10 |  |  | 3741 |  | 3741 |  |  | 25/09/2026 | 28/09/2026 | 17/09/2026 | 19/09/2026 | 3741 | 2886 | 855 |  | 543 | 23/09/2026 | 25/09/2026 | 16/09/2026 | 18/09/2026 | 3741 | 2886 | 855
ADIDAS | 0903155586-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 300 | 31/10/2026 | 300 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903155586 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300
ADIDAS | 0903155606-1 KB5965 | BLACK | 120D | S2608MR0900A | 989 | 29/09/2026 | 989 | SA | SA26/06/2026 | G2D | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155606 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 989 |  | 989 |  |  | 24/09/2026 | 25/09/2026 |  |  | 989 |  | 989 |  |  | 22/09/2026 | 23/09/2026 |  |  | 989 |  | 989
ADIDAS | 0903155635-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 467 | 31/10/2026 | 467 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | (Airowes). T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 650034 | HT+PAD SUB PROCESS_V3 | 0903155635 KB5961 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 467 |  | 467 |  |  | 21/10/2026 | 22/10/2026 | 19/09/2026 | 19/09/2026 | 467 | 37 | 430 |  | 37 | 19/10/2026 | 20/10/2026 | 18/09/2026 | 18/09/2026 | 467 | 37 | 430
ADIDAS | 0903155643-1 KB5965 | BLACK | 120D | S2608MR0900A | 5978 | 29/09/2026 | 5978 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903155643 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/09/2026 | Run Ess Tee M |  | SS27-TI | 21/09/2026 | 25/09/2026 |  |  | 5978 |  | 5978 |  |  | 17/09/2026 | 22/09/2026 |  |  | 5978 |  | 5978 |  |  | 15/09/2026 | 19/09/2026 |  |  | 5978 |  | 5978
ADIDAS | 0903155770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 558 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 680015 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903155770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903155848-1 KB5965 | BLACK | 120D | S2608MR0900A | 985 | 31/10/2026 | 985 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155848 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 985 |  | 985 |  |  | 19/10/2026 | 20/10/2026 |  |  | 985 |  | 985 |  |  | 16/10/2026 | 17/10/2026 |  |  | 985 |  | 985
ADIDAS | 0903155908-1 KB5960 | WHITE | 120D | S2608MR0900A | 460 | 31/10/2026 | 460 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903155908 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 27/10/2026 | Run Ess Tee M |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 460 |  | 460 |  |  | 23/10/2026 | 24/10/2026 |  |  | 460 |  | 460 |  |  | 21/10/2026 | 22/10/2026 |  |  | 460 |  | 460
ADIDAS | 0903155916-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155916 KW9039 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 20/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 20/10/2026 | 21/10/2026 |  |  | 224 |  | 224 |  |  | 16/10/2026 | 17/10/2026 |  |  | 224 |  | 224
ADIDAS | 0903155939-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 908 | 31/10/2026 | 908 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). 684009 | HT+PAD SUB PROCESS_V3 | 0903155939 KB5961 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 23/10/2026 | Run Ess Tee M |  | SS27-TI | 23/10/2026 | 23/10/2026 |  |  | 908 |  | 908 |  |  | 20/10/2026 | 20/10/2026 | 18/09/2026 | 19/09/2026 | 908 | 667 | 241 |  | 35 | 17/10/2026 | 17/10/2026 | 18/09/2026 | 18/09/2026 | 908 | 666 | 242
ADIDAS | 0903155960-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 25/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903155960 JD1877 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 23/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903155978-1 KY7184 | TEAM ROYAL BLUE | 75D | S2706CHUC008 | 1218 | 2026-09-09 | 1218 | ID | ID26/06/2026 | G2S | SHORTS | G2 | ok | ok | 08/09: ex-fty 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903155978 KY7184 | 2026-11-08 | KAHATEX CIJERAH | CHILE | SEA | 2026-01-09 | UCH DNA SHO TEAM ROYAL BLUE |  | SS27 | 2026-01-09 | 2026-08-09 | 2026-01-09 | 2026-08-09 | 1218 | 1218 |  |  |  | 28/08/2026 | 2026-04-09 | 31/08/2026 | 2026-08-09 | 1218 | 1218
ADIDAS | 0903155986-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903155986 KY3734 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 312 |  | 312 |  |  | 29/09/2026 | 30/09/2026 |  |  | 312 |  | 312
ADIDAS | 0903156009-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 24/09: ex-fty 684009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903156009 JE6341 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 21/09/2026 | M 3S FT FZ HD |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 17/09/2026 | 18/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903156065-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 344 | 23/09/2026 | 344 | SA | SA26/06/2026 | G3K | PANTS | G3 | ok | ok | 23/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO SUB PROCESS_V1 | 0903156065 JD1881 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 15/09/2026 | M 3S FT TC PT |  | SS27 | 15/09/2026 | 19/09/2026 | 16/09/2026 | 17/09/2026 | 344 | 338 | 6 |  |  | 2026-11-09 | 16/09/2026 | 14/05/2026 | 15/09/2026 | 344 | 344
ADIDAS | 0903156091-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 126 | 31/10/2026 | 126 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156091 LG9666 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-10-11 | W SL WV TT BLACK |  | SS27 | 2026-10-11 | 13/11/2026 |  |  | 126 |  | 126 |  |  | 2026-05-11 | 2026-10-11 |  |  | 126 |  | 126
ADIDAS | 0903156120-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 131 | 31/10/2026 | 131 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903156120 LG9664 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-11 | W SL WV TT LEGEND IVY S19 |  | SS27 | 2026-09-11 | 2026-11-11 |  |  | 131 |  | 131 |  |  | 2026-04-11 | 2026-06-11 |  |  | 131 |  | 131
ADIDAS | 0903156157-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 401 | 23/09/2026 | 401 | SA | SA26/06/2026 | G3C | PANTS | G3 | ok | ok | 22/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156157 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 401 | 395 | 6 |  | 265 | 15/09/2026 | 17/09/2026 | 14/08/2026 | 16/09/2026 | 401 | 400 | 1
ADIDAS | 0903156162-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 435 | 15/10/2026 | 435 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156162 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 435 |  | 435 |  |  | 15/10/2026 | 17/10/2026 |  |  | 435 |  | 435
ADIDAS | 0903156174-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 938 | 2026-07-10 | 938 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156174 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 30/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 938 |  | 938 |  |  | 26/09/2026 | 28/09/2026 |  |  | 938 |  | 938
ADIDAS | 0903156181-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 375 | 15/10/2026 | 375 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | T2 Gistex, PI Date 10-Aug, actual receives 10-Aug (switch with PO 26024056). T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156181 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 375 |  | 375 |  |  | 17/10/2026 | 19/10/2026 |  |  | 375 |  | 375
ADIDAS | 0903156184-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 23/09/2026 | 610 | AN | AN26/06/2026 | G3F | PANTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156184 KZ3198 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 14/09/2026 | 19/09/2026 | 610 | 593 | 17 |  | 69 | 2026-12-09 | 17/09/2026 | 2026-11-09 | 2026-12-09 | 610 | 610
ADIDAS | 0903156224-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1251 | 2026-07-10 | 1251 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156224 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1251 |  | 1251 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1251 |  | 1251
ADIDAS | 0903156225-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 360 | 15/10/2026 | 360 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156225 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 360 |  | 360 |  |  | 19/10/2026 | 20/10/2026 |  |  | 360 |  | 360
ADIDAS | 0903156247-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156247 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 345 |  | 345 |  |  | 19/10/2026 | 20/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156282-1 KA4331 | BLACK | 90D | S2608MR0902 | 399 | 2026-07-10 | 399 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516277 | PAD+HT SUB PROCESS_V3 | 0903156282 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 399 |  | 399 |  |  | 29/09/2026 | 30/09/2026 |  |  | 399 |  | 399 |  |  | 28/09/2026 | 29/09/2026 |  |  | 399 |  | 399
ADIDAS | 0903156297-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 345 | 15/10/2026 | 345 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156297 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 345 |  | 345 |  |  | 20/10/2026 | 22/10/2026 |  |  | 345 |  | 345
ADIDAS | 0903156313-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 525 | 15/10/2026 | 525 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516405 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156313 KY4155 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 525 |  | 525 |  |  | 20/10/2026 | 22/10/2026 |  |  | 525 |  | 525
ADIDAS | 0903156320-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1051 | 30/09/2026 | 1051 | SI | SI26/06/2026 | G2S | PANTS | G2 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156320 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 15/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 1051 | 822 | 229 |  | 283 | 2026-11-09 | 17/09/2026 | 2026-11-09 | 19/09/2026 | 1051 | 1042 | 9 |  | 39
ADIDAS | 0903156341-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 624 | 30/09/2026 | 624 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156341 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 624 | 600 | 24 |  | 41 | 2026-12-09 | 17/09/2026 | 2026-10-09 | 2026-12-09 | 624 | 623 | 1
ADIDAS | 0903156375-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 349 | 30/09/2026 | 349 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | (29/07/2026) | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156375 KW2924 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 349 |  | 349 |  |  | 2026-01-10 | 2026-03-10 |  |  | 349 |  | 349
ADIDAS | 0903156407-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 741 | 30/09/2026 | 741 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156407 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 741 |  | 741 |  |  | 26/09/2026 | 28/09/2026 |  |  | 741 |  | 741
ADIDAS | 0903156431-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 1249 | 30/09/2026 | 1249 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903156431 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 1249 |  | 1249 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1249 |  | 1249
ADIDAS | 0903156456-1 LC7300 | WHITE | 90D | S2725M926A | 207 | 23/10/2026 | 207 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903156456 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL WHITE |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 207 |  | 207 |  |  | 26/09/2026 | 26/09/2026 |  |  | 207 |  | 207
ADIDAS | 0903156487-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 110 | 15/10/2026 | 110 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156487 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 110 |  | 110 |  |  | 30/09/2026 | 30/09/2026 |  |  | 110 |  | 110
ADIDAS | 0903156511-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2S | SHORTS | G2 | ok | ok | 26/09: ex-fty 848016 | EMBRO SUB PROCESS_V1 | 0903156511 JE6417 | 2026-10-09 | KAHATEX CIJERAH | MOROCCO | SEA | 30/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 100 |  | 100 |  |  | 26/09/2026 | 28/09/2026 | 2026-01-09 | 2026-01-09 | 100 | 100
ADIDAS | 0903156518-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 122 | 2026-07-10 | 122 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156518 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 122 |  | 122 |  |  | 29/09/2026 | 30/09/2026 |  |  | 122 |  | 122
ADIDAS | 0903156531-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903156531 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903156547-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 800 | 15/10/2026 | 800 | SI | SI26/06/2026 | G3F | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, PI Date 07-Sep, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 07-Sep, ETD ?? T2 Libolon, PI Date 18-Aug, actual receives 10-Aug. 659018 | HT SUB PROCESS_V1 | 0903156547 HB7454 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 17/10/2026 | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 800 |  | 800 |  |  | 15/10/2026 | 16/10/2026 |  |  | 800 |  | 800 |  |  | 14/10/2026 | 15/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903156549-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 198 | 23/10/2026 | 198 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156549 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-07-10 | 2026-08-10 |  |  | 198 |  | 198 |  |  | 2026-03-10 | 2026-05-10 |  |  | 198 |  | 198
ADIDAS | 0903156595-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 150 | 30/09/2026 | 150 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 25/09: ex-fty. Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156595 JW7182 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/09/2026 | W 3S FT OH PT |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 150 |  | 150 |  |  | 16/09/2026 | 17/09/2026 | 20/08/2026 | 18/09/2026 | 150 | 150
ADIDAS | 0903156599-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 300 | 23/10/2026 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156599 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300
ADIDAS | 0903156613-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 540 | 15/10/2026 | 540 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (Mexico). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903156613 KE6716 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-08-10 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 540 |  | 540 |  |  | 2026-05-10 | 2026-08-10 |  |  | 540 |  | 540 |  |  | 2026-03-10 | 2026-07-10 |  |  | 540 |  | 540
ADIDAS | 0903156885-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 416 | 30/09/2026 | 416 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 29/09: ex-fty (Airowes). T2 Formosa, actual receives 04-Jul (PO 26021877). T2 Libolon, actual receives 05-Jun (PO 26021876). T2 Kahatex, PI Date 29-Jul, actual receives 28-May (PO NT-347). 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903156885 KV7863 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 18/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 |  |  | 416 |  | 416 |  |  | 15/09/2026 | 17/09/2026 |  |  | 416 |  | 416
ADIDAS | 0903157062-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 124 | 15/10/2026 | 124 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157062 KU8797 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 124 |  | 124 |  |  | 2026-01-10 | 2026-02-10 |  |  | 124 |  | 124
ADIDAS | 0903157093-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 148 | 15/10/2026 | 148 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903157093 KW8934 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 148 |  | 148 |  |  | 30/09/2026 | 30/09/2026 |  |  | 148 |  | 148
ADIDAS | 0903157098-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903157098 KX0126 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/10/2026 | M RESORT T OLIVE FOUR S27 |  | SS27 | 14/10/2026 | 14/10/2026 |  |  | 128 |  | 128 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-08 | 2026-11-08 | 128 | 84 | 44
ADIDAS | 0903157127-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 273 | 30/09/2026 | 273 | SI | SI26/06/2026 | G3J | PANTS | G3 | ok | (04/08/2026) | 29/09: ex-fty (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 650034 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157127 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA | 21/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 | 19/09/2026 | 19/09/2026 | 273 | 220 | 53 |  | 220 | 17/09/2026 | 18/09/2026 | 15/09/2026 | 16/09/2026 | 273 | 253 | 20
ADIDAS | 0903157138-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 106 | 23/10/2026 | 106 | AN | AN26/06/2026 | G2P | T-SHIRT | G2 | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903157138 LC8943 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 19/10/2026 | M TATTOO SPRT T BLACK |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 106 |  | 106 |  |  | 15/10/2026 | 16/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903157647-1 KE8424 | BLACK | 120D | S2608MR0906A | 890 | 2026-02-10 | 890 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | HT+PAD SUB PROCESS_V3 | 0903157647 KE8424 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-10 | Run Ess LS M BLACK |  | SS27-TI | 2026-12-10 | 13/10/2026 |  |  | 890 |  | 890 |  |  | 2026-08-10 | 2026-09-10 |  |  | 890 |  | 890 |  |  | 2026-06-10 | 2026-07-10 |  |  | 890 |  | 890
ADIDAS | 0903157666-1 KB5965 | BLACK | 120D | S2608MR0900A | 1085 | 31/10/2026 | 1085 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157666 KB5965 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 23/10/2026 | Run Ess Tee M |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 1085 |  | 1085 |  |  | 20/10/2026 | 21/10/2026 |  |  | 1085 |  | 1085 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1085 |  | 1085
ADIDAS | 0903157667-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 1500 | 2026-12-09 | 1500 | SA | SA26/06/2026 | G2Q,G2S,G2T | SHORTS | G2 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 678002 | PRINT L1 SUB PROCESS_V3 | 0903157667 JC9346 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-02-09 | M LIN SJ SHO |  | SS27 | 2026-02-09 | 2026-10-09 | 2026-01-09 | 2026-10-09 | 1500 | 1500 |  |  |  | 29/08/2026 | 2026-07-09 | 31/08/2026 | 2026-10-09 | 1500 | 1500
ADIDAS | 0903157694-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 909 | 31/10/2026 | 909 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903157694 KE8420 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 30/10/2026 | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI | 30/10/2026 | 2026-02-11 |  |  | 909 |  | 909 |  |  | 27/10/2026 | 29/10/2026 |  |  | 909 |  | 909 |  |  | 24/10/2026 | 27/10/2026 |  |  | 909 |  | 909
ADIDAS | 0903157699-1 KB5960 | WHITE | 120D | S2608MR0900A | 191 | 31/10/2026 | 191 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157699 KB5960 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 191 |  | 191 |  |  | 21/10/2026 | 22/10/2026 |  |  | 191 |  | 191 |  |  | 19/10/2026 | 20/10/2026 |  |  | 191 |  | 191
ADIDAS | 0903157718-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 850 | 31/10/2026 | 850 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 680015 | HT+PAD SUB PROCESS_V3 | 0903157718 KF5311 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 17/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 850 |  | 850 |  |  | 14/10/2026 | 15/10/2026 |  |  | 850 |  | 850 |  |  | 2026-12-10 | 13/10/2026 |  |  | 850 |  | 850
ADIDAS | 0903157733-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 198 | 15/10/2026 | 198 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903157733 KD0738 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 17/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 198 |  | 198 |  |  | 14/10/2026 | 15/10/2026 |  |  | 198 |  | 198 |  |  | 2026-08-10 | 2026-09-10 |  |  | 198 |  | 198
ADIDAS | 0903157738-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 306 | 23/09/2026 | 306 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157738 JD5302 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 28/08/2026 | W 3S FT CF PT |  | SS27 | 28/08/2026 | 31/08/2026 | 29/08/2026 | 31/08/2026 | 306 | 306 |  |  |  | 24/08/2026 | 27/08/2026 | 20/08/2026 | 27/08/2026 | 306 | 306
ADIDAS | 0903157739-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 1210 | 23/10/2026 | 1210 | SI | SI26/06/2026 | G1A | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157739 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 1210 |  | 1210 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903157745-1 JE9016 | BLACK/WHITE | 90D | S2554MESS642WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | 29/09: ex-fty. T2 Gistex, PI Date 10-Aug, actual receives 22-Aug. 1st Art (TC 10 pcs) 678002 | PRINT L1+PPH L1 SUB PROCESS_V3 | 0903157745 JE9016 | 2026-10-09 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/09/2026 | M LIN CHELSEA |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1500 |  | 1500 |  |  | 19/09/2026 | 22/09/2026 | 15/09/2026 | 18/09/2026 | 1500 | 590 | 910
ADIDAS | 0903157766-1 KE6899 | BLACK | 105D | S2608WR0601B | 120 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Airowes). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903157766 KE6899 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903157768-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 303 | 15/10/2026 | 303 | SI | SI26/06/2026 | G1J | SHORTS | G1 | (10/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 10-Aug, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, using fabric stock. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157768 KY4155 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 303 |  | 303 |  |  | 20/10/2026 | 22/10/2026 |  |  | 303 |  | 303
ADIDAS | 0903157787-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 546 | 30/10/2026 | 546 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). 684009 | HT+PAD SUB PROCESS_V3 | 0903157787 KX3655 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA | 17/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 546 |  | 546 |  |  | 14/10/2026 | 15/10/2026 |  |  | 546 |  | 546 |  |  | 2026-12-10 | 13/10/2026 |  |  | 546 |  | 546
ADIDAS | 0903157799-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 31/10/2026 | 114 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157799 KF5311 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 16/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 114 |  | 114 |  |  | 13/10/2026 | 14/10/2026 |  |  | 114 |  | 114 |  |  | 2026-10-10 | 2026-12-10 |  |  | 114 |  | 114
ADIDAS | 0903157804-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 118 | 30/09/2026 | 118 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Formosa, PI Date 03-Jul, actual receives 13-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903157804 KZ3204 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 23/09/2026 | 26/09/2026 |  |  | 118 |  | 118 |  |  | 19/09/2026 | 23/09/2026 | 31/08/2026 | 2026-05-09 | 118 | 104 | 14
ADIDAS | 0903157810-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G2J | JACKET | G2 | (08/08/2026) | ok | 28/09: ex-fty 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903157810 JE0052 | 2026-10-09 | KAHATEX CIJERAH | PERU | SEA | 23/09/2026 | W 3S FT FZ HD |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903157899-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 108 | 15/10/2026 | 108 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | (Airowes). T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157899 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-02-10 | M SL WV TP PT BLACK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 108 |  | 108 |  |  | 29/09/2026 | 30/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903157900-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 961 | 31/10/2026 | 961 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157900 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 18/11/2026 | 21/11/2026 |  |  | 961 |  | 961 |  |  | 13/11/2026 | 18/11/2026 |  |  | 961 |  | 961
ADIDAS | 0903157925-1 LG9669 | BLACK | 120D | S2754WAS514C | 100 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric (Airowes). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903157925 LG9669 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903157926-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 1091 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 60000 | PRINT L3+PPA SUB PROCESS_V3 | 0903157926 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903157953-1 KE8424 | BLACK | 120D | S2608MR0906A | 489 | 29/09/2026 | 489 | SI | SI26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PAD SUB PROCESS_V3 | 0903157953 KE8424 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 25/09/2026 | Run Ess LS M BLACK |  | SS27-TI | 25/09/2026 | 25/09/2026 |  |  | 489 |  | 489 |  |  | 22/09/2026 | 22/09/2026 | 14/09/2026 | 18/09/2026 | 489 | 441 | 48 |  |  | 19/09/2026 | 19/09/2026 | 14/09/2026 | 18/09/2026 | 489 | 440 | 49
ADIDAS | 0903158029-1 KE6712 | BLACK | 105D | S2608MR0601A | 102 | 31/10/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric (Airowes). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903158029 KE6712 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | adi365 SHORT M BLACK |  | SS27-TRAX
ADIDAS | 0903158101-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 266 | 31/10/2026 | 266 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158101 KX3655 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 16/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 266 |  | 266 |  |  | 13/10/2026 | 14/10/2026 |  |  | 266 |  | 266 |  |  | 2026-10-10 | 2026-12-10 |  |  | 266 |  | 266
ADIDAS | 0903158133-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 379 | 31/10/2026 | 379 | AN | AN26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903158133 KX3654 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 17/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 379 |  | 379 |  |  | 14/10/2026 | 15/10/2026 |  |  | 379 |  | 379 |  |  | 2026-12-10 | 13/10/2026 |  |  | 379 |  | 379
ADIDAS | 0903158148-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 162 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158148 LG9673 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158151-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 436 | 23/10/2026 | 436 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158151 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-07-10 | 2026-08-10 |  |  | 436 |  | 436 |  |  | 2026-03-10 | 2026-05-10 |  |  | 436 |  | 436
ADIDAS | 0903158174-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 142 | 31/10/2026 | 142 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903158174 KE8420 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 30/10/2026 | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI | 30/10/2026 | 30/10/2026 |  |  | 142 |  | 142 |  |  | 27/10/2026 | 27/10/2026 |  |  | 142 |  | 142 |  |  | 24/10/2026 | 24/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903158195-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 160 | 31/10/2026 | 160 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903158195 KF5311 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 16/10/2026 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 160 |  | 160 |  |  | 13/10/2026 | 14/10/2026 |  |  | 160 |  | 160 |  |  | 2026-10-10 | 2026-12-10 |  |  | 160 |  | 160
ADIDAS | 0903158219-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 168 | 23/10/2026 | 168 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158219 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 18/11/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 18/11/2026 | 18/11/2026 |  |  | 168 |  | 168 |  |  | 13/11/2026 | 13/11/2026 |  |  | 168 |  | 168
ADIDAS | 0903158261-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903158261 JG8639 | 2026-10-09 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 23/09/2026 | 15/09/2026 | 18/09/2026 | 300 | 300 |  |  |  | 2026-11-09 | 19/09/2026 | 2026-03-08 | 24/08/2026 | 300 | 300
ADIDAS | 0903158265-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 11222 | 30/09/2026 | 11222 | AT | AT26/06/2026 | G2A | T-SHIRT | G2 | ok | (30/07/2026) | 25/09: ex-fty 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903158265 KA5089 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 2026-02-10 |  |  | 11222 |  | 11222 |  |  | 21/09/2026 | 29/09/2026 | 2026-11-09 | 17/09/2026 | 11222 | 132 | 11090 |  |  | 18/09/2026 | 26/09/2026 | 2026-07-09 | 19/09/2026 | 11222 | 3257 | 7965 |  | 507
ADIDAS | 0903158287-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 624 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPA SUB PROCESS_V3 | 0903158287 LG9672 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903158297-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 482 | 15/10/2026 | 482 | SI | SI26/06/2026 | G3H | JACKET | G3 | (08/08/2026) | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158297 JE0052 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/10/2026 | W 3S FT FZ HD |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 482 |  | 482 |  |  | 20/10/2026 | 21/10/2026 |  |  | 482 |  | 482
ADIDAS | 0903158314-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 492 | 31/10/2026 | 492 | SA | SA26/06/2026 | G1O | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158314 LC6790 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-11-11 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 2026-11-11 | 14/11/2026 |  |  | 492 |  | 492 |  |  | 2026-06-11 | 2026-11-11 |  |  | 492 |  | 492 |  |  | 2026-03-11 | 2026-06-11 |  |  | 492 |  | 492
ADIDAS | 0903158394-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 571 | 31/10/2026 | 571 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903158394 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 571 |  | 571 |  |  | 16/10/2026 | 17/10/2026 |  |  | 571 |  | 571 |  |  | 14/10/2026 | 15/10/2026 |  |  | 571 |  | 571
ADIDAS | 0903158432-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 2411 | 23/10/2026 | 2411 | SI | SI26/06/2026 | G3K | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158432 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-04-11 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 2026-04-11 | 2026-10-11 |  |  | 2411 |  | 2411 |  |  | 31/10/2026 | 2026-05-11 |  |  | 2411 |  | 2411 |  |  | 28/10/2026 | 2026-02-11 |  |  | 2411 |  | 2411
ADIDAS | 0903158445-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 900 | 31/10/2026 | 900 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158445 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 28/11/2026 | 2026-02-12 |  |  | 900 |  | 900 |  |  | 25/11/2026 | 27/11/2026 |  |  | 900 |  | 900
ADIDAS | 0903158467-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 347 | 23/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158467 KY9391 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903158492-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 332 | 15/10/2026 | 332 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158492 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | M SL WV TP PT BLACK |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 332 |  | 332 |  |  | 30/09/2026 | 2026-01-10 |  |  | 332 |  | 332
ADIDAS | 0903158495-1 KZ3207 | SILVER BLUE S27/WHITE | 90D | S2754WESS422WV | 101 | 15/10/2026 | 101 | SI | SI26/06/2026 | G1F | JACKET | G1 | ok | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Libolon, PI Date 22-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 512107 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158495 KZ3207 | 2026-10-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | W 3S WV BOMBER SILVER BLUE S27/WHITE |  | SS27 | 22/10/2026 | 2026-10-11 |  |  | 101 |  | 101 |  |  | 19/10/2026 | 2026-05-11 |  |  | 101 |  | 101
ADIDAS | 0903158556-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1004 | 31/10/2026 | 1004 | SI | SI26/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158556 KR3066 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/11/2026 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 1004 |  | 1004 |  |  | 2026-10-11 | 2026-11-11 |  |  | 1004 |  | 1004 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1004 |  | 1004
ADIDAS | 0903158646-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 507 | 31/10/2026 | 507 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | (28/08/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903158646 LD0930 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-11 | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI | 2026-02-11 | 2026-02-11 |  |  | 507 |  | 507 |  |  | 29/10/2026 | 29/10/2026 |  |  | 507 |  | 507 |  |  | 27/10/2026 | 27/10/2026 |  |  | 507 |  | 507
ADIDAS | 0903158663-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 107 | 2026-07-10 | 107 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158663 KW9039 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 19/10/2026 | 20/10/2026 |  |  | 107 |  | 107 |  |  | 15/10/2026 | 16/10/2026 |  |  | 107 |  | 107
ADIDAS | 0903158671-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 319 | 31/10/2026 | 319 | SA | SA26/06/2026 | G1O | SHORTS | G1 | (25/08/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903158671 LC6790 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 319 |  | 319 |  |  | 2026-11-11 | 2026-12-11 |  |  | 319 |  | 319 |  |  | 2026-06-11 | 2026-09-11 |  |  | 319 |  | 319
ADIDAS | 0903158691-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 118 | 2026-07-10 | 118 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903158691 KW8934 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-01-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 118 |  | 118 |  |  | 28/09/2026 | 29/09/2026 |  |  | 118 |  | 118
ADIDAS | 0903158714-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV-MTF | 300 | 29/09/2026 | 300 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158714 LG9660 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-05-10 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 2026-01-10 | 2026-01-10 |  |  | 300 |  | 300
ADIDAS | 0903158739-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 332 | 15/10/2026 | 332 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158739 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 332 |  | 332 |  |  | 2026-05-10 | 2026-06-10 |  |  | 332 |  | 332
ADIDAS | 0903158761-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 239 | 19/09/2026 | 239 | SA | SA26/06/2026 | G3C | PANTS | G3 | (08/08/2026(13)) |  | 18/09: ex-fty 806020 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903158761 JW7177 | 2026-10-09 | KAHATEX CIJERAH | HONGKONG | SEA | 28/07/2026 | W 3S FT OH PT |  | SS27 | 28/07/2026 | 2026-04-08 | 29/07/2026 | 29/07/2026 | 239 | 239 |  |  |  | 23/07/2026 | 30/07/2026 | 28/07/2026 | 29/07/2026 | 239 | 239
ADIDAS | 0903158798-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 229 | 15/10/2026 | 229 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158798 LF0721 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | M SL WV OH PT OLIVE ONE S27 |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 229 |  | 229 |  |  | 2026-05-10 | 2026-06-10 |  |  | 229 |  | 229
ADIDAS | 0903158825-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 451 | 15/10/2026 | 451 | SA | SA26/06/2026 | G3B | PANTS | G3 | (28/08/2026) | (04/08/2026) | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158825 LE8181 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-09-10 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 451 |  | 451 |  |  | 2026-06-10 | 2026-07-10 |  |  | 451 |  | 451
ADIDAS | 0903158829-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2B | T-SHIRT | G2 | ok | (17/07/2026) | 25/09: ex-fty 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158829 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | DICE TEE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 415 |  | 415 |  |  | 18/09/2026 | 19/09/2026 |  |  | 415 |  | 415 |  |  | 16/09/2026 | 17/09/2026 |  |  | 415 |  | 415
ADIDAS | 0903158854-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 107 | 31/10/2026 | 107 | AN | AN26/06/2026 | G2G | T-SHIRT | G2 | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158854 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-11 | PDX HBR TEE |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 107 |  | 107 |  |  | 2026-04-11 | 2026-05-11 | 15/08/2026 | 26/08/2026 | 107 | 107
ADIDAS | 0903158880-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2E | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158880 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | DICE TEE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 311 |  | 311 |  |  | 15/10/2026 | 15/10/2026 |  |  | 311 |  | 311 |  |  | 13/10/2026 | 13/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903158907-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 245 | 30/09/2026 | 245 | AN | AN26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158907 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PDX HBR TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 245 |  | 245 |  |  | 30/09/2026 | 2026-01-10 | 2026-11-08 | 2026-11-08 | 245 | 244 | 1
ADIDAS | 0903158935-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 415 | 30/09/2026 | 415 | SA | SA26/06/2026 | G2B | T-SHIRT | G2 | ok | (17/07/2026) | 24/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158935 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | PIZZA TEE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 415 |  | 415 |  |  | 17/09/2026 | 18/09/2026 | 2026-07-08 | 19/08/2026 | 415 | 414 | 1
ADIDAS | 0903158955-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 187 | 30/09/2026 | 187 | AN | AN26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158955 KR2020 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | PDX HBR TEE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 187 |  | 187 |  |  | 30/09/2026 | 2026-01-10 | 2026-11-08 | 15/08/2026 | 187 | 187
ADIDAS | 0903158980-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100-MTF | 1203 | 23/09/2026 | 1203 | AN | AN26/06/2026 | G2P | T-SHIRT | G2 | ok | ok | 21/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903158980 KS2152 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/09/2026 | LA PALMS TEE |  | SS27 | 15/09/2026 | 22/09/2026 | 16/09/2026 | 17/09/2026 | 1203 | 990 | 213 |  |  | 2026-11-09 | 18/09/2026 | 2026-08-09 | 19/09/2026 | 1203 | 1098 | 105 |  | 35
ADIDAS | 0903159040-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 862 | 30/09/2026 | 862 | ID | ID26/06/2026 | G2B | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159040 KR2006 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 24/09/2026 | SPORT GOODS T |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 862 |  | 862 |  |  | 21/09/2026 | 22/09/2026 | 2026-08-09 | 18/09/2026 | 862 | 853 | 9
ADIDAS | 0903159048-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 340 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903159048 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903159067-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 31/10/2026 | 311 | SA | SA26/06/2026 | G2L | T-SHIRT | G2 | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159067 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | PIZZA TEE |  | SS27 | 16/10/2026 | 16/10/2026 |  |  | 311 |  | 311 |  |  | 13/10/2026 | 13/10/2026 | 21/08/2026 | 22/08/2026 | 311 | 308 | 3
ADIDAS | 0903159157-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 312 | 15/10/2026 | 312 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159157 KW8932 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 312 |  | 312 |  |  | 30/09/2026 | 2026-01-10 |  |  | 312 |  | 312
ADIDAS | 0903159180-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 274 | 15/10/2026 | 274 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159180 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-06-10 | 2026-06-10 |  |  | 274 |  | 274 |  |  | 2026-02-10 | 2026-02-10 |  |  | 274 |  | 274
ADIDAS | 0903159200-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 346 | 15/10/2026 | 346 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159200 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 346 |  | 346 |  |  | 2026-01-10 | 2026-02-10 |  |  | 346 |  | 346
ADIDAS | 0903159205-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 128 | 15/10/2026 | 128 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159205 LC8884 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 128 |  | 128 |  |  | 2026-10-10 | 2026-12-10 | 2026-11-08 | 2026-11-08 | 128 | 126 | 2
ADIDAS | 0903159207-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 257 | 15/10/2026 | 257 | SI | SI26/06/2026 | G3C | SHORTS | G3 | ok | ok | (Airowes). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 650034 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903159207 KA2571 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 22/10/2026 | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 257 |  | 257 |  |  | 19/10/2026 | 20/10/2026 |  |  | 257 |  | 257 |  |  | 13/10/2026 | 14/10/2026 |  |  | 257 |  | 257
ADIDAS | 0903159239-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 238 | 15/10/2026 | 238 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903159239 KW8935 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-06-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-06-10 | 2026-06-10 |  |  | 238 |  | 238 |  |  | 2026-02-10 | 2026-02-10 |  |  | 238 |  | 238
ADIDAS | 0903159261-1 KT4840 | ONIX | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA26/06/2026 | G1N | T-SHIRT | G1 | (04/08/2026) | ok | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650036 | HT SUB PROCESS_V1 | 0903159261 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 18/11/2026 | ADIZERO E TEE |  | SS27-YTI | 18/11/2026 | 19/11/2026 |  |  | 324 |  | 324 |  |  | 16/11/2026 | 17/11/2026 |  |  | 324 |  | 324 |  |  | 13/11/2026 | 16/11/2026 |  |  | 324 |  | 324
ADIDAS | 0903159282-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 132 | 15/10/2026 | 132 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | (Cargoport). T2 Kahatex, PI Date 28-Aug, actual receives 27-Aug. T2 Teijin Nantong, PI Date 03-Aug, actual receives 24-Aug. 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159282 LD5446 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 14/10/2026 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 132 |  | 132 |  |  | 2026-10-10 | 2026-12-10 |  |  | 132 |  | 132
ADIDAS | 0903159289-1 KA0235 | BLACK | 90D | S2608WR0901 | 1180 | 23/10/2026 | 1180 | SI | SI26/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 516415 | PAD+HT SUB PROCESS_V3 | 0903159289 KA0235 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 1180 |  | 1180 |  |  | 2026-11-11 | 2026-12-11 |  |  | 1180 |  | 1180 |  |  | 2026-10-11 | 2026-11-11 |  |  | 1180 |  | 1180
ADIDAS | 0903159308-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 102 | 15/10/2026 | 102 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (Cargoport). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650036 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159308 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-09-10 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 102 |  | 102 |  |  | 2026-06-10 | 2026-07-10 |  |  | 102 |  | 102
ADIDAS | 0903159320-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 222 | 30/09/2026 | 222 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 29/09: ex-fty (Cargoport). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650036 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159320 LF1392 | 2026-10-09 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-01-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-01-10 | 2026-01-10 |  |  | 222 |  | 222 |  |  | 28/09/2026 | 28/09/2026 | 28/08/2026 | 28/08/2026 | 222 | 221 | 1
ADIDAS | 0903159340-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 313 | 30/09/2026 | 313 | SI | SI26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 838103 | PRINT L1 SUB PROCESS_V3 | 0903159340 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-01-10 | LFC GR TEE1 BLACK |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 313 |  | 313 |  |  | 28/09/2026 | 29/09/2026 |  |  | 313 |  | 313
ADIDAS | 0903159374-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 100 | 15/10/2026 | 100 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903159374 KW8932 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 30/09/2026 | 2026-01-10 |  |  | 100 |  | 100
ADIDAS | 0903159424-1 LG9669 | BLACK | 120D | S2754WAS514C | 120 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric (Cargoport). T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 650036 | PRINT L3+PPA SUB PROCESS_V3 | 0903159424 LG9669 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903159447-1 KE6899 | BLACK | 105D | S2608WR0601B | 102 | 31/10/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric (Cargoport). T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903159447 KE6899 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | adi365 Short W BLACK |  | SS27-TRAX
ADIDAS | 0903159551-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159551 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 19/09/2026 | 21/09/2026 | 2026-02-09 | 2026-10-09 | 300 | 92 | 208
ADIDAS | 0903159571-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 2026-12-09 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159571 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 2026-05-09 | 29/08/2026 | 31/08/2026 | 522 | 522 |  |  |  | 27/08/2026 | 2026-02-09 | 24/08/2026 | 2026-08-09 | 522 | 522
ADIDAS | 0903159587-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 522 | 23/09/2026 | 522 | SI | SI26/06/2026 | G3K | PANTS | G3 | ok | ok | 21/09: ex-fty 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903159587 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | W 3S FT CF PT |  | SS27 | 31/08/2026 | 19/09/2026 | 31/08/2026 | 18/09/2026 | 522 | 521 | 1 |  |  | 27/08/2026 | 16/09/2026 | 27/08/2026 | 2026-09-09 | 522 | 518 | 4
ADIDAS | 0903159678-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 159 | 23/10/2026 | 159 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903159678 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 16/10/2026 |  |  | 159 |  | 159 |  |  | 2026-12-10 | 13/10/2026 |  |  | 159 |  | 159 |  |  | 2026-10-10 | 2026-12-10 |  |  | 159 |  | 159
ADIDAS | 0903159703-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 101 | 23/10/2026 | 101 | AN | AN26/06/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159703 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-10-11 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 101 |  | 101 |  |  | 2026-05-11 | 2026-11-11 |  |  | 101 |  | 101
ADIDAS | 0903159732-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 155 | 23/10/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 512106 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159732 KU8975 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903159856-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 606 | 30/09/2026 | 606 | SA | SA26/06/2026 | G1D | SHORTS | G1 | ok |  | 29/09: ex-fty. T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 25-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 1st Art (TC 10 pcs) 630001 | PAD+HT SUB PROCESS_V3 | 0903159856 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 23/09/2026 | 24/09/2026 |  |  | 606 |  | 606 |  |  | 19/09/2026 | 21/09/2026 |  |  | 606 |  | 606 |  |  | 18/09/2026 | 19/09/2026 |  |  | 606 |  | 606
ADIDAS | 0903159879-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 300 | 31/10/2026 | 300 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903159879 KB5960 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300 |  |  | 21/10/2026 | 22/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 20/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903159916-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 305 | 31/10/2026 | 305 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | DRC 0051-T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159916 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 26/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 305 |  | 305 |  |  | 22/10/2026 | 24/10/2026 |  |  | 305 |  | 305 |  |  | 19/10/2026 | 21/10/2026 |  |  | 305 |  | 305
ADIDAS | 0903159937-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 920 | 31/10/2026 | 920 | SA | SA26/06/2026 | G1I | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 630001 | PAD+HT SUB PROCESS_V3 | 0903159937 JZ7775 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 13/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 920 |  | 920 |  |  | 2026-10-11 | 2026-11-11 |  |  | 920 |  | 920 |  |  | 2026-09-11 | 2026-10-11 |  |  | 920 |  | 920
ADIDAS | 0903159964-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 607 | 15/10/2026 | 607 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903159964 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 607 |  | 607 |  |  | 29/09/2026 | 29/09/2026 |  |  | 607 |  | 607 |  |  | 28/09/2026 | 28/09/2026 |  |  | 607 |  | 607
ADIDAS | 0903159994-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B-MTF | 328 | 15/10/2026 | 328 | AN | AN26/06/2026 | G1G | JACKET | G1 | (12/08/2026) | (31/07/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 29-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159994 KX7716 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 16/10/2026 | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 16/10/2026 | 21/10/2026 |  |  | 328 |  | 328 |  |  | 13/10/2026 | 17/10/2026 |  |  | 328 |  | 328
ADIDAS | 0903160003-1 KA3530 | BLACK | 105D | S2650MTR402 | 237 | 15/10/2026 | 237 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | T2 Far Eastern, material quality issues (hairy, approve by Weldan), PI Date 27-Jul, actual receives 08-Sep. 830009 | PAD+HT SUB PROCESS_V3 | 0903160003 KA3530 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | WE FR T BLACK |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 237 |  | 237 |  |  | 29/09/2026 | 29/09/2026 |  |  | 237 |  | 237 |  |  | 28/09/2026 | 28/09/2026 |  |  | 237 |  | 237
ADIDAS | 0903160021-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 328 | 15/10/2026 | 328 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 630001 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160021 KX7715 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 13/10/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 13/10/2026 | 16/10/2026 |  |  | 328 |  | 328 |  |  | 2026-09-10 | 13/10/2026 |  |  | 328 |  | 328
ADIDAS | 0903160116-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 364 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 630001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903160116 KV7863 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903160143-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 382 | 31/10/2026 | 382 | AN | AN26/06/2026 | G2P | SHORTS | G2 | (29/07/2026) | ok | T2 Kahatex, PI Date 29-Jun, actual receives 13-Aug. T2 Libolon, PI Date 21-Jul, actual receives 22-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160143 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 27/10/2026 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 382 |  | 382 |  |  | 23/10/2026 | 24/10/2026 |  |  | 382 |  | 382
ADIDAS | 0903160371-1 KA0246 | BLACK | 90D | S2608WR0902 | 1181 | 15/10/2026 | 1181 | SI | SI26/06/2026 | G1B | SHORTS | G1 | ok |  | 29/09: ex-fty. DRC 0051-T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 27-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160371 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 1181 |  | 1181 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1181 |  | 1181 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1181 |  | 1181
ADIDAS | 0903160415-1 KA0246 | BLACK | 90D | S2608WR0902 | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G2L | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516404 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160415 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-01-10 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 28/09/2026 |  |  | 300 |  | 300 |  |  | 23/09/2026 | 24/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903160502-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 852 | 31/10/2026 | 852 | SI | SI26/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160502 LD0908 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 21/10/2026 | 23/10/2026 |  |  | 852 |  | 852 |  |  | 17/10/2026 | 20/10/2026 |  |  | 852 |  | 852 |  |  | 14/10/2026 | 16/10/2026 |  |  | 852 |  | 852
ADIDAS | 0903160693-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 359 | 31/10/2026 | 359 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160693 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/11/2026 | W SL WV TT BLACK |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 359 |  | 359 |  |  | 2026-10-11 | 2026-11-11 |  |  | 359 |  | 359
ADIDAS | 0903160711-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 758 | 31/10/2026 | 758 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | ok | DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903160711 KX3650 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI | 23/10/2026 | 23/10/2026 |  |  | 758 |  | 758 |  |  | 20/10/2026 | 20/10/2026 |  |  | 758 |  | 758 |  |  | 17/10/2026 | 17/10/2026 |  |  | 758 |  | 758
ADIDAS | 0903160743-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 594 | 31/10/2026 | 594 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | (28/08/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903160743 KX3655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 594 |  | 594 |  |  | 14/10/2026 | 15/10/2026 |  |  | 594 |  | 594 |  |  | 2026-12-10 | 13/10/2026 |  |  | 594 |  | 594
ADIDAS | 0903160769-1 LG9675 | BLACK | 120D | S2754WAS513C | 392 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903160769 LG9675 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903160834-1 LE8187 | BLACK | 105D | S2754MAS513 | 217 | 15/10/2026 | 217 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160834 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-02-10 | M SL WV TP PT BLACK |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 217 |  | 217 |  |  | 29/09/2026 | 30/09/2026 |  |  | 217 |  | 217
ADIDAS | 0903160891-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 317 | 31/10/2026 | 317 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903160891 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 25/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 25/11/2026 | 28/11/2026 |  |  | 317 |  | 317 |  |  | 20/11/2026 | 25/11/2026 |  |  | 317 |  | 317
ADIDAS | 0903161081-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 300 | 15/10/2026 | 300 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | (KN GLT). T2 Teijin Nantong, PI Date 03-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 01-Aug (PO NT-365). 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903161081 LE8181 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300
ADIDAS | 0903161114-1 KS0802 | TECH INDIGO S20/WHITE | 105D | S2608WR0601B | 7 | 15/10/2026 | 7 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | (KN GLT). T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 16-Sep. 650010 | PAD+HT SUB PROCESS_V3 | 0903161114 KS0802 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | adi365 Short W TECH INDIGO S20/WHITE |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 7 |  | 7 |  |  | 22/10/2026 | 24/10/2026 |  |  | 7 |  | 7 |  |  | 21/10/2026 | 23/10/2026 |  |  | 7 |  | 7
ADIDAS | 0903161148-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 5352 | 15/10/2026 | 5352 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Libolon, PI Date 22-Jul. actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 29-Jul. T2 Formosa, PI Date 09-Jun, actual receives 22-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161148 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 2026-06-10 | 14/10/2026 |  |  | 5352 |  | 5352 |  |  | 2026-02-10 | 2026-10-10 |  |  | 5352 |  | 5352
ADIDAS | 0903161212-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 8768 | 30/09/2026 | 8768 | SI | SI26/06/2026 | G3F,G3G | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903161212 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 21/09/2026 | 30/09/2026 |  |  | 8768 |  | 8768 |  |  | 17/09/2026 | 26/09/2026 | 2026-11-09 | 19/09/2026 | 8768 | 8335 | 433 |  | 1
ADIDAS | 0903161277-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 141 | 23/09/2026 | 141 | AN | AN26/06/2026 | G1R | T-SHIRT | G1 | ok | ok | 21/09: ex-fty 516342 | PRINT L3+PAD SUB PROCESS_V3 | 0903161277 LC8882 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T BLACK |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 18/09/2026 | 141 | 141 |  |  |  | 2026-11-09 | 15/09/2026 | 2026-11-08 | 13/08/2026 | 141 | 141
ADIDAS | 0903162196-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 313 | 23/09/2026 | 313 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 18/09: ex-fty. T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162196 KV7963 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 313 | 313 |  |  |  | 2026-05-09 | 2026-10-09 | 14/08/2026 | 19/09/2026 | 313 | 309 | 4 |  | 5
ADIDAS | 0903162215-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV-MTF | 846 | 30/09/2026 | 846 | AN | AN26/06/2026 | G2Q | SHORTS | G2 | (29/07/2026) | ok | 28/09: ex-fty. T2 Libolon, PI Date 20-Jul, actual receives 09-Jul. T2 Formosa, actual receives 04-Jul (PO 26022032). T2 Kahatex, PI Date 29-Jun, actual receives 22-Jun (PO NT-351). 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162215 KW2924 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-10 | W 3S WV BER SHO BLACK/WHITE |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 846 |  | 846 |  |  | 2026-01-10 | 2026-03-10 |  |  | 846 |  | 846
ADIDAS | 0903162243-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 321 | 15/10/2026 | 321 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162243 LE8188 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 29/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 321 |  | 321 |  |  | 25/09/2026 | 26/09/2026 |  |  | 321 |  | 321
ADIDAS | 0903162307-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162307 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-11-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-11-11 | 2026-12-11 |  |  | 153 |  | 153 |  |  | 2026-06-11 | 2026-09-11 |  |  | 153 |  | 153 |  |  | 2026-05-11 | 2026-06-11 |  |  | 153 |  | 153
ADIDAS | 0903162341-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 205 | 15/10/2026 | 205 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | ok | ok | Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162341 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 205 |  | 205 |  |  | 29/09/2026 | 29/09/2026 |  |  | 205 |  | 205 |  |  | 28/09/2026 | 28/09/2026 |  |  | 205 |  | 205
ADIDAS | 0903162369-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 1229 | 30/09/2026 | 1229 | SA | SA26/06/2026 | G1B | JACKET | G1 | (03/08/2026) | ok | 29/09: ex-fty. T2 Libolon, PI Date 23-Jul, actual receives 29-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903162369 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 23/09/2026 | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 1229 |  | 1229 |  |  | 19/09/2026 | 22/09/2026 |  |  | 1229 |  | 1229
ADIDAS | 0903162384-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162384 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/11/2026 | M SERENO SHO WHITE |  | SS27-STX | 17/11/2026 | 18/11/2026 |  |  | 327 |  | 327 |  |  | 2026-12-11 | 13/11/2026 |  |  | 327 |  | 327 |  |  | 2026-11-11 | 2026-12-11 |  |  | 327 |  | 327
ADIDAS | 0903162397-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900-MTF | 1526 | 31/10/2026 | 1526 | AN | AN29/06/2026 | G2J | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162397 LD0285 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-10-10 | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI | 2026-10-10 | 2026-12-10 |  |  | 1526 |  | 1526 |  |  | 2026-07-10 | 2026-08-10 |  |  | 1526 |  | 1526 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1526 |  | 1526
ADIDAS | 0903162420-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 100 | 15/10/2026 | 100 | ID | ID26/06/2026 | G1L | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162420 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO 3S T BLACK |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 29/09/2026 |  |  | 100 |  | 100 |  |  | 28/09/2026 | 28/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903162423-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 1500 | 31/10/2026 | 1500 | AN | AN29/06/2026 | G2H | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162423 LD0287 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 1500 |  | 1500 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1500 |  | 1500 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1500 |  | 1500
ADIDAS | 0903162450-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 300 | 31/10/2026 | 300 | AN | AN29/06/2026 | G2Q | T-SHIRT | G2 |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162450 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 21/10/2026 | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI | 21/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 17/10/2026 | 17/10/2026 | 19/09/2026 | 19/09/2026 | 300 | 1 | 299 |  | 1 | 15/10/2026 | 15/10/2026 | 18/09/2026 | 18/09/2026 | 300 | 1 | 299
ADIDAS | 0903162460-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 327 | 30/10/2026 | 327 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. DRC 0002-T2 Fu Hsun, LLT material, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162460 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 17/11/2026 | M SERENO SHO BLACK |  | SS27-STX | 17/11/2026 | 18/11/2026 |  |  | 327 |  | 327 |  |  | 2026-12-11 | 13/11/2026 |  |  | 327 |  | 327 |  |  | 2026-11-11 | 2026-12-11 |  |  | 327 |  | 327
ADIDAS | 0903162479-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 300 | 31/10/2026 | 300 | AN | AN26/06/2026 | G1K | JACKET | G1 | ok | (07/08/2026) | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 20-Jul, actual receives 31-Aug. 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903162479 LF0727 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-03-11 | M SL WV TT BLACK |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 300 |  | 300 |  |  | 30/10/2026 | 2026-02-11 |  |  | 300 |  | 300
ADIDAS | 0903162500-1 LC6341 | BLACK | 90D | S27GMGFX130 | 246 | 30/09/2026 | 246 | SA | SA26/06/2026 | G2G | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 1st Art (TC 10 pcs) 630001 | PRINT L3+PAD SUB PROCESS_V3 | 0903162500 LC6341 | 2026-10-09 | KAHATEX CIJERAH | CANADA | SEA | 16/10/2026 | M SEE2X SHO12X T BLACK |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 246 |  | 246 |  |  | 13/10/2026 | 14/10/2026 | 2026-09-09 | 17/09/2026 | 246 | 245 | 1
ADIDAS | 0903162572-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 153 | 15/10/2026 | 153 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162572 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO SHO WHITE |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 153 |  | 153 |  |  | 29/09/2026 | 30/09/2026 |  |  | 153 |  | 153 |  |  | 28/09/2026 | 29/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903162593-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 624 | 15/10/2026 | 624 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162593 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-11-11 | M SERENO SHO BLACK |  | SS27-STX | 2026-11-11 | 2026-12-11 |  |  | 624 |  | 624 |  |  | 2026-06-11 | 2026-09-11 |  |  | 624 |  | 624 |  |  | 2026-05-11 | 2026-06-11 |  |  | 624 |  | 624
ADIDAS | 0903162621-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 512 | 15/10/2026 | 512 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903162621 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M SERENO SHO WHITE |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 512 |  | 512 |  |  | 29/09/2026 | 30/09/2026 |  |  | 512 |  | 512 |  |  | 28/09/2026 | 29/09/2026 |  |  | 512 |  | 512
ADIDAS | 0903162642-1 KZ0645 | BLACK | 90D | S2706CHLF022 | 195 | 30/09/2026 | 195 | SI | SI26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 814006 | PRINT L1 SUB PROCESS_V3 | 0903162642 KZ0645 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-01-10 | LFC GR TEE1 BLACK |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 195 |  | 195 |  |  | 28/09/2026 | 29/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903163124-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 372 | 31/10/2026 | 372 | SA | SA26/06/2026 | G1C | JACKET | G1 | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903163124 LG9661 | 24/09/2026 | KAHATEX CIJERAH | INDIA | SEA | 13/11/2026 | W SL WV TT AURORA COFFEE S26 |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 372 |  | 372 |  |  | 2026-10-11 | 2026-11-11 |  |  | 372 |  | 372
ADIDAS | 0903163142-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 344 | 15/10/2026 | 344 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903163142 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 344 |  | 344 |  |  | 29/09/2026 | 30/09/2026 |  |  | 344 |  | 344
ADIDAS | 0903163156-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 8 | 15/10/2026 | 8 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric (KN GLT). T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903163156 KE6716 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 8 |  | 8 |  |  | 2026-05-10 | 2026-08-10 |  |  | 8 |  | 8 |  |  | 2026-03-10 | 2026-07-10 |  |  | 8 |  | 8
ADIDAS | 0903163238-1 KB5960 | WHITE | 120D | S2608MR0900A | 887 | 31/10/2026 | 887 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163238 KB5960 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | Run Ess Tee M |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 887 |  | 887 |  |  | 24/10/2026 | 26/10/2026 |  |  | 887 |  | 887 |  |  | 22/10/2026 | 23/10/2026 |  |  | 887 |  | 887
ADIDAS | 0903163335-1 KB5965 | BLACK | 120D | S2608MR0900A | 1228 | 31/10/2026 | 1228 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163335 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 1228 |  | 1228 |  |  | 21/10/2026 | 22/10/2026 |  |  | 1228 |  | 1228 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1228 |  | 1228
ADIDAS | 0903163398-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 300 | 31/10/2026 | 300 | SI | SI26/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903163398 KD3854 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 24/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 21/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903163494-1 KE6899 | BLACK | 105D | S2608WR0601B | 1139 | 15/10/2026 | 1139 | SI | SI26/06/2026 | G3H | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163494 KE6899 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 28/10/2026 | adi365 Short W BLACK |  | SS27-TRAX | 28/10/2026 | 30/10/2026 |  |  | 1139 |  | 1139 |  |  | 24/10/2026 | 27/10/2026 |  |  | 1139 |  | 1139 |  |  | 23/10/2026 | 26/10/2026 |  |  | 1139 |  | 1139
ADIDAS | 0903163534-1 KE6716 | TECH INDIGO S20 | 105D | S2608MR0601A | 688 | 15/10/2026 | 688 | SA | SA26/06/2026 | G3E | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903163534 KE6716 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | adi365 SHORT M TECH INDIGO S20 |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 688 |  | 688 |  |  | 2026-08-10 | 2026-12-10 |  |  | 688 |  | 688 |  |  | 2026-07-10 | 2026-10-10 |  |  | 688 |  | 688
ADIDAS | 0903163589-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 336 | 15/10/2026 | 336 | AN | AN26/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric replacement (KN GLT). DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 650010 | PRINT L2+HT SUB PROCESS_V3 | 0903163589 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 15/10/2026 |  |  | 336 |  | 336 |  |  | 2026-12-10 | 2026-12-10 |  |  | 336 |  | 336 |  |  | 2026-10-10 | 2026-10-10 |  |  | 336 |  | 336
ADIDAS | 0903163782-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 300 | 30/09/2026 | 300 | SA | SA26/06/2026 | G1D | JACKET | G1 | ok | ok | 28/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 1st Art (TC 10 pcs) 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903163782 JM1772 | 2026-10-09 | KAHATEX CIJERAH | BRAZIL | SEA | 28/09/2026 | M SL WV TT |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 26/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903164375-1 KW5050 | MAROON | 90D | F2625M101 | 1414 | 23/10/2026 | 1414 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | (29/07/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164375 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | ESS REG |  | SS27-STX | 2026-09-10 | 2026-10-10 |  |  | 1414 |  | 1414 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1414 |  | 1414
ADIDAS | 0903164418-1 KW5050 | MAROON | 90D | F2625M101 | 230 | 15/10/2026 | 230 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164418 KW5050 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 13/10/2026 | ESS REG |  | SS27-STX | 13/10/2026 | 13/10/2026 |  |  | 230 |  | 230 |  |  | 2026-09-10 | 2026-09-10 |  |  | 230 |  | 230
ADIDAS | 0903164473-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 776 | 23/10/2026 | 776 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164473 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-10-10 | 2026-12-10 |  |  | 776 |  | 776 |  |  | 2026-07-10 | 2026-08-10 |  |  | 776 |  | 776
ADIDAS | 0903164544-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 214 | 15/10/2026 | 214 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903164544 KT7396 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-02-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 214 |  | 214 |  |  | 29/09/2026 | 30/09/2026 |  |  | 214 |  | 214
ADIDAS | 0903164569-1 KW5050 | MAROON | 90D | F2625M101 | 170 | 2026-07-10 | 170 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164569 KW5050 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | ESS REG |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 170 |  | 170 |  |  | 2026-01-10 | 2026-01-10 | 17/09/2026 | 17/09/2026 | 170 | 159 | 11
ADIDAS | 0903164595-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 416 | 2026-07-10 | 416 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903164595 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/10/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 13/10/2026 | 14/10/2026 |  |  | 416 |  | 416 |  |  | 2026-09-10 | 2026-10-10 |  |  | 416 |  | 416 |  |  | 2026-08-10 | 2026-09-10 |  |  | 416 |  | 416
ADIDAS | 0903164629-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 808 | 2026-07-10 | 808 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 |  | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903164629 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-03-10 | 2026-03-10 |  |  | 808 |  | 808 |  |  | 30/09/2026 | 30/09/2026 |  |  | 808 |  | 808
ADIDAS | 0903164697-1 IN1172 | BLACK | 90D | S2408WR1600-SLT | 133 | 31/10/2026 | 133 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164697 IN1172 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 133 | 133 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 133 | 133 |  |  |  | 2026-11-08 | 26/08/2026 | 15/07/2026 | 23/07/2026 | 133 | 133
ADIDAS | 0903164732-1 IN1156 | BLACK | 90D | S2408MR1600-SLT | 264 | 31/10/2026 | 264 | ID | ID26/06/2026 | G1M | T-SHIRT | G1 | ok | ok | Waiting schedule (NYK warehouse). DRC 0047-hold shipment customer. T2 Far Eastern, using fabric booking (PO 26009343). T2 Fu Hsun, using fabric booking (PO 26009344). 800005 | HT SUB PROCESS_V1 | 0903164732 IN1156 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-SLT-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 264 | 264 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-03-08 | 2026-03-08 | 264 | 264 |  |  |  | 2026-11-08 | 26/08/2026 | 13/07/2026 | 27/07/2026 | 264 | 264
ADIDAS | 0903164830-1 KT4840 | ONIX | 90D | S2408MR1600 | 102 | 30/09/2026 | 102 | SA | SA26/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Far Eastern, PI Date 03-Aug, actual receives 08-Aug (switch fabric from Y.T.I.). T2 Fu Hsun, PI Date 25-Jul, actual receives 08-Aug (switch fabric from Y.T.I.). 830009 | HT SUB PROCESS_V1 | 0903164830 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 24/09/2026 |  |  | 102 |  | 102 |  |  | 22/09/2026 | 22/09/2026 | 16/09/2026 | 18/09/2026 | 102 | 101 | 1 |  |  | 21/09/2026 | 21/09/2026 | 14/09/2026 | 17/09/2026 | 102 | 101 | 1
ADIDAS | 0903164987-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 110 | 2026-07-10 | 110 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 1st Art (TC 10 pcs) 800187 | EMBRO SUB PROCESS_V1 | 0903164987 KT7396 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 110 |  | 110 |  |  | 29/09/2026 | 30/09/2026 | 16/09/2026 | 16/09/2026 | 110 | 110
ADIDAS | 0903165005-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 135 | 15/10/2026 | 135 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165005 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | M SL WV TP PT BLACK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 135 |  | 135 |  |  | 28/09/2026 | 29/09/2026 |  |  | 135 |  | 135
ADIDAS | 0903165033-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 408 | 2026-07-10 | 408 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903165033 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 30/09/2026 | 2026-02-10 |  |  | 408 |  | 408 |  |  | 26/09/2026 | 29/09/2026 |  |  | 408 |  | 408 |  |  | 25/09/2026 | 28/09/2026 |  |  | 408 |  | 408
ADIDAS | 0903165037-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 273 | 31/10/2026 | 273 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165037 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 25/11/2026 | 28/11/2026 |  |  | 273 |  | 273 |  |  | 20/11/2026 | 25/11/2026 |  |  | 273 |  | 273
ADIDAS | 0903165054-1 KW5050 | MAROON | 90D | F2625M101 | 447 | 15/10/2026 | 447 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903165054 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | ESS REG |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 447 |  | 447 |  |  | 2026-01-10 | 2026-01-10 |  |  | 447 |  | 447
ADIDAS | 0903165062-1 LF0727 | BLACK | 120D | S2754MAS510B | 562 | 31/10/2026 | 562 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165062 LF0727 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-11 | M SL WV TT BLACK |  | SS27 | 2026-05-11 | 2026-10-11 |  |  | 562 |  | 562 |  |  | 2026-02-11 | 2026-05-11 |  |  | 562 |  | 562
ADIDAS | 0903165070-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 309 | 30/09/2026 | 309 | SI | SI26/06/2026 | G1B | SHORTS | G1 | (27/08/2026) |  | 25/09: ex-fty. Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903165070 LD0908 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 309 |  | 309 |  |  | 23/09/2026 | 24/09/2026 |  |  | 309 |  | 309 |  |  | 19/09/2026 | 21/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903165085-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 303 | 31/10/2026 | 303 | SI | SI26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165085 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/11/2026 | M SL WV TT LEGEND IVY S19 |  | SS27 | 25/11/2026 | 28/11/2026 |  |  | 303 |  | 303 |  |  | 20/11/2026 | 25/11/2026 |  |  | 303 |  | 303
ADIDAS | 0903165109-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 495 | 15/10/2026 | 495 | AN | AN26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165109 LE8187 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | M SL WV TP PT BLACK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 495 |  | 495 |  |  | 28/09/2026 | 29/09/2026 |  |  | 495 |  | 495
ADIDAS | 0903165167-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 900 | 30/09/2026 | 900 | SA | SA26/06/2026 | G1D | JACKET | G1 | (29/07/2026) | ok | 28/09: ex-fty. T2 Libolon, PI Date 30-Jun, actual receives 17-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903165167 JM1772 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | M SL WV TT |  | SS27 | 28/09/2026 | 30/09/2026 |  |  | 900 |  | 900 |  |  | 24/09/2026 | 26/09/2026 |  |  | 900 |  | 900
ADIDAS | 0903165226-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 999 | 30/09/2026 | 999 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165226 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 999 |  | 999 |  |  | 21/09/2026 | 23/09/2026 |  |  | 999 |  | 999
ADIDAS | 0903165306-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 168 | 2026-07-10 | 168 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165306 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 168 |  | 168 |  |  | 21/09/2026 | 21/09/2026 |  |  | 168 |  | 168
ADIDAS | 0903165362-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165362 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903165408-1 LG9675 | BLACK | 120D | S2754WAS513C | 384 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903165408 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903165425-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 315 | 30/09/2026 | 315 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 26/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903165425 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 315 |  | 315 |  |  | 23/09/2026 | 23/09/2026 |  |  | 315 |  | 315
ADIDAS | 0903165470-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 1248 | 30/09/2026 | 1248 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165470 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-01-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 1248 |  | 1248 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1248 |  | 1248
ADIDAS | 0903165496-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 300 | 31/10/2026 | 300 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165496 LF0729 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-11 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 31/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903165506-1 LC7300 | WHITE | 90D | S2725M926A | 318 | 30/09/2026 | 318 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L1 SUB PROCESS_V3 | 0903165506 LC7300 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-10 | MONO TREFOIL WHITE |  | SS27-STX | 2026-09-10 | 2026-09-10 |  |  | 318 |  | 318 |  |  | 2026-06-10 | 2026-06-10 |  |  | 318 |  | 318
ADIDAS | 0903165542-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 517 | 2026-07-10 | 517 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903165542 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 19/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 19/10/2026 | 20/10/2026 |  |  | 517 |  | 517 |  |  | 15/10/2026 | 16/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903165585-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 1245 | 30/09/2026 | 1245 | SI | SI26/06/2026 | G1K | POLO SHIRT | G1 | (12/08/2026) | ok | 25/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903165585 KW9039 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/09/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 21/09/2026 | 23/09/2026 |  |  | 1245 |  | 1245 |  |  | 17/09/2026 | 19/09/2026 |  |  | 1245 |  | 1245
ADIDAS | 0903165644-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 243 | 19/09/2026 | 243 | AN | AN26/06/2026 | G1Q | T-SHIRT | G1 | (28/07/2026) | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_18_08_2026 EARLY HOLD SHIPMENT). 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903165644 KX0123 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | M ADI RETRO T WHITE |  | SS27 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 18/09/2026 | 243 | 243 |  |  |  | 2026-11-09 | 15/09/2026 | 31/07/2026 | 2026-08-08 | 243 | 243
ADIDAS | 0903165645-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 428 | 31/10/2026 | 428 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903165645 KG3190 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | Run Ess Tee M CARBON S18 |  | SS27-TI | 15/10/2026 | 16/10/2026 |  |  | 428 |  | 428 |  |  | 2026-12-10 | 13/10/2026 |  |  | 428 |  | 428 |  |  | 2026-09-10 | 2026-10-10 |  |  | 428 |  | 428
ADIDAS | 0903166391-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 22/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903166391 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-12-09 | 21/09/2026 | 2026-12-09 | 15/09/2026 | 300 | 253 | 47 |  |  | 2026-09-09 | 17/09/2026 | 29/08/2026 | 15/09/2026 | 300 | 300
ADIDAS | 0903166456-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 704 | 2026-07-10 | 704 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903166456 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 704 |  | 704 |  |  | 26/09/2026 | 28/09/2026 |  |  | 704 |  | 704
ADIDAS | 0903166626-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 123 | 16/10/2026 | 123 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903166626 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-04-11 | W SL WV TT BLACK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 123 |  | 123 |  |  | 31/10/2026 | 31/10/2026 |  |  | 123 |  | 123
ADIDAS | 0903166659-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 319 | 30/09/2026 | 319 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 830009 | PRINT L1 SUB PROCESS_V3 | 0903166659 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-10 | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX | 2026-09-10 | 2026-09-10 |  |  | 319 |  | 319 |  |  | 2026-06-10 | 2026-06-10 |  |  | 319 |  | 319
ADIDAS | 0903167086-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 523 | 15/10/2026 | 523 | AN | AN26/06/2026 | G3F | PANTS | G3 | (28/08/2026) | ok | 516199 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167086 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 14/10/2026 | 15/10/2026 |  |  | 523 |  | 523 |  |  | 2026-10-10 | 2026-12-10 |  |  | 523 |  | 523 |  |  | 2026-05-10 | 2026-06-10 |  |  | 523 |  | 523
ADIDAS | 0903167126-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 1460 | 15/10/2026 | 1460 | AN | AN26/06/2026 | G3G | PANTS | G3 | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903167126 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 14/10/2026 | 16/10/2026 |  |  | 1460 |  | 1460 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1460 |  | 1460 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1460 |  | 1460
ADIDAS | 0903167166-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 271 | 15/10/2026 | 271 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167166 KU8797 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-06-10 |  |  | 271 |  | 271 |  |  | 2026-01-10 | 2026-02-10 |  |  | 271 |  | 271
ADIDAS | 0903167173-1 LF0727 | BLACK | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167173 LF0727 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-11 | M SL WV TT BLACK |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 2026-02-11 |  |  | 127 |  | 127
ADIDAS | 0903167198-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 116 | 15/10/2026 | 116 | AN | AN26/06/2026 | G3B | PANTS | G3 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167198 LF0718 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-10 | M SL WV OH PT BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 116 |  | 116 |  |  | 2026-02-10 | 2026-05-10 |  |  | 116 |  | 116
ADIDAS | 0903167227-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 410 | 2026-07-10 | 410 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903167227 KT7396 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 410 |  | 410 |  |  | 30/09/2026 | 2026-01-10 | 17/09/2026 | 19/09/2026 | 410 | 406 | 4 |  | 26
ADIDAS | 0903167251-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 31/10/2026 | 311 | SI | SI26/06/2026 | G2L | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167251 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | LV COLLEGIATE T |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 311 |  | 311 |  |  | 14/10/2026 | 15/10/2026 |  |  | 311 |  | 311
ADIDAS | 0903167268-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 415 | 30/09/2026 | 415 | SI | SI26/06/2026 | G2B | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167268 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | LV COLLEGIATE T |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 415 |  | 415 |  |  | 18/09/2026 | 19/09/2026 | 2026-10-09 | 2026-10-09 | 415 | 394 | 21
ADIDAS | 0903167275-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 267 | 2026-07-10 | 267 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167275 KW8935 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 267 |  | 267 |  |  | 29/09/2026 | 29/09/2026 |  |  | 267 |  | 267
ADIDAS | 0903167316-1 KY5866 | BLACK | 90D | S2750MTR052 | 139 | 15/10/2026 | 139 | SI | SI26/06/2026 | G2C | SHORTS | G2 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903167316 KY5866 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | D18T ESS SHORTS BLACK |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 139 |  | 139 |  |  | 25/09/2026 | 26/09/2026 |  |  | 139 |  | 139 |  |  | 24/09/2026 | 25/09/2026 |  |  | 139 |  | 139
ADIDAS | 0903167324-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 255 | 15/10/2026 | 255 | SI | SI26/06/2026 | G3B | SHORTS | G3 | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903167324 KD0738 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI | 17/10/2026 | 19/10/2026 |  |  | 255 |  | 255 |  |  | 14/10/2026 | 15/10/2026 |  |  | 255 |  | 255 |  |  | 2026-08-10 | 2026-09-10 |  |  | 255 |  | 255
ADIDAS | 0903167339-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 673 | 2026-07-10 | 673 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903167339 KU8797 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 673 |  | 673 |  |  | 29/09/2026 | 30/09/2026 |  |  | 673 |  | 673
ADIDAS | 0903167370-1 KW8935 | AURORA COFFEE S26/BLACK | 90D | S2754MESS676SJ | 210 | 15/10/2026 | 210 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903167370 KW8935 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-06-10 | M 39B SJ LF T AURORA COFFEE S26/BLACK |  | SS27-STX | 2026-06-10 | 2026-06-10 |  |  | 210 |  | 210 |  |  | 2026-02-10 | 2026-02-10 |  |  | 210 |  | 210
ADIDAS | 0903167433-1 KW8934 | WARM CLAY S25/BLACK | 90D | S2754MESS676SJ | 501 | 2026-07-10 | 501 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167433 KW8934 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-01-10 | M 30B SJ LF T WARM CLAY S25/BLACK |  | SS27-STX | 2026-01-10 | 2026-02-10 |  |  | 501 |  | 501 |  |  | 28/09/2026 | 29/09/2026 |  |  | 501 |  | 501
ADIDAS | 0903167439-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1157 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903167439 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167457-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 405 | 2026-07-10 | 405 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167457 KW8932 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-02-10 | 2026-02-10 |  |  | 405 |  | 405 |  |  | 29/09/2026 | 29/09/2026 |  |  | 405 |  | 405
ADIDAS | 0903167485-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 130 | 2026-07-10 | 130 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167485 KW9039 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 19/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 19/10/2026 | 20/10/2026 |  |  | 130 |  | 130 |  |  | 15/10/2026 | 16/10/2026 |  |  | 130 |  | 130
ADIDAS | 0903167519-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 733 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167519 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167551-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 700 | 31/10/2026 |  | AN | AN26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 04-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167551 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903167564-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 652 | 15/10/2026 | 652 | AN | AN26/06/2026 | G1D | SHORTS | G1 | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167564 KV8149 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX | 30/09/2026 | 2026-02-10 |  |  | 652 |  | 652 |  |  | 26/09/2026 | 29/09/2026 |  |  | 652 |  | 652 |  |  | 25/09/2026 | 28/09/2026 |  |  | 652 |  | 652
ADIDAS | 0903167589-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 554 | 15/10/2026 | 554 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903167589 KY3734 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 554 |  | 554 |  |  | 29/09/2026 | 30/09/2026 |  |  | 554 |  | 554
ADIDAS | 0903167609-1 LF0727 | BLACK | 120D | S2754MAS510B | 718 | 31/10/2026 | 718 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167609 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-11 | M SL WV TT BLACK |  | SS27 | 2026-05-11 | 2026-10-11 |  |  | 718 |  | 718 |  |  | 2026-02-11 | 2026-05-11 |  |  | 718 |  | 718
ADIDAS | 0903167625-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 494 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 11-Aug, actual receives 31-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 03-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167625 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167678-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516403 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167678 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 300 |  | 300 |  |  | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903167694-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 362 | 15/10/2026 | 362 | SI | SI26/06/2026 | G3I | PANTS | G3 | (28/08/2026) | ok | T2 Kahatex, PI Date 28-Aug, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 04-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167694 LE8188 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 362 |  | 362 |  |  | 25/09/2026 | 26/09/2026 |  |  | 362 |  | 362
ADIDAS | 0903167696-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/09/2026 | 500 | SI | SI26/06/2026 | G3G | PANTS | G3 | ok | ok | 28/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167696 KV7863 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 18/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 500 | 117 | 383 |  |  | 15/09/2026 | 17/09/2026 | 2026-12-09 | 19/09/2026 | 500 | 500 |  |  | 378
ADIDAS | 0903167722-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 754 | 15/10/2026 | 754 | ID | ID26/06/2026 | G1R | T-SHIRT | G1 | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903167722 KV8142 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 13/10/2026 | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX | 13/10/2026 | 14/10/2026 |  |  | 754 |  | 754 |  |  | 2026-09-10 | 2026-10-10 |  |  | 754 |  | 754 |  |  | 2026-08-10 | 2026-09-10 |  |  | 754 |  | 754
ADIDAS | 0903167723-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 517 | 15/10/2026 | 517 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 27-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167723 LE8188 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M SL WV TP PT LEGEND IVY S19 |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 517 |  | 517 |  |  | 26/09/2026 | 28/09/2026 |  |  | 517 |  | 517
ADIDAS | 0903167736-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 356 | 2026-07-10 | 356 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877)., ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903167736 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 356 |  | 356 |  |  | 28/09/2026 | 29/09/2026 |  |  | 356 |  | 356
ADIDAS | 0903167751-1 KW5050 | MAROON | 90D | F2625M101 | 2163 | 15/09/2026 | 2163 | AN | AN26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 15/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO SUB PROCESS_V1 | 0903167751 KW5050 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-12-09 | ESS REG |  | SS27-STX | 2026-12-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 2163 | 2163 |  |  |  | 2026-09-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 2163 | 2163
ADIDAS | 0903167760-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 127 | 31/10/2026 | 127 | SI | SI26/06/2026 | G1I | JACKET | G1 | ok | ok | T2 Teijin Nantong, PI Date 18-Aug, actual receives 22-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167760 LF0729 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-11 | M SL WV TT OLIVE ONE S27 |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 127 |  | 127 |  |  | 29/10/2026 | 31/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903167776-1 KA4331 | BLACK | 90D | S2608MR0902 | 1200 | 30/09/2026 | 1200 | SA | SA26/06/2026 | G1D | SHORTS | G1 | ok |  | 29/09: ex-fty. T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 25-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 1st Art (TC 10 pcs) 516267 | PAD+HT SUB PROCESS_V3 | 0903167776 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/09/2026 | 28/09/2026 |  |  | 1200 |  | 1200 |  |  | 22/09/2026 | 24/09/2026 |  |  | 1200 |  | 1200 |  |  | 21/09/2026 | 23/09/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903167792-1 KA4331 | BLACK | 90D | S2608MR0902 | 335 | 2026-07-10 | 335 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516400 | PAD+HT SUB PROCESS_V3 | 0903167792 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-02-10 | 2026-03-10 |  |  | 335 |  | 335 |  |  | 29/09/2026 | 30/09/2026 |  |  | 335 |  | 335 |  |  | 28/09/2026 | 29/09/2026 |  |  | 335 |  | 335
ADIDAS | 0903167804-1 KW5050 | MAROON | 90D | F2625M101 | 334 | 15/10/2026 | 334 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903167804 KW5050 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 13/10/2026 | ESS REG |  | SS27-STX | 13/10/2026 | 13/10/2026 |  |  | 334 |  | 334 |  |  | 2026-09-10 | 2026-09-10 |  |  | 334 |  | 334
ADIDAS | 0903167827-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 504 | 31/10/2026 | 504 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167827 LG9665 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-11 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 504 |  | 504 |  |  | 30/10/2026 | 2026-02-11 |  |  | 504 |  | 504
ADIDAS | 0903167883-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 262 | 15/10/2026 | 262 | SA | SA26/06/2026 | G1C | JACKET | G1 | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD 22-Aug, ETA-Kaha 10-Sep. T2 Libolon, PI Date 06-Aug, actual receives 26-Aug. T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167883 LD6542 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 262 |  | 262 |  |  | 16/10/2026 | 17/10/2026 |  |  | 262 |  | 262
ADIDAS | 0903167908-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 627 | 15/10/2026 | 627 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167908 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-11 | W SL WV TT BLACK |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 627 |  | 627 |  |  | 29/10/2026 | 31/10/2026 |  |  | 627 |  | 627
ADIDAS | 0903167943-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 555 | 15/10/2026 | 555 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 516333 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167943 KX7715 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 13/10/2026 | 16/10/2026 |  |  | 555 |  | 555 |  |  | 2026-09-10 | 13/10/2026 |  |  | 555 |  | 555
ADIDAS | 0903167963-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 332 | 31/10/2026 | 332 | SA | SA26/06/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 18-Aug, actual receives 31-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167963 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | W SL WV TT KHAKI THREE F26 |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 332 |  | 332 |  |  | 30/10/2026 | 2026-02-11 |  |  | 332 |  | 332
ADIDAS | 0903168065-1 KB5960 | WHITE | 120D | S2608MR0900A | 304 | 31/10/2026 | 304 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0903168065 KB5960 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | Run Ess Tee M |  | SS27-TI | 26/10/2026 | 26/10/2026 |  |  | 304 |  | 304 |  |  | 22/10/2026 | 22/10/2026 |  |  | 304 |  | 304 |  |  | 20/10/2026 | 20/10/2026 |  |  | 304 |  | 304
ADIDAS | 0903168109-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 26/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168109 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 400 | 400 |  |  |  | 2026-05-09 | 2026-10-09 | 2026-11-08 | 15/09/2026 | 400 | 387 | 13
ADIDAS | 0903168155-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 209 | 23/10/2026 | 209 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168155 KT7396 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-10-10 | 2026-12-10 |  |  | 209 |  | 209 |  |  | 2026-07-10 | 2026-08-10 |  |  | 209 |  | 209
ADIDAS | 0903168201-1 KW5050 | MAROON | 90D | F2625M101 | 339 | 23/10/2026 | 339 | AN | AN26/06/2026 | G2E | T-SHIRT | G2 | ok | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903168201 KW5050 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-08-10 | ESS REG |  | SS27-STX | 2026-08-10 | 2026-09-10 |  |  | 339 |  | 339 |  |  | 2026-05-10 | 2026-06-10 |  |  | 339 |  | 339
ADIDAS | 0903168275-1 KA0246 | BLACK | 90D | S2608WR0902 | 339 | 2026-07-10 | 339 | SI | SI26/06/2026 | G2L | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903168275 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/09/2026 | 2026-01-10 |  |  | 339 |  | 339 |  |  | 26/09/2026 | 28/09/2026 |  |  | 339 |  | 339 |  |  | 23/09/2026 | 24/09/2026 |  |  | 339 |  | 339
ADIDAS | 0903168299-1 KA0246 | BLACK | 90D | S2608WR0902 | 608 | 15/10/2026 | 608 | SI | SI26/06/2026 | G1B | SHORTS | G1 | ok |  | 29/09: ex-fty. DRC 0051-T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 27-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903168299 KA0246 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 608 |  | 608 |  |  | 2026-07-10 | 2026-08-10 |  |  | 608 |  | 608 |  |  | 2026-03-10 | 2026-05-10 |  |  | 608 |  | 608
ADIDAS | 0903168302-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 300 | 30/09/2026 | 300 | SI | SI26/06/2026 | G1L | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168302 KV8005 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 300 |  | 300 |  |  | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903168327-1 KA0246 | BLACK | 90D | S2608WR0902 | 301 | 30/09/2026 | 301 | SI | SI26/06/2026 | G1B | SHORTS | G1 | ok |  | 25/09: ex-fty. T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 27-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903168327 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 26/09/2026 | 28/09/2026 |  |  | 301 |  | 301 |  |  | 23/09/2026 | 24/09/2026 |  |  | 301 |  | 301 |  |  | 19/09/2026 | 21/09/2026 |  |  | 301 |  | 301
ADIDAS | 0903168356-1 KA0246 | BLACK | 90D | S2608WR0902 | 314 | 2026-07-10 | 314 | SI | SI26/06/2026 | G2L | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903168356 KA0246 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-03-10 |  |  | 314 |  | 314 |  |  | 28/09/2026 | 30/09/2026 |  |  | 314 |  | 314 |  |  | 24/09/2026 | 26/09/2026 |  |  | 314 |  | 314
ADIDAS | 0903168388-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 186 | 30/09/2026 | 186 | AN | AN26/06/2026 | G1H | JACKET | G1 | ok | ok | 24/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903168388 KZ3205 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 15/09/2026 | 23/09/2026 | 15/09/2026 | 17/09/2026 | 186 | 165 | 21 |  |  | 2026-11-09 | 19/09/2026 | 27/08/2026 | 2026-07-09 | 186 | 168 | 18
ADIDAS | 0903168468-1 KA4331 | BLACK | 90D | S2608MR0902 | 364 | 2026-07-10 | 364 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903168468 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-03-10 | 2026-05-10 |  |  | 364 |  | 364 |  |  | 30/09/2026 | 2026-01-10 |  |  | 364 |  | 364 |  |  | 29/09/2026 | 30/09/2026 |  |  | 364 |  | 364
ADIDAS | 0903168653-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 190 | 31/10/2026 | 190 | AN | AN26/06/2026 | G1J | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 03-Sep. T2 Teijin Nantong, PI Date 03-Aug, actual receives 31-Aug. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903168653 LG9666 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W SL WV TT BLACK |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 190 |  | 190 |  |  | 2026-10-11 | 2026-11-11 |  |  | 190 |  | 190
ADIDAS | 0903169170-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 204 | 15/10/2026 | 204 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516443 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169170 KU8975 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 15/10/2026 | 19/10/2026 |  |  | 204 |  | 204 |  |  | 2026-12-10 | 15/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903169256-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 701 | 15/10/2026 | 701 | SI | SI26/06/2026 | G3K | JACKET | G3 | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169256 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS | 15/10/2026 | 19/10/2026 |  |  | 701 |  | 701 |  |  | 2026-12-10 | 15/10/2026 |  |  | 701 |  | 701
ADIDAS | 0903169653-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 438 | 31/10/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903169653 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903169715-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 328 | 15/10/2026 | 328 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169715 KU8797 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 328 |  | 328 |  |  | 2026-01-10 | 2026-01-10 |  |  | 328 |  | 328
ADIDAS | 0903169772-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 300 | 15/10/2026 | 300 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169772 KY3734 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-10 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300 |  |  | 29/09/2026 | 30/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903169855-1 KW9039 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS659PQ | 150 | 15/10/2026 | 150 | SI | SI26/06/2026 | G1N | POLO SHIRT | G1 | (12/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903169855 KW9039 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 20/10/2026 | M 3B PQ PS MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 20/10/2026 | 21/10/2026 |  |  | 150 |  | 150 |  |  | 16/10/2026 | 17/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903169976-1 KU8797 | BLACK/WHITE | 90D | S2754MESS676SJ | 259 | 15/10/2026 | 259 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | ok | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903169976 KU8797 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-05-10 | M 3B SJ LF T BLACK/WHITE |  | SS27-STX | 2026-05-10 | 2026-05-10 |  |  | 259 |  | 259 |  |  | 2026-01-10 | 2026-01-10 |  |  | 259 |  | 259
ADIDAS | 0903170085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 538 | 15/09/2026 | 538 | AN | AN26/06/2026 | G3A | SHORTS | G3 | ok | (07/08/2026) | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 14-Jul. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 20-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170085 LD5446 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV SHO KHAKI THREE F26 |  | SS27 | 2026-05-09 | 2026-11-09 | 2026-09-09 | 14/09/2026 | 538 | 538 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-05-09 | 16/09/2026 | 538 | 538
ADIDAS | 0903170105-1 LE5609 | CARBON S18/SEMI SOLAR AQUA S27 | 105D | S2650MTR436 | 1240 | 15/09/2026 | 1240 | SA | SA26/06/2026 | G3E,G3K | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903170105 LE5609 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-11-09 | WE ALLSET 122S PT CARBON S18/SEMI SOLAR AQUA S27 |  | SS27-TI | 2026-11-09 | 15/09/2026 | 2026-11-09 | 15/09/2026 | 1240 | 1240 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 1240 | 1240 |  |  |  | 2026-02-09 | 2026-05-09 | 2026-09-09 | 14/09/2026 | 1240 | 1240
ADIDAS | 0903170139-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 574 | 15/09/2026 | 574 | AN | AN26/06/2026 | G3A | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903170139 LE8181 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-09 | M SL WV OH PT LEGEND IVY S19 |  | SS27 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 574 | 574 |  |  |  | 2026-05-09 | 2026-08-09 | 2026-07-09 | 2026-11-09 | 574 | 574
ADIDAS | 0903170160-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 400 | 26/09/2026 | 400 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 25/09: ex-fty. T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170160 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-09 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-09-09 | 16/09/2026 | 2026-11-09 | 15/09/2026 | 400 | 400 |  |  |  | 2026-05-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 400 | 395 | 5
ADIDAS | 0903170187-1 KB5965 | BLACK | 120D | S2608MR0900A | 509 | 31/10/2026 | 509 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170187 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | Run Ess Tee M |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 509 |  | 509 |  |  | 16/10/2026 | 17/10/2026 |  |  | 509 |  | 509 |  |  | 14/10/2026 | 15/10/2026 | 2026-11-09 | 2026-11-09 | 509 |  | 509
ADIDAS | 0903170289-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 23/09/2026 | 300 | AN | AN26/06/2026 | G3J | SHORTS | G3 | ok | ok | 21/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903170289 KV7963 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 15/09/2026 | 16/09/2026 | 300 | 300 |  |  |  | 2026-12-09 | 17/09/2026 | 14/09/2026 | 14/09/2026 | 300 | 299 | 1
ADIDAS | 0903170312-1 KB5960 | WHITE | 120D | S2608MR0900A | 164 | 31/10/2026 | 164 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903170312 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 164 |  | 164 |  |  | 21/10/2026 | 22/10/2026 |  |  | 164 |  | 164 |  |  | 19/10/2026 | 20/10/2026 |  |  | 164 |  | 164
ADIDAS | 0903170946-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 260 | 15/10/2026 | 260 | SI | SI26/06/2026 | G2J | T-SHIRT | G2 | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903170946 KD5507 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-10 | WE FR T GREY FIVE F17 |  | SS27-TI | 2026-02-10 | 2026-02-10 |  |  | 260 |  | 260 |  |  | 29/09/2026 | 29/09/2026 |  |  | 260 |  | 260 |  |  | 28/09/2026 | 28/09/2026 |  |  | 260 |  | 260
ADIDAS | 0903170968-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 160 | 23/10/2026 | 160 | SA | SA26/06/2026 | G2C | T-SHIRT | G2 | ok | ok | 830009 | PRINT L1 SUB PROCESS_V3 | 0903170968 LC7301 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX | 30/09/2026 | 30/09/2026 |  |  | 160 |  | 160 |  |  | 26/09/2026 | 26/09/2026 |  |  | 160 |  | 160
ADIDAS | 0903170993-1 KY3734 | WHITE/BLACK | 90D | S2754MESS676SJ | 327 | 2026-07-10 | 327 | SI | SI26/06/2026 | G2R | T-SHIRT | G2 | ok | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903170993 KY3734 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 30/09/2026 | M 57B SJ LF T WHITE/BLACK |  | SS27-STX | 30/09/2026 | 2026-01-10 |  |  | 327 |  | 327 |  |  | 26/09/2026 | 28/09/2026 |  |  | 327 |  | 327
ADIDAS | 0903171021-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 500 | 15/10/2026 | 500 | AN | AN26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903171021 KT7396 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA | 2026-03-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 500 |  | 500 |  |  | 30/09/2026 | 2026-01-10 |  |  | 500 |  | 500
ADIDAS | 0903172164-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 1591 | 15/09/2026 | 1591 | AN | AN26/06/2026 | G3B,G3J | PANTS | G3 | ok | ok | 15/09: ex-fty (STOOD). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 28-Aug, actual receives 13-Aug. T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 13-Aug. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903172164 LE8187 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-09 | M SL WV TP PT BLACK |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-08-09 | 14/09/2026 | 1591 | 1591 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-03-09 | 18/09/2026 | 1591 | 1588 | 3
ADIDAS | 0903173197-1 KW8932 | MEDIUM GREY HEATHER/WHITE | 90D | S2754MESS676SJ | 1686 | 30/09/2026 | 1686 | SI | SI26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 29/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903173197 KW8932 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-10 | M 12B SJ LF T MEDIUM GREY HEATHER/WHITE |  | SS27-STX | 2026-03-10 | 2026-05-10 |  |  | 1686 |  | 1686 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1686 |  | 1686
ADIDAS | 0903173246-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1225 | 30/09/2026 | 1225 | SI | SI26/06/2026 | G2S | PANTS | G2 | ok | ok | 22/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173246 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 21/09/2026 | 24/09/2026 |  |  | 1225 |  | 1225 |  |  | 17/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 1225 | 1220 | 5
ADIDAS | 0903173302-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 410 | 30/09/2026 | 410 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 29/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516461 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173302 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 17/09/2026 | 19/09/2026 | 410 | 390 | 20 |  | 8 | 2026-12-09 | 17/09/2026 | 2026-12-09 | 14/09/2026 | 410 | 400 | 10
ADIDAS | 0903173331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2400 | 2026-07-10 | 2400 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 24-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173331 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 2400 |  | 2400 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2400 |  | 2400
ADIDAS | 0903173353-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1500 | 30/09/2026 | 1500 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul. 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173353 KV7863 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 15/09/2026 | 19/09/2026 | 1500 | 1308 | 192 |  | 16 | 2026-12-09 | 17/09/2026 | 2026-11-09 | 15/09/2026 | 1500 | 1470 | 30
ADIDAS | 0903173426-1 LG9669 | BLACK | 120D | S2754WAS514C | 276 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903173426 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903173473-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173473 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 21/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903173490-1 LG9669 | BLACK | 120D | S2754WAS514C | 161 | 31/10/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | ok | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903173490 LG9669 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903173515-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-10 | 300 | SI | SI26/06/2026 | G3I | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 27-Aug. T2 Libolon, PI Date 22-Jul, actual receives 10-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. 516244 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173515 KZ3199 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 24/09/2026 | 25/09/2026 |  |  | 300 |  | 300 |  |  | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903173545-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 800 | 30/09/2026 | 800 | AN | AN26/06/2026 | G3G | PANTS | G3 | ok | ok | 25/09: ex-fty. T2 Kahatex, PI Date 29-Jul, actual receives 31-Jul. T2 Libolon, PI Date 29-Jun, actual receives 14-Jul (PO 26024706). T2 Formosa, actual receives 04-Jul (PO 26021877). 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173545 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/09/2026 | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27 | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 800 | 706 | 94 |  | 362 | 15/09/2026 | 17/09/2026 | 14/09/2026 | 15/09/2026 | 800 | 797 | 3
ADIDAS | 0903173563-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 2026-12-09 | 300 | SI | SI26/06/2026 | G3F | PANTS | G3 | ok | ok | 10/09: ex-fty. DRC 0090-early shipment customer (BTP_29_07_2026 EARLY HOLD SHIPMENT). T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 20-Jul. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 516400 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903173563 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-03-09 | 2026-07-09 | 2026-03-09 | 2026-07-09 | 300 | 300 |  |  |  | 31/08/2026 | 2026-03-09 | 31/08/2026 | 2026-02-09 | 300 | 300
ADIDAS | 0903174134-1 KA4331 | BLACK | 90D | S2608MR0902 | 303 | 30/09/2026 | 303 | SA | SA26/06/2026 | G1D | SHORTS | G1 | ok |  | 25/09: ex-fty. T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 25-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903174134 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 303 |  | 303 |  |  | 21/09/2026 | 22/09/2026 |  |  | 303 |  | 303 |  |  | 19/09/2026 | 21/09/2026 |  |  | 303 |  | 303
ADIDAS | 0903174404-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 400 | 31/10/2026 | 400 | AN | AN26/06/2026 | G2P | SHORTS | G2 |  |  | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 21-Jul, ETD ?? T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903174404 LG9660 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 27/10/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 400 |  | 400 |  |  | 23/10/2026 | 24/10/2026 |  |  | 400 |  | 400
ADIDAS | 0903176681-1 KA4331 | BLACK | 90D | S2608MR0902 | 371 | 2026-07-10 | 371 | SA | SA26/06/2026 | G1C | SHORTS | G1 | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516394 | PAD+HT SUB PROCESS_V3 | 0903176681 KA4331 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-03-10 | 2026-05-10 |  |  | 371 |  | 371 |  |  | 30/09/2026 | 2026-01-10 |  |  | 371 |  | 371 |  |  | 29/09/2026 | 30/09/2026 |  |  | 371 |  | 371
ADIDAS | 0903176702-1 KA4331 | BLACK | 90D | S2608MR0902 | 700 | 30/09/2026 | 700 | SA | SA26/06/2026 | G1D | SHORTS | G1 | ok |  | 25/09: ex-fty. T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 25-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516443 | PAD+HT SUB PROCESS_V3 | 0903176702 KA4331 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/09/2026 | 25/09/2026 |  |  | 700 |  | 700 |  |  | 21/09/2026 | 22/09/2026 |  |  | 700 |  | 700 |  |  | 19/09/2026 | 21/09/2026 |  |  | 700 |  | 700
ADIDAS | 0903176748-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 309 | 15/10/2026 | 309 | AN | AN26/06/2026 | G3E | PANTS | G3 | ok | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176748 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-08-10 | 2026-08-10 |  |  | 309 |  | 309 |  |  | 2026-05-10 | 2026-05-10 |  |  | 309 |  | 309 |  |  | 29/09/2026 | 29/09/2026 |  |  | 309 |  | 309
ADIDAS | 0903176770-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 2305 | 15/10/2026 | 2305 | SA | SA26/06/2026 | G3G | PANTS | G3 | ok | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176770 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 16/10/2026 | 20/10/2026 |  |  | 2305 |  | 2305 |  |  | 13/10/2026 | 16/10/2026 |  |  | 2305 |  | 2305 |  |  | 2026-07-10 | 2026-10-10 |  |  | 2305 |  | 2305
ADIDAS | 0903176795-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 459 | 15/10/2026 | 459 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176795 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-06-10 | 2026-08-10 |  |  | 459 |  | 459 |  |  | 2026-02-10 | 2026-05-10 |  |  | 459 |  | 459 |  |  | 26/09/2026 | 29/09/2026 |  |  | 459 |  | 459
ADIDAS | 0903176816-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 314 | 23/10/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 516443 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903176816 KC8152 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903176840-1 IN1159 | BLACK | 90D | S2408MR1601 | 223 | 2026-07-10 | 223 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903176840 IN1159 | 2026-10-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 223 |  | 223 |  |  | 2026-01-10 | 2026-03-10 |  |  | 223 |  | 223 |  |  | 28/09/2026 | 30/09/2026 |  |  | 223 |  | 223
ADIDAS | 0903176865-1 KA0246 | BLACK | 90D | S2608WR0902 | 450 | 2026-07-10 | 450 | SI | SI26/06/2026 | G2L | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 New Wide, PI Date 13-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. 516244 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903176865 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-01-10 | 2026-03-10 |  |  | 450 |  | 450 |  |  | 28/09/2026 | 30/09/2026 |  |  | 450 |  | 450 |  |  | 24/09/2026 | 26/09/2026 |  |  | 450 |  | 450
ADIDAS | 0903194096-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 249 | 31/10/2026 | 249 | SA | SA30/06/2026 | G1O | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194096 LC6790 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 249 |  | 249 |  |  | 2026-11-11 | 2026-12-11 |  |  | 249 |  | 249 |  |  | 2026-06-11 | 2026-09-11 |  |  | 249 |  | 249
ADIDAS | 0903194098-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 317 | 31/10/2026 | 317 | SA | SA30/06/2026 | G1O | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194098 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 14/11/2026 | 17/11/2026 |  |  | 317 |  | 317 |  |  | 2026-11-11 | 2026-12-11 |  |  | 317 |  | 317 |  |  | 2026-06-11 | 2026-09-11 |  |  | 317 |  | 317
ADIDAS | 0903194100-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 | 300 | SI | SI30/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194100 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-11-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-11-11 | 2026-12-11 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-09-11 |  |  | 300 |  | 300 |  |  | 2026-03-11 | 2026-04-11 |  |  | 300 |  | 300
ADIDAS | 0903194104-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 314 | 31/10/2026 | 314 | SI | SI30/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194104 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-06-11 | 2026-07-11 |  |  | 314 |  | 314 |  |  | 2026-03-11 | 2026-04-11 |  |  | 314 |  | 314 |  |  | 30/10/2026 | 31/10/2026 |  |  | 314 |  | 314
ADIDAS | 0903194107-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1210 | 31/10/2026 | 1210 | SI | SI30/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194107 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 16/11/2026 | 18/11/2026 |  |  | 1210 |  | 1210 |  |  | 2026-11-11 | 13/11/2026 |  |  | 1210 |  | 1210 |  |  | 2026-06-11 | 2026-10-11 |  |  | 1210 |  | 1210
ADIDAS | 0903194109-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 31/10/2026 | 302 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194109 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 302 |  | 302 |  |  | 31/10/2026 | 2026-03-11 |  |  | 302 |  | 302 |  |  | 28/10/2026 | 30/10/2026 |  |  | 302 |  | 302
ADIDAS | 0903194115-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 900 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194115 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194119-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1516 | 31/10/2026 | 1516 | SI | SI30/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194119 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 2026-03-11 | 2026-06-11 |  |  | 1516 |  | 1516 |  |  | 30/10/2026 | 2026-03-11 |  |  | 1516 |  | 1516 |  |  | 27/10/2026 | 30/10/2026 |  |  | 1516 |  | 1516
ADIDAS | 0903194120-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 399 | 31/10/2026 | 399 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516277 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194120 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 399 |  | 399 |  |  | 31/10/2026 | 2026-03-11 |  |  | 399 |  | 399 |  |  | 28/10/2026 | 30/10/2026 |  |  | 399 |  | 399
ADIDAS | 0903194122-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 660 | 31/10/2026 | 660 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194122 LF9775 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-02-11 | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 660 |  | 660 |  |  | 29/10/2026 | 30/10/2026 |  |  | 660 |  | 660 |  |  | 26/10/2026 | 27/10/2026 |  |  | 660 |  | 660
ADIDAS | 0903194123-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1198 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194123 KY9391 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194130-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 107 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194130 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194137-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1214 | 31/10/2026 | 1214 | SI | SI30/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194137 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/11/2026 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 1214 |  | 1214 |  |  | 13/11/2026 | 17/11/2026 |  |  | 1214 |  | 1214 |  |  | 2026-10-11 | 2026-12-11 |  |  | 1214 |  | 1214
ADIDAS | 0903194145-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 133 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194145 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194293-1 IN1156 | BLACK | 90D | S2408MR1600 | 532 | 31/10/2026 | 532 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194293 IN1156 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-07-11 | ADIZERO E TEE |  | SS27-YTI | 2026-07-11 | 2026-09-11 |  |  | 532 |  | 532 |  |  | 2026-05-11 | 2026-05-11 |  |  | 532 |  | 532 |  |  | 2026-04-11 | 2026-04-11 |  |  | 532 |  | 532
ADIDAS | 0903194295-1 IN1157 | WHITE | 90D | S2408MR1600 | 328 | 31/10/2026 | 328 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194295 IN1157 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 14/11/2026 | ADIZERO E TEE |  | SS27-YTI | 14/11/2026 | 16/11/2026 |  |  | 328 |  | 328 |  |  | 2026-12-11 | 2026-12-11 |  |  | 328 |  | 328 |  |  | 2026-11-11 | 2026-11-11 |  |  | 328 |  | 328
ADIDAS | 0903194296-1 IN1172 | BLACK | 90D | S2408WR1600 | 645 | 31/10/2026 | 645 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194296 IN1172 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-12-11 | ADIZERO E TEE |  | SS27-YTI | 2026-12-11 | 13/11/2026 |  |  | 645 |  | 645 |  |  | 2026-10-11 | 2026-11-11 |  |  | 645 |  | 645 |  |  | 2026-09-11 | 2026-10-11 |  |  | 645 |  | 645
ADIDAS | 0903194298-1 IN1173 | WHITE | 90D | S2408WR1600 | 356 | 31/10/2026 | 356 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194298 IN1173 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 356 |  | 356 |  |  | 21/10/2026 | 22/10/2026 |  |  | 356 |  | 356 |  |  | 20/10/2026 | 21/10/2026 |  |  | 356 |  | 356
ADIDAS | 0903194299-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 116 | 31/10/2026 | 116 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903194299 IT1828 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 21/11/2026 | ADIZERO E TEE |  | SS27-YTI | 21/11/2026 | 23/11/2026 |  |  | 116 |  | 116 |  |  | 19/11/2026 | 19/11/2026 |  |  | 116 |  | 116 |  |  | 18/11/2026 | 18/11/2026 |  |  | 116 |  | 116
ADIDAS | 0903194300-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 31/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194300 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 14/11/2026 | ADIZERO E TEE |  | SS27-YTI | 14/11/2026 | 16/11/2026 |  |  | 120 |  | 120 |  |  | 2026-12-11 | 2026-12-11 |  |  | 120 |  | 120 |  |  | 2026-11-11 | 2026-11-11 |  |  | 120 |  | 120
ADIDAS | 0903194302-1 IN1173 | WHITE | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194302 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194303-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 31/10/2026 | 324 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903194303 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-07-11 | ADIZERO E TEE |  | SS27-YTI | 2026-07-11 | 2026-09-11 |  |  | 324 |  | 324 |  |  | 2026-05-11 | 2026-05-11 |  |  | 324 |  | 324 |  |  | 2026-04-11 | 2026-04-11 |  |  | 324 |  | 324
ADIDAS | 0903194305-1 IN1156 | BLACK | 90D | S2408MR1600 | 180 | 15/10/2026 | 180 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194305 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 180 |  | 180 |  |  | 2026-05-10 | 2026-06-10 | 2026-09-09 | 17/09/2026 | 180 | 20 | 160 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 17/09/2026 | 180 | 180
ADIDAS | 0903194307-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/10/2026 | 120 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194307 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 17/10/2026 | 19/10/2026 | 2026-09-09 | 17/09/2026 | 120 | 120 |  |  |  | 16/10/2026 | 17/10/2026 | 2026-03-09 | 17/09/2026 | 120 | 120
ADIDAS | 0903194308-1 IN1172 | BLACK | 90D | S2408WR1600 | 120 | 15/10/2026 | 120 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194308 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 120 |  | 120 |  |  | 14/10/2026 | 15/10/2026 |  |  | 120 |  | 120 |  |  | 13/10/2026 | 14/10/2026 | 2026-05-09 | 19/09/2026 | 120 | 120 |  |  | 3
ADIDAS | 0903194309-1 IN1156 | BLACK | 90D | S2408MR1600 | 1308 | 15/10/2026 | 1308 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 07-Aug. 659018 | HT SUB PROCESS_V1 | 0903194309 IN1156 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 1308 |  | 1308 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1308 |  | 1308 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1308 |  | 1308
ADIDAS | 0903194311-1 IN1172 | BLACK | 90D | S2408WR1600 | 1174 | 15/10/2026 | 1174 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 659018 | HT SUB PROCESS_V1 | 0903194311 IN1172 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 20/10/2026 |  |  | 1174 |  | 1174 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1174 |  | 1174 |  |  | 14/10/2026 | 16/10/2026 | 2026-03-09 | 19/09/2026 | 1174 | 1164 | 10 |  | 6
ADIDAS | 0903194312-1 IN1157 | WHITE | 90D | S2408MR1600 | 1525 | 15/10/2026 | 1525 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | T2 Y.T.I, Body & mesh actual receives 06-Aug. 659018 | HT SUB PROCESS_V1 | 0903194312 IN1157 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 24/10/2026 |  |  | 1525 |  | 1525 |  |  | 20/10/2026 | 22/10/2026 | 2026-09-09 | 18/09/2026 | 1525 | 1421 | 104 |  |  | 19/10/2026 | 21/10/2026 | 2026-02-09 | 19/09/2026 | 1525 | 1459 | 66 |  | 17
ADIDAS | 0903194314-1 IN1173 | WHITE | 90D | S2408WR1600 | 1776 | 30/09/2026 | 1776 | SI | SI30/06/2026 | G1E | T-SHIRT | G1 | ok | ok | 28/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. 672027 | HT SUB PROCESS_V1 | 0903194314 IN1173 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 28/09/2026 | ADIZERO E TEE |  | SS27-YTI | 28/09/2026 | 29/09/2026 |  |  | 1776 |  | 1776 |  |  | 25/09/2026 | 26/09/2026 | 2026-10-08 | 24/08/2026 | 1776 | 1776 |  |  |  | 24/09/2026 | 25/09/2026 | 2026-08-08 | 24/08/2026 | 1776 | 1776
ADIDAS | 0903194315-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 1508 | 15/10/2026 | 1508 | SA | SA30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194315 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-02-10 | 2026-07-10 |  |  | 1508 |  | 1508 |  |  | 29/09/2026 | 2026-03-10 |  |  | 1508 |  | 1508 |  |  | 25/09/2026 | 30/09/2026 |  |  | 1508 |  | 1508
ADIDAS | 0903194317-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1167 | 15/10/2026 | 1167 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903194317 IT1828 | 14/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 1167 |  | 1167 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1167 |  | 1167 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1167 |  | 1167
ADIDAS | 0903194318-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 443 | 15/10/2026 | 443 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? T2 Formosa, PI Date 05-Aug, actual receives 31-Aug. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194318 KA0248 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 16/10/2026 | 19/10/2026 |  |  | 443 |  | 443 |  |  | 13/10/2026 | 15/10/2026 |  |  | 443 |  | 443 |  |  | 2026-09-10 | 2026-12-10 |  |  | 443 |  | 443
ADIDAS | 0903194321-1 KA4331 | BLACK | 90D | S2608MR0902 | 239 | 15/10/2026 | 239 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 980004 | PAD+HT SUB PROCESS_V3 | 0903194321 KA4331 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-10-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 239 |  | 239 |  |  | 2026-07-10 | 2026-08-10 |  |  | 239 |  | 239 |  |  | 2026-06-10 | 2026-07-10 |  |  | 239 |  | 239
ADIDAS | 0903194323-1 IN8707 | BLACK | 90D | S2408WR1601A | 194 | 15/10/2026 | 194 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194323 IN8707 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 14/10/2026 | 16/10/2026 |  |  | 194 |  | 194 |  |  | 2026-10-10 | 13/10/2026 |  |  | 194 |  | 194 |  |  | 2026-07-10 | 2026-09-10 |  |  | 194 |  | 194
ADIDAS | 0903194325-1 IN1156 | BLACK | 90D | S2408MR1600 | 566 | 15/10/2026 | 566 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903194325 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 566 |  | 566 |  |  | 2026-08-10 | 2026-09-10 |  |  | 566 |  | 566 |  |  | 2026-07-10 | 2026-08-10 |  |  | 566 |  | 566
ADIDAS | 0903194326-1 KA0246 | BLACK | 90D | S2608WR0902 | 377 | 15/10/2026 | 377 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194326 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 377 |  | 377 |  |  | 2026-03-10 | 2026-05-10 |  |  | 377 |  | 377 |  |  | 30/09/2026 | 2026-01-10 |  |  | 377 |  | 377
ADIDAS | 0903194330-1 KA0235 | BLACK | 90D | S2608WR0901 | 348 | 15/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 960026 | PAD+HT SUB PROCESS_V3 | 0903194330 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 348 |  | 348 |  |  | 22/10/2026 | 24/10/2026 |  |  | 348 |  | 348 |  |  | 21/10/2026 | 23/10/2026 |  |  | 348 |  | 348
ADIDAS | 0903194331-1 IN1156 | BLACK | 90D | S2408MR1600 | 231 | 15/10/2026 | 231 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516343 | HT SUB PROCESS_V1 | 0903194331 IN1156 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 231 |  | 231 |  |  | 2026-05-10 | 2026-06-10 | 2026-08-09 | 2026-11-09 | 231 | 198 | 33 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 2026-11-09 | 231 | 198 | 33
ADIDAS | 0903194332-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 23/10/2026 | 100 | SI | SI30/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194332 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 20/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 20/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 13/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903194333-1 IN1172 | BLACK | 90D | S2408WR1600 | 423 | 15/10/2026 | 423 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 516443 | HT SUB PROCESS_V1 | 0903194333 IN1172 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 423 |  | 423 |  |  | 14/10/2026 | 15/10/2026 |  |  | 423 |  | 423 |  |  | 13/10/2026 | 14/10/2026 | 2026-07-09 | 19/09/2026 | 423 | 416 | 7 |  | 2
ADIDAS | 0903194334-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/10/2026 | 200 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903194334 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-12-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 200 |  | 200 |  |  | 2026-09-11 | 2026-10-11 |  |  | 200 |  | 200 |  |  | 2026-06-11 | 2026-09-11 |  |  | 200 |  | 200
ADIDAS | 0903194337-1 IN8707 | BLACK | 90D | S2408WR1601A | 1643 | 23/10/2026 | 1643 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 823016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194337 IN8707 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 20/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 20/10/2026 | 22/10/2026 |  |  | 1643 |  | 1643 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1643 |  | 1643 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1643 |  | 1643
ADIDAS | 0903194338-1 IN1156 | BLACK | 90D | S2408MR1600 | 697 | 23/10/2026 | 697 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194338 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 697 |  | 697 |  |  | 26/10/2026 | 27/10/2026 |  |  | 697 |  | 697 |  |  | 24/10/2026 | 26/10/2026 |  |  | 697 |  | 697
ADIDAS | 0903194339-1 KA0235 | BLACK | 90D | S2608WR0901 | 229 | 23/10/2026 | 229 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903194339 KA0235 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 229 |  | 229 |  |  | 2026-10-11 | 2026-11-11 |  |  | 229 |  | 229 |  |  | 2026-09-11 | 2026-10-11 |  |  | 229 |  | 229
ADIDAS | 0903194340-1 IN1157 | WHITE | 90D | S2408MR1600 | 375 | 15/10/2026 | 375 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | DRC 0010-hold shipment customer (BTP_01_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 06-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903194340 IN1157 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 375 |  | 375 |  |  | 17/10/2026 | 19/10/2026 | 2026-10-09 | 19/09/2026 | 375 | 375 |  |  | 2 | 16/10/2026 | 17/10/2026 | 2026-07-09 | 18/09/2026 | 375 | 375
ADIDAS | 0903194342-1 KA0246 | BLACK | 90D | S2608WR0902 | 106 | 23/10/2026 | 106 | SI | SI30/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194342 KA0246 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 19/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 19/10/2026 | 20/10/2026 |  |  | 106 |  | 106 |  |  | 15/10/2026 | 16/10/2026 |  |  | 106 |  | 106 |  |  | 2026-12-10 | 13/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903194343-1 IN1173 | WHITE | 90D | S2408WR1600 | 613 | 23/10/2026 | 613 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903194343 IN1173 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 23/10/2026 |  |  | 613 |  | 613 |  |  | 20/10/2026 | 21/10/2026 |  |  | 613 |  | 613 |  |  | 19/10/2026 | 20/10/2026 |  |  | 613 |  | 613
ADIDAS | 0903194344-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 568 | 23/10/2026 | 568 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 19-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 804028 | PAD+HT SUB PROCESS_V3 | 0903194344 KA0238 | 14/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-12-11 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 568 |  | 568 |  |  | 2026-09-11 | 2026-10-11 |  |  | 568 |  | 568 |  |  | 2026-06-11 | 2026-09-11 |  |  | 568 |  | 568
ADIDAS | 0903194347-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 112 | 23/10/2026 | 112 | SI | SI30/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194347 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 20/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 20/10/2026 | 20/10/2026 |  |  | 112 |  | 112 |  |  | 16/10/2026 | 16/10/2026 |  |  | 112 |  | 112 |  |  | 13/10/2026 | 13/10/2026 |  |  | 112 |  | 112
ADIDAS | 0903194349-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194349 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 500 |  | 500 |  |  | 2026-10-11 | 2026-11-11 |  |  | 500 |  | 500 |  |  | 2026-09-11 | 2026-10-11 |  |  | 500 |  | 500
ADIDAS | 0903194351-1 KA4331 | BLACK | 90D | S2608MR0902 | 500 | 23/10/2026 | 500 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960018 | PAD+HT SUB PROCESS_V3 | 0903194351 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 500 |  | 500 |  |  | 2026-10-11 | 2026-11-11 |  |  | 500 |  | 500 |  |  | 2026-09-11 | 2026-10-11 |  |  | 500 |  | 500
ADIDAS | 0903194354-1 KA0235 | BLACK | 90D | S2608WR0901 | 518 | 23/10/2026 | 518 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 980004 | PAD+HT SUB PROCESS_V3 | 0903194354 KA0235 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 13/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 13/11/2026 | 14/11/2026 |  |  | 518 |  | 518 |  |  | 2026-10-11 | 2026-11-11 |  |  | 518 |  | 518 |  |  | 2026-09-11 | 2026-10-11 |  |  | 518 |  | 518
ADIDAS | 0903194356-1 KG8549 | ONIX | 90D | S2408WR1601A | 264 | 31/10/2026 | 264 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650031 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194356 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 27/10/2026 | 28/10/2026 |  |  | 264 |  | 264 |  |  | 23/10/2026 | 24/10/2026 |  |  | 264 |  | 264 |  |  | 20/10/2026 | 21/10/2026 |  |  | 264 |  | 264
ADIDAS | 0903194358-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194358 KX9851 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 20/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 20/11/2026 | 21/11/2026 |  |  | 102 |  | 102 |  |  | 17/11/2026 | 18/11/2026 |  |  | 102 |  | 102 |  |  | 2026-12-11 | 13/11/2026 |  |  | 102 |  | 102
ADIDAS | 0903194360-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 104 | 31/10/2026 | 104 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194360 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 29/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 104 |  | 104 |  |  | 26/10/2026 | 28/10/2026 |  |  | 104 |  | 104 |  |  | 22/10/2026 | 24/10/2026 |  |  | 104 |  | 104
ADIDAS | 0903194361-1 IN1156 | BLACK | 90D | S2408MR1600 | 4002 | 15/10/2026 | 4002 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 516438 | HT SUB PROCESS_V1 | 0903194361 IN1156 | 14/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 21/10/2026 |  |  | 4002 |  | 4002 |  |  | 13/10/2026 | 19/10/2026 | 2026-08-09 | 18/09/2026 | 4002 | 3828 | 174 |  |  | 2026-12-10 | 17/10/2026 | 29/08/2026 | 18/09/2026 | 4002 | 3837 | 165
ADIDAS | 0903194363-1 KA0246 | BLACK | 90D | S2608WR0902 | 228 | 31/10/2026 | 228 | SI | SI30/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194363 KA0246 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 19/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 19/10/2026 | 20/10/2026 |  |  | 228 |  | 228 |  |  | 15/10/2026 | 16/10/2026 |  |  | 228 |  | 228 |  |  | 2026-12-10 | 13/10/2026 |  |  | 228 |  | 228
ADIDAS | 0903194364-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 516404 | HT SUB PROCESS_V1 | 0903194364 IN1172 | 14/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903194365-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 394 | 31/10/2026 | 394 | SA | SA30/06/2026 | G1I | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug. Waiting fabric. T2 New Wide, PI Date 25-Aug. Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903194365 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 13/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 13/11/2026 | 16/11/2026 |  |  | 394 |  | 394 |  |  | 2026-10-11 | 2026-11-11 |  |  | 394 |  | 394 |  |  | 2026-09-11 | 2026-10-11 |  |  | 394 |  | 394
ADIDAS | 0903194367-1 KA0235 | BLACK | 90D | S2608WR0901 | 459 | 31/10/2026 | 459 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194367 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 459 |  | 459 |  |  | 13/11/2026 | 17/11/2026 |  |  | 459 |  | 459 |  |  | 2026-12-11 | 16/11/2026 |  |  | 459 |  | 459
ADIDAS | 0903194370-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 543 | 31/10/2026 | 543 | SA | SA30/06/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194370 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 26/11/2026 | 27/11/2026 |  |  | 543 |  | 543 |  |  | 23/11/2026 | 24/11/2026 |  |  | 543 |  | 543 |  |  | 20/11/2026 | 23/11/2026 |  |  | 543 |  | 543
ADIDAS | 0903194372-1 KA0235 | BLACK | 90D | S2608WR0901 | 434 | 31/10/2026 | 434 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194372 KA0235 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 18/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 434 |  | 434 |  |  | 13/11/2026 | 17/11/2026 |  |  | 434 |  | 434 |  |  | 2026-12-11 | 16/11/2026 |  |  | 434 |  | 434
ADIDAS | 0903194375-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 348 | 31/10/2026 | 348 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903194375 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 2026-06-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-06-11 | 2026-10-11 |  |  | 348 |  | 348 |  |  | 2026-03-11 | 2026-05-11 |  |  | 348 |  | 348 |  |  | 2026-02-11 | 2026-04-11 |  |  | 348 |  | 348
ADIDAS | 0903194378-1 KG8549 | ONIX | 90D | S2408WR1601A | 120 | 31/10/2026 | 120 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194378 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 27/10/2026 | 28/10/2026 |  |  | 120 |  | 120 |  |  | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903194380-1 KA0246 | BLACK | 90D | S2608WR0902 | 564 | 31/10/2026 | 564 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194380 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 564 |  | 564 |  |  | 23/10/2026 | 26/10/2026 |  |  | 564 |  | 564 |  |  | 20/10/2026 | 22/10/2026 |  |  | 564 |  | 564
ADIDAS | 0903194383-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 452 | 31/10/2026 | 452 | SI | SI30/06/2026 | G2D | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194383 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 20/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 20/10/2026 | 21/10/2026 |  |  | 452 |  | 452 |  |  | 16/10/2026 | 17/10/2026 |  |  | 452 |  | 452 |  |  | 13/10/2026 | 14/10/2026 |  |  | 452 |  | 452
ADIDAS | 0903194384-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 450 | 31/10/2026 | 450 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903194384 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-06-11 | 2026-10-11 |  |  | 450 |  | 450 |  |  | 2026-03-11 | 2026-05-11 |  |  | 450 |  | 450 |  |  | 2026-02-11 | 2026-04-11 |  |  | 450 |  | 450
ADIDAS | 0903194387-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 330 | 31/10/2026 | 330 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194387 KX9851 | 14/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 20/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 20/11/2026 | 21/11/2026 |  |  | 330 |  | 330 |  |  | 17/11/2026 | 18/11/2026 |  |  | 330 |  | 330 |  |  | 2026-12-11 | 13/11/2026 |  |  | 330 |  | 330
ADIDAS | 0903194391-1 IN8707 | BLACK | 90D | S2408WR1601A | 201 | 31/10/2026 | 201 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194391 IN8707 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 22/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 201 |  | 201 |  |  | 19/10/2026 | 21/10/2026 |  |  | 201 |  | 201 |  |  | 15/10/2026 | 17/10/2026 |  |  | 201 |  | 201
ADIDAS | 0903194394-1 KG8549 | ONIX | 90D | S2408WR1601A | 144 | 31/10/2026 | 144 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194394 KG8549 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 27/10/2026 | 28/10/2026 |  |  | 144 |  | 144 |  |  | 23/10/2026 | 24/10/2026 |  |  | 144 |  | 144 |  |  | 20/10/2026 | 21/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903194397-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 319 | 31/10/2026 | 319 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Airowes). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 650034 | PAD+HT SUB PROCESS_V3 | 0903194397 LD0292 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 2026-06-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-06-11 | 2026-10-11 |  |  | 319 |  | 319 |  |  | 2026-03-11 | 2026-05-11 |  |  | 319 |  | 319 |  |  | 2026-02-11 | 2026-04-11 |  |  | 319 |  | 319
ADIDAS | 0903194400-1 KA0246 | BLACK | 90D | S2608WR0902 | 591 | 31/10/2026 | 591 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194400 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 27/10/2026 | 29/10/2026 |  |  | 591 |  | 591 |  |  | 23/10/2026 | 26/10/2026 |  |  | 591 |  | 591 |  |  | 20/10/2026 | 22/10/2026 |  |  | 591 |  | 591
ADIDAS | 0903194402-1 KA0235 | BLACK | 90D | S2608WR0901 | 807 | 31/10/2026 | 807 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194402 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 20/11/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 20/11/2026 | 21/11/2026 |  |  | 807 |  | 807 |  |  | 17/11/2026 | 18/11/2026 |  |  | 807 |  | 807 |  |  | 16/11/2026 | 17/11/2026 |  |  | 807 |  | 807
ADIDAS | 0903194405-1 KA4331 | BLACK | 90D | S2608MR0902 | 628 | 31/10/2026 | 628 | SA | SA30/06/2026 | G1G | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903194405 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 628 |  | 628 |  |  | 13/11/2026 | 17/11/2026 |  |  | 628 |  | 628 |  |  | 2026-12-11 | 16/11/2026 |  |  | 628 |  | 628
ADIDAS | 0903194447-1 KA6229 | BLACK | 120D | S2608WR0202 | 1079 | 31/10/2026 | 1079 | SA | SA30/06/2026 | G1O | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194447 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-07-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-07-11 | 2026-11-11 |  |  | 1079 |  | 1079 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1079 |  | 1079 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1079 |  | 1079
ADIDAS | 0903194453-1 KA6229 | BLACK | 120D | S2608WR0202 | 516 | 23/10/2026 | 516 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194453 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 516 |  | 516 |  |  | 2026-04-11 | 2026-06-11 |  |  | 516 |  | 516 |  |  | 31/10/2026 | 2026-03-11 |  |  | 516 |  | 516
ADIDAS | 0903194462-1 KA6229 | BLACK | 120D | S2608WR0202 | 150 | 23/10/2026 | 150 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD 20-Aug, ETA-Kaha 10-Sep. Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD 27-Aug, ETA-Kaha 10-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194462 KA6229 | 28/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 150 |  | 150 |  |  | 2026-04-11 | 2026-06-11 |  |  | 150 |  | 150 |  |  | 31/10/2026 | 2026-03-11 |  |  | 150 |  | 150
ADIDAS | 0903194468-1 KA6229 | BLACK | 120D | S2608WR0202 | 880 | 31/10/2026 | 880 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194468 KA6229 | 28/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-11-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-11-11 | 16/11/2026 |  |  | 880 |  | 880 |  |  | 2026-06-11 | 2026-11-11 |  |  | 880 |  | 880 |  |  | 2026-03-11 | 2026-06-11 |  |  | 880 |  | 880
ADIDAS | 0903194475-1 KA6229 | BLACK | 120D | S2608WR0202 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194475 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-03-11 |  |  | 631 |  | 631 |  |  | 27/10/2026 | 30/10/2026 |  |  | 631 |  | 631 |  |  | 23/10/2026 | 27/10/2026 | 15/09/2026 | 15/09/2026 | 631 | 303 | 328
ADIDAS | 0903194486-1 KA6229 | BLACK | 120D | S2608WR0202 | 526 | 15/10/2026 | 526 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). T2 Best Pacific, PI Date 28-Aug, actual receives 03-Sep (using fabric from TRAX). 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194486 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 30/10/2026 | 2026-03-11 |  |  | 526 |  | 526 |  |  | 27/10/2026 | 30/10/2026 |  |  | 526 |  | 526 |  |  | 23/10/2026 | 27/10/2026 | 18/09/2026 | 19/09/2026 | 526 | 399 | 127 |  | 23
ADIDAS | 0903194488-1 KA6229 | BLACK | 120D | S2608WR0202 | 310 | 15/10/2026 | 310 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194488 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 310 |  | 310 |  |  | 30/10/2026 | 2026-02-11 |  |  | 310 |  | 310 |  |  | 27/10/2026 | 29/10/2026 | 17/09/2026 | 19/09/2026 | 310 | 310 |  |  | 38
ADIDAS | 0903194490-1 KA6229 | BLACK | 120D | S2608WR0202 | 369 | 15/10/2026 | 369 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194490 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-03-11 | 2026-05-11 |  |  | 369 |  | 369 |  |  | 30/10/2026 | 2026-02-11 |  |  | 369 |  | 369 |  |  | 27/10/2026 | 29/10/2026 | 14/09/2026 | 19/09/2026 | 369 | 355 | 14 |  | 42
ADIDAS | 0903194492-1 KA6229 | BLACK | 120D | S2608WR0202 | 926 | 2026-07-10 | 926 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194492 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-12-10 | 15/10/2026 |  |  | 926 |  | 926 |  |  | 2026-08-10 | 2026-12-10 |  |  | 926 |  | 926 |  |  | 2026-05-10 | 2026-08-10 | 15/09/2026 | 19/09/2026 | 926 | 919 | 7 |  | 30
ADIDAS | 0903194495-1 KA6229 | BLACK | 120D | S2608WR0202 | 321 | 2026-07-10 | 321 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194495 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 321 |  | 321 |  |  | 2026-12-10 | 14/10/2026 |  |  | 321 |  | 321 |  |  | 2026-08-10 | 2026-10-10 | 18/09/2026 | 18/09/2026 | 321 | 243 | 78
ADIDAS | 0903194496-1 KA6229 | BLACK | 120D | S2608WR0202 | 779 | 15/10/2026 | 779 | SA | SA30/06/2026 | G1B | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0051-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194496 KA6229 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-05-11 | 2026-09-11 |  |  | 779 |  | 779 |  |  | 2026-02-11 | 2026-04-11 |  |  | 779 |  | 779 |  |  | 29/10/2026 | 31/10/2026 | 14/09/2026 | 19/09/2026 | 779 | 756 | 23 |  | 63
ADIDAS | 0903194499-1 KA6229 | BLACK | 120D | S2608WR0202 | 346 | 2026-07-10 | 346 | SA | SA30/06/2026 | G1N | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. DRC 0002-T2 Far Easten, material delayed, PI Date 25-Aug, ETD ?? T2 Best Pacific, PI Date 28-Aug, actual receives 14-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep (using fabric from TRAX). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194499 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 15/10/2026 | 17/10/2026 |  |  | 346 |  | 346 |  |  | 2026-12-10 | 14/10/2026 |  |  | 346 |  | 346 |  |  | 2026-08-10 | 2026-10-10 | 16/09/2026 | 19/09/2026 | 346 | 271 | 75 |  | 94
ADIDAS | 0903194501-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194501 KA6229 | 28/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-11-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-11-11 | 16/11/2026 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-11-11 |  |  | 300 |  | 300 |  |  | 2026-03-11 | 2026-06-11 |  |  | 300 |  | 300
ADIDAS | 0903194663-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 1069 | 29/09/2026 | 1069 | AN | AN26/06/2026 | G1D | JACKET | G1 | ok | (07/08/2026) | 28/09: ex-fty. DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Teijin Nantong, material quality issues (moir膿), PI Date 03-Aug, actual receives 18-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 25-May (PO NT-354). 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194663 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-09 | M SL WV TT LEGEND IVY S19 |  | SS27 | 2026-10-09 | 19/09/2026 | 2026-10-09 | 19/09/2026 | 1069 | 358 | 711 |  | 18 | 2026-07-09 | 16/09/2026 | 2026-02-09 | 2026-11-09 | 1069 | 383 | 686
ADIDAS | 0903194835-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 623 | 30/09/2026 | 623 | AN | AN26/06/2026 | G3J | PANTS | G3 | ok | ok | 24/09: ex-fty. T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903194835 KV7863 | 2026-10-09 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 17/09/2026 | 18/09/2026 | 623 | 607 | 16 |  |  | 2026-12-09 | 17/09/2026 | 2026-10-09 | 15/09/2026 | 623 | 613 | 10
ADIDAS | 0903195508-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 471 | 15/10/2026 | 471 | AN | AN30/06/2026 | G2L | T-SHIRT | G2 | (31/07/2026) | ok | 29/09: ex-fty. Waiting fabric replacement. DRC 0001-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, ETD ?? 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903195508 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 15/10/2026 | 15/10/2026 |  |  | 471 |  | 471 |  |  | 2026-12-10 | 2026-12-10 |  |  | 471 |  | 471 |  |  | 2026-10-10 | 2026-10-10 |  |  | 471 |  | 471
ADIDAS | 0903196020-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 891 | 15/10/2026 | 891 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196020 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 891 |  | 891 |  |  | 2026-07-10 | 2026-08-10 |  |  | 891 |  | 891 |  |  | 2026-06-10 | 2026-07-10 |  |  | 891 |  | 891
ADIDAS | 0903196021-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 12 | 15/10/2026 | 12 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903196021 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 12 |  | 12 |  |  | 2026-07-10 | 2026-08-10 |  |  | 12 |  | 12 |  |  | 2026-06-10 | 2026-07-10 |  |  | 12 |  | 12
ADIDAS | 0903196022-1 IN1172 | BLACK | 90D | S2408WR1600 | 2616 | 15/10/2026 | 2616 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 823016 | HT SUB PROCESS_V1 | 0903196022 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 23/10/2026 |  |  | 2616 |  | 2616 |  |  | 17/10/2026 | 21/10/2026 |  |  | 2616 |  | 2616 |  |  | 16/10/2026 | 20/10/2026 | 2026-04-09 | 17/09/2026 | 2616 | 2595 | 21
ADIDAS | 0903196023-1 IN1156 | BLACK | 90D | S2408MR1600 | 3287 | 15/10/2026 | 3287 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 823016 | HT SUB PROCESS_V1 | 0903196023 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 15/10/2026 |  |  | 3287 |  | 3287 |  |  | 2026-09-10 | 13/10/2026 | 18/09/2026 | 19/09/2026 | 3287 | 2388 | 899 |  | 1503 | 2026-08-10 | 2026-12-10 | 18/09/2026 | 19/09/2026 | 3287 | 3130 | 157 |  | 733
ADIDAS | 0903196024-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960006 | HT SUB PROCESS_V1 | 0903196024 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100 |  |  | 23/10/2026 | 24/10/2026 | 2026-05-09 | 19/09/2026 | 100 | 100 |  |  | 3
ADIDAS | 0903196025-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960006 | HT SUB PROCESS_V1 | 0903196025 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 200 |  | 200 |  |  | 2026-05-10 | 2026-06-10 | 2026-09-09 | 2026-11-09 | 200 | 199 | 1 |  |  | 2026-03-10 | 2026-05-10 | 31/08/2026 | 2026-10-09 | 200 | 199 | 1
ADIDAS | 0903196026-1 IN1172 | BLACK | 90D | S2408WR1600 | 134 | 15/10/2026 | 134 | SI | SI30/06/2026 | G1J | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 960026 | HT SUB PROCESS_V1 | 0903196026 IN1172 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 134 |  | 134 |  |  | 24/10/2026 | 26/10/2026 |  |  | 134 |  | 134 |  |  | 23/10/2026 | 24/10/2026 | 2026-05-09 | 2026-12-09 | 134 | 134
ADIDAS | 0903196027-1 IN1156 | BLACK | 90D | S2408MR1600 | 143 | 15/10/2026 | 143 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 960026 | HT SUB PROCESS_V1 | 0903196027 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 143 |  | 143 |  |  | 2026-08-10 | 2026-09-10 | 2026-08-09 | 2026-10-09 | 143 | 142 | 1 |  |  | 2026-07-10 | 2026-08-10 | 29/08/2026 | 2026-10-09 | 143 | 142 | 1
ADIDAS | 0903196028-1 IN1156 | BLACK | 90D | S2408MR1600 | 631 | 15/10/2026 | 631 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 07-Aug. 980004 | HT SUB PROCESS_V1 | 0903196028 IN1156 | 14/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 631 |  | 631 |  |  | 2026-10-10 | 2026-12-10 |  |  | 631 |  | 631 |  |  | 2026-09-10 | 2026-10-10 |  |  | 631 |  | 631
ADIDAS | 0903196030-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 1200 | 15/10/2026 | 1200 | SA | SA30/06/2026 | G1P | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196030 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 1200 |  | 1200 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1200 |  | 1200 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903196031-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 1200 | 15/10/2026 | 1200 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 650031 | HT SUB PROCESS_V1 | 0903196031 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 1200 |  | 1200 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1200 |  | 1200 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903196032-1 IN1157 | WHITE | 90D | S2408MR1600 | 290 | 15/10/2026 | 290 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | (07/08/2026) | (Damco offline). T2 Y.T.I, body & mesh actual receives 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903196032 IN1157 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 290 |  | 290 |  |  | 19/10/2026 | 20/10/2026 | 2026-09-09 | 18/09/2026 | 290 | 290 |  |  |  | 17/10/2026 | 19/10/2026 | 2026-02-09 | 18/09/2026 | 290 | 290
ADIDAS | 0903196033-1 IN1156 | BLACK | 90D | S2408MR1600 | 236 | 15/10/2026 | 236 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | (07/08/2026) | (Damco offline). T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 688010 | HT SUB PROCESS_V1 | 0903196033 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 2026-12-10 |  |  | 236 |  | 236 |  |  | 2026-08-10 | 2026-09-10 |  |  | 236 |  | 236 |  |  | 2026-07-10 | 2026-08-10 | 2026-02-09 | 19/09/2026 | 236 | 235 | 1 |  | 38
ADIDAS | 0903196034-1 IN1173 | WHITE | 90D | S2408WR1600 | 114 | 15/10/2026 | 114 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 01-Aug. 688010 | HT SUB PROCESS_V1 | 0903196034 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 114 |  | 114 |  |  | 2026-06-10 | 2026-07-10 | 13/08/2026 | 26/08/2026 | 114 | 114 |  |  |  | 2026-05-10 | 2026-06-10 | 13/08/2026 | 22/08/2026 | 114 | 114
ADIDAS | 0903196035-1 IN1172 | BLACK | 90D | S2408WR1600 | 528 | 15/10/2026 | 528 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 688010 | HT SUB PROCESS_V1 | 0903196035 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-03-10 |  |  | 528 |  | 528 |  |  | 30/09/2026 | 2026-01-10 |  |  | 528 |  | 528 |  |  | 29/09/2026 | 30/09/2026 | 2026-05-09 | 19/09/2026 | 528 | 527 | 1 |  | 11
ADIDAS | 0903196036-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600 | 144 | 15/10/2026 | 144 | SI | SI30/06/2026 | G1H | T-SHIRT | G1 | (10/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196036 IT1824 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 144 |  | 144 |  |  | 13/10/2026 | 14/10/2026 |  |  | 144 |  | 144 |  |  | 2026-12-10 | 13/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903196037-1 IT1828 | TEAM POWER RED 2 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/08/2026) | (07/08/2026) | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 01-Aug, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903196037 IT1828 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 248 |  | 248 |  |  | 2026-06-10 | 2026-07-10 |  |  | 248 |  | 248 |  |  | 2026-05-10 | 2026-06-10 |  |  | 248 |  | 248
ADIDAS | 0903196038-1 IN1172 | BLACK | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI30/06/2026 | G1G | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196038 IN1172 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-10-11 | ADIZERO E TEE |  | SS27-YTI | 2026-10-11 | 2026-11-11 |  |  | 138 |  | 138 |  |  | 2026-06-11 | 2026-09-11 |  |  | 138 |  | 138 |  |  | 2026-05-11 | 2026-06-11 |  |  | 138 |  | 138
ADIDAS | 0903196039-1 IN1173 | WHITE | 90D | S2408WR1600 | 142 | 31/10/2026 | 142 | SI | SI30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196039 IN1173 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 142 |  | 142 |  |  | 21/10/2026 | 22/10/2026 |  |  | 142 |  | 142 |  |  | 20/10/2026 | 21/10/2026 |  |  | 142 |  | 142
ADIDAS | 0903196040-1 IN1156 | BLACK | 90D | S2408MR1600 | 496 | 31/10/2026 | 496 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | (07/08/2026) | Waiting fabric (KN GLT). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650031 | HT SUB PROCESS_V1 | 0903196040 IN1156 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-09-11 | ADIZERO E TEE |  | SS27-YTI | 2026-09-11 | 2026-10-11 |  |  | 496 |  | 496 |  |  | 2026-05-11 | 2026-06-11 |  |  | 496 |  | 496 |  |  | 2026-04-11 | 2026-05-11 |  |  | 496 |  | 496
ADIDAS | 0903197147-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 652 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197147 KY9391 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197425-1 IN8707 | BLACK | 90D | S2408WR1601A | 156 | 15/10/2026 | 156 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197425 IN8707 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 14/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 14/10/2026 | 16/10/2026 |  |  | 156 |  | 156 |  |  | 2026-10-10 | 13/10/2026 |  |  | 156 |  | 156 |  |  | 2026-07-10 | 2026-09-10 |  |  | 156 |  | 156
ADIDAS | 0903197427-1 KA0235 | BLACK | 90D | S2608WR0901 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 826010 | PAD+HT SUB PROCESS_V3 | 0903197427 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 22/10/2026 | 24/10/2026 |  |  | 200 |  | 200 |  |  | 21/10/2026 | 23/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903197429-1 KA0246 | BLACK | 90D | S2608WR0902 | 200 | 15/10/2026 | 200 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197429 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 200 |  | 200 |  |  | 2026-03-10 | 2026-05-10 |  |  | 200 |  | 200 |  |  | 30/09/2026 | 2026-01-10 |  |  | 200 |  | 200
ADIDAS | 0903197431-1 IN8707 | BLACK | 90D | S2408WR1601A | 361 | 15/10/2026 | 361 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197431 IN8707 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 14/10/2026 | 16/10/2026 |  |  | 361 |  | 361 |  |  | 2026-10-10 | 13/10/2026 |  |  | 361 |  | 361 |  |  | 2026-07-10 | 2026-09-10 |  |  | 361 |  | 361
ADIDAS | 0903197433-1 KA0246 | BLACK | 90D | S2608WR0902 | 264 | 15/10/2026 | 264 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197433 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 264 |  | 264 |  |  | 2026-03-10 | 2026-05-10 |  |  | 264 |  | 264 |  |  | 30/09/2026 | 2026-01-10 |  |  | 264 |  | 264
ADIDAS | 0903197435-1 KA0235 | BLACK | 90D | S2608WR0901 | 708 | 15/10/2026 | 708 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 688010 | PAD+HT SUB PROCESS_V3 | 0903197435 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 31/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 31/10/2026 | 2026-03-11 |  |  | 708 |  | 708 |  |  | 28/10/2026 | 30/10/2026 |  |  | 708 |  | 708 |  |  | 27/10/2026 | 29/10/2026 |  |  | 708 |  | 708
ADIDAS | 0903197436-1 KA0246 | BLACK | 90D | S2608WR0902 | 268 | 15/10/2026 | 268 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197436 KA0246 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-08-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-08-10 | 2026-10-10 |  |  | 268 |  | 268 |  |  | 2026-05-10 | 2026-07-10 |  |  | 268 |  | 268 |  |  | 2026-01-10 | 2026-03-10 |  |  | 268 |  | 268
ADIDAS | 0903197439-1 KA0235 | BLACK | 90D | S2608WR0901 | 155 | 15/10/2026 | 155 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 826010 | PAD+HT SUB PROCESS_V3 | 0903197439 KA0235 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 26/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 26/10/2026 | 28/10/2026 |  |  | 155 |  | 155 |  |  | 22/10/2026 | 24/10/2026 |  |  | 155 |  | 155 |  |  | 21/10/2026 | 23/10/2026 |  |  | 155 |  | 155
ADIDAS | 0903197440-1 KA4331 | BLACK | 90D | S2608MR0902 | 277 | 15/10/2026 | 277 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 826010 | PAD+HT SUB PROCESS_V3 | 0903197440 KA4331 | 14/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-10-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 277 |  | 277 |  |  | 2026-07-10 | 2026-08-10 |  |  | 277 |  | 277 |  |  | 2026-06-10 | 2026-07-10 |  |  | 277 |  | 277
ADIDAS | 0903197442-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 335 | 15/10/2026 | 335 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? T2 Formosa, PI Date 05-Aug, actual receives 31-Aug. 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197442 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 16/10/2026 | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX | 16/10/2026 | 19/10/2026 |  |  | 335 |  | 335 |  |  | 13/10/2026 | 15/10/2026 |  |  | 335 |  | 335 |  |  | 2026-09-10 | 2026-12-10 |  |  | 335 |  | 335
ADIDAS | 0903197444-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 520 | 15/10/2026 | 520 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? T2 Formosa, PI Date 05-Aug, actual receives 30-Aug. 680015 | PAD+HT SUB PROCESS_V3 | 0903197444 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-08-10 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 520 |  | 520 |  |  | 2026-05-10 | 2026-08-10 |  |  | 520 |  | 520 |  |  | 2026-03-10 | 2026-07-10 |  |  | 520 |  | 520
ADIDAS | 0903197446-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 630 | 15/10/2026 | 630 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 11-Sep. T2 Formosa, PI Date 19-Aug, actual receives 31-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197446 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 630 |  | 630 |  |  | 2026-05-10 | 2026-06-10 |  |  | 630 |  | 630 |  |  | 2026-03-10 | 2026-05-10 |  |  | 630 |  | 630
ADIDAS | 0903197448-1 KA0235 | BLACK | 90D | S2608WR0901 | 675 | 15/10/2026 | 675 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903197448 KA0235 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 675 |  | 675 |  |  | 26/10/2026 | 28/10/2026 |  |  | 675 |  | 675 |  |  | 24/10/2026 | 27/10/2026 |  |  | 675 |  | 675
ADIDAS | 0903197449-1 KA0246 | BLACK | 90D | S2608WR0902 | 547 | 15/10/2026 | 547 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197449 KA0246 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-08-10 | 2026-10-10 |  |  | 547 |  | 547 |  |  | 2026-05-10 | 2026-07-10 |  |  | 547 |  | 547 |  |  | 2026-01-10 | 2026-03-10 |  |  | 547 |  | 547
ADIDAS | 0903197451-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903197451 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-05-10 |  |  | 300 |  | 300 |  |  | 2026-02-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903197453-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 681 | 15/10/2026 | 681 | SA | SA30/06/2026 | G1F | SHORTS | G1 | ok |  | T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Far Eastern, PI Date 25-Aug, actual receives 05-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197453 JZ7775 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-08-10 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 681 |  | 681 |  |  | 2026-05-10 | 2026-08-10 |  |  | 681 |  | 681 |  |  | 2026-03-10 | 2026-07-10 |  |  | 681 |  | 681
ADIDAS | 0903197455-1 KA4331 | BLACK | 90D | S2608MR0902 | 346 | 15/10/2026 | 346 | SA | SA30/06/2026 | G1C | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 960026 | PAD+HT SUB PROCESS_V3 | 0903197455 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-10-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-10-10 | 2026-12-10 |  |  | 346 |  | 346 |  |  | 2026-07-10 | 2026-08-10 |  |  | 346 |  | 346 |  |  | 2026-06-10 | 2026-07-10 |  |  | 346 |  | 346
ADIDAS | 0903197456-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 822 | 15/10/2026 | 822 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197456 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 26/10/2026 | 27/10/2026 |  |  | 822 |  | 822 |  |  | 22/10/2026 | 23/10/2026 |  |  | 822 |  | 822 |  |  | 19/10/2026 | 20/10/2026 |  |  | 822 |  | 822
ADIDAS | 0903197458-1 KA0235 | BLACK | 90D | S2608WR0901 | 999 | 15/10/2026 | 999 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 680015 | PAD+HT SUB PROCESS_V3 | 0903197458 KA0235 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-11 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-03-11 | 2026-06-11 |  |  | 999 |  | 999 |  |  | 30/10/2026 | 2026-03-11 |  |  | 999 |  | 999 |  |  | 29/10/2026 | 2026-02-11 |  |  | 999 |  | 999
ADIDAS | 0903197459-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 102 | 15/10/2026 | 102 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197459 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 102 |  | 102 |  |  | 17/10/2026 | 19/10/2026 |  |  | 102 |  | 102 |  |  | 14/10/2026 | 15/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903197461-1 KA0235 | BLACK | 90D | S2608WR0901 | 420 | 15/10/2026 | 420 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650036 | PAD+HT SUB PROCESS_V3 | 0903197461 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 420 |  | 420 |  |  | 24/10/2026 | 26/10/2026 |  |  | 420 |  | 420 |  |  | 23/10/2026 | 24/10/2026 |  |  | 420 |  | 420
ADIDAS | 0903197465-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 307 | 15/10/2026 | 307 | SI | SI30/06/2026 | G2R | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? T2 Formosa, PI Date 05-Aug, actual receives 31-Aug. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197465 LD0908 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 16/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 16/10/2026 | 16/10/2026 |  |  | 307 |  | 307 |  |  | 13/10/2026 | 13/10/2026 |  |  | 307 |  | 307 |  |  | 2026-09-10 | 2026-09-10 |  |  | 307 |  | 307
ADIDAS | 0903197472-1 KZ2988 | SOLAR TURBO F26 | 90D | S2408WR1601A | 408 | 15/10/2026 | 408 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197472 KZ2988 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 408 |  | 408 |  |  | 17/10/2026 | 19/10/2026 |  |  | 408 |  | 408 |  |  | 14/10/2026 | 15/10/2026 |  |  | 408 |  | 408
ADIDAS | 0903197475-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 498 | 15/10/2026 | 498 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 688010 | PAD+HT SUB PROCESS_V3 | 0903197475 LD0292 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-03-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 498 |  | 498 |  |  | 30/09/2026 | 2026-02-10 |  |  | 498 |  | 498 |  |  | 29/09/2026 | 2026-01-10 |  |  | 498 |  | 498
ADIDAS | 0903197478-1 KA4331 | BLACK | 90D | S2608MR0902 | 18 | 15/10/2026 | 18 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903197478 KA4331 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 18 |  | 18 |  |  | 2026-03-10 | 2026-05-10 |  |  | 18 |  | 18 |  |  | 2026-02-10 | 2026-03-10 |  |  | 18 |  | 18
ADIDAS | 0903197480-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 530 | 15/10/2026 | 530 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 11-Sep. T2 Formosa, PI Date 19-Aug, actual receives 31-Aug. 659018 | PAD+HT SUB PROCESS_V3 | 0903197480 KA0238 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-06-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-06-10 | 2026-08-10 |  |  | 530 |  | 530 |  |  | 2026-02-10 | 2026-05-10 |  |  | 530 |  | 530 |  |  | 2026-01-10 | 2026-03-10 |  |  | 530 |  | 530
ADIDAS | 0903197482-1 KA0235 | BLACK | 90D | S2608WR0901 | 300 | 15/10/2026 | 300 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 650010 | PAD+HT SUB PROCESS_V3 | 0903197482 KA0235 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 28/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 300 |  | 300 |  |  | 24/10/2026 | 26/10/2026 |  |  | 300 |  | 300 |  |  | 23/10/2026 | 24/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197484-1 KA0246 | BLACK | 90D | S2608WR0902 | 611 | 15/10/2026 | 611 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197484 KA0246 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 13/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 13/10/2026 | 13/10/2026 |  |  | 611 |  | 611 |  |  | 2026-09-10 | 2026-09-10 |  |  | 611 |  | 611 |  |  | 2026-06-10 | 2026-06-10 |  |  | 611 |  | 611
ADIDAS | 0903197486-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 544 | 15/10/2026 | 544 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903197486 LD0292 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 544 |  | 544 |  |  | 30/09/2026 | 2026-02-10 |  |  | 544 |  | 544 |  |  | 29/09/2026 | 2026-01-10 |  |  | 544 |  | 544
ADIDAS | 0903197487-1 KA0235 | BLACK | 90D | S2608WR0901 | 106 | 15/10/2026 | 106 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 834012 | PAD+HT SUB PROCESS_V3 | 0903197487 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 29/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 106 |  | 106 |  |  | 26/10/2026 | 28/10/2026 |  |  | 106 |  | 106 |  |  | 24/10/2026 | 27/10/2026 |  |  | 106 |  | 106
ADIDAS | 0903197489-1 KA0246 | BLACK | 90D | S2608WR0902 | 204 | 15/10/2026 | 204 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197489 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-10-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-10-10 | 13/10/2026 |  |  | 204 |  | 204 |  |  | 2026-07-10 | 2026-09-10 |  |  | 204 |  | 204 |  |  | 2026-03-10 | 2026-06-10 |  |  | 204 |  | 204
ADIDAS | 0903197490-1 KA4331 | BLACK | 90D | S2608MR0902 | 790 | 15/10/2026 | 790 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 834012 | PAD+HT SUB PROCESS_V3 | 0903197490 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-07-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 790 |  | 790 |  |  | 2026-03-10 | 2026-05-10 |  |  | 790 |  | 790 |  |  | 2026-02-10 | 2026-03-10 |  |  | 790 |  | 790
ADIDAS | 0903197494-1 KA0246 | BLACK | 90D | S2608WR0902 | 772 | 15/10/2026 | 772 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197494 KA0246 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-10-10 | 13/10/2026 |  |  | 772 |  | 772 |  |  | 2026-07-10 | 2026-09-10 |  |  | 772 |  | 772 |  |  | 2026-03-10 | 2026-06-10 |  |  | 772 |  | 772
ADIDAS | 0903197496-1 KA0235 | BLACK | 90D | S2608WR0901 | 6000 | 15/10/2026 | 6000 | SI | SI30/06/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 678002 | PAD+HT SUB PROCESS_V3 | 0903197496 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 31/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 31/10/2026 | 2026-11-11 |  |  | 6000 |  | 6000 |  |  | 28/10/2026 | 2026-06-11 |  |  | 6000 |  | 6000 |  |  | 27/10/2026 | 2026-05-11 |  |  | 6000 |  | 6000
ADIDAS | 0903197498-1 KA0238 | MEDIUM GREY HEATHER | 90D | S2608WR0901 | 636 | 15/10/2026 | 636 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 11-Sep. T2 Formosa, PI Date 19-Aug, actual receives 31-Aug. 678002 | PAD+HT SUB PROCESS_V3 | 0903197498 KA0238 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-09-10 | Run Ess Shor W MEDIUM GREY HEATHER |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 636 |  | 636 |  |  | 2026-06-10 | 2026-07-10 |  |  | 636 |  | 636 |  |  | 2026-05-10 | 2026-06-10 |  |  | 636 |  | 636
ADIDAS | 0903197499-1 KA0235 | BLACK | 90D | S2608WR0901 | 1428 | 15/10/2026 | 1428 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903197499 KA0235 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-01-10 | Run Ess Shor W BLACK |  | SS27-TRAX | 2026-01-10 | 2026-03-10 |  |  | 1428 |  | 1428 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1428 |  | 1428 |  |  | 26/09/2026 | 29/09/2026 |  |  | 1428 |  | 1428
ADIDAS | 0903197500-1 KA4331 | BLACK | 90D | S2608MR0902 | 1450 | 15/10/2026 | 1450 | SA | SA30/06/2026 | G1F | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 09-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903197500 KA4331 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-12-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 1450 |  | 1450 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1450 |  | 1450 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1450 |  | 1450
ADIDAS | 0903197745-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 1860 | 31/10/2026 | 1860 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197745 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 16/11/2026 | 23/11/2026 |  |  | 1860 |  | 1860 |  |  | 2026-11-11 | 18/11/2026 |  |  | 1860 |  | 1860 |  |  | 2026-06-11 | 13/11/2026 |  |  | 1860 |  | 1860
ADIDAS | 0903197746-1 JZ7711 | BLACK | 120D | S2608MR0202 | 3000 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516415 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197746 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197760-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 600 | 15/10/2026 | 600 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 600000 | PAD+HT SUB PROCESS_V3 | 0903197760 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 600 |  | 600 |  |  | 30/09/2026 | 2026-03-10 |  |  | 600 |  | 600 |  |  | 29/09/2026 | 2026-02-10 |  |  | 600 |  | 600
ADIDAS | 0903197762-1 KF5802 | TECH INDIGO S20 | 105D | S2608MR0602A | 778 | 15/10/2026 | 778 | SA | SA30/06/2026 | G3G | SHORTS | G3 | (25/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date 11-Aug, ETD ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903197762 KF5802 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | adi365 2in1 S M TECH INDIGO S20 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 778 |  | 778 |  |  | 30/09/2026 | 2026-03-10 |  |  | 778 |  | 778 |  |  | 29/09/2026 | 2026-02-10 |  |  | 778 |  | 778
ADIDAS | 0903197769-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 1700 | 15/10/2026 | 1700 | SI | SI30/06/2026 | G3J | SHORTS | G3 | (15/08/2026) |  | T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 16-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197769 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-03-10 | 2026-07-10 |  |  | 1700 |  | 1700 |  |  | 30/09/2026 | 2026-03-10 |  |  | 1700 |  | 1700 |  |  | 26/09/2026 | 30/09/2026 |  |  | 1700 |  | 1700
ADIDAS | 0903197773-1 KE9656 | BLACK | 105D | S2608WR0201A | 7617 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug. Waiting fabric. T2 Y.R.C, PI Date 15-Aug. Waiting fabric. T2 Best Pacific, PI Date 14-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197773 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903197775-1 KE9656 | BLACK | 105D | S2608WR0201A | 322 | 15/10/2026 | 322 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (22/08/2026) |  | T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Far Eastern, PI Date 22-Aug, actual receives 15-Sep. T2 Best Pacific, PI Date 14-Aug, actual receives 14-Sep. T2 Grand Tex, PI Date 30-Jul, actual receives 28-Aug. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197775 KE9656 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | ADI365 SHO W BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 322 |  | 322 |  |  | 2026-02-10 | 2026-03-10 |  |  | 322 |  | 322 |  |  | 29/09/2026 | 30/09/2026 |  |  | 322 |  | 322
ADIDAS | 0903197777-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 2329 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197777 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197785-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1015 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197785 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197795-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 197 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | DRC 0090-early shipment customer (ROW - FW: Critical PODD improvement request- RDD Jan availability - LO comm). Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197795 KY9393 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197798-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 527 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197798 KY9391 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197807-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 341 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197807 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197811-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 249 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197811 KY9391 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197815-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 390 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197815 KY9393 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197818-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1039 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197818 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197829-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 445 | 31/10/2026 | 445 | SI | SI30/06/2026 | G3F | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197829 KY9385 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-11 | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX | 2026-03-11 | 2026-03-11 |  |  | 445 |  | 445 |  |  | 30/10/2026 | 30/10/2026 |  |  | 445 |  | 445 |  |  | 27/10/2026 | 27/10/2026 |  |  | 445 |  | 445
ADIDAS | 0903197840-1 JZ7711 | BLACK | 120D | S2608MR0202 | 615 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197840 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197849-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 300 | 31/10/2026 | 300 | SI | SI30/06/2026 | G3D | SHORTS | G3 | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197849 KY9384 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX | 2026-04-11 | 2026-06-11 |  |  | 300 |  | 300 |  |  | 31/10/2026 | 2026-03-11 |  |  | 300 |  | 300 |  |  | 28/10/2026 | 30/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903197853-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1291 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197853 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197856-1 JZ7711 | BLACK | 120D | S2608MR0202 | 330 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197856 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197859-1 JZ7711 | BLACK | 120D | S2608MR0202 | 601 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197859 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197863-1 JZ7711 | BLACK | 120D | S2608MR0202 | 366 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197863 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197870-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 300 | 31/10/2026 | 300 | SI | SI30/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197870 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-11-11 | 2026-12-11 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-09-11 |  |  | 300 |  | 300 |  |  | 2026-03-11 | 2026-04-11 |  |  | 300 |  | 300
ADIDAS | 0903197872-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 695 | 31/10/2026 | 695 | SI | SI30/06/2026 | G3G | SHORTS | G3 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516267 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197872 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-11 | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 695 |  | 695 |  |  | 2026-09-11 | 2026-10-11 |  |  | 695 |  | 695 |  |  | 2026-04-11 | 2026-05-11 |  |  | 695 |  | 695
ADIDAS | 0903197875-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 300 | 31/10/2026 | 300 | SA | SA30/06/2026 | G1P | SHORTS | G1 | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516403 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197875 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX | 16/11/2026 | 16/11/2026 |  |  | 300 |  | 300 |  |  | 2026-11-11 | 2026-11-11 |  |  | 300 |  | 300 |  |  | 2026-06-11 | 2026-06-11 |  |  | 300 |  | 300
ADIDAS | 0903197879-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 408 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197879 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197886-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1556 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197886 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903197889-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 816 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197889 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903201074-1 JZ7711 | BLACK | 120D | S2608MR0202 | 211 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201074 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903201075-1 JZ7711 | BLACK | 120D | S2608MR0202 | 102 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903201075 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903203165-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 251 | 31/10/2026 |  | SI | SI29/05/2026 |  | SHORTS |  | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903203165 LF0725 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903203168-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV-MTF | 186 | 2026-05-09 | 186 | AN | AN12/06/2026 | G3B | PANTS | G3 | ok | (03/07/2026) | 04/09: ex-fty. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 06-Jul, actual receives 03-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 30-Jun (PO NT-347). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903203168 KZ3199 | 28/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-08 | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27 | 2026-06-08 | 14/08/2026 | 2026-06-08 | 14/08/2026 | 186 | 186 |  |  |  | 2026-03-08 | 2026-11-08 | 2026-04-08 | 14/08/2026 | 186 | 186
ADIDAS | 0903203169-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 425 | 30/09/2026 | 425 | SI | SI26/06/2026 | G3J | PANTS | G3 | ok |  | 24/09: ex-fty. T2 Formosa, PI Date 26-Jul, actual receives 07-Jul (switch from PO 26021877).ETA-Kaha 07-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 30-Jul. T2 Libolon, PI Date 22-Jul, actual receives 09-Jul. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903203169 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 16/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 425 | 390 | 35 |  | 82 | 2026-12-09 | 17/09/2026 | 2026-02-09 | 17/09/2026 | 425 | 415 | 10
ADIDAS | 0903203170-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 240 | 15/09/2026 | 240 | SA | SA29/05/2026 | G3K | PANTS | G3 | ok | (22/06/2026) | 14/09: ex-fty 1st Art (TC 10 pcs) 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203170 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-09 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-05-09 | 2026-11-09 | 2026-07-09 | 2026-10-09 | 240 | 240 |  |  |  | 2026-02-09 | 2026-08-09 | 2026-07-09 | 14/09/2026 | 240 | 240 |  |  |  | 27/08/2026 | 2026-02-09 | 28/07/2026 | 15/09/2026 | 240 | 240
ADIDAS | 0903203171-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 347 | 15/10/2026 | 347 | AN | AN26/06/2026 | G3E | PANTS | G3 | (28/08/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903203171 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI | 2026-06-10 | 2026-08-10 |  |  | 347 |  | 347 |  |  | 2026-02-10 | 2026-05-10 |  |  | 347 |  | 347 |  |  | 26/09/2026 | 29/09/2026 |  |  | 347 |  | 347
ADIDAS | 0903205276-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 300 | 30/09/2026 | 300 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516403 | HT SUB PROCESS_V1 | 0903205276 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 21/09/2026 | 22/09/2026 |  |  | 300 |  | 300 |  |  | 18/09/2026 | 19/09/2026 | 13/08/2026 | 26/08/2026 | 300 | 300 |  |  |  | 17/09/2026 | 18/09/2026 | 13/08/2026 | 24/08/2026 | 300 | 300
ADIDAS | 0903208394-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 152 | 2026-12-09 | 152 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 10/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 516342 | HT SUB PROCESS_V1 | 0903208394 KX9855 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-01-09 | 2026-04-09 | 2026-04-09 | 2026-10-09 | 152 | 152 |  |  |  | 29/08/2026 | 2026-02-09 | 13/08/2026 | 21/08/2026 | 152 | 152 |  |  |  | 28/08/2026 | 2026-01-09 | 13/08/2026 | 20/08/2026 | 152 | 152
ADIDAS | 0903208396-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 459 | 23/09/2026 | 459 | SI | SI03/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 18/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208396 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 16/09/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 16/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 459 | 459 |  |  |  | 14/09/2026 | 17/09/2026 | 19/08/2026 | 17/09/2026 | 459 | 459 |  |  |  | 2026-12-09 | 16/09/2026 | 18/08/2026 | 17/09/2026 | 459 | 459
ADIDAS | 0903208397-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 494 | 15/10/2026 | 494 | SI | SI03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903208397 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 494 |  | 494 |  |  | 23/10/2026 | 24/10/2026 | 19/08/2026 | 2026-12-09 | 494 | 490 | 4 |  |  | 22/10/2026 | 23/10/2026 | 18/08/2026 | 2026-02-09 | 494 | 490 | 4
ADIDAS | 0903208398-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 13 | 2026-02-10 | 13 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 680015 | HT SUB PROCESS_V1 | 0903208398 KX9855 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-03-10 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 2026-03-10 | 2026-03-10 |  |  | 13 |  | 13 |  |  | 2026-01-10 | 2026-01-10 | 17/09/2026 | 17/09/2026 | 13 | 13 |  |  |  | 30/09/2026 | 30/09/2026 | 17/09/2026 | 17/09/2026 | 13 | 13
ADIDAS | 0903208399-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 80 | 31/10/2026 | 80 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208399 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 80 |  | 80 |  |  | 27/10/2026 | 28/10/2026 |  |  | 80 |  | 80 |  |  | 26/10/2026 | 27/10/2026 |  |  | 80 |  | 80
ADIDAS | 0903208400-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1268 | 31/10/2026 | 1268 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903208400 KX9855 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 30/10/2026 | 31/10/2026 |  |  | 1268 |  | 1268 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1268 |  | 1268 |  |  | 27/10/2026 | 28/10/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903208407-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 302 | 30/09/2026 | 302 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | 24/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 600000 | HT SUB PROCESS_V1 | 0903208407 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 302 | 292 | 10 |  | 69 | 16/09/2026 | 17/09/2026 | 2026-08-09 | 15/09/2026 | 302 | 296 | 6 |  |  | 15/09/2026 | 16/09/2026 | 2026-08-09 | 14/09/2026 | 302 | 296 | 6
ADIDAS | 0903208408-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 597 | 23/09/2026 | 597 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903208408 IT1469 | 17/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 597 | 582 | 15 |  | 477 | 16/09/2026 | 17/09/2026 | 2026-08-09 | 18/09/2026 | 597 | 597 |  |  |  | 15/09/2026 | 16/09/2026 | 2026-08-09 | 14/09/2026 | 597 | 596 | 1
ADIDAS | 0903208410-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 361 | 2026-07-10 | 361 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516443 | HT SUB PROCESS_V1 | 0903208410 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 361 |  | 361 |  |  | 15/10/2026 | 16/10/2026 | 2026-08-09 | 19/09/2026 | 361 | 358 | 3 |  | 2 | 14/10/2026 | 15/10/2026 | 2026-08-09 | 2026-12-09 | 361 | 358 | 3
ADIDAS | 0903208411-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1107 | 15/10/2026 | 1107 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 678002 | HT SUB PROCESS_V1 | 0903208411 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 1107 |  | 1107 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1107 |  | 1107 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1107 |  | 1107
ADIDAS | 0903208412-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 1026 | 15/10/2026 | 1026 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug.. 834012 | HT SUB PROCESS_V1 | 0903208412 IT1469 | 17/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 1026 |  | 1026 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1026 |  | 1026 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1026 |  | 1026
ADIDAS | 0903208413-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 266 | 15/10/2026 | 266 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, body & mesh actual receives 12-Aug. 688010 | HT SUB PROCESS_V1 | 0903208413 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 266 |  | 266 |  |  | 19/10/2026 | 20/10/2026 |  |  | 266 |  | 266 |  |  | 17/10/2026 | 19/10/2026 |  |  | 266 |  | 266
ADIDAS | 0903208414-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 415 | 14/10/2026 | 415 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903208414 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 415 |  | 415 |  |  | 2026-06-10 | 2026-07-10 |  |  | 415 |  | 415 |  |  | 2026-05-10 | 2026-06-10 |  |  | 415 |  | 415
ADIDAS | 0903208415-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 138 | 31/10/2026 | 138 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650031 | HT SUB PROCESS_V1 | 0903208415 IT1469 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/11/2026 | ADIZERO E TEE |  | SS27-YTI | 24/11/2026 | 25/11/2026 |  |  | 138 |  | 138 |  |  | 20/11/2026 | 23/11/2026 |  |  | 138 |  | 138 |  |  | 19/11/2026 | 20/11/2026 |  |  | 138 |  | 138
ADIDAS | 0903208416-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 143 | 31/10/2026 | 143 | SA | SA03/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Airowes). T2 Y.T.I, body & mesh actual receives 12-Aug. 650034 | HT SUB PROCESS_V1 | 0903208416 IT1469 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/11/2026 | ADIZERO E TEE |  | SS27-YTI | 24/11/2026 | 25/11/2026 |  |  | 143 |  | 143 |  |  | 20/11/2026 | 23/11/2026 |  |  | 143 |  | 143 |  |  | 19/11/2026 | 20/11/2026 |  |  | 143 |  | 143
ADIDAS | 0903208419-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903208419 KG8548 | 17/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/08/2026 | ADIZERO E TEE |  | SS27-YTI | 27/08/2026 | 2026-01-09 | 27/08/2026 | 2026-01-09 | 300 | 300 |  |  |  | 24/08/2026 | 29/08/2026 | 2026-12-08 | 21/08/2026 | 300 | 300 |  |  |  | 21/08/2026 | 28/08/2026 | 2026-11-08 | 21/08/2026 | 300 | 300
ADIDAS | 0903208420-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 301 | 2026-09-09 | 301 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 09/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208420 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 14/08/2026 | ADIZERO E TEE |  | SS27-YTI | 14/08/2026 | 29/08/2026 | 19/08/2026 | 31/08/2026 | 301 | 301 |  |  |  | 2026-12-08 | 27/08/2026 | 2026-12-08 | 2026-12-08 | 301 | 301 |  |  |  | 2026-11-08 | 26/08/2026 | 2026-11-08 | 20/08/2026 | 301 | 301
ADIDAS | 0903208421-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 300 | 2026-09-09 | 300 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 08/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208421 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-01-09 | 31/08/2026 | 2026-04-09 | 300 | 300 |  |  |  | 27/08/2026 | 29/08/2026 | 2026-10-08 | 2026-12-08 | 300 | 300 |  |  |  | 26/08/2026 | 28/08/2026 | 2026-08-08 | 2026-11-08 | 300 | 300
ADIDAS | 0903208423-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 244 | 23/09/2026 | 244 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 05-Aug. 516342 | HT SUB PROCESS_V1 | 0903208423 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 21/09/2026 | 2026-01-09 | 2026-07-09 | 244 | 239 | 5 |  |  | 27/08/2026 | 18/09/2026 | 2026-10-08 | 2026-12-08 | 244 | 244 |  |  |  | 26/08/2026 | 17/09/2026 | 2026-08-08 | 2026-11-08 | 244 | 244
ADIDAS | 0903208424-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 176 | 2026-07-10 | 176 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 814006 | HT SUB PROCESS_V1 | 0903208424 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-07-10 |  |  | 176 |  | 176 |  |  | 2026-05-10 | 2026-05-10 | 2026-12-08 | 26/08/2026 | 176 | 176 |  |  |  | 2026-03-10 | 2026-03-10 | 2026-11-08 | 24/08/2026 | 176 | 176
ADIDAS | 0903208425-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 220 | 2026-07-10 | 220 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 838103 | HT SUB PROCESS_V1 | 0903208425 KG8548 | 17/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-07-10 |  |  | 220 |  | 220 |  |  | 2026-05-10 | 2026-05-10 | 2026-11-08 | 2026-01-09 | 220 | 220 |  |  |  | 2026-03-10 | 2026-03-10 | 2026-10-08 | 31/08/2026 | 220 | 220
ADIDAS | 0903208426-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 616 | 15/10/2026 | 616 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 800187 | HT SUB PROCESS_V1 | 0903208426 KG8548 | 17/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 616 |  | 616 |  |  | 22/10/2026 | 24/10/2026 | 14/08/2026 | 2026-02-09 | 616 | 616 |  |  |  | 21/10/2026 | 23/10/2026 | 13/08/2026 | 2026-02-09 | 616 | 616
ADIDAS | 0903208427-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 248 | 15/10/2026 | 248 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 05-Aug. 839055 | HT SUB PROCESS_V1 | 0903208427 KG8548 | 17/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 248 |  | 248 |  |  | 22/10/2026 | 24/10/2026 | 15/08/2026 | 26/08/2026 | 248 | 248 |  |  |  | 21/10/2026 | 23/10/2026 | 14/08/2026 | 24/08/2026 | 248 | 248
ADIDAS | 0903208428-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 2070 | 15/10/2026 | 2070 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 678002 | HT SUB PROCESS_V1 | 0903208428 KG8548 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 20/10/2026 |  |  | 2070 |  | 2070 |  |  | 14/10/2026 | 17/10/2026 |  |  | 2070 |  | 2070 |  |  | 13/10/2026 | 16/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903208429-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 466 | 23/09/2026 | 466 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 680015 | HT SUB PROCESS_V1 | 0903208429 KG8548 | 17/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 466 | 434 | 32 |  |  | 16/09/2026 | 18/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 465 | 1 |  |  | 15/09/2026 | 17/09/2026 | 2026-12-08 | 21/08/2026 | 466 | 466
ADIDAS | 0903208430-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 648 | 15/10/2026 | 648 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 05-Aug. 659018 | HT SUB PROCESS_V1 | 0903208430 KG8548 | 17/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 648 |  | 648 |  |  | 22/10/2026 | 24/10/2026 | 13/08/2026 | 14/09/2026 | 648 | 648 |  |  |  | 21/10/2026 | 23/10/2026 | 13/08/2026 | 2026-03-09 | 648 | 648
ADIDAS | 0903208431-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 424 | 15/10/2026 | 424 | SA | SA03/07/2026 | G1O | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, Body & mesh actual receives 05-Aug. s650010 | HT SUB PROCESS_V1 | 0903208431 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 424 |  | 424 |  |  | 2026-05-10 | 2026-06-10 | 2026-12-08 | 27/08/2026 | 424 | 424 |  |  |  | 2026-03-10 | 2026-05-10 | 2026-12-08 | 26/08/2026 | 424 | 424
ADIDAS | 0903208432-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 550 | 2026-12-09 | 550 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 11/09: ex-fty (Damco offline). DRC 0090-early shipment customer (PODD Improvement Request). T2 Y.T.I, body & mesh actual receives 18-Aug. 688010 | HT SUB PROCESS_V1 | 0903208432 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/08/2026 | ADIZERO E TEE |  | SS27-YTI | 26/08/2026 | 29/08/2026 | 26/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 21/08/2026 | 27/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 20/08/2026 | 26/08/2026 | 20/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903208433-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 240 | 15/10/2026 | 240 | SA | SA03/07/2026 | G1P | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Y.T.I, Body & mesh actual receives 05-Aug. 688010 | HT SUB PROCESS_V1 | 0903208433 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 27/10/2026 |  |  | 240 |  | 240 |  |  | 22/10/2026 | 24/10/2026 | 15/08/2026 | 22/08/2026 | 240 | 240 |  |  |  | 21/10/2026 | 23/10/2026 | 15/08/2026 | 22/08/2026 | 240 | 240
ADIDAS | 0903208434-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 472 | 14/10/2026 | 472 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & mesh actual receives 05-Aug. 684009 | HT SUB PROCESS_V1 | 0903208434 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 472 |  | 472 |  |  | 2026-12-10 | 13/10/2026 | 18/08/2026 | 29/08/2026 | 472 | 470 | 2 |  |  | 2026-10-10 | 2026-12-10 | 15/08/2026 | 28/08/2026 | 472 | 472
ADIDAS | 0903208435-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1324 | 15/10/2026 | 1324 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 814006 | HT SUB PROCESS_V1 | 0903208435 KG8548 | 17/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-04-11 |  |  | 1324 |  | 1324 |  |  | 30/10/2026 | 2026-02-11 |  |  | 1324 |  | 1324 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1324 |  | 1324
ADIDAS | 0903208436-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 102 | 31/10/2026 | 102 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208436 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 102 |  | 102 |  |  | 13/11/2026 | 16/11/2026 |  |  | 102 |  | 102 |  |  | 2026-12-11 | 13/11/2026 |  |  | 102 |  | 102
ADIDAS | 0903208437-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 163 | 31/10/2026 | 163 | SA | SA03/07/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208437 KG8548 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 163 |  | 163 |  |  | 13/11/2026 | 16/11/2026 |  |  | 163 |  | 163 |  |  | 2026-12-11 | 13/11/2026 |  |  | 163 |  | 163
ADIDAS | 0903208440-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 456 | 15/10/2026 | 456 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 678002 | HT SUB PROCESS_V1 | 0903208440 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 456 |  | 456 |  |  | 2026-02-10 | 2026-03-10 | 24/08/2026 | 2026-04-09 | 456 | 456 |  |  |  | 2026-01-10 | 2026-02-10 | 24/08/2026 | 2026-04-09 | 456 | 456
ADIDAS | 0903208441-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 459 | 15/10/2026 | 459 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 07-Aug. 650010 | HT SUB PROCESS_V1 | 0903208441 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-05-10 |  |  | 459 |  | 459 |  |  | 2026-02-10 | 2026-02-10 | 28/08/2026 | 13/09/2026 | 459 | 459 |  |  |  | 2026-01-10 | 2026-01-10 | 26/08/2026 | 2026-03-09 | 459 | 459
ADIDAS | 0903208442-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 518 | 15/10/2026 | 518 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 688010 | HT SUB PROCESS_V1 | 0903208442 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-05-10 | ADIZERO E TEE |  | SS27-YTI | 2026-05-10 | 2026-06-10 |  |  | 518 |  | 518 |  |  | 2026-02-10 | 2026-03-10 |  |  | 518 |  | 518 |  |  | 2026-01-10 | 2026-02-10 | 31/08/2026 | 14/09/2026 | 518 | 517 | 1
ADIDAS | 0903208443-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 653 | 14/10/2026 | 653 | SI | SI03/07/2026 | G1H | T-SHIRT | G1 | (10/07/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 684009 | HT SUB PROCESS_V1 | 0903208443 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-05-10 |  |  | 653 |  | 653 |  |  | 2026-01-10 | 2026-02-10 |  |  | 653 |  | 653 |  |  | 30/09/2026 | 2026-01-10 | 28/08/2026 | 2026-03-09 | 653 | 652 | 1
ADIDAS | 0903208444-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 102 | 31/10/2026 | 102 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208444 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 102 |  | 102 |  |  | 29/10/2026 | 30/10/2026 |  |  | 102 |  | 102 |  |  | 28/10/2026 | 29/10/2026 |  |  | 102 |  | 102
ADIDAS | 0903208445-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 136 | 31/10/2026 | 136 | SI | SI03/07/2026 | G1K | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208445 KZ2984 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 136 |  | 136 |  |  | 29/10/2026 | 30/10/2026 |  |  | 136 |  | 136 |  |  | 28/10/2026 | 29/10/2026 |  |  | 136 |  | 136
ADIDAS | 0903209735-1 KT4840 | ONIX | 90D | S2408MR1600 | 1046 | 14/10/2026 | 1046 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Far Eatern, PI Date 04-Aug, actul recieves 08-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 684009 | HT SUB PROCESS_V1 | 0903209735 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 1046 |  | 1046 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1046 |  | 1046 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1046 |  | 1046
ADIDAS | 0903209736-1 KT4840 | ONIX | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Far Eatern, PI Date 04-Aug, actul recieves 08-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 650010 | HT SUB PROCESS_V1 | 0903209736 KT4840 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903209737-1 KT4840 | ONIX | 90D | S2408MR1600 | 2722 | 15/10/2026 | 2722 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eatern, PI Date 04-Aug, actul recieves 08-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 678002 | HT SUB PROCESS_V1 | 0903209737 KT4840 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 22/10/2026 |  |  | 2722 |  | 2722 |  |  | 16/10/2026 | 20/10/2026 |  |  | 2722 |  | 2722 |  |  | 15/10/2026 | 19/10/2026 |  |  | 2722 |  | 2722
ADIDAS | 0903209739-1 IN1156 | BLACK | 90D | S2408MR1600 | 324 | 15/09/2026 | 324 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516443 | HT SUB PROCESS_V1 | 0903209739 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 15/09/2026 | 324 | 324 |  |  |  | 29/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 324 | 324 |  |  |  | 28/08/2026 | 29/08/2026 | 22/08/2026 | 2026-11-09 | 324 | 324
ADIDAS | 0903209741-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 23/09/2026 | 300 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209741 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 21/09/2026 | 2026-05-09 | 15/09/2026 | 300 | 221 | 79 |  |  | 29/08/2026 | 18/09/2026 | 24/08/2026 | 2026-03-09 | 300 | 300 |  |  |  | 28/08/2026 | 17/09/2026 | 22/08/2026 | 2026-04-09 | 300 | 300
ADIDAS | 0903209742-1 IN1156 | BLACK | 90D | S2408MR1600 | 319 | 23/09/2026 | 319 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516443 | HT SUB PROCESS_V1 | 0903209742 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 18/09/2026 | 2026-05-09 | 15/09/2026 | 319 | 319 |  |  |  | 29/08/2026 | 16/09/2026 | 24/08/2026 | 2026-03-09 | 319 | 319 |  |  |  | 28/08/2026 | 15/09/2026 | 22/08/2026 | 2026-08-09 | 319 | 319
ADIDAS | 0903209744-1 IN1156 | BLACK | 90D | S2408MR1600 | 3278 | 15/10/2026 | 3278 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 21-Sep, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 678002 | HT SUB PROCESS_V1 | 0903209744 IN1156 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 26/10/2026 |  |  | 3278 |  | 3278 |  |  | 20/10/2026 | 23/10/2026 |  |  | 3278 |  | 3278 |  |  | 19/10/2026 | 22/10/2026 |  |  | 3278 |  | 3278
ADIDAS | 0903209745-1 IN1156 | BLACK | 90D | S2408MR1600 | 145 | 23/09/2026 | 145 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209745 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 145 | 142 | 3 |  |  | 2026-12-09 | 18/09/2026 | 17/09/2026 | 18/09/2026 | 145 | 145 |  |  |  | 2026-11-09 | 17/09/2026 | 17/09/2026 | 17/09/2026 | 145 | 145
ADIDAS | 0903209746-1 IN1156 | BLACK | 90D | S2408MR1600 | 726 | 15/10/2026 | 726 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903209746 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 726 |  | 726 |  |  | 2026-09-10 | 2026-10-10 | 18/09/2026 | 19/09/2026 | 726 | 627 | 99 |  | 460 | 2026-08-10 | 2026-09-10 | 18/09/2026 | 19/09/2026 | 726 | 627 | 99 |  | 460
ADIDAS | 0903209747-1 IN1156 | BLACK | 90D | S2408MR1600 | 6000 | 15/10/2026 | 6000 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 18-Sep. 672027 | HT SUB PROCESS_V1 | 0903209747 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-11-11 | ADIZERO E TEE |  | SS27-YTI | 2026-11-11 | 18/11/2026 |  |  | 6000 |  | 6000 |  |  | 2026-09-11 | 16/11/2026 |  |  | 6000 |  | 6000 |  |  | 2026-06-11 | 13/11/2026 |  |  | 6000 |  | 6000
ADIDAS | 0903209748-1 IN1156 | BLACK | 90D | S2408MR1600 | 1095 | 15/10/2026 | 1095 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 18-Sep. 672027 | HT SUB PROCESS_V1 | 0903209748 IN1156 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 1095 |  | 1095 |  |  | 14/10/2026 | 15/10/2026 |  |  | 1095 |  | 1095 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1095 |  | 1095
ADIDAS | 0903209749-1 IN1156 | BLACK | 90D | S2408MR1600 | 1353 | 15/10/2026 | 1353 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 21-Sep, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 680015 | HT SUB PROCESS_V1 | 0903209749 IN1156 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 20/10/2026 |  |  | 1353 |  | 1353 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1353 |  | 1353 |  |  | 14/10/2026 | 16/10/2026 |  |  | 1353 |  | 1353
ADIDAS | 0903209750-1 IN1156 | BLACK | 90D | S2408MR1600 | 1119 | 15/10/2026 | 1119 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | (Mexico). T2 Far Eastern, PI Date 21-Sep, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 08-Sep. 652001 | HT SUB PROCESS_V1 | 0903209750 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 16/10/2026 |  |  | 1119 |  | 1119 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1119 |  | 1119 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1119 |  | 1119
ADIDAS | 0903209751-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Sep, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 18-Sep. 650010 | HT SUB PROCESS_V1 | 0903209751 IN1156 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-10-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300
ADIDAS | 0903209752-1 IN1156 | BLACK | 90D | S2408MR1600 | 1969 | 31/10/2026 | 1969 | SA | SA07/07/2026 | G1O | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903209752 IN1156 | 21/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-04-11 | ADIZERO E TEE |  | SS27-YTI | 2026-04-11 | 2026-07-11 |  |  | 1969 |  | 1969 |  |  | 2026-02-11 | 2026-05-11 |  |  | 1969 |  | 1969 |  |  | 31/10/2026 | 2026-04-11 |  |  | 1969 |  | 1969
ADIDAS | 0903209755-1 IN1157 | WHITE | 90D | S2408MR1600 | 2425 | 15/10/2026 | 2425 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 18-Sep. 678002 | HT SUB PROCESS_V1 | 0903209755 IN1157 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 28/10/2026 |  |  | 2425 |  | 2425 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2425 |  | 2425 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2425 |  | 2425
ADIDAS | 0903209756-1 IN1157 | WHITE | 90D | S2408MR1600 | 310 | 15/10/2026 | 310 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Far Eastern, PI Date 21-Sep, actual recieves 06-Aug (using fabric from Y.T.I.) T2 Y.T.I, Mesh: ETD 10-Jul, actual recieves 06-Aug. 650010 | HT SUB PROCESS_V1 | 0903209756 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 310 |  | 310 |  |  | 19/10/2026 | 20/10/2026 | 2026-10-09 | 17/09/2026 | 310 | 308 | 2 |  |  | 17/10/2026 | 19/10/2026 | 2026-03-09 | 17/09/2026 | 310 | 308 | 2
ADIDAS | 0903209757-1 IN1157 | WHITE | 90D | S2408MR1600 | 8000 | 30/09/2026 | 8000 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 29/09: ex-fty (Damco offline). DRC 0090-early shipment customer (BTP_19_07_2026 EARLY HOLD SHIPMENT). T2 Far Eastern, PI Date 21-Sep, actual receives 15-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 11-Sep. 688010 | HT SUB PROCESS_V1 | 0903209757 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 22/09/2026 | ADIZERO E TEE |  | SS27-YTI | 22/09/2026 | 2026-01-10 |  |  | 8000 |  | 8000 |  |  | 19/09/2026 | 29/09/2026 |  |  | 8000 |  | 8000 |  |  | 18/09/2026 | 28/09/2026 |  |  | 8000 |  | 8000
ADIDAS | 0903209758-1 IN1157 | WHITE | 90D | S2408MR1600 | 1268 | 14/10/2026 | 1268 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 21-Sep, ETD ?? T2 Fu Hsun, PI Date 03-Aug, actual receives 18-Sep. 684009 | HT SUB PROCESS_V1 | 0903209758 IN1157 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 19/10/2026 | ADIZERO E TEE |  | SS27-YTI | 19/10/2026 | 20/10/2026 |  |  | 1268 |  | 1268 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1268 |  | 1268 |  |  | 15/10/2026 | 16/10/2026 |  |  | 1268 |  | 1268
ADIDAS | 0903209760-1 IN1172 | BLACK | 90D | S2408WR1600 | 302 | 15/09/2026 | 302 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516406 | HT SUB PROCESS_V1 | 0903209760 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 2026-07-09 | 302 | 302 |  |  |  | 29/08/2026 | 31/08/2026 | 29/08/2026 | 2026-09-09 | 302 | 302 |  |  |  | 28/08/2026 | 29/08/2026 | 29/08/2026 | 2026-05-09 | 302 | 302
ADIDAS | 0903209762-1 IN1172 | BLACK | 90D | S2408WR1600 | 300 | 23/09/2026 | 300 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 21/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516403 | HT SUB PROCESS_V1 | 0903209762 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | ADIZERO E TEE |  | SS27-YTI | 16/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 300 | 267 | 33 |  | 18 | 14/09/2026 | 17/09/2026 | 27/08/2026 | 28/08/2026 | 300 | 300 |  |  |  | 2026-12-09 | 16/09/2026 | 26/08/2026 | 28/08/2026 | 300 | 300
ADIDAS | 0903209764-1 IN1172 | BLACK | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 516254 | HT SUB PROCESS_V1 | 0903209764 IN1172 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 349 |  | 349 |  |  | 24/10/2026 | 26/10/2026 |  |  | 349 |  | 349 |  |  | 23/10/2026 | 24/10/2026 |  |  | 349 |  | 349
ADIDAS | 0903209765-1 IN1172 | BLACK | 90D | S2408WR1600 | 2646 | 15/10/2026 | 2646 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 07-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903209765 IN1172 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 29/10/2026 | ADIZERO E TEE |  | SS27-YTI | 29/10/2026 | 2026-02-11 |  |  | 2646 |  | 2646 |  |  | 27/10/2026 | 30/10/2026 |  |  | 2646 |  | 2646 |  |  | 26/10/2026 | 29/10/2026 |  |  | 2646 |  | 2646
ADIDAS | 0903209766-1 IN1172 | BLACK | 90D | S2408WR1600 | 428 | 15/10/2026 | 428 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 29-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 14-Aug. 672027 | HT SUB PROCESS_V1 | 0903209766 IN1172 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 428 |  | 428 |  |  | 13/10/2026 | 14/10/2026 |  |  | 428 |  | 428 |  |  | 2026-12-10 | 13/10/2026 |  |  | 428 |  | 428
ADIDAS | 0903209767-1 IN1172 | BLACK | 90D | S2408WR1600 | 945 | 15/10/2026 | 945 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 07-Aug, ETD ?? 680015 | HT SUB PROCESS_V1 | 0903209767 IN1172 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 945 |  | 945 |  |  | 26/10/2026 | 27/10/2026 |  |  | 945 |  | 945 |  |  | 24/10/2026 | 26/10/2026 |  |  | 945 |  | 945
ADIDAS | 0903209768-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 15/10/2026 | 760 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 07-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903209768 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 760 |  | 760 |  |  | 23/10/2026 | 24/10/2026 |  |  | 760 |  | 760 |  |  | 22/10/2026 | 23/10/2026 |  |  | 760 |  | 760
ADIDAS | 0903209769-1 IN1172 | BLACK | 90D | S2408WR1600 | 677 | 14/10/2026 | 677 | SI | SI07/07/2026 | G1J | T-SHIRT | G1 | (14/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (KN GLT). T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 07-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903209769 IN1172 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 677 |  | 677 |  |  | 23/10/2026 | 24/10/2026 |  |  | 677 |  | 677 |  |  | 22/10/2026 | 23/10/2026 |  |  | 677 |  | 677
ADIDAS | 0903209770-1 IN1172 | BLACK | 90D | S2408WR1600 | 400 | 23/10/2026 | 400 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | 516205 | HT SUB PROCESS_V1 | 0903209770 IN1172 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-09-11 | ADIZERO E TEE |  | SS27-YTI | 2026-09-11 | 2026-09-11 |  |  | 400 |  | 400 |  |  | 2026-05-11 | 2026-05-11 |  |  | 400 |  | 400 |  |  | 2026-04-11 | 2026-04-11 |  |  | 400 |  | 400
ADIDAS | 0903209777-1 KG8547 | ONIX | 90D | S2408WR1600 | 319 | 31/10/2026 | 319 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Airowes). 650034 | HT SUB PROCESS_V1 | 0903209777 KG8547 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 319 |  | 319 |  |  | 24/10/2026 | 26/10/2026 |  |  | 319 |  | 319 |  |  | 23/10/2026 | 24/10/2026 |  |  | 319 |  | 319
ADIDAS | 0903209778-1 KG8547 | ONIX | 90D | S2408WR1600 | 150 | 31/10/2026 | 150 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). 650031 | HT SUB PROCESS_V1 | 0903209778 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 150 |  | 150 |  |  | 24/10/2026 | 26/10/2026 |  |  | 150 |  | 150 |  |  | 23/10/2026 | 24/10/2026 |  |  | 150 |  | 150
ADIDAS | 0903209779-1 KG8547 | ONIX | 90D | S2408WR1600 | 120 | 31/10/2026 | 120 | SI | SI07/07/2026 | G1K | T-SHIRT | G1 | (14/08/2026) | ok | (Cargoport). 650036 | HT SUB PROCESS_V1 | 0903209779 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 120 |  | 120 |  |  | 24/10/2026 | 26/10/2026 |  |  | 120 |  | 120 |  |  | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903209780-1 KG8547 | ONIX | 90D | S2408WR1600 | 278 | 15/10/2026 | 278 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | ok | ok | (Damco offline). T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 688010 | HT SUB PROCESS_V1 | 0903209780 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 278 |  | 278 |  |  | 17/10/2026 | 19/10/2026 |  |  | 278 |  | 278 |  |  | 16/10/2026 | 17/10/2026 |  |  | 278 |  | 278
ADIDAS | 0903209781-1 KG8547 | ONIX | 90D | S2408WR1600 | 532 | 15/10/2026 | 532 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | (KN GLT). T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 650010 | HT SUB PROCESS_V1 | 0903209781 KG8547 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 532 |  | 532 |  |  | 17/10/2026 | 19/10/2026 |  |  | 532 |  | 532 |  |  | 16/10/2026 | 17/10/2026 |  |  | 532 |  | 532
ADIDAS | 0903209782-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | (14/08/2026) | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903209782 KG8547 | 21/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 17/10/2026 | 16/09/2026 | 19/09/2026 | 100 | 53 | 47 |  | 45
ADIDAS | 0903209783-1 KG8547 | ONIX | 90D | S2408WR1600 | 382 | 15/10/2026 | 382 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 960026 | HT SUB PROCESS_V1 | 0903209783 KG8547 | 21/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 382 |  | 382 |  |  | 2026-10-10 | 2026-12-10 |  |  | 382 |  | 382 |  |  | 2026-09-10 | 2026-10-10 |  |  | 382 |  | 382
ADIDAS | 0903209784-1 KG8547 | ONIX | 90D | S2408WR1600 | 902 | 15/10/2026 | 902 | SI | SI07/07/2026 | G1I | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 14-Aug, actual receives 07-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. 678002 | HT SUB PROCESS_V1 | 0903209784 KG8547 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 902 |  | 902 |  |  | 19/10/2026 | 20/10/2026 |  |  | 902 |  | 902 |  |  | 17/10/2026 | 19/10/2026 |  |  | 902 |  | 902
ADIDAS | 0903209785-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 104 | 23/09/2026 | 104 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 22/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 1st Art (TC 10 pcs) 516443 | HT SUB PROCESS_V1 | 0903209785 KX9838 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/09/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 17/09/2026 | 18/09/2026 | 104 | 103 | 1 |  |  | 2026-12-09 | 18/09/2026 | 21/08/2026 | 27/08/2026 | 104 | 104 |  |  |  | 2026-11-09 | 17/09/2026 | 15/08/2026 | 26/08/2026 | 104 | 104
ADIDAS | 0903209787-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 512 | 15/10/2026 | 512 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 659018 | HT SUB PROCESS_V1 | 0903209787 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 27/10/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 512 |  | 512 |  |  | 24/10/2026 | 26/10/2026 | 21/08/2026 | 31/08/2026 | 512 | 512 |  |  |  | 23/10/2026 | 24/10/2026 | 21/08/2026 | 29/08/2026 | 512 | 512
ADIDAS | 0903209788-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 628 | 15/10/2026 | 628 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (KN GLT). T2 Y.T.I, body & mesh actual receives 12-Aug. 650010 | HT SUB PROCESS_V1 | 0903209788 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 2026-02-11 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 2026-02-11 | 2026-02-11 |  |  | 628 |  | 628 |  |  | 30/10/2026 | 30/10/2026 | 21/08/2026 | 31/08/2026 | 628 | 628 |  |  |  | 29/10/2026 | 29/10/2026 | 21/08/2026 | 29/08/2026 | 628 | 628
ADIDAS | 0903209790-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 397 | 31/10/2026 | 397 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903209790 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 24/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 24/11/2026 | 24/11/2026 |  |  | 397 |  | 397 |  |  | 20/11/2026 | 20/11/2026 |  |  | 397 |  | 397 |  |  | 19/11/2026 | 19/11/2026 |  |  | 397 |  | 397
ADIDAS | 0903209791-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 840 | 31/10/2026 | 840 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 659018 | HT SUB PROCESS_V1 | 0903209791 KX9838 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 25/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 25/11/2026 | 26/11/2026 |  |  | 840 |  | 840 |  |  | 23/11/2026 | 24/11/2026 |  |  | 840 |  | 840 |  |  | 20/11/2026 | 23/11/2026 |  |  | 840 |  | 840
ADIDAS | 0903209792-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 114 | 31/10/2026 | 114 | SA | SA07/07/2026 | G1N | T-SHIRT | G1 | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903209792 KX9838 | 21/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 24/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 24/11/2026 | 24/11/2026 |  |  | 114 |  | 114 |  |  | 20/11/2026 | 20/11/2026 |  |  | 114 |  | 114 |  |  | 19/11/2026 | 19/11/2026 |  |  | 114 |  | 114
ADIDAS | 0903209799-1 KG8547 | ONIX | 90D | S2408WR1600 | 1750 | 23/09/2026 | 1750 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 23/09: ex-fty. T2 Y.T.I, body & mesh actual receives 08-Aug. 672027 | HT SUB PROCESS_V1 | 0903209799 KG8547 | 21/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/09/2026 | ADIZERO E TEE |  | SS27-YTI | 21/09/2026 | 23/09/2026 |  |  | 1750 |  | 1750 |  |  | 18/09/2026 | 21/09/2026 | 2026-09-09 | 18/09/2026 | 1750 | 1593 | 157 |  |  | 17/09/2026 | 19/09/2026 | 2026-09-09 | 19/09/2026 | 1750 | 1620 | 130 |  | 28
ADIDAS | 0903209801-1 IN1173 | WHITE | 90D | S2408WR1600 | 349 | 15/10/2026 | 349 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516254 | HT SUB PROCESS_V1 | 0903209801 IN1173 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 349 |  | 349 |  |  | 2026-06-10 | 2026-07-10 | 14/08/2026 | 2026-01-09 | 349 | 349 |  |  |  | 2026-05-10 | 2026-06-10 | 13/08/2026 | 31/08/2026 | 349 | 349
ADIDAS | 0903209802-1 IN1173 | WHITE | 90D | S2408WR1600 | 1288 | 15/10/2026 | 1288 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 678002 | HT SUB PROCESS_V1 | 0903209802 IN1173 | 21/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 1288 |  | 1288 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 2026-04-09 | 1288 | 1288 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 31/08/2026 | 1288 | 1288
ADIDAS | 0903209803-1 IN1173 | WHITE | 90D | S2408WR1600 | 550 | 14/10/2026 | 550 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 680015 | HT SUB PROCESS_V1 | 0903209803 IN1173 | 21/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-10-10 | ADIZERO E TEE |  | SS27-YTI | 2026-10-10 | 13/10/2026 |  |  | 550 |  | 550 |  |  | 2026-08-10 | 2026-10-10 | 15/08/2026 | 31/08/2026 | 550 | 550 |  |  |  | 2026-07-10 | 2026-09-10 | 14/08/2026 | 31/08/2026 | 550 | 550
ADIDAS | 0903209804-1 IN1173 | WHITE | 90D | S2408WR1600 | 1445 | 15/10/2026 | 1445 | SI | SI07/07/2026 | G1P | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & Mesh actual receives 03-Aug. 659018 | HT SUB PROCESS_V1 | 0903209804 IN1173 | 21/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-12-10 |  |  | 1445 |  | 1445 |  |  | 2026-07-10 | 2026-09-10 | 19/08/2026 | 2026-02-09 | 1445 | 1445 |  |  |  | 2026-06-10 | 2026-08-10 | 15/08/2026 | 2026-02-09 | 1445 | 1445
ADIDAS | 0903209805-1 IN1173 | WHITE | 90D | S2408WR1600 | 555 | 15/10/2026 | 555 | SI | SI07/07/2026 | G1G | T-SHIRT | G1 | (14/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 07-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903209805 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 555 |  | 555 |  |  | 19/10/2026 | 20/10/2026 |  |  | 555 |  | 555 |  |  | 17/10/2026 | 19/10/2026 |  |  | 555 |  | 555
ADIDAS | 0903209806-1 IN1173 | WHITE | 90D | S2408WR1600 | 892 | 14/10/2026 | 892 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Y.T.I, Body & Mesh actual receives 03-Aug. 684009 | HT SUB PROCESS_V1 | 0903209806 IN1173 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 2026-10-10 |  |  | 892 |  | 892 |  |  | 2026-07-10 | 2026-08-10 | 19/08/2026 | 27/08/2026 | 892 | 890 | 2 |  |  | 2026-06-10 | 2026-07-10 | 15/08/2026 | 27/08/2026 | 892 | 890 | 2
ADIDAS | 0903209808-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 1211 | 30/09/2026 | 1211 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903209808 IT1462 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 25/09/2026 | ADIZERO E TEE |  | SS27-YTI | 25/09/2026 | 28/09/2026 |  |  | 1211 |  | 1211 |  |  | 23/09/2026 | 25/09/2026 | 2026-07-09 | 19/09/2026 | 1211 | 1203 | 8 |  | 2 | 22/09/2026 | 24/09/2026 | 2026-07-09 | 19/09/2026 | 1211 | 1205 | 6 |  | 2
ADIDAS | 0903209809-1 IT1462 | TEAM ROYAL BLUE | 90D | S2408WR1600 | 451 | 15/10/2026 | 451 | SI | SI07/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 684009 | HT SUB PROCESS_V1 | 0903209809 IT1462 | 21/09/2026 | KAHATEX CIJERAH | PERU | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 451 |  | 451 |  |  | 13/10/2026 | 14/10/2026 | 2026-09-09 | 19/09/2026 | 451 | 441 | 10 |  | 2 | 2026-12-10 | 13/10/2026 | 2026-09-09 | 19/09/2026 | 451 | 441 | 10 |  | 2
ADIDAS | 0903245372-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903245372 IN8707 | 2026-08-10 | KAHATEX CIJERAH | CHILE | SEA | 22/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 15/10/2026 | 17/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903245395-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 1st Art (TC 10 pcs) 680015 | PAD+HT SUB PROCESS_V3 | 0903245395 KA4331 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 2026-12-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-07-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903245423-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903245423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 13/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300
ADIDAS | 0903247791-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 501 | 15/10/2026 | 501 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 630001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903247791 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-08-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 501 |  | 501 |  |  | 2026-05-10 | 2026-06-10 |  |  | 501 |  | 501
ADIDAS | 0903247818-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 118 | 15/10/2026 | 118 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 630001 | PRINT L1 SUB PROCESS_V3 | 0903247818 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 118 |  | 118 |  |  | 2026-02-10 | 2026-03-10 |  |  | 118 |  | 118
ADIDAS | 0903247851-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247851 LG8052 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 13/10/2026 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-09-10 | 2026-10-10 |  |  | 100 |  | 100
ADIDAS | 0903247873-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L1 SUB PROCESS_V3 | 0903247873 LI7657 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 30/09/2026 | MER GR NNTEE M BLACK |  | SS27-MS | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 26/09/2026 | 26/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903247906-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 630001 | PRINT L3 SUB PROCESS_V3 | 0903247906 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 0903247928-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 210 | 15/10/2026 | 210 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L2 SUB PROCESS_V3 | 0903247928 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-09-10 |  |  | 210 |  | 210 |  |  | 2026-03-10 | 2026-06-10 |  |  | 210 |  | 210
ADIDAS | 0903247950-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 377 | 15/10/2026 | 377 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 630001 | PRINT L2 SUB PROCESS_V3 | 0903247950 LI7659 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-10-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-10-10 | 2026-12-10 |  |  | 377 |  | 377 |  |  | 2026-07-10 | 2026-08-10 |  |  | 377 |  | 377
ADIDAS | 0903247975-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 15/10/2026 | 65 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903247975 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 65 |  | 65 |  |  | 2026-09-10 | 2026-10-10 |  |  | 65 |  | 65 |  |  | 2026-06-10 | 2026-07-10 |  |  | 65 |  | 65
ADIDAS | 0903247991-1 IN1159 | BLACK | 90D | S2408MR1601 | 15 | 15/10/2026 | 15 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903247991 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 15 |  | 15 |  |  | 2026-09-10 | 2026-10-10 |  |  | 15 |  | 15 |  |  | 2026-06-10 | 2026-07-10 |  |  | 15 |  | 15
ADIDAS | 0903248016-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 14 | 30/09/2026 | 14 | AN | AN10/07/2026 | G1H | JACKET | G1 | ok | ok | 29/09: ex-fty. T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248016 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 14 |  | 14 |  |  | 19/09/2026 | 21/09/2026 |  |  | 14 |  | 14
ADIDAS | 0903248036-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 12 | 31/10/2026 | 12 | SI | SI10/07/2026 | G2N | T-SHIRT | G2 |  |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903248036 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 30/10/2026 | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI | 30/10/2026 | 30/10/2026 |  |  | 12 |  | 12 |  |  | 27/10/2026 | 27/10/2026 |  |  | 12 |  | 12 |  |  | 24/10/2026 | 24/10/2026 |  |  | 12 |  | 12
ADIDAS | 0903248063-1 LG9660 | COLLEGIATE GREEN/BRIGHT PINK F27 | 90D | S2754WESS703WV | 36 | 30/10/2026 | 36 | AN | AN10/07/2026 | G2R | SHORTS | G2 |  |  | 29/09: ex-fty. Waiting fabric. DRC 0064-T2 Kahatex, PI Date 22-Sep. Waiting fabrIc. T2 Formosa, PI Date 12-Sep. T2 Libolon, PI Date 08-Sep, actual receives 28-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248063 LG9660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 53S WV BER SHO COLLEGIATE GREEN/BRIGHT PINK F27 |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 36 |  | 36 |  |  | 15/10/2026 | 15/10/2026 |  |  | 36 |  | 36
ADIDAS | 0903248578-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 485 | 15/10/2026 | 485 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903248578 KV7863 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 485 |  | 485 |  |  | 24/10/2026 | 26/10/2026 |  |  | 485 |  | 485
ADIDAS | 0903248603-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1020 | 23/10/2026 | 1020 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903248603 JN1948 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/10/2026 | W 3S FT QZ HD |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 1020 |  | 1020 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1020 |  | 1020
ADIDAS | 0903248633-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 256 | 23/10/2026 | 256 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 960026 | PRINT L2 SUB PROCESS_V3 | 0903248633 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 20/10/2026 | 20/10/2026 |  |  | 256 |  | 256 |  |  | 16/10/2026 | 16/10/2026 |  |  | 256 |  | 256
ADIDAS | 0903248979-1 IN1160 | WHITE | 90D | S2408MR1601 | 1173 | 15/10/2026 | 1173 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903248979 IN1160 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 1173 |  | 1173 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1173 |  | 1173 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1173 |  | 1173
ADIDAS | 0903249024-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 383 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249024 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249045-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 337 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903249045 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903249675-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249675 JE6338 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 1150 |  | 1150 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1150 |  | 1150
ADIDAS | 0903249702-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516442 | PAD+HT SUB PROCESS_V3 | 0903249702 IT3474 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 23/10/2026 | 26/10/2026 |  |  | 1795 |  | 1795 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1795 |  | 1795 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249724-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516318 | PAD+HT SUB PROCESS_V3 | 0903249724 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 21/10/2026 | 23/10/2026 |  |  | 300 |  | 300 |  |  | 17/10/2026 | 20/10/2026 |  |  | 300 |  | 300 |  |  | 16/10/2026 | 19/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903249752-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249752 JD1877 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 1610 |  | 1610 |  |  | 2026-03-10 | 2026-07-10 |  |  | 1610 |  | 1610
ADIDAS | 0903249777-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249777 JE6341 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 432 |  | 432 |  |  | 2026-03-10 | 2026-07-10 |  |  | 432 |  | 432
ADIDAS | 0903249802-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 600 | 15/10/2026 | 600 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903249802 JE6338 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 600 |  | 600 |  |  | 2026-01-10 | 2026-03-10 |  |  | 600 |  | 600
ADIDAS | 0903249832-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 299 | 15/10/2026 | 299 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249832 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | M SL WV PT 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 299 |  | 299 |  |  | 2026-12-10 | 13/10/2026 |  |  | 299 |  | 299
ADIDAS | 0903249858-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249858 JM1776 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 575 |  | 575 |  |  | 13/10/2026 | 16/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903249889-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 1795 | 15/10/2026 | 1795 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516205 | PAD+HT SUB PROCESS_V3 | 0903249889 IT3474 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 26/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 26/10/2026 | 28/10/2026 |  |  | 1795 |  | 1795 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1795 |  | 1795 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1795 |  | 1795
ADIDAS | 0903249918-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 600 | 31/10/2026 | 600 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249918 KA0237 | 2026-08-10 | KAHATEX CIJERAH | CHILE | SEA | 2026-09-11 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 600 |  | 600 |  |  | 2026-04-11 | 2026-06-11 |  |  | 600 |  | 600 |  |  | 2026-03-11 | 2026-05-11 |  |  | 600 |  | 600
ADIDAS | 0903249936-1 IN2961 | BLACK | 105D | S2408WR2400 | 460 | 31/10/2026 | 460 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249936 IN2961 | 2026-08-10 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/11/2026 | OTR B TEE BLACK |  | SS27 | 23/11/2026 | 24/11/2026 |  |  | 460 |  | 460 |  |  | 19/11/2026 | 20/11/2026 |  |  | 460 |  | 460 |  |  | 18/11/2026 | 19/11/2026 |  |  | 460 |  | 460
ADIDAS | 0903249960-1 IK7442 | WHITE | 105D | S2408WR2400 | 476 | 31/10/2026 | 476 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903249960 IK7442 | 2026-08-10 | KAHATEX CIJERAH | COLOMBIA | SEA | 2026-03-11 | OTR B TEE WHITE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 476 |  | 476 |  |  | 31/10/2026 | 2026-02-11 |  |  | 476 |  | 476 |  |  | 30/10/2026 | 31/10/2026 |  |  | 476 |  | 476
ADIDAS | 0903249963-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/10/2026 | 300 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903249963 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | M SL WV PT 2 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903249983-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 679 | 31/10/2026 | 679 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 680015 | PAD+HT SUB PROCESS_V3 | 0903249983 LD0277 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 679 |  | 679 |  |  | 13/11/2026 | 17/11/2026 |  |  | 679 |  | 679 |  |  | 2026-12-11 | 16/11/2026 |  |  | 679 |  | 679
ADIDAS | 0903250004-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 23/09/2026 | 300 | SI | SI10/07/2026 | G2Q | SHORTS | G2 | ok | ok | 19/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | PRINT L1 SUB PROCESS_V3 | 0903250004 JG8642 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 23/09/2026 | 16/09/2026 | 19/09/2026 | 300 | 300 |  |  | 5 | 2026-11-09 | 19/09/2026 | 2026-10-09 | 18/09/2026 | 300 | 300
ADIDAS | 0903250015-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 575 | 15/10/2026 | 575 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250015 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 575 |  | 575 |  |  | 13/10/2026 | 16/10/2026 |  |  | 575 |  | 575
ADIDAS | 0903250038-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 326 | 2026-12-09 | 326 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250038 KA0544 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 326 | 326 |  |  |  | 31/08/2026 | 2026-09-09 | 31/08/2026 | 31/08/2026 | 326 | 326
ADIDAS | 0903250069-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 304 | 2026-12-09 | 304 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903250069 KA0546 | 26/08/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-03-09 | 304 | 304
ADIDAS | 0903250091-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 840 | 15/10/2026 | 840 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250091 JD1877 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 840 |  | 840 |  |  | 23/09/2026 | 25/09/2026 |  |  | 840 |  | 840
ADIDAS | 0903250102-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 378 | 15/10/2026 | 378 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250102 JM1775 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-12-10 | M SL WV PT 2 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 378 |  | 378 |  |  | 2026-08-10 | 2026-09-10 |  |  | 378 |  | 378
ADIDAS | 0903250117-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250117 JE6341 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-10-10 |  |  | 828 |  | 828 |  |  | 2026-03-10 | 2026-07-10 |  |  | 828 |  | 828
ADIDAS | 0903250128-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903250128 JM1776 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 15/10/2026 | M SL WV PT 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 342 |  | 342 |  |  | 2026-12-10 | 13/10/2026 |  |  | 342 |  | 342
ADIDAS | 0903250411-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 116 | 15/10/2026 | 116 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 516443 | PRINT L2 SUB PROCESS_V3 | 0903250411 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 19/10/2026 |  |  | 116 |  | 116 |  |  | 15/10/2026 | 15/10/2026 |  |  | 116 |  | 116
ADIDAS | 0903250431-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 157 | 31/10/2026 | 157 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903250431 KU7520 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 157 |  | 157 |  |  | 24/10/2026 | 26/10/2026 |  |  | 157 |  | 157 |  |  | 21/10/2026 | 22/10/2026 |  |  | 157 |  | 157
ADIDAS | 0903250451-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 503 | 31/10/2026 | 503 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903250451 KU7520 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 503 |  | 503 |  |  | 24/10/2026 | 26/10/2026 |  |  | 503 |  | 503 |  |  | 21/10/2026 | 22/10/2026 |  |  | 503 |  | 503
ADIDAS | 0903250476-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 264 | 16/10/2026 | 264 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L2 SUB PROCESS_V3 | 0903250476 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 264 |  | 264 |  |  | 2026-06-10 | 2026-07-10 |  |  | 264 |  | 264
ADIDAS | 0903250503-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903250503 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 107 |  | 107 |  |  | 29/09/2026 | 2026-01-10 |  |  | 107 |  | 107
ADIDAS | 0903250530-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 107 | 15/10/2026 | 107 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903250530 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 107 |  | 107 |  |  | 30/09/2026 | 2026-01-10 |  |  | 107 |  | 107
ADIDAS | 0903250563-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 449 | 15/10/2026 | 449 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (03/08/2026) | 600000 | PRINT L1 SUB PROCESS_V3 | 0903250563 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 449 |  | 449 |  |  | 29/09/2026 | 29/09/2026 |  |  | 449 |  | 449
ADIDAS | 0903250948-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 127 | 31/10/2026 | 127 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903250948 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 24/11/2026 | 24/11/2026 |  |  | 127 |  | 127 |  |  | 20/11/2026 | 20/11/2026 |  |  | 127 |  | 127 |  |  | 19/11/2026 | 19/11/2026 |  |  | 127 |  | 127
ADIDAS | 0903250949-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L1 SUB PROCESS_V3 | 0903250949 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-09-10 | 2026-10-10 |  |  | 100 |  | 100
ADIDAS | 0903250973-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903250973 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 0903250977-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903250977 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | M 3S FT FZ HD |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 372 |  | 372 |  |  | 2026-09-10 | 2026-12-10 |  |  | 372 |  | 372
ADIDAS | 0903250999-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903250999 LE4307 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-10-11 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-10-11 | 13/11/2026 |  |  | 100 |  | 100 |  |  | 2026-05-11 | 2026-10-11 |  |  | 100 |  | 100
ADIDAS | 0903251020-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251020 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | W 3S FT FZ HD |  | SS27 | 23/10/2026 | 24/10/2026 |  |  | 230 |  | 230 |  |  | 20/10/2026 | 21/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903251026-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251026 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | MINI EMB T |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 590 |  | 590 |  |  | 2026-02-10 | 2026-03-10 |  |  | 590 |  | 590 |  |  | 30/09/2026 | 2026-01-10 |  |  | 590 |  | 590
ADIDAS | 0903251047-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903251047 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 396 |  | 396 |  |  | 26/09/2026 | 28/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903251051-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G3D | SHORTS | G3 | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 848012 | PAD+HT SUB PROCESS_V3 | 0903251051 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | RUN IT SHORT BLACK |  | SS27-TI | 30/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 26/09/2026 | 26/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 25/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903251082-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1720 | 15/10/2026 | 1720 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903251082 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-10 | M 3S FT FZ HD |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1720 |  | 1720 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1720 |  | 1720
ADIDAS | 0903251098-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 277 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877).. 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251098 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903251111-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1136 | 15/10/2026 | 1136 | SI | SI10/07/2026 | G3E | PANTS | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251111 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S FT CF PT |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 1136 |  | 1136 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1136 |  | 1136
ADIDAS | 0903251135-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251135 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 1610 |  | 1610 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1610 |  | 1610
ADIDAS | 0903251161-1 KA0246 | BLACK | 105D | S2608WR0902 | 600 | 31/10/2026 | 600 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251161 KA0246 | 2026-08-10 | KAHATEX CIJERAH | PERU | SEA | 2026-02-11 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 600 |  | 600 |  |  | 29/10/2026 | 30/10/2026 |  |  | 600 |  | 600 |  |  | 26/10/2026 | 27/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903251312-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 230 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903251312 KD0738 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903251454-1 KA0246 | BLACK | 105D | S2608WR0902 | 322 | 31/10/2026 | 322 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251454 KA0246 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 322 |  | 322 |  |  | 27/10/2026 | 29/10/2026 |  |  | 322 |  | 322 |  |  | 23/10/2026 | 26/10/2026 |  |  | 322 |  | 322
ADIDAS | 0903251481-1 KA0246 | BLACK | 105D | S2608WR0902 | 636 | 31/10/2026 | 636 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251481 KA0246 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 30/10/2026 | 2026-02-11 |  |  | 636 |  | 636 |  |  | 27/10/2026 | 29/10/2026 |  |  | 636 |  | 636 |  |  | 23/10/2026 | 26/10/2026 |  |  | 636 |  | 636
ADIDAS | 0903251540-1 KA0246 | BLACK | 105D | S2608WR0902 | 491 | 31/10/2026 | 491 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251540 KA0246 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 29/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 491 |  | 491 |  |  | 26/10/2026 | 27/10/2026 |  |  | 491 |  | 491 |  |  | 22/10/2026 | 23/10/2026 |  |  | 491 |  | 491
ADIDAS | 0903251605-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 200 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251605 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251695-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 714 | 15/10/2026 | 714 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251695 JE0052 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/10/2026 | W 3S FT FZ HD |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 714 |  | 714 |  |  | 21/10/2026 | 22/10/2026 |  |  | 714 |  | 714
ADIDAS | 0903251716-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 848 | 31/10/2026 | 848 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 960006 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903251716 KA4914 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | ESS SH 8IN |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 848 |  | 848 |  |  | 17/10/2026 | 19/10/2026 |  |  | 848 |  | 848 |  |  | 2026-12-10 | 13/10/2026 |  |  | 848 |  | 848
ADIDAS | 0903251728-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA10/07/2026 | G2N | T-SHIRT | G2 | (09/08/2026) | ok | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903251728 KA5089 | 26/08/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-06-10 | MINI EMB T |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 602 |  | 602 |  |  | 2026-02-10 | 2026-03-10 |  |  | 602 |  | 602 |  |  | 30/09/2026 | 2026-01-10 |  |  | 602 |  | 602
ADIDAS | 0903251751-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 124 | 15/10/2026 | 124 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3 SUB PROCESS_V3 | 0903251751 IU0217 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-10 | IN RANGE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 124 |  | 124 |  |  | 30/09/2026 | 2026-01-10 | 2026-10-09 | 19/09/2026 | 124 | 72 | 52 |  | 52
ADIDAS | 0903251769-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 890 | 15/10/2026 | 890 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251769 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | W 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 890 |  | 890 |  |  | 19/10/2026 | 20/10/2026 |  |  | 890 |  | 890
ADIDAS | 0903251816-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 800 | 23/10/2026 | 800 | SI | SI10/07/2026 | G3J | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251816 KC5231 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 26/10/2026 | W 3S WV SHO |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 800 |  | 800 |  |  | 22/10/2026 | 23/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903251842-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1686 | 15/10/2026 | 1686 | SA | SA10/07/2026 | G2D | SHORTS | G2 | (20/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903251842 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 1686 |  | 1686 |  |  | 2026-07-10 | 2026-10-10 |  |  | 1686 |  | 1686
ADIDAS | 0903251866-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1760 | 23/10/2026 | 1760 | SA | SA10/07/2026 | G2A | SHORTS | G2 | (20/08/2026) | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903251866 KD4872 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-02-10 | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-07-10 |  |  | 1760 |  | 1760 |  |  | 29/09/2026 | 2026-03-10 |  |  | 1760 |  | 1760
ADIDAS | 0903251870-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 118 | 31/10/2026 | 118 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251870 KV8005 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 16/11/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 118 |  | 118 |  |  | 2026-11-11 | 13/11/2026 |  |  | 118 |  | 118
ADIDAS | 0903251936-1 KT4839 | ONIX | 90D | S2408MR1601 | 566 | 31/10/2026 | 566 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251936 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-11 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 566 |  | 566 |  |  | 29/10/2026 | 30/10/2026 |  |  | 566 |  | 566 |  |  | 26/10/2026 | 27/10/2026 |  |  | 566 |  | 566
ADIDAS | 0903251958-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 469 | 15/10/2026 | 469 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 826010 | PRINT L2+PAD SUB PROCESS_V3 | 0903251958 LC8884 |  | KAHATEX CIJERAH | TURKEY | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 469 |  | 469 |  |  | 2026-10-10 | 2026-12-10 | 26/08/2026 | 17/09/2026 | 469 | 462 | 7
ADIDAS | 0903251993-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 187 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903251993 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903252040-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 324 | 31/10/2026 | 324 | SI | SI10/07/2026 | G3H | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903252040 IN0088 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | RUN IT SHORT DARK BLUE |  | SS27-TI | 2026-03-11 | 2026-05-11 |  |  | 324 |  | 324 |  |  | 30/10/2026 | 2026-02-11 |  |  | 324 |  | 324 |  |  | 29/10/2026 | 31/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903252045-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 229 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 547012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903252045 KY5988 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903252061-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 481 | 15/10/2026 | 481 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252061 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 27/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 481 |  | 481 |  |  | 23/10/2026 | 24/10/2026 |  |  | 481 |  | 481
ADIDAS | 0903252085-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 354 | 15/10/2026 | 354 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252085 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 354 |  | 354 |  |  | 24/10/2026 | 26/10/2026 |  |  | 354 |  | 354
ADIDAS | 0903252116-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 128 | 15/10/2026 | 128 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903252116 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | M ADI RETRO T WHITE |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 128 |  | 128 |  |  | 19/10/2026 | 19/10/2026 | 2026-11-09 | 2026-11-09 | 128 | 110 | 18
ADIDAS | 0903252138-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 141 | 31/10/2026 | 141 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252138 KA0237 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-11 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 141 |  | 141 |  |  | 2026-04-11 | 2026-06-11 |  |  | 141 |  | 141 |  |  | 2026-03-11 | 2026-05-11 |  |  | 141 |  | 141
ADIDAS | 0903252154-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 468 | 31/10/2026 | 468 | SI | SI10/07/2026 | G3H | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903252154 IN0088 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-03-11 | RUN IT SHORT DARK BLUE |  | SS27-TI | 2026-03-11 | 2026-05-11 |  |  | 468 |  | 468 |  |  | 30/10/2026 | 2026-02-11 |  |  | 468 |  | 468 |  |  | 29/10/2026 | 31/10/2026 |  |  | 468 |  | 468
ADIDAS | 0903252175-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252175 JM1775 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | M SL WV PT 2 |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 576 |  | 576 |  |  | 2026-10-10 | 2026-12-10 |  |  | 576 |  | 576
ADIDAS | 0903252182-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 360 | 15/10/2026 | 360 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903252182 KX8875 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 28/09/2026 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 360 |  | 360 |  |  | 24/09/2026 | 24/09/2026 |  |  | 360 |  | 360
ADIDAS | 0903252230-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 826010 | HT SUB PROCESS_V1 | 0903252230 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-03-10 | 2026-05-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903252254-1 IN1156 | BLACK | 90D | S2408MR1600 | 590 | 15/10/2026 | 590 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 826010 | HT SUB PROCESS_V1 | 0903252254 IN1156 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 590 |  | 590 |  |  | 2026-10-10 | 2026-12-10 |  |  | 590 |  | 590 |  |  | 2026-09-10 | 2026-10-10 |  |  | 590 |  | 590
ADIDAS | 0903252275-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 126 | 31/10/2026 | 126 | SI | SI10/07/2026 | G3D | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 826010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252275 KY9383 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA | 2026-02-11 | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 126 |  | 126 |  |  | 29/10/2026 | 30/10/2026 |  |  | 126 |  | 126 |  |  | 26/10/2026 | 27/10/2026 |  |  | 126 |  | 126
ADIDAS | 0903252439-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252439 LI7657 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 30/09/2026 | MER GR NNTEE M BLACK |  | SS27-MS | 30/09/2026 | 30/09/2026 |  |  | 101 |  | 101 |  |  | 26/09/2026 | 26/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903252473-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L2 SUB PROCESS_V3 | 0903252473 LI7658 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 117 |  | 117 |  |  | 2026-03-10 | 2026-03-10 |  |  | 117 |  | 117
ADIDAS | 0903252503-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 101 | 15/10/2026 | 101 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (09/08/2026) | ok | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903252503 LI7656 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/10/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 14/10/2026 | 14/10/2026 |  |  | 101 |  | 101 |  |  | 2026-10-10 | 2026-10-10 |  |  | 101 |  | 101
ADIDAS | 0903252539-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 117 | 15/10/2026 | 117 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | (Mexico). 652001 | PRINT L2 SUB PROCESS_V3 | 0903252539 LI7659 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-10-10 | 2026-12-10 |  |  | 117 |  | 117 |  |  | 2026-07-10 | 2026-08-10 |  |  | 117 |  | 117
ADIDAS | 0903252570-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 230 | 2026-12-09 | 230 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 1st Art (TC 10 pcs) 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903252570 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-09 | MINI EMB T |  | SS27 | 2026-08-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-04-09 | 2026-09-09 | 2026-10-09 | 2026-11-09 | 230 | 230 |  |  |  | 2026-02-09 | 2026-07-09 | 2026-05-09 | 2026-10-09 | 230 | 230
ADIDAS | 0903252595-1 IN1172 | BLACK | 90D | S2408WR1600 | 264 | 31/10/2026 | 264 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903252595 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | ADIZERO E TEE |  | SS27-YTI | 2026-10-11 | 2026-11-11 |  |  | 264 |  | 264 |  |  | 2026-06-11 | 2026-09-11 |  |  | 264 |  | 264 |  |  | 2026-05-11 | 2026-06-11 |  |  | 264 |  | 264
ADIDAS | 0903252620-1 IN1157 | WHITE | 90D | S2408MR1600 | 1027 | 31/10/2026 | 1027 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903252620 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 18/11/2026 | ADIZERO E TEE |  | SS27-YTI | 18/11/2026 | 19/11/2026 |  |  | 1027 |  | 1027 |  |  | 16/11/2026 | 17/11/2026 |  |  | 1027 |  | 1027 |  |  | 13/11/2026 | 16/11/2026 |  |  | 1027 |  | 1027
ADIDAS | 0903252644-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/10/2026 | 140 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252644 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 20/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 140 |  | 140 |  |  | 16/10/2026 | 17/10/2026 |  |  | 140 |  | 140
ADIDAS | 0903253096-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 201 | 15/10/2026 | 201 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903253096 KV0458 |  | KAHATEX CIJERAH | THAILAND | SEA | 21/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 21/10/2026 | 22/10/2026 |  |  | 201 |  | 201 |  |  | 17/10/2026 | 19/10/2026 |  |  | 201 |  | 201
ADIDAS | 0903253164-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1421 | 15/10/2026 | 1421 | SA | SA10/07/2026 | G2O | JACKET | G2 | ok | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253164 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1421 |  | 1421 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1421 |  | 1421
ADIDAS | 0903253174-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253174 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | M SL WV PT 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 288 |  | 288 |  |  | 2026-12-10 | 13/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903253193-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1909 | 15/10/2026 | 1909 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903253193 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 13/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 13/10/2026 | 16/10/2026 |  |  | 1909 |  | 1909 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1909 |  | 1909
ADIDAS | 0903253200-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 267 | 31/10/2026 | 267 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903253200 LD0278 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 26/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 26/11/2026 | 27/11/2026 |  |  | 267 |  | 267 |  |  | 23/11/2026 | 24/11/2026 |  |  | 267 |  | 267 |  |  | 20/11/2026 | 23/11/2026 |  |  | 267 |  | 267
ADIDAS | 0903253221-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253221 LE8188 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253229-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253229 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 20/10/2026 | M SL WV PT 2 |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 600 |  | 600 |  |  | 16/10/2026 | 17/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253259-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 650 | 15/10/2026 | 650 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253259 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 15/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 650 |  | 650 |  |  | 2026-12-10 | 13/10/2026 |  |  | 650 |  | 650
ADIDAS | 0903253286-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253286 JE0052 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 20/10/2026 | W 3S FT FZ HD |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 600 |  | 600 |  |  | 16/10/2026 | 17/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253287-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 200 | 15/10/2026 | 200 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903253287 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 14/10/2026 |  |  | 200 |  | 200 |  |  | 2026-10-10 | 2026-10-10 |  |  | 200 |  | 200 |  |  | 2026-09-10 | 2026-09-10 |  |  | 200 |  | 200
ADIDAS | 0903253302-1 KT4840 | ONIX | 90D | S2408MR1600 | 181 | 31/10/2026 | 181 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253302 KT4840 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 18/11/2026 | ADIZERO E TEE |  | SS27-YTI | 18/11/2026 | 19/11/2026 |  |  | 181 |  | 181 |  |  | 16/11/2026 | 17/11/2026 |  |  | 181 |  | 181 |  |  | 13/11/2026 | 16/11/2026 |  |  | 181 |  | 181
ADIDAS | 0903253312-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 374 | 15/10/2026 | 374 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253312 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 374 |  | 374 |  |  | 16/10/2026 | 17/10/2026 |  |  | 374 |  | 374
ADIDAS | 0903253327-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 600 | 15/10/2026 | 600 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253327 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 15/10/2026 | M SL WV PT 2 |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 600 |  | 600 |  |  | 2026-12-10 | 14/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903253337-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 105 | 15/10/2026 | 105 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903253337 KX0123 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 22/10/2026 | M ADI RETRO T WHITE |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 105 |  | 105 |  |  | 19/10/2026 | 19/10/2026 | 2026-11-09 | 18/09/2026 | 105 | 99 | 6
ADIDAS | 0903253341-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 582 | 15/10/2026 | 582 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253341 JE6341 |  | KAHATEX CIJERAH | UKRAINE | SEA | 13/10/2026 | M 3S FT FZ HD |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 582 |  | 582 |  |  | 2026-09-10 | 2026-12-10 |  |  | 582 |  | 582
ADIDAS | 0903253374-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G3E | PANTS | G3 | (20/08/2026) | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253374 JD5302 |  | KAHATEX CIJERAH | UKRAINE | SEA | 26/10/2026 | W 3S FT CF PT |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 1000 |  | 1000 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1000 |  | 1000
ADIDAS | 0903253396-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903253396 JE6419 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-01-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 558 |  | 558 |  |  | 28/09/2026 | 29/09/2026 |  |  | 558 |  | 558
ADIDAS | 0903253447-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 100 | 15/10/2026 | 100 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | Request Re-route (06_092026 Wrong Tradeco model & wrong currency 1st Batch - LOs). T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 512110 | PRINT L2+HT SUB PROCESS_V3 | 0903253447 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 14/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-10-10 |  |  | 100 |  | 100 |  |  | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100
ADIDAS | 0903253455-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 191 | 15/10/2026 | 191 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 516342 | PAD+HT SUB PROCESS_V3 | 0903253455 LD0277 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 191 |  | 191 |  |  | 2026-02-10 | 2026-03-10 |  |  | 191 |  | 191 |  |  | 2026-01-10 | 2026-02-10 |  |  | 191 |  | 191
ADIDAS | 0903253468-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 331 | 23/10/2026 | 331 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512106 | PRINT L2+PAD SUB PROCESS_V3 | 0903253468 LC8884 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 15/10/2026 | M RESORT T BLACK |  | SS27 | 15/10/2026 | 15/10/2026 |  |  | 331 |  | 331 |  |  | 2026-12-10 | 2026-12-10 | 26/08/2026 | 16/09/2026 | 331 | 317 | 14
ADIDAS | 0903253478-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 266 | 31/10/2026 | 266 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 516342 | HT SUB PROCESS_V1 | 0903253478 KX9838 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 24/11/2026 | 25/11/2026 |  |  | 266 |  | 266 |  |  | 20/11/2026 | 23/11/2026 |  |  | 266 |  | 266 |  |  | 19/11/2026 | 20/11/2026 |  |  | 266 |  | 266
ADIDAS | 0903253530-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 216 | 23/10/2026 | 216 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 960026 | PRINT L2 SUB PROCESS_V3 | 0903253530 LI7658 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-12-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-12-10 | 13/10/2026 |  |  | 216 |  | 216 |  |  | 2026-08-10 | 2026-09-10 |  |  | 216 |  | 216
ADIDAS | 0903253532-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 20 | 15/10/2026 | 20 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 826010 | PRINT L2+HT SUB PROCESS_V3 | 0903253532 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA | 13/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 20 |  | 20 |  |  | 2026-09-10 | 2026-10-10 |  |  | 20 |  | 20 |  |  | 2026-08-10 | 2026-09-10 |  |  | 20 |  | 20
ADIDAS | 0903253536-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 542 | 31/10/2026 | 542 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253536 IT1467 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 17/11/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 17/11/2026 | 19/11/2026 |  |  | 542 |  | 542 |  |  | 2026-12-11 | 16/11/2026 |  |  | 542 |  | 542 |  |  | 2026-09-11 | 2026-11-11 |  |  | 542 |  | 542
ADIDAS | 0903253551-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 637 | 30/09/2026 | 637 | SA | SA10/07/2026 | G2B | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 1st Art (TC 10 pcs) 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253551 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 637 |  | 637 |  |  | 19/09/2026 | 21/09/2026 | 2026-04-09 | 16/09/2026 | 637 | 605 | 32
ADIDAS | 0903253557-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 268 | 15/10/2026 | 268 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253557 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 17/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 268 |  | 268 |  |  | 14/10/2026 | 16/10/2026 |  |  | 268 |  | 268
ADIDAS | 0903253577-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 347 | 30/09/2026 | 347 | SA | SA10/07/2026 | G2B | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253577 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 347 |  | 347 |  |  | 19/09/2026 | 21/09/2026 | 31/08/2026 | 16/09/2026 | 347 | 330 | 17
ADIDAS | 0903253578-1 IN1157 | WHITE | 90D | S2408MR1600 | 1664 | 31/10/2026 | 1664 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903253578 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 19/11/2026 | ADIZERO E TEE |  | SS27-YTI | 19/11/2026 | 21/11/2026 |  |  | 1664 |  | 1664 |  |  | 17/11/2026 | 19/11/2026 |  |  | 1664 |  | 1664 |  |  | 16/11/2026 | 18/11/2026 |  |  | 1664 |  | 1664
ADIDAS | 0903253594-1 KG8547 | ONIX | 90D | S2408WR1600 | 194 | 31/10/2026 | 194 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903253594 KG8547 |  | KAHATEX CIJERAH | MOROCCO | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 194 |  | 194 |  |  | 24/10/2026 | 26/10/2026 |  |  | 194 |  | 194 |  |  | 23/10/2026 | 24/10/2026 |  |  | 194 |  | 194
ADIDAS | 0903253608-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253608 IT1467 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 17/11/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 17/11/2026 | 19/11/2026 |  |  | 102 |  | 102 |  |  | 2026-12-11 | 16/11/2026 |  |  | 102 |  | 102 |  |  | 2026-09-11 | 2026-11-11 |  |  | 102 |  | 102
ADIDAS | 0903253610-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 351 | 30/09/2026 | 351 | AN | AN10/07/2026 | G2B | T-SHIRT | G2 | ok | ok | 25/09: ex-fty 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253610 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M FB NOVELTY T WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 351 |  | 351 |  |  | 19/09/2026 | 21/09/2026 | 28/08/2026 | 16/09/2026 | 351 | 343 | 8
ADIDAS | 0903253635-1 IN8707 | BLACK | 105D | S2408WR1601A | 781 | 31/10/2026 | 781 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253635 IN8707 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 24/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 781 |  | 781 |  |  | 21/10/2026 | 23/10/2026 |  |  | 781 |  | 781 |  |  | 17/10/2026 | 20/10/2026 |  |  | 781 |  | 781
ADIDAS | 0903253654-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 382 | 23/10/2026 | 382 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253654 LF1392 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-10-11 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 382 |  | 382 |  |  | 2026-05-11 | 2026-11-11 |  |  | 382 |  | 382
ADIDAS | 0903253694-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903253694 JC8238 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 1500 |  | 1500 |  |  | 25/09/2026 | 26/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903253780-1 IN1173 | WHITE | 90D | S2408WR1600 | 152 | 31/10/2026 | 152 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903253780 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | ADIZERO E TEE |  | SS27-YTI | 23/10/2026 | 24/10/2026 |  |  | 152 |  | 152 |  |  | 21/10/2026 | 22/10/2026 |  |  | 152 |  | 152 |  |  | 20/10/2026 | 21/10/2026 |  |  | 152 |  | 152
ADIDAS | 0903253801-1 KG8547 | ONIX | 90D | S2408WR1600 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903253801 KG8547 |  | KAHATEX CIJERAH | ISRAEL | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 26/10/2026 | 27/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903253810-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903253810 KX8875 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/09/2026 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 28/09/2026 | 28/09/2026 |  |  | 368 |  | 368 |  |  | 24/09/2026 | 24/09/2026 |  |  | 368 |  | 368
ADIDAS | 0903253860-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 163 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253860 KY5988 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253870-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 936 | 15/10/2026 | 936 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | IMPROVE. T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 31-Jul. 516204 | PAD+HT SUB PROCESS_V3 | 0903253870 IT3474 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 21/10/2026 | 23/10/2026 |  |  | 936 |  | 936 |  |  | 17/10/2026 | 20/10/2026 |  |  | 936 |  | 936 |  |  | 16/10/2026 | 19/10/2026 |  |  | 936 |  | 936
ADIDAS | 0903253904-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1150 | 15/10/2026 | 1150 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253904 JE6338 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | M 3S FT FZ HD |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1150 |  | 1150 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1150 |  | 1150
ADIDAS | 0903253915-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 118 | 31/10/2026 | 118 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903253915 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 118 |  | 118 |  |  | 13/11/2026 | 16/11/2026 |  |  | 118 |  | 118 |  |  | 2026-12-11 | 13/11/2026 |  |  | 118 |  | 118
ADIDAS | 0903253948-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253948 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253967-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 828 | 15/10/2026 | 828 | SA | SA10/07/2026 | G2O | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253967 JE6341 |  | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | M 3S FT FZ HD |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 828 |  | 828 |  |  | 2026-12-10 | 13/10/2026 |  |  | 828 |  | 828
ADIDAS | 0903253995-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1610 | 15/10/2026 | 1610 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253995 JD1877 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1610 |  | 1610 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1610 |  | 1610
ADIDAS | 0903254003-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 425 | 23/10/2026 | 425 | SI | SI10/07/2026 | G1F | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254003 KV8005 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-10-11 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 425 |  | 425 |  |  | 2026-05-11 | 2026-11-11 |  |  | 425 |  | 425
ADIDAS | 0903254029-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1232 | 23/10/2026 | 1232 | SA | SA10/07/2026 | G3E | PANTS | G3 | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254029 JW7178 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/10/2026 | W 3S FT OH PT |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 1232 |  | 1232 |  |  | 26/10/2026 | 27/10/2026 |  |  | 1232 |  | 1232
ADIDAS | 0903254049-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 230 | 15/10/2026 | 230 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254049 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | W 3S FT FZ HD |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 230 |  | 230 |  |  | 15/10/2026 | 16/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903254053-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 116 | 15/10/2026 | 116 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 848016 | PRINT L2+HT SUB PROCESS_V3 | 0903254053 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 14/10/2026 |  |  | 116 |  | 116 |  |  | 2026-10-10 | 2026-10-10 |  |  | 116 |  | 116 |  |  | 2026-09-10 | 2026-09-10 |  |  | 116 |  | 116
ADIDAS | 0903254056-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 576 | 15/10/2026 | 576 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 10-Aug, inspect ok 10-Aug. 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254056 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 13/10/2026 | M SL WV PT 2 |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 576 |  | 576 |  |  | 2026-09-10 | 2026-10-10 |  |  | 576 |  | 576
ADIDAS | 0903254089-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903254089 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 396 |  | 396 |  |  | 2026-05-10 | 2026-07-10 |  |  | 396 |  | 396
ADIDAS | 0903254114-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 990 | 23/10/2026 | 990 | SI | SI10/07/2026 | G2M | SWEATSHIRT | G2 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254114 KD4874 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | M 3S FT SWT |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 990 |  | 990 |  |  | 2026-12-10 | 13/10/2026 |  |  | 990 |  | 990
ADIDAS | 0903254125-1 IN1156 | BLACK | 90D | S2408MR1600 | 335 | 31/10/2026 | 335 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903254125 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-11 | ADIZERO E TEE |  | SS27-YTI | 2026-09-11 | 2026-10-11 |  |  | 335 |  | 335 |  |  | 2026-05-11 | 2026-06-11 |  |  | 335 |  | 335 |  |  | 2026-04-11 | 2026-05-11 |  |  | 335 |  | 335
ADIDAS | 0903254175-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1182 | 15/10/2026 | 1182 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877).. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254175 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 1182 |  | 1182 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1182 |  | 1182
ADIDAS | 0903254182-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 100 | 31/10/2026 | 100 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903254182 KG3234 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-05-11 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 2026-05-11 | 2026-09-11 |  |  | 100 |  | 100 |  |  | 2026-02-11 | 2026-04-11 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 2026-03-11 |  |  | 100 |  | 100
ADIDAS | 0903254188-1 IN1157 | WHITE | 90D | S2408MR1600 | 621 | 31/10/2026 | 621 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254188 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 16/11/2026 | ADIZERO E TEE |  | SS27-YTI | 16/11/2026 | 17/11/2026 |  |  | 621 |  | 621 |  |  | 2026-12-11 | 13/11/2026 |  |  | 621 |  | 621 |  |  | 2026-11-11 | 2026-12-11 |  |  | 621 |  | 621
ADIDAS | 0903254192-1 KT4839 | ONIX | 90D | S2408MR1601 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254192 KT4839 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 275 |  | 275 |  |  | 28/10/2026 | 29/10/2026 |  |  | 275 |  | 275 |  |  | 24/10/2026 | 26/10/2026 |  |  | 275 |  | 275
ADIDAS | 0903254214-1 IN1156 | BLACK | 90D | S2408MR1600 | 572 | 31/10/2026 | 572 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848024 | HT SUB PROCESS_V1 | 0903254214 IN1156 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-10-11 | ADIZERO E TEE |  | SS27-YTI | 2026-10-11 | 2026-11-11 |  |  | 572 |  | 572 |  |  | 2026-06-11 | 2026-09-11 |  |  | 572 |  | 572 |  |  | 2026-05-11 | 2026-06-11 |  |  | 572 |  | 572
ADIDAS | 0903254241-1 IN1173 | WHITE | 90D | S2408WR1600 | 217 | 31/10/2026 | 217 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848024 | HT SUB PROCESS_V1 | 0903254241 IN1173 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 217 |  | 217 |  |  | 23/10/2026 | 24/10/2026 |  |  | 217 |  | 217 |  |  | 22/10/2026 | 23/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903254247-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 31/10/2026 | 512 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254247 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 27/11/2026 | 28/11/2026 |  |  | 512 |  | 512 |  |  | 24/11/2026 | 25/11/2026 |  |  | 512 |  | 512 |  |  | 23/11/2026 | 24/11/2026 |  |  | 512 |  | 512
ADIDAS | 0903254266-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254266 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 20/11/2026 | 21/11/2026 |  |  | 100 |  | 100 |  |  | 17/11/2026 | 18/11/2026 |  |  | 100 |  | 100 |  |  | 2026-12-11 | 13/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903254325-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903254325 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 340 |  | 340 |  |  | 29/09/2026 | 2026-01-10 |  |  | 340 |  | 340
ADIDAS | 0903254326-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1080 | 31/10/2026 | 1080 | SI | SI10/07/2026 | G3K | SHORTS | G3 | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254326 JZ7709 | 2026-08-10 | KAHATEX CIJERAH | HONGKONG | SEA | 2026-10-11 | ADI365/// SHO M BLACK |  | SS27-TRAX | 2026-10-11 | 2026-12-11 |  |  | 1080 |  | 1080 |  |  | 2026-05-11 | 2026-09-11 |  |  | 1080 |  | 1080 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1080 |  | 1080
ADIDAS | 0903254356-1 KZ3049 | BLACK | 90D | S2762LHMEDR109W | 330 | 15/10/2026 | 330 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903254356 KZ3049 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER GR GFCTP W BLACK |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 330 |  | 330 |  |  | 2026-03-10 | 2026-03-10 |  |  | 330 |  | 330
ADIDAS | 0903254368-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G2N | T-SHIRT | G2 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254368 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | J FOOTBALL T |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 100 |  | 100 |  |  | 14/10/2026 | 14/10/2026 | 2026-11-09 | 17/09/2026 | 100 | 81 | 19
ADIDAS | 0903254387-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 372 | 15/10/2026 | 372 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903254387 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 372 |  | 372 |  |  | 30/09/2026 | 2026-01-10 |  |  | 372 |  | 372
ADIDAS | 0903254402-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 130 | 15/10/2026 | 130 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903254402 KV0458 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 21/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 21/10/2026 | 22/10/2026 |  |  | 130 |  | 130 |  |  | 17/10/2026 | 19/10/2026 |  |  | 130 |  | 130
ADIDAS | 0903254520-1 IN1156 | BLACK | 90D | S2408MR1600 | 422 | 31/10/2026 | 422 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903254520 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-10-11 | ADIZERO E TEE |  | SS27-YTI | 2026-10-11 | 2026-11-11 |  |  | 422 |  | 422 |  |  | 2026-06-11 | 2026-09-11 |  |  | 422 |  | 422 |  |  | 2026-05-11 | 2026-06-11 |  |  | 422 |  | 422
ADIDAS | 0903254581-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 457 | 15/10/2026 | 457 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903254581 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 20/10/2026 |  |  | 457 |  | 457 |  |  | 15/10/2026 | 16/10/2026 |  |  | 457 |  | 457
ADIDAS | 0903254614-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 380 | 15/10/2026 | 380 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L3 SUB PROCESS_V3 | 0903254614 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/09/2026 | MER KA GFCTP W BLACK |  | SS27-MS | 29/09/2026 | 30/09/2026 |  |  | 380 |  | 380 |  |  | 25/09/2026 | 26/09/2026 |  |  | 380 |  | 380
ADIDAS | 0903254634-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 355 | 31/10/2026 | 355 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254634 KY4155 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 31/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 355 |  | 355 |  |  | 28/10/2026 | 30/10/2026 |  |  | 355 |  | 355
ADIDAS | 0903254722-1 LF0723 | BLACK | 105D | S2754MAS511B | 505 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254722 LF0723 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903254741-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903254741 JD1881 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-05-10 | M 3S FT TC PT |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1203 |  | 1203 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1203 |  | 1203
ADIDAS | 0903254769-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 271 | 31/10/2026 | 271 | SI | SI10/07/2026 | G2D | SHORTS | G2 | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254769 LD0908 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/10/2026 | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX | 20/10/2026 | 21/10/2026 |  |  | 271 |  | 271 |  |  | 16/10/2026 | 17/10/2026 |  |  | 271 |  | 271 |  |  | 13/10/2026 | 14/10/2026 |  |  | 271 |  | 271
ADIDAS | 0903254804-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 353 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254804 LE8181 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903254860-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 229 | 15/10/2026 | 229 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903254860 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | M ADI RETRO T BLACK |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 229 |  | 229 |  |  | 19/10/2026 | 19/10/2026 | 2026-11-09 | 2026-11-09 | 229 | 201 | 28
ADIDAS | 0903254861-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 312 | 15/10/2026 | 312 | SI | SI10/07/2026 | G3H | JACKET | G3 | ok | ok | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254861 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 3S FT FZ HD |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 312 |  | 312 |  |  | 15/10/2026 | 16/10/2026 |  |  | 312 |  | 312
ADIDAS | 0903254872-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 558 | 15/10/2026 | 558 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 547012 | EMBRO SUB PROCESS_V1 | 0903254872 JE6417 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-08-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 558 |  | 558 |  |  | 2026-05-10 | 2026-07-10 |  |  | 558 |  | 558
ADIDAS | 0903254887-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 108 | 15/10/2026 | 108 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254887 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 108 |  | 108 |  |  | 2026-05-10 | 2026-06-10 |  |  | 108 |  | 108
ADIDAS | 0903254895-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 263 | 31/10/2026 | 263 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903254895 LD0292 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-10-11 | 2026-11-11 |  |  | 263 |  | 263 |  |  | 2026-05-11 | 2026-06-11 |  |  | 263 |  | 263 |  |  | 2026-04-11 | 2026-05-11 |  |  | 263 |  | 263
ADIDAS | 0903254914-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 1750 | 15/10/2026 | 1750 | AN | AN10/07/2026 | G1L | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 09-Jun, ETD 10-Aug, ETA-Kaha 21-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254914 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 23/10/2026 | 29/10/2026 |  |  | 1750 |  | 1750 |  |  | 20/10/2026 | 26/10/2026 |  |  | 1750 |  | 1750
ADIDAS | 0903254921-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G3B | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254921 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-10 | M SL WV PT 2 |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 288 |  | 288 |  |  | 2026-08-10 | 2026-09-10 |  |  | 288 |  | 288
ADIDAS | 0903254929-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 233 | 31/10/2026 | 233 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254929 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 233 |  | 233 |  |  | 18/11/2026 | 18/11/2026 |  |  | 233 |  | 233 |  |  | 13/11/2026 | 13/11/2026 |  |  | 233 |  | 233
ADIDAS | 0903254967-1 KT4839 | ONIX | 90D | S2408MR1601 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512108 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254967 KT4839 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 100 |  | 100 |  |  | 28/10/2026 | 29/10/2026 |  |  | 100 |  | 100 |  |  | 24/10/2026 | 26/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903254980-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 619 | 15/10/2026 | 619 | SI | SI10/07/2026 | G1H | JACKET | G1 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254980 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/10/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 619 |  | 619 |  |  | 13/10/2026 | 15/10/2026 |  |  | 619 |  | 619
ADIDAS | 0903255005-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 494 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255005 LF0721 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255009-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 389 | 15/10/2026 | 389 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255009 LG8051 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-05-10 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 2026-05-10 | 2026-05-10 |  |  | 389 |  | 389 |  |  | 2026-01-10 | 2026-01-10 |  |  | 389 |  | 389
ADIDAS | 0903255022-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 135 | 15/10/2026 | 135 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903255022 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 15/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 135 |  | 135 |  |  | 2026-12-10 | 13/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903255023-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1203 | 2026-09-09 | 1203 | SA | SA10/07/2026 | G3G | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255023 IB8688 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-04-09 | 29/08/2026 | 2026-05-09 | 1203 | 1203 |  |  |  | 27/08/2026 | 2026-01-09 | 22/08/2026 | 2026-04-09 | 1203 | 1203
ADIDAS | 0903255038-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903255038 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 169 |  | 169 |  |  | 2026-06-10 | 2026-07-10 |  |  | 169 |  | 169
ADIDAS | 0903255050-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255050 IZ0443 | 2026-11-08 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-02-09 | 2026-09-09 | 276 | 276
ADIDAS | 0903255078-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 161 | 15/10/2026 | 161 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903255078 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 161 |  | 161 |  |  | 2026-10-10 | 2026-12-10 |  |  | 161 |  | 161 |  |  | 2026-09-10 | 2026-10-10 |  |  | 161 |  | 161
ADIDAS | 0903255083-1 IL7232 | BLACK | 105D | S2408MR3202 | 468 | 31/10/2026 | 468 | SI | SI10/07/2026 | G3H | SHORTS | G3 | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 512102 | PAD+HT SUB PROCESS_V3 | 0903255083 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-02-11 | RUN IT SHORT BLACK |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 468 |  | 468 |  |  | 29/10/2026 | 30/10/2026 |  |  | 468 |  | 468 |  |  | 28/10/2026 | 29/10/2026 |  |  | 468 |  | 468
ADIDAS | 0903255103-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 276 | 2026-12-09 | 276 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903255103 KA0546 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-03-09 | 2026-09-09 | 276 | 276 |  |  |  | 28/08/2026 | 2026-09-09 | 13/08/2026 | 2026-03-09 | 276 | 276
ADIDAS | 0903255107-1 KT4840 | ONIX | 90D | S2408MR1600 | 770 | 31/10/2026 | 770 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903255107 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/11/2026 | ADIZERO E TEE |  | SS27-YTI | 19/11/2026 | 20/11/2026 |  |  | 770 |  | 770 |  |  | 17/11/2026 | 18/11/2026 |  |  | 770 |  | 770 |  |  | 16/11/2026 | 17/11/2026 |  |  | 770 |  | 770
ADIDAS | 0903255118-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 344 | 15/10/2026 | 344 | SI | SI10/07/2026 | G2I | SWEATSHIRT | G2 | ok | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903255118 LG8052 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 344 |  | 344 |  |  | 2026-09-10 | 2026-10-10 |  |  | 344 |  | 344
ADIDAS | 0903255151-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2C | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 600000 | PRINT L1 SUB PROCESS_V3 | 0903255151 LI7657 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 30/09/2026 | MER GR NNTEE M BLACK |  | SS27-MS | 30/09/2026 | 30/09/2026 |  |  | 300 |  | 300 |  |  | 26/09/2026 | 26/09/2026 |  |  | 300 |  | 300
ADIDAS | 0903255192-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 492 | 15/10/2026 | 492 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | T2 Formosa, PI Date 08-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255192 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/10/2026 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 492 |  | 492 |  |  | 24/10/2026 | 26/10/2026 |  |  | 492 |  | 492
ADIDAS | 0903255212-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1894 | 15/10/2026 | 1894 | SI | SI10/07/2026 | G3B | PANTS | G3 | (10/08/2026) | ok | Waiting fabric. T2 Formosa, PI Date 08-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255212 LI8103 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 29/10/2026 | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 1894 |  | 1894 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1894 |  | 1894
ADIDAS | 0903255230-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 287 | 15/10/2026 | 287 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903255230 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-10-10 | 2026-12-10 |  |  | 287 |  | 287 |  |  | 2026-07-10 | 2026-08-10 |  |  | 287 |  | 287
ADIDAS | 0903255239-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 16/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255239 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-09-10 | 2026-12-10 |  |  | 120 |  | 120 |  |  | 2026-06-10 | 2026-08-10 |  |  | 120 |  | 120
ADIDAS | 0903255277-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 234 | 15/10/2026 | 234 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903255277 LI7658 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-09-10 |  |  | 234 |  | 234 |  |  | 2026-03-10 | 2026-06-10 |  |  | 234 |  | 234
ADIDAS | 0903255316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 365 | 15/10/2026 | 365 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L2 SUB PROCESS_V3 | 0903255316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-09-10 |  |  | 365 |  | 365 |  |  | 2026-03-10 | 2026-06-10 |  |  | 365 |  | 365
ADIDAS | 0903255344-1 IN1173 | WHITE | 90D | S2408WR1600 | 2980 | 15/10/2026 | 2980 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903255344 IN1173 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 22/10/2026 | ADIZERO E TEE |  | SS27-YTI | 22/10/2026 | 27/10/2026 |  |  | 2980 |  | 2980 |  |  | 20/10/2026 | 24/10/2026 |  |  | 2980 |  | 2980 |  |  | 19/10/2026 | 23/10/2026 |  |  | 2980 |  | 2980
ADIDAS | 0903255352-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 180 | 15/10/2026 | 180 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903255352 LI7659 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 180 |  | 180 |  |  | 2026-06-10 | 2026-07-10 |  |  | 180 |  | 180
ADIDAS | 0903255377-1 IN1157 | WHITE | 90D | S2408MR1600 | 3100 | 15/10/2026 | 3100 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 960006 | HT SUB PROCESS_V1 | 0903255377 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-09-10 | ADIZERO E TEE |  | SS27-YTI | 2026-09-10 | 14/10/2026 |  |  | 3100 |  | 3100 |  |  | 2026-07-10 | 2026-12-10 | 2026-09-09 | 19/09/2026 | 3100 | 1022 | 2078 |  | 18 | 2026-06-10 | 2026-10-10 | 2026-04-09 | 19/09/2026 | 3100 | 1657 | 1443 |  | 625
ADIDAS | 0903255384-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 204 | 15/10/2026 | 204 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516443 | PRINT L2 SUB PROCESS_V3 | 0903255384 LI7658 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 204 |  | 204 |  |  | 2026-03-10 | 2026-03-10 |  |  | 204 |  | 204
ADIDAS | 0903255415-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 516343 | PRINT L2 SUB PROCESS_V3 | 0903255415 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-07-10 |  |  | 300 |  | 300
ADIDAS | 0903255423-1 IN1159 | BLACK | 90D | S2408MR1601 | 3310 | 15/10/2026 | 3310 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. DRC 0051-T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255423 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 20/10/2026 | 26/10/2026 |  |  | 3310 |  | 3310 |  |  | 16/10/2026 | 22/10/2026 |  |  | 3310 |  | 3310 |  |  | 13/10/2026 | 19/10/2026 |  |  | 3310 |  | 3310
ADIDAS | 0903255441-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 960 | 15/10/2026 | 960 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L3 SUB PROCESS_V3 | 0903255441 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 16/10/2026 |  |  | 960 |  | 960 |  |  | 2026-12-10 | 13/10/2026 |  |  | 960 |  | 960
ADIDAS | 0903255459-1 JZ7774 | TECH INDIGO S20 | 90D | S2608MR0902 | 1200 | 31/10/2026 | 1200 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 1st Art (TC 10 pcs) 834012 | PAD+HT SUB PROCESS_V3 | 0903255459 JZ7774 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 28/11/2026 | Run Ess 21 S M TECH INDIGO S20 |  | SS27-TRAX | 28/11/2026 | 2026-02-12 |  |  | 1200 |  | 1200 |  |  | 25/11/2026 | 27/11/2026 |  |  | 1200 |  | 1200 |  |  | 24/11/2026 | 26/11/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903255467-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 1080 | 15/10/2026 | 1080 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516400 | PRINT L1 SUB PROCESS_V3 | 0903255467 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 17/10/2026 | 19/10/2026 |  |  | 1080 |  | 1080 |  |  | 14/10/2026 | 15/10/2026 |  |  | 1080 |  | 1080
ADIDAS | 0903255507-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 23/10/2026 | 200 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255507 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 30/10/2026 | 31/10/2026 |  |  | 200 |  | 200 |  |  | 27/10/2026 | 28/10/2026 |  |  | 200 |  | 200 |  |  | 23/10/2026 | 24/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903255515-1 LF0718 | BLACK | 105D | S2754MAS512B | 512 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255515 LF0718 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255565-1 IN1173 | WHITE | 90D | S2408WR1600 | 219 | 31/10/2026 | 219 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 512102 | HT SUB PROCESS_V1 | 0903255565 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 219 |  | 219 |  |  | 23/10/2026 | 24/10/2026 |  |  | 219 |  | 219 |  |  | 22/10/2026 | 23/10/2026 |  |  | 219 |  | 219
ADIDAS | 0903255580-1 KT4839 | ONIX | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255580 KT4839 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 30/10/2026 | 31/10/2026 |  |  | 125 |  | 125 |  |  | 27/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 23/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903255584-1 IN1156 | BLACK | 90D | S2408MR1600 | 543 | 31/10/2026 | 543 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903255584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-11-11 | ADIZERO E TEE |  | SS27-YTI | 2026-11-11 | 2026-12-11 |  |  | 543 |  | 543 |  |  | 2026-09-11 | 2026-10-11 |  |  | 543 |  | 543 |  |  | 2026-06-11 | 2026-09-11 |  |  | 543 |  | 543
ADIDAS | 0903255589-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903255589 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 300 |  | 300 |  |  | 2026-09-10 | 2026-10-10 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-09-10 |  |  | 300 |  | 300
ADIDAS | 0903255616-1 IN1172 | BLACK | 90D | S2408WR1600 | 4574 | 15/10/2026 | 4574 | SI | SI10/07/2026 | G1I | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903255616 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 20/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-12-10 | 17/10/2026 |  |  | 4574 |  | 4574 |  |  | 2026-10-10 | 16/10/2026 |  |  | 4574 |  | 4574
ADIDAS | 0903255630-1 KA4331 | BLACK | 90D | S2608MR0902 | 1734 | 15/10/2026 | 1734 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903255630 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 14/10/2026 | 17/10/2026 |  |  | 1734 |  | 1734 |  |  | 2026-10-10 | 14/10/2026 |  |  | 1734 |  | 1734 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1734 |  | 1734
ADIDAS | 0903255643-1 IN1173 | WHITE | 90D | S2408WR1600 | 4544 | 15/10/2026 | 4544 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903255643 IN1173 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 2026-02-11 |  |  | 4544 |  | 4544 |  |  | 24/10/2026 | 30/10/2026 |  |  | 4544 |  | 4544 |  |  | 23/10/2026 | 29/10/2026 |  |  | 4544 |  | 4544
ADIDAS | 0903255648-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 251 | 31/10/2026 | 251 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255648 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/11/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 21/11/2026 | 23/11/2026 |  |  | 251 |  | 251 |  |  | 18/11/2026 | 18/11/2026 |  |  | 251 |  | 251
ADIDAS | 0903255693-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1026 | 15/10/2026 | 1026 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516204 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255693 KF5295 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-10 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 2026-10-10 | 13/10/2026 |  |  | 1026 |  | 1026 |  |  | 2026-07-10 | 2026-09-10 |  |  | 1026 |  | 1026 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1026 |  | 1026
ADIDAS | 0903255699-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 509 | 15/10/2026 | 509 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255699 KV7863 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 29/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 509 |  | 509 |  |  | 26/10/2026 | 27/10/2026 |  |  | 509 |  | 509
ADIDAS | 0903255746-1 IN1157 | WHITE | 90D | S2408MR1600 | 414 | 31/10/2026 | 414 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903255746 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 414 |  | 414 |  |  | 13/11/2026 | 16/11/2026 |  |  | 414 |  | 414 |  |  | 2026-12-11 | 13/11/2026 |  |  | 414 |  | 414
ADIDAS | 0903255776-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1452 | 15/10/2026 | 1452 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255776 JE6414 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 16/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 16/10/2026 | 19/10/2026 |  |  | 1452 |  | 1452 |  |  | 13/10/2026 | 15/10/2026 |  |  | 1452 |  | 1452
ADIDAS | 0903255794-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 367 | 23/10/2026 | 367 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903255794 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 367 |  | 367 |  |  | 16/10/2026 | 17/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903255800-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 149 | 15/10/2026 | 149 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 512102 | PRINT L2+HT SUB PROCESS_V3 | 0903255800 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 149 |  | 149 |  |  | 2026-10-10 | 2026-12-10 |  |  | 149 |  | 149 |  |  | 2026-09-10 | 2026-10-10 |  |  | 149 |  | 149
ADIDAS | 0903255801-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1140 | 15/10/2026 | 1140 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255801 JE6338 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-08-10 | M 3S FT FZ HD |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 1140 |  | 1140 |  |  | 2026-05-10 | 2026-07-10 |  |  | 1140 |  | 1140
ADIDAS | 0903255833-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 918 | 15/10/2026 | 918 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255833 JM1775 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 15/10/2026 | M SL WV PT 2 |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 918 |  | 918 |  |  | 2026-12-10 | 13/10/2026 |  |  | 918 |  | 918
ADIDAS | 0903255882-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1546 | 15/10/2026 | 1546 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255882 JE6341 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M 3S FT FZ HD |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1546 |  | 1546 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1546 |  | 1546
ADIDAS | 0903255908-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903255908 JE6419 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-05-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 1278 |  | 1278 |  |  | 2026-01-10 | 2026-03-10 |  |  | 1278 |  | 1278
ADIDAS | 0903255912-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255912 KF5295 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA | 16/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 16/10/2026 | 20/10/2026 |  |  | 1967 |  | 1967 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1967 |  | 1967
ADIDAS | 0903255968-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 1967 | 15/10/2026 | 1967 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516442 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255968 KF5295 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 13/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 13/10/2026 | 16/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-09-10 | 13/10/2026 |  |  | 1967 |  | 1967 |  |  | 2026-06-10 | 2026-09-10 |  |  | 1967 |  | 1967
ADIDAS | 0903255969-1 IN1156 | BLACK | 90D | S2408MR1600 | 1798 | 31/10/2026 | 1798 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 834012 | HT SUB PROCESS_V1 | 0903255969 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 14/11/2026 | ADIZERO E TEE |  | SS27-YTI | 14/11/2026 | 17/11/2026 |  |  | 1798 |  | 1798 |  |  | 2026-12-11 | 13/11/2026 |  |  | 1798 |  | 1798 |  |  | 2026-11-11 | 2026-12-11 |  |  | 1798 |  | 1798
ADIDAS | 0903255971-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 803 | 31/10/2026 | 803 | SI | SI10/07/2026 | G2D | SHORTS | G2 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255971 KA0247 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 23/10/2026 | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX | 23/10/2026 | 26/10/2026 |  |  | 803 |  | 803 |  |  | 20/10/2026 | 22/10/2026 |  |  | 803 |  | 803 |  |  | 16/10/2026 | 19/10/2026 |  |  | 803 |  | 803
ADIDAS | 0903255977-1 LF0718 | BLACK | 105D | S2754MAS512B | 453 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 03-Sep. T2 Teijin Nantong, PI Date 06-Sep, actual receives 31-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255977 LF0718 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903255999-1 IN1173 | WHITE | 90D | S2408WR1600 | 1056 | 31/10/2026 | 1056 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903255999 IN1173 |  | KAHATEX CIJERAH | ISRAEL | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI | 27/10/2026 | 28/10/2026 |  |  | 1056 |  | 1056 |  |  | 24/10/2026 | 26/10/2026 |  |  | 1056 |  | 1056 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1056 |  | 1056
ADIDAS | 0903256009-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903256009 KA0237 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-11-11 | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX | 2026-11-11 | 14/11/2026 |  |  | 1250 |  | 1250 |  |  | 2026-06-11 | 2026-11-11 |  |  | 1250 |  | 1250 |  |  | 2026-05-11 | 2026-10-11 |  |  | 1250 |  | 1250
ADIDAS | 0903256022-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256022 JM1776 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | M SL WV PT 2 |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 896 |  | 896 |  |  | 19/10/2026 | 21/10/2026 |  |  | 896 |  | 896
ADIDAS | 0903256042-1 IK7442 | WHITE | 105D | S2408WR2400 | 2500 | 31/10/2026 | 2500 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903256042 IK7442 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-11 | OTR B TEE WHITE |  | SS27 | 2026-05-11 | 2026-09-11 |  |  | 2500 |  | 2500 |  |  | 2026-03-11 | 2026-05-11 |  |  | 2500 |  | 2500 |  |  | 2026-02-11 | 2026-04-11 |  |  | 2500 |  | 2500
ADIDAS | 0903256045-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 181 | 15/10/2026 | 181 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 848024 | PRINT L2+HT SUB PROCESS_V3 | 0903256045 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 181 |  | 181 |  |  | 2026-10-10 | 2026-12-10 |  |  | 181 |  | 181 |  |  | 2026-09-10 | 2026-10-10 |  |  | 181 |  | 181
ADIDAS | 0903256052-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 107 | 23/10/2026 | 107 | AN | AN10/07/2026 | G2E | T-SHIRT | G2 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256052 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-10-10 | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L | 2026-10-10 | 2026-12-10 |  |  | 107 |  | 107 |  |  | 2026-07-10 | 2026-08-10 |  |  | 107 |  | 107
ADIDAS | 0903256056-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 455 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256056 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256058-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 564 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256058 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256065-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1251 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256065 KQ8640 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256137-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 516244 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256137 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903256160-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 154 | 31/10/2026 | 154 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256160 KG8553 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA | 16/11/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 16/11/2026 | 17/11/2026 |  |  | 154 |  | 154 |  |  | 2026-11-11 | 2026-12-11 |  |  | 154 |  | 154 |  |  | 2026-06-11 | 2026-09-11 |  |  | 154 |  | 154
ADIDAS | 0903256216-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 160 | 23/10/2026 | 160 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903256216 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 20/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 20/10/2026 | 21/10/2026 |  |  | 160 |  | 160 |  |  | 16/10/2026 | 17/10/2026 |  |  | 160 |  | 160
ADIDAS | 0903256347-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 896 | 15/10/2026 | 896 | SI | SI10/07/2026 | G3E | PANTS | G3 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256347 JD5302 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/10/2026 | W 3S FT CF PT |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 896 |  | 896 |  |  | 21/10/2026 | 22/10/2026 |  |  | 896 |  | 896
ADIDAS | 0903256411-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2P | SHORTS | G2 | (20/08/2026) | ok | 848024 | EMBRO SUB PROCESS_V1 | 0903256411 JE6417 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-07-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1278 |  | 1278 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1278 |  | 1278
ADIDAS | 0903256435-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1230 | 15/10/2026 | 1230 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903256435 JE6341 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-03-10 | M 3S FT FZ HD |  | SS27 | 2026-03-10 | 2026-07-10 |  |  | 1230 |  | 1230 |  |  | 30/09/2026 | 2026-03-10 |  |  | 1230 |  | 1230
ADIDAS | 0903256461-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 792 | 15/10/2026 | 792 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256461 JM1776 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 21/10/2026 | M SL WV PT 2 |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 792 |  | 792 |  |  | 17/10/2026 | 19/10/2026 |  |  | 792 |  | 792
ADIDAS | 0903256486-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 113 | 15/10/2026 | 113 | AN | AN10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903256486 LC8882 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 22/10/2026 | M ADI RETRO T BLACK |  | SS27 | 22/10/2026 | 22/10/2026 |  |  | 113 |  | 113 |  |  | 19/10/2026 | 19/10/2026 |  |  | 113 |  | 113
ADIDAS | 0903256510-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1210 | 15/10/2026 | 1210 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256510 JM1775 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/10/2026 | M SL WV PT 2 |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 1210 |  | 1210 |  |  | 16/10/2026 | 19/10/2026 |  |  | 1210 |  | 1210
ADIDAS | 0903256620-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 610 | 14/10/2026 | 610 | AN | AN10/07/2026 | G3D | PANTS | G3 | ok | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256620 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 19/10/2026 | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 610 |  | 610 |  |  | 15/10/2026 | 16/10/2026 |  |  | 610 |  | 610
ADIDAS | 0903256659-1 KT4840 | ONIX | 90D | S2408MR1600 | 200 | 31/10/2026 | 200 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256659 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/11/2026 | ADIZERO E TEE |  | SS27-YTI | 19/11/2026 | 20/11/2026 |  |  | 200 |  | 200 |  |  | 17/11/2026 | 18/11/2026 |  |  | 200 |  | 200 |  |  | 16/11/2026 | 17/11/2026 |  |  | 200 |  | 200
ADIDAS | 0903256662-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 557 | 31/10/2026 | 557 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 12-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256662 KY4155 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 557 |  | 557 |  |  | 28/10/2026 | 30/10/2026 |  |  | 557 |  | 557
ADIDAS | 0903256720-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 302 | 31/10/2026 | 302 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256720 KY6510 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA | 2026-06-11 | M 3S CHELSEA B7 |  | SS27 | 2026-06-11 | 2026-06-11 |  |  | 302 |  | 302 |  |  | 2026-03-11 | 2026-03-11 |  |  | 302 |  | 302
ADIDAS | 0903256755-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 209 | 15/10/2026 | 209 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256755 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 209 |  | 209 |  |  | 29/09/2026 | 2026-01-10 |  |  | 209 |  | 209
ADIDAS | 0903256760-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1957 | 31/10/2026 | 1957 | SI | SI10/07/2026 | G1J | SHORTS | G1 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256760 KY6510 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-11 | M 3S CHELSEA B7 |  | SS27 | 2026-06-11 | 2026-10-11 |  |  | 1957 |  | 1957 |  |  | 2026-03-11 | 2026-05-11 |  |  | 1957 |  | 1957
ADIDAS | 0903256777-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 280 | 23/10/2026 | 280 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903256777 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 21/10/2026 | 21/10/2026 |  |  | 280 |  | 280 |  |  | 17/10/2026 | 17/10/2026 |  |  | 280 |  | 280
ADIDAS | 0903256779-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 119 | 15/10/2026 | 119 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903256779 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 119 |  | 119 |  |  | 29/09/2026 | 2026-01-10 |  |  | 119 |  | 119
ADIDAS | 0903256801-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 121 | 15/10/2026 | 121 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (09/09/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903256801 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-05-10 |  |  | 121 |  | 121 |  |  | 29/09/2026 | 2026-01-10 |  |  | 121 |  | 121
ADIDAS | 0903256825-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 132 | 15/10/2026 | 132 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516443 | PRINT L2 SUB PROCESS_V3 | 0903256825 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-03-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-03-10 | 2026-05-10 |  |  | 132 |  | 132 |  |  | 30/09/2026 | 2026-01-10 |  |  | 132 |  | 132
ADIDAS | 0903256829-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 364 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256829 LE8188 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903256846-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 216 | 15/10/2026 | 216 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903256846 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 216 |  | 216 |  |  | 29/09/2026 | 30/09/2026 |  |  | 216 |  | 216
ADIDAS | 0903256847-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 210 | 15/10/2026 | 210 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256847 JE6346 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | M 3S FT TC PT |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 210 |  | 210 |  |  | 26/09/2026 | 28/09/2026 |  |  | 210 |  | 210
ADIDAS | 0903256851-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 288 | 15/10/2026 | 288 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256851 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 288 |  | 288 |  |  | 14/10/2026 | 16/10/2026 |  |  | 288 |  | 288
ADIDAS | 0903256866-1 KA0246 | BLACK | 105D | S2608WR0902 | 230 | 31/10/2026 | 230 | SI | SI10/07/2026 | G2D | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256866 KA0246 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 19/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 19/10/2026 | 20/10/2026 |  |  | 230 |  | 230 |  |  | 15/10/2026 | 16/10/2026 |  |  | 230 |  | 230 |  |  | 2026-12-10 | 13/10/2026 |  |  | 230 |  | 230
ADIDAS | 0903256871-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 124 | 15/10/2026 | 124 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903256871 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-02-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 124 |  | 124 |  |  | 29/09/2026 | 30/09/2026 |  |  | 124 |  | 124
ADIDAS | 0903256876-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 266 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848024 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903256876 KY5988 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903256878-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 299 | 15/10/2026 | 299 | SA | SA10/07/2026 | G3D | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903256878 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-03-10 | M 3S FT TC PT |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 299 |  | 299 |  |  | 30/09/2026 | 2026-01-10 |  |  | 299 |  | 299
ADIDAS | 0903256884-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 342 | 15/10/2026 | 342 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256884 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 27/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 342 |  | 342 |  |  | 23/10/2026 | 24/10/2026 |  |  | 342 |  | 342
ADIDAS | 0903256891-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 269 | 15/10/2026 | 269 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 516343 | PRINT L2 SUB PROCESS_V3 | 0903256891 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 20/10/2026 |  |  | 269 |  | 269 |  |  | 15/10/2026 | 16/10/2026 |  |  | 269 |  | 269
ADIDAS | 0903256901-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256901 LF1392 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 107 |  | 107 |  |  | 2026-06-10 | 2026-09-10 |  |  | 107 |  | 107
ADIDAS | 0903256903-1 LE8187 | BLACK | 105D | S2754MAS513 | 212 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256903 LE8187 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903256918-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 31/10/2026 | 148 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903256918 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 148 |  | 148 |  |  | 13/11/2026 | 16/11/2026 |  |  | 148 |  | 148 |  |  | 2026-12-11 | 13/11/2026 |  |  | 148 |  | 148
ADIDAS | 0903256955-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 219 | 15/10/2026 | 219 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903256955 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 21/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 219 |  | 219 |  |  | 17/10/2026 | 17/10/2026 |  |  | 219 |  | 219
ADIDAS | 0903256972-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 123 | 15/10/2026 | 123 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 512102 | PRINT L2+PAD SUB PROCESS_V3 | 0903256972 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 123 |  | 123 |  |  | 2026-10-10 | 2026-12-10 | 16/09/2026 | 16/09/2026 | 123 | 118 | 5
ADIDAS | 0903257022-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257022 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 120 |  | 120 |  |  | 2026-06-10 | 2026-09-10 |  |  | 120 |  | 120
ADIDAS | 0903257051-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 144 | 31/10/2026 | 144 | SI | SI10/07/2026 | G3J | SHORTS | G3 |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257051 KC5231 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 26/10/2026 | W 3S WV SHO |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 144 |  | 144 |  |  | 22/10/2026 | 23/10/2026 |  |  | 144 |  | 144
ADIDAS | 0903257161-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 176 | 15/10/2026 | 176 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257161 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 176 |  | 176 |  |  | 26/09/2026 | 28/09/2026 |  |  | 176 |  | 176
ADIDAS | 0903257172-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 119 | 15/10/2026 | 119 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257172 LG8055 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 119 |  | 119 |  |  | 2026-02-10 | 2026-02-10 |  |  | 119 |  | 119
ADIDAS | 0903257177-1 IS1413 | BLACK | 60D | S2425M405 | 1203 | 2026-12-09 | 1203 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 11/09: ex-fty 834012 | PRINT L3 SUB PROCESS_V3 | 0903257177 IS1413 | 26/08/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | IN RANGE |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-10-09 | 2026-11-09 | 1203 | 1203 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-03-09 | 2026-11-09 | 1203 | 1203
ADIDAS | 0903257182-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 336 | 15/10/2026 | 336 | SA | SA10/07/2026 | G2T | JACKET | G2 | ok | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257182 JE6338 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | M 3S FT FZ HD |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 336 |  | 336 |  |  | 2026-01-10 | 2026-03-10 |  |  | 336 |  | 336
ADIDAS | 0903257188-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 246 | 23/10/2026 | 246 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | (09/09/2026) | ok | 960026 | PRINT L2 SUB PROCESS_V3 | 0903257188 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/10/2026 | MER KA GFSWT M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 246 |  | 246 |  |  | 2026-12-10 | 2026-12-10 |  |  | 246 |  | 246
ADIDAS | 0903257198-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 404 | 15/10/2026 | 404 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257198 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 404 |  | 404 |  |  | 2026-02-10 | 2026-03-10 |  |  | 404 |  | 404
ADIDAS | 0903257203-1 HK7309 | BLACK | 45D | F2225M402 | 1653 | 2026-09-09 | 1653 | SA | SA10/07/2026 | G1N,G1P | SWEATSHIRT | G1 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257203 HK7309 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 1653 | 1653 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-10-09 | 1653 | 1653
ADIDAS | 0903257220-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257220 KU7520 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA | 28/10/2026 | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX | 28/10/2026 | 29/10/2026 |  |  | 180 |  | 180 |  |  | 24/10/2026 | 26/10/2026 |  |  | 180 |  | 180 |  |  | 21/10/2026 | 22/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257227-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 101 | 15/10/2026 | 101 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | (09/09/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257227 LG8056 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-10 | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS | 2026-06-10 | 2026-06-10 |  |  | 101 |  | 101 |  |  | 2026-02-10 | 2026-02-10 |  |  | 101 |  | 101
ADIDAS | 0903257245-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 180 | 31/10/2026 | 180 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 848016 | HT SUB PROCESS_V1 | 0903257245 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 180 |  | 180 |  |  | 27/10/2026 | 28/10/2026 |  |  | 180 |  | 180 |  |  | 26/10/2026 | 27/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903257251-1 IN1159 | BLACK | 90D | S2408MR1601 | 162 | 31/10/2026 | 162 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257251 IN1159 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-10-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 162 |  | 162 |  |  | 2026-05-11 | 2026-05-11 |  |  | 162 |  | 162 |  |  | 2026-02-11 | 2026-02-11 |  |  | 162 |  | 162
ADIDAS | 0903257252-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 848 | 15/10/2026 | 848 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257252 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-09-10 | 2026-12-10 |  |  | 848 |  | 848 |  |  | 2026-06-10 | 2026-08-10 |  |  | 848 |  | 848
ADIDAS | 0903257264-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257264 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 25/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 25/11/2026 | 26/11/2026 |  |  | 100 |  | 100 |  |  | 23/11/2026 | 24/11/2026 |  |  | 100 |  | 100 |  |  | 20/11/2026 | 23/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903257280-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1098 | 15/10/2026 | 1098 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903257280 IB8686 |  | KAHATEX CIJERAH | ISRAEL | SEA | 2026-01-10 | ESS TEE |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 1098 |  | 1098 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1098 |  | 1098
ADIDAS | 0903257284-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 169 | 15/10/2026 | 169 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257284 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 169 |  | 169 |  |  | 2026-12-10 | 2026-12-10 |  |  | 169 |  | 169
ADIDAS | 0903257292-1 JC8238 | BLACK/WHITE | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903257292 JC8238 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 29/09/2026 | W LIN SJ T |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 195 |  | 195 |  |  | 25/09/2026 | 26/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903257307-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 177 | 15/10/2026 | 177 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257307 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 177 |  | 177 |  |  | 2026-09-10 | 2026-10-10 |  |  | 177 |  | 177
ADIDAS | 0903257329-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257329 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-02-10 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 2026-02-10 | 2026-07-10 |  |  | 100 |  | 100 |  |  | 29/09/2026 | 2026-03-10 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 30/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903257350-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 140 | 15/10/2026 | 140 | SA | SA10/07/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257350 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-06-10 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 140 |  | 140 |  |  | 2026-02-10 | 2026-03-10 |  |  | 140 |  | 140 |  |  | 2026-01-10 | 2026-02-10 |  |  | 140 |  | 140
ADIDAS | 0903257370-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 302 | 15/10/2026 | 302 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257370 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-01-10 | W 3S WV SHO |  | SS27 | 2026-01-10 | 2026-02-10 |  |  | 302 |  | 302 |  |  | 28/09/2026 | 29/09/2026 |  |  | 302 |  | 302
ADIDAS | 0903257378-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 178 | 15/10/2026 | 178 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257378 LF1392 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 178 |  | 178 |  |  | 2026-06-10 | 2026-09-10 |  |  | 178 |  | 178
ADIDAS | 0903257558-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 296 | 2026-12-09 | 296 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 10/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903257558 KA0544 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-09 | J FOOTBALL T |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-04-09 | 2026-09-09 | 296 | 296 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-01-09 | 2026-01-09 | 296 | 296
ADIDAS | 0903257658-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 272 | 15/10/2026 | 272 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257658 KY3737 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 21/10/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 21/10/2026 | 21/10/2026 |  |  | 272 |  | 272 |  |  | 17/10/2026 | 17/10/2026 |  |  | 272 |  | 272
ADIDAS | 0903257668-1 IN1173 | WHITE | 90D | S2408WR1600 | 269 | 31/10/2026 | 269 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257668 IN1173 |  | KAHATEX CIJERAH | MOROCCO | SEA | 26/10/2026 | ADIZERO E TEE |  | SS27-YTI | 26/10/2026 | 27/10/2026 |  |  | 269 |  | 269 |  |  | 23/10/2026 | 24/10/2026 |  |  | 269 |  | 269 |  |  | 22/10/2026 | 23/10/2026 |  |  | 269 |  | 269
ADIDAS | 0903257671-1 IN1159 | BLACK | 90D | S2408MR1601 | 2727 | 15/10/2026 | 2727 | SA | SA10/07/2026 | G1D | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257671 IN1159 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 14/10/2026 | 20/10/2026 |  |  | 2727 |  | 2727 |  |  | 2026-10-10 | 16/10/2026 |  |  | 2727 |  | 2727 |  |  | 2026-07-10 | 13/10/2026 |  |  | 2727 |  | 2727
ADIDAS | 0903257687-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 224 | 15/10/2026 | 224 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903257687 KV0458 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 21/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 21/10/2026 | 22/10/2026 |  |  | 224 |  | 224 |  |  | 17/10/2026 | 19/10/2026 |  |  | 224 |  | 224
ADIDAS | 0903257700-1 IN8707 | BLACK | 105D | S2408WR1601A | 2203 | 15/10/2026 | 2203 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257700 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 21/10/2026 |  |  | 2203 |  | 2203 |  |  | 13/10/2026 | 17/10/2026 |  |  | 2203 |  | 2203 |  |  | 2026-09-10 | 14/10/2026 |  |  | 2203 |  | 2203
ADIDAS | 0903257706-1 IS1413 | BLACK | 60D | S2425M405 | 396 | 2026-07-10 | 396 | SI | SI10/07/2026 | G2S | T-SHIRT | G2 | ok | ok | 30/09: ex-fty 547012 | PRINT L3 SUB PROCESS_V3 | 0903257706 IS1413 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 2026-03-10 | IN RANGE |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 396 |  | 396 |  |  | 30/09/2026 | 2026-01-10 | 19/09/2026 | 19/09/2026 | 396 | 374 | 22 |  | 374
ADIDAS | 0903257710-1 IN1159 | BLACK | 90D | S2408MR1601 | 125 | 23/10/2026 | 125 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257710 IN1159 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 30/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 30/10/2026 | 31/10/2026 |  |  | 125 |  | 125 |  |  | 27/10/2026 | 28/10/2026 |  |  | 125 |  | 125 |  |  | 23/10/2026 | 24/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903257728-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 300 | 15/10/2026 | 300 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903257728 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 300 |  | 300 |  |  | 19/10/2026 | 20/10/2026 |  |  | 300 |  | 300 |  |  | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903257736-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 636 | 15/10/2026 | 636 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L3 SUB PROCESS_V3 | 0903257736 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 636 |  | 636 |  |  | 2026-12-10 | 2026-12-10 |  |  | 636 |  | 636
ADIDAS | 0903257739-1 LF0723 | BLACK | 105D | S2754MAS511B | 207 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257739 LF0723 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257740-1 KA4331 | BLACK | 90D | S2608MR0902 | 483 | 15/10/2026 | 483 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903257740 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-12-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 483 |  | 483 |  |  | 2026-08-10 | 2026-10-10 |  |  | 483 |  | 483 |  |  | 2026-07-10 | 2026-09-10 |  |  | 483 |  | 483
ADIDAS | 0903257744-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 500 | 30/09/2026 | 500 | SA | SA10/07/2026 | G2A | T-SHIRT | G2 | ok | ok | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903257744 KA5089 | 26/08/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 24/09/2026 | MINI EMB T |  | SS27 | 24/09/2026 | 24/09/2026 |  |  | 500 |  | 500 |  |  | 21/09/2026 | 21/09/2026 |  |  | 500 |  | 500 |  |  | 18/09/2026 | 18/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903257763-1 IN1157 | WHITE | 90D | S2408MR1600 | 275 | 31/10/2026 | 275 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512102 | HT SUB PROCESS_V1 | 0903257763 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/11/2026 | ADIZERO E TEE |  | SS27-YTI | 14/11/2026 | 16/11/2026 |  |  | 275 |  | 275 |  |  | 2026-12-11 | 2026-12-11 |  |  | 275 |  | 275 |  |  | 2026-11-11 | 2026-11-11 |  |  | 275 |  | 275
ADIDAS | 0903257766-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 727 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257766 KV7863 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903257771-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 534 | 15/10/2026 | 534 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 600000 | PRINT L1 SUB PROCESS_V3 | 0903257771 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 16/10/2026 | 17/10/2026 |  |  | 534 |  | 534 |  |  | 13/10/2026 | 14/10/2026 |  |  | 534 |  | 534
ADIDAS | 0903257777-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 441 | 31/10/2026 | 441 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Far Eastern, PI Date 20-Aug, actual receives 01-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 01-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903257777 KX9855 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/10/2026 | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI | 29/10/2026 | 30/10/2026 |  |  | 441 |  | 441 |  |  | 27/10/2026 | 28/10/2026 |  |  | 441 |  | 441 |  |  | 26/10/2026 | 27/10/2026 |  |  | 441 |  | 441
ADIDAS | 0903257785-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 218 | 15/10/2026 | 218 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848024 | PRINT L2+PAD SUB PROCESS_V3 | 0903257785 LC8884 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 218 |  | 218 |  |  | 2026-10-10 | 2026-12-10 | 26/08/2026 | 18/09/2026 | 218 | 216 | 2
ADIDAS | 0903257807-1 KA4331 | BLACK | 90D | S2608MR0902 | 334 | 15/10/2026 | 334 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 516343 | PAD+HT SUB PROCESS_V3 | 0903257807 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 334 |  | 334 |  |  | 2026-06-10 | 2026-07-10 |  |  | 334 |  | 334 |  |  | 2026-05-10 | 2026-06-10 |  |  | 334 |  | 334
ADIDAS | 0903257817-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 113 | 15/10/2026 | 113 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 848024 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257817 LE4307 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 17/10/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 17/10/2026 | 20/10/2026 |  |  | 113 |  | 113 |  |  | 14/10/2026 | 16/10/2026 |  |  | 113 |  | 113
ADIDAS | 0903257826-1 KA4331 | BLACK | 90D | S2608MR0902 | 395 | 23/10/2026 | 395 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257826 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 395 |  | 395 |  |  | 2026-09-11 | 2026-10-11 |  |  | 395 |  | 395 |  |  | 2026-06-11 | 2026-09-11 |  |  | 395 |  | 395
ADIDAS | 0903257828-1 IN2961 | BLACK | 105D | S2408WR2400 | 3750 | 31/10/2026 | 3750 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903257828 IN2961 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 25/11/2026 | OTR B TEE BLACK |  | SS27 | 25/11/2026 | 27/11/2026 |  |  | 3750 |  | 3750 |  |  | 23/11/2026 | 25/11/2026 |  |  | 3750 |  | 3750 |  |  | 20/11/2026 | 24/11/2026 |  |  | 3750 |  | 3750
ADIDAS | 0903257833-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 128 | 15/10/2026 | 128 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 848012 | EMBRO SUB PROCESS_V1 | 0903257833 HK7303 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 128 |  | 128 |  |  | 26/09/2026 | 28/09/2026 |  |  | 128 |  | 128
ADIDAS | 0903257836-1 IN1159 | BLACK | 90D | S2408MR1601 | 130 | 31/10/2026 | 130 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257836 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-10-11 | 2026-10-11 |  |  | 130 |  | 130 |  |  | 2026-05-11 | 2026-05-11 |  |  | 130 |  | 130 |  |  | 2026-02-11 | 2026-02-11 |  |  | 130 |  | 130
ADIDAS | 0903257863-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 111 | 15/10/2026 | 111 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | EMBRO SUB PROCESS_V1 | 0903257863 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 30/09/2026 | ESS TEE |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 111 |  | 111 |  |  | 26/09/2026 | 28/09/2026 |  |  | 111 |  | 111
ADIDAS | 0903257892-1 LE8187 | BLACK | 105D | S2754MAS513 | 180 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257892 LE8187 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257897-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1278 | 15/10/2026 | 1278 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 848024 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903257897 JD1877 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-01-10 | M 3S FT FZ HD |  | SS27 | 2026-01-10 | 2026-05-10 |  |  | 1278 |  | 1278 |  |  | 28/09/2026 | 2026-01-10 |  |  | 1278 |  | 1278
ADIDAS | 0903257898-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3008 | 15/10/2026 | 3008 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903257898 JE6419 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-01-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-01-10 | 2026-08-10 |  |  | 3008 |  | 3008 |  |  | 28/09/2026 | 2026-05-10 |  |  | 3008 |  | 3008
ADIDAS | 0903257900-1 KG3234 | DUAL MAGENTA F26 | 105D | S2608WR0901 | 1250 | 31/10/2026 | 1250 | SI | SI10/07/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 804028 | PAD+HT SUB PROCESS_V3 | 0903257900 KG3234 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-11 | Run Ess Shor W DUAL MAGENTA F26 |  | SS27-TRAX | 2026-05-11 | 2026-09-11 |  |  | 1250 |  | 1250 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1250 |  | 1250 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1250 |  | 1250
ADIDAS | 0903257913-1 KA4331 | BLACK | 90D | S2608MR0902 | 306 | 15/10/2026 | 306 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903257913 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-09-10 | 2026-10-10 |  |  | 306 |  | 306 |  |  | 2026-06-10 | 2026-07-10 |  |  | 306 |  | 306 |  |  | 2026-05-10 | 2026-06-10 |  |  | 306 |  | 306
ADIDAS | 0903257952-1 IN1172 | BLACK | 90D | S2408WR1600 | 380 | 31/10/2026 | 380 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903257952 IN1172 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-10-11 | ADIZERO E TEE |  | SS27-YTI | 2026-10-11 | 2026-11-11 |  |  | 380 |  | 380 |  |  | 2026-06-11 | 2026-09-11 |  |  | 380 |  | 380 |  |  | 2026-05-11 | 2026-06-11 |  |  | 380 |  | 380
ADIDAS | 0903257978-1 IN1159 | BLACK | 90D | S2408MR1601 | 163 | 31/10/2026 | 163 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257978 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-09-11 | 2026-10-11 |  |  | 163 |  | 163 |  |  | 2026-04-11 | 2026-05-11 |  |  | 163 |  | 163 |  |  | 31/10/2026 | 2026-02-11 |  |  | 163 |  | 163
ADIDAS | 0903257985-1 IK7442 | WHITE | 105D | S2408WR2400 | 1056 | 31/10/2026 | 1056 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903257985 IK7442 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-04-11 | OTR B TEE WHITE |  | SS27 | 2026-04-11 | 2026-05-11 |  |  | 1056 |  | 1056 |  |  | 2026-02-11 | 2026-03-11 |  |  | 1056 |  | 1056 |  |  | 31/10/2026 | 2026-02-11 |  |  | 1056 |  | 1056
ADIDAS | 0903258010-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1100 | 15/10/2026 | 1100 | SI | SI10/07/2026 | G2Q | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903258010 JG8642 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 15/09/2026 | W LIN FT SHO |  | SS27 | 15/09/2026 | 23/09/2026 | 16/09/2026 | 18/09/2026 | 1100 | 568 | 532 |  |  | 2026-11-09 | 19/09/2026 | 2026-09-09 | 19/09/2026 | 1100 | 1087 | 13 |  | 31
ADIDAS | 0903258044-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 304 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258044 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258059-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 1550 | 31/10/2026 | 1550 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 804028 | HT SUB PROCESS_V1 | 0903258059 JW9678 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-09-11 | OTR B TEE POWDER PLUM F25 |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 1550 |  | 1550 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1550 |  | 1550 |  |  | 2026-04-11 | 2026-05-11 |  |  | 1550 |  | 1550
ADIDAS | 0903258064-1 KA0527 | PURE RUBY S25 | 60D | S26KJUGFX003 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | ok | ok | 1st Art (TC 10 pcs) 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258064 KA0527 | 26/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | J SUMMER T |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-06-10 | 15/09/2026 | 17/09/2026 | 100 | 73 | 27
ADIDAS | 0903258089-1 LE8187 | BLACK | 105D | S2754MAS513 | 1030 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258089 LE8187 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903258094-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 100 | 31/10/2026 | 100 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 10-Aug, ETD 10-Aug, ETA KH 21-Aug. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258094 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/11/2026 | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 100 |  | 100 |  |  | 2026-11-11 | 13/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903258118-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 368 | 15/10/2026 | 368 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | (09/08/2026) | ok | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903258118 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 368 |  | 368 |  |  | 23/09/2026 | 24/09/2026 | 2026-09-09 | 2026-09-09 | 368 | 349 | 19
ADIDAS | 0903258121-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 117 | 15/10/2026 | 117 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258121 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 117 |  | 117 |  |  | 2026-06-10 | 2026-09-10 |  |  | 117 |  | 117
ADIDAS | 0903258126-1 IN1157 | WHITE | 90D | S2408MR1600 | 319 | 23/10/2026 | 319 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903258126 IN1157 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | ADIZERO E TEE |  | SS27-YTI | 13/11/2026 | 14/11/2026 |  |  | 319 |  | 319 |  |  | 2026-11-11 | 2026-12-11 |  |  | 319 |  | 319 |  |  | 2026-10-11 | 2026-11-11 |  |  | 319 |  | 319
ADIDAS | 0903258151-1 IN1160 | WHITE | 90D | S2408MR1601 | 585 | 31/10/2026 | 585 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258151 IN1160 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 19/11/2026 | ADIZERO E SHORT WHITE |  | SS27-TRAX | 19/11/2026 | 20/11/2026 |  |  | 585 |  | 585 |  |  | 16/11/2026 | 17/11/2026 |  |  | 585 |  | 585 |  |  | 2026-11-11 | 2026-12-11 |  |  | 585 |  | 585
ADIDAS | 0903258170-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258170 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/11/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 18/11/2026 | 18/11/2026 |  |  | 107 |  | 107 |  |  | 13/11/2026 | 13/11/2026 |  |  | 107 |  | 107
ADIDAS | 0903258209-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 272 | 15/10/2026 | 272 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L1 SUB PROCESS_V3 | 0903258209 LI7655 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 16/10/2026 | 17/10/2026 |  |  | 272 |  | 272 |  |  | 13/10/2026 | 14/10/2026 |  |  | 272 |  | 272
ADIDAS | 0903258217-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 584 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 516343 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258217 KC8152 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258233-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1002 | 15/10/2026 | 1002 | SA | SA10/07/2026 | G2P | SHORTS | G2 | ok | ok | 834012 | EMBRO SUB PROCESS_V1 | 0903258233 JE6419 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-02-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 1002 |  | 1002 |  |  | 29/09/2026 | 2026-01-10 |  |  | 1002 |  | 1002
ADIDAS | 0903258257-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1403 | 2026-09-09 | 1403 | SA | SA10/07/2026 | G3H | SWEATSHIRT | G3 | ok | ok | 09/09: ex-fty. DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258257 HK7311 | 2026-11-08 | KAHATEX CIJERAH | ISRAEL | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 2026-08-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403 |  |  |  | 27/08/2026 | 2026-04-09 | 2026-03-09 | 2026-09-09 | 1403 | 1403
ADIDAS | 0903258260-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 107 | 23/10/2026 | 107 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903258260 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/11/2026 | M 3B PQ PS WHITE/BLACK |  | SS27-STX | 18/11/2026 | 18/11/2026 |  |  | 107 |  | 107 |  |  | 13/11/2026 | 13/11/2026 |  |  | 107 |  | 107
ADIDAS | 0903258292-1 KT4839 | ONIX | 90D | S2408MR1601 | 161 | 31/10/2026 | 161 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258292 KT4839 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 161 |  | 161 |  |  | 28/10/2026 | 29/10/2026 |  |  | 161 |  | 161 |  |  | 24/10/2026 | 26/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903258321-1 IN1172 | BLACK | 90D | S2408WR1600 | 1722 | 31/10/2026 | 1722 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 834012 | HT SUB PROCESS_V1 | 0903258321 IN1172 |  | KAHATEX CIJERAH | ISRAEL | SEA | 13/11/2026 | ADIZERO E TEE |  | SS27-YTI | 13/11/2026 | 16/11/2026 |  |  | 1722 |  | 1722 |  |  | 2026-11-11 | 2026-12-11 |  |  | 1722 |  | 1722 |  |  | 2026-10-11 | 2026-11-11 |  |  | 1722 |  | 1722
ADIDAS | 0903258325-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 111 | 15/10/2026 | 111 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516443 | PRINT L3 SUB PROCESS_V3 | 0903258325 LI7660 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 15/10/2026 | 15/10/2026 |  |  | 111 |  | 111 |  |  | 2026-12-10 | 2026-12-10 |  |  | 111 |  | 111
ADIDAS | 0903258342-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 1448 | 15/10/2026 | 1448 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903258342 LI7659 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-12-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-12-10 | 2026-12-10 |  |  | 1448 |  | 1448 |  |  | 2026-08-10 | 2026-08-10 |  |  | 1448 |  | 1448
ADIDAS | 0903258375-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/10/2026 | 300 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | ok | ok | 600000 | PRINT L2 SUB PROCESS_V3 | 0903258375 LI7658 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 300 |  | 300 |  |  | 2026-03-10 | 2026-03-10 |  |  | 300 |  | 300
ADIDAS | 0903258612-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 2 | 15/10/2026 | 2 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903258612 IT1469 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 2 |  | 2 |  |  | 19/10/2026 | 20/10/2026 |  |  | 2 |  | 2 |  |  | 17/10/2026 | 19/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903258647-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 4605 | 15/10/2026 | 4605 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903258647 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-12-10 |  |  | 4605 |  | 4605 |  |  | 2026-03-10 | 2026-09-10 |  |  | 4605 |  | 4605 |  |  | 2026-02-10 | 2026-08-10 |  |  | 4605 |  | 4605
ADIDAS | 0903258660-1 KT4839 | ONIX | 90D | S2408MR1601 | 112 | 31/10/2026 | 112 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258660 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 31/10/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 31/10/2026 | 2026-02-11 |  |  | 112 |  | 112 |  |  | 28/10/2026 | 29/10/2026 |  |  | 112 |  | 112 |  |  | 24/10/2026 | 26/10/2026 |  |  | 112 |  | 112
ADIDAS | 0903258675-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 2130 | 15/10/2026 | 2130 | SI | SI10/07/2026 | G1D | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258675 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 27/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 27/10/2026 | 31/10/2026 |  |  | 2130 |  | 2130 |  |  | 23/10/2026 | 28/10/2026 |  |  | 2130 |  | 2130 |  |  | 20/10/2026 | 24/10/2026 |  |  | 2130 |  | 2130
ADIDAS | 0903258696-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 510 | 14/10/2026 | 510 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. T2 Libolon, PI Date 28-May, actual receives 12-Jun. 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258696 KZ3205 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 510 |  | 510 |  |  | 2026-03-10 | 2026-06-10 |  |  | 510 |  | 510
ADIDAS | 0903258702-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G2L | T-SHIRT | G2 | (09/08/2026) | ok | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258702 LC6339 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 120 |  | 120 |  |  | 23/09/2026 | 24/09/2026 | 2026-11-09 | 16/09/2026 | 120 | 113 | 7
ADIDAS | 0903258720-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1066 | 15/10/2026 | 1066 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903258720 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 1066 |  | 1066 |  |  | 17/10/2026 | 20/10/2026 |  |  | 1066 |  | 1066
ADIDAS | 0903258750-1 IN1157 | WHITE | 90D | S2408MR1600 | 6183 | 15/10/2026 | 6183 | SA | SA10/07/2026 | G1L | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 1st Art (TC 10 pcs) 672027 | HT SUB PROCESS_V1 | 0903258750 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 21/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-12-10 | 19/10/2026 |  |  | 6183 |  | 6183 |  |  | 2026-10-10 | 17/10/2026 |  |  | 6183 |  | 6183
ADIDAS | 0903258776-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 488 | 15/10/2026 | 488 | AN | AN10/07/2026 | G1I | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903258776 LF1392 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-09-10 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 488 |  | 488 |  |  | 2026-06-10 | 2026-09-10 |  |  | 488 |  | 488
ADIDAS | 0903258807-1 IN8707 | BLACK | 105D | S2408WR1601A | 65 | 15/10/2026 | 65 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258807 IN8707 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 16/10/2026 | 21/10/2026 |  |  | 65 |  | 65 |  |  | 13/10/2026 | 17/10/2026 |  |  | 65 |  | 65 |  |  | 2026-09-10 | 14/10/2026 |  |  | 65 |  | 65
ADIDAS | 0903258822-1 IN1156 | BLACK | 90D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258822 IN1156 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 13/10/2026 |  |  | 1 |  | 1 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1 |  | 1 |  |  | 2026-08-10 | 2026-09-10 |  |  | 1 |  | 1
ADIDAS | 0903258858-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 659018 672027 | HT SUB PROCESS_V1 | 0903258858 IN1172 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 250 |  | 250 |  |  | 13/10/2026 | 14/10/2026 |  |  | 250 |  | 250 |  |  | 2026-12-10 | 13/10/2026 | 2026-04-09 | 19/09/2026 | 250 | 246 | 4 |  | 4
ADIDAS | 0903258880-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 138 | 31/10/2026 | 138 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848016 | HT SUB PROCESS_V1 | 0903258880 KZ2984 |  | KAHATEX CIJERAH | MOROCCO | SEA | 31/10/2026 | ADIZERO E TEE |  | SS27-YTI | 31/10/2026 | 2026-02-11 |  |  | 138 |  | 138 |  |  | 29/10/2026 | 30/10/2026 |  |  | 138 |  | 138 |  |  | 28/10/2026 | 29/10/2026 |  |  | 138 |  | 138
ADIDAS | 0903258889-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 672027 | HT SUB PROCESS_V1 | 0903258889 IT1469 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 17/10/2026 | 19/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903258929-1 IN1157 | WHITE | 90D | S2408MR1600 | 145 | 15/10/2026 | 145 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 06-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258929 IN1157 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27-YTI | 21/10/2026 | 22/10/2026 |  |  | 145 |  | 145 |  |  | 19/10/2026 | 20/10/2026 | 17/09/2026 | 19/09/2026 | 145 | 36 | 109 |  | 9 | 17/10/2026 | 19/10/2026 | 17/09/2026 | 18/09/2026 | 145 | 36 | 109
ADIDAS | 0903258964-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 05-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903258964 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 14/10/2026 | ADIZERO E TEE |  | SS27-YTI | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-12-10 | 13/10/2026 | 20/08/2026 | 29/08/2026 | 100 | 99 | 1 |  |  | 2026-10-10 | 2026-12-10 | 19/08/2026 | 28/08/2026 | 100 | 99 | 1
ADIDAS | 0903258997-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258997 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 60 |  | 60 |  |  | 2026-03-10 | 2026-05-10 |  |  | 60 |  | 60 |  |  | 30/09/2026 | 2026-01-10 |  |  | 60 |  | 60
ADIDAS | 0903259051-1 KA4331 | BLACK | 90D | S2608MR0902 | 62 | 15/10/2026 | 62 | SA | SA10/07/2026 | G1C | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. 672027 | PAD+HT SUB PROCESS_V3 | 0903259051 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 62 |  | 62 |  |  | 2026-08-10 | 2026-10-10 |  |  | 62 |  | 62 |  |  | 2026-07-10 | 2026-09-10 |  |  | 62 |  | 62
ADIDAS | 0903259083-1 KT4839 | ONIX | 90D | S2408MR1601 | 60 | 15/10/2026 | 60 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259083 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/09/2026 | 2026-02-10 |  |  | 60 |  | 60 |  |  | 25/09/2026 | 29/09/2026 |  |  | 60 |  | 60 |  |  | 22/09/2026 | 25/09/2026 |  |  | 60 |  | 60
ADIDAS | 0903259087-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | 630001 | PRINT L2 SUB PROCESS_V3 | 0903259087 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-02-10 | MER KA GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200 |  |  | 29/09/2026 | 30/09/2026 |  |  | 200 |  | 200
ADIDAS | 0903259113-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 228 | 15/10/2026 | 228 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 630001 | PRINT L2 SUB PROCESS_V3 | 0903259113 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 20/10/2026 |  |  | 228 |  | 228 |  |  | 15/10/2026 | 16/10/2026 |  |  | 228 |  | 228
ADIDAS | 0903259117-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 135 | 15/10/2026 | 135 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903259117 KZ0028 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 13/10/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 13/10/2026 | 14/10/2026 |  |  | 135 |  | 135 |  |  | 2026-09-10 | 2026-10-10 |  |  | 135 |  | 135 |  |  | 2026-08-10 | 2026-09-10 |  |  | 135 |  | 135
ADIDAS | 0903259145-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 100 | 15/10/2026 | 100 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | ok | ok | T2 Y.T.I., PI Date 14-Aug, material quality issues body: stain), body&mesh actual receives 18-Aug. 672027 | HT SUB PROCESS_V1 | 0903259145 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-03-10 | ADIZERO E TEE |  | SS27-YTI | 2026-03-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 | 2026-04-09 | 16/09/2026 | 100 | 100 |  |  |  | 30/09/2026 | 2026-01-10 | 29/08/2026 | 15/09/2026 | 100 | 100
ADIDAS | 0903259225-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 101 | 15/10/2026 | 101 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903259225 JE6419 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 101 |  | 101 |  |  | 26/09/2026 | 28/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903259421-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 35000 | 30/09/2026 | 35000 | SA | SA10/07/2026 | G2G,G2I,G2J,G2M | T-SHIRT | G2 | ok | ok | 29/09: ex-fty (1x20). DRC 0090-early shipment customer (GTS89140-1 Early Shipment Order 0903259421). 834012 | HT+PAD SUB PROCESS_V3 | 0903259421 KB5966 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA | 15/09/2026 | Run Ess Tee M |  | SS27-TI | 15/09/2026 | 2026-02-10 | 16/09/2026 | 19/09/2026 | 35000 | 5235 | 29765 |  | 2200 | 2026-11-09 | 29/09/2026 | 2026-10-09 | 19/09/2026 | 35000 | 31020 | 3980 |  | 1178 | 2026-09-09 | 26/09/2026 | 2026-10-09 | 19/09/2026 | 35000 | 32611 | 2389 |  | 2667
ADIDAS | 0903259496-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 1820 | 15/10/2026 | 1820 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 1st Art (TC 10 pcs) 960006 | EMBRO SUB PROCESS_V1 | 0903259496 JE6346 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-01-10 | M 3S FT TC PT |  | SS27 | 2026-01-10 | 2026-03-10 |  |  | 1820 |  | 1820 |  |  | 28/09/2026 | 30/09/2026 |  |  | 1820 |  | 1820
ADIDAS | 0903259552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 440 | 15/10/2026 | 440 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259552 KV7963 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-07-10 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 440 |  | 440 |  |  | 2026-03-10 | 2026-05-10 |  |  | 440 |  | 440
ADIDAS | 0903259561-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903259561 KC8152 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903259603-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 900 | 31/10/2026 | 900 | SI | SI10/07/2026 | G2R | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259603 KF5295 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 900 |  | 900 |  |  | 21/10/2026 | 23/10/2026 |  |  | 900 |  | 900 |  |  | 17/10/2026 | 20/10/2026 |  |  | 900 |  | 900
ADIDAS | 0903259631-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 425 | 15/10/2026 | 425 | AN | AN10/07/2026 | G3K | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259631 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | W 3S WV SHO 4 BLACK/WHITE |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 425 |  | 425 |  |  | 2026-03-10 | 2026-05-10 |  |  | 425 |  | 425
ADIDAS | 0903259633-1 KA0246 | BLACK | 105D | S2608WR0902 | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G2T | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259633 KA0246 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 22/10/2026 | 23/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903259656-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 396 | 15/10/2026 | 396 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259656 JD1877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/09/2026 | M 3S FT FZ HD |  | SS27 | 26/09/2026 | 29/09/2026 |  |  | 396 |  | 396 |  |  | 23/09/2026 | 25/09/2026 |  |  | 396 |  | 396
ADIDAS | 0903259689-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 270 | 15/10/2026 | 270 | SI | SI10/07/2026 | G3E | PANTS | G3 | (20/08/2026) | ok | 512102 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259689 JD5302 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/10/2026 | W 3S FT CF PT |  | SS27 | 24/10/2026 | 26/10/2026 |  |  | 270 |  | 270 |  |  | 21/10/2026 | 22/10/2026 |  |  | 270 |  | 270
ADIDAS | 0903259717-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 432 | 15/10/2026 | 432 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 512102 | EMBRO SUB PROCESS_V1 | 0903259717 JE6414 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 432 |  | 432 |  |  | 2026-10-10 | 2026-12-10 |  |  | 432 |  | 432
ADIDAS | 0903259814-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 371 | 15/10/2026 | 371 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259814 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 371 |  | 371 |  |  | 26/10/2026 | 27/10/2026 |  |  | 371 |  | 371
ADIDAS | 0903259841-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 225 | 31/10/2026 | 225 | SA | SA10/07/2026 | G3E | PANTS | G3 | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903259841 JW7178 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/10/2026 | W 3S FT OH PT |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 225 |  | 225 |  |  | 27/10/2026 | 28/10/2026 |  |  | 225 |  | 225
ADIDAS | 0903259865-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 195 | 15/10/2026 | 195 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259865 JC8239 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 195 |  | 195 |  |  | 24/09/2026 | 25/09/2026 |  |  | 195 |  | 195
ADIDAS | 0903259916-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 346 | 23/10/2026 | 346 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259916 LE4307 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 2026-10-11 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 346 |  | 346 |  |  | 2026-05-11 | 2026-11-11 |  |  | 346 |  | 346
ADIDAS | 0903259938-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 200 | 15/10/2026 | 200 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903259938 JG8642 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | W LIN FT SHO |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 200 |  | 200 |  |  | 26/09/2026 | 26/09/2026 | 2026-11-09 | 19/09/2026 | 200 | 200 |  |  | 6
ADIDAS | 0903260151-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 84 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 02-Sep. T2 Teijin Nantong, PI Date 30-Aug, actual receives 31-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260151 LD5446 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903260153-1 IN8707 | BLACK | 105D | S2408WR1601A | 135 | 31/10/2026 | 135 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903260153 IN8707 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 22/10/2026 | 24/10/2026 |  |  | 135 |  | 135 |  |  | 19/10/2026 | 21/10/2026 |  |  | 135 |  | 135 |  |  | 15/10/2026 | 17/10/2026 |  |  | 135 |  | 135
ADIDAS | 0903260154-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 208 | 23/10/2026 | 208 | AN | AN10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 31-Jul. T2 Formosa, PI Date 03-Jul, actual receives 18-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260154 KZ3204 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-11 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 2026-10-11 | 16/11/2026 |  |  | 208 |  | 208 |  |  | 2026-05-11 | 2026-11-11 |  |  | 208 |  | 208
ADIDAS | 0903260162-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 160 | 31/10/2026 | 160 | SI | SI10/07/2026 | G3J | SHORTS | G3 | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 980004 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903260162 KA4914 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 21/10/2026 | ESS SH 8IN |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 160 |  | 160 |  |  | 17/10/2026 | 19/10/2026 |  |  | 160 |  | 160 |  |  | 2026-12-10 | 13/10/2026 |  |  | 160 |  | 160
ADIDAS | 0903260176-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 647 | 31/10/2026 | 647 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903260176 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 24/11/2026 | 25/11/2026 |  |  | 647 |  | 647 |  |  | 20/11/2026 | 23/11/2026 |  |  | 647 |  | 647 |  |  | 19/11/2026 | 20/11/2026 |  |  | 647 |  | 647
ADIDAS | 0903260189-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 180 | 31/10/2026 | 180 | SA | SA10/07/2026 | G1L | SWEATSHIRT | G1 | (20/08/2026) | ok | 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260189 JN1948 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/10/2026 | W 3S FT QZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 180 |  | 180 |  |  | 27/10/2026 | 28/10/2026 |  |  | 180 |  | 180
ADIDAS | 0903260199-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1203 | 15/10/2026 | 1203 | SA | SA10/07/2026 | G2B | JACKET | G2 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903260199 JD1877 |  | KAHATEX CIJERAH | ISRAEL | SEA | 29/09/2026 | M 3S FT FZ HD |  | SS27 | 29/09/2026 | 2026-01-10 |  |  | 1203 |  | 1203 |  |  | 25/09/2026 | 28/09/2026 |  |  | 1203 |  | 1203
ADIDAS | 0903260204-1 IN1156 | BLACK | 90D | S2408MR1600 | 445 | 31/10/2026 | 445 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903260204 IN1156 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-11 | ADIZERO E TEE |  | SS27-YTI | 2026-11-11 | 2026-12-11 |  |  | 445 |  | 445 |  |  | 2026-09-11 | 2026-10-11 |  |  | 445 |  | 445 |  |  | 2026-06-11 | 2026-09-11 |  |  | 445 |  | 445
ADIDAS | 0903260210-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 100 | 31/10/2026 | 100 | SA | SA10/07/2026 | G2A | SHORTS | G2 | (20/08/2026) | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903260210 KD4872 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-07-10 | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-03-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903260217-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 703 | 15/10/2026 | 703 | SI | SI10/07/2026 | G3H | JACKET | G3 | (20/08/2026) | ok | 834012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260217 JE0052 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 21/10/2026 | W 3S FT FZ HD |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 703 |  | 703 |  |  | 17/10/2026 | 19/10/2026 |  |  | 703 |  | 703
ADIDAS | 0903260237-1 IN1173 | WHITE | 90D | S2408WR1600 | 663 | 31/10/2026 | 663 | SI | SI10/07/2026 | G1Q | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260237 IN1173 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/10/2026 | ADIZERO E TEE |  | SS27-YTI | 24/10/2026 | 26/10/2026 |  |  | 663 |  | 663 |  |  | 22/10/2026 | 23/10/2026 |  |  | 663 |  | 663 |  |  | 21/10/2026 | 22/10/2026 |  |  | 663 |  | 663
ADIDAS | 0903260251-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 102 | 31/10/2026 | 102 | SA | SA10/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903260251 LD0277 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 18/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 102 |  | 102 |  |  | 13/11/2026 | 17/11/2026 |  |  | 102 |  | 102 |  |  | 2026-12-11 | 16/11/2026 |  |  | 102 |  | 102
ADIDAS | 0903260280-1 IN1159 | BLACK | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903260280 IN1159 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-09-11 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-09-11 | 2026-10-11 |  |  | 300 |  | 300 |  |  | 2026-04-11 | 2026-05-11 |  |  | 300 |  | 300 |  |  | 31/10/2026 | 2026-02-11 |  |  | 300 |  | 300
ADIDAS | 0903260281-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 285 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260281 LF0721 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260282-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 302 | 15/10/2026 | 302 | SA | SA10/07/2026 | G3K | PANTS | G3 | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260282 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | W 3S FT OH PT |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 302 |  | 302 |  |  | 2026-05-10 | 2026-06-10 |  |  | 302 |  | 302
ADIDAS | 0903260342-1 KG8547 | ONIX | 90D | S2408WR1600 | 209 | 31/10/2026 | 209 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903260342 KG8547 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 209 |  | 209 |  |  | 26/10/2026 | 27/10/2026 |  |  | 209 |  | 209 |  |  | 24/10/2026 | 26/10/2026 |  |  | 209 |  | 209
ADIDAS | 0903260350-1 LF0723 | BLACK | 105D | S2754MAS511B | 252 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 30-Aug, actual receives 04-Sep. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260350 LF0723 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903260366-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 400 | 31/10/2026 | 400 | SI | SI10/07/2026 | G1F | JACKET | G1 | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903260366 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 16/11/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 16/11/2026 | 18/11/2026 |  |  | 400 |  | 400 |  |  | 2026-11-11 | 13/11/2026 |  |  | 400 |  | 400
ADIDAS | 0903260410-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 252 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260410 LE8181 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903260434-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260434 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 327 | 228 | 99 |  | 228 | 16/09/2026 | 17/09/2026 | 2026-08-09 | 18/09/2026 | 327 | 315 | 12 |  |  | 15/09/2026 | 16/09/2026 | 2026-08-09 | 17/09/2026 | 327 | 315 | 12
ADIDAS | 0903260463-1 IN1172 | BLACK | 90D | S2408WR1600 | 676 | 31/10/2026 | 676 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903260463 IN1172 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-11-11 | ADIZERO E TEE |  | SS27-YTI | 2026-11-11 | 2026-12-11 |  |  | 676 |  | 676 |  |  | 2026-09-11 | 2026-10-11 |  |  | 676 |  | 676 |  |  | 2026-06-11 | 2026-09-11 |  |  | 676 |  | 676
ADIDAS | 0903260486-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 473 | 31/10/2026 | 473 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | ok | ok | (Mexico). T2 Y.T.I, body & mesh actual receives 12-Aug. 652001 | HT SUB PROCESS_V1 | 0903260486 IT1469 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/11/2026 | ADIZERO E TEE |  | SS27-YTI | 24/11/2026 | 25/11/2026 |  |  | 473 |  | 473 |  |  | 20/11/2026 | 23/11/2026 |  |  | 473 |  | 473 |  |  | 19/11/2026 | 20/11/2026 |  |  | 473 |  | 473
ADIDAS | 0903260517-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 331 | 23/10/2026 |  | AN | AN10/07/2026 |  | SHORTS |  | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. T2 Formosa, actual receives 19-Jun (PO 26022035). 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903260517 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903260543-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 252 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | (Mexico). T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260543 LF0718 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903260741-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 212 | 15/10/2026 | 212 | SI | SI10/07/2026 | G1N | POLO SHIRT | G1 | (10/08/2026) | ok | 800187 | EMBRO SUB PROCESS_V1 | 0903260741 KV0458 |  | KAHATEX CIJERAH | VIETNAM | SEA | 21/10/2026 | M 3B PQ PS BLACK/WHITE |  | SS27-STX | 21/10/2026 | 22/10/2026 |  |  | 212 |  | 212 |  |  | 17/10/2026 | 19/10/2026 |  |  | 212 |  | 212
ADIDAS | 0903261098-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | ok | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903261098 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-02-10 | MER GR GFSWT M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 29/09/2026 | 29/09/2026 | 15/09/2026 | 15/09/2026 | 2 | 2
ADIDAS | 0903261108-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | (China). 825054 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903261108 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-02-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 29/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903261122-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 2 | 29/09/2026 | 2 | SA | SA10/07/2026 | G2M | SWEATSHIRT | G2 | ok | ok | (China). 825054 | PRINT L2 SUB PROCESS_V3 | 0903261122 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 15/09/2026 | MER KA GFSWT M BLACK |  | SS27-MS | 15/09/2026 | 15/09/2026 |  |  | 2 |  | 2 |  |  | 2026-11-09 | 2026-11-09 |  |  | 2 |  | 2
ADIDAS | 0903261168-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 35 | 15/10/2026 | 35 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903261168 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 21/10/2026 | 22/10/2026 |  |  | 35 |  | 35 |  |  | 17/10/2026 | 19/10/2026 |  |  | 35 |  | 35 |  |  | 14/10/2026 | 15/10/2026 |  |  | 35 |  | 35
ADIDAS | 0903261379-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 434 | 31/10/2026 | 434 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903261379 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 434 |  | 434 |  |  | 18/11/2026 | 18/11/2026 |  |  | 434 |  | 434 |  |  | 13/11/2026 | 13/11/2026 |  |  | 434 |  | 434
ADIDAS | 0903261439-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 700 | 31/10/2026 | 700 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261439 LD0277 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 21/11/2026 | 24/11/2026 |  |  | 700 |  | 700 |  |  | 18/11/2026 | 19/11/2026 |  |  | 700 |  | 700 |  |  | 17/11/2026 | 18/11/2026 |  |  | 700 |  | 700
ADIDAS | 0903261459-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 531 | 31/10/2026 | 531 | SA | SA10/07/2026 | G2H | T-SHIRT | G2 | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903261459 KX3654 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 28/10/2026 | 29/10/2026 |  |  | 531 |  | 531 |  |  | 24/10/2026 | 26/10/2026 |  |  | 531 |  | 531 |  |  | 22/10/2026 | 23/10/2026 |  |  | 531 |  | 531
ADIDAS | 0903261492-1 IN1157 | WHITE | 90D | S2408MR1600 | 507 | 31/10/2026 | 507 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261492 IN1157 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 507 |  | 507 |  |  | 13/11/2026 | 16/11/2026 |  |  | 507 |  | 507 |  |  | 2026-12-11 | 13/11/2026 |  |  | 507 |  | 507
ADIDAS | 0903261529-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1E | SHORTS | G1 | (07/09/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903261529 LD0292 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 2026-10-11 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-10-11 | 2026-11-11 |  |  | 300 |  | 300 |  |  | 2026-05-11 | 2026-06-11 |  |  | 300 |  | 300 |  |  | 2026-04-11 | 2026-05-11 |  |  | 300 |  | 300
ADIDAS | 0903261558-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 1889 | 31/10/2026 | 1889 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | ok | ok | (Mexico). T2 Far Easten, PI Date 21-Sep, actual receives 11-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 11-Aug (using fabric from Y.T.I.). 652001 | HT SUB PROCESS_V1 | 0903261558 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 26/11/2026 | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI | 26/11/2026 | 28/11/2026 |  |  | 1889 |  | 1889 |  |  | 24/11/2026 | 26/11/2026 |  |  | 1889 |  | 1889 |  |  | 23/11/2026 | 25/11/2026 |  |  | 1889 |  | 1889
ADIDAS | 0903261586-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 360 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903261586 KY5988 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903261602-1 KA0246 | BLACK | 105D | S2608WR0902 | 12 | 31/10/2026 | 12 | SI | SI10/07/2026 | G2D | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric (Mexico). T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903261602 KA0246 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 19/10/2026 | Run Ess 21 S BLACK |  | SS27-TRAX | 19/10/2026 | 20/10/2026 |  |  | 12 |  | 12 |  |  | 15/10/2026 | 16/10/2026 |  |  | 12 |  | 12 |  |  | 2026-12-10 | 13/10/2026 |  |  | 12 |  | 12
ADIDAS | 0903261626-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 349 | 15/10/2026 | 349 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903261626 KG8553 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-07-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-07-10 | 2026-08-10 |  |  | 349 |  | 349 |  |  | 2026-03-10 | 2026-05-10 |  |  | 349 |  | 349 |  |  | 30/09/2026 | 2026-01-10 |  |  | 349 |  | 349
ADIDAS | 0903261645-1 KT4840 | ONIX | 90D | S2408MR1600 | 2134 | 31/10/2026 | 2134 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903261645 KT4840 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 20/11/2026 | ADIZERO E TEE |  | SS27-YTI | 20/11/2026 | 24/11/2026 |  |  | 2134 |  | 2134 |  |  | 18/11/2026 | 20/11/2026 |  |  | 2134 |  | 2134 |  |  | 17/11/2026 | 19/11/2026 |  |  | 2134 |  | 2134
ADIDAS | 0903262069-1 IS1413 | BLACK | 60D | S2425M405 | 944 | 2026-09-09 | 944 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 09/09: ex-fty 804028 | PRINT L3 SUB PROCESS_V3 | 0903262069 IS1413 | 26/08/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-07-09 | IN RANGE |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-09-09 | 944 | 944 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 944 | 944
ADIDAS | 0903262104-1 IL7232 | BLACK | 105D | S2408MR3202 | 367 | 31/10/2026 | 367 | SI | SI10/07/2026 | G3H | SHORTS | G3 | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 804028 | PAD+HT SUB PROCESS_V3 | 0903262104 IL7232 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-11 | RUN IT SHORT BLACK |  | SS27-TI | 2026-02-11 | 2026-03-11 |  |  | 367 |  | 367 |  |  | 29/10/2026 | 30/10/2026 |  |  | 367 |  | 367 |  |  | 28/10/2026 | 29/10/2026 |  |  | 367 |  | 367
ADIDAS | 0903262266-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 395 | 15/10/2026 | 395 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903262266 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 395 |  | 395 |  |  | 2026-10-10 | 2026-12-10 |  |  | 395 |  | 395
ADIDAS | 0903262302-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 285 | 15/10/2026 | 285 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (09/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903262302 LI7656 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 14/10/2026 | 14/10/2026 |  |  | 285 |  | 285 |  |  | 2026-10-10 | 2026-10-10 |  |  | 285 |  | 285
ADIDAS | 0903262654-1 KA4331 | BLACK | 90D | S2608MR0902 | 1174 | 30/10/2026 | 1174 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  | ok | (Mexico). DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262654 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 16/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 16/11/2026 | 18/11/2026 |  |  | 1174 |  | 1174 |  |  | 2026-11-11 | 13/11/2026 |  |  | 1174 |  | 1174 |  |  | 2026-10-11 | 2026-12-11 |  |  | 1174 |  | 1174
ADIDAS | 0903262676-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 878 | 31/10/2026 | 878 | SI | SI10/07/2026 | G3F | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262676 KD3854 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 28/10/2026 | 31/10/2026 |  |  | 878 |  | 878 |  |  | 24/10/2026 | 28/10/2026 |  |  | 878 |  | 878 |  |  | 21/10/2026 | 24/10/2026 |  |  | 878 |  | 878
ADIDAS | 0903262703-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 126 | 15/10/2026 | 126 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262703 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 29/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 126 |  | 126 |  |  | 26/10/2026 | 27/10/2026 |  |  | 126 |  | 126
ADIDAS | 0903262736-1 KG8547 | ONIX | 90D | S2408WR1600 | 343 | 31/10/2026 | 343 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262736 KG8547 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 343 |  | 343 |  |  | 26/10/2026 | 27/10/2026 |  |  | 343 |  | 343 |  |  | 24/10/2026 | 26/10/2026 |  |  | 343 |  | 343
ADIDAS | 0903262752-1 IK7442 | WHITE | 105D | S2408WR2400 | 190 | 31/10/2026 | 190 | SA | SA10/07/2026 | G1M | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903262752 IK7442 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-03-11 | OTR B TEE WHITE |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 190 |  | 190 |  |  | 31/10/2026 | 2026-02-11 |  |  | 190 |  | 190 |  |  | 30/10/2026 | 31/10/2026 |  |  | 190 |  | 190
ADIDAS | 0903262767-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 1656 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903262767 KY5988 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903262778-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 125 | 31/10/2026 | 125 | SI | SI10/07/2026 | G2R | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262778 KF5295 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 24/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 125 |  | 125 |  |  | 21/10/2026 | 23/10/2026 |  |  | 125 |  | 125 |  |  | 17/10/2026 | 20/10/2026 |  |  | 125 |  | 125
ADIDAS | 0903262788-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 1466 | 31/10/2026 | 1466 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903262788 KG8548 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 18/11/2026 | ADIZERO E TEE |  | SS27-YTI | 18/11/2026 | 20/11/2026 |  |  | 1466 |  | 1466 |  |  | 16/11/2026 | 18/11/2026 |  |  | 1466 |  | 1466 |  |  | 13/11/2026 | 17/11/2026 |  |  | 1466 |  | 1466
ADIDAS | 0903262820-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 190 | 15/10/2026 | 190 | SA | SA10/07/2026 | G3D | PANTS | G3 | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903262820 JE6346 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | M 3S FT TC PT |  | SS27 | 30/09/2026 | 2026-01-10 |  |  | 190 |  | 190 |  |  | 26/09/2026 | 28/09/2026 |  |  | 190 |  | 190
ADIDAS | 0903262839-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 31/10/2026 | 300 | SA | SA10/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric (Mexico). T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903262839 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 27/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 27/11/2026 | 28/11/2026 |  |  | 300 |  | 300 |  |  | 24/11/2026 | 25/11/2026 |  |  | 300 |  | 300 |  |  | 23/11/2026 | 24/11/2026 |  |  | 300 |  | 300
ADIDAS | 0903262846-1 LE8187 | BLACK | 105D | S2754MAS513 | 329 | 31/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 07-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 04-Sep, actual receives 04-Sep. 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262846 LE8187 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903262866-1 KT4839 | ONIX | 90D | S2408MR1601 | 2542 | 30/10/2026 | 2542 | SA | SA10/07/2026 | G1C | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262866 KT4839 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-11 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 2026-03-11 | 2026-09-11 |  |  | 2542 |  | 2542 |  |  | 30/10/2026 | 2026-04-11 |  |  | 2542 |  | 2542 |  |  | 27/10/2026 | 31/10/2026 |  |  | 2542 |  | 2542
ADIDAS | 0903262869-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/10/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903262869 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903262892-1 IN8707 | BLACK | 105D | S2408WR1601A | 300 | 31/10/2026 | 300 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262892 IN8707 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 24/10/2026 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 24/10/2026 | 27/10/2026 |  |  | 300 |  | 300 |  |  | 21/10/2026 | 23/10/2026 |  |  | 300 |  | 300 |  |  | 17/10/2026 | 20/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903262893-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 407 | 23/10/2026 | 407 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903262893 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 21/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 21/10/2026 | 21/10/2026 |  |  | 407 |  | 407 |  |  | 17/10/2026 | 17/10/2026 |  |  | 407 |  | 407
ADIDAS | 0903262897-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 300 | 31/10/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 09-Sep, actual receives 05-Sep. T2 Teijin Nantong, material quality issues (moir膿), PI Date 06-Sep, actual receives 27-Aug. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262897 LE8181 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262920-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 1163 | 31/10/2026 | 1163 | SI | SI10/07/2026 | G1K | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903262920 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-02-11 | ADIZERO E TEE |  | SS27-YTI | 2026-02-11 | 2026-03-11 |  |  | 1163 |  | 1163 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1163 |  | 1163 |  |  | 29/10/2026 | 30/10/2026 |  |  | 1163 |  | 1163
ADIDAS | 0903262943-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 406 | 31/10/2026 | 406 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | (09/09/2026) | ok | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903262943 KX3655 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 19/10/2026 | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI | 19/10/2026 | 19/10/2026 |  |  | 406 |  | 406 |  |  | 15/10/2026 | 15/10/2026 |  |  | 406 |  | 406 |  |  | 13/10/2026 | 13/10/2026 |  |  | 406 |  | 406
ADIDAS | 0903262965-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 1142 | 31/10/2026 | 1142 | SI | SI10/07/2026 | G1A | SHORTS | G1 | (14/09/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262965 KZ2988 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA | 29/10/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 29/10/2026 | 31/10/2026 |  |  | 1142 |  | 1142 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1142 |  | 1142 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1142 |  | 1142
ADIDAS | 0903262992-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 572 | 30/09/2026 | 572 | SI | SI10/07/2026 | G1E | T-SHIRT | G1 | (20/08/2026) | ok | (Mexico). IMPROVE. DRC 0010-T2 Y.T.I, body & mesh, material quality issues (body: stain), actual receives 18-Aug. 652001 | HT SUB PROCESS_V1 | 0903262992 KZ2984 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 25/09/2026 |  |  | 572 |  | 572 |  |  | 22/09/2026 | 23/09/2026 | 29/08/2026 | 2026-04-09 | 572 | 569 | 3 |  |  | 21/09/2026 | 22/09/2026 | 24/08/2026 | 2026-04-09 | 572 | 569 | 3
ADIDAS | 0903263275-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 160 | 15/10/2026 | 160 | AN | AN10/07/2026 | G2L | T-SHIRT | G2 | (06/08/2026) | ok | T2 Sue's, PI Date 18-Aug, actual receives 14-Sep. 512106 | PRINT L2+HT SUB PROCESS_V3 | 0903263275 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA | 14/10/2026 | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX | 14/10/2026 | 15/10/2026 |  |  | 160 |  | 160 |  |  | 2026-10-10 | 2026-12-10 |  |  | 160 |  | 160 |  |  | 2026-09-10 | 2026-10-10 |  |  | 160 |  | 160
ADIDAS | 0903263330-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 160 | 31/10/2026 | 160 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263330 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/11/2026 | ADIZERO E TEE |  | SS27-YTI | 17/11/2026 | 18/11/2026 |  |  | 160 |  | 160 |  |  | 13/11/2026 | 16/11/2026 |  |  | 160 |  | 160 |  |  | 2026-12-11 | 13/11/2026 |  |  | 160 |  | 160
ADIDAS | 0903263545-1 IN1172 | BLACK | 90D | S2408WR1600 | 250 | 31/10/2026 | 250 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903263545 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-11 | ADIZERO E TEE |  | SS27-YTI | 2026-12-11 | 13/11/2026 |  |  | 250 |  | 250 |  |  | 2026-10-11 | 2026-11-11 |  |  | 250 |  | 250 |  |  | 2026-09-11 | 2026-10-11 |  |  | 250 |  | 250
ADIDAS | 0903263584-1 IN1156 | BLACK | 90D | S2408MR1600 | 1058 | 31/10/2026 | 1058 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263584 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-12-11 | ADIZERO E TEE |  | SS27-YTI | 2026-12-11 | 14/11/2026 |  |  | 1058 |  | 1058 |  |  | 2026-10-11 | 2026-12-11 |  |  | 1058 |  | 1058 |  |  | 2026-09-11 | 2026-11-11 |  |  | 1058 |  | 1058
ADIDAS | 0903263669-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 568 | 30/10/2026 | 568 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | DRC 0090-early shipment customer (BTP_03_08_2026 EARLY HOLD SHIPMENT). Waiting fabric (Mexico). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263669 IT1467 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/11/2026 | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX | 17/11/2026 | 19/11/2026 |  |  | 568 |  | 568 |  |  | 2026-12-11 | 16/11/2026 |  |  | 568 |  | 568 |  |  | 2026-09-11 | 2026-11-11 |  |  | 568 |  | 568
ADIDAS | 0903263698-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2330 | 15/10/2026 | 2330 | AN | AN10/07/2026 | G3B | PANTS | G3 | ok | ok | (Mexico). T2 Kahatex, PI Date 10-Aug, actual receives 14-Aug. T2 Libolon, PI Date 03-Jul, actual receives 28-Jul. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263698 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 31/10/2026 | W 3S WV OH PT BLACK/WHITE |  | SS27 | 31/10/2026 | 2026-04-11 |  |  | 2330 |  | 2330 |  |  | 28/10/2026 | 31/10/2026 |  |  | 2330 |  | 2330
ADIDAS | 0903263747-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 250 | 15/10/2026 | 250 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 980004 | PRINT L1 SUB PROCESS_V3 | 0903263747 JG8639 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 30/09/2026 | W LIN FT SHO |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 250 |  | 250 |  |  | 26/09/2026 | 29/09/2026 | 18/09/2026 | 18/09/2026 | 250 | 52 | 198
ADIDAS | 0903263877-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 340 | 15/10/2026 | 340 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263877 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-07-10 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 340 |  | 340 |  |  | 2026-03-10 | 2026-03-10 |  |  | 340 |  | 340
ADIDAS | 0903264038-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ | 1500 | 15/10/2026 | 1500 | SI | SI10/07/2026 | G2J | T-SHIRT | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264038 JC8239 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 28/09/2026 | W LIN SJ T |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 1500 |  | 1500 |  |  | 24/09/2026 | 25/09/2026 |  |  | 1500 |  | 1500
ADIDAS | 0903264065-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 301 | 15/10/2026 | 301 | SA | SA10/07/2026 | G2D | SHORTS | G2 | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903264065 JE6414 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 14/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 301 |  | 301 |  |  | 2026-10-10 | 2026-12-10 |  |  | 301 |  | 301
ADIDAS | 0903264103-1 IN2961 | BLACK | 105D | S2408WR2400 | 1320 | 31/10/2026 | 1320 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903264103 IN2961 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/11/2026 | OTR B TEE BLACK |  | SS27 | 24/11/2026 | 25/11/2026 |  |  | 1320 |  | 1320 |  |  | 20/11/2026 | 23/11/2026 |  |  | 1320 |  | 1320 |  |  | 19/11/2026 | 20/11/2026 |  |  | 1320 |  | 1320
ADIDAS | 0903264129-1 KZ3065 | BLACK | 90D | S2762LHMEDR209W | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G2C | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903264129 KZ3065 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 29/09/2026 | MER KA GFCTP W BLACK |  | SS27-MS | 29/09/2026 | 30/09/2026 |  |  | 100 |  | 100 |  |  | 25/09/2026 | 26/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903264137-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 1000 | 15/10/2026 | 1000 | SI | SI10/07/2026 | G2M | SHORTS | G2 | ok | ok | 960006 | PRINT L1 SUB PROCESS_V3 | 0903264137 JG8639 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 30/09/2026 | W LIN FT SHO |  | SS27 | 30/09/2026 | 2026-02-10 |  |  | 1000 |  | 1000 |  |  | 26/09/2026 | 29/09/2026 | 17/09/2026 | 18/09/2026 | 1000 | 983 | 17
ADIDAS | 0903265194-1 KA4331 | BLACK | 90D | S2608MR0902 | 5581 | 15/10/2026 | 5581 | SA | SA10/07/2026 | G1B | SHORTS | G1 |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903265194 KA4331 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 21/10/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 21/10/2026 | 28/10/2026 |  |  | 5581 |  | 5581 |  |  | 17/10/2026 | 24/10/2026 |  |  | 5581 |  | 5581 |  |  | 16/10/2026 | 23/10/2026 |  |  | 5581 |  | 5581
ADIDAS | 0903265258-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 831 | 15/10/2026 | 831 | SI | SI10/07/2026 | G3K | SHORTS | G3 | (31/08/2026) | ok | T2 Y.R.C, PI Date 15-Aug, actual receives 16-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265258 KD3854 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX | 2026-12-10 | 14/10/2026 |  |  | 831 |  | 831 |  |  | 2026-08-10 | 2026-10-10 |  |  | 831 |  | 831 |  |  | 2026-05-10 | 2026-07-10 |  |  | 831 |  | 831
ADIDAS | 0903265296-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 300 | 15/10/2026 | 300 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265296 KF5311 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI | 2026-12-10 | 2026-12-10 |  |  | 300 |  | 300 |  |  | 2026-08-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-06-10 | 2026-06-10 |  |  | 300 |  | 300
ADIDAS | 0903265322-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 572 | 15/10/2026 | 572 | AN | AN10/07/2026 | G2N | T-SHIRT | G2 | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903265322 KE8424 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 16/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 16/10/2026 | 17/10/2026 |  |  | 572 |  | 572 |  |  | 13/10/2026 | 14/10/2026 |  |  | 572 |  | 572 |  |  | 2026-10-10 | 2026-12-10 |  |  | 572 |  | 572
ADIDAS | 0903265342-1 KG8547 | ONIX | 90D | S2408WR1600 | 3535 | 15/10/2026 | 3535 | SI | SI10/07/2026 | G1H | T-SHIRT | G1 | (20/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903265342 KG8547 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | ADIZERO E TEE |  | SS27-YTI | 2026-12-10 | 15/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-09-10 | 13/10/2026 |  |  | 3535 |  | 3535 |  |  | 2026-08-10 | 2026-12-10 |  |  | 3535 |  | 3535
ADIDAS | 0903265374-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 5948 | 15/10/2026 | 5948 | SA | SA10/07/2026 | G1O | T-SHIRT | G1 | ok | ok | T2 Far Easten, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 08-Aug, actual receives 05-Aug (using fabric from Y.T.I.). 672027 | HT SUB PROCESS_V1 | 0903265374 KG8548 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 15/10/2026 |  |  | 5948 |  | 5948 |  |  | 2026-06-10 | 13/10/2026 | 2026-12-08 | 16/09/2026 | 5948 | 5947 | 1 |  |  | 2026-05-10 | 2026-12-10 | 2026-12-08 | 14/09/2026 | 5948 | 5944 | 4
ADIDAS | 0903265404-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 1408 | 15/10/2026 | 1408 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265404 KG8553 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-08-10 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 2026-08-10 | 2026-12-10 |  |  | 1408 |  | 1408 |  |  | 2026-05-10 | 2026-08-10 |  |  | 1408 |  | 1408 |  |  | 2026-01-10 | 2026-05-10 |  |  | 1408 |  | 1408
ADIDAS | 0903265435-1 KT4840 | ONIX | 90D | S2408MR1600 | 5404 | 15/10/2026 | 5404 | SA | SA10/07/2026 | G1N | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903265435 KT4840 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-04-11 | ADIZERO E TEE |  | SS27-YTI | 2026-04-11 | 2026-11-11 |  |  | 5404 |  | 5404 |  |  | 2026-02-11 | 2026-09-11 |  |  | 5404 |  | 5404 |  |  | 31/10/2026 | 2026-06-11 |  |  | 5404 |  | 5404
ADIDAS | 0903265463-1 KT4839 | ONIX | 90D | S2408MR1601 | 1613 | 15/10/2026 | 1613 | SA | SA10/07/2026 | G1E | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903265463 KT4839 | 24/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 29/09/2026 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 29/09/2026 | 2026-02-10 |  |  | 1613 |  | 1613 |  |  | 25/09/2026 | 29/09/2026 |  |  | 1613 |  | 1613 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1613 |  | 1613
ADIDAS | 0903266153-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 309 | 15/10/2026 | 309 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903266153 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 19/10/2026 |  |  | 309 |  | 309 |  |  | 15/10/2026 | 15/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903266170-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 285 | 15/10/2026 | 285 | SA | SA10/07/2026 | G2F | T-SHIRT | G2 | ok | ok | 516333 | PRINT L2 SUB PROCESS_V3 | 0903266170 KZ3055 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | MER KA GFTEE K BLACK |  | SS27-MS | 19/10/2026 | 19/10/2026 |  |  | 285 |  | 285 |  |  | 15/10/2026 | 15/10/2026 |  |  | 285 |  | 285
ADIDAS | 0903266198-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 177 | 15/10/2026 | 177 | SI | SI10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | (06/08/2026) | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266198 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-02-10 | MER GR NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 177 |  | 177 |  |  | 29/09/2026 | 29/09/2026 |  |  | 177 |  | 177
ADIDAS | 0903266331-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 200 | 15/10/2026 | 200 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903266331 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 200 |  | 200 |  |  | 2026-02-10 | 2026-03-10 |  |  | 200 |  | 200
ADIDAS | 0903266349-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903266349 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-10 | MER GR GFTEE K BLACK |  | SS27-MS | 2026-06-10 | 2026-07-10 |  |  | 143 |  | 143 |  |  | 2026-02-10 | 2026-03-10 |  |  | 143 |  | 143
ADIDAS | 0903266371-1 IN1157 | WHITE | 90D | S2408MR1600 | 350 | 23/10/2026 | 350 | SA | SA10/07/2026 | G1R | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516290 | HT SUB PROCESS_V1 | 0903266371 IN1157 | 24/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 13/11/2026 | ADIZERO E TEE |  | SS27-YTI | 13/11/2026 | 14/11/2026 |  |  | 350 |  | 350 |  |  | 2026-11-11 | 2026-12-11 |  |  | 350 |  | 350 |  |  | 2026-10-11 | 2026-11-11 |  |  | 350 |  | 350
ADIDAS | 0903266377-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 355 | 23/10/2026 | 355 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | 960026 | PRINT L2 SUB PROCESS_V3 | 0903266377 LI7659 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-12-10 | MER KA NNTEE M BLACK |  | SS27-MS | 2026-12-10 | 13/10/2026 |  |  | 355 |  | 355 |  |  | 2026-08-10 | 2026-09-10 |  |  | 355 |  | 355
ADIDAS | 0903266421-1 IN1172 | BLACK | 90D | S2408WR1600 | 1030 | 23/10/2026 | 1030 | SI | SI10/07/2026 | G1G | T-SHIRT | G1 | (20/08/2026) | ok | 516438 | HT SUB PROCESS_V1 | 0903266421 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | ADIZERO E TEE |  | SS27-YTI | 2026-09-11 | 2026-10-11 |  |  | 1030 |  | 1030 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1030 |  | 1030 |  |  | 2026-04-11 | 2026-05-11 |  |  | 1030 |  | 1030
ADIDAS | 0903266452-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 23/10/2026 | 100 | SA | SA10/07/2026 | G2J | T-SHIRT | G2 | (09/08/2026) | ok | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903266452 LC6339 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903266525-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 310 | 15/10/2026 | 310 | SA | SA10/07/2026 | G3K | SHORTS | G3 |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266525 LH4535 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 2026-07-10 | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27 | 2026-07-10 | 2026-07-10 |  |  | 310 |  | 310 |  |  | 2026-03-10 | 2026-03-10 |  |  | 310 |  | 310
ADIDAS | 0903266526-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 273 | 15/10/2026 | 273 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266526 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-09-10 | 2026-12-10 |  |  | 273 |  | 273 |  |  | 2026-06-10 | 2026-08-10 |  |  | 273 |  | 273
ADIDAS | 0903266546-1 IN2961 | BLACK | 105D | S2408WR2400 | 240 | 31/10/2026 | 240 | SA | SA10/07/2026 | G1P | T-SHIRT | G1 | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903266546 IN2961 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 23/11/2026 | OTR B TEE BLACK |  | SS27 | 23/11/2026 | 24/11/2026 |  |  | 240 |  | 240 |  |  | 19/11/2026 | 20/11/2026 |  |  | 240 |  | 240 |  |  | 18/11/2026 | 19/11/2026 |  |  | 240 |  | 240
ADIDAS | 0903266548-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 120 | 15/10/2026 | 120 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516343 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266548 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 120 |  | 120 |  |  | 2026-05-10 | 2026-06-10 |  |  | 120 |  | 120
ADIDAS | 0903266578-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 143 | 15/10/2026 | 143 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266578 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 143 |  | 143 |  |  | 2026-05-10 | 2026-06-10 |  |  | 143 |  | 143
ADIDAS | 0903266593-1 KD4874 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS612FT | 210 | 31/10/2026 | 210 | SI | SI10/07/2026 | G2M | SWEATSHIRT | G2 | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903266593 KD4874 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA | 16/10/2026 | M 3S FT SWT |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 210 |  | 210 |  |  | 13/10/2026 | 14/10/2026 |  |  | 210 |  | 210
ADIDAS | 0903266599-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 100 | 15/10/2026 | 100 | SA | SA10/07/2026 | G1J | SWEATSHIRT | G1 | (10/08/2026) | ok | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266599 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | MER KA NNHD M BLACK |  | SS27-MS | 2026-09-10 | 2026-12-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-08-10 |  |  | 100 |  | 100
ADIDAS | 0903269490-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 120 | 15/10/2026 | 120 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269490 LI7655 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 120 |  | 120 |  |  | 2026-09-10 | 2026-10-10 |  |  | 120 |  | 120
ADIDAS | 0903269545-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 100 | 15/10/2026 | 100 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516343 | PRINT L3 SUB PROCESS_V3 | 0903269545 LI7660 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 100 |  | 100 |  |  | 2026-10-10 | 2026-12-10 |  |  | 100 |  | 100
ADIDAS | 0903269592-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 337 | 15/10/2026 | 337 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (09/08/2026) | ok | 516343 | PRINT L1 SUB PROCESS_V3 | 0903269592 LI7656 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 14/10/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 14/10/2026 | 14/10/2026 |  |  | 337 |  | 337 |  |  | 2026-10-10 | 2026-10-10 |  |  | 337 |  | 337
ADIDAS | 0903269617-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 103 | 15/10/2026 | 103 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 1st Art (TC 10 pcs) 516333 | PRINT L1 SUB PROCESS_V3 | 0903269617 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 103 |  | 103 |  |  | 2026-09-10 | 2026-10-10 |  |  | 103 |  | 103
ADIDAS | 0903270238-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 29 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | T2 Teijin Nantong, PI Date 04-Sep, actual receives 31-Aug. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270238 LF0718 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27-SPOMA
ADIDAS | 0903271653-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 107 | 15/10/2026 | 107 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L1 SUB PROCESS_V3 | 0903271653 LI7655 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 107 |  | 107 |  |  | 2026-09-10 | 2026-10-10 |  |  | 107 |  | 107
ADIDAS | 0903271675-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 150 | 15/10/2026 | 150 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | 516333 | PRINT L3 SUB PROCESS_V3 | 0903271675 LI7660 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 14/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 150 |  | 150 |  |  | 2026-10-10 | 2026-12-10 |  |  | 150 |  | 150
ADIDAS | 0903272051-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 179 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903272051 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903273743-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 309 | 15/10/2026 | 309 | SI | SI10/07/2026 | G3D | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273743 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 21/10/2026 | 21/10/2026 |  |  | 309 |  | 309 |  |  | 17/10/2026 | 17/10/2026 |  |  | 309 |  | 309
ADIDAS | 0903273803-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 305 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903273803 KV7863 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903274149-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 607 | 23/10/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903274149 KV7863 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903274607-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L3 SUB PROCESS_V3 | 0903274607 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 14/10/2026 | MER GR GFTEE M BLACK |  | SS27-MS | 14/10/2026 | 15/10/2026 |  |  | 2 |  | 2 |  |  | 2026-10-10 | 2026-12-10 | 15/09/2026 | 15/09/2026 | 2 | 2
ADIDAS | 0903274622-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 2 | 2026-07-10 | 2 | ID | ID10/07/2026 | G2K | T-SHIRT | G2 | (09/08/2026) | ok | (China). 825054 | PRINT L2 SUB PROCESS_V3 | 0903274622 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-07-10 | MER KA NNTEE M WHITE |  | SS27-MS | 2026-07-10 | 2026-07-10 |  |  | 2 |  | 2 |  |  | 2026-03-10 | 2026-03-10 | 26/08/2026 | 26/08/2026 | 2 | 1 | 1
ADIDAS | 0903274637-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 2 | 2026-07-10 | 2 | AN | AN10/07/2026 | G2F | T-SHIRT | G2 | (10/08/2026) | ok | (China). 825054 | PRINT L1 SUB PROCESS_V3 | 0903274637 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 13/10/2026 | MER KA GFTEE M BLACK |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 2 |  | 2 |  |  | 2026-09-10 | 2026-10-10 | 15/09/2026 | 15/09/2026 | 2 | 2
ADIDAS | 0903276235-1 KY5870 | GREY | 90D | S2750MTR052 | 114 | 15/10/2026 | 114 | SI | SI10/07/2026 | G2C | SHORTS | G2 | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 830009 | HT SUB PROCESS_V1 | 0903276235 KY5870 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | D74T ESS SHORTS GREY |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 114 |  | 114 |  |  | 25/09/2026 | 26/09/2026 |  |  | 114 |  | 114 |  |  | 24/09/2026 | 25/09/2026 |  |  | 114 |  | 114
ADIDAS | 0903305162-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 158 | 15/10/2026 | 158 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848016 | PRINT L2+PAD SUB PROCESS_V3 | 0903305162 LC8884 |  | KAHATEX CIJERAH | MOROCCO | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 158 |  | 158 |  |  | 2026-10-10 | 2026-12-10 | 15/09/2026 | 15/09/2026 | 158 | 144 | 14
ADIDAS | 0903305163-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 198 | 15/10/2026 | 198 | AN | AN10/07/2026 | G2I | T-SHIRT | G2 | ok | ok | 848012 | PRINT L2+PAD SUB PROCESS_V3 | 0903305163 LC8884 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 14/10/2026 | M RESORT T BLACK |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 198 |  | 198 |  |  | 2026-10-10 | 2026-12-10 | 26/08/2026 | 16/09/2026 | 198 | 197 | 1
ADIDAS | 0903305164-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436-MTF | 317 | 31/10/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903305164 KY5988 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903306652-1 KA6229 | BLACK | 120D | S2608WR0202 | 255 | 15/10/2026 | 255 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306652 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-05-11 | 2026-09-11 |  |  | 255 |  | 255 |  |  | 2026-02-11 | 2026-04-11 |  |  | 255 |  | 255 |  |  | 29/10/2026 | 31/10/2026 |  |  | 255 |  | 255
ADIDAS | 0903306653-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 15/10/2026 | 1009 | SA | SA15/07/2026 | G1B | SHORTS | G1 | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306653 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-09-11 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 2026-09-11 | 2026-11-11 |  |  | 1009 |  | 1009 |  |  | 2026-04-11 | 2026-06-11 |  |  | 1009 |  | 1009 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1009 |  | 1009
ADIDAS | 0903309141-1 KA4331 | BLACK | 90D | S2608MR0902 | 6720 | 15/10/2026 | 6720 | SA | SA20/07/2026 | G1D | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 25-Aug, ETD ?? T2 New Wide, PI Date 25-Aug, actual receives 10-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 28-Aug. 516333 | PAD+HT SUB PROCESS_V3 | 0903309141 KA4331 | 2026-02-10 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-03-10 | 13/10/2026 |  |  | 6720 |  | 6720 |  |  | 30/09/2026 | 2026-09-10 |  |  | 6720 |  | 6720 |  |  | 29/09/2026 | 2026-08-10 |  |  | 6720 |  | 6720
ADIDAS | 0903309142-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 3 | 15/10/2026 | 3 | AN | AN20/07/2026 | G2R | SHORTS | G2 |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? Waiting fabroc. T2 Formosa, PI Date ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309142 KZ3231 | 2026-02-10 | KAHATEX CIJERAH | UNITED STATES | SEA | 19/10/2026 | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 3 |  | 3 |  |  | 15/10/2026 | 15/10/2026 |  |  | 3 |  | 3
ADIDAS | 0903309143-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 28 | 15/10/2026 | 28 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309143 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 28 |  | 28 |  |  | 19/10/2026 | 20/10/2026 |  |  | 28 |  | 28 |  |  | 17/10/2026 | 19/10/2026 |  |  | 28 |  | 28
ADIDAS | 0903309144-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 1 | 15/10/2026 | 1 | SA | SA20/07/2026 | G1Q | T-SHIRT | G1 | ok |  | T2 Y.T.I, body & mesh actual receives 12-Aug. 600000 | HT SUB PROCESS_V1 | 0903309144 IT1469 | 16/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | ADIZERO E TEE |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 1 |  | 1 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1 |  | 1 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1 |  | 1
ADIDAS | 0903309880-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 28/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309880 JE6414 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 2637 |  | 2637 |  |  | 22/09/2026 | 26/09/2026 | 31/08/2026 | 2026-01-09 | 2637 | 2637
ADIDAS | 0903309881-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 6599 | 30/09/2026 | 6599 | SI | SI26/06/2026 | G2N,G2P | JACKET | G2 | (08/08/2026) | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309881 JE0052 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | W 3S FT FZ HD |  | SS27 | 22/09/2026 | 2026-06-10 |  |  | 6599 |  | 6599 |  |  | 18/09/2026 | 2026-02-10 |  |  | 6599 |  | 6599
ADIDAS | 0903309882-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 4400 | 30/09/2026 | 4400 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | (28/07/2026) | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309882 IB8686 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | ESS TEE |  | SS27 | 22/09/2026 | 25/09/2026 |  |  | 4400 |  | 4400 |  |  | 18/09/2026 | 22/09/2026 | 2026-02-09 | 17/09/2026 | 4400 | 4399 | 1
ADIDAS | 0903309883-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3522 | 30/09/2026 | 3522 | SA | SA26/06/2026 | G2R | JACKET | G2 | ok | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309883 JE6338 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | M 3S FT FZ HD |  | SS27 | 23/09/2026 | 30/09/2026 |  |  | 3522 |  | 3522 |  |  | 19/09/2026 | 26/09/2026 | 17/09/2026 | 19/09/2026 | 3522 | 2358 | 1164 |  | 13
ADIDAS | 0903309884-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1321 | 30/09/2026 | 1321 | SA | SA26/06/2026 | G2O | JACKET | G2 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309884 JE6340 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | M 3S FT FZ HD |  | SS27 | 25/09/2026 | 29/09/2026 |  |  | 1321 |  | 1321 |  |  | 22/09/2026 | 25/09/2026 |  |  | 1321 |  | 1321
ADIDAS | 0903309885-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 3277 | 31/10/2026 | 3277 | SA | SA10/07/2026 | G3B | SHORTS | G3 | ok | ok | T2 Libolon, PI Date 04-Aug, actual receives 27-Aug. T2 Gistex, PI Date 23-Aug, actual receives 14-Aug. 516318 | PAD+HT SUB PROCESS_V3 | 0903309885 IT3474 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI | 2026-04-11 | 2026-09-11 |  |  | 3277 |  | 3277 |  |  | 31/10/2026 | 2026-04-11 |  |  | 3277 |  | 3277 |  |  | 30/10/2026 | 2026-03-11 |  |  | 3277 |  | 3277
ADIDAS | 0903309886-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 7920 | 30/09/2026 | 7920 | SI | SI26/06/2026 | G3C,G3K | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309886 JD5302 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 25/09/2026 | W 3S FT CF PT |  | SS27 | 25/09/2026 | 30/09/2026 |  |  | 7920 |  | 7920 |  |  | 22/09/2026 | 26/09/2026 | 24/08/2026 | 19/09/2026 | 7920 | 6413 | 1507 |  | 609
ADIDAS | 0903309887-1 HZ0747 | BLACK | 90D | F2325M414 | 9088 | 30/09/2026 | 9088 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 26/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309887 HZ0747 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PL TEE |  | SS27 | 21/09/2026 | 30/09/2026 |  |  | 9088 |  | 9088 |  |  | 17/09/2026 | 26/09/2026 | 15/09/2026 | 19/09/2026 | 9088 | 3065 | 6023 |  | 20
ADIDAS | 0903309888-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 3520 | 30/09/2026 | 3520 | SA | SA26/06/2026 | G2T | JACKET | G2 | ok | ok | 28/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309888 JD1877 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 30/09/2026 | M 3S FT FZ HD |  | SS27 | 30/09/2026 | 2026-05-10 |  |  | 3520 |  | 3520 |  |  | 26/09/2026 | 2026-01-10 |  |  | 3520 |  | 3520
ADIDAS | 0903309889-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 6600 | 30/09/2026 | 6600 | SI | SI26/06/2026 | G2D,G2R | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309889 JE0055 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 14/09/2026 | W 3S FT FZ HD |  | SS27 | 14/09/2026 | 23/09/2026 | 16/09/2026 | 19/09/2026 | 6600 | 1564 | 5036 |  | 343 | 2026-10-09 | 19/09/2026 | 13/08/2026 | 18/09/2026 | 6600 | 5721 | 879
ADIDAS | 0903309890-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1050 | 15/10/2026 | 1050 | SI | SI10/07/2026 | G3A | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309890 JM1776 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M SL WV PT 2 |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 1050 |  | 1050 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1050 |  | 1050
ADIDAS | 0903309891-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1760 | 30/09/2026 | 1760 | SI | SI26/06/2026 | G1N | T-SHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309891 KD3911 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | RELEASED |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 1760 |  | 1760 |  |  | 18/09/2026 | 19/09/2026 |  |  | 1760 |  | 1760
ADIDAS | 0903309892-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1761 | 30/09/2026 | 1761 | SA | SA26/06/2026 | G2S | JACKET | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309892 JE6341 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | M 3S FT FZ HD |  | SS27 | 24/09/2026 | 28/09/2026 |  |  | 1761 |  | 1761 |  |  | 21/09/2026 | 24/09/2026 |  |  | 1761 |  | 1761
ADIDAS | 0903309893-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 6602 | 30/09/2026 | 6602 | SI | SI26/06/2026 | G1B | PANTS | G1 | ok | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309893 HR8583 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | ESS SWTP |  | SS27 | 28/09/2026 | 2026-10-10 |  |  | 6602 |  | 6602 |  |  | 24/09/2026 | 2026-07-10 |  |  | 6602 |  | 6602
ADIDAS | 0903309894-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 2637 | 30/09/2026 | 2637 | SA | SA26/06/2026 | G2E | SHORTS | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309894 JE6417 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 28/09/2026 | 2026-02-10 |  |  | 2637 |  | 2637 |  |  | 24/09/2026 | 29/09/2026 | 18/09/2026 | 19/09/2026 | 2637 | 2547 | 90 |  | 9
ADIDAS | 0903309895-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2638 | 30/09/2026 | 2638 | SA | SA26/06/2026 | G2Q | SHORTS | G2 | ok | ok | 24/09: ex-fty 516318 | EMBRO SUB PROCESS_V1 | 0903309895 JE6419 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 17/09/2026 | 23/09/2026 | 17/09/2026 | 19/09/2026 | 2638 | 1384 | 1254 |  | 292 | 14/09/2026 | 19/09/2026 | 29/08/2026 | 2026-08-09 | 2638 | 2484 | 154
ADIDAS | 0903309897-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 5722 | 30/09/2026 | 5722 | SI | SI26/06/2026 | G1R | PANTS | G1 | ok | ok | 28/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309897 HK7317 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 13/10/2026 |  |  | 5722 |  | 5722 |  |  | 25/09/2026 | 2026-09-10 |  |  | 5722 |  | 5722
ADIDAS | 0903309899-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 24312 | 19/09/2026 | 24312 | SA | SA10/07/2026 | G1D, G1E, G1F, G1K, G1L, G1N, G1P, G2A, G2R, G2T, G3A, G3D, G3G, G3H, G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 17/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309899 IB8688 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 19/09/2026 | 31/08/2026 | 17/09/2026 | 24312 | 24312 |  |  |  | 27/08/2026 | 16/09/2026 | 24/08/2026 | 17/09/2026 | 24312 | 24312
ADIDAS | 0903309900-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2100 | 15/10/2026 | 2100 | SA | SA10/07/2026 | G2Q | JACKET | G2 | ok | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309900 JE6338 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 2100 |  | 2100 |  |  | 13/10/2026 | 16/10/2026 |  |  | 2100 |  | 2100
ADIDAS | 0903309901-1 HK7319 | BLACK | 90D | F2225M403 | 5282 | 30/09/2026 | 5282 | SI | SI26/06/2026 | G1N | PANTS | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903309901 HK7319 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 29/09/2026 | ESS SWTP |  | SS27 | 29/09/2026 | 2026-12-10 |  |  | 5282 |  | 5282 |  |  | 25/09/2026 | 2026-08-10 | 15/09/2026 | 19/09/2026 | 5282 | 3383 | 1899 |  | 956
ADIDAS | 0903309902-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2940 | 15/10/2026 | 2940 | SA | SA10/07/2026 | G2Q | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309902 JD1877 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-10 | M 3S FT FZ HD |  | SS27 | 2026-09-10 | 14/10/2026 |  |  | 2940 |  | 2940 |  |  | 2026-06-10 | 2026-10-10 |  |  | 2940 |  | 2940
ADIDAS | 0903309903-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1051 | 15/10/2026 | 1051 | SI | SI10/07/2026 | G3C | PANTS | G3 | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903309903 JM1775 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M SL WV PT 2 |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 1051 |  | 1051 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1051 |  | 1051
ADIDAS | 0903309904-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 24142 | 19/09/2026 | 24142 | SA | SA10/07/2026 | G1E,G1F,G1K,G1N,G1P,G2A,G2R,G2T,G3A,G3G,G3H,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 18/09: ex-fty 9, 182pcs. 17/09: ex-fty 14, 960pcs (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309904 HK7311 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 19/09/2026 | 2026-01-09 | 17/09/2026 | 24142 | 24142 |  |  |  | 27/08/2026 | 16/09/2026 | 2026-01-09 | 17/09/2026 | 24142 | 24142
ADIDAS | 0903309905-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2642 | 30/09/2026 | 2642 | SI | SI26/06/2026 | G3J | SHORTS | G3 | ok | ok | 24/09: ex-fty. T2 Gistex, (3S) PI Date 10-Aug, actual receives 06-Aug (using fabric stock from libolon). T2 Libolon, (Body) PI Date 20-Jul, actual receives 09-Jul. 1st Art (TC 10 pcs) 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309905 JE1309 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 28/09/2026 | W 3S WV SHO |  | SS27 | 28/09/2026 | 2026-01-10 |  |  | 2642 |  | 2642 |  |  | 24/09/2026 | 28/09/2026 |  |  | 2642 |  | 2642
ADIDAS | 0903309907-1 HK7309 | BLACK | 45D | F2225M402 | 24310 | 19/09/2026 | 24310 | SA | SA10/07/2026 | G1D,G1E,G1F,G1K,G1N,G1P,G2R,G2T,G3G,G3I | SWEATSHIRT | G1,G2,G3 | ok | ok | 18/09: ex-fty (FCL 7x40, 1x20). DRC 0027-EX-FACTORY DATE ADIDAS FREIGHT SCHEDULE. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903309907 HK7309 | 2026-11-08 | KAHATEX CIJERAH | GERMANY | SEA | 31/08/2026 | ESS HDY |  | SS27 | 31/08/2026 | 19/09/2026 | 28/08/2026 | 17/09/2026 | 24310 | 24310 |  |  |  | 27/08/2026 | 16/09/2026 | 27/08/2026 | 16/09/2026 | 24310 | 24310
ADIDAS | 0903309908-1 KF5295 | FROZEN PURPLE F26 | 105D | S2608WR0902 | 3591 | 31/10/2026 | 3591 | SI | SI10/07/2026 | G2D | SHORTS | G2 | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516318 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903309908 KF5295 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA | 26/10/2026 | Run Ess 21 S FROZEN PURPLE F26 |  | SS27-TRAX | 26/10/2026 | 31/10/2026 |  |  | 3591 |  | 3591 |  |  | 22/10/2026 | 28/10/2026 |  |  | 3591 |  | 3591 |  |  | 19/10/2026 | 24/10/2026 |  |  | 3591 |  | 3591
ADIDAS | 0903309910-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1512 | 15/10/2026 | 1512 | SA | SA10/07/2026 | G2R | JACKET | G2 | (20/08/2026) | ok | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903309910 JE6341 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-10 | M 3S FT FZ HD |  | SS27 | 2026-10-10 | 14/10/2026 |  |  | 1512 |  | 1512 |  |  | 2026-07-10 | 2026-10-10 |  |  | 1512 |  | 1512
ADIDAS | 0903316928-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 327 | 30/09/2026 | 327 | SA | SA03/07/2026 | G1M | T-SHIRT | G1 | ok |  | 29/09: ex-fty (NYK warehouse). T2 Y.T.I, Body & mesh actual receives 05-Aug. 800005 | HT SUB PROCESS_V1 | 0903316928 KG8548 | 17/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 21/09/2026 | 2026-05-09 | 15/09/2026 | 327 | 325 | 2 |  |  | 29/08/2026 | 18/09/2026 | 2026-11-08 | 22/08/2026 | 327 | 327 |  |  |  | 28/08/2026 | 17/09/2026 | 2026-11-08 | 21/08/2026 | 327 | 327
ADIDAS | 0903316929-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 585 | 30/09/2026 | 585 | AN | AN23/06/2026 | G2D | T-SHIRT | G2 | (31/07/2026) |  | (NYK warehouse). DRC 0064-T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives 11-Sep. 800005 | PRINT L2+HT SUB PROCESS_V3 | 0903316929 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | INDONESIA | SEA | 21/09/2026 | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX | 21/09/2026 | 22/09/2026 |  |  | 585 |  | 585 |  |  | 17/09/2026 | 18/09/2026 | 19/09/2026 | 19/09/2026 | 585 | 218 | 367 |  | 218 | 16/09/2026 | 17/09/2026 | 18/09/2026 | 19/09/2026 | 585 | 272 | 313 |  | 182
ADIDAS | 0903316930-1 KG8547 | ONIX | 90D | S2408WR1600 | 107 | 15/10/2026 | 107 | SI | SI30/06/2026 | G1I | T-SHIRT | G1 | ok |  | (NYK warehouse). T2 Y.T.I, body & mesh actual receives 08-Aug. 800005 | HT SUB PROCESS_V1 | 0903316930 KG8547 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 13/10/2026 | ADIZERO E TEE |  | SS27-YTI | 13/10/2026 | 14/10/2026 |  |  | 107 |  | 107 |  |  | 2026-10-10 | 2026-12-10 |  |  | 107 |  | 107 |  |  | 2026-09-10 | 2026-10-10 |  |  | 107 |  | 107
ADIDAS | 0903316932-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 798 | 31/10/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316932 KY9391 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903322460-1 IN1159 | BLACK | 90D | S2408MR1601 | 331 | 2026-07-10 | 331 | SA | SA26/06/2026 | G1P | SHORTS | G1 | (01/09/2026) |  | Waiting fabric. DRC 0002-T2 Hua Feng, material delayed, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322460 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | ADIZERO E SHORT BLACK |  | SS27-TRAX | 2026-05-10 | 2026-07-10 |  |  | 331 |  | 331 |  |  | 2026-01-10 | 2026-03-10 |  |  | 331 |  | 331 |  |  | 28/09/2026 | 30/09/2026 |  |  | 331 |  | 331
ADIDAS | 0903322461-1 IN1157 | WHITE | 90D | S2408MR1600 | 335 | 15/10/2026 | 335 | SA | SA30/06/2026 | G1R | T-SHIRT | G1 | ok | ok | T2 Y.T.I, Body & mesh actual receives 06-Aug. 516471 | HT SUB PROCESS_V1 | 0903322461 IN1157 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | ADIZERO E TEE |  | SS27-YTI | 20/10/2026 | 21/10/2026 |  |  | 335 |  | 335 |  |  | 17/10/2026 | 19/10/2026 | 2026-09-09 | 17/09/2026 | 335 | 310 | 25 |  |  | 16/10/2026 | 17/10/2026 | 2026-02-09 | 17/09/2026 | 335 | 310 | 25
ADIDAS | 0903322476-1 IN1157 | WHITE | 90D | S2408MR1600 | 845 | 2026-07-10 | 845 | SA | SA07/07/2026 | G1R | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, actual receives 06-Aug. T2 Fu Hsun, Mesh PI Date 03-Aug, actual receives 06-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322476 IN1157 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 19/10/2026 |  |  | 845 |  | 845 |  |  | 14/10/2026 | 16/10/2026 | 2026-10-09 | 16/09/2026 | 845 | 828 | 17 |  |  | 13/10/2026 | 15/10/2026 | 2026-03-09 | 14/09/2026 | 845 | 831 | 14
ADIDAS | 0903322477-1 IN1156 | BLACK | 90D | S2408MR1600 | 553 | 15/09/2026 | 553 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322477 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-02-09 | 2026-05-09 | 553 | 553 |  |  |  | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-02-09 | 553 | 553
ADIDAS | 0903322478-1 IN1173 | WHITE | 90D | S2408WR1600 | 304 | 15/09/2026 | 304 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. 516471 | HT SUB PROCESS_V1 | 0903322478 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 15/09/2026 | 2026-04-09 | 15/09/2026 | 304 | 304 |  |  |  | 29/08/2026 | 2026-12-09 | 15/08/2026 | 15/08/2026 | 304 | 304 |  |  |  | 28/08/2026 | 2026-11-09 | 2026-11-08 | 2026-11-08 | 304 | 304
ADIDAS | 0903322479-1 IN1172 | BLACK | 90D | S2408WR1600 | 807 | 15/09/2026 | 807 | SI | SI07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322479 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-01-09 | ADIZERO E TEE |  | SS27-YTI | 2026-01-09 | 2026-02-09 | 2026-03-09 | 15/09/2026 | 807 | 807 |  |  |  | 29/08/2026 | 31/08/2026 | 26/08/2026 | 14/09/2026 | 807 | 807 |  |  |  | 28/08/2026 | 29/08/2026 | 26/08/2026 | 2026-12-09 | 807 | 807
ADIDAS | 0903322480-1 IN1156 | BLACK | 90D | S2408MR1600 | 924 | 15/09/2026 | 924 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 15/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) 516471 | HT SUB PROCESS_V1 | 0903322480 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 29/08/2026 | ADIZERO E TEE |  | SS27-YTI | 29/08/2026 | 2026-02-09 | 2026-01-09 | 15/09/2026 | 924 | 924 |  |  |  | 27/08/2026 | 31/08/2026 | 22/08/2026 | 2026-09-09 | 924 | 924 |  |  |  | 26/08/2026 | 29/08/2026 | 22/08/2026 | 2026-08-09 | 924 | 924
ADIDAS | 0903322484-1 IN1156 | BLACK | 90D | S2408MR1600 | 300 | 2026-07-10 | 300 | SA | SA07/07/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Far Eastern, PI Date 21-Sep, actual receives 07-Aug (using fabric from Y.T.I.). T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). 516471 | HT SUB PROCESS_V1 | 0903322484 IN1156 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | ADIZERO E TEE |  | SS27-YTI | 2026-07-10 | 2026-08-10 |  |  | 300 |  | 300 |  |  | 2026-05-10 | 2026-06-10 | 26/08/2026 | 2026-02-09 | 300 | 297 | 3 |  |  | 2026-03-10 | 2026-05-10 | 24/08/2026 | 2026-05-09 | 300 | 300
ADIDAS | 0903322486-1 IN1172 | BLACK | 90D | S2408WR1600 | 265 | 15/10/2026 | 265 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322486 IN1172 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ADIZERO E TEE |  | SS27-YTI | 16/10/2026 | 17/10/2026 |  |  | 265 |  | 265 |  |  | 14/10/2026 | 15/10/2026 |  |  | 265 |  | 265 |  |  | 13/10/2026 | 14/10/2026 | 2026-05-09 | 15/09/2026 | 265 | 204 | 61
ADIDAS | 0903322488-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 352 | 2026-07-10 | 352 | SA | SA03/07/2026 | G1N | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 12-Aug. 516471 | HT SUB PROCESS_V1 | 0903322488 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | ADIZERO E TEE |  | SS27-YTI | 17/10/2026 | 19/10/2026 |  |  | 352 |  | 352 |  |  | 15/10/2026 | 16/10/2026 | 2026-07-09 | 19/09/2026 | 352 | 350 | 2 |  | 175 | 14/10/2026 | 15/10/2026 | 2026-07-09 | 2026-12-09 | 352 | 177 | 175
ADIDAS | 0903322491-1 IN1172 | BLACK | 90D | S2408WR1600 | 324 | 30/09/2026 | 324 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. 516471 | HT SUB PROCESS_V1 | 0903322491 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/09/2026 | ADIZERO E TEE |  | SS27-YTI | 16/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 324 | 290 | 34 |  | 276 | 14/09/2026 | 17/09/2026 | 26/08/2026 | 2026-07-09 | 324 | 324 |  |  |  | 2026-12-09 | 16/09/2026 | 26/08/2026 | 2026-04-09 | 324 | 324
ADIDAS | 0903322492-1 IT1824 | TEAM POWER RED 2 | 90D | S2408WR1600-MTF | 254 | 2026-07-10 | 254 | NT | NT24/04/2026 | G1M | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Libolon, using fabric stock. T2 Fu Hsun, using fabric stock. 516471 | HT SUB PROCESS_V1 | 0903322492 IT1824 | 14/07/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | ADIZERO E TEE |  | FW26 | 2026-08-10 | 2026-08-10 |  |  | 254 |  | 254 |  |  | 2026-06-10 | 2026-06-10 | 2026-05-08 | 2026-10-08 | 254 | 254 |  |  |  | 2026-05-10 | 2026-05-10 | 2026-05-08 | 2026-10-08 | 254 | 254
ADIDAS | 0903322493-1 IN1156 | BLACK | 90D | S2408MR1600 | 372 | 23/10/2026 | 372 | SA | SA10/07/2026 | G1Q | T-SHIRT | G1 | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322493 IN1156 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | ADIZERO E TEE |  | SS27-YTI | 28/10/2026 | 29/10/2026 |  |  | 372 |  | 372 |  |  | 26/10/2026 | 27/10/2026 |  |  | 372 |  | 372 |  |  | 24/10/2026 | 26/10/2026 |  |  | 372 |  | 372
ADIDAS | 0903348712-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 634 | 31/10/2026 | 634 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348712 KU0073 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX | 2026-03-11 | 2026-04-11 |  |  | 634 |  | 634 |  |  | 30/10/2026 | 31/10/2026 |  |  | 634 |  | 634
ADIDAS | 0903348833-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 1013 | 31/10/2026 | 1013 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348833 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-11 | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX | 2026-04-11 | 2026-05-11 |  |  | 1013 |  | 1013 |  |  | 31/10/2026 | 2026-02-11 |  |  | 1013 |  | 1013
ADIDAS | 0903348882-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 858 | 31/10/2026 | 858 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903348882 KY1335 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/11/2026 | M PANCAKE T OFF WHITE |  | SS27-STX | 21/11/2026 | 23/11/2026 |  |  | 858 |  | 858 |  |  | 18/11/2026 | 18/11/2026 |  |  | 858 |  | 858
ADIDAS | 0903351210-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 285 | 31/10/2026 | 285 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903351210 KS4777 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX | 2026-03-11 | 2026-04-11 |  |  | 285 |  | 285 |  |  | 30/10/2026 | 31/10/2026 |  |  | 285 |  | 285
ADIDAS | 0903353792-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 117 | 31/10/2026 | 117 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353792 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-11 | 3S TEE SLIM WHITE/BLACK |  | SS27-STX | 2026-03-11 | 2026-03-11 |  |  | 117 |  | 117 |  |  | 30/10/2026 | 30/10/2026 |  |  | 117 |  | 117
ADIDAS | 0903353862-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353862 KC6387 |  | KAHATEX CIJERAH | VIETNAM | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 400 |  | 400 |  |  | 26/09/2026 | 26/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903354120-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 244 | 31/10/2026 | 244 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903354120 KU3269 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | 3S RINGER T |  | SS27-STX | 22/10/2026 | 23/10/2026 |  |  | 244 |  | 244 |  |  | 19/10/2026 | 20/10/2026 |  |  | 244 |  | 244
ADIDAS | 0903356221-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 594 | 31/10/2026 | 594 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903356221 KU3274 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | 3S RINGER T |  | SS27-STX | 22/10/2026 | 23/10/2026 |  |  | 594 |  | 594 |  |  | 19/10/2026 | 20/10/2026 |  |  | 594 |  | 594
ADIDAS | 0903356606-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 104 | 31/10/2026 | 104 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903356606 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 22/10/2026 | 3S RINGER T |  | SS27-STX | 22/10/2026 | 23/10/2026 |  |  | 104 |  | 104 |  |  | 19/10/2026 | 20/10/2026 |  |  | 104 |  | 104
ADIDAS | 0903357761-1 KA4331 | BLACK | 90D | S2608MR0902 | 1089 | 31/10/2026 | 1089 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357761 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 25/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 25/11/2026 | 27/11/2026 |  |  | 1089 |  | 1089 |  |  | 20/11/2026 | 24/11/2026 |  |  | 1089 |  | 1089 |  |  | 19/11/2026 | 23/11/2026 |  |  | 1089 |  | 1089
ADIDAS | 0903357814-1 KA4331 | BLACK | 90D | S2608MR0902 | 343 | 31/10/2026 | 343 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | PAD+HT SUB PROCESS_V3 | 0903357814 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 18/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 18/11/2026 | 20/11/2026 |  |  | 343 |  | 343 |  |  | 13/11/2026 | 17/11/2026 |  |  | 343 |  | 343 |  |  | 2026-12-11 | 16/11/2026 |  |  | 343 |  | 343
ADIDAS | 0903357841-1 KA4331 | BLACK | 90D | S2608MR0902 | 816 | 31/10/2026 | 816 | SA | SA31/07/2026 | G1G | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357841 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 20/11/2026 | 21/11/2026 |  |  | 816 |  | 816 |  |  | 17/11/2026 | 18/11/2026 |  |  | 816 |  | 816 |  |  | 16/11/2026 | 17/11/2026 |  |  | 816 |  | 816
ADIDAS | 0903361428-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 369 | 23/09/2026 | 369 | SA | SA31/07/2026 | G2B | T-SHIRT | G2 | ok |  | 23/09: ex-fty 1st Art (TC 10 pcs) 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361428 KT7554 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/09/2026 | M CLUB AM TAT |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 369 |  | 369 |  |  | 17/09/2026 | 18/09/2026 | 2026-11-09 | 17/09/2026 | 369 | 357 | 12
ADIDAS | 0903361463-1 KT7554 | OFF WHITE | 60D | F26FBGFXP105 | 887 | 31/10/2026 | 887 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903361463 KT7554 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 24/10/2026 | M CLUB AM TAT |  | SS27 | 24/10/2026 | 24/10/2026 |  |  | 887 |  | 887 |  |  | 21/10/2026 | 21/10/2026 | 2026-12-09 | 14/09/2026 | 887 | 862 | 25
ADIDAS | 0903361907-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1504 | 31/10/2026 | 1504 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361907 KD7980 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-11 | 3S TEE SLIM BLACK/WHITE |  | SS27-STX | 2026-05-11 | 2026-07-11 |  |  | 1504 |  | 1504 |  |  | 2026-02-11 | 2026-04-11 |  |  | 1504 |  | 1504
ADIDAS | 0903361937-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 400 | 15/10/2026 | 400 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361937 KD9090 |  | KAHATEX CIJERAH | VIETNAM | SEA | 29/09/2026 | K BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 400 |  | 400 |  |  | 25/09/2026 | 26/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903362010-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 237 | 31/10/2026 | 237 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903362010 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA | 20/11/2026 | M PANCAKE T OFF WHITE |  | SS27-STX | 20/11/2026 | 21/11/2026 |  |  | 237 |  | 237 |  |  | 17/11/2026 | 18/11/2026 |  |  | 237 |  | 237
ADIDAS | 0903362075-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 531 | 15/09/2026 | 531 | ID | ID31/07/2026 | G2H | T-SHIRT | G2 | ok |  | 14/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903362075 KB5965 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-05-09 | Run Ess Tee M |  | SS27-TI-SLT | 2026-05-09 | 2026-08-09 | 2026-04-09 | 2026-08-09 | 531 | 531 |  |  |  | 2026-02-09 | 2026-04-09 | 29/08/2026 | 2026-08-09 | 531 | 531 |  |  |  | 31/08/2026 | 2026-02-09 | 29/08/2026 | 2026-07-09 | 531 | 531
ADIDAS | 0903363689-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 2740 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903363689 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903364417-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 367 | 31/10/2026 | 367 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903364417 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 367 |  | 367 |  |  | 2026-06-10 | 2026-07-10 |  |  | 367 |  | 367
ADIDAS | 0903364604-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 702 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903364604 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903365140-1 IS1413 | BLACK | 60D | S2425M405 | 241 | 31/10/2026 | 241 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903365140 IS1413 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-10 | IN RANGE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 241 |  | 241 |  |  | 2026-07-10 | 2026-08-10 |  |  | 241 |  | 241
ADIDAS | 0903365289-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 650 | 2026-07-10 | 650 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365289 KB5965 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-06-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-06-10 | 2026-07-10 |  |  | 650 |  | 650 |  |  | 2026-02-10 | 2026-03-10 |  |  | 650 |  | 650 |  |  | 30/09/2026 | 2026-01-10 |  |  | 650 |  | 650
ADIDAS | 0903365322-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 500 | 2026-07-10 | 500 | ID | ID31/07/2026 | G2I | T-SHIRT | G2 | ok |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903365322 KB5960 | 29/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA | 2026-05-10 | Run Ess Tee M |  | SS27-TI-SLT | 2026-05-10 | 2026-06-10 |  |  | 500 |  | 500 |  |  | 2026-01-10 | 2026-02-10 | 27/08/2026 | 16/09/2026 | 500 | 400 | 100 |  |  | 29/09/2026 | 30/09/2026 | 27/08/2026 | 29/08/2026 | 500 | 500
ADIDAS | 0903366562-1 IS1413 | BLACK | 60D | S2425M405 | 7 | 23/09/2026 | 7 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903366562 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 21/09/2026 |  |  | 7 |  | 7 |  |  | 2026-11-09 | 17/09/2026 |  |  | 7 |  | 7
ADIDAS | 0903366668-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 101 | 31/10/2026 | 101 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366668 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 22/10/2026 | 3S RINGER T |  | SS27-STX | 22/10/2026 | 23/10/2026 |  |  | 101 |  | 101 |  |  | 19/10/2026 | 20/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903367183-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 1603 | 31/10/2026 | 1603 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367183 KD7980 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-07-11 | 3S TEE SLIM BLACK/WHITE |  | SS27-STX | 2026-07-11 | 2026-09-11 |  |  | 1603 |  | 1603 |  |  | 2026-04-11 | 2026-04-11 |  |  | 1603 |  | 1603
ADIDAS | 0903367215-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 303 | 21/10/2026 | 303 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | PRINT L3 SUB PROCESS_V3 | 0903367215 IU0217 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-10-10 |  |  | 303 |  | 303 |  |  | 2026-06-10 | 2026-07-10 |  |  | 303 |  | 303
ADIDAS | 0903367328-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 277 | 31/10/2026 | 277 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367328 KD3683 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | 3S TEE SLIM WHITE/BLACK |  | SS27-STX | 2026-03-11 | 2026-03-11 |  |  | 277 |  | 277 |  |  | 30/10/2026 | 30/10/2026 |  |  | 277 |  | 277
ADIDAS | 0903368244-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 | 1379 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903368244 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-02-11 | ESS SWTP |  | SS27 | 2026-02-11 | 2026-05-11 |  |  | 1379 |  | 1379 |  |  | 29/10/2026 | 2026-02-11 |  |  | 1379 |  | 1379
ADIDAS | 0903368357-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 | 690 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368357 JE6340 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 21/10/2026 | M 3S FT FZ HD |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 690 |  | 690 |  |  | 17/10/2026 | 20/10/2026 |  |  | 690 |  | 690
ADIDAS | 0903368397-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 | 461 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516205 | HT SUB PROCESS_V1 | 0903368397 JC9584 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 461 |  | 461 |  |  | 16/10/2026 | 17/10/2026 |  |  | 461 |  | 461 |  |  | 15/10/2026 | 16/10/2026 |  |  | 461 |  | 461
ADIDAS | 0903368443-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 | 1150 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368443 JE6341 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | M 3S FT FZ HD |  | SS27 | 14/10/2026 | 16/10/2026 |  |  | 1150 |  | 1150 |  |  | 2026-10-10 | 13/10/2026 |  |  | 1150 |  | 1150
ADIDAS | 0903368477-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 | 2070 | SA | SA31/07/2026 | G2F | JACKET | G2 | (16/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903368477 JE6338 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 24/10/2026 | M 3S FT FZ HD |  | SS27 | 24/10/2026 | 28/10/2026 |  |  | 2070 |  | 2070 |  |  | 21/10/2026 | 24/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903368508-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4599 | 31/10/2026 | 4599 | SI | SI31/07/2026 | G3I | JACKET | G3 | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903368508 JE0052 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 24/10/2026 | W 3S FT FZ HD |  | SS27 | 24/10/2026 | 2026-02-11 |  |  | 4599 |  | 4599 |  |  | 21/10/2026 | 29/10/2026 |  |  | 4599 |  | 4599
ADIDAS | 0903368552-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2520 | 15/09/2026 | 2520 | SA | SA31/07/2026 | G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368552 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 2520 | 2520 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-09-09 | 16/09/2026 | 2520 | 2520
ADIDAS | 0903368598-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903368598 JE6414 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 21/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 21/10/2026 | 24/10/2026 |  |  | 1380 |  | 1380 |  |  | 17/10/2026 | 21/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903368635-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 401 | 15/09/2026 | 401 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903368635 HK7311 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 2026-11-09 | 401 | 401 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-10-09 | 16/09/2026 | 401 | 401
ADIDAS | 0903369017-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 535 | 30/09/2026 | 535 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | ok |  | 25/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369017 IU0217 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 25/09/2026 | IN RANGE |  | SS27 | 25/09/2026 | 26/09/2026 |  |  | 535 |  | 535 |  |  | 22/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 535 | 451 | 84 |  | 451
ADIDAS | 0903369058-1 IS1413 | BLACK | 60D | S2425M405 | 374 | 23/09/2026 | 374 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 22/09: ex-fty 672027 | PRINT L3 SUB PROCESS_V3 | 0903369058 IS1413 | 16/09/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 15/09/2026 | IN RANGE |  | SS27 | 15/09/2026 | 21/09/2026 |  |  | 374 |  | 374 |  |  | 2026-11-09 | 17/09/2026 | 17/09/2026 | 17/09/2026 | 374 | 333 | 41
ADIDAS | 0903369096-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 514 | 30/09/2026 | 514 | SI | SI31/07/2026 | G2B | T-SHIRT | G2 | ok |  | 24/09: ex-fty 672027 | PRINT L3+PAD SUB PROCESS_V3 | 0903369096 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | BRAZIL | SEA | 26/09/2026 | POS TABLE LK |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 514 |  | 514 |  |  | 23/09/2026 | 23/09/2026 | 2026-08-09 | 16/09/2026 | 514 | 510 | 4
ADIDAS | 0903369734-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 100 | 28/10/2026 | 100 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | PRINT L3 SUB PROCESS_V3 | 0903369734 IU0217 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 100 |  | 100 |  |  | 2026-06-10 | 2026-06-10 |  |  | 100 |  | 100
ADIDAS | 0903370112-1 IS1413 | BLACK | 60D | S2425M405 | 109 | 31/10/2026 | 109 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903370112 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-10-10 | IN RANGE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 109 |  | 109 |  |  | 2026-07-10 | 2026-08-10 |  |  | 109 |  | 109
ADIDAS | 0903370723-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 | 2300 | SA | SA31/07/2026 | G2E | JACKET | G2 | (12/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370723 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 23/10/2026 |  |  | 2300 |  | 2300 |  |  | 15/10/2026 | 20/10/2026 |  |  | 2300 |  | 2300
ADIDAS | 0903370771-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 | 1839 | SA | SA31/07/2026 | G3E | PANTS | G3 | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903370771 JW7178 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-04-11 | W 3S FT OH PT |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 1839 |  | 1839 |  |  | 31/10/2026 | 2026-03-11 |  |  | 1839 |  | 1839
ADIDAS | 0903370821-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 2100 | 31/10/2026 | 2100 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903370821 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | M 3S FT FZ HD |  | SS27 | 16/10/2026 | 22/10/2026 |  |  | 2100 |  | 2100 |  |  | 13/10/2026 | 19/10/2026 |  |  | 2100 |  | 2100
ADIDAS | 0903370885-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370885 IB8688 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 1840 | 1840 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-12-09 | 16/09/2026 | 1840 | 1835 | 5
ADIDAS | 0903370934-1 HK7309 | BLACK | 45D | F2225M402 | 399 | 15/09/2026 | 399 | SA | SA31/07/2026 | G1K | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370934 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-10-09 | 14/09/2026 | 399 | 399 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-09-09 | 14/09/2026 | 399 | 399
ADIDAS | 0903370987-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 600 | 15/09/2026 | 600 | SA | SA31/07/2026 | G2A | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903370987 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-09 | ESS HDY |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 600 | 600 |  |  |  | 2026-04-09 | 2026-11-09 | 2026-08-09 | 17/09/2026 | 600 | 600
ADIDAS | 0903371005-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 124 | 31/10/2026 | 124 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371005 JD5308 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | W 3S FT CF PT |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 124 |  | 124 |  |  | 2026-04-11 | 2026-05-11 |  |  | 124 |  | 124
ADIDAS | 0903371033-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 4200 | 31/10/2026 | 4200 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903371033 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/10/2026 | M 3S FT FZ HD |  | SS27 | 19/10/2026 | 24/10/2026 |  |  | 4200 |  | 4200 |  |  | 15/10/2026 | 21/10/2026 |  |  | 4200 |  | 4200
ADIDAS | 0903371106-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1800 | 15/10/2026 | 1800 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903371106 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | RELEASED |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 1800 |  | 1800 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1800 |  | 1800
ADIDAS | 0903371252-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371252 JE6377 |  | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | M 3S FT SWT |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903371280-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (16/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371280 JE6374 |  | KAHATEX CIJERAH | PERU | SEA | 16/10/2026 | M 3S FT SWT |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903371315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 310 | 31/10/2026 | 310 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371315 JE6372 |  | KAHATEX CIJERAH | PERU | SEA | 17/10/2026 | M 3S FT SWT |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 310 |  | 310 |  |  | 14/10/2026 | 14/10/2026 |  |  | 310 |  | 310
ADIDAS | 0903371346-1 IC5188 | BLACK | 90D | S23080640 | 802 | 31/10/2026 | 802 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371346 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 802 |  | 802 |  |  | 28/10/2026 | 29/10/2026 |  |  | 802 |  | 802 |  |  | 27/10/2026 | 28/10/2026 |  |  | 802 |  | 802
ADIDAS | 0903371391-1 IC5189 | WHITE | 90D | S23080640 | 601 | 31/10/2026 | 601 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371391 IC5189 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 31/10/2026 | OWN THE RUN TEE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 601 |  | 601 |  |  | 29/10/2026 | 31/10/2026 |  |  | 601 |  | 601 |  |  | 28/10/2026 | 30/10/2026 |  |  | 601 |  | 601
ADIDAS | 0903371424-1 IC5188 | BLACK | 90D | S23080640 | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 659018 | HT SUB PROCESS_V1 | 0903371424 IC5188 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 29/10/2026 | OWN THE RUN TEE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 301 |  | 301 |  |  | 27/10/2026 | 28/10/2026 |  |  | 301 |  | 301 |  |  | 26/10/2026 | 27/10/2026 |  |  | 301 |  | 301
ADIDAS | 0903371472-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 400 | 2026-02-10 | 400 | SI | SI31/07/2026 | G2P | SWEATSHIRT | G2 | (16/09/2026) |  | 30/09: ex-fty. DRC 0090-early shipment customer (BTP_28_08_2026 EARLY HOLD SHIPMENT). 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903371472 JE6374 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA | 26/09/2026 | M 3S FT SWT |  | SS27 | 26/09/2026 | 28/09/2026 |  |  | 400 |  | 400 |  |  | 23/09/2026 | 24/09/2026 |  |  | 400 |  | 400
ADIDAS | 0903371511-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 304 | 2026-09-09 | 304 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 848016 | PRINT L3+PAD SUB PROCESS_V3 | 0903371511 IW2479 | 2026-03-09 | KAHATEX CIJERAH | MOROCCO | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 304 | 304 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 304 | 304
ADIDAS | 0903372005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 389 | 31/10/2026 | 389 | SI | SI31/07/2026 | G3I | JACKET | G3 | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 14/10/2026 | W 3S FT FZ HD |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 389 |  | 389 |  |  | 2026-10-10 | 2026-12-10 |  |  | 389 |  | 389
ADIDAS | 0903372035-1 JC5948 | BLACK/WHITE | 90D | S2554WES428FT | 2021 | 31/10/2026 | 2021 | SA | SA31/07/2026 | G1A | PANTS | G1 | (12/09/2026) |  | (Mexico). 1st Art (TC 10 pcs) 652001 | PRINT L1 SUB PROCESS_V3 | 0903372035 JC5948 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 2026-03-11 | W LIN FT CF PT |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 2021 |  | 2021 |  |  | 30/10/2026 | 2026-02-11 |  |  | 2021 |  | 2021
ADIDAS | 0903372134-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2083 | 31/10/2026 | 2083 | SA | SA31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | (Mexico). 652001 | EMBRO SUB PROCESS_V1 | 0903372134 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 23/10/2026 | 28/10/2026 |  |  | 2083 |  | 2083 |  |  | 20/10/2026 | 24/10/2026 |  |  | 2083 |  | 2083
ADIDAS | 0903372828-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT-SLT | 149 | 2026-09-09 | 149 | ID | ID31/07/2026 | G3K | PANTS | G3 | ok |  | 09/09: ex-fty 838103 | EMBRO SUB PROCESS_V1 | 0903372828 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/08/2026 | M 3S FT TC PT |  | SS27-SLT | 31/08/2026 | 2026-09-09 | 2026-03-09 | 2026-09-09 | 149 | 149 |  |  |  | 27/08/2026 | 2026-05-09 | 31/08/2026 | 2026-07-09 | 149 | 149
ADIDAS | 0903372885-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372885 HK7309 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-09 | ESS HDY |  | SS27 | 2026-05-09 | 14/09/2026 | 2026-09-09 | 15/09/2026 | 1495 | 1495 |  |  |  | 2026-02-09 | 2026-10-09 | 2026-08-09 | 16/09/2026 | 1495 | 1490 | 5
ADIDAS | 0903372932-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 959 | 31/10/2026 | 959 | SA | SA31/07/2026 | G3E | PANTS | G3 | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372932 JW7178 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 31/10/2026 | W 3S FT OH PT |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 959 |  | 959 |  |  | 28/10/2026 | 29/10/2026 |  |  | 959 |  | 959
ADIDAS | 0903372967-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 296 | 30/09/2026 | 296 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 516333 | PRINT L3 SUB PROCESS_V3 | 0903372967 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 296 |  | 296 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 18/09/2026 | 296 | 289 | 7
ADIDAS | 0903372970-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1079 | 31/10/2026 | 1079 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372970 JD5302 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-11 | W 3S FT CF PT |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 1079 |  | 1079 |  |  | 2026-05-11 | 2026-06-11 |  |  | 1079 |  | 1079
ADIDAS | 0903373006-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373006 HK7311 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-03-09 | ESS HDY |  | SS27 | 2026-03-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  |  | 31/08/2026 | 2026-11-09 | 2026-09-09 | 16/09/2026 | 1379 | 1379
ADIDAS | 0903373044-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1200 | 31/10/2026 | 1200 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373044 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/10/2026 | M 3S FT FZ HD |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1200 |  | 1200 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903373080-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903373080 JE6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/10/2026 | M 3S FT FZ HD |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 600 |  | 600 |  |  | 21/10/2026 | 23/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903373118-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1840 | 15/09/2026 | 1840 | SA | SA31/07/2026 | G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug.. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373118 IB8688 | 2026-03-09 | KAHATEX CIJERAH | SPAIN | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 14/09/2026 | 1840 | 1840 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-09-09 | 15/09/2026 | 1840 | 1840
ADIDAS | 0903373141-1 HK7319 | BLACK | 90D | F2225M403 | 276 | 31/10/2026 | 276 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 512102 | EMBRO+PPA SUB PROCESS_V3 | 0903373141 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/10/2026 | ESS SWTP |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 276 |  | 276 |  |  | 17/10/2026 | 19/10/2026 |  |  | 276 |  | 276
ADIDAS | 0903373659-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1680 | 31/10/2026 | 1680 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903373659 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 15/10/2026 | 19/10/2026 |  |  | 1680 |  | 1680 |  |  | 2026-12-10 | 15/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903373776-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 199 | 31/10/2026 | 199 | SA | SA31/07/2026 | G3E | PANTS | G3 | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903373776 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA | 30/10/2026 | W 3S FT OH PT |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 199 |  | 199 |  |  | 27/10/2026 | 28/10/2026 |  |  | 199 |  | 199
ADIDAS | 0903373810-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 10 | 23/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373810 LI2671 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 18/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 10 | 6 | 4 |  |  | 15/09/2026 | 19/09/2026 | 2026-09-09 | 19/09/2026 | 10 | 8 | 2 |  | 2
ADIDAS | 0903373816-1 HK7309 | BLACK | 45D | F2225M402 | 1495 | 15/09/2026 | 1495 | SA | SA31/07/2026 | G1K,G1P | SWEATSHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373816 HK7309 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 14/09/2026 | 2026-10-09 | 14/09/2026 | 1495 | 1495 |  |  |  | 2026-03-09 | 2026-10-09 | 2026-09-09 | 17/09/2026 | 1495 | 1492 | 3
ADIDAS | 0903373846-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 10 | 23/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373846 LI2645 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 19/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 10 |  | 10 |  |  | 16/09/2026 | 17/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373872-1 HK7309 | BLACK | 45D | F2225M402 | 2730 | 15/09/2026 | 2730 | SA | SA31/07/2026 | G1D,G1E,G1F | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373872 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 14/09/2026 | 2026-10-09 | 15/09/2026 | 2730 | 2730 |  |  |  | 2026-03-09 | 2026-10-09 | 2026-10-09 | 17/09/2026 | 2730 | 2730
ADIDAS | 0903373878-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 10 | 23/09/2026 | 10 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903373878 LI2672 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 10 |  | 10 |  |  | 19/09/2026 | 21/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373912-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 10 | 23/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373912 LI2647 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 10 |  | 10 |  |  | 19/09/2026 | 21/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373917-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1080 | 31/10/2026 | 1080 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516318 | HT SUB PROCESS_V1 | 0903373917 JC9584 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 20/10/2026 | 21/10/2026 |  |  | 1080 |  | 1080 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1080 |  | 1080 |  |  | 16/10/2026 | 17/10/2026 |  |  | 1080 |  | 1080
ADIDAS | 0903373945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 10 | 23/09/2026 | 10 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 659018 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903373945 LI2646 | 16/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 10 |  | 10 |  |  | 18/09/2026 | 19/09/2026 |  |  | 10 |  | 10
ADIDAS | 0903373958-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2520 | 31/10/2026 | 2520 | SI | SI31/07/2026 | G3C | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903373958 HK7317 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-03-11 | ESS SWTP |  | SS27 | 2026-03-11 | 2026-09-11 |  |  | 2520 |  | 2520 |  |  | 30/10/2026 | 2026-04-11 |  |  | 2520 |  | 2520
ADIDAS | 0903374005-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 4199 | 31/10/2026 | 4199 | SI | SI31/07/2026 | G3I | JACKET | G3 | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903374005 JE0052 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/10/2026 | W 3S FT FZ HD |  | SS27 | 17/10/2026 | 24/10/2026 |  |  | 4199 |  | 4199 |  |  | 14/10/2026 | 21/10/2026 |  |  | 4199 |  | 4199
ADIDAS | 0903374039-1 HK7309 | BLACK | 45D | F2225M402 | 3000 | 15/09/2026 | 3000 | SA | SA31/07/2026 | G1D,G1E,G1F,G1K,G1L,G1N,G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903374039 HK7309 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 14/09/2026 | 15/09/2026 | 3000 | 3000 |  |  |  | 2026-03-09 | 2026-11-09 | 13/09/2026 | 17/09/2026 | 3000 | 2998 | 2
ADIDAS | 0903374083-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903374083 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 13/10/2026 | ESS TEE |  | SS27 | 13/10/2026 | 13/10/2026 |  |  | 600 |  | 600 |  |  | 2026-09-10 | 2026-09-10 |  |  | 600 |  | 600
ADIDAS | 0903374122-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 3779 | 31/10/2026 | 3779 | SA | SA31/07/2026 | G2F | JACKET | G2 | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903374122 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | M 3S FT FZ HD |  | SS27 | 28/10/2026 | 2026-04-11 |  |  | 3779 |  | 3779 |  |  | 24/10/2026 | 31/10/2026 |  |  | 3779 |  | 3779
ADIDAS | 0903374608-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374608 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 | 19/09/2026 | 19/09/2026 | 460 | 91 | 369 |  | 91 | 19/09/2026 | 21/09/2026 | 17/09/2026 | 18/09/2026 | 460 | 444 | 16
ADIDAS | 0903374636-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 140 | 23/10/2026 | 140 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374636 LI2647 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 140 |  | 140 |  |  | 2026-04-11 | 2026-04-11 |  |  | 140 |  | 140
ADIDAS | 0903374883-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 103 | 23/09/2026 | 103 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374883 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 103 |  | 103 |  |  | 18/09/2026 | 19/09/2026 |  |  | 103 |  | 103
ADIDAS | 0903374887-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 604 | 31/10/2026 | 604 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903374887 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 21/11/2026 | 24/11/2026 |  |  | 604 |  | 604 |  |  | 18/11/2026 | 19/11/2026 |  |  | 604 |  | 604 |  |  | 17/11/2026 | 18/11/2026 |  |  | 604 |  | 604
ADIDAS | 0903374908-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 107 | 30/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903374908 LI2668 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 107 |  | 107 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 18/09/2026 | 107 | 106 | 1
ADIDAS | 0903374971-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 111 | 30/09/2026 | 111 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903374971 LI2669 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 111 |  | 111 |  |  | 17/09/2026 | 18/09/2026 | 2026-12-09 | 19/09/2026 | 111 | 110 | 1 |  | 80
ADIDAS | 0903375052-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 200 | 31/10/2026 | 200 | SI | SI31/07/2026 | G3J | SHORTS | G3 | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375052 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | W 3S WV SHO |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 200 |  | 200 |  |  | 23/10/2026 | 26/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903375054-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 519 | 30/09/2026 | 519 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 28/09: ex-fty 1st Art (TC 10 pcs) 684009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903375054 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PERU | SEA | 2026-05-10 | M L SLIDE PKT T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 519 |  | 519 |  |  | 2026-01-10 | 2026-02-10 | 19/09/2026 | 19/09/2026 | 519 | 412 | 107 |  | 412 | 29/09/2026 | 30/09/2026 | 15/09/2026 | 19/09/2026 | 519 | 504 | 15 |  | 40
ADIDAS | 0903375259-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 599 | 31/10/2026 | 599 | SA | SA31/07/2026 | G2B | SHORTS | G2 | (12/09/2026) |  | 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375259 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 13/10/2026 | AFA DNA SHO |  | SS27-WC | 13/10/2026 | 14/10/2026 |  |  | 599 |  | 599 |  |  | 2026-09-10 | 2026-10-10 |  |  | 599 |  | 599
ADIDAS | 0903375527-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 128 | 31/10/2026 | 128 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375527 JN1958 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-11 | W 3S FT QZ HD |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 128 |  | 128 |  |  | 31/10/2026 | 2026-03-11 |  |  | 128 |  | 128
ADIDAS | 0903375654-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 720 | 31/10/2026 | 720 | SI | SI31/07/2026 | G3K | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375654 HR8583 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 19/10/2026 | ESS SWTP |  | SS27 | 19/10/2026 | 22/10/2026 |  |  | 720 |  | 720 |  |  | 15/10/2026 | 19/10/2026 |  |  | 720 |  | 720
ADIDAS | 0903375690-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1800 | 31/10/2026 | 1800 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375690 IB8686 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 13/10/2026 | ESS TEE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 1800 |  | 1800 |  |  | 2026-09-10 | 2026-12-10 |  |  | 1800 |  | 1800
ADIDAS | 0903375727-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1079 | 31/10/2026 | 1079 | SA | SA31/07/2026 | G2F | JACKET | G2 | (16/09/2026) |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375727 JE6338 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 1079 |  | 1079 |  |  | 19/10/2026 | 21/10/2026 |  |  | 1079 |  | 1079
ADIDAS | 0903375762-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 481 | 31/10/2026 | 481 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903375762 JE6417 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-08-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 481 |  | 481 |  |  | 2026-05-10 | 2026-07-10 |  |  | 481 |  | 481
ADIDAS | 0903375797-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 359 | 31/10/2026 | 359 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516204 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903375797 JE6340 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/10/2026 | M 3S FT FZ HD |  | SS27 | 21/10/2026 | 23/10/2026 |  |  | 359 |  | 359 |  |  | 17/10/2026 | 20/10/2026 |  |  | 359 |  | 359
ADIDAS | 0903375840-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 600 | 31/10/2026 | 600 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375840 JN1948 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 30/10/2026 | W 3S FT QZ HD |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 600 |  | 600 |  |  | 27/10/2026 | 28/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903375868-1 HK7309 | BLACK | 45D | F2225M402 | 780 | 15/09/2026 | 780 | SA | SA31/07/2026 | G1P | SWEATSHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 24-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903375868 HK7309 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-10-09 | ESS HDY |  | SS27 | 2026-10-09 | 14/09/2026 | 2026-11-09 | 14/09/2026 | 780 | 780 |  |  |  | 2026-07-09 | 2026-10-09 | 2026-11-09 | 16/09/2026 | 780 | 780
ADIDAS | 0903375907-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 719 | 31/10/2026 | 719 | SI | SI31/07/2026 | G3C | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375907 HK7317 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 26/10/2026 | ESS SWTP |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 719 |  | 719 |  |  | 22/10/2026 | 24/10/2026 |  |  | 719 |  | 719
ADIDAS | 0903375937-1 HK7319 | BLACK | 90D | F2225M403 | 720 | 31/10/2026 | 720 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903375937 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/10/2026 | ESS SWTP |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 720 |  | 720 |  |  | 21/10/2026 | 23/10/2026 |  |  | 720 |  | 720
ADIDAS | 0903375980-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 | 1381 | SI | SI31/07/2026 | G3C | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903375980 HK7317 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 28/10/2026 | ESS SWTP |  | SS27 | 28/10/2026 | 31/10/2026 |  |  | 1381 |  | 1381 |  |  | 24/10/2026 | 28/10/2026 |  |  | 1381 |  | 1381
ADIDAS | 0903376012-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 960 | 31/10/2026 | 960 | SI | SI31/07/2026 | G3H | JACKET | G3 | (16/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376012 JE0055 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-11 | W 3S FT FZ HD |  | SS27 | 2026-05-11 | 2026-06-11 |  |  | 960 |  | 960 |  |  | 2026-02-11 | 2026-03-11 |  |  | 960 |  | 960
ADIDAS | 0903376053-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376053 JN1948 |  | KAHATEX CIJERAH | SPAIN | SEA | 31/10/2026 | W 3S FT QZ HD |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 1151 |  | 1151 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903376092-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 | 1609 | SI | SI31/07/2026 | G3J | SHORTS | G3 | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376092 JE1309 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 29/10/2026 | W 3S WV SHO |  | SS27 | 29/10/2026 | 31/10/2026 |  |  | 1609 |  | 1609 |  |  | 26/10/2026 | 28/10/2026 |  |  | 1609 |  | 1609
ADIDAS | 0903376133-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903376133 JV5068 |  | KAHATEX CIJERAH | SPAIN | SEA | 29/10/2026 | I ADIRAPTOR T |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 919 |  | 919 |  |  | 26/10/2026 | 27/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903376163-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 3358 | 31/10/2026 | 3358 | SA | SA31/07/2026 | G3E | PANTS | G3 | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376163 JW7178 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-11 | W 3S FT OH PT |  | SS27 | 2026-06-11 | 2026-10-11 |  |  | 3358 |  | 3358 |  |  | 2026-03-11 | 2026-05-11 |  |  | 3358 |  | 3358
ADIDAS | 0903376197-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 6300 | 31/10/2026 | 6300 | SA | SA31/07/2026 | G2O | T-SHIRT | G2 | (01/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376197 IB8686 |  | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | ESS TEE |  | SS27 | 27/10/2026 | 2026-03-11 |  |  | 6300 |  | 6300 |  |  | 23/10/2026 | 30/10/2026 |  |  | 6300 |  | 6300
ADIDAS | 0903376238-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 200 | 31/10/2026 | 200 | SA | SA31/07/2026 | G2S | JACKET | G2 | (16/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376238 JE6338 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 200 |  | 200 |  |  | 19/10/2026 | 20/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903376260-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 246 | 30/09/2026 | 246 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903376260 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 246 |  | 246 |  |  | 24/09/2026 | 25/09/2026 |  |  | 246 |  | 246
ADIDAS | 0903376273-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 300 | 31/10/2026 | 300 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376273 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 3S FT FZ HD |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 300 |  | 300 |  |  | 16/10/2026 | 17/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903376325-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903376325 JV5069 |  | KAHATEX CIJERAH | GERMANY | SEA | 27/10/2026 | I ADIRAPTOR T |  | SS27 | 27/10/2026 | 28/10/2026 |  |  | 1680 |  | 1680 |  |  | 23/10/2026 | 24/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903376368-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3359 | 31/10/2026 | 3359 | SI | SI31/07/2026 | G3H | JACKET | G3 | (16/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376368 JE0055 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-11 | W 3S FT FZ HD |  | SS27 | 2026-06-11 | 2026-12-11 |  |  | 3359 |  | 3359 |  |  | 2026-03-11 | 2026-09-11 |  |  | 3359 |  | 3359
ADIDAS | 0903376414-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 361 | 31/10/2026 | 361 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376414 JE6417 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-08-10 | 2026-10-10 |  |  | 361 |  | 361 |  |  | 2026-05-10 | 2026-07-10 |  |  | 361 |  | 361
ADIDAS | 0903376447-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 6033 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903376447 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903376448-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 1080 | 31/10/2026 | 1080 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376448 JN1958 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-06-11 | W 3S FT QZ HD |  | SS27 | 2026-06-11 | 2026-07-11 |  |  | 1080 |  | 1080 |  |  | 2026-03-11 | 2026-04-11 |  |  | 1080 |  | 1080
ADIDAS | 0903376489-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2521 | 31/10/2026 | 2521 | SA | SA31/07/2026 | G2A | SHORTS | G2 | ok |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376489 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 24/10/2026 | 30/10/2026 |  |  | 2521 |  | 2521 |  |  | 21/10/2026 | 27/10/2026 |  |  | 2521 |  | 2521
ADIDAS | 0903376520-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 400 | 31/10/2026 | 400 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903376520 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 20/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 400 |  | 400 |  |  | 16/10/2026 | 17/10/2026 |  |  | 400 |  | 400
ADIDAS | 0903376565-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 2099 | 31/10/2026 | 2099 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903376565 JN1948 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | W 3S FT QZ HD |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 2099 |  | 2099 |  |  | 31/10/2026 | 2026-03-11 |  |  | 2099 |  | 2099
ADIDAS | 0903376600-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 401 | 31/10/2026 | 401 | SA | SA31/07/2026 | G2O | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903376600 JE6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/10/2026 | M 3S FT FZ HD |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 401 |  | 401 |  |  | 21/10/2026 | 23/10/2026 |  |  | 401 |  | 401
ADIDAS | 0903377291-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 301 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 684009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377291 KV7863 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903377363-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 155 | 31/10/2026 | 155 | SA | SA31/07/2026 | G3K | PANTS | G3 | (12/09/2026) |  | 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903377363 JW7182 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-11 | W 3S FT OH PT |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 155 |  | 155 |  |  | 30/10/2026 | 31/10/2026 |  |  | 155 |  | 155
ADIDAS | 0903377539-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 1560 | 31/10/2026 | 1560 | SI | SI31/07/2026 | G2R | SHORTS | G2 | ok |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903377539 JG8642 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | W LIN FT SHO |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 1560 |  | 1560 |  |  | 19/10/2026 | 21/10/2026 | 15/09/2026 | 16/09/2026 | 1560 | 1193 | 367
ADIDAS | 0903377653-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 167 | 30/09/2026 | 167 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377653 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 167 |  | 167 |  |  | 21/09/2026 | 23/09/2026 |  |  | 167 |  | 167
ADIDAS | 0903377680-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 175 | 23/09/2026 | 175 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903377680 LI2671 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 175 |  | 175 |  |  | 19/09/2026 | 21/09/2026 | 2026-09-09 | 18/09/2026 | 175 | 175
ADIDAS | 0903377733-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 1230 | 31/10/2026 | 1230 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903377733 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 16/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 16/11/2026 | 18/11/2026 |  |  | 1230 |  | 1230 |  |  | 2026-11-11 | 13/11/2026 |  |  | 1230 |  | 1230 |  |  | 2026-10-11 | 2026-12-11 |  |  | 1230 |  | 1230
ADIDAS | 0903377770-1 KA4331 | BLACK | 90D | S2608MR0902 | 1737 | 31/10/2026 | 1737 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903377770 KA4331 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-10-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-10-11 | 13/11/2026 |  |  | 1737 |  | 1737 |  |  | 2026-05-11 | 2026-10-11 |  |  | 1737 |  | 1737 |  |  | 2026-04-11 | 2026-09-11 |  |  | 1737 |  | 1737
ADIDAS | 0903377912-1 KG2951 | NIGHT NAVY | 90D | F2606CHRM009 | 70 | 31/10/2026 | 70 | SI | SI31/07/2026 | G3F | PANTS | G3 | (12/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377912 KG2951 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 26/10/2026 | REAL DNA PNT |  | SS27 | 26/10/2026 | 26/10/2026 |  |  | 70 |  | 70 |  |  | 22/10/2026 | 22/10/2026 |  |  | 70 |  | 70
ADIDAS | 0903378225-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 1680 | 31/10/2026 | 1680 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378225 JV5068 |  | KAHATEX CIJERAH | GERMANY | SEA | 31/10/2026 | I ADIRAPTOR T |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 1680 |  | 1680 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903378242-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 506 | 31/10/2026 | 506 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903378242 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA | 20/11/2026 | M PANCAKE T OFF WHITE |  | SS27-STX | 20/11/2026 | 21/11/2026 |  |  | 506 |  | 506 |  |  | 17/11/2026 | 18/11/2026 |  |  | 506 |  | 506
ADIDAS | 0903378264-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 201 | 31/10/2026 | 201 | SA | SA31/07/2026 | G2A | SHORTS | G2 | ok |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378264 JE6419 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 201 |  | 201 |  |  | 2026-03-10 | 2026-05-10 |  |  | 201 |  | 201
ADIDAS | 0903378323-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 923 | 23/09/2026 | 923 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378323 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 923 |  | 923 |  |  | 16/09/2026 | 17/09/2026 | 17/09/2026 | 18/09/2026 | 923 | 877 | 46
ADIDAS | 0903378350-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 2940 | 31/10/2026 | 2940 | SI | SI31/07/2026 | G3J | SHORTS | G3 | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378350 JE1309 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | W 3S WV SHO |  | SS27 | 2026-04-11 | 2026-10-11 |  |  | 2940 |  | 2940 |  |  | 31/10/2026 | 2026-05-11 |  |  | 2940 |  | 2940
ADIDAS | 0903378381-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 657 | 23/09/2026 | 657 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378381 LI2645 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 657 |  | 657 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 19/09/2026 | 657 | 643 | 14 |  | 411
ADIDAS | 0903378390-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2519 | 31/10/2026 | 2519 | SA | SA31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903378390 JE6414 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 28/10/2026 | 2026-02-11 |  |  | 2519 |  | 2519 |  |  | 24/10/2026 | 29/10/2026 |  |  | 2519 |  | 2519
ADIDAS | 0903378401-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 140 | 30/09/2026 | 140 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378401 LI2646 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 140 |  | 140 |  |  | 18/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 140 | 115 | 25 |  | 115
ADIDAS | 0903378425-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 200 | 31/10/2026 | 200 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378425 JD1877 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 200 |  | 200 |  |  | 19/10/2026 | 20/10/2026 |  |  | 200 |  | 200
ADIDAS | 0903378433-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 230 | 30/09/2026 | 230 | SI | SI31/07/2026 | G1M | ACCESSORIES | G1 | ok |  | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378433 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 2026-02-10 | 2026-03-10 |  |  | 230 |  | 230 |  |  | 29/09/2026 | 30/09/2026 |  |  | 230 |  | 230
ADIDAS | 0903378460-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 151 | 23/10/2026 | 151 | SA | SA31/07/2026 | G1O | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378460 LI2671 |  | KAHATEX CIJERAH | ITALY | SEA | 28/10/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 151 |  | 151 |  |  | 24/10/2026 | 26/10/2026 |  |  | 151 |  | 151
ADIDAS | 0903378462-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 3780 | 31/10/2026 | 3780 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378462 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-11-11 | W 3S FT CF PT |  | SS27 | 2026-11-11 | 16/11/2026 |  |  | 3780 |  | 3780 |  |  | 2026-06-11 | 2026-11-11 |  |  | 3780 |  | 3780
ADIDAS | 0903378476-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 28/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378476 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 113 |  | 113 |  |  | 21/09/2026 | 23/09/2026 |  |  | 113 |  | 113
ADIDAS | 0903378501-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 114 | 30/09/2026 | 114 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 516443 | PRINT L3 SUB PROCESS_V3 | 0903378501 LI2667 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 114 |  | 114 |  |  | 18/09/2026 | 19/09/2026 | 17/09/2026 | 17/09/2026 | 114 | 114
ADIDAS | 0903378502-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1260 | 31/10/2026 | 1260 | SA | SA31/07/2026 | G2T | JACKET | G2 | ok |  | 516318 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903378502 JE6340 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | M 3S FT FZ HD |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1260 |  | 1260 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1260 |  | 1260
ADIDAS | 0903378523-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 121 | 30/09/2026 | 121 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3 SUB PROCESS_V3 | 0903378523 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 121 |  | 121 |  |  | 17/09/2026 | 18/09/2026 | 2026-12-09 | 19/09/2026 | 121 | 121 |  |  | 12
ADIDAS | 0903378534-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2520 | 31/10/2026 | 2520 | SI | SI31/07/2026 | G3K | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903378534 HR8583 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 28/10/2026 | ESS SWTP |  | SS27 | 28/10/2026 | 2026-03-11 |  |  | 2520 |  | 2520 |  |  | 24/10/2026 | 30/10/2026 |  |  | 2520 |  | 2520
ADIDAS | 0903378548-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 145 | 31/10/2026 | 145 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903378548 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA | 2026-05-11 | 3S TEE SLIM BLACK/WHITE |  | SS27-STX | 2026-05-11 | 2026-07-11 |  |  | 145 |  | 145 |  |  | 2026-02-11 | 2026-04-11 |  |  | 145 |  | 145
ADIDAS | 0903378553-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 131 | 23/10/2026 | 131 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378553 LI2669 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 131 |  | 131 |  |  | 2026-04-11 | 2026-04-11 | 19/09/2026 | 19/09/2026 | 131 | 130 | 1 |  | 130
ADIDAS | 0903378584-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1890 | 31/10/2026 | 1890 | SI | SI31/07/2026 | G2E | T-SHIRT | G2 | (01/09/2026) |  | 516318 | PRINT L2 SUB PROCESS_V3 | 0903378584 JV5067 |  | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | I ADIRAPTOR T |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 1890 |  | 1890 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1890 |  | 1890
ADIDAS | 0903378603-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 351 | 23/09/2026 | 351 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378603 LI2646 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 351 |  | 351 |  |  | 18/09/2026 | 18/09/2026 | 19/09/2026 | 19/09/2026 | 351 | 166 | 185 |  | 166
ADIDAS | 0903378612-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 31/10/2026 | 200 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378612 JD5302 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-09-11 | W 3S FT CF PT |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 200 |  | 200 |  |  | 2026-04-11 | 2026-05-11 |  |  | 200 |  | 200
ADIDAS | 0903378670-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 1200 | 31/10/2026 | 1200 | SI | SI31/07/2026 | G3I | JACKET | G3 | (12/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378670 JE0052 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | W 3S FT FZ HD |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 1200 |  | 1200 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903378692-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 132 | 23/09/2026 | 132 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378692 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 132 |  | 132 |  |  | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 132 | 125 | 7 |  | 125
ADIDAS | 0903378707-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2E | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903378707 JV5067 |  | KAHATEX CIJERAH | SPAIN | SEA | 13/10/2026 | I ADIRAPTOR T |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 1036 |  | 1036 |  |  | 2026-09-10 | 2026-10-10 |  |  | 1036 |  | 1036
ADIDAS | 0903378741-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 721 | 15/09/2026 | 721 | SA | SA31/07/2026 | G3I | SWEATSHIRT | G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378741 HK7311 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-10-09 | 15/09/2026 | 721 | 721 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-10-09 | 16/09/2026 | 721 | 721
ADIDAS | 0903378787-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903378787 IB8686 |  | KAHATEX CIJERAH | SPAIN | SEA | 15/10/2026 | ESS TEE |  | SS27 | 15/10/2026 | 20/10/2026 |  |  | 3452 |  | 3452 |  |  | 2026-12-10 | 16/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903378816-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 | 1380 | SI | SI31/07/2026 | G3K | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903378816 HR8583 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 22/10/2026 | ESS SWTP |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 1380 |  | 1380 |  |  | 19/10/2026 | 22/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903378844-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 4140 | 31/10/2026 | 4140 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903378844 JD5302 |  | KAHATEX CIJERAH | SPAIN | SEA | 16/11/2026 | W 3S FT CF PT |  | SS27 | 16/11/2026 | 21/11/2026 |  |  | 4140 |  | 4140 |  |  | 2026-11-11 | 18/11/2026 |  |  | 4140 |  | 4140
ADIDAS | 0903378881-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 539 | 31/10/2026 | 539 | SI | SI31/07/2026 | G2E | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903378881 JV5067 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | I ADIRAPTOR T |  | SS27 | 2026-12-10 | 13/10/2026 |  |  | 539 |  | 539 |  |  | 2026-08-10 | 2026-09-10 |  |  | 539 |  | 539
ADIDAS | 0903378923-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 840 | 31/10/2026 | 840 | SI | SI31/07/2026 | G3J | SHORTS | G3 | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903378923 JE1309 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 27/10/2026 | W 3S WV SHO |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 840 |  | 840 |  |  | 23/10/2026 | 26/10/2026 |  |  | 840 |  | 840
ADIDAS | 0903378980-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 153 | 30/09/2026 | 153 | SA | SA31/07/2026 | G1N | ACCESSORIES | G1 | (12/09/2026) |  | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903378980 LI2670 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 25/09/2026 |  |  | 153 |  | 153 |  |  | 19/09/2026 | 22/09/2026 |  |  | 153 |  | 153
ADIDAS | 0903379027-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 960 | 15/09/2026 | 960 | SA | SA31/07/2026 | G3G,G3H,G3I | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379027 IB8688 | 2026-03-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-03-09 | ESS HDY |  | SS27 | 2026-03-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 960 | 960 |  |  |  | 31/08/2026 | 2026-11-09 | 2026-08-09 | 17/09/2026 | 960 | 960
ADIDAS | 0903379058-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 719 | 31/10/2026 | 719 | SA | SA31/07/2026 | G2A | SHORTS | G2 | ok |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379058 JE6419 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-07-10 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 2026-07-10 | 2026-08-10 |  |  | 719 |  | 719 |  |  | 2026-03-10 | 2026-05-10 |  |  | 719 |  | 719
ADIDAS | 0903379083-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/09/2026 | 2000 | SA | SA31/07/2026 | G2A,G2R,G2T | SWEATSHIRT | G2 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379083 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 2000 | 2000 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-11-09 | 17/09/2026 | 2000 | 2000
ADIDAS | 0903379104-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 3360 | 15/09/2026 | 3360 | SA | SA31/07/2026 | G2A,G2R,G2T,G3A,G3H,G3I | SWEATSHIRT | G2,G3 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379104 IB8688 | 2026-03-09 | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-12-09 | 15/09/2026 | 3360 | 3360 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-12-09 | 17/09/2026 | 3360 | 3360
ADIDAS | 0903379129-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 720 | 31/10/2026 | 720 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516204 | EMBRO SUB PROCESS_V1 | 0903379129 JE6414 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 20/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 720 |  | 720 |  |  | 16/10/2026 | 17/10/2026 |  |  | 720 |  | 720
ADIDAS | 0903379176-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 197 | 31/10/2026 | 197 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379176 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 13/11/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 197 |  | 197 |  |  | 2026-10-11 | 2026-11-11 |  |  | 197 |  | 197
ADIDAS | 0903379338-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 471 | 31/10/2026 | 471 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379338 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 13/11/2026 | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27 | 13/11/2026 | 16/11/2026 |  |  | 471 |  | 471 |  |  | 2026-10-11 | 2026-11-11 |  |  | 471 |  | 471
ADIDAS | 0903379415-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 324 | 31/10/2026 | 324 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379415 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/11/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 18/11/2026 | 21/11/2026 |  |  | 324 |  | 324 |  |  | 13/11/2026 | 18/11/2026 |  |  | 324 |  | 324
ADIDAS | 0903379576-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 152 | 31/10/2026 | 152 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379576 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/11/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 18/11/2026 | 21/11/2026 |  |  | 152 |  | 152 |  |  | 13/11/2026 | 18/11/2026 |  |  | 152 |  | 152
ADIDAS | 0903379743-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 127 | 31/10/2026 | 127 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 839055 | HT SUB PROCESS_V1 | 0903379743 IL4127 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 127 |  | 127 |  |  | 31/10/2026 | 31/10/2026 |  |  | 127 |  | 127 |  |  | 30/10/2026 | 30/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903380052-1 IC5189 | WHITE | 90D | S23080640 | 297 | 31/10/2026 | 297 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380052 IC5189 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 31/10/2026 | OWN THE RUN TEE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 297 |  | 297 |  |  | 29/10/2026 | 31/10/2026 |  |  | 297 |  | 297 |  |  | 28/10/2026 | 30/10/2026 |  |  | 297 |  | 297
ADIDAS | 0903380079-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 198 | 31/10/2026 | 198 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903380079 IL4127 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 198 |  | 198 |  |  | 31/10/2026 | 31/10/2026 |  |  | 198 |  | 198 |  |  | 30/10/2026 | 30/10/2026 |  |  | 198 |  | 198
ADIDAS | 0903380268-1 KE8425 | WHITE | 120D | S2608MR0906A | 873 | 31/10/2026 | 873 | SI | SI31/07/2026 | G2N | T-SHIRT | G2 | (02/10/2026) |  | DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | HT+PAD SUB PROCESS_V3 | 0903380268 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | Run Ess LS M WHITE |  | SS27-TI | 23/10/2026 | 24/10/2026 |  |  | 873 |  | 873 |  |  | 20/10/2026 | 21/10/2026 |  |  | 873 |  | 873 |  |  | 17/10/2026 | 19/10/2026 |  |  | 873 |  | 873
ADIDAS | 0903380322-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 109 | 23/09/2026 | 109 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380322 LI2647 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 109 |  | 109 |  |  | 19/09/2026 | 21/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380373-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 109 | 30/09/2026 | 109 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380373 LI2672 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 24/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 109 |  | 109 |  |  | 21/09/2026 | 23/09/2026 |  |  | 109 |  | 109
ADIDAS | 0903380418-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 187 | 23/10/2026 | 187 | SI | SI31/07/2026 | G1R | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380418 LI2646 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 187 |  | 187 |  |  | 31/10/2026 | 31/10/2026 |  |  | 187 |  | 187
ADIDAS | 0903380504-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 460 | 23/09/2026 | 460 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 600000 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380504 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 22/09/2026 |  |  | 460 |  | 460 |  |  | 18/09/2026 | 18/09/2026 | 17/09/2026 | 18/09/2026 | 460 | 406 | 54
ADIDAS | 0903380507-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 180 | 23/10/2026 | 180 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380507 LI2667 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 180 |  | 180 |  |  | 2026-04-11 | 2026-04-11 | 16/09/2026 | 19/09/2026 | 180 | 179 | 1 |  | 14
ADIDAS | 0903380516-1 KT7552 | BLACK | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903380516 KT7552 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 13/10/2026 | SOC CAT GFX T BLACK |  | SS27 | 13/10/2026 | 14/10/2026 |  |  | 2099 |  | 2099 |  |  | 2026-09-10 | 2026-10-10 |  |  | 2099 |  | 2099
ADIDAS | 0903380521-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380521 LI2646 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 32 |  | 32 |  |  | 18/09/2026 | 19/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380549-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 32 | 30/09/2026 | 32 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 848012 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903380549 LI2670 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 32 |  | 32 |  |  | 21/09/2026 | 23/09/2026 | 16/09/2026 | 16/09/2026 | 32 | 16 | 16
ADIDAS | 0903380551-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 1254 | 2026-09-09 | 1254 | NT | NT31/07/2026 | G2Q | PANTS | G2 | ok |  | 09/09: ex-fty 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903380551 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-09 | M FEELCOZY PANT |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-07-09 | 2026-09-09 | 1254 | 1254 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-04-09 | 2026-09-09 | 1254 | 1254
ADIDAS | 0903380577-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 32 | 30/09/2026 | 32 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 24/09: ex-fty 848012 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380577 LI2645 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 28/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 32 |  | 32 |  |  | 24/09/2026 | 25/09/2026 |  |  | 32 |  | 32
ADIDAS | 0903380597-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 15544 | 31/10/2026 | 15544 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380597 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-10-10 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 2026-10-10 | 22/10/2026 |  |  | 15544 |  | 15544 |  |  | 2026-07-10 | 19/10/2026 |  |  | 15544 |  | 15544
ADIDAS | 0903380602-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 65 | 23/09/2026 | 65 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380602 LI2645 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 19/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 19/09/2026 | 21/09/2026 |  |  | 65 |  | 65 |  |  | 16/09/2026 | 17/09/2026 |  |  | 65 |  | 65
ADIDAS | 0903380624-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 442 | 23/09/2026 | 442 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3 SUB PROCESS_V3 | 0903380624 LI2668 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 21/09/2026 |  |  | 442 |  | 442 |  |  | 17/09/2026 | 17/09/2026 | 18/09/2026 | 19/09/2026 | 442 | 441 | 1 |  | 5
ADIDAS | 0903380631-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 50 | 23/09/2026 | 50 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903380631 LI2667 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 18/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 50 | 9 | 41 |  | 9
ADIDAS | 0903380644-1 LI7744 | WHITE | 90D | F2606LEMPM107MF | 8870 | 31/10/2026 | 8870 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380644 LI7744 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/09/2026 | PSMM A JSY FAN WHITE |  | SS27-L2L | 30/09/2026 | 2026-09-10 |  |  | 8870 |  | 8870 |  |  | 26/09/2026 | 2026-06-10 |  |  | 8870 |  | 8870
ADIDAS | 0903380648-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1379 | 15/09/2026 | 1379 | SA | SA31/07/2026 | G3G | SWEATSHIRT | G3 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0002-T2 Paiho, LLT material, PI Date 01-Sep, ETD 27-Aug. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380648 HK7311 | 2026-03-09 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-09 | ESS HDY |  | SS27 | 2026-07-09 | 15/09/2026 | 2026-09-09 | 14/09/2026 | 1379 | 1379 |  |  |  | 2026-03-09 | 2026-11-09 | 2026-09-09 | 16/09/2026 | 1379 | 1379
ADIDAS | 0903380681-1 HK7319 | BLACK | 90D | F2225M403 | 2519 | 31/10/2026 | 2519 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903380681 HK7319 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-11 | ESS SWTP |  | SS27 | 2026-05-11 | 2026-11-11 |  |  | 2519 |  | 2519 |  |  | 2026-02-11 | 2026-06-11 |  |  | 2519 |  | 2519
ADIDAS | 0903380684-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 393 | 23/09/2026 | 393 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380684 LI2647 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 393 |  | 393 |  |  | 19/09/2026 | 21/09/2026 |  |  | 393 |  | 393
ADIDAS | 0903380713-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3452 | 31/10/2026 | 3452 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903380713 IB8686 |  | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | ESS TEE |  | SS27 | 20/10/2026 | 24/10/2026 |  |  | 3452 |  | 3452 |  |  | 16/10/2026 | 21/10/2026 |  |  | 3452 |  | 3452
ADIDAS | 0903380751-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 204 | 31/10/2026 | 204 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903380751 IL4127 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 204 |  | 204 |  |  | 31/10/2026 | 31/10/2026 |  |  | 204 |  | 204 |  |  | 30/10/2026 | 30/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903380795-1 LI7745 | TEAM COLL BURGUNDY 2 | 90D | F2606LEMPM207MF | 1477 | 31/10/2026 | 1477 | NT | NT31/07/2026 | G2C | T-SHIRT | G2 | (29/08/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903380795 LI7745 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-10 | PSMM H JSY FAN TEAM COLL BURGUNDY 2 |  | SS27-L2L | 2026-09-10 | 2026-10-10 |  |  | 1477 |  | 1477 |  |  | 2026-06-10 | 2026-07-10 |  |  | 1477 |  | 1477
ADIDAS | 0903380896-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 301 | 31/10/2026 | 301 | SI | SI31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903380896 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-06-11 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-06-11 | 2026-10-11 |  |  | 301 |  | 301 |  |  | 2026-03-11 | 2026-05-11 |  |  | 301 |  | 301
ADIDAS | 0903380949-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 130 | 30/09/2026 | 130 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380949 LI2647 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 130 |  | 130 |  |  | 19/09/2026 | 21/09/2026 |  |  | 130 |  | 130
ADIDAS | 0903380973-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 327 | 30/09/2026 | 327 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380973 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 327 |  | 327 |  |  | 24/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 327 | 213 | 114 |  | 213
ADIDAS | 0903380993-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 154 | 31/10/2026 | 154 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380993 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 154 |  | 154 |  |  | 31/10/2026 | 31/10/2026 |  |  | 154 |  | 154 |  |  | 30/10/2026 | 30/10/2026 |  |  | 154 |  | 154
ADIDAS | 0903381000-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 113 | 30/09/2026 | 113 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 28/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381000 LI2671 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 113 |  | 113 |  |  | 23/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 113 | 93 | 20 |  | 93
ADIDAS | 0903381024-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 379 | 30/09/2026 | 379 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381024 LI2645 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 28/09/2026 | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27 | 28/09/2026 | 29/09/2026 |  |  | 379 |  | 379 |  |  | 24/09/2026 | 25/09/2026 | 19/09/2026 | 19/09/2026 | 379 | 313 | 66 |  | 313
ADIDAS | 0903381048-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 265 | 30/09/2026 | 265 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 28/09: ex-fty 516443 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381048 LI2672 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 265 |  | 265 |  |  | 21/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 265 | 255 | 10 |  | 255
ADIDAS | 0903381059-1 KT7550 | BLACK | 90D | F26FBGFXP103 | 1228 | 31/10/2026 | 1228 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903381059 KT7550 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 16/10/2026 | M MX LIFESTL T |  | SS27 | 16/10/2026 | 17/10/2026 |  |  | 1228 |  | 1228 |  |  | 13/10/2026 | 14/10/2026 |  |  | 1228 |  | 1228 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1228 |  | 1228
ADIDAS | 0903381067-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 271 | 15/10/2026 | 271 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381067 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 19/10/2026 | M BLANK TEE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 271 |  | 271 |  |  | 15/10/2026 | 15/10/2026 |  |  | 271 |  | 271
ADIDAS | 0903381072-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 241 | 30/09/2026 | 241 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 516443 | PRINT L3 SUB PROCESS_V3 | 0903381072 LI2669 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 23/09/2026 | 23/09/2026 |  |  | 241 |  | 241 |  |  | 19/09/2026 | 19/09/2026 | 17/09/2026 | 17/09/2026 | 241 | 209 | 32
ADIDAS | 0903381112-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 307 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516394 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381112 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903381150-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 3678 | 31/10/2026 | 3678 | SI | SI31/07/2026 | G3H | JACKET | G3 | (16/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381150 JE0055 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-12-11 | W 3S FT FZ HD |  | SS27 | 2026-12-11 | 19/11/2026 |  |  | 3678 |  | 3678 |  |  | 2026-09-11 | 16/11/2026 |  |  | 3678 |  | 3678
ADIDAS | 0903381183-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 479 | 31/10/2026 | 479 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381183 JV5068 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 28/10/2026 | I ADIRAPTOR T |  | SS27 | 28/10/2026 | 29/10/2026 |  |  | 479 |  | 479 |  |  | 24/10/2026 | 26/10/2026 |  |  | 479 |  | 479
ADIDAS | 0903381211-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381211 JN1958 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-04-11 | W 3S FT QZ HD |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 460 |  | 460 |  |  | 31/10/2026 | 2026-03-11 |  |  | 460 |  | 460
ADIDAS | 0903381242-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 | 919 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381242 JE6417 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 13/10/2026 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 13/10/2026 | 15/10/2026 |  |  | 919 |  | 919 |  |  | 2026-09-10 | 2026-12-10 |  |  | 919 |  | 919
ADIDAS | 0903381274-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516205 | PRINT L2 SUB PROCESS_V3 | 0903381274 JV5069 |  | KAHATEX CIJERAH | SPAIN | SEA | 23/10/2026 | I ADIRAPTOR T |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 919 |  | 919 |  |  | 20/10/2026 | 22/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903381304-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2A | SHORTS | G2 | ok |  | 516205 | EMBRO SUB PROCESS_V1 | 0903381304 JE6419 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA | 19/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 19/10/2026 | 21/10/2026 |  |  | 1380 |  | 1380 |  |  | 15/10/2026 | 17/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903381342-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 480 | 31/10/2026 | 480 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516204 | PRINT L2 SUB PROCESS_V3 | 0903381342 JV5069 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 23/10/2026 | I ADIRAPTOR T |  | SS27 | 23/10/2026 | 23/10/2026 |  |  | 480 |  | 480 |  |  | 20/10/2026 | 20/10/2026 |  |  | 480 |  | 480
ADIDAS | 0903381645-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 1400 | 31/10/2026 | 1400 | SI | SI31/07/2026 | G3H | PANTS | G3 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381645 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA | 31/10/2026 | UCH DNA PNT |  | SS27 | 31/10/2026 | 2026-02-11 |  |  | 1400 |  | 1400 |  |  | 28/10/2026 | 29/10/2026 |  |  | 1400 |  | 1400
ADIDAS | 0903381685-1 JE6353 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS605FT | 1200 | 31/10/2026 | 1200 | SA | SA31/07/2026 | G3D | PANTS | G3 | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903381685 JE6353 |  | KAHATEX CIJERAH | JAPAN | SEA | 30/10/2026 | M 3S FT TC PT |  | SS27 | 30/10/2026 | 2026-02-11 |  |  | 1200 |  | 1200 |  |  | 27/10/2026 | 29/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903381705-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 173 | 23/10/2026 | 173 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | (08/09/2026) |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381705 LI2668 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-07-11 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 2026-07-11 | 2026-09-11 |  |  | 173 |  | 173 |  |  | 2026-04-11 | 2026-04-11 |  |  | 173 |  | 173
ADIDAS | 0903381723-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 130 | 30/09/2026 | 130 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516443 | PRINT L3 SUB PROCESS_V3 | 0903381723 LI2668 | 16/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 130 |  | 130 |  |  | 17/09/2026 | 18/09/2026 | 18/09/2026 | 18/09/2026 | 130 | 129 | 1
ADIDAS | 0903381732-1 JE8969 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS623FT | 2104 | 31/10/2026 | 2104 | SA | SA31/07/2026 | G3A | PANTS | G3 | (16/09/2026) |  | 1st Art (TC 10 pcs) 804028 | PRINT L1 SUB PROCESS_V3 | 0903381732 JE8969 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-02-11 | M BL FT PT |  | SS27 | 2026-02-11 | 2026-05-11 |  |  | 2104 |  | 2104 |  |  | 29/10/2026 | 2026-02-11 |  |  | 2104 |  | 2104
ADIDAS | 0903381751-1 KG5349 | TEAM ROYAL BLUE | 90D | F2606CHUC004 | 798 | 31/10/2026 | 798 | SI | SI31/07/2026 | G3H | PANTS | G3 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381751 KG5349 |  | KAHATEX CIJERAH | CHILE | SEA | 30/10/2026 | UCH DNA PNT |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 798 |  | 798 |  |  | 27/10/2026 | 28/10/2026 |  |  | 798 |  | 798
ADIDAS | 0903381763-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 150 | 23/09/2026 | 150 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381763 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 150 | 148 | 2 |  |  | 15/09/2026 | 19/09/2026 | 2026-09-09 | 2026-12-09 | 150 | 150
ADIDAS | 0903381776-1 JE6377 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS612FT | 1200 | 31/10/2026 | 1200 | SI | SI31/07/2026 | G2F | SWEATSHIRT | G2 | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381776 JE6377 |  | KAHATEX CIJERAH | JAPAN | SEA | 21/10/2026 | M 3S FT SWT |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 1200 |  | 1200 |  |  | 17/10/2026 | 19/10/2026 |  |  | 1200 |  | 1200
ADIDAS | 0903381784-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1091 | 31/10/2026 | 1091 | SA | SA31/07/2026 | G3J | PANTS | G3 | (12/09/2026) |  | 1st Art (TC 10 pcs) 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381784 KG5347 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA | 22/10/2026 | COLO DNA PNT |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 1091 |  | 1091 |  |  | 19/10/2026 | 20/10/2026 |  |  | 1091 |  | 1091
ADIDAS | 0903381803-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 498 | 23/09/2026 | 498 | AN | AN31/07/2026 | G1K | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3 SUB PROCESS_V3 | 0903381803 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 19/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 498 | 485 | 13 |  | 485 | 16/09/2026 | 17/09/2026 | 16/09/2026 | 17/09/2026 | 498 | 379 | 119
ADIDAS | 0903381815-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 532 | 31/10/2026 | 532 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381815 HK7311 |  | KAHATEX CIJERAH | CANADA | SEA | 2026-10-11 | ESS HDY |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 532 |  | 532 |  |  | 2026-05-11 | 2026-06-11 |  |  | 532 |  | 532
ADIDAS | 0903381828-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 568 | 23/09/2026 | 568 | AN | AN31/07/2026 | G1K | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3 SUB PROCESS_V3 | 0903381828 LI2667 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 17/09/2026 | 19/09/2026 | 18/09/2026 | 19/09/2026 | 568 | 564 | 4 |  | 47 | 14/09/2026 | 16/09/2026 | 2026-11-09 | 17/09/2026 | 568 | 565 | 3
ADIDAS | 0903381848-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 732 | 31/10/2026 | 732 | SA | SA31/07/2026 | G1C | SWEATSHIRT | G1 | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381848 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA | 2026-11-11 | ESS HDY |  | SS27 | 2026-11-11 | 2026-12-11 |  |  | 732 |  | 732 |  |  | 2026-06-11 | 2026-09-11 |  |  | 732 |  | 732
ADIDAS | 0903381881-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 732 | 23/09/2026 | 732 | SA | SA31/07/2026 | G1F,G1L,G1N | SWEATSHIRT | G1 | ok |  | 22/09: ex-fty 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381881 HK7311 | 2026-03-09 | KAHATEX CIJERAH | CANADA | SEA | 14/09/2026 | ESS HDY |  | SS27 | 14/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 732 | 638 | 94 |  | 47 | 2026-10-09 | 16/09/2026 | 15/09/2026 | 16/09/2026 | 732 | 703 | 29
ADIDAS | 0903382074-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 314 | 31/10/2026 | 314 | SI | SI31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382074 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 18/11/2026 | W 3S WV BOMBER BLACK/WHITE |  | SS27 | 18/11/2026 | 21/11/2026 |  |  | 314 |  | 314 |  |  | 13/11/2026 | 18/11/2026 |  |  | 314 |  | 314
ADIDAS | 0903382140-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 420 | 2026-09-09 | 420 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903382140 IW2479 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-04-09 | 2026-09-09 | 420 | 420 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-01-09 | 2026-08-09 | 420 | 420
ADIDAS | 0903382660-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 40 | 23/09/2026 | 40 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382660 LI2671 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 18/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 40 | 10 | 30 |  |  | 15/09/2026 | 19/09/2026 | 2026-11-09 | 2026-11-09 | 40 | 23 | 17
ADIDAS | 0903382688-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 50 | 23/09/2026 | 50 | SI | SI31/07/2026 | G1A | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382688 LI2646 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 22/09/2026 | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 50 |  | 50 |  |  | 18/09/2026 | 19/09/2026 | 19/09/2026 | 19/09/2026 | 50 | 33 | 17 |  | 33
ADIDAS | 0903382689-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 149 | 30/09/2026 | 149 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382689 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 24/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 24/09/2026 | 26/09/2026 |  |  | 149 |  | 149 |  |  | 21/09/2026 | 23/09/2026 | 18/09/2026 | 18/09/2026 | 149 | 137 | 12
ADIDAS | 0903382714-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 40 | 23/09/2026 | 40 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 22/09: ex-fty 848016 | PRINT L3 SUB PROCESS_V3 | 0903382714 LI2668 | 16/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA | 21/09/2026 | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 40 |  | 40 |  |  | 17/09/2026 | 18/09/2026 | 19/09/2026 | 19/09/2026 | 40 | 40 |  |  | 40
ADIDAS | 0903382830-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2D,G2G,G2N,G2O,G2P,G2S | SWEATSHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382830 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-08-09 | M FEELCOZY HD |  | SS27 | 2026-08-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 15000 |  |  |  | 2026-04-09 | 2026-11-09 | 2026-08-09 | 15/09/2026 | 15000 | 15000
ADIDAS | 0903383170-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 325 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516343 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383170 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903383240-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 234 | 23/09/2026 | 234 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903383240 LI2670 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | PET RUFFLE TEE BLACK/WHITE |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 234 |  | 234 |  |  | 19/09/2026 | 21/09/2026 | 13/09/2026 | 18/09/2026 | 234 | 181 | 53
ADIDAS | 0903383252-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 292 | 15/10/2026 | 292 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383252 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 19/10/2026 | M BLANK TEE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 292 |  | 292 |  |  | 15/10/2026 | 16/10/2026 |  |  | 292 |  | 292
ADIDAS | 0903383295-1 KT7539 | CARBON S18 | 60D | F26FBGFXP101 | 1225 | 31/10/2026 | 1225 | AN | AN31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903383295 KT7539 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 20/11/2026 | IN RANGE |  | SS27 | 20/11/2026 | 20/11/2026 |  |  | 1225 |  | 1225 |  |  | 17/11/2026 | 17/11/2026 |  |  | 1225 |  | 1225
ADIDAS | 0903383996-1 JZ6293 | CREW BLUE S21 | 90D | S2606CHAG011-MTF | 361 | 31/10/2026 | 361 | AN | AN31/07/2026 | G1B | PANTS | G1 | (12/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903383996 JZ6293 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 23/11/2026 | AFA DNA PNT |  | SS27-WC | 23/11/2026 | 24/11/2026 |  |  | 361 |  | 361 |  |  | 18/11/2026 | 19/11/2026 |  |  | 361 |  | 361
ADIDAS | 0903384024-1 JZ6297 | CREW BLUE S21 | 90D | S2606CHAG014 | 915 | 31/10/2026 | 915 | SA | SA31/07/2026 | G2B | SHORTS | G2 | (12/09/2026) |  | 1st Art (TC 10 pcs) 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384024 JZ6297 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 2026-10-10 | AFA DNA SHO |  | SS27-WC | 2026-10-10 | 13/10/2026 |  |  | 915 |  | 915 |  |  | 2026-07-10 | 2026-09-10 |  |  | 915 |  | 915
ADIDAS | 0903384123-1 LE8210 | BLACK | 90D | F2606LHLF103FYL | 82 | 31/10/2026 | 82 | SI | SI31/07/2026 | G1L | T-SHIRT | G1 | (07/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903384123 LE8210 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-06-11 | LFC 3FY JSYL SE BLACK |  | SS27-FJ | 2026-06-11 | 2026-06-11 |  |  | 82 |  | 82 |  |  | 2026-03-11 | 2026-03-11 |  |  | 82 |  | 82
ADIDAS | 0903384138-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 104 | 30/09/2026 | 104 | SI | SI31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 29/09: ex-fty 839055 | PRINT L2 SUB PROCESS_V3 | 0903384138 KB7172 | 16/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 26/09/2026 | HOT COMMUNITY |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 104 |  | 104 |  |  | 23/09/2026 | 23/09/2026 |  |  | 104 |  | 104
ADIDAS | 0903384176-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 480 | 2026-09-09 | 480 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 684009 | PRINT L3+PAD SUB PROCESS_V3 | 0903384176 IZ0443 | 2026-03-09 | KAHATEX CIJERAH | PERU | SEA | 2026-04-09 | POS TABLE LK |  | SS27 | 2026-04-09 | 2026-09-09 | 2026-05-09 | 2026-09-09 | 480 | 480 |  |  |  | 2026-01-09 | 2026-05-09 | 2026-04-09 | 2026-08-09 | 480 | 480
ADIDAS | 0903384240-1 JG8642 | CLEAR PINK/WHITE | 90D | S2554WES429FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2R | SHORTS | G2 | ok |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903384240 JG8642 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 21/10/2026 | W LIN FT SHO |  | SS27 | 21/10/2026 | 22/10/2026 |  |  | 300 |  | 300 |  |  | 17/10/2026 | 19/10/2026 | 15/09/2026 | 15/09/2026 | 300 | 275 | 25
ADIDAS | 0903384315-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 300 | 31/10/2026 | 300 | SI | SI31/07/2026 | G2M | SWEATSHIRT | G2 | (12/09/2026) |  | (Mexico). 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384315 JE6372 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA | 17/10/2026 | M 3S FT SWT |  | SS27 | 17/10/2026 | 17/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903384565-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903384565 KX8877 |  | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-10 | M CHIP T WHITE |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 100 |  | 100 |  |  | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100
ADIDAS | 0903384949-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 1138 | 2026-07-10 | 1138 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903384949 JC5283 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-05-10 | M L SLIDE PKT T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 1138 |  | 1138 |  |  | 2026-01-10 | 2026-02-10 |  |  | 1138 |  | 1138 |  |  | 29/09/2026 | 30/09/2026 |  |  | 1138 |  | 1138
ADIDAS | 0903385022-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 1278 | 2026-07-10 | 1278 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 30/09: ex-fty 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385022 JC5282 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-03-10 | M L SLIDE PKT T |  | SS27 | 2026-03-10 | 2026-05-10 |  |  | 1278 |  | 1278 |  |  | 30/09/2026 | 2026-01-10 |  |  | 1278 |  | 1278 |  |  | 28/09/2026 | 29/09/2026 |  |  | 1278 |  | 1278
ADIDAS | 0903385097-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 1076 | 2026-07-10 | 1076 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | ok |  | 30/09: ex-fty 1st Art (TC 10 pcs) 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903385097 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-06-10 | M L SLIDE PKT T |  | SS27 | 2026-06-10 | 2026-06-10 |  |  | 1076 |  | 1076 |  |  | 2026-02-10 | 2026-02-10 |  |  | 1076 |  | 1076 |  |  | 30/09/2026 | 30/09/2026 |  |  | 1076 |  | 1076
ADIDAS | 0903385671-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903385671 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-04-11 | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX | 2026-04-11 | 2026-05-11 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 2026-02-11 |  |  | 100 |  | 100
ADIDAS | 0903385727-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 1635 | 31/10/2026 | 1635 | SA | SA31/07/2026 | G1Q | T-SHIRT | G1 | (01/09/2026) |  | 838103 | PRINT L1+PAD SUB PROCESS_V3 | 0903385727 KY1335 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 23/11/2026 | M PANCAKE T OFF WHITE |  | SS27-STX | 23/11/2026 | 24/11/2026 |  |  | 1635 |  | 1635 |  |  | 18/11/2026 | 19/11/2026 |  |  | 1635 |  | 1635
ADIDAS | 0903385935-1 KX8877 | WHITE | 90D | S27GMGFX100 | 110 | 31/10/2026 | 110 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903385935 KX8877 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-08-10 | M CHIP T WHITE |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 110 |  | 110 |  |  | 2026-05-10 | 2026-05-10 |  |  | 110 |  | 110
ADIDAS | 0903385968-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 100 | 15/10/2026 | 100 | SI | SI31/07/2026 | G1P | T-SHIRT | G1 | (12/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903385968 KD3936 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | RELEASED |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 21/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903385970-1 KG5347 | BLACK | 90D | F2606CHCC004 | 1400 | 31/10/2026 | 1400 | SA | SA31/07/2026 | G3J | PANTS | G3 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385970 KG5347 |  | KAHATEX CIJERAH | CHILE | SEA | 23/10/2026 | COLO DNA PNT |  | SS27 | 23/10/2026 | 26/10/2026 |  |  | 1400 |  | 1400 |  |  | 20/10/2026 | 22/10/2026 |  |  | 1400 |  | 1400
ADIDAS | 0903385989-1 IS1413 | BLACK | 60D | S2425M405 | 598 | 31/10/2026 | 598 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903385989 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-12-10 | IN RANGE |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 598 |  | 598 |  |  | 2026-08-10 | 2026-08-10 |  |  | 598 |  | 598
ADIDAS | 0903386031-1 KY7166 | BLACK | 75D | S2706CHCC008 | 1328 | 15/10/2026 | 1328 | ID | ID31/07/2026 | G2S | SHORTS | G2 | (12/09/2026) |  | 680015 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386031 KY7166 |  | KAHATEX CIJERAH | CHILE | SEA | 2026-07-10 | CC DNA SHO BLACK |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1328 |  | 1328 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1328 |  | 1328
ADIDAS | 0903386106-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 300 | 31/10/2026 | 300 | AN | AN31/07/2026 | G1F | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 684009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386106 LF1392 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA | 21/11/2026 | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27 | 21/11/2026 | 23/11/2026 |  |  | 300 |  | 300 |  |  | 18/11/2026 | 18/11/2026 |  |  | 300 |  | 300
ADIDAS | 0903386123-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 304 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 680015 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386123 KV7863 | 15/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386150-1 LC6341 | BLACK | 90D | S27GMGFX130 | 368 | 31/10/2026 | 368 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903386150 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-04-11 | M SEE2X SHO12X T BLACK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 368 |  | 368 |  |  | 31/10/2026 | 31/10/2026 |  |  | 368 |  | 368
ADIDAS | 0903386171-1 JH1039 | ALUMINA S20 | 45D | F224CSIM430 | 15000 | 15/09/2026 | 15000 | NT | NT31/07/2026 | G2E,G2F,G2Q,G2S | PANTS | G2 | ok |  | 15/09: ex-fty (STOOD) 600000 | EMBRO+PPA SUB PROCESS_V3 | 0903386171 JH1039 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-09-09 | M FEELCOZY PANT |  | SS27 | 2026-09-09 | 15/09/2026 | 2026-08-09 | 15/09/2026 | 15000 | 15000 |  |  |  | 2026-05-09 | 2026-11-09 | 2026-07-09 | 16/09/2026 | 15000 | 15000
ADIDAS | 0903386195-1 KT7553 | WHITE | 60D | F26FBGFXP104 | 2099 | 31/10/2026 | 2099 | SI | SI31/07/2026 | G2K | T-SHIRT | G2 | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903386195 KT7553 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 14/10/2026 | SOC CAT GFX T WHITE |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 2099 |  | 2099 |  |  | 2026-10-10 | 2026-12-10 |  |  | 2099 |  | 2099
ADIDAS | 0903386246-1 IS1413 | BLACK | 60D | S2425M405 | 385 | 31/10/2026 | 385 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903386246 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-10 | IN RANGE |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 385 |  | 385 |  |  | 2026-07-10 | 2026-08-10 |  |  | 385 |  | 385
ADIDAS | 0903386305-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 230 | 23/09/2026 | 230 | SA | SA31/07/2026 | G2A | T-SHIRT | G2 | ok |  | 23/09: ex-fty 512102 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903386305 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 21/09/2026 | MINI EMB T |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 230 |  | 230 |  |  | 17/09/2026 | 18/09/2026 | 19/09/2026 | 19/09/2026 | 230 | 200 | 30 |  | 200 | 15/09/2026 | 16/09/2026 | 16/09/2026 | 19/09/2026 | 230 | 206 | 24 |  | 6
ADIDAS | 0903386331-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 680 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516462 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386331 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386485-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 104 | 31/10/2026 | 104 | SI | SI31/07/2026 | G3E | SHORTS | G3 | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386485 JD9944 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 2026-10-11 | W SL FT SHO |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 104 |  | 104 |  |  | 2026-05-11 | 2026-06-11 |  |  | 104 |  | 104
ADIDAS | 0903387168-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 107 | 23/09/2026 | 107 | AN | AN31/07/2026 | G1G | ACCESSORIES | G1 | ok |  | 23/09: ex-fty 516394 | PRINT L3 SUB PROCESS_V3 | 0903387168 LI2667 | 16/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 22/09/2026 | PET SWEATSHIRT BLACK/WHITE |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 107 |  | 107 |  |  | 18/09/2026 | 19/09/2026 | 2026-11-09 | 16/09/2026 | 107 | 104 | 3
ADIDAS | 0903387206-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 463 | 23/09/2026 | 463 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 22/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903387206 LI2672 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/09/2026 | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 463 |  | 463 |  |  | 19/09/2026 | 21/09/2026 | 18/09/2026 | 18/09/2026 | 463 | 409 | 54
ADIDAS | 0903387271-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 71 | 31/10/2026 | 71 | SA | SA31/07/2026 | G1B | SHORTS | G1 |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Men Chuen, PI Date ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903387271 KX9851 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 21/11/2026 | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 71 |  | 71 |  |  | 18/11/2026 | 18/11/2026 |  |  | 71 |  | 71 |  |  | 13/11/2026 | 13/11/2026 |  |  | 71 |  | 71
ADIDAS | 0903387336-1 HK7319 | BLACK | 90D | F2225M403 | 500 | 31/10/2026 | 500 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 547012 | EMBRO+PPA SUB PROCESS_V3 | 0903387336 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 24/10/2026 | ESS SWTP |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 500 |  | 500 |  |  | 21/10/2026 | 23/10/2026 |  |  | 500 |  | 500
ADIDAS | 0903387369-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 690 | 31/10/2026 | 690 | SA | SA31/07/2026 | G2T | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387369 JE6340 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 20/10/2026 | M 3S FT FZ HD |  | SS27 | 20/10/2026 | 21/10/2026 |  |  | 690 |  | 690 |  |  | 16/10/2026 | 17/10/2026 |  |  | 690 |  | 690
ADIDAS | 0903387402-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2P | SHORTS | G2 | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387402 JE6414 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 24/10/2026 | M 3S FT SHO BLACK/WHITE |  | SS27 | 24/10/2026 | 27/10/2026 |  |  | 1380 |  | 1380 |  |  | 21/10/2026 | 23/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903387487-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 461 | 31/10/2026 | 461 | SI | SI31/07/2026 | G2R | SHORTS | G2 | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 516442 | HT SUB PROCESS_V1 | 0903387487 JC9584 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 19/10/2026 | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 461 |  | 461 |  |  | 16/10/2026 | 17/10/2026 |  |  | 461 |  | 461 |  |  | 15/10/2026 | 16/10/2026 |  |  | 461 |  | 461
ADIDAS | 0903387523-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1380 | 31/10/2026 | 1380 | SI | SI31/07/2026 | G3K | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903387523 HR8583 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | ESS SWTP |  | SS27 | 26/10/2026 | 28/10/2026 |  |  | 1380 |  | 1380 |  |  | 22/10/2026 | 24/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903387560-1 JV5067 | OFF WHITE | 60D | F25KIUGFX010 | 1036 | 31/10/2026 | 1036 | SI | SI31/07/2026 | G2E | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903387560 JV5067 |  | KAHATEX CIJERAH | ITALY | SEA | 14/10/2026 | I ADIRAPTOR T |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 1036 |  | 1036 |  |  | 2026-10-10 | 2026-12-10 |  |  | 1036 |  | 1036
ADIDAS | 0903387602-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 919 | 31/10/2026 | 919 | SA | SA31/07/2026 | G2A | SHORTS | G2 | (12/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903387602 JE6417 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-10-10 | M 17S FT SHO DARK BLUE/WHITE |  | SS27 | 2026-10-10 | 13/10/2026 |  |  | 919 |  | 919 |  |  | 2026-07-10 | 2026-09-10 |  |  | 919 |  | 919
ADIDAS | 0903387638-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 1150 | 31/10/2026 | 1150 | SA | SA31/07/2026 | G2S | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903387638 JE6341 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | M 3S FT FZ HD |  | SS27 | 2026-12-10 | 14/10/2026 |  |  | 1150 |  | 1150 |  |  | 2026-08-10 | 2026-10-10 |  |  | 1150 |  | 1150
ADIDAS | 0903387764-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 1 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387764 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903388131-1 IC5189 | WHITE | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903388131 IC5189 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 31/10/2026 | OWN THE RUN TEE |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 217 |  | 217 |  |  | 29/10/2026 | 31/10/2026 |  |  | 217 |  | 217 |  |  | 28/10/2026 | 30/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903388403-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388403 KX8875 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 31/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903388432-1 KX8877 | WHITE | 90D | S27GMGFX100 | 416 | 31/10/2026 | 416 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388432 KX8877 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-08-10 | M CHIP T WHITE |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 416 |  | 416 |  |  | 2026-05-10 | 2026-05-10 |  |  | 416 |  | 416
ADIDAS | 0903388455-1 LC6341 | BLACK | 90D | S27GMGFX130 | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | (01/09/2026) |  | 516320 | PRINT L3+PAD SUB PROCESS_V3 | 0903388455 LC6341 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 2026-04-11 | M SEE2X SHO12X T BLACK |  | SS27 | 2026-04-11 | 2026-04-11 |  |  | 100 |  | 100 |  |  | 31/10/2026 | 31/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903388544-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 773 | 31/10/2026 | 773 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388544 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 20/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 20/11/2026 | 23/11/2026 |  |  | 773 |  | 773 |  |  | 17/11/2026 | 18/11/2026 |  |  | 773 |  | 773 |  |  | 16/11/2026 | 17/11/2026 |  |  | 773 |  | 773
ADIDAS | 0903388567-1 KA4331 | BLACK | 90D | S2608MR0902 | 1066 | 31/10/2026 | 1066 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903388567 KA4331 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 24/11/2026 | 25/11/2026 |  |  | 1066 |  | 1066 |  |  | 19/11/2026 | 20/11/2026 |  |  | 1066 |  | 1066 |  |  | 18/11/2026 | 19/11/2026 |  |  | 1066 |  | 1066
ADIDAS | 0903388591-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 770 | 31/10/2026 | 770 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903388591 LD0277 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 24/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 24/11/2026 | 26/11/2026 |  |  | 770 |  | 770 |  |  | 19/11/2026 | 23/11/2026 |  |  | 770 |  | 770 |  |  | 18/11/2026 | 20/11/2026 |  |  | 770 |  | 770
ADIDAS | 0903388611-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 158 | 31/10/2026 | 158 | SA | SA31/07/2026 | G1G | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 512102 | PAD+HT SUB PROCESS_V3 | 0903388611 LD0277 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 24/11/2026 | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX | 24/11/2026 | 26/11/2026 |  |  | 158 |  | 158 |  |  | 19/11/2026 | 23/11/2026 |  |  | 158 |  | 158 |  |  | 18/11/2026 | 20/11/2026 |  |  | 158 |  | 158
ADIDAS | 0903388672-1 IC5188 | BLACK | 90D | S23080640 | 473 | 31/10/2026 | 473 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903388672 IC5188 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA | 29/10/2026 | OWN THE RUN TEE |  | SS27 | 29/10/2026 | 30/10/2026 |  |  | 473 |  | 473 |  |  | 27/10/2026 | 28/10/2026 |  |  | 473 |  | 473 |  |  | 26/10/2026 | 27/10/2026 |  |  | 473 |  | 473
ADIDAS | 0903388692-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 104 | 31/10/2026 | 104 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 848012 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903388692 JD1877 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 104 |  | 104 |  |  | 19/10/2026 | 20/10/2026 |  |  | 104 |  | 104
ADIDAS | 0903388840-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 110 | 31/10/2026 | 110 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388840 KW2909 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 27/11/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 27/11/2026 | 27/11/2026 |  |  | 110 |  | 110 |  |  | 24/11/2026 | 24/11/2026 |  |  | 110 |  | 110
ADIDAS | 0903388861-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV-MTF | 116 | 31/10/2026 | 116 | AN | AN31/07/2026 | G1B | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388861 KW2909 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 27/11/2026 | W 3S WV WB BLACK/WHITE |  | SS27 | 27/11/2026 | 27/11/2026 |  |  | 116 |  | 116 |  |  | 24/11/2026 | 24/11/2026 |  |  | 116 |  | 116
ADIDAS | 0903388888-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 166 | 31/10/2026 | 166 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388888 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 16/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 16/11/2026 | 17/11/2026 |  |  | 166 |  | 166 |  |  | 2026-11-11 | 2026-12-11 |  |  | 166 |  | 166
ADIDAS | 0903388890-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 430 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388890 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388903-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 150 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug. 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388903 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388929-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV-MTF | 125 | 31/10/2026 | 125 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388929 KZ3204 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA | 16/11/2026 | W 3S WV BOMBER WHITE/BLACK |  | SS27 | 16/11/2026 | 17/11/2026 |  |  | 125 |  | 125 |  |  | 2026-11-11 | 2026-12-11 |  |  | 125 |  | 125
ADIDAS | 0903388990-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 10048 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388990 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389129-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903389129 KW1544 |  | KAHATEX CIJERAH | VIETNAM | SEA | 19/10/2026 | M BLANK TEE |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 800 |  | 800 |  |  | 15/10/2026 | 16/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903389677-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 460 | 31/10/2026 | 460 | SA | SA31/07/2026 | G1I | SWEATSHIRT | G1 | ok |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389677 JN1958 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-04-11 | W 3S FT QZ HD |  | SS27 | 2026-04-11 | 2026-06-11 |  |  | 460 |  | 460 |  |  | 31/10/2026 | 2026-03-11 |  |  | 460 |  | 460
ADIDAS | 0903389678-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 207 | 30/09/2026 | 207 | SI | SI31/07/2026 | G1Q | T-SHIRT | G1 | ok |  | 29/09: ex-fty (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903389678 KD3911 | 16/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 18/09/2026 | RELEASED |  | SS27 | 18/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 207 | 99 | 108 |  | 99 | 15/09/2026 | 17/09/2026 | 15/09/2026 | 18/09/2026 | 207 | 207
ADIDAS | 0903389747-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2070 | 31/10/2026 | 2070 | SA | SA31/07/2026 | G2T | JACKET | G2 | (16/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903389747 JE6338 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | M 3S FT FZ HD |  | SS27 | 26/10/2026 | 29/10/2026 |  |  | 2070 |  | 2070 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2070 |  | 2070
ADIDAS | 0903389758-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 109 | 30/09/2026 | 109 | SI | SI31/07/2026 | G1Q | T-SHIRT | G1 | ok |  | 25/09: ex-fty 814006 | EMBRO SUB PROCESS_V1 | 0903389758 KD3911 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA | 18/09/2026 | RELEASED |  | SS27 | 18/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 109 | 69 | 40 |  | 69 | 15/09/2026 | 17/09/2026 | 14/09/2026 | 18/09/2026 | 109 | 107 | 2
ADIDAS | 0903389769-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 232 | 30/09/2026 | 232 | SA | SA31/07/2026 | G1I | ACCESSORIES | G1 | ok |  | 25/09: ex-fty 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903389769 LI2671 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/09/2026 | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27 | 26/09/2026 | 26/09/2026 |  |  | 232 |  | 232 |  |  | 23/09/2026 | 23/09/2026 | 19/09/2026 | 19/09/2026 | 232 | 4 | 228 |  | 4
ADIDAS | 0903389788-1 JV5068 | HALO MINT F21 | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903389788 JV5068 |  | KAHATEX CIJERAH | ITALY | SEA | 30/10/2026 | I ADIRAPTOR T |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 919 |  | 919 |  |  | 27/10/2026 | 28/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903389808-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 415 | 23/09/2026 | 415 | AN | AN31/07/2026 | G1K | ACCESSORIES | G1 | ok |  | 19/09: ex-fty. DRC 0090-early shipment customer (BTP_27_08_2026 EARLY HOLD SHIPMENT). 516333 | PRINT L3 SUB PROCESS_V3 | 0903389808 LI2669 | 16/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 17/09/2026 | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27 | 17/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 415 | 415 |  |  | 63 | 14/09/2026 | 16/09/2026 | 2026-11-09 | 18/09/2026 | 415 | 416 | -1 | 1
ADIDAS | 0903389891-1 JN1948 | WHITE/BLACK | 90D | S2554WES413FTB | 1151 | 31/10/2026 | 1151 | SA | SA31/07/2026 | G1L | SWEATSHIRT | G1 | (12/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389891 JN1948 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-03-11 | W 3S FT QZ HD |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 1151 |  | 1151 |  |  | 30/10/2026 | 31/10/2026 |  |  | 1151 |  | 1151
ADIDAS | 0903389932-1 HK7319 | BLACK | 90D | F2225M403 | 1379 | 31/10/2026 | 1379 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389932 HK7319 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | ESS SWTP |  | SS27 | 29/10/2026 | 2026-02-11 |  |  | 1379 |  | 1379 |  |  | 26/10/2026 | 29/10/2026 |  |  | 1379 |  | 1379
ADIDAS | 0903389964-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1609 | 31/10/2026 | 1609 | SI | SI31/07/2026 | G3J | SHORTS | G3 | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389964 JE1309 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | W 3S WV SHO |  | SS27 | 31/10/2026 | 2026-04-11 |  |  | 1609 |  | 1609 |  |  | 28/10/2026 | 31/10/2026 |  |  | 1609 |  | 1609
ADIDAS | 0903389996-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1381 | 31/10/2026 | 1381 | SI | SI31/07/2026 | G3C | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903389996 HK7317 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 31/10/2026 | ESS SWTP |  | SS27 | 31/10/2026 | 2026-03-11 |  |  | 1381 |  | 1381 |  |  | 28/10/2026 | 30/10/2026 |  |  | 1381 |  | 1381
ADIDAS | 0903390024-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1380 | 31/10/2026 | 1380 | SA | SA31/07/2026 | G2A | SHORTS | G2 | ok |  | 516442 | EMBRO SUB PROCESS_V1 | 0903390024 JE6419 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27 | 21/10/2026 | 24/10/2026 |  |  | 1380 |  | 1380 |  |  | 17/10/2026 | 21/10/2026 |  |  | 1380 |  | 1380
ADIDAS | 0903390063-1 JV5069 | CLEAR PINK | 60D | F25KIUGFX010 | 919 | 31/10/2026 | 919 | SI | SI31/07/2026 | G2G | T-SHIRT | G2 | (01/09/2026) |  | 516442 | PRINT L2 SUB PROCESS_V3 | 0903390063 JV5069 |  | KAHATEX CIJERAH | ITALY | SEA | 26/10/2026 | I ADIRAPTOR T |  | SS27 | 26/10/2026 | 27/10/2026 |  |  | 919 |  | 919 |  |  | 22/10/2026 | 23/10/2026 |  |  | 919 |  | 919
ADIDAS | 0903390099-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1839 | 31/10/2026 | 1839 | SA | SA31/07/2026 | G3E | PANTS | G3 | (16/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390099 JW7178 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-02-11 | W 3S FT OH PT |  | SS27 | 2026-02-11 | 2026-04-11 |  |  | 1839 |  | 1839 |  |  | 29/10/2026 | 31/10/2026 |  |  | 1839 |  | 1839
ADIDAS | 0903390198-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 377 | 31/10/2026 | 377 | SA | SA31/07/2026 | G1J | SHORTS | G1 |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 834012 | PAD+HT SUB PROCESS_V3 | 0903390198 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 20/11/2026 | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX | 20/11/2026 | 23/11/2026 |  |  | 377 |  | 377 |  |  | 17/11/2026 | 18/11/2026 |  |  | 377 |  | 377 |  |  | 16/11/2026 | 17/11/2026 |  |  | 377 |  | 377
ADIDAS | 0903390259-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 500 | 30/09/2026 | 500 | SA | SA31/07/2026 | G2A | T-SHIRT | G2 | ok |  | 30/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). 547012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390259 KA5090 | 16/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA | 23/09/2026 | MINI EMB T |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 500 |  | 500 |  |  | 19/09/2026 | 21/09/2026 |  |  | 500 |  | 500 |  |  | 17/09/2026 | 18/09/2026 |  |  | 500 |  | 500
ADIDAS | 0903390291-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 276 | 2026-09-09 | 276 | SI | SI31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 09/09: ex-fty 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903390291 IW2479 | 2026-03-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-07-09 | POS TABLE LK |  | SS27 | 2026-07-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 276 | 276 |  |  |  | 2026-03-09 | 2026-05-09 | 2026-03-09 | 2026-08-09 | 276 | 276
ADIDAS | 0903390301-1 JM0374 | OFF WHITE | 60D | S25SPRMGFX233 | 2062 | 15/10/2026 | 2062 | SA | SA31/07/2026 | G2L | T-SHIRT | G2 | (01/09/2026) |  | 804028 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903390301 JM0374 | 16/09/2026 | KAHATEX CIJERAH | JAPAN | SEA | 2026-06-10 | M L SLIDE PKT T |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 2062 |  | 2062 |  |  | 2026-02-10 | 2026-05-10 |  |  | 2062 |  | 2062 |  |  | 30/09/2026 | 2026-02-10 |  |  | 2062 |  | 2062
ADIDAS | 0903390768-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 233 | 31/10/2026 | 233 | SI | SI31/07/2026 | G3C | PANTS | G3 | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390768 JD5302 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-11 | W 3S FT CF PT |  | SS27 | 2026-09-11 | 2026-10-11 |  |  | 233 |  | 233 |  |  | 2026-04-11 | 2026-05-11 |  |  | 233 |  | 233
ADIDAS | 0903390837-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 106 | 31/10/2026 | 106 | SI | SI31/07/2026 | G3E | SHORTS | G3 | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903390837 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-11 | W SL FT SHO |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 106 |  | 106 |  |  | 2026-05-11 | 2026-06-11 |  |  | 106 |  | 106
ADIDAS | 0903391146-1 HK7319 | BLACK | 90D | F2225M403 | 1122 | 31/10/2026 | 1122 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903391146 HK7319 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 27/10/2026 | ESS SWTP |  | SS27 | 27/10/2026 | 29/10/2026 |  |  | 1122 |  | 1122 |  |  | 23/10/2026 | 26/10/2026 |  |  | 1122 |  | 1122
ADIDAS | 0903391266-1 HK7319 | BLACK | 90D | F2225M403 | 900 | 31/10/2026 | 900 | SI | SI31/07/2026 | G3G | PANTS | G3 | (02/09/2026) |  | IMPROVE. DRC 0002-T2 YKK, LLT material, PI Date 15-Oct, ETD 18-Sep. 848024 | EMBRO+PPA SUB PROCESS_V3 | 0903391266 HK7319 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 22/10/2026 | ESS SWTP |  | SS27 | 22/10/2026 | 24/10/2026 |  |  | 900 |  | 900 |  |  | 19/10/2026 | 21/10/2026 |  |  | 900 |  | 900
ADIDAS | 0903391415-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 604 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516438 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391415 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903391521-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 190 | 31/10/2026 | 190 | SA | SA31/07/2026 | G3K | PANTS | G3 | (12/09/2026) |  | 512114 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903391521 JW7182 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-03-11 | W 3S FT OH PT |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 190 |  | 190 |  |  | 30/10/2026 | 31/10/2026 |  |  | 190 |  | 190
ADIDAS | 0903391655-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 800 | 15/10/2026 | 800 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903391655 KW1543 |  | KAHATEX CIJERAH | VIETNAM | SEA | 19/10/2026 | M BLANK TEE |  | SS27 | 19/10/2026 | 19/10/2026 |  |  | 800 |  | 800 |  |  | 15/10/2026 | 15/10/2026 |  |  | 800 |  | 800
ADIDAS | 0903391682-1 IC5188 | BLACK | 90D | S23080640 | 217 | 31/10/2026 | 217 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903391682 IC5188 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 30/10/2026 | OWN THE RUN TEE |  | SS27 | 30/10/2026 | 31/10/2026 |  |  | 217 |  | 217 |  |  | 28/10/2026 | 29/10/2026 |  |  | 217 |  | 217 |  |  | 27/10/2026 | 28/10/2026 |  |  | 217 |  | 217
ADIDAS | 0903392177-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2300 | 31/10/2026 | 2300 | SA | SA31/07/2026 | G2E | JACKET | G2 | (12/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903392177 JD1877 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | M 3S FT FZ HD |  | SS27 | 23/10/2026 | 27/10/2026 |  |  | 2300 |  | 2300 |  |  | 20/10/2026 | 23/10/2026 |  |  | 2300 |  | 2300
ADIDAS | 0903392343-1 LI8103 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS404WV | 315 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903392343 LI8103 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903393703-1 IZ4760 | ALUMINA S20 | 45D | F213CSIM105FL | 1833 | 2026-12-09 | 1833 | NT | NT31/07/2026 | G2P | SWEATSHIRT | G2 | ok |  | 10/09: ex-fty 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393703 IZ4760 | 2026-03-09 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-03-09 | M FEELCOZY HD |  | SS27 | 2026-03-09 | 2026-12-09 | 2026-05-09 | 2026-10-09 | 1833 | 1833 |  |  |  | 31/08/2026 | 2026-09-09 | 2026-04-09 | 2026-11-09 | 1833 | 1833
ADIDAS | 0903393839-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 500 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393839 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903393868-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 219 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393868 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903393909-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 1153 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903393909 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903394744-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 509 | 31/10/2026 | 509 | SI | SI31/07/2026 | G3A | PANTS | G3 | (12/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903394744 JF3604 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-05-11 | M WIDE PANT FT |  | SS27 | 2026-05-11 | 2026-05-11 |  |  | 509 |  | 509 |  |  | 2026-02-11 | 2026-02-11 |  |  | 509 |  | 509
ADIDAS | 0903394768-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 891 | 30/09/2026 | 891 | SA | SA31/07/2026 | G2A | T-SHIRT | G2 | ok |  | 23/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394768 KA5090 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 21/09/2026 | MINI EMB T |  | SS27 | 21/09/2026 | 22/09/2026 |  |  | 891 |  | 891 |  |  | 17/09/2026 | 18/09/2026 | 19/09/2026 | 19/09/2026 | 891 | 531 | 360 |  | 531 | 15/09/2026 | 16/09/2026 | 2026-09-09 | 19/09/2026 | 891 | 771 | 120 |  | 18
ADIDAS | 0903394796-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 940 | 30/09/2026 | 940 | SA | SA31/07/2026 | G2A | T-SHIRT | G2 | ok |  | 24/09: ex-fty 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394796 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 22/09/2026 | MINI EMB T |  | SS27 | 22/09/2026 | 23/09/2026 |  |  | 940 |  | 940 |  |  | 18/09/2026 | 19/09/2026 |  |  | 940 |  | 940 |  |  | 16/09/2026 | 17/09/2026 | 16/09/2026 | 18/09/2026 | 940 | 729 | 211
ADIDAS | 0903394896-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 | 563 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394896 KA5088 | 16/09/2026 | KAHATEX CIJERAH | CANADA | SEA | 2026-03-11 | MINI EMB T |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 563 |  | 563 |  |  | 30/10/2026 | 30/10/2026 |  |  | 563 |  | 563 |  |  | 28/10/2026 | 28/10/2026 |  |  | 563 |  | 563
ADIDAS | 0903394920-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 563 | 31/10/2026 | 563 | SA | SA31/07/2026 | G2N | T-SHIRT | G2 | ok |  | 630001 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903394920 KA5090 |  | KAHATEX CIJERAH | CANADA | SEA | 2026-03-11 | MINI EMB T |  | SS27 | 2026-03-11 | 2026-04-11 |  |  | 563 |  | 563 |  |  | 30/10/2026 | 31/10/2026 |  |  | 563 |  | 563 |  |  | 28/10/2026 | 29/10/2026 |  |  | 563 |  | 563
ADIDAS | 0903395478-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 370 | 31/10/2026 | 370 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 672027 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903395478 JD1877 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 370 |  | 370 |  |  | 19/10/2026 | 20/10/2026 |  |  | 370 |  | 370
ADIDAS | 0903395527-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 172 | 31/10/2026 | 172 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | ok |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395527 LC6339 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 172 |  | 172 |  |  | 2026-05-10 | 2026-05-10 |  |  | 172 |  | 172
ADIDAS | 0903395611-1 KX8877 | WHITE | 90D | S27GMGFX100 | 210 | 31/10/2026 | 210 | SA | SA31/07/2026 | G2J | T-SHIRT | G2 | (01/09/2026) |  | 516427 | PRINT L3+PAD SUB PROCESS_V3 | 0903395611 KX8877 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-08-10 | M CHIP T WHITE |  | SS27 | 2026-08-10 | 2026-08-10 |  |  | 210 |  | 210 |  |  | 2026-05-10 | 2026-05-10 |  |  | 210 |  | 210
ADIDAS | 0903396292-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 316 | 15/10/2026 | 316 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396292 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 30/09/2026 | K BLANK TEE |  | SS27 | 30/09/2026 | 30/09/2026 |  |  | 316 |  | 316 |  |  | 26/09/2026 | 26/09/2026 |  |  | 316 |  | 316
ADIDAS | 0903396384-1 KD9090 | WHITE | 30D | F25GFXBLANKY | 435 | 15/10/2026 | 435 | SA | SA31/07/2026 | G2M | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396384 KD9090 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 29/09/2026 | K BLANK TEE |  | SS27 | 29/09/2026 | 30/09/2026 |  |  | 435 |  | 435 |  |  | 25/09/2026 | 26/09/2026 |  |  | 435 |  | 435
ADIDAS | 0903397096-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 461 | 30/10/2026 | 461 | SA | SA31/07/2026 | G1B | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397096 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 16/11/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 16/11/2026 | 17/11/2026 |  |  | 461 |  | 461 |  |  | 2026-11-11 | 2026-12-11 |  |  | 461 |  | 461 |  |  | 2026-06-11 | 2026-09-11 |  |  | 461 |  | 461
ADIDAS | 0903397121-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/10/2026 | 300 | SA | SA31/07/2026 | G1C | SHORTS | G1 | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397121 KT4839 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-02-11 | ADIZERO E SHORT ONIX |  | SS27-TRAX | 2026-02-11 | 2026-03-11 |  |  | 300 |  | 300 |  |  | 29/10/2026 | 30/10/2026 |  |  | 300 |  | 300 |  |  | 26/10/2026 | 27/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903397664-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 300 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903397664 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903397808-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 105 | 31/10/2026 | 105 | SI | SI31/07/2026 | G1M | T-SHIRT | G1 | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903397808 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-03-11 | OWN THE RUN TEE |  | SS27 | 2026-03-11 | 2026-03-11 |  |  | 105 |  | 105 |  |  | 31/10/2026 | 31/10/2026 |  |  | 105 |  | 105 |  |  | 30/10/2026 | 30/10/2026 |  |  | 105 |  | 105
ADIDAS | 0903397832-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 356 | 30/09/2026 | 356 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 28/09: ex-fty 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397832 JC5283 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-05-10 | M L SLIDE PKT T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 356 |  | 356 |  |  | 2026-01-10 | 2026-02-10 |  |  | 356 |  | 356 |  |  | 29/09/2026 | 30/09/2026 | 15/09/2026 | 15/09/2026 | 356 | 351 | 5
ADIDAS | 0903397854-1 KA4331 | BLACK | 90D | S2608MR0902 | 1280 | 31/10/2026 | 1280 | SA | SA31/07/2026 | G1I | SHORTS | G1 | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903397854 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-07-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-07-11 | 2026-10-11 |  |  | 1280 |  | 1280 |  |  | 2026-04-11 | 2026-05-11 |  |  | 1280 |  | 1280 |  |  | 2026-03-11 | 2026-04-11 |  |  | 1280 |  | 1280
ADIDAS | 0903397883-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 258 | 30/09/2026 | 258 | SA | SA31/07/2026 | G2G | T-SHIRT | G2 | ok |  | 28/09: ex-fty 1st Art (TC 10 pcs) 830009 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903397883 JC5282 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-05-10 | M L SLIDE PKT T |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 258 |  | 258 |  |  | 2026-01-10 | 2026-02-10 |  |  | 258 |  | 258 |  |  | 29/09/2026 | 30/09/2026 | 2026-04-09 | 18/09/2026 | 258 | 256 | 2
ADIDAS | 0903397901-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 3558 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903397901 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903398085-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 114 | 31/10/2026 | 114 | SI | SI31/07/2026 | G3E | SHORTS | G3 | (12/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398085 JD9944 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-10-11 | W SL FT SHO |  | SS27 | 2026-10-11 | 2026-11-11 |  |  | 114 |  | 114 |  |  | 2026-05-11 | 2026-06-11 |  |  | 114 |  | 114
ADIDAS | 0903398370-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 129 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398370 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903398417-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 341 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398417 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398667-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 609 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398667 KV7863 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903398692-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 827 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398692 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903398713-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 685 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903398713 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903398767-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 796 | 31/10/2026 | 796 | AN | AN31/07/2026 | G1L | JACKET | G1 | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903398767 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-06-11 | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27 | 2026-06-11 | 2026-10-11 |  |  | 796 |  | 796 |  |  | 2026-03-11 | 2026-05-11 |  |  | 796 |  | 796
ADIDAS | 0903400198-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 102 | 31/10/2026 | 102 | SI | SI31/07/2026 | G2S | T-SHIRT | G2 | ok |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903400198 IU0217 |  | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 102 |  | 102 |  |  | 2026-06-10 | 2026-06-10 |  |  | 102 |  | 102
ADIDAS | 0903400562-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 100 | 31/10/2026 | 100 | SA | SA31/07/2026 | G2Q | JACKET | G2 | (12/09/2026) |  | 839055 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903400562 JD1877 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA | 22/10/2026 | M 3S FT FZ HD |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903401786-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 31/10/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516254 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401786 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903401814-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 161 | 31/10/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD 02-Sep, ETA-Kaha 14-Sep. T2 Kahatex, PI Date 02-Sep, actual receives 07-Sep. T2 Libolon, PI Date 28-Aug, actual receives 29-Aug. 516443 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903401814 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903445381-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 2861 | 30/09/2026 | 2861 | SA | SA26/06/2026 | G3I | PANTS | G3 | ok | ok | 25/09: ex-fty 1st Art (TC 10 pcs) 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445381 JW7178 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 15/09/2026 | W 3S FT OH PT |  | SS27 | 15/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 2861 | 1803 | 1058 |  | 410 | 2026-11-09 | 16/09/2026 | 2026-02-09 | 18/09/2026 | 2861 | 2822 | 39
ADIDAS | 0903445382-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA26/06/2026 | G2F | T-SHIRT | G2 | ok | ok | 24/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445382 LC6339 | 2026-10-09 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M CHIP T CRYSTAL SKY S26 |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-02-10 | 2026-09-09 | 2026-09-09 | 100 | 100
ADIDAS | 0903445383-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/09/2026 | 100 | SA | SA12/06/2026 | G2F | T-SHIRT | G2 | (11/07/2026) | (04/07/2026) | 25/09: ex-fty 516204 | PRINT L3+PAD SUB PROCESS_V3 | 0903445383 KX8877 | 28/08/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | M CHIP T WHITE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 100 |  | 100 |  |  | 2026-01-10 | 2026-01-10 | 17/09/2026 | 17/09/2026 | 100 | 97 | 3
ADIDAS | 0903445384-1 JW7177 | WONDER ALUMINA S25/WHITE | 90D | S2554WES512FT | 3083 | 30/09/2026 | 3083 | SA | SA26/06/2026 | G3E | PANTS | G3 | ok | ok | 25/09: ex-fty 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903445384 JW7177 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT OH PT |  | SS27 | 18/09/2026 | 22/09/2026 | 17/09/2026 | 19/09/2026 | 3083 | 2217 | 866 |  | 827 | 15/09/2026 | 18/09/2026 | 15/09/2026 | 19/09/2026 | 3083 | 3025 | 58 |  | 53
ADIDAS | 0903445385-1 JN1958 | WONDER ALUMINA S25/WHITE | 90D | S2554WES413FTB | 3082 | 30/09/2026 | 3082 | SA | SA26/06/2026 | G1L | SWEATSHIRT | G1 | ok | ok | 24/09: ex-fty 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903445385 JN1958 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA | 18/09/2026 | W 3S FT QZ HD |  | SS27 | 18/09/2026 | 23/09/2026 | 18/09/2026 | 19/09/2026 | 3082 | 1235 | 1847 |  | 745 | 15/09/2026 | 19/09/2026 | 17/09/2026 | 19/09/2026 | 3082 | 2031 | 1051 |  | 360
ADIDAS | 0903450147-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 98 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450147 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450148-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1114 | 2026-05-09 | 1114 | SA | SA15/05/2026 | G2L | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450148 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 2026-01-09 | 2026-04-09 | 1114 | 1114 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-03-09 | 1114 | 1114 |  |  |  | 24/08/2026 | 31/08/2026 | 22/08/2026 | 2026-02-09 | 1114 | 1114
ADIDAS | 0903450149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 3791 | 2026-05-09 | 3791 | SA | SA15/05/2026 | G2J,G2K | T-SHIRT | G2 | ok |  | 04/09: ex-fty. DRC 0090-early shipment customer (Kahatex IPF). 600000 | HT+PAD SUB PROCESS_V3 | 0903450149 KX3654 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 31/08/2026 | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI | 31/08/2026 | 2026-05-09 | 31/08/2026 | 2026-04-09 | 3791 | 3791 |  |  |  | 27/08/2026 | 2026-02-09 | 22/08/2026 | 2026-02-09 | 3791 | 3791 |  |  |  | 24/08/2026 | 31/08/2026 | 21/08/2026 | 2026-02-09 | 3791 | 3791
ADIDAS | 0903450150-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 129 | 23/09/2026 | 129 | SI | SI12/06/2026 | G2H,G2L | T-SHIRT | G2 | ok |  | 21/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450150 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 31/08/2026 | 2026-06-08 | 2026-01-09 | 129 | 129 |  |  |  | 2026-04-08 | 27/08/2026 | 31/07/2026 | 29/08/2026 | 129 | 129
ADIDAS | 0903450151-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 152 | 31/10/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450151 KC9082 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903450152-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 172 | 19/09/2026 | 172 | SI | SI12/06/2026 | G2L | T-SHIRT | G2 | ok | (04/07/2026) | 18/09: ex-fty 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903450152 KS1804 | 28/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-08 | BIG APPLE TEE |  | SS27 | 2026-07-08 | 2026-12-08 | 2026-06-08 | 2026-07-08 | 172 | 172 |  |  |  | 2026-04-08 | 2026-07-08 | 31/07/2026 | 29/08/2026 | 172 | 172
ADIDAS | 0903450153-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 942 | 15/10/2026 | 942 | SA | SA24/01/2026 | G1M | T-SHIRT | G1 | ok |  | DRC 0010-hold shipment customer (BTP_24_06_2026 -> Req. PO Cancel & Quantity Change). T2 Far Eastern, PI Date 21-Sep (switch with fabric from Libolon for 500pcs). T2 Fu Hsun, PI Date 18-Aug. 814006 | HT SUB PROCESS_V1 | 0903450153 KG8548 | 2026-08-04 | KAHATEX CIJERAH | THAILAND | SEA | 30/06/2026 | ADIZERO E TEE |  | FW26 | 30/06/2026 | 21/09/2026 | 30/06/2026 | 2026-07-07 | 942 | 273 | 669 |  |  | 26/06/2026 | 18/09/2026 | 20/06/2026 | 20/06/2026 | 942 | 273 | 669 |  |  | 25/06/2026 | 17/09/2026 | 2026-12-08 | 2026-12-08 | 942 | 273 | 669
ADIDAS | 0903467951-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903467951 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 920 |  | 920 |  |  | 2026-12-10 | 13/10/2026 |  |  | 920 |  | 920
ADIDAS | 0903472791-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1P | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472791 IB8688 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-07-10 | ESS HDY |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 2000 |  | 2000 |  |  | 2026-03-10 | 2026-06-10 |  |  | 2000 |  | 2000
ADIDAS | 0903472864-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903472864 IB8688 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 480 |  | 480 |  |  | 2026-12-10 | 13/10/2026 |  |  | 480 |  | 480
ADIDAS | 0903476466-1 JZ7711 | BLACK | 120D | S2608MR0202 | 249 | 30/09/2026 | 249 | SA | SA14/08/2026 | G3E | SHORTS | G3 | ok |  | DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903476466 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 24/09/2026 | 24/09/2026 |  |  | 249 |  | 249 |  |  | 21/09/2026 | 21/09/2026 |  |  | 249 |  | 249 |  |  | 17/09/2026 | 17/09/2026 | 16/09/2026 | 19/09/2026 | 249 | 177 | 72 |  | 170
ADIDAS | 0903478300-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 24/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478300 HK7311 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 29/10/2026 | ESS HDY |  | SS27 | 29/10/2026 | 2026-02-11 |  |  | 2001 |  | 2001 |  |  | 26/10/2026 | 29/10/2026 |  |  | 2001 |  | 2001
ADIDAS | 0903478487-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 202 | 15/09/2026 | 202 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478487 IN1172 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 202 | 202 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-10-09 | 14/09/2026 | 202 | 202 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-10-09 | 14/09/2026 | 202 | 202
ADIDAS | 0903478570-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 2001 | 15/10/2026 | 2001 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478570 HK7311 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-08-10 |  |  | 2001 |  | 2001 |  |  | 2026-01-10 | 2026-05-10 |  |  | 2001 |  | 2001
ADIDAS | 0903478582-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 139 | 15/09/2026 | 139 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 839055 | HT SUB PROCESS_V1 | 0903478582 IN1156 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 139 | 139 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 139 | 139 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 139 | 139
ADIDAS | 0903478609-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 164 | 15/09/2026 | 164 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty (STOOD). IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 839055 | HT SUB PROCESS_V1 | 0903478609 IN1157 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 164 | 164 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 164 | 164 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-12-09 | 14/09/2026 | 164 | 164
ADIDAS | 0903478627-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903478627 HK7311 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 920 |  | 920 |  |  | 2026-08-10 | 2026-12-10 |  |  | 920 |  | 920
ADIDAS | 0903480271-1 IS1413 | BLACK | 60D | S2425M405 | 900 | 15/10/2026 | 900 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848024 | PRINT L3 SUB PROCESS_V3 | 0903480271 IS1413 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 2026-05-10 | IN RANGE |  | SS27 | 2026-05-10 | 2026-06-10 |  |  | 900 |  | 900 |  |  | 2026-01-10 | 2026-02-10 |  |  | 900 |  | 900
ADIDAS | 0903480314-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 602 | 15/10/2026 | 602 | SA | SA14/08/2026 | G2A | T-SHIRT | G2 | (14/09/2026) |  | 848024 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903480314 KA5090 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA | 23/09/2026 | MINI EMB T |  | SS27 | 23/09/2026 | 24/09/2026 |  |  | 602 |  | 602 |  |  | 19/09/2026 | 21/09/2026 |  |  | 602 |  | 602 |  |  | 17/09/2026 | 18/09/2026 |  |  | 602 |  | 602
ADIDAS | 0903480517-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 378 | 23/10/2026 | 378 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848016 | PRINT L3 SUB PROCESS_V3 | 0903480517 IU0217 |  | KAHATEX CIJERAH | MOROCCO | SEA | 2026-09-10 | IN RANGE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 378 |  | 378 |  |  | 2026-06-10 | 2026-06-10 |  |  | 378 |  | 378
ADIDAS | 0903480831-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 335 | 15/10/2026 | 335 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480831 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-09-10 | W BLANK TEE |  | SS27 | 2026-09-10 | 2026-09-10 |  |  | 335 |  | 335 |  |  | 2026-06-10 | 2026-06-10 |  |  | 335 |  | 335
ADIDAS | 0903480958-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1F | SWEATSHIRT | G1 | (15/09/2026) |  | 26/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480958 HK7309 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | ESS HDY |  | SS27 | 2026-02-10 | 2026-06-10 |  |  | 2250 |  | 2250 |  |  | 29/09/2026 | 2026-02-10 |  |  | 2250 |  | 2250
ADIDAS | 0903480993-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 1679 | 15/10/2026 | 1679 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903480993 HK7311 |  | KAHATEX CIJERAH | GERMANY | SEA | 15/10/2026 | ESS HDY |  | SS27 | 15/10/2026 | 17/10/2026 |  |  | 1679 |  | 1679 |  |  | 2026-12-10 | 14/10/2026 |  |  | 1679 |  | 1679
ADIDAS | 0903481767-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 5210 | 15/10/2026 | 5210 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | ok |  | 800187 | EMBRO SUB PROCESS_V1 | 0903481767 KD9097 |  | KAHATEX CIJERAH | VIETNAM | SEA | 2026-09-10 | W BLANK TEE |  | SS27 | 2026-09-10 | 13/10/2026 |  |  | 5210 |  | 5210 |  |  | 2026-06-10 | 2026-09-10 |  |  | 5210 |  | 5210
ADIDAS | 0903482244-1 HK7309 | BLACK | 45D | F2225M402 | 480 | 15/10/2026 | 480 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482244 HK7309 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 480 |  | 480 |  |  | 2026-01-10 | 2026-03-10 |  |  | 480 |  | 480
ADIDAS | 0903482398-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482398 HK7311 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-10-10 | ESS HDY |  | SS27 | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920 |  |  | 2026-07-10 | 2026-08-10 |  |  | 920 |  | 920
ADIDAS | 0903482505-1 HK7309 | BLACK | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482505 HK7309 |  | KAHATEX CIJERAH | GERMANY | SEA | 2026-07-10 | ESS HDY |  | SS27 | 2026-07-10 | 2026-09-10 |  |  | 1680 |  | 1680 |  |  | 2026-03-10 | 2026-06-10 |  |  | 1680 |  | 1680
ADIDAS | 0903483394-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483394 HK7309 |  | KAHATEX CIJERAH | SPAIN | SEA | 2026-05-10 | ESS HDY |  | SS27 | 2026-05-10 | 2026-07-10 |  |  | 920 |  | 920 |  |  | 2026-01-10 | 2026-03-10 |  |  | 920 |  | 920
ADIDAS | 0903483669-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2000 | 15/10/2026 | 2000 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 28/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483669 IB8688 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 26/10/2026 | ESS HDY |  | SS27 | 26/10/2026 | 29/10/2026 |  |  | 2000 |  | 2000 |  |  | 22/10/2026 | 26/10/2026 |  |  | 2000 |  | 2000
ADIDAS | 0903483726-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1680 | 15/10/2026 | 1680 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483726 IB8688 |  | KAHATEX CIJERAH | GERMANY | SEA | 16/10/2026 | ESS HDY |  | SS27 | 16/10/2026 | 20/10/2026 |  |  | 1680 |  | 1680 |  |  | 13/10/2026 | 16/10/2026 |  |  | 1680 |  | 1680
ADIDAS | 0903484758-1 HK7309 | BLACK | 45D | F2225M402 | 2250 | 15/10/2026 | 2250 | SA | SA14/08/2026 | G1N | SWEATSHIRT | G1 | (15/09/2026) |  | 25/09: ex-fty. DRC 0002/T2 Capacity Long LT from Paiho (IDN), PI date: 25-Sep (DOL 19D). 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484758 HK7309 | 17/09/2026 | KAHATEX CIJERAH | SPAIN | SEA | 22/10/2026 | ESS HDY |  | SS27 | 22/10/2026 | 26/10/2026 |  |  | 2250 |  | 2250 |  |  | 19/10/2026 | 22/10/2026 |  |  | 2250 |  | 2250
ADIDAS | 0903484802-1 HK7311 | WONDER STEEL F22 | 45D | F2225M402 | 481 | 15/10/2026 | 481 | SA | SA14/08/2026 | G1A | SWEATSHIRT | G1 | (15/09/2026) |  | 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484802 HK7311 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 2026-12-10 | ESS HDY |  | SS27 | 2026-12-10 | 15/10/2026 |  |  | 481 |  | 481 |  |  | 2026-08-10 | 2026-12-10 |  |  | 481 |  | 481
ADIDAS | 0903484985-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1C | SWEATSHIRT | G1 | (15/09/2026) |  | 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484985 IB8688 |  | KAHATEX CIJERAH | SPAIN | SEA | 14/10/2026 | ESS HDY |  | SS27 | 14/10/2026 | 15/10/2026 |  |  | 920 |  | 920 |  |  | 2026-10-10 | 2026-12-10 |  |  | 920 |  | 920
ADIDAS | 0903485610-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 30/09/2026 | 100 | SI | SI14/08/2026 | G3E | SHORTS | G3 | ok |  | DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485610 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA | 22/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 22/09/2026 | 23/09/2026 |  |  | 100 |  | 100 |  |  | 18/09/2026 | 19/09/2026 |  |  | 100 |  | 100 |  |  | 15/09/2026 | 16/09/2026 |  |  | 100 |  | 100
ADIDAS | 0903486292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 243 | 30/10/2026 | 243 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903486292 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 27/10/2026 | 27/10/2026 |  |  | 243 |  | 243 |  |  | 24/10/2026 | 24/10/2026 |  |  | 243 |  | 243 |  |  | 23/10/2026 | 23/10/2026 |  |  | 243 |  | 243
ADIDAS | 0903486365-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 238 | 30/10/2026 | 238 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | ok |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903486365 IN1157 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/11/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 21/11/2026 | 23/11/2026 |  |  | 238 |  | 238 |  |  | 19/11/2026 | 19/11/2026 |  |  | 238 |  | 238 |  |  | 18/11/2026 | 18/11/2026 |  |  | 238 |  | 238
ADIDAS | 0903486405-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 136 | 30/10/2026 | 136 | ID | ID14/08/2026 | G1R | T-SHIRT | G1 | (11/09/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903486405 IN1157 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/11/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 21/11/2026 | 23/11/2026 |  |  | 136 |  | 136 |  |  | 19/11/2026 | 19/11/2026 |  |  | 136 |  | 136 |  |  | 18/11/2026 | 18/11/2026 |  |  | 136 |  | 136
ADIDAS | 0903486465-1 IS1413 | BLACK | 60D | S2425M405 | 1322 | 15/10/2026 | 1322 | SI | SI14/08/2026 | G2S | T-SHIRT | G2 | (15/09/2026) |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903486465 IS1413 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-06-10 | IN RANGE |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1322 |  | 1322 |  |  | 2026-02-10 | 2026-03-10 |  |  | 1322 |  | 1322
ADIDAS | 0903486480-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 138 | 30/10/2026 | 138 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903486480 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-06-10 | 2026-07-10 |  |  | 138 |  | 138 |  |  | 2026-03-10 | 2026-05-10 |  |  | 138 |  | 138 |  |  | 2026-02-10 | 2026-03-10 |  |  | 138 |  | 138
ADIDAS | 0903486515-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 428 | 30/10/2026 | 428 | ID | ID14/08/2026 | G1Q | T-SHIRT | G1 | (11/09/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903486515 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-06-11 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-06-11 | 2026-07-11 |  |  | 428 |  | 428 |  |  | 2026-04-11 | 2026-05-11 |  |  | 428 |  | 428 |  |  | 2026-03-11 | 2026-04-11 |  |  | 428 |  | 428
ADIDAS | 0903486554-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 207 | 15/09/2026 | 207 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 830009 | HT SUB PROCESS_V1 | 0903486554 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 207 | 207 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-08-09 | 14/09/2026 | 207 | 207 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-08-09 | 14/09/2026 | 207 | 207
ADIDAS | 0903486586-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 30/09/2026 | 106 | SA | SA14/08/2026 | G3E | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486586 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 106 |  | 106 |  |  | 21/09/2026 | 23/09/2026 |  |  | 106 |  | 106 |  |  | 17/09/2026 | 19/09/2026 | 17/09/2026 | 18/09/2026 | 106 | 50 | 56
ADIDAS | 0903486633-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 103 | 15/09/2026 | 103 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 15/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, PI Date 23-Oct, switch from order 0903443493). T2 Fu Hsun, PI Date 11-Sep, switch from order 903443493). 830009 | HT SUB PROCESS_V1 | 0903486633 IN1156 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 103 | 103 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 103 | 103 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 103 | 103
ADIDAS | 0903486753-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 2974 | 31/10/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486753 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486870-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1164 | 15/10/2026 | 1164 | SI | SI14/08/2026 | G3J | SHORTS | G3 | (11/09/2026) |  | IMPROVE. DRC 0084-T2 Y.R.C, Unfc material, PI Date 15-Aug, actual receives 16-Sep. T2 Grand tex, PI Date 11-Aug, actual receives 16-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486870 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX | 17/10/2026 | 21/10/2026 |  |  | 1164 |  | 1164 |  |  | 14/10/2026 | 17/10/2026 |  |  | 1164 |  | 1164 |  |  | 2026-10-10 | 14/10/2026 |  |  | 1164 |  | 1164
ADIDAS | 0903487218-1 HK7309 | BLACK | 45D | F2225M402 | 920 | 15/10/2026 | 920 | SA | SA14/08/2026 | G1L | SWEATSHIRT | G1 | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487218 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA | 2026-02-10 | ESS HDY |  | SS27 | 2026-02-10 | 2026-05-10 |  |  | 920 |  | 920 |  |  | 29/09/2026 | 2026-01-10 |  |  | 920 |  | 920
ADIDAS | 0903487925-1 JZ7709 | BLACK | 120D | S2608MR0201 | 249 | 30/09/2026 | 249 | SI | SI14/08/2026 | G3E | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487925 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 23/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 23/09/2026 | 24/09/2026 |  |  | 249 |  | 249 |  |  | 19/09/2026 | 21/09/2026 |  |  | 249 |  | 249 |  |  | 16/09/2026 | 17/09/2026 | 18/09/2026 | 19/09/2026 | 249 | 186 | 63 |  | 184
ADIDAS | 0903488008-1 JZ7709 | BLACK | 120D | S2608MR0201 | 706 | 30/09/2026 | 706 | SI | SI14/08/2026 | G3E | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488008 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 23/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 23/09/2026 | 24/09/2026 |  |  | 706 |  | 706 |  |  | 19/09/2026 | 21/09/2026 |  |  | 706 |  | 706 |  |  | 16/09/2026 | 17/09/2026 | 18/09/2026 | 19/09/2026 | 706 | 463 | 243 |  | 233
ADIDAS | 0903488538-1 JZ7711 | BLACK | 120D | S2608MR0202 | 690 | 30/09/2026 | 690 | SA | SA14/08/2026 | G3E | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488538 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA | 24/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 690 |  | 690 |  |  | 21/09/2026 | 23/09/2026 |  |  | 690 |  | 690 |  |  | 17/09/2026 | 19/09/2026 | 16/09/2026 | 18/09/2026 | 690 | 139 | 551
ADIDAS | 0903488669-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 221 | 30/10/2026 | 221 | ID | ID14/08/2026 | G1K | T-SHIRT | G1 | (11/09/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastern, Unfc material, PI Date 23-Oct. Waiting fabric.T2 Fu Hsun, PI Date 11-Sep, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903488669 IN1172 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 27/10/2026 | ADIZERO E TEE |  | SS27-YTI-SLT | 27/10/2026 | 27/10/2026 |  |  | 221 |  | 221 |  |  | 24/10/2026 | 24/10/2026 |  |  | 221 |  | 221 |  |  | 23/10/2026 | 23/10/2026 |  |  | 221 |  | 221
ADIDAS | 0903488735-1 JZ7709 | BLACK | 120D | S2608MR0201 | 101 | 30/09/2026 | 101 | SI | SI14/08/2026 | G3E | SHORTS | G3 | ok |  | DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 03-Sep. T2 Y.R.C, PI Date 14-Sep, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488735 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/09/2026 | ADI365/// SHO M BLACK |  | SS27-L2L | 22/09/2026 | 23/09/2026 |  |  | 101 |  | 101 |  |  | 18/09/2026 | 19/09/2026 |  |  | 101 |  | 101 |  |  | 15/09/2026 | 16/09/2026 |  |  | 101 |  | 101
ADIDAS | 0903489269-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 714 | 15/10/2026 | 714 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 848012 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903489269 KA5090 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 17/10/2026 | MINI EMB T |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 714 |  | 714 |  |  | 14/10/2026 | 15/10/2026 |  |  | 714 |  | 714 |  |  | 2026-12-10 | 13/10/2026 |  |  | 714 |  | 714
ADIDAS | 0903490564-1 JZ7711 | BLACK | 120D | S2608MR0202 | 241 | 30/09/2026 | 241 | SA | SA14/08/2026 | G3E | SHORTS | G3 | ok |  | 21/09: ex-fty. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep. T2 Far Eastern, PI Date 12-Oct, actual receives 03-Sep. 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490564 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA | 24/09/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 24/09/2026 | 26/09/2026 |  |  | 241 |  | 241 |  |  | 21/09/2026 | 23/09/2026 |  |  | 241 |  | 241 |  |  | 17/09/2026 | 19/09/2026 | 18/09/2026 | 18/09/2026 | 241 | 183 | 58
ADIDAS | 0903491252-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G2H | SWEATSHIRT | G2 | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903491252 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-03-11 | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS | 2026-03-11 | 2026-03-11 |  |  | 2 |  | 2 |  |  | 30/10/2026 | 30/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903491267-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 825054 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903491267 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 16/10/2026 | AMG SEL GFX T CREAM WHITE |  | SS27-MS | 16/10/2026 | 16/10/2026 |  |  | 2 |  | 2 |  |  | 13/10/2026 | 13/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903491589-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1017 | 31/10/2026 | 1017 | SI | SI14/08/2026 | G2E | T-SHIRT | G2 | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903491589 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 17/10/2026 | LA PALMS TEE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 1017 |  | 1017 |  |  | 14/10/2026 | 15/10/2026 |  |  | 1017 |  | 1017
ADIDAS | 0903492007-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 2604 | 15/10/2026 | 2604 | SI | SI14/08/2026 | G2M | T-SHIRT | G2 | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903492007 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-12-10 | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L | 2026-12-10 | 15/10/2026 |  |  | 2604 |  | 2604 |  |  | 2026-08-10 | 2026-12-10 |  |  | 2604 |  | 2604
ADIDAS | 0903492168-1 JM6500 | COLLEGIATE GREEN | 60D | F25SPRMGFX040 | 70 | 15/10/2026 | 70 | NT | NT14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 848012 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903492168 JM6500 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 20/10/2026 | M DDL SKATE T |  | SS27 | 20/10/2026 | 20/10/2026 |  |  | 70 |  | 70 |  |  | 16/10/2026 | 16/10/2026 |  |  | 70 |  | 70
ADIDAS | 0903492638-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 120 | 15/10/2026 | 120 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3+HT SUB PROCESS_V3 | 0903492638 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 120 |  | 120 |  |  | 20/10/2026 | 21/10/2026 |  |  | 120 |  | 120 |  |  | 19/10/2026 | 20/10/2026 |  |  | 120 |  | 120
ADIDAS | 0903492648-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1200 | 2026-12-09 | 1200 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 11/09: ex-fty 960026 | EMBRO SUB PROCESS_V1 | 0903492648 KX7410 | 2026-04-09 | KAHATEX CIJERAH | AUSTRALIA | SEA | 2026-08-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-08-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 1200 | 1200 |  |  |  | 2026-04-09 | 2026-08-09 | 2026-04-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903492683-1 KX7410 | OFF WHITE | 30D | F25ORIGFXBLANKM | 1352 | 15/09/2026 | 1352 | SI | SI14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903492683 KX7410 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE OFF WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-11-09 | 14/09/2026 | 1352 | 1352 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-05-09 | 2026-11-09 | 1352 | 1352
ADIDAS | 0903493699-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1299 | 15/10/2026 | 1299 | ID | ID14/08/2026 | G2N | T-SHIRT | G2 | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493699 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 15/10/2026 | SPORT GOODS T |  | SS27 | 15/10/2026 | 16/10/2026 |  |  | 1299 |  | 1299 |  |  | 2026-12-10 | 13/10/2026 |  |  | 1299 |  | 1299
ADIDAS | 0903493969-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 2 | 2026-07-10 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903493969 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-02-10 | MER GR NNHD M BLACK |  | SS27-MS | 2026-02-10 | 2026-02-10 |  |  | 2 |  | 2 |  |  | 29/09/2026 | 29/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903494009-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G2I | SWEATSHIRT | G2 | (10/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494009 LG8052 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 13/10/2026 | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS | 13/10/2026 | 14/10/2026 |  |  | 2 |  | 2 |  |  | 2026-09-10 | 2026-10-10 |  |  | 2 |  | 2
ADIDAS | 0903494023-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G1J | SWEATSHIRT | G1 | (15/10/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494023 LG8051 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-10-11 | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS | 2026-10-11 | 2026-10-11 |  |  | 2 |  | 2 |  |  | 2026-05-11 | 2026-05-11 |  |  | 2 |  | 2
ADIDAS | 0903494061-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 2 | 2026-07-10 | 2 | AN | AN14/08/2026 | G2F | T-SHIRT | G2 | (14/09/2026) |  | IMPROVE (AP Siti FU). DRC 0051/a.Insufficient LT Less than LT. 825054 | PRINT L1 SUB PROCESS_V3 | 0903494061 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 14/10/2026 | MER GR NNTEE M WHITE |  | SS27-MS | 14/10/2026 | 14/10/2026 |  |  | 2 |  | 2 |  |  | 2026-10-10 | 2026-10-10 |  |  | 2 |  | 2
ADIDAS | 0903494081-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 2 | 29/10/2026 | 2 | SI | SI14/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 825054 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903494081 LI5438 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 16/10/2026 | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS | 16/10/2026 | 16/10/2026 |  |  | 2 |  | 2 |  |  | 13/10/2026 | 13/10/2026 |  |  | 2 |  | 2
ADIDAS | 0903494139-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 2 | 29/10/2026 | 2 | SA | SA14/08/2026 | G1J | SWEATSHIRT | G1 | (15/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903494139 LJ4075 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA | 2026-10-11 | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS | 2026-10-11 | 2026-10-11 |  |  | 2 |  | 2 |  |  | 2026-05-11 | 2026-05-11 |  |  | 2 |  | 2
ADIDAS | 0903494327-1 LJ9158 | WHITE | 90D | 226205_JZSJ | 8582 | 15/10/2026 | 8582 | SA | SA14/08/2026 | G2M | T-SHIRT | G2 | (11/09/2026) |  | (NYK warehouse). 1st Art (TC 10 pcs) 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903494327 LJ9158 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 2026-05-10 | PSJ A JSY FAN WHITE |  | SS27-L2L | 2026-05-10 | 2026-12-10 |  |  | 8582 |  | 8582 |  |  | 2026-01-10 | 2026-08-10 |  |  | 8582 |  | 8582
ADIDAS | 0903494405-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 116 | 15/09/2026 | 116 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2 Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494405 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 116 | 116 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-05-09 | 2026-11-09 | 116 | 116 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-04-09 | 2026-11-09 | 116 | 116
ADIDAS | 0903494445-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 126 | 15/09/2026 | 126 | ID | ID14/08/2026 | G1M | T-SHIRT | G1 | ok |  | 14/09: ex-fty. IMPROVE. DRC 0064-T2 Far Eastern, using fabric stock. T2-Fu Hsun, using fabric stock. 814006 | HT SUB PROCESS_V1 | 0903494445 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA | 2026-04-09 | ADIZERO E TEE |  | SS27-YTI-SLT | 2026-04-09 | 15/09/2026 | 14/09/2026 | 14/09/2026 | 126 | 126 |  |  |  | 2026-02-09 | 2026-12-09 | 2026-12-09 | 14/09/2026 | 126 | 126 |  |  |  | 2026-01-09 | 2026-11-09 | 2026-11-09 | 14/09/2026 | 126 | 126
ADIDAS | 0903494678-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 100 | 15/10/2026 | 100 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 400147 | PRINT L3 SUB PROCESS_V3 | 0903494678 LE1858 | 30/09/2026 | KAHATEX CIJERAH | SWITZERLAND | SEA | 24/10/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 24/10/2026 | 24/10/2026 |  |  | 100 |  | 100 |  |  | 21/10/2026 | 21/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903495174-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 2 | 29/09/2026 | 2 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(24)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495174 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 21/09/2026 |  |  | 2 |  | 2 |  |  | 18/09/2026 | 19/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903495387-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 2 | 29/09/2026 | 2 | SI | SI14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(24)) |  | 825054 | PRINT L3+HT SUB PROCESS_V3 | 0903495387 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 21/09/2026 |  |  | 2 |  | 2 |  |  | 18/09/2026 | 19/09/2026 |  |  | 2 |  | 2
ADIDAS | 0903495400-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 2 | 29/09/2026 | 2 | ID | ID14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026(24)) |  | 825054 | PRINT L3 SUB PROCESS_V3 | 0903495400 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA | 23/09/2026 | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS | 23/09/2026 | 24/09/2026 |  |  | 2 |  | 2 |  |  | 19/09/2026 | 21/09/2026 | 15/09/2026 | 15/09/2026 | 2 | 2
ADIDAS | 0903496564-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 29 | 15/10/2026 | 29 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496564 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 29 |  | 29 |  |  | 17/10/2026 | 19/10/2026 |  |  | 29 |  | 29 |  |  | 16/10/2026 | 17/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496599-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 29 | 15/10/2026 | 29 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903496599 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 29 |  | 29 |  |  | 20/10/2026 | 21/10/2026 |  |  | 29 |  | 29 |  |  | 19/10/2026 | 20/10/2026 |  |  | 29 |  | 29
ADIDAS | 0903496637-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 517 | 15/10/2026 | 517 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903496637 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 517 |  | 517 |  |  | 17/10/2026 | 19/10/2026 |  |  | 517 |  | 517 |  |  | 16/10/2026 | 17/10/2026 |  |  | 517 |  | 517
ADIDAS | 0903497305-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 161 | 15/10/2026 | 161 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 600000 | PRINT L3+HT SUB PROCESS_V3 | 0903497305 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 161 |  | 161 |  |  | 20/10/2026 | 21/10/2026 |  |  | 161 |  | 161 |  |  | 19/10/2026 | 20/10/2026 |  |  | 161 |  | 161
ADIDAS | 0903497830-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 9287 | 15/10/2026 | 9287 | SA | SA14/08/2026 | G2N | T-SHIRT | G2 | (14/09/2026) |  | 600000 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903497830 KA5089 |  | KAHATEX CIJERAH | UNITED STATES | SEA | 2026-07-10 | MINI EMB T |  | SS27 | 2026-07-10 | 15/10/2026 |  |  | 9287 |  | 9287 |  |  | 2026-03-10 | 2026-12-10 |  |  | 9287 |  | 9287 |  |  | 2026-01-10 | 2026-09-10 |  |  | 9287 |  | 9287
ADIDAS | 0903500463-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 889 | 15/10/2026 | 889 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903500463 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 23/10/2026 |  |  | 889 |  | 889 |  |  | 19/10/2026 | 20/10/2026 |  |  | 889 |  | 889 |  |  | 17/10/2026 | 19/10/2026 |  |  | 889 |  | 889
ADIDAS | 0903501618-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 122 | 15/10/2026 | 122 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903501618 LE4570 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 122 |  | 122 |  |  | 20/10/2026 | 21/10/2026 |  |  | 122 |  | 122 |  |  | 19/10/2026 | 20/10/2026 |  |  | 122 |  | 122
ADIDAS | 0903502054-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 823 | 15/10/2026 | 823 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | (Mexico). 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903502054 LE4570 | 30/09/2026 | KAHATEX CIJERAH | MEXICO | SEA | 22/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 22/10/2026 | 23/10/2026 |  |  | 823 |  | 823 |  |  | 19/10/2026 | 20/10/2026 |  |  | 823 |  | 823 |  |  | 17/10/2026 | 19/10/2026 |  |  | 823 |  | 823
ADIDAS | 0903502085-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 166 | 15/10/2026 | 166 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 848012 | PRINT L3+HT SUB PROCESS_V3 | 0903502085 LE4570 | 30/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 166 |  | 166 |  |  | 20/10/2026 | 21/10/2026 |  |  | 166 |  | 166 |  |  | 19/10/2026 | 20/10/2026 |  |  | 166 |  | 166
ADIDAS | 0903502271-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 842 | 2026-12-09 | 842 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903502271 KC6386 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-09-09 | M BLANK TEE |  | SS27 | 2026-09-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 842 | 842 |  |  |  | 2026-05-09 | 2026-08-09 | 31/08/2026 | 16/09/2026 | 842 | 842
ADIDAS | 0903502599-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 324 | 15/10/2026 | 324 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903502599 KD9094 |  | KAHATEX CIJERAH | THAILAND | SEA | 17/10/2026 | M BLANK TEE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 324 |  | 324 |  |  | 14/10/2026 | 15/10/2026 |  |  | 324 |  | 324
ADIDAS | 0903503153-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 124 | 15/10/2026 | 124 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 1st Art (TC 10 pcs) 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503153 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 124 |  | 124 |  |  | 20/10/2026 | 21/10/2026 |  |  | 124 |  | 124 |  |  | 19/10/2026 | 20/10/2026 |  |  | 124 |  | 124
ADIDAS | 0903503177-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 204 | 15/10/2026 | 204 | SA | SA14/08/2026 | G1I | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503177 LE4570 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 23/10/2026 | AU TW PET JSY SIMPLE BROWN |  | SS27-MS | 23/10/2026 | 24/10/2026 |  |  | 204 |  | 204 |  |  | 20/10/2026 | 21/10/2026 |  |  | 204 |  | 204 |  |  | 19/10/2026 | 20/10/2026 |  |  | 204 |  | 204
ADIDAS | 0903503204-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 244 | 15/10/2026 | 244 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503204 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 244 |  | 244 |  |  | 17/10/2026 | 19/10/2026 |  |  | 244 |  | 244 |  |  | 16/10/2026 | 17/10/2026 |  |  | 244 |  | 244
ADIDAS | 0903503236-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 226 | 15/10/2026 | 226 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516333 | PRINT L3+HT SUB PROCESS_V3 | 0903503236 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | GERMANY | SEA | 22/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 22/10/2026 | 23/10/2026 |  |  | 226 |  | 226 |  |  | 19/10/2026 | 20/10/2026 |  |  | 226 |  | 226 |  |  | 17/10/2026 | 19/10/2026 |  |  | 226 |  | 226
ADIDAS | 0903503267-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 127 | 15/10/2026 | 127 | SI | SI14/08/2026 | G1L | ACCESSORIES | G1 | (15/10/2026) |  | 516443 | PRINT L3+HT SUB PROCESS_V3 | 0903503267 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | ITALY | SEA | 21/10/2026 | MER DNA PT JSY BLACK |  | SS27-MS | 21/10/2026 | 22/10/2026 |  |  | 127 |  | 127 |  |  | 17/10/2026 | 19/10/2026 |  |  | 127 |  | 127 |  |  | 16/10/2026 | 17/10/2026 |  |  | 127 |  | 127
ADIDAS | 0903503360-1 KD4066 | BLACK | 30D | F25ORIGFXBLANKM | 2004 | 15/09/2026 | 2004 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503360 KD4066 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-09-09 | M BLANK TEE BLACK |  | SS27 | 2026-09-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2004 | 2004 |  |  |  | 2026-05-09 | 2026-09-09 | 2026-01-09 | 2026-08-09 | 2004 | 2004
ADIDAS | 0903503397-1 KE3742 | WHITE | 30D | F25ORIGFXBLANKM | 2503 | 15/09/2026 | 2503 | SI | SI14/08/2026 | G2G,G2H | T-SHIRT | G2 | ok |  | 15/09: ex-fty (STOOD) 834012 | EMBRO SUB PROCESS_V1 | 0903503397 KE3742 | 2026-04-09 | KAHATEX CIJERAH | ISRAEL | SEA | 2026-11-09 | M BLANK TEE WHITE |  | SS27 | 2026-11-09 | 15/09/2026 | 2026-12-09 | 14/09/2026 | 2503 | 2503 |  |  |  | 2026-08-09 | 2026-11-09 | 2026-07-09 | 14/09/2026 | 2503 | 2503
ADIDAS | 0903503800-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 300 | 15/10/2026 | 300 | SA | SA14/08/2026 | G2G | T-SHIRT | G2 | (14/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903503800 KC6386 |  | KAHATEX CIJERAH | THAILAND | SEA | 17/10/2026 | M BLANK TEE |  | SS27 | 17/10/2026 | 19/10/2026 |  |  | 300 |  | 300 |  |  | 14/10/2026 | 15/10/2026 |  |  | 300 |  | 300
ADIDAS | 0903504690-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 1006 | 2026-12-09 | 1006 | SA | SA14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504690 KD9094 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | M BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-10-09 | 2026-12-09 | 1006 | 1006 |  |  |  | 2026-07-09 | 2026-09-09 | 2026-08-09 | 2026-12-09 | 1006 | 1006
ADIDAS | 0903504729-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 2022 | 2026-12-09 | 2022 | SI | SI14/08/2026 | G2H | T-SHIRT | G2 | ok |  | 12/09: ex-fty 830009 | EMBRO SUB PROCESS_V1 | 0903504729 KD9097 | 2026-04-09 | KAHATEX CIJERAH | PHILIPPINES | SEA | 2026-10-09 | W BLANK TEE |  | SS27 | 2026-10-09 | 2026-12-09 | 2026-11-09 | 2026-12-09 | 2022 | 2022 |  |  |  | 2026-07-09 | 2026-09-09 | 31/08/2026 | 2026-08-09 | 2022 | 2022
ADIDAS | 0903535974-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 804028 | PRINT L3 SUB PROCESS_V3 | 0903535974 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | JAPAN | AIR-COLLECT | 28/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 28/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 24/09/2026 | 25/09/2026 | 2026-11-09 | 17/09/2026 | 500 | 497 | 3
ADIDAS | 0903535975-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 500 | 30/09/2026 | 500 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). DRC 0064-other customer related delay reason. 960026 | PRINT L3 SUB PROCESS_V3 | 0903535975 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | AUSTRALIA | AIR-COLLECT | 29/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 29/09/2026 | 29/09/2026 |  |  | 500 |  | 500 |  |  | 25/09/2026 | 25/09/2026 | 2026-11-09 | 2026-11-09 | 500 | 500
ADIDAS | 0903545582-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 214 | 31/10/2026 | 214 | ID | ID28/08/2026 | G2K | T-SHIRT | G2 | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903545582 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI-SLT | 22/10/2026 | 23/10/2026 |  |  | 214 |  | 214 |  |  | 19/10/2026 | 20/10/2026 |  |  | 214 |  | 214 |  |  | 16/10/2026 | 17/10/2026 |  |  | 214 |  | 214
ADIDAS | 0903548414-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 141 | 30/09/2026 | 141 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | (06/08/2026) |  | 29/09: ex-fty 800005 | HT+PAD SUB PROCESS_V3 | 0903548414 KB5961 | 24/11/2026 | KAHATEX CIJERAH | INDONESIA | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 28/09/2026 | 28/09/2026 |  |  | 141 |  | 141 |  |  | 24/09/2026 | 24/09/2026 |  |  | 141 |  | 141 |  |  | 22/09/2026 | 22/09/2026 |  |  | 141 |  | 141
ADIDAS | 0903550837-1 JC8239 | WHITE/BLACK | 90D | S2554WES139SJ-SLT | 898 | 30/09/2026 | 898 | ID | ID28/08/2026 | G2G | T-SHIRT | G2 | ok |  | 24/09: ex-fty 516333 | PRINT L1 SUB PROCESS_V3 | 0903550837 JC8239 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-05-10 | W LIN SJ T |  | SS27-SLT | 2026-05-10 | 2026-05-10 |  |  | 898 |  | 898 |  |  | 2026-01-10 | 2026-01-10 | 14/09/2026 | 18/09/2026 | 898 | 898
ADIDAS | 0903553857-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 123 | 30/09/2026 | 123 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | ok |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553857 KB5965 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 25/09/2026 | 28/09/2026 |  |  | 123 |  | 123 |  |  | 22/09/2026 | 24/09/2026 |  |  | 123 |  | 123 |  |  | 19/09/2026 | 22/09/2026 |  |  | 123 |  | 123
ADIDAS | 0903553911-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 134 | 30/09/2026 | 134 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | (06/08/2026) |  | 25/09: ex-fty 800187 | HT+PAD SUB PROCESS_V3 | 0903553911 KB5961 | 24/11/2026 | KAHATEX CIJERAH | VIETNAM | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 28/09/2026 | 28/09/2026 |  |  | 134 |  | 134 |  |  | 24/09/2026 | 24/09/2026 |  |  | 134 |  | 134 |  |  | 22/09/2026 | 22/09/2026 |  |  | 134 |  | 134
ADIDAS | 0903554010-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 108 | 30/09/2026 | 108 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | ok |  | 25/09: ex-fty 814006 | HT+PAD SUB PROCESS_V3 | 0903554010 KB5965 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 25/09/2026 | 28/09/2026 |  |  | 108 |  | 108 |  |  | 22/09/2026 | 24/09/2026 |  |  | 108 |  | 108 |  |  | 19/09/2026 | 22/09/2026 |  |  | 108 |  | 108
ADIDAS | 0903556417-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 107 | 30/09/2026 | 107 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | (06/08/2026) |  | 24/09: ex-fty 830009 | HT+PAD SUB PROCESS_V3 | 0903556417 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 28/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 28/09/2026 | 28/09/2026 |  |  | 107 |  | 107 |  |  | 24/09/2026 | 24/09/2026 |  |  | 107 |  | 107 |  |  | 22/09/2026 | 22/09/2026 |  |  | 107 |  | 107
ADIDAS | 0903557215-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 19/09/2026 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 16/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 859013 | PRINT L3 SUB PROCESS_V3 | 0903557215 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | TAIWAN | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-10-09 | 2026-11-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-11-09 | 300 | 300
ADIDAS | 0903557229-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2 | 30/09/2026 | 2 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 16/09: ex-fty (CMA test) (By Air-Express). DRC 0064-other customer related delay reason. 825054 | PRINT L3 SUB PROCESS_V3 | 0903557229 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | AIR-EXPRESS | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 14/09/2026 | 14/09/2026 | 14/09/2026 | 2 | 2 |  |  |  | 2026-08-09 | 2026-10-09 | 2026-03-09 | 2026-03-09 | 2 | 2
ADIDAS | 0903557263-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2600 | 30/09/2026 | 2600 | SI | SI28/08/2026 | G2I,G2K,G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 18/09: ex-fty (China) (By Air-Collect). DRC 0064-other customer related delay reason. 825066 | PRINT L3 SUB PROCESS_V3 | 0903557263 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | CHINA | AIR-COLLECT | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 19/09/2026 | 2026-12-09 | 16/09/2026 | 2600 | 2600 |  |  |  | 2026-08-09 | 16/09/2026 | 2026-02-09 | 18/09/2026 | 2600 | 2600
ADIDAS | 0903562605-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 3578 | 31/10/2026 | 3578 | SA | SA28/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 652001 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903562605 JC5283 |  | KAHATEX CIJERAH | MEXICO | SEA | 20/10/2026 | M L SLIDE PKT T |  | SS27 | 20/10/2026 | 22/10/2026 |  |  | 3578 |  | 3578 |  |  | 16/10/2026 | 19/10/2026 |  |  | 3578 |  | 3578 |  |  | 14/10/2026 | 16/10/2026 |  |  | 3578 |  | 3578
ADIDAS | 0903565164-1 IS1413 | BLACK | 60D | S2425M405 | 1 | 31/10/2026 | 1 | SI | SI28/08/2026 | G2S | T-SHIRT | G2 | (26/09/2026) |  | 672027 | PRINT L3 SUB PROCESS_V3 | 0903565164 IS1413 |  | KAHATEX CIJERAH | BRAZIL | SEA | 2026-12-10 | IN RANGE |  | SS27 | 2026-12-10 | 2026-12-10 |  |  | 1 |  | 1 |  |  | 2026-08-10 | 2026-08-10 |  |  | 1 |  | 1
ADIDAS | 0903565505-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 1473 | 30/09/2026 | 1473 | ID | ID28/08/2026 | G2D | T-SHIRT | G2 | ok |  | 25/09: ex-fty 960026 | HT+PAD SUB PROCESS_V3 | 0903565505 KB5965 | 24/11/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA | 25/09/2026 | Run Ess Tee M |  | SS27-TI-SLT | 25/09/2026 | 28/09/2026 |  |  | 1473 |  | 1473 |  |  | 22/09/2026 | 24/09/2026 | 17/09/2026 | 19/09/2026 | 1473 | 1315 | 158 |  | 7 | 19/09/2026 | 22/09/2026 | 16/09/2026 | 18/09/2026 | 1473 | 1325 | 148
ADIDAS | 0903566115-1 HL2231 | LEGEND INK F17/WHITE | 45D | F224CSIM430 | 71 | 15/10/2026 | 71 | NT | NT28/08/2026 | G2M | PANTS | G2 | (02/10/2026) |  | 848012 | EMBRO+PPA SUB PROCESS_V3 | 0903566115 HL2231 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-05-10 | IN RANGE |  | SS27 | 2026-05-10 | 2026-05-10 |  |  | 71 |  | 71 |  |  | 2026-01-10 | 2026-01-10 |  |  | 71 |  | 71
ADIDAS | 0903569115-1 LK0714 | WONDER SAGE S26 | 90D | 226291_EFOA | 3335 | 21/10/2026 | 3335 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (12/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 12-Sep, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903569115 LK0714 | 2026-10-11 | KAHATEX CIJERAH | INDONESIA | SEA | 19/10/2026 | WF JRF 26 WONDER SAGE S26 |  | SS27-L2L-JRF | 19/10/2026 | 22/10/2026 |  |  | 3335 |  | 3335 |  |  | 16/10/2026 | 20/10/2026 |  |  | 3335 |  | 3335 |  |  | 15/10/2026 | 19/10/2026 |  |  | 3335 |  | 3335
ADIDAS | 0903577750-1 JC5283 | BLACK | 60D | S25SPRMGFX233 | 600 | 31/10/2026 | 600 | SA | SA28/08/2026 | G2L | T-SHIRT | G2 | (25/09/2026) |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903577750 JC5283 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | M L SLIDE PKT T |  | SS27 | 19/10/2026 | 20/10/2026 |  |  | 600 |  | 600 |  |  | 15/10/2026 | 16/10/2026 |  |  | 600 |  | 600 |  |  | 13/10/2026 | 14/10/2026 |  |  | 600 |  | 600
ADIDAS | 0903595003-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 4024 | 19/09/2026 | 4024 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(16)) |  | 17/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595003 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | AIR-COLLECT | 2026-11-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-11-09 | 16/09/2026 | 14/09/2026 | 16/09/2026 | 4024 | 4024 |  |  |  | 2026-08-09 | 2026-12-09 | 2026-03-09 | 2026-03-09 | 4024 | 4024
ADIDAS | 0903595010-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 5004 | 19/09/2026 | 5004 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 19/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595010 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 16/09/2026 | 2026-10-09 | 16/09/2026 | 5004 | 5004 |  |  |  | 2026-07-09 | 2026-12-09 | 2026-02-09 | 2026-02-09 | 5004 | 5004
ADIDAS | 0903595012-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 890 | 19/09/2026 | 890 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 19/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903595012 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 16/09/2026 | 2026-10-09 | 16/09/2026 | 890 | 890 |  |  |  | 2026-07-09 | 2026-12-09 | 2026-02-09 | 2026-11-09 | 890 | 890
ADIDAS | 0903595017-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 310 | 19/09/2026 | 310 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 17/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516343 | PRINT L3 SUB PROCESS_V3 | 0903595017 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 14/09/2026 | 2026-12-09 | 14/09/2026 | 310 | 310 |  |  |  | 2026-07-09 | 2026-10-09 | 2026-02-09 | 2026-04-09 | 310 | 310
ADIDAS | 0903595019-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 300 | 2026-12-09 | 300 | SI | SI28/08/2026 | G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 12/09: ex-fty (By Air-Collect). 806020 | PRINT L3 SUB PROCESS_V3 | 0903595019 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | HONGKONG | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 2026-11-09 | 2026-11-09 | 2026-12-09 | 300 | 300 |  |  |  | 2026-07-09 | 2026-08-09 | 2026-02-09 | 2026-12-09 | 300 | 300
ADIDAS | 0903597586-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 108 | 31/10/2026 | 108 | SA | SA10/07/2026 | G1B | SHORTS | G1 | (22/09/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903597586 KG8553 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA | 16/11/2026 | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX | 16/11/2026 | 17/11/2026 |  |  | 108 |  | 108 |  |  | 2026-11-11 | 2026-12-11 |  |  | 108 |  | 108 |  |  | 2026-06-11 | 2026-09-11 |  |  | 108 |  | 108
ADIDAS | 0903602357-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 700 | 30/09/2026 | 700 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 800005 | PRINT L3 SUB PROCESS_V3 | 0903602357 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | INDONESIA | AIR-COLLECT | 2026-07-10 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-07-10 | 2026-08-10 |  |  | 700 |  | 700 |  |  | 2026-03-10 | 2026-05-10 | 2026-10-09 | 17/09/2026 | 700 | 700
ADIDAS | 0903602358-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1400 | 30/09/2026 | 1400 | SI | SI08/09/2026 | G2F | T-SHIRT | G2 |  |  | (By Air-Collect). 839055 | PRINT L3 SUB PROCESS_V3 | 0903602358 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | SINGAPORE | AIR-COLLECT | 2026-08-10 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-08-10 | 2026-09-10 |  |  | 1400 |  | 1400 |  |  | 2026-05-10 | 2026-06-10 | 2026-10-09 | 17/09/2026 | 1400 | 1147 | 253
ADIDAS | 0903602359-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1880 | 30/09/2026 | 1880 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 814006 | PRINT L3 SUB PROCESS_V3 | 0903602359 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | THAILAND | AIR-COLLECT | 29/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 29/09/2026 | 30/09/2026 |  |  | 1880 |  | 1880 |  |  | 25/09/2026 | 26/09/2026 | 2026-10-09 | 17/09/2026 | 1880 | 1861 | 19
ADIDAS | 0903602360-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2100 | 30/09/2026 | 2100 | SI | SI08/09/2026 | G2K | T-SHIRT | G2 |  |  | (By Air-Collect). 838103 | PRINT L3 SUB PROCESS_V3 | 0903602360 LZ9161 | 2026-07-11 | KAHATEX CIJERAH | MALAYSIA | AIR-COLLECT | 30/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 30/09/2026 | 2026-02-10 |  |  | 2100 |  | 2100 |  |  | 26/09/2026 | 29/09/2026 | 2026-10-09 | 17/09/2026 | 2100 | 2096 | 4
ADIDAS | 0903602828-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1200 | 23/09/2026 | 1200 | SI | SI07/09/2026 | G2K | T-SHIRT | G2 |  |  | 21/09: ex-fty (By Air-Collect). DRC 0064-other customer related delay reason. 600000 | PRINT L3 SUB PROCESS_V3 | 0903602828 LZ9161 | 18/11/2026 | KAHATEX CIJERAH | UNITED STATES | AIR-COLLECT | 26/09/2026 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 26/09/2026 | 28/09/2026 |  |  | 1200 |  | 1200 |  |  | 23/09/2026 | 24/09/2026 | 2026-11-09 | 2026-11-09 | 1200 | 1200
ADIDAS | 0903603199-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 221 | 19/09/2026 | 221 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 19/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603199 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 16/09/2026 | 2026-11-09 | 16/09/2026 | 221 | 221 |  |  |  | 2026-07-09 | 2026-12-09 | 2026-02-09 | 2026-05-09 | 221 | 221
ADIDAS | 0903603200-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 484 | 19/09/2026 | 484 | SI | SI28/08/2026 | G2I,G2N | T-SHIRT | G2 | (25/09/2026(17)) |  | 19/09: ex-fty (By Air-Collect). DRC 0047-hold shipment customer. 516333 | PRINT L3 SUB PROCESS_V3 | 0903603200 LZ9161 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | AIR-COLLECT | 2026-10-09 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | 2026-10-09 | 16/09/2026 | 2026-12-09 | 16/09/2026 | 484 | 484 |  |  |  | 2026-07-09 | 2026-12-09 | 2026-03-09 | 2026-03-09 | 484 | 484
ADIDAS | 0903610424-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 101 | 31/10/2026 | 101 | ID | ID11/09/2026 | G2I | T-SHIRT | G2 |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610424 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 24/10/2026 | Run Ess Tee M |  | SS27-TI | 24/10/2026 | 26/10/2026 |  |  | 101 |  | 101 |  |  | 21/10/2026 | 22/10/2026 |  |  | 101 |  | 101 |  |  | 19/10/2026 | 20/10/2026 |  |  | 101 |  | 101
ADIDAS | 0903610478-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 100 | 31/10/2026 | 100 | ID | ID11/09/2026 | G2K | T-SHIRT | G2 |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610478 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 |  |  | 100 |  | 100 |  |  | 16/10/2026 | 17/10/2026 |  |  | 100 |  | 100
ADIDAS | 0903613711-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 345 | 15/10/2026 | 345 | ID | ID11/09/2026 | G2F | T-SHIRT | G2 |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903613711 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA | 19/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 19/10/2026 | 19/10/2026 |  |  | 345 |  | 345 |  |  | 15/10/2026 | 15/10/2026 |  |  | 345 |  | 345 |  |  | 13/10/2026 | 13/10/2026 |  |  | 345 |  | 345
ADIDAS | 4501769841-6 IS4418 | PRELOVED INK S24/IVORY S24 | 60D | S2315KSWU253 | 383 | 2026-05-09 | 383 | AN | AN13/03/2026 | G2Q | SHORTS | G2 | ok | (04/04/2026) | 04/09: ex-fty ZA30 | PRINT L3 SUB PROCESS_V3 | 4501769841 IS4418 | 2026-08-05 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 27/07/2026 | IN RANGE |  | FW26 | 27/07/2026 | 2026-03-08 | 29/07/2026 | 2026-03-08 | 383 | 383 |  |  |  | 22/07/2026 | 29/07/2026 | 2026-08-07 | 27/07/2026 | 383 | 383
ADIDAS | 4501928489-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 444 | 31/10/2026 | 444 | SA | SA29/05/2026 | G2K | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501928489 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 19/10/2026 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 444 |  | 444 |  |  | 15/10/2026 | 16/10/2026 | 18/09/2026 | 18/09/2026 | 444 | 328 | 116 |  |  | 13/10/2026 | 14/10/2026 | 17/09/2026 | 18/09/2026 | 444 | 329 | 115
ADIDAS | 4501928501-1 LG9669 | BLACK | 120D | S2754WAS514C | 189 | 14/10/2026 | 189 | ID | ID29/05/2026 | G3C | SKIRT | G3 | ok | (22/06/2026) | T2 Teijin Nantong, PI Date 15-Jul, actual receives 24-Aug. ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928501 LG9669 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | W SL WV SK BLACK |  | SS27 | 2026-08-10 | 2026-09-10 |  |  | 189 |  | 189 |  |  | 2026-05-10 | 2026-06-10 |  |  | 189 |  | 189
ADIDAS | 4501929295-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 160 | 14/10/2026 | 160 | SA | SA29/05/2026 | G2P | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929295 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 28/09/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 28/09/2026 | 29/09/2026 |  |  | 160 |  | 160 |  |  | 24/09/2026 | 25/09/2026 |  |  | 160 |  | 160 |  |  | 22/09/2026 | 23/09/2026 |  |  | 160 |  | 160
ADIDAS | 4501929321-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 582 | 14/10/2026 | 582 | SA | SA29/05/2026 | G2I | T-SHIRT | G2 | ok | (22/06/2026) | ZA30 | HT+PAD SUB PROCESS_V3 | 4501929321 KX3651 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-07-10 | Run Ess Tee M LIME TINT S27 |  | SS27-TI | 2026-07-10 | 2026-08-10 |  |  | 582 |  | 582 |  |  | 2026-03-10 | 2026-05-10 | 17/09/2026 | 17/09/2026 | 582 | 483 | 99 |  |  | 2026-01-10 | 2026-02-10 | 17/09/2026 | 19/09/2026 | 582 | 488 | 94 |  | 5
ADIDAS | 4502065732-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 671 | 14/10/2026 | 671 | SA | SA26/06/2026 | G1G | JACKET | G1 | (16/08/2026) | (04/08/2026) | T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. T2 Libolon, PI Date 23-Jul, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS | 2026-08-10 | 13/10/2026 |  |  | 671 |  | 671 |  |  | 2026-05-10 | 2026-09-10 |  |  | 671 |  | 671
ADIDAS | 4502066600-1 LF0727 | BLACK | 120D | S2754MAS510B | 181 | 31/10/2026 | 181 | SI | SI26/06/2026 | G1K | JACKET | G1 | ok | ok | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502066600 LF0727 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-03-11 | M SL WV TT BLACK |  | SS27 | 2026-03-11 | 2026-05-11 |  |  | 181 |  | 181 |  |  | 30/10/2026 | 2026-02-11 |  |  | 181 |  | 181
ADIDAS | 4502066601-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1481 | 21/10/2026 | 1481 | SI | SI26/06/2026 | G1P | T-SHIRT | G1 | (08/08/2026) | ok | ZA30 | EMBRO SUB PROCESS_V1 | 4502066601 KD3911 |  | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-11 | RELEASED |  | SS27 | 2026-06-11 | 2026-09-11 |  |  | 1481 |  | 1481 |  |  | 2026-03-11 | 2026-04-11 |  |  | 1481 |  | 1481
ADIDAS | 4502066684-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 100 | 31/10/2026 | 100 | SA | SA26/06/2026 | G2K | T-SHIRT | G2 | ok | ok | T2 Fu Hsun, PI Date 30-Jul, actual receives 01-Sep (switch from PO 26030472). ZA30 | HT+PAD SUB PROCESS_V3 | 4502066684 KB5961 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 22/10/2026 | Run Ess Tee M |  | SS27-TI | 22/10/2026 | 23/10/2026 |  |  | 100 |  | 100 |  |  | 19/10/2026 | 20/10/2026 | 19/09/2026 | 19/09/2026 | 100 | 94 | 6 |  | 94 | 16/10/2026 | 17/10/2026 | 18/09/2026 | 18/09/2026 | 100 | 94 | 6
ADIDAS | 4502066806-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 959 | 21/10/2026 | 959 | AT | AT26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | ZA30 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 4502066806 KA5090 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 22/10/2026 | MINI EMB T |  | SS27 | 22/10/2026 | 23/10/2026 |  |  | 959 |  | 959 |  |  | 19/10/2026 | 20/10/2026 |  |  | 959 |  | 959 |  |  | 16/10/2026 | 17/10/2026 | 2026-02-09 | 19/09/2026 | 959 | 748 | 211 |  | 27
ADIDAS | 4502066844-1 KB5965 | BLACK | 120D | S2608MR0900A | 300 | 31/10/2026 | 300 | SA | SA26/06/2026 | G2H | T-SHIRT | G2 | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 19/10/2026 | Run Ess Tee M |  | SS27-TI | 19/10/2026 | 20/10/2026 |  |  | 300 |  | 300 |  |  | 15/10/2026 | 16/10/2026 |  |  | 300 |  | 300 |  |  | 13/10/2026 | 14/10/2026 |  |  | 300 |  | 300
ADIDAS | 4502066871-1 KE8424 | BLACK | 120D | S2608MR0906A | 164 | 31/10/2026 | 164 | SI | SI26/06/2026 | G2N | T-SHIRT | G2 | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 28/10/2026 | Run Ess LS M BLACK |  | SS27-TI | 28/10/2026 | 30/10/2026 |  |  | 164 |  | 164 |  |  | 24/10/2026 | 27/10/2026 |  |  | 164 |  | 164 |  |  | 22/10/2026 | 24/10/2026 |  |  | 164 |  | 164
ADIDAS | 4502066873-1 KB5960 | WHITE | 120D | S2608MR0900A | 756 | 31/10/2026 | 756 | SA | SA26/06/2026 | G2I | T-SHIRT | G2 | ok | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 27/10/2026 | Run Ess Tee M |  | SS27-TI | 27/10/2026 | 28/10/2026 |  |  | 756 |  | 756 |  |  | 23/10/2026 | 24/10/2026 |  |  | 756 |  | 756 |  |  | 21/10/2026 | 22/10/2026 |  |  | 756 |  | 756
ADIDAS | 4502070409-1 LF0718 | BLACK | 105D | S2754MAS512B | 140 | 14/10/2026 | 140 | SA | SA26/06/2026 | G3B | PANTS | G3 | ok | (04/08/2026) | T2 Teijin Nantong, material quality issues (moir膿), PI Date 18-Aug, actual receives 24-Aug. T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | M SL WV OH PT BLACK |  | SS27 | 2026-06-10 | 2026-08-10 |  |  | 140 |  | 140 |  |  | 2026-02-10 | 2026-05-10 |  |  | 140 |  | 140
ADIDAS | 4502075077-1 IN1173 | WHITE | 90D | S2408WR1600 | 190 | 2026-07-10 | 190 | SI | SI30/06/2026 | G1M | T-SHIRT | G1 | (10/07/2026) | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 01-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075077 IN1173 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | ADIZERO E TEE |  | SS27-YTI | 2026-08-10 | 2026-09-10 |  |  | 190 |  | 190 |  |  | 2026-06-10 | 2026-07-10 | 2026-11-08 | 26/08/2026 | 190 | 190 |  |  |  | 2026-05-10 | 2026-06-10 | 2026-08-08 | 22/08/2026 | 190 | 190
ADIDAS | 4502075081-1 KA0246 | BLACK | 90D | S2608WR0902 | 961 | 14/10/2026 | 961 | SI | SI30/06/2026 | G2O | SHORTS | G2 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? T2 Grand tex, PI Date 30-Jul, actual receives 28-Aug. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075081 KA0246 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | Run Ess 21 S BLACK |  | SS27-TRAX | 2026-06-10 | 2026-07-10 |  |  | 961 |  | 961 |  |  | 2026-02-10 | 2026-03-10 |  |  | 961 |  | 961 |  |  | 29/09/2026 | 30/09/2026 |  |  | 961 |  | 961
ADIDAS | 4502075922-1 KT4840 | ONIX | 90D | S2408MR1600 | 100 | 14/10/2026 | 100 | SA | SA30/06/2026 | G1M | T-SHIRT | G1 | ok | ok | T2 Y.T.I, body & mesh actual receives 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075922 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/10/2026 | ADIZERO E TEE |  | SS27-YTI | 15/10/2026 | 16/10/2026 |  |  | 100 |  | 100 |  |  | 13/10/2026 | 14/10/2026 | 19/09/2026 | 19/09/2026 | 100 | 69 | 31 |  | 69 | 2026-12-10 | 13/10/2026 | 19/09/2026 | 19/09/2026 | 100 | 72 | 28 |  | 72
ADIDAS | 4502075923-1 IN1156 | BLACK | 90D | S2408MR1600 | 413 | 2026-07-10 | 413 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. 1st Art (TC 10 pcs) ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-06-10 | ADIZERO E TEE |  | SS27-YTI | 2026-06-10 | 2026-07-10 |  |  | 413 |  | 413 |  |  | 2026-03-10 | 2026-05-10 | 26/08/2026 | 2026-12-09 | 413 | 413 |  |  |  | 2026-02-10 | 2026-03-10 | 18/08/2026 | 2026-05-09 | 413 | 413
ADIDAS | 4502075923-2 IN1156 | BLACK | 90D | S2408MR1600 | 100 | 31/10/2026 | 100 | SA | SA30/06/2026 | G1Q | T-SHIRT | G1 | (10/07/2026) |  | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075923 IN1156 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-11-11 | ADIZERO E TEE |  | SS27-YTI | 2026-11-11 | 2026-12-11 |  |  | 100 |  | 100 |  |  | 2026-09-11 | 2026-10-11 |  |  | 100 |  | 100 |  |  | 2026-06-11 | 2026-09-11 |  |  | 100 |  | 100
ADIDAS | 4502075924-1 IN1172 | BLACK | 90D | S2408WR1600 | 212 | 2026-07-10 | 212 | SI | SI30/06/2026 | G1K | T-SHIRT | G1 | ok | ok | 30/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075924 IN1172 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-02-10 | ADIZERO E TEE |  | SS27-YTI | 2026-02-10 | 2026-03-10 |  |  | 212 |  | 212 |  |  | 30/09/2026 | 2026-01-10 | 27/08/2026 | 2026-04-09 | 212 | 212 |  |  |  | 29/09/2026 | 30/09/2026 | 27/08/2026 | 2026-04-09 | 212 | 212
ADIDAS | 4502075929-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 326 | 31/10/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 1st Art (TC 10 pcs) ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075929 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502075931-1 LD0292 | SILVER BLUE S27 | 90D | S2608WR0901 | 179 | 14/10/2026 | 179 | SI | SI30/06/2026 | G1A | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Fu Hsun, PI Date 03-Aug, actual receives 09-Sep. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075931 LD0292 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-03-10 | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX | 2026-03-10 | 2026-06-10 |  |  | 179 |  | 179 |  |  | 30/09/2026 | 2026-02-10 |  |  | 179 |  | 179 |  |  | 29/09/2026 | 2026-01-10 |  |  | 179 |  | 179
ADIDAS | 4502075932-1 KA0235 | BLACK | 90D | S2608WR0901 | 971 | 14/10/2026 | 971 | SI | SI30/06/2026 | G1E | SHORTS | G1 | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? T2 Grand Tex, PI Date 16-Aug, actual receives 11-Sep. T2 Grand Tex, PI Date 16-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502075932 KA0235 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 22/10/2026 | Run Ess Shor W BLACK |  | SS27-TRAX | 22/10/2026 | 26/10/2026 |  |  | 971 |  | 971 |  |  | 19/10/2026 | 22/10/2026 |  |  | 971 |  | 971 |  |  | 17/10/2026 | 21/10/2026 |  |  | 971 |  | 971
ADIDAS | 4502076908-1 KA4331 | BLACK | 90D | S2608MR0902 | 1102 | 14/10/2026 | 1102 | SA | SA03/07/2026 | G1C | SHORTS | G1 | (26/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? T2 Grand tex, PI Date 15-Aug, actual receives 26-Aug. ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-08-10 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-08-10 | 2026-09-10 |  |  | 1102 |  | 1102 |  |  | 2026-05-10 | 2026-06-10 |  |  | 1102 |  | 1102 |  |  | 2026-03-10 | 2026-05-10 |  |  | 1102 |  | 1102
ADIDAS | 4502076908-2 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 21/10/2026 | 100 | SA | SA03/07/2026 | G1B | SHORTS | G1 | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502076908 KA4331 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-12-11 | Run Ess 21 S M BLACK |  | SS27-TRAX | 2026-12-11 | 13/11/2026 |  |  | 100 |  | 100 |  |  | 2026-09-11 | 2026-10-11 |  |  | 100 |  | 100 |  |  | 2026-06-11 | 2026-09-11 |  |  | 100 |  | 100
ADIDAS | 4502077517-1 IN1172 | BLACK | 90D | S2408WR1600 | 292 | 30/09/2026 | 292 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 29/09: ex-fty. T2 Y.T.I, body & mesh actual receives 07-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077517 IN1172 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 19/09/2026 | ADIZERO E TEE |  | SS27-YTI | 19/09/2026 | 21/09/2026 | 19/09/2026 | 19/09/2026 | 292 | 96 | 196 |  | 96 | 17/09/2026 | 18/09/2026 | 27/08/2026 | 2026-10-09 | 292 | 292 |  |  |  | 16/09/2026 | 17/09/2026 | 24/08/2026 | 2026-09-09 | 292 | 292
ADIDAS | 4502077518-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 30/09/2026 | 167 | SA | SA07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502077518 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 24/09/2026 | ADIZERO E TEE |  | SS27-YTI | 24/09/2026 | 24/09/2026 |  |  | 167 |  | 167 |  |  | 22/09/2026 | 22/09/2026 | 24/08/2026 | 2026-07-09 | 167 | 167 |  |  |  | 21/09/2026 | 21/09/2026 | 22/08/2026 | 2026-05-09 | 167 | 167
ADIDAS | 4502077519-1 IN1157 | WHITE | 90D | S2408MR1600 | 706 | 30/09/2026 | 706 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & mesh actual receives 06-Aug. ZA30 | HT SUB PROCESS_V1 | 4502077519 IN1157 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 18/09/2026 | ADIZERO E TEE |  | SS27-YTI | 18/09/2026 | 21/09/2026 | 18/09/2026 | 19/09/2026 | 706 | 675 | 31 |  | 341 | 16/09/2026 | 18/09/2026 | 2026-09-09 | 2026-11-09 | 706 | 703 | 3 |  |  | 15/09/2026 | 17/09/2026 | 2026-02-09 | 2026-10-09 | 706 | 703 | 3
ADIDAS | 4502080370-1 IN1156 | BLACK | 90D | S2408MR1600 | 527 | 30/09/2026 | 527 | SA | SA07/07/2026 | G1M | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, actual receives 07-Aug. T2 Fu Hsun, PI Date 03-Aug, actual receives 07-Aug (using fabric from Y.T.I.). ZA30 | HT SUB PROCESS_V1 | 4502080370 IN1156 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 15/09/2026 | ADIZERO E TEE |  | SS27-YTI | 15/09/2026 | 21/09/2026 | 15/09/2026 | 18/09/2026 | 527 | 525 | 2 |  |  | 2026-12-09 | 18/09/2026 | 26/08/2026 | 2026-10-09 | 527 | 527 |  |  |  | 2026-11-09 | 17/09/2026 | 24/08/2026 | 2026-09-09 | 527 | 527
ADIDAS | 4502080372-1 IN1173 | WHITE | 90D | S2408WR1600 | 109 | 30/09/2026 | 109 | SI | SI07/07/2026 | G1E | T-SHIRT | G1 | ok | ok | 25/09: ex-fty. T2 Y.T.I, Body & Mesh actual receives 03-Aug. ZA30 | HT SUB PROCESS_V1 | 4502080372 IN1173 | 21/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 19/09/2026 | ADIZERO E TEE |  | SS27-YTI | 19/09/2026 | 21/09/2026 |  |  | 109 |  | 109 |  |  | 17/09/2026 | 18/09/2026 | 2026-12-08 | 21/08/2026 | 109 | 109 |  |  |  | 16/09/2026 | 17/09/2026 | 2026-11-08 | 20/08/2026 | 109 | 109
ADIDAS | 4502347774-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 800 | 15/09/2026 | 800 | SI | SI10/07/2026 | G2P | T-SHIRT | G2 | ok | ok | 15/09: ex-fty. DRC 0090-early shipment customer (no need open ticket). ZA30 | PRINT L3+PAD SUB PROCESS_V3 | 4502347774 KA0546 | 26/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA | 2026-01-09 | J FOOTBALL T |  | SS27 | 2026-01-09 | 2026-12-09 | 2026-02-09 | 2026-10-09 | 800 | 800 |  |  |  | 28/08/2026 | 2026-09-09 | 14/08/2026 | 2026-09-09 | 800 | 800
ADIDAS | 46075347-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 1622 | 30/09/2026 | 1622 | SI | SI22/08/2026 | G2F | T-SHIRT | G2 |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 46075347 LZ9161 | 2026-04-11 | KAHATEX CIJERAH | SINGAPORE | SEA | 2026-06-10 | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27 | 2026-06-10 | 2026-07-10 |  |  | 1622 |  | 1622 |  |  | 2026-02-10 | 2026-03-10 | 29/08/2026 | 17/09/2026 | 1622 | 1622
ADIDAS | OFC-07092026-002 | MULTI COLOR | 45D | F213CSIM105FL | 12295 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-002 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-003 | MULTI COLOR | 45D | F213CSIM109FL | 6 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-003 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-012 | MULTI COLOR | 45D | F2225M402 | 991 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-012 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-020 | MULTI COLOR | 45D | F224CSIM430 | 10836 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-020 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-032 | MULTI COLOR | 45D | F24KLKGFX003 | 268 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-032 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-048 | MULTI COLOR | 60D | F25KLKGFX011 | 801 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-048 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1134 | MULTI COLOR | 60D | S27FBGFXP510 | 5 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1134 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-142 | MULTI COLOR | 90D | F2625M101 | 232 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-303 | MULTI COLOR | 60D | PH_F_SWK_A | 204 | 31/10/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-303 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-427 | MULTI COLOR | 45D | S211CSIM117FLRO | 6 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-427 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-430 | MULTI COLOR | 45D | S211CSIW114SJ | 215 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PAD SUB PROCESS_V3 | OFC-07092026-430 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-443 | MULTI COLOR | 60D | S2315KSWU253 | 723 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-443 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-522 | MULTI COLOR | 60D | S2525M200 | 1 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-522 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-535 | MULTI COLOR | 90D | S2554MESS605FT | 18 | 31/10/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-535 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-592 | MULTI COLOR | 60D | S25ORISW311 | 1 | 31/10/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | OFC-07092026-592 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-769 | MULTI COLOR | 90D | S2625M018 | 135 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-769 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-774 | MULTI COLOR | 90D | S2625M036 | 330 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-774 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-848 | MULTI COLOR | 60D | S26KJUGFX009 | 357 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-848 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-856 | MULTI COLOR | 60D | S26SPRWGFX004 | 4 | 31/10/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | OFC-07092026-856 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
Total |  |  |  |  | 2372593 |  | 2238214 | [22 empty] | 2238214 | 677070 | 1561144 |  | 23187 |  |  |  |  | 2238214 | 922234 | 1315980 | 35 | 26800 |  |  |  |  | 731906 | 207545 | 524361 |  | 9443