## Sheet1
JO Tracking Report
Factory: | KAHATEX CIJERAH | Floor | G1,G2,G3,G4,G5,SPL | JO: |  | Style No: |  | Delivery Date: | 01/11/2026 - 15/12/2026 | JO Status: | Uncompleted, Completed, Export | Printed by: | REYNALDI | Print time: | 22/09/2026 11:36:55
Customer Name | Order No. | Color | Lot No | Factory Style | Qty | Delivery Date | Plan Qty | Merchaniser | PO.NO | Line | Product Type | Floor | Fabrics | Auxiliary | JO Remarks | Process Route Name | Cust_Order_No | Pre-production event finish date | Factory | Ship To | Ship Mode | Sewing Start | Style Description | Plan Remarks | Season | SEWING | [8 empty] | COMPLETE ASSEMBLY | [8 empty] | HEAT TRANSFER
[26 empty] | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output | schedule start date | Schedule end date | Actual go live time | Actual completed time | Plan qty | Qty. | Non-finished Qty | Extra Amount | Last daily output
ADIDAS | 0902859677-1 JZ7808 | BLACK | 60D | S2608WR0900 | 364 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902859677 JZ7808 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862146-1 JZ7808 | BLACK | 60D | S2608WR0900 | 332 | 23/11/2026 |  | AT | AT24/04/2026 |  | T-SHIRT |  | ok | (14/05/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902862146 JZ7808 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W |  | FW26
ADIDAS | 0902862401-1 LD5435 | OLIVE FOUR S27/OFF WHITE | 105D | F2654MESS608WVB | 425 | 2026-07-12 |  | SI | SI24/04/2026 |  | SHORTS |  | ok | (04/06/2026) | T2 Formosa, material quality issues (shading), PI Date 07-Jun, actual receives 03-Jul. T2 Kahatex, PI Date 10-Jun, actual receives 29-May. T2 Gistex, material quality issues (shading), PI Date 07-Jun, actual receives 01-Jul (FOC 327yd). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902862401 LD5435 | 28/07/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 OLIVE FOUR S27/OFF WHITE |  | SS27
ADIDAS | 0902887722-1 KD0677 | DARK BLUE/WHITE | 90D | S2650MTR434 | 329 | 2026-07-11 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 516443 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887722 KD0677 | 22/07/2026 | KAHATEX CIJERAH | ITALY | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902887725-1 KA3521 | BLACK/WHITE | 90D | S2650MTR434 | 759 | 30/11/2026 |  | SI | SI05/05/2026 |  | SHORTS |  | ok | ok | T2 Libolon, using fabric stock. 600000 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0902887725 KA3521 | 22/07/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | WE BAS 3SWV SH |  | FW26
ADIDAS | 0902900852-1 LD0930 | TEAM NAVY BLUE 2 | 120D | S2608MR0906A | 312 | 30/11/2026 |  | SI | SI15/05/2026 |  | T-SHIRT |  | (13/07/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0902900852 LD0930 | 14/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902901036-1 JZ7808 | BLACK | 120D | S2608WR0900 | 483 | 2026-07-11 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | ok | 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0902901036 JZ7808 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902902915-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 306 | 2026-07-11 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | (08/06/2026) | 516342 | HT+PAD SUB PROCESS_V3 | 0902902915 KX3655 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0902904621-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 315 | 2026-07-12 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902904621 LD0283 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902905709-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 322 | 2026-07-12 |  | SA | SA15/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902905709 LD0285 | 14/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902930249-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 563 | 2026-07-11 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930249 KX3713 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930252-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 342 | 23/11/2026 |  | SI | SI21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902930252 KX3713 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0902930257-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 483 | 2026-07-12 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902930257 LD0283 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902930261-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 326 | 2026-07-12 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930261 LD0283 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902930263-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 334 | 2026-07-11 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902930263 LD0283 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902931103-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 483 | 2026-07-12 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0902931103 LD0285 | 21/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902931104-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 335 | 2026-07-11 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902931104 LD0285 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902931105-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 324 | 2026-07-12 |  | SA | SA21/05/2026 |  | T-SHIRT |  | ok | ok | 516342 | HT+PAD SUB PROCESS_V3 | 0902931105 LD0285 | 21/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0902933084-1 KZ3204 | WHITE/BLACK | 90D | S2754WESS422WV | 429 | 2026-07-12 |  | SI | SI15/05/2026 |  | JACKET |  | ok |  | T2 Formosa, PI Date 10-Jul, actual receives 16-Jul. T2 Libolon, PI Date 06-Jul, actual receives 14-Jul. T2 Kahatex, PI Date 13-Jun, actual receives 30-May.. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902933084 KZ3204 | 31/07/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER WHITE/BLACK |  | SS27
ADIDAS | 0902954134-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 322 | 2026-07-11 |  | SA | SA29/05/2026 |  | JACKET |  | (15/07/2026) | (24/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual recieves 25-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954134 LG9664 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0902954770-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 453 | 2026-07-11 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954770 LE8186 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0902954935-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 340 | 2026-07-11 |  | SI | SI29/05/2026 |  | PANTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 24-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902954935 LE8188 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0902956034-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 355 | 2026-07-11 |  | SI | SI29/05/2026 |  | SHORTS |  | (28/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? T2 Kahatex, PI date 28-Jul, actual receives 23-Jun. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956034 LD5446 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0902956935-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 370 | 2026-07-11 |  | AN | AN29/05/2026 |  | JACKET |  | (29/06/2026) | (19/06/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Jun, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 20-Jun, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0902956935 LG9666 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0902957063-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 696 | 2026-07-12 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902957063 LG9674 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0902959310-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 1615 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902959310 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902959425-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 707 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902959425 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902959517-1 LH3758 | BLACK | 120D | S2754WAS518B | 365 | 2026-07-12 |  | SI | SI29/05/2026 |  | PANTS |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 15-Jul, ETD ?? T2 Kahatex, PI Date 28-Jun, actual receives 25-Jun. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0902959517 LH3758 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0902960904-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 410 | 15/12/2026 |  | SA | SA29/05/2026 |  | SHORTS |  | ok | (25/06/2026) | DRC 0090-early shipment customer (no need open ticket). T2 Libolon, PI Date 25-Jun, actual receives 09-Jul. T2 Formosa, PI Date 29-Jun, actual receives 03-Jul. 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0902960904 LH4535 | 13/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0902960952-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 110 | 15/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902960952 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961002-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 120 | 2026-07-11 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961002 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902961906-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 856 | 15/12/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516443 | HT+PAD SUB PROCESS_V3 | 0902961906 LD0283 | 31/08/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902961947-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 136 | 23/11/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 830009 | HT+PAD SUB PROCESS_V3 | 0902961947 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902962237-1 JZ7808 | BLACK | 120D | S2608WR0900 | 300 | 2026-07-11 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 516403 | HT+PAD SUB PROCESS_V3 | 0902962237 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee W BLACK |  | SS27-TI
ADIDAS | 0902962367-1 JZ7808 | BLACK | 120D | S2608WR0900-SLT | 105 | 15/12/2026 |  | ID | ID29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (27/06/2026) | 838103 | HT+PAD SUB PROCESS_V3 | 0902962367 JZ7808 | 31/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee W BLACK |  | SS27-SLT-TI
ADIDAS | 0902969632-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 535 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 672027 | HT+PAD SUB PROCESS_V3 | 0902969632 KF5311 | 31/08/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0902975836-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 2400 | 2026-07-11 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0902975836 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0902982744-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900 | 300 | 15/12/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0902982744 LD0283 | 31/08/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0902987712-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 319 | 2026-07-11 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987712 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987796-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 451 | 23/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | (28/07/2026) | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987796 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902987830-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 814006 | HT+PAD SUB PROCESS_V3 | 0902987830 LD0287 | 31/08/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902988826-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 229 | 2026-07-11 |  | SA | SA29/05/2026 |  | PANTS |  | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988826 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0902988871-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 199 | 2026-07-12 |  | SA | SA29/05/2026 |  | PANTS |  | ok | (22/06/2026) | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0902988871 KC8152 | 31/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0902990823-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 128 | 30/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990823 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0902990853-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900 | 100 | 15/11/2026 |  | SA | SA29/05/2026 |  | T-SHIRT |  | ok | (22/06/2026) | 839055 | HT+PAD SUB PROCESS_V3 | 0902990853 LD0287 | 31/08/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI
ADIDAS | 0903043395-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4200 | 2026-07-11 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043395 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903043496-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 8400 | 2026-07-11 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043496 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903043590-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 4800 | 2026-07-11 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903043590 LE7508 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903045667-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 4800 | 2026-07-11 |  | AN | AN12/06/2026 |  | PANTS |  | ok | (04/07/2026) | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903045667 LE7510 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903045765-1 LE5390 | WARM CLAY S25/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-11 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045765 LE5390 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903045811-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1200 | 2026-07-11 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045811 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903045956-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 4800 | 2026-07-11 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | EMBRO SUB PROCESS_V1 | 0903045956 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27
ADIDAS | 0903046008-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 948 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 600000 | HT+PAD SUB PROCESS_V3 | 0903046008 KX3650 | 2026-11-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903046882-1 KB5965 | BLACK | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046882 KB5965 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903046898-1 KB5960 | WHITE | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 512107 | HT+PAD SUB PROCESS_V3 | 0903046898 KB5960 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047008-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV-MTF | 282 | 2026-07-11 |  | AN | AN12/06/2026 |  | JACKET |  | ok | (03/07/2026) | T2 Kahatex, PI Date 13-Jul, actual receives 27-Jul. T2 Formosa, PI Date 03-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 27-Jun. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903047008 KV8005 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903047031-1 LG9675 | BLACK | 120D | S2754WAS513C | 208 | 30/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047031 LG9675 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047059-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 120 | 30/11/2026 |  | AN | AN12/06/2026 |  | SKIRT |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903047059 LG9669 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903047122-1 KB5960 | WHITE | 120D | S2608MR0900A | 300 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903047122 KB5960 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047142-1 KB5965 | BLACK | 120D | S2608MR0900A | 400 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903047142 KB5965 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903047322-1 LG9675 | BLACK | 120D | S2754WAS513C | 383 | 2026-07-11 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903047322 LG9675 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903047397-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903047397 LH3759 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903048576-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV-MTF | 112 | 2026-07-11 | 112 | AN | AN12/06/2026 | G3F | PANTS | G3 | ok | ok | T2 Kahatex, PI Date 13-Jul, actual receives 22-Jul. T2 Libolon, PI Date 29-Jun, actual receives 09-Jul. T2 Formosa, PI Date 09-Jun, actual receives 07-Jul. 512110 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903048576 KZ3200 | 28/08/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA | 2026-11-09 | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27 | 2026-11-09 | 17/09/2026 | 16/09/2026 | 16/09/2026 | 112 | 112 |  |  |  | 2026-08-09 | 14/09/2026 | 14/09/2026 | 15/09/2026 | 112 | 112
ADIDAS | 0903048584-1 LD0287 | SILVER BLUE S27 | 120D | S2608WR0900-MTF | 459 | 30/11/2026 | 459 | AN | AN12/06/2026 | G2Q | T-SHIRT | G2 | ok | (03/07/2026) | 804028 | HT+PAD SUB PROCESS_V3 | 0903048584 LD0287 | 2026-11-09 | KAHATEX CIJERAH | JAPAN | SEA | 29/10/2026 | Run Ess Tee W SILVER BLUE S27 |  | SS27-TI | 29/10/2026 | 30/10/2026 |  |  | 459 |  | 459 |  |  | 26/10/2026 | 27/10/2026 | 27/08/2026 | 22/09/2026 | 459 | 460 | -1 | 1 |  | 23/10/2026 | 24/10/2026 | 26/08/2026 | 18/09/2026 | 459 | 459
ADIDAS | 0903049235-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 508 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (03/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903049235 LC8943 | 28/08/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903053818-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 450 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 630001 | HT+PAD SUB PROCESS_V3 | 0903053818 KX3650 | 2026-11-09 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903054588-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054588 LH3759 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903054623-1 LH3761 | LEGEND IVY S19 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI12/06/2026 |  | PANTS |  | (27/07/2026) | (04/07/2026) | Waiting fabric. T2 Kahatex, PI Date 13-Jul, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903054623 LH3761 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903056025-1 KB5965 | BLACK | 120D | S2608MR0900A | 408 | 15/11/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056025 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903056057-1 KB5965 | BLACK | 120D | S2608MR0900A | 138 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | (11/08/2026) | (04/07/2026) | 826010 | HT+PAD SUB PROCESS_V3 | 0903056057 KB5965 | 2026-11-09 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903056557-1 KY1361 | BLACK/BLACK | 75D | S2706CHRM031 | 141 | 15/11/2026 |  | AN | AN12/06/2026 |  | SWEATSHIRT |  | ok | (17/07/2026) | 516205 | PRINT L2+EMBRO SUB PROCESS_V3 | 0903056557 KY1361 | 29/07/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | REAL HER CR BLACK/BLACK |  | SS27
ADIDAS | 0903058736-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 303 | 2026-07-12 |  | SA | SA12/06/2026 |  | PANTS |  | (11/08/2026) | (04/07/2026) | 516342 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903058736 KY5988 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903059435-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 109 | 2026-07-12 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059435 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059465-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 865 | 2026-07-11 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059465 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059549-1 KZ3201 | TEAM MAROON 2/WHITE | 90D | S2754WESS404WV | 118 | 2026-07-12 |  | SI | SI12/06/2026 |  | PANTS |  | ok | (03/07/2026) | T2 Formosa, PI Date 08-Jul, actual receives 22-Jul. T2 Libolon, PI Date 06-Jul, actual receives 20-Jul. T2 Kahatex, PI Date 13-Jul, actual receives 01-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903059549 KZ3201 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903059897-1 LD0285 | HAZE CORAL S17 | 120D | S2608WR0900 | 480 | 15/12/2026 |  | SA | SA12/06/2026 |  | T-SHIRT |  | ok | (04/07/2026) | 516421 | HT+PAD SUB PROCESS_V3 | 0903059897 LD0285 | 2026-11-09 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee W HAZE CORAL S17 |  | SS27-TI
ADIDAS | 0903060334-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B-MTF | 300 | 2026-07-12 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (03/07/2026) | Waiting fabric. T2 Kahatex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060334 LF0729 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903060669-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 188 | 2026-07-12 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 20-Jul, ETD ?? T2 Kahatex, PI Date 11-Aug, actual receives 27-Jun (PO NT-354). 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060669 LF0726 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903060691-1 LF0727 | BLACK | 120D | S2754MAS510B-MTF | 275 | 2026-07-12 |  | AN | AN12/06/2026 |  | JACKET |  | (11/08/2026) | (04/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 11-Aug, actual receives 28-May (PO NT-354). 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903060691 LF0727 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903060718-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 100 | 2026-07-12 |  | AN | AN12/06/2026 |  | SKIRT |  | (27/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903060718 LG9669 | 2026-11-09 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903060727-1 LH4536 | WHITE/BLACK | 90D | S2754WESS421WV | 200 | 2026-07-12 |  | SA | SA12/06/2026 |  | SHORTS |  | (20/07/2026) |  | T2 Formosa, PI Date 20-Jul, actual receives 27-jul. T2 Libolon, PI Date 16-Jul, actual receives 09-Jul. 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903060727 LH4536 | 28/08/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 74 WHITE/BLACK |  | SS27
ADIDAS | 0903061680-1 LE5038 | BLACK | 105D | S2750MTR104A | 180 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903061680 LE5038 | 2026-11-09 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061955-1 LE5038 | BLACK | 105D | S2750MTR104A | 241 | 30/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061955 LE5038 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903061985-1 LE5038 | BLACK | 105D | S2750MTR104A | 221 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903061985 LE5038 | 2026-11-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903062051-1 LE5038 | BLACK | 105D | S2750MTR104A | 252 | 15/11/2026 |  | AN | AN12/06/2026 |  | T-SHIRT |  | ok | (06/07/2026) | T2 Sue's, PI Date 02-Aug, actual receives 20-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903062051 LE5038 | 2026-11-09 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP GFX T BLACK |  | SS27-TI
ADIDAS | 0903063396-1 LG9669 | BLACK | 120D | S2754WAS514C-MTF | 394 | 2026-07-11 |  | AN | AN12/06/2026 |  | SKIRT |  | (20/07/2026) | (03/07/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 27-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903063396 LG9669 | 2026-11-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903093131-1 KF5803 | BLACK | 105D | S2608MR0602A | 727 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 1st Art (TC 10 pcs) 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093131 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093134-1 KF5803 | BLACK | 105D | S2608MR0602A | 302 | 30/11/2026 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Trax, (body&mesh) PI Date 10-Jul, ETD ?? Waiting fabric. T2 Dar Eastern, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Far Eastern, PI Date ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093134 KF5803 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | adi365 2in1 S M BLACK |  | SS27-TRAX
ADIDAS | 0903093432-1 KZ4392 | WHITE | 120D | F2608WR1500 | 50 | 30/11/2026 | 50 | ID | ID23/06/2026 | G1R | T-SHIRT | G1 |  |  | TRAX (MOQ Issue) Waiting fabric. DRC 0064-T2 Men Chuen, PI Date ?? 600000 | PAD+HT SUB PROCESS_V3 | 0903093432 KZ4392 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/11/2026 | ADIZERO A TEE W WHITE |  | SS27-TRAX | 20/11/2026 | 20/11/2026 |  |  | 50 |  | 50 |  |  | 17/11/2026 | 17/11/2026 |  |  | 50 |  | 50 |  |  | 16/11/2026 | 16/11/2026 |  |  | 50 |  | 50
ADIDAS | 0903093481-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 1637 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093481 KY9385 | 21/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903093484-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 350 | 2026-07-11 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516290 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093484 KY9384 | 21/09/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903093496-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 379 | 2026-07-12 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/07/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD 30-Jul, ETA-Kaha 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 31-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093496 KD3854 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903093497-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 333 | 2026-07-12 |  | SI | SI23/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 24-Jul, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903093497 LF9808 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903093896-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 6 | 23/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 960026 | PRINT L2+HT SUB PROCESS_V3 | 0903093896 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093897-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 478 | 15/11/2026 |  | AN | AN23/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 830009 | PRINT L2+HT SUB PROCESS_V3 | 0903093897 KZ0028 | 2026-07-09 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903093913-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 749 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903093913 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093914-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 323 | 30/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093914 KV0333 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093915-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 179 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903093915 KV0333 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 0903093916-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 320 | 15/11/2026 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516254 | PAD+HT SUB PROCESS_V3 | 0903093916 LG1784 | 21/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903093917-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 61 | 2026-07-12 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903093917 LG1784 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903093918-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 324 | 2026-07-12 |  | ID | ID23/06/2026 |  | T-SHIRT |  | (20/08/2026) | ok | Waiting fabric. T2 Men Chuen, PI Date 06-Aug, ETD ?? 516342 | PAD+HT SUB PROCESS_V3 | 0903093918 LG1784 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903095148-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 366 | 30/11/2026 |  | SI | SI23/06/2026 |  | SHORTS |  | (10/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Trax, PI Date 24-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095148 KY9431 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903095159-1 KZ1333 | HAZE CORAL S17 | 105D | S2608WR0201A | 60 | 15/11/2026 | 60 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | Waiting fabric. DRC 0064-Waiting fabric. T2 Best Pacific, PI Date 30-Sep. Waiting fabric. T2 Far Eastern, PI Date 05-Sep, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 05-Sep, ETD ?? Waiting fabric. T2 Grand tex, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Grand Tex, PI Date ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095159 KZ1333 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/11/2026 | ADI365 SHO W HAZE CORAL S17 |  | SS27-TRAX | 20/11/2026 | 20/11/2026 |  |  | 60 |  | 60 |  |  | 17/11/2026 | 17/11/2026 |  |  | 60 |  | 60 |  |  | 2026-12-11 | 2026-12-11 |  |  | 60 |  | 60
ADIDAS | 0903095166-1 LF4208 | TEAM ROYAL BLUE | 105D | S2608WR0201A | 50 | 15/11/2026 | 50 | SI | SI23/06/2026 | G3D | SHORTS | G3 |  |  | Waiting fabric. DRC 0064-Waiting fabric. T2 Best Pacific, PI Date 30-Sep. Waiting fabric. T2 Far Eastern, PI Date 05-Sep, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 05-Sep, ETD ?? Waiting fabric. T2 Grand tex, PI Date 01-Sep, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095166 LF4208 | 21/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA | 20/11/2026 | ADI365 SHO W TEAM ROYAL BLUE |  | SS27-TRAX | 20/11/2026 | 20/11/2026 |  |  | 50 |  | 50 |  |  | 17/11/2026 | 17/11/2026 |  |  | 50 |  | 50 |  |  | 2026-12-11 | 2026-12-11 |  |  | 50 |  | 50
ADIDAS | 0903095181-1 LC6791 | SILVER DAWN S23 | 120D | S2608WR0202 | 235 | 2026-07-11 |  | SA | SA23/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 07-Sep. Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095181 LC6791 | 21/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903095207-1 KC4947 | BLACK | 105D | S2608WR0216 | 304 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 804028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095207 KC4947 | 21/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095212-1 KC4947 | BLACK | 105D | S2608WR0216 | 100 | 23/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 512110 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095212 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903095214-1 KC4947 | BLACK | 105D | S2608WR0216 | 109 | 15/11/2026 |  | SA | SA23/06/2026 |  | PANTS |  | (14/08/2026) | ok | Waiting fabric. T2 Huge Bamboo, PI Date 29-Aug, ETD ?? Waiting fabric. T2 Nan Ya, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903095214 KC4947 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | adi365 Astro W |  | SS27-TRAX
ADIDAS | 0903110808-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 1204 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 14-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903110808 LE4307 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903128980-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C-MTF | 367 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903128980 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903130792-1 LC5741 | AURORA COFFEE S26/SEMI SOLAR AQUA S27 | 105D | F2654MESS614WVB | 1497 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? T2 Libolon, PI Date 06-Aug, actual receives 01-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903130792 LC5741 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 72S WV WB LND AURORA COFFEE S26/SEMI SOLAR AQUA S27 |  | SS27
ADIDAS | 0903130818-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 200 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130818 LI2646 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903130858-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 200 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130858 LI2645 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903130900-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 2415 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | (04/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903130900 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903130905-1 LF0723 | BLACK | 105D | S2754MAS511B | 427 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130905 LF0723 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903130944-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 300 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903130944 LF0725 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903131188-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 200 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 960006 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903131188 LI2647 | 2026-10-08 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903133687-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 1580 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133687 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903133962-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 1891 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903133962 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903134663-1 KW2909 | BLACK/WHITE | 90D | S2754WESS420WV | 582 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. T2 Libolon, PI Date 23-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903134663 KW2909 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV WB BLACK/WHITE |  | SS27
ADIDAS | 0903134760-1 KS1804 | BLACK | 60D | F26KCNYGFX100 | 803 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | (15/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903134760 KS1804 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903135025-1 KS1836 | LIGHT GREY HEATHER | 60D | F26KCNYGFX110 | 804 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (29/07/2026) | (05/08/2026) | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903135025 KS1836 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARCH SEAL TEE |  | SS27
ADIDAS | 0903135275-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 119 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135275 LI2669 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135319-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 532 | 2026-07-12 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903135319 LG9673 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135338-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 182 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135338 LI2645 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903135342-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 568 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903135342 LI2669 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903135375-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 498 | 2026-07-11 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903135375 LG9673 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135514-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 418 | 2026-07-12 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903135514 LG9664 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903135996-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 1281 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903135996 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136768-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 529 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136768 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903136798-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 1276 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903136798 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903136945-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 127 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903136945 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903137343-1 KZ3227 | SILVER BLUE S27/WHITE | 90D | S2754WESS420WV | 826 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (03/08/2026) | ok | Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? T2 Kahatex, PI Date 29-Jul, actual receives 07-Aug. T2 Formosa, PI Date 27-Jul, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137343 KZ3227 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 48S WV WB SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903137463-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 465 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903137463 KV8005 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903138115-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 719 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903138115 LI2647 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903138412-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 525 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903138412 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903139689-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 993 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903139689 LI2672 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903142659-1 KB5965 | BLACK | 120D | S2608MR0900A | 1804 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142659 KB5965 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903142864-1 KB5960 | WHITE | 120D | S2608MR0900A | 677 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903142864 KB5960 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903143517-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143517 LI2645 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903143521-1 LF0723 | BLACK | 105D | S2754MAS511B | 564 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143521 LF0723 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903143540-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143540 LI2671 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903143546-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 215 | 2026-07-12 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143546 LF0726 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903143571-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 450 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143571 LI2647 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903143577-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 100 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143577 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903143597-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 3300 | 23/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 804028 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903143597 LI2646 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903143604-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 230 | 2026-07-12 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143604 LF0718 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903143634-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 600 | 23/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | ok | ok | 804028 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903143634 LI2670 | 2026-10-08 | KAHATEX CIJERAH | JAPAN | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903143641-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 335 | 2026-07-12 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903143641 LE8181 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903144865-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 173 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903144865 JG5832 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903144982-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 1140 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903144982 LF0726 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145068-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 366 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145068 LF0726 | 24/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145411-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 1000 | 2026-07-11 |  | AN | AN26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145411 LG9666 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903145447-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 199 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903145447 KR3066 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903145474-1 LG9669 | BLACK | 120D | S2754WAS514C | 106 | 2026-07-11 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903145474 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903145521-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903145521 LG9674 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903145548-1 LG9675 | BLACK | 120D | S2754WAS513C | 1000 | 2026-07-11 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903145548 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903145603-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 1400 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145603 LG9661 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903145666-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 204 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145666 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903145710-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 562 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800187 | PRINT L1+HT SUB PROCESS_V3 | 0903145710 KU8361 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903145834-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 503 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903145834 KY5936 | 2026-11-08 | KAHATEX CIJERAH | THAILAND | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903145950-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 405 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145950 LE8181 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903145998-1 LG9666 | BLACK | 120D | S2754WAS512C | 230 | 15/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903145998 LG9666 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903146035-1 LE8187 | BLACK | 105D | S2754MAS513 | 497 | 15/12/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146035 LE8187 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903146070-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 798 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903146070 KU8361 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146104-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 370 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146104 LF0726 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903146143-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 445 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146143 LF0718 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903146231-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 581 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146231 KY5936 | 2026-11-08 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146256-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146256 KY5936 | 2026-11-08 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146268-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 132 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146268 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903146275-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 527 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 830009 | PRINT L1+HT SUB PROCESS_V3 | 0903146275 KU8361 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903146301-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146301 LF0725 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903146321-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 355 | 2026-07-12 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146321 LF0725 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903146384-1 LG9666 | BLACK | 120D | S2754WAS512C-MTF | 325 | 2026-07-12 |  | AN | AN26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146384 LG9666 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903146405-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 1844 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146405 LD5446 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903146460-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 192 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Cargoport). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146460 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903146508-1 JZ7711 | BLACK | 120D | S2608MR0202 | 144 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (Cargoport). T2 Trax, PI Date 24-Jul, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903146508 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903146544-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 390 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903146544 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146570-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 1000 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903146570 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903146595-1 KU8357 | BLACK | 105D | S2750MTR051 | 733 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903146595 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903146621-1 LC6583 | GREY | 105D | S2750MTR051 | 680 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 814006 | HT SUB PROCESS_V1 | 0903146621 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903146650-1 LE8187 | BLACK | 105D | S2754MAS513 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903146650 LE8187 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903146681-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903146681 KA3549 | 2026-11-08 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903147883-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 205 | 2026-07-12 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903147883 LF0721 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903147919-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 100 | 2026-07-12 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 800187 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903147919 LF0729 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903147964-1 LC6583 | GREY | 105D | S2750MTR051 | 210 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800187 | HT SUB PROCESS_V1 | 0903147964 LC6583 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148024-1 KU8357 | BLACK | 105D | S2750MTR051 | 331 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800187 | HT SUB PROCESS_V1 | 0903148024 KU8357 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148048-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 221 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148048 KY5901 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148127-1 KY5936 | PURE BLUE S27 | 135D | S2650MTR412 | 213 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903148127 KY5936 | 2026-11-08 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148646-1 LC6583 | GREY | 105D | S2750MTR051 | 283 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (01/08/2026) | ok | Waiting fabric replacement. T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903148646 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148668-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148668 LC6583 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903148676-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 2259 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903148676 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903148711-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 285 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148711 LF0721 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903148723-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 120 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148723 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148742-1 KU8357 | BLACK | 105D | S2750MTR051 | 221 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148742 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148757-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 128 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 826010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903148757 KA2571 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903148774-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 325 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148774 LF0729 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903148833-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1032 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903148833 KC8152 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903148848-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 427 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903148848 KY5901 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903148870-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 308 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 826010 | HT+PAD SUB PROCESS_V3 | 0903148870 KB5961 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148873-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 390 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903148873 LF0725 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903148894-1 KB5965 | BLACK | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 826010 | HT+PAD SUB PROCESS_V3 | 0903148894 KB5965 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903148901-1 KU8357 | BLACK | 105D | S2750MTR051 | 450 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 814006 | HT SUB PROCESS_V1 | 0903148901 KU8357 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903148944-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 732 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903148944 LD0283 | 25/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903149176-1 JZ7711 | BLACK | 120D | S2608MR0202 | 540 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 14-Aug, ETD ?? Waiting fabric (KN GLT). T2 Trax, PI Date 24-Jul, ETD ?? 650031 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149176 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903149522-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 108 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903149522 KR3066 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903149602-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 100 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (NYK warehouse). 800005 | PAD+HT SUB PROCESS_V3 | 0903149602 JJ0052 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903149641-1 KA3530 | BLACK | 105D | S2650MTR402 | 128 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903149641 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903149843-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 396 | 30/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149843 JW7182 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903149931-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO SUB PROCESS_V1 | 0903149931 JD1881 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903149955-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 301 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 659018 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903149955 JW7182 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903150153-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 125 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150153 LF0725 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903150446-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 340 | 30/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903150446 LF0726 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903150468-1 KE8424 | BLACK | 120D | S2608MR0906A | 487 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | 804028 | HT+PAD SUB PROCESS_V3 | 0903150468 KE8424 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903150575-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1906 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 03-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903150575 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903150999-1 LG9669 | BLACK | 120D | S2754WAS514C | 143 | 15/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512102 | PRINT L3+PPA SUB PROCESS_V3 | 0903150999 LG9669 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151026-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 739 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 659018 | HT+PAD SUB PROCESS_V3 | 0903151026 KB5961 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903151173-1 KA3530 | BLACK | 105D | S2650MTR402 | 376 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151173 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151201-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 314 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151201 LF0729 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151239-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 240 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151239 LF0721 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151246-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 222 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151246 KD5507 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903151262-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 240 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 11-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151262 LF0725 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903151271-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 27-Jul, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903151271 KA3530 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903151331-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 208 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151331 LF0721 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903151379-1 LG9669 | BLACK | 120D | S2754WAS514C | 600 | 2026-07-11 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516415 | PRINT L3+PPA SUB PROCESS_V3 | 0903151379 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903151446-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 1400 | 30/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903151446 LG9668 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903151598-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 539 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903151598 KU8361 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903151643-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 117 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903151643 LF0718 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903152441-1 LF0727 | BLACK | 120D | S2754MAS510B | 813 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903152441 LF0727 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903152456-1 KB5965 | BLACK | 120D | S2608MR0900A | 926 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903152456 KB5965 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903152478-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 533 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (29/07/2026) | ok | 630001 | EMBRO+PPA SUB PROCESS_V3 | 0903152478 HR8583 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903152536-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1831 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152536 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903152617-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1627 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152617 KY9391 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903152941-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903152941 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903153406-1 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 477 | 2026-07-11 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. 823016 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903153406 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903153476-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 102 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? 680014 | PRINT L2+HT SUB PROCESS_V3 | 0903153476 KZ0028 | 2026-10-09 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903153531-1 KT4840 | ONIX | 90D | S2408MR1600 | 348 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 688010 | HT SUB PROCESS_V1 | 0903153531 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903153589-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1010 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Damco offline). 688010 | HT+PAD SUB PROCESS_V3 | 0903153589 KX3654 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903153628-1 KU2430 | WHITE | 60D | S27FBGFXP510-MTF | 774 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (Damco offline). 688010 | PRINT L2+PAD SUB PROCESS_V3 | 0903153628 KU2430 | 2026-10-08 | KAHATEX CIJERAH | PANAMA | SEA |  | M FB NOVELTY T WHITE |  | SS27
ADIDAS | 0903153664-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 228 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | HT+PAD SUB PROCESS_V3 | 0903153664 KX3655 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903153687-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 212 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153687 LF0718 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903153698-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 409 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 680015 | HT+PAD SUB PROCESS_V3 | 0903153698 KB5961 | 24/09/2026 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903153817-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 170 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153817 LF0726 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903153919-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 100 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153919 LE8181 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903153964-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 242 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903153964 LD5446 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903154007-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 150 | 2026-07-12 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903154007 LF0726 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903154776-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 1663 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154776 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154799-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 13 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154799 KX3653 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903154849-1 KA3549 | BLACK | 135D | S2650MTR412 | 108 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154849 KA3549 | 2026-11-08 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903154868-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 393 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | 659018 | HT+PAD SUB PROCESS_V3 | 0903154868 KX3655 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903154889-1 KA3549 | BLACK | 135D | S2650MTR412 | 126 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154889 KA3549 | 2026-11-08 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903154917-1 KA3549 | BLACK | 135D | S2650MTR412 | 102 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903154917 KA3549 | 2026-11-08 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903155043-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 210 | 15/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903155043 LC8943 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903155243-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 200 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155243 KD3854 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903155535-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 180 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155535 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155567-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155567 KF5311 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903155594-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 114 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 680014 | HT+PAD SUB PROCESS_V3 | 0903155594 KX3654 | 24/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903155612-1 KT4840 | ONIX | 90D | S2408MR1600 | 186 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 680014 | HT SUB PROCESS_V1 | 0903155612 KT4840 | 2026-10-09 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903155678-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 224 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903155678 KY9384 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903155800-1 LC7300 | WHITE | 90D | S2725M926A | 262 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903155800 LC7300 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903155810-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 1129 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155810 KX3650 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903155820-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 282 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | (Damco offline). T2 Kahatex, PI Date 28-Aug, actual receives 09-Sep. T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 688010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903155820 KA2571 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903155831-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 112 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903155831 LC7301 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903155836-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 282 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (Damco offline). T2 Kahatex, PI Date 28-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 688010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903155836 KD0738 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903155872-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | EMBRO SUB PROCESS_V1 | 0903155872 KW8933 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903155878-1 KB5960 | WHITE | 120D | S2608MR0900A | 591 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903155878 KB5960 | 24/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903155947-1 KA3549 | BLACK | 135D | S2650MTR412 | 110 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903155947 KA3549 | 2026-11-08 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156012-1 KA3549 | BLACK | 135D | S2650MTR412 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903156012 KA3549 | 2026-11-08 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903156032-1 KE8424 | BLACK | 120D | S2608MR0906A | 522 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903156032 KE8424 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903156064-1 KY5901 | PURE BLUE S27 | 105D | S2650MTR402 | 124 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Easten, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903156064 KY5901 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T PURE BLUE S27 |  | SS27-TI
ADIDAS | 0903156098-1 LC6583 | GREY | 105D | S2750MTR051 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 839055 | HT SUB PROCESS_V1 | 0903156098 LC6583 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156126-1 KU8357 | BLACK | 105D | S2750MTR051 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 839055 | HT SUB PROCESS_V1 | 0903156126 KU8357 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156155-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 684 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  | ok | 659018 | HT+PAD SUB PROCESS_V3 | 0903156155 LD0288 | 25/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903156632-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 245 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | EMBRO SUB PROCESS_V1 | 0903156632 KW8933 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903156637-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 320 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903156637 KB0246 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903156704-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 101 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. (NYK warehouse). 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903156704 LD0908 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903156821-1 LC6583 | GREY | 105D | S2750MTR051 | 196 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903156821 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903156916-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 422 | 15/12/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | (04/08/2026) | (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156916 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903156923-1 KU8357 | BLACK | 105D | S2750MTR051 | 232 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903156923 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903156947-1 KT4840 | ONIX | 90D | S2408MR1600 | 451 | 15/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric (Airowes). T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 650034 | HT SUB PROCESS_V1 | 0903156947 KT4840 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903156956-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 114 | 2026-07-11 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903156956 LC8884 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903156980-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 553 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (29/07/2026) | ok | (Airowes). T2 Libolon, PI Date 22-Jul, actual receives 14-Jul (PO 26028534). T2 Formosa, actual receives 04-Jul. (PO 26021877). T2 Kahatex, PI Date 29-Jul, actual receives 03-Jun (PO NT-347). 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903156980 KV7863 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903157033-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 839055 | PRINT L1 SUB PROCESS_V3 | 0903157033 LC7300 | 2026-10-09 | KAHATEX CIJERAH | SINGAPORE | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903157034-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 198 | 15/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157034 KF5311 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903157056-1 LC6583 | GREY | 105D | S2750MTR051 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 800005 | HT SUB PROCESS_V1 | 0903157056 LC6583 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903157058-1 KE8424 | BLACK | 120D | S2608MR0906A | 165 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157058 KE8424 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903157123-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 312 | 15/12/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 814006 | EMBRO SUB PROCESS_V1 | 0903157123 KW8933 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903157615-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 102 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157615 LG9664 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903157637-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B-MTF | 149 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903157637 LD5446 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903157760-1 KB5965 | BLACK | 120D | S2608MR0900A | 410 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 684009 | HT+PAD SUB PROCESS_V3 | 0903157760 KB5965 | 24/09/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157832-1 KB5960 | WHITE | 120D | S2608MR0900A | 1492 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157832 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157859-1 KB5965 | BLACK | 120D | S2608MR0900A | 3535 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 678002 | HT+PAD SUB PROCESS_V3 | 0903157859 KB5965 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157884-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 502 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (30/07/2026) | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 30-Jul, ETD ?? 678002 | HT+PAD SUB PROCESS_V3 | 0903157884 KB5961 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903157922-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 3009 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903157922 KR3066 | 24/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903157960-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 198 | 15/12/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/08/2026) | (28/07/2026) | (Airowes). 650034 | HT+PAD SUB PROCESS_V3 | 0903157960 KX3655 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903158055-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 229 | 15/12/2026 |  | AN | AN26/06/2026 |  | JACKET |  | ok | ok | (Airowes). T2 Kahatex, PI Date 29-Jul, actual receives 23-Jul. T2 Libolon, actual receives 12-Jun (PO 26022038). T2 Formosa, actual receives 04-Jul (PO 26022040). 650034 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903158055 LF1392 | 2026-10-09 | KAHATEX CIJERAH | URUGUAY | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903158194-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 838103 | HT SUB PROCESS_V1 | 0903158194 KY5866 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903158242-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 550 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903158242 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903158307-1 KX3651 | LIME TINT S27 | 120D | S2608MR0900A | 310 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903158307 KX3651 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M LIME TINT S27 |  | SS27-TI
ADIDAS | 0903158332-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158332 LG9664 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158354-1 LG9673 | LEGEND IVY S19 | 120D | S2754WAS513C | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158354 LG9673 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158375-1 LG9666 | BLACK | 120D | S2754WAS512C | 201 | 30/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158375 LG9666 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903158398-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 188 | 23/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158398 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158417-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 738 | 30/11/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158417 LE8187 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903158426-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPA SUB PROCESS_V3 | 0903158426 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158447-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 152 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158447 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158468-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512110 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158468 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158523-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 200 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158523 LE8181 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903158528-1 KB5960 | WHITE | 120D | S2608MR0900A | 450 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903158528 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903158543-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158543 LG9674 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158570-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158570 LG9661 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158596-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 150 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903158596 LG9670 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903158627-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 201 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903158627 LG9665 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903158788-1 KR2020 | BLACK | 60D | F26KCPDXGFX100 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903158788 KR2020 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | PDX HBR TEE |  | SS27
ADIDAS | 0903158813-1 KR1994 | DARK BLUE | 60D | F26KCLVGFX110 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | EMBRO+HT+PAD SUB PROCESS_V3 | 0903158813 KR1994 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA |  | DICE TEE |  | SS27
ADIDAS | 0903159008-1 KS2145 | BLACK | 60D | F26KCCHIGFX100 | 311 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | (17/07/2026) | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903159008 KS2145 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA |  | PIZZA TEE |  | SS27
ADIDAS | 0903159089-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV-MTF | 300 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | ok | ok | T2 Formosa, actual receives 19-Jun (P0 26022035). T2 Libolon, actual receives 09-Jun (PO 26022034). 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903159089 KV7963 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903159152-1 JZ7711 | BLACK | 120D | S2608MR0202 | 187 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (14/08/2026) | ok | Waiting fabric (Airowes). T2 Hua Feng, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 650034 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159152 JZ7711 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903159185-1 KU8357 | BLACK | 105D | S2750MTR051 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 800005 | HT SUB PROCESS_V1 | 0903159185 KU8357 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903159233-1 KX0126 | OLIVE FOUR S27 | 90D | S27SPRMGFXP0800-MTF | 114 | 2026-07-11 |  | AN | AN26/06/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L2+PAD SUB PROCESS_V3 | 0903159233 KX0126 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M RESORT T OLIVE FOUR S27 |  | SS27
ADIDAS | 0903159243-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 227 | 15/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | (04/08/2026) | Waiting fabric (Airowes). T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159243 LF0726 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159272-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 228 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159272 LC7301 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903159311-1 LC7300 | WHITE | 90D | S2725M926A | 228 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903159311 LC7300 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903159349-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 156 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (Cargoport). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159349 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903159476-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 312 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 839055 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159476 LE8181 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159754-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 584 | 23/11/2026 |  | AN | AN26/06/2026 |  | JACKET |  | (28/08/2026) | (07/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903159754 LF0726 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903159774-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903159774 KR3066 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903159800-1 LG9669 | BLACK | 120D | S2754WAS514C | 396 | 23/11/2026 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903159800 LG9669 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903160049-1 KA3530 | BLACK | 105D | S2650MTR402 | 244 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903160049 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160055-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 657 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 630001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160055 KD3854 | 24/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903160079-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 130 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903160079 KB0237 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903160125-1 KA3530 | BLACK | 105D | S2650MTR402 | 257 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903160125 KA3530 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903160245-1 KY5866 | BLACK | 90D | S2750MTR052 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160245 KY5866 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160344-1 KY5866 | BLACK | 90D | S2750MTR052 | 184 | 23/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800005 | HT SUB PROCESS_V1 | 0903160344 KY5866 | 2026-10-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903160388-1 KA0246 | BLACK | 90D | S2608WR0902 | 405 | 15/12/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 516400 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903160388 KA0246 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903160662-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 1461 | 15/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (12/08/2026) |  | Waiting fabric. T2 Formosa, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 06-Aug. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903160662 LD6542 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903160682-1 KB5960 | WHITE | 120D | S2608MR0900A | 250 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903160682 KB5960 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903161120-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 100 | 2026-07-12 |  | SI | SI26/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903161120 KD3854 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903161179-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 2545 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Kahatex, PI Date 29-Jul, actual receives 05-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161179 KZ3202 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903161241-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2662 | 15/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | ok | (07/08/2026) | T2 Kahatex, PI Date 29-Jul, actual receives 11-Aug. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 17-Jul. 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903161241 KZ3200 | 2026-10-09 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903162158-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 127 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162158 KB0234 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903162234-1 JZ1077 | BLACK | 90D | S2654MSERENO742 | 324 | 2026-07-11 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162234 JZ1077 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T BLACK |  | SS27-STX
ADIDAS | 0903162276-1 KA3530 | BLACK | 105D | S2650MTR402 | 1263 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903162276 KA3530 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903162278-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 1526 | 15/11/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162278 LD0283 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903162311-1 LD0288 | SEMI SOLAR AQUA S27 | 120D | S2608WR0900-MTF | 1226 | 15/12/2026 |  | AN | AN29/06/2026 |  | T-SHIRT |  |  |  | 630001 | HT+PAD SUB PROCESS_V3 | 0903162311 LD0288 | 25/09/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee W SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903162492-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 348 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903162492 KB0247 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903162518-1 KA3549 | BLACK | 135D | S2650MTR412 | 208 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162518 KA3549 | 2026-11-08 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903162545-1 KA3549 | BLACK | 135D | S2650MTR412 | 921 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (16/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 01-Aug, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903162545 KA3549 | 2026-11-08 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE BAS WV SHO BLACK |  | SS27-TI
ADIDAS | 0903163092-1 KU8357 | BLACK | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, PI Date 01-Aug, actual receives 27-Aug. 838103 | HT SUB PROCESS_V1 | 0903163092 KU8357 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T BLACK |  | SS27-TI
ADIDAS | 0903163452-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 411 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | (KN GLT). 650010 | HT+PAD SUB PROCESS_V3 | 0903163452 KF5311 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903163561-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 610 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (21/08/2026) |  | Waiting fabric (KN GLT). T2 Far Eastern, PI Date 21-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 04-Aug, ETD ?? Waiting fabric. T2 Trax, PI Date 10-Jul, ETD ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903163561 KZ1286 | 24/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903164394-1 KB0237 | PURE RUBY S25/WHITE | 90D | S2615KSWJ751 | 940 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164394 KB0237 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T PURE RUBY S25/WHITE |  | SS27-STX
ADIDAS | 0903164435-1 KB0234 | BLACK/WHITE | 90D | S2615KSWJ751 | 280 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164435 KB0234 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164449-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 892 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903164449 KS3009 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903164515-1 KA3530 | BLACK | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903164515 KA3530 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903164654-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 651 | 15/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516439 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903164654 LF0726 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903164675-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 141 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164675 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164712-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 100 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164712 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903164747-1 KB0246 | BLACK/WHITE | 90D | S2615KSWJ753 | 205 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (10/09/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164747 KB0246 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE SHO BLACK/WHITE |  | SS27-STX
ADIDAS | 0903164777-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 102 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164777 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164808-1 JZ1089 | WHITE | 90D | S2654MSERENO743 | 278 | 15/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164808 JZ1089 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO WHITE |  | SS27-STX
ADIDAS | 0903164853-1 KT4840 | ONIX | 90D | S2408MR1600 | 206 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (04/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 03-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 25-Jul, ETD ?? 830009 | HT SUB PROCESS_V1 | 0903164853 KT4840 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903164866-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 522 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric (NYK warehouse). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903164866 KU8361 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903164923-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 182 | 2026-07-11 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164923 KV8149 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164958-1 KV8142 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO742 | 150 | 2026-07-11 |  | ID | ID26/06/2026 |  | T-SHIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 30-Aug. 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903164958 KV8142 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO 3S T OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903164977-1 KW8933 | SILVER LEAF S27/BLACK | 90D | S2754MESS676SJ | 845 | 23/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  |  | ok | 830009 | EMBRO SUB PROCESS_V1 | 0903164977 KW8933 | 2026-10-09 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 21B SJ LF T SILVER LEAF S27/BLACK |  | SS27-STX
ADIDAS | 0903165093-1 KY5866 | BLACK | 90D | S2750MTR052 | 294 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903165093 KY5866 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903165114-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 152 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903165114 KS3009 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903165135-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 378 | 2026-07-12 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165135 LF0726 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903165143-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 120 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903165143 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165365-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 400 | 2026-07-11 |  | SA | SA26/06/2026 |  | JACKET |  | (18/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903165365 LG9665 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903165453-1 KV8149 | OLIVE FOUR S27/BLACK | 90D | S2654MSERENO743 | 924 | 30/11/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903165453 KV8149 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SERENO SHO OLIVE FOUR S27/BLACK |  | SS27-STX
ADIDAS | 0903165549-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 124 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903165549 KD5507 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903165577-1 JG5832 | BLACK/WHITE | 90D | S2506GHTM400M | 178 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PAD+HT SUB PROCESS_V3 | 0903165577 JG5832 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA133 JSY M BLACK/WHITE |  | SS27-TI
ADIDAS | 0903165613-1 LC7300 | WHITE | 90D | S2725M926A | 240 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903165613 LC7300 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903166410-1 JJ0052 | BLACK/WHITE | 90D | S2506GHTM400Y | 217 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 838103 | PAD+HT SUB PROCESS_V3 | 0903166410 JJ0052 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 JSY Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903166569-1 JJ2417 | BLACK/WHITE | 90D | S2506GHTM401Y | 174 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | 1st Art (TC 10 pcs) 838103 | PAD+HT SUB PROCESS_V3 | 0903166569 JJ2417 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | SQUA25 SHO Y BLACK/WHITE |  | SS27-TI
ADIDAS | 0903167257-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 852 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903167257 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167292-1 KR6693 | BLACK | 60D | F26KCLVGFX100 | 311 | 30/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/07/2026) | ok | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903167292 KR6693 | 2026-10-08 | KAHATEX CIJERAH | UNITED STATES | SEA |  | LV COLLEGIATE T |  | SS27
ADIDAS | 0903167354-1 KU8361 | CARBON S18/BLACK | 105D | S2750MTR045 | 180 | 30/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 09-Aug, ETD ?? 839055 | PRINT L1+HT SUB PROCESS_V3 | 0903167354 KU8361 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T AOP S CARBON S18/BLACK |  | SS27-TI
ADIDAS | 0903167377-1 JZ1090 | BLACK | 90D | S2654MSERENO743 | 475 | 15/12/2026 |  | AN | AN26/06/2026 |  | SHORTS |  | (13/09/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 13-Sep. Waiting fabric. T2 Kahatex, PI Date 14-Aug, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903167377 JZ1090 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | M SERENO SHO BLACK |  | SS27-STX
ADIDAS | 0903167397-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 615 | 30/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  |  | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903167397 LC7301 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903167406-1 KB0247 | WHITE/BLACK | 90D | S2615KSWJ753 | 160 | 30/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | ok | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903167406 KB0247 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE SHO WHITE/BLACK |  | SS27-STX
ADIDAS | 0903167413-1 LC7300 | WHITE | 90D | S2725M926A | 354 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903167413 LC7300 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167435-1 LF0727 | BLACK | 120D | S2754MAS510B | 884 | 30/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167435 LF0727 | 24/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903167477-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 770 | 2026-07-12 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167477 LH3759 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903167515-1 LC7300 | WHITE | 90D | S2725M926A | 100 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 800187 | PRINT L1 SUB PROCESS_V3 | 0903167515 LC7300 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA |  | MONO TREFOIL WHITE |  | SS27-STX
ADIDAS | 0903167539-1 KY5866 | BLACK | 90D | S2750MTR052 | 100 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903167539 KY5866 | 2026-10-09 | KAHATEX CIJERAH | VIETNAM | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167578-1 KY5866 | BLACK | 90D | S2750MTR052 | 1639 | 15/11/2026 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903167578 KY5866 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903167656-1 LC6583 | GREY | 105D | S2750MTR051 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | T2 Hua Feng, material quality issues (shading, creasemark), PI Date 01-Aug, actual receives 08-Sep (100% QC panel). 838103 | HT SUB PROCESS_V1 | 0903167656 LC6583 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D4T ESS T GREY |  | SS27-TI
ADIDAS | 0903167699-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 100 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903167699 KD5507 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903167750-1 KA4331 | BLACK | 90D | S2608MR0902 | 668 | 15/12/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903167750 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903167765-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 536 | 2026-07-11 |  | SI | SI26/06/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 29-Jul, actual receives 04-Sep. T2 Formosa, PI Date 26-Jul, actual receives 06-Aug. T2 Libolon, PI Date 22-Jul, actual receives 22-Jul. 516267 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903167765 KV7863 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903167819-1 KA4331 | BLACK | 90D | S2608MR0902 | 418 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (25/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 25-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? 516400 | PAD+HT SUB PROCESS_V3 | 0903167819 KA4331 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903167866-1 LG9675 | BLACK | 120D | S2754WAS513C | 530 | 2026-07-11 |  | SI | SI26/06/2026 |  | PANTS |  | (18/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903167866 LG9675 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903167978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 344 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903167978 LD5446 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903168007-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1036 | 15/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | ok | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903168007 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903168036-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 707 | 15/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | ok | 516400 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903168036 KC8152 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903168237-1 KA3530 | BLACK | 105D | S2650MTR402 | 224 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903168237 KA3530 | 24/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | WE FR T BLACK |  | SS27-TI
ADIDAS | 0903169208-1 KU8975 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTW534 | 320 | 23/11/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (20/08/2026) | (08/08/2026) | Waiting fabric. T2 Gistex, PI Date 20-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 12-Aug, ETD ?? Waiting fabric. T2 Shinih, PI Date 24-Jul, ETD ?? Waiting fabric. T2 Libolon, PI Date 23-Jul, ETD ?? 516333 | PRINT L2+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903169208 KU8975 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W ESS RV BOMBER BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 0903169300-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 150 | 2026-07-11 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 800187 | PAD+HT SUB PROCESS_V3 | 0903169300 KD5507 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903169676-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 310 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L1 SUB PROCESS_V3 | 0903169676 LC7301 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903169815-1 KY5866 | BLACK | 90D | S2750MTR052 | 259 | 2026-07-11 |  | SI | SI26/06/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Gistex, PI Date 21-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903169815 KY5866 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | D18T ESS SHORTS BLACK |  | SS27-TI
ADIDAS | 0903170004-1 LC7301 | COLLEGIATE BURGUNDY | 90D | S2725M926A | 100 | 15/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | ok | ok | 838103 | PRINT L1 SUB PROCESS_V3 | 0903170004 LC7301 | 2026-10-09 | KAHATEX CIJERAH | MALAYSIA | SEA |  | MONO TREFOIL COLLEGIATE BURGUNDY |  | SS27-STX
ADIDAS | 0903171050-1 KD5507 | GREY FIVE F17 | 105D | S2650MTR402 | 600 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (27/07/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Jul, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903171050 KD5507 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T GREY FIVE F17 |  | SS27-TI
ADIDAS | 0903171134-1 KS3009 | BLACK/PURE RUBY S25 | 90D | S2615KSWJ751 | 222 | 15/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903171134 KS3009 | 2026-10-09 | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T BLACK/PURE RUBY S25 |  | SS27-STX
ADIDAS | 0903173165-1 KE9633 | BLACK | 105D | S2650MTR810B | 243 | 15/11/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (02/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 02-Aug, ETD ?? Waiting fabric. T2 Sue's, PI Date 28-Jul, ETD ?? 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903173165 KE9633 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHES 2in1 SHO BLACK |  | SS27-TI
ADIDAS | 0903173400-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 1400 | 30/11/2026 |  | SI | SI26/06/2026 |  | PANTS |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 29-Jul, ETD ?? 516439 | PRINT L3+PPA SUB PROCESS_V3 | 0903173400 LH3759 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903173451-1 LG9669 | BLACK | 120D | S2754WAS514C | 348 | 2026-07-12 |  | ID | ID26/06/2026 |  | SKIRT |  | (11/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 11-Aug, ETD ?? 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903173451 LG9669 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903194097-1 LC6790 | HAZE CORAL S17 | 120D | S2608WR0202 | 533 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194097 LC6790 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903194102-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194102 KR3066 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194106-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 415 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194106 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194111-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 320 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194111 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194112-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 329 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194112 KY9384 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903194125-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 100 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194125 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194126-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 289 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194126 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194127-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 221 | 2026-07-11 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194127 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194129-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 1331 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194129 KY9391 | 28/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903194131-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 616 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194131 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903194134-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1011 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194134 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903194139-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1080 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194139 KR3066 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903194143-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 262 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194143 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194144-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 145 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194144 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903194289-1 IN1157 | WHITE | 90D | S2408MR1600 | 120 | 15/12/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194289 IN1157 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194291-1 IN1156 | BLACK | 90D | S2408MR1600 | 181 | 15/12/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | (07/08/2026) | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194291 IN1156 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194292-1 IN1172 | BLACK | 90D | S2408WR1600 | 112 | 15/12/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903194292 IN1172 | 14/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194320-1 KG8547 | ONIX | 90D | S2408WR1600 | 224 | 30/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194320 KG8547 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194322-1 KT4840 | ONIX | 90D | S2408MR1600 | 212 | 30/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 838103 | HT SUB PROCESS_V1 | 0903194322 KT4840 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194348-1 KT4840 | ONIX | 90D | S2408MR1600 | 243 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194348 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194350-1 KG8547 | ONIX | 90D | S2408WR1600 | 365 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194350 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194353-1 KG8547 | ONIX | 90D | S2408WR1600 | 308 | 2026-07-11 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194353 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194355-1 KG8547 | ONIX | 90D | S2408WR1600 | 235 | 23/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194355 KG8547 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194359-1 KT4840 | ONIX | 90D | S2408MR1600 | 414 | 23/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903194359 KT4840 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903194450-1 KA6229 | BLACK | 120D | S2608WR0202 | 354 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194450 KA6229 | 28/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903194470-1 KA6229 | BLACK | 120D | S2608WR0202 | 130 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 28-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903194470 KA6229 | 28/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903194986-1 LE8187 | BLACK | 105D | S2754MAS513-MTF | 105 | 15/12/2026 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric (Airowes). T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? 650034 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903194986 LE8187 | 24/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903195079-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 177 | 2026-07-11 |  | AN | AN26/06/2026 |  | PANTS |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 03-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 19-Jul (PO NT-365). 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195079 LF0718 | 24/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903195509-1 LG9664 | LEGEND IVY S19 | 120D | S2754WAS512C | 221 | 2026-07-11 |  | SA | SA30/06/2026 |  | JACKET |  | (23/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 23-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903195509 LG9664 | 28/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903196029-1 IN1156 | BLACK | 90D | S2408MR1600 | 200 | 2026-07-11 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 960006 | HT SUB PROCESS_V1 | 0903196029 IN1156 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903197367-1 KT4839 | ONIX | 90D | S2408MR1601 | 236 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 839055 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197367 KT4839 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197369-1 KG8549 | ONIX | 90D | S2408WR1601A | 265 | 2026-07-12 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197369 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197373-1 KT4839 | ONIX | 90D | S2408MR1601 | 317 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197373 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197374-1 KG8549 | ONIX | 90D | S2408WR1601A | 160 | 2026-07-12 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 839055 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197374 KG8549 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197375-1 KA4331 | BLACK | 90D | S2608MR0902 | 184 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960026 | PAD+HT SUB PROCESS_V3 | 0903197375 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903197377-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 204 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197377 KX9851 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197378-1 KG8549 | ONIX | 90D | S2408WR1601A | 116 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197378 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197380-1 KG8549 | ONIX | 90D | S2408WR1601A | 154 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197380 KG8549 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197384-1 KT4839 | ONIX | 90D | S2408MR1601 | 237 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197384 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197385-1 KT4839 | ONIX | 90D | S2408MR1601 | 400 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197385 KT4839 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197391-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 100 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197391 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197393-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 148 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 839055 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197393 LD0908 | 14/09/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197395-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 2026-07-11 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903197395 LD0278 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903197397-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197397 LD0293 | 14/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197399-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 190 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197399 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197401-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 305 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197401 LD0908 | 14/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197403-1 LD0908 | SILVER BLUE S27 | 90D | S2608WR0902 | 380 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197403 LD0908 | 14/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903197405-1 KG8549 | ONIX | 90D | S2408WR1601A | 181 | 15/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197405 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197406-1 KT4839 | ONIX | 90D | S2408MR1601 | 188 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 1st Art (TC 10 pcs) 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197406 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197408-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 8 | 15/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (KN GLT). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 1st Art (TC 10 pcs) 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197408 IT1467 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903197410-1 KA4331 | BLACK | 90D | S2608MR0902 | 200 | 23/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (26/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903197410 KA4331 | 14/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903197411-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 102 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 650036 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197411 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197413-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 182 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric (Damco offline). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197413 KX9851 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197415-1 KU7520 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1601A | 116 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197415 KU7520 | 14/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903197416-1 KG8549 | ONIX | 90D | S2408WR1601A | 282 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197416 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197418-1 KG8549 | ONIX | 90D | S2408WR1601A | 254 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197418 KG8549 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197420-1 KT4839 | ONIX | 90D | S2408MR1601 | 233 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197420 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197422-1 KT4839 | ONIX | 90D | S2408MR1601 | 134 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (22/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197422 KT4839 | 14/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903197423-1 KA0248 | MEDIUM GREY HEATHER | 90D | S2608WR0902 | 514 | 30/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (27/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 05-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197423 KA0248 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903197467-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 478 | 15/11/2026 | 478 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 07-Oct. T2 New Wide, PI Date 25-Sep, actual receives 10-Sep. T2 Grand tex, PI Date 18-Sep, actual receives 09-Sep. 1st Art (TC 10 pcs) 659018 | PAD+HT SUB PROCESS_V3 | 0903197467 LD0278 | 14/09/2026 | KAHATEX CIJERAH | COLOMBIA | SEA | 26/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 26/11/2026 | 30/11/2026 |  |  | 478 |  | 478 |  |  | 23/11/2026 | 25/11/2026 |  |  | 478 |  | 478 |  |  | 20/11/2026 | 24/11/2026 |  |  | 478 |  | 478
ADIDAS | 0903197470-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 708 | 30/11/2026 | 708 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 20-Oct. Waiting fabric. T2 Grand Tex, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 25-Sep. 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197470 LD0293 | 14/09/2026 | KAHATEX CIJERAH | CHILE | SEA | 18/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 18/11/2026 | 21/11/2026 |  |  | 708 |  | 708 |  |  | 13/11/2026 | 18/11/2026 |  |  | 708 |  | 708 |  |  | 2026-10-11 | 13/11/2026 |  |  | 708 |  | 708
ADIDAS | 0903197491-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 118 | 15/11/2026 | 118 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 07-Oct. T2 New Wide, PI Date 25-Sep, actual receives 10-Sep. T2 Grand tex, PI Date 18-Sep, actual receives 09-Sep. 834012 | PAD+HT SUB PROCESS_V3 | 0903197491 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA | 26/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 26/11/2026 | 30/11/2026 |  |  | 118 |  | 118 |  |  | 23/11/2026 | 25/11/2026 |  |  | 118 |  | 118 |  |  | 20/11/2026 | 24/11/2026 |  |  | 118 |  | 118
ADIDAS | 0903197493-1 LD0293 | SEMI SOLAR AQUA S27 | 90D | S2608WR0901 | 676 | 30/11/2026 | 676 | SI | SI30/06/2026 | G1A | SHORTS | G1 |  |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 20-Oct. Waiting fabric. T2 Grand Tex, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 25-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197493 LD0293 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 18/11/2026 | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX | 18/11/2026 | 21/11/2026 |  |  | 676 |  | 676 |  |  | 13/11/2026 | 18/11/2026 |  |  | 676 |  | 676 |  |  | 2026-10-11 | 13/11/2026 |  |  | 676 |  | 676
ADIDAS | 0903197502-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 653 | 15/11/2026 | 653 | SA | SA30/06/2026 | G1F | SHORTS | G1 |  |  | Waiting fabric. DRC 0064-T2 Far Eastern, PI Date 07-Oct. T2 New Wide, PI Date 25-Sep, actual receives 10-Sep. T2 Grand tex, PI Date 18-Sep, actual receives 09-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903197502 LD0278 | 14/09/2026 | KAHATEX CIJERAH | ARGENTINA | SEA | 26/11/2026 | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX | 26/11/2026 | 30/11/2026 |  |  | 653 |  | 653 |  |  | 23/11/2026 | 25/11/2026 |  |  | 653 |  | 653 |  |  | 20/11/2026 | 24/11/2026 |  |  | 653 |  | 653
ADIDAS | 0903197750-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 738 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197750 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903197752-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 951 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197752 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903197755-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 749 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197755 KY9391 | 28/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903197765-1 KZ1305 | VISTA GREEN S14 | 105D | S2608MR0201B | 104 | 15/12/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Grand tex, PI Date 11-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197765 KZ1305 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903197780-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 964 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197780 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197782-1 KZ1331 | OLIVE TWO S27 | 105D | S2608WR0201A | 1337 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (22/08/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 22-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 11-Aug, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197782 KZ1331 | 28/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903197791-1 LF9775 | SILVER LEAF S27 | 120D | S2608MR0201 | 303 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197791 LF9775 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER LEAF S27 |  | SS27-TRAX
ADIDAS | 0903197802-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 321 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197802 KY9393 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903197832-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 367 | 23/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197832 KY9385 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903197837-1 JZ7711 | BLACK | 120D | S2608MR0202 | 379 | 2026-07-11 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197837 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197843-1 JZ7711 | BLACK | 120D | S2608MR0202 | 622 | 2026-07-11 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197843 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197845-1 JZ7711 | BLACK | 120D | S2608MR0202 | 322 | 2026-07-11 |  | SA | SA30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197845 JZ7711 | 28/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903197882-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 304 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug. Waiting fabric. T2 Y.R.C, PI Date 10-Aug. Waiting fabric. T2 Best Pacific, PI Date 09-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903197882 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903203174-1 KB5960 | WHITE | 120D | S2608MR0900A | 108 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903203174 KB5960 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903208401-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 100 | 23/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903208401 KX9855 | 17/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208402-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 168 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903208402 KX9855 | 17/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208403-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 182 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903208403 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208404-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 102 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Cargoport). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650036 | HT SUB PROCESS_V1 | 0903208404 KX9855 | 17/09/2026 | KAHATEX CIJERAH | PARAGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208405-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 170 | 30/11/2026 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Airowes). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 650034 | HT SUB PROCESS_V1 | 0903208405 KX9855 | 17/09/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208406-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 332 | 2026-07-12 |  | SI | SI03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516443 | HT SUB PROCESS_V1 | 0903208406 KX9855 | 17/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903208438-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 252 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 830009 | HT SUB PROCESS_V1 | 0903208438 KG8548 | 17/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903208439-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 474 | 15/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903208439 KG8548 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209753-1 IN1156 | BLACK | 90D | S2408MR1600 | 640 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 03-Aug, ETD ?? 512107 | HT SUB PROCESS_V1 | 0903209753 IN1156 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209759-1 IN1157 | WHITE | 90D | S2408MR1600 | 253 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 21-Sep. Waiting fabric. T2 Y.T.I, Mesh: ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209759 IN1157 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209771-1 IN1172 | BLACK | 90D | S2408WR1600 | 100 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209771 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209776-1 KG8547 | ONIX | 90D | S2408WR1600 | 234 | 30/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 680014 | HT SUB PROCESS_V1 | 0903209776 KG8547 |  | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209793-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 120 | 15/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512107 | HT SUB PROCESS_V1 | 0903209793 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209794-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 418 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209794 KX9838 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209795-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 100 | 23/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 512110 | HT SUB PROCESS_V1 | 0903209795 KX9838 | 21/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209796-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 234 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 680014 | HT SUB PROCESS_V1 | 0903209796 KX9838 | 21/09/2026 | KAHATEX CIJERAH | BOLIVIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209797-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 342 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric (Damco offline). T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 688010 | HT SUB PROCESS_V1 | 0903209797 KX9838 | 21/09/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209798-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 9675 | 15/12/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Eastern, Body PI Date 21-Sep (6999 yd). T2 Fu Hsun, Mesh PI Date 03-Aug, ETD ?? Waiting fabric. T2 Y.T.I, Body: ETD 10-Jul, ETA-Kaha 08-Aug (2017 yd). 814006 | HT SUB PROCESS_V1 | 0903209798 KX9838 | 21/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903209807-1 IN1173 | WHITE | 90D | S2408WR1600 | 427 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 512107 | HT SUB PROCESS_V1 | 0903209807 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209905-1 IN1173 | WHITE | 90D | S2408WR1600 | 338 | 2026-07-12 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903209905 IN1173 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209906-1 IN1172 | BLACK | 90D | S2408WR1600 | 321 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903209906 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209908-1 KZ2984 | SOLAR TURBO F26 | 90D | S2408WR1600 | 511 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903209908 KZ2984 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903209909-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 341 | 30/11/2026 |  | SA | SA07/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516342 | HT SUB PROCESS_V1 | 0903209909 KG8548 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903244360-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 404 | 2026-07-12 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903244360 LF0718 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903245450-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 300 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 680015 | HT+PAD SUB PROCESS_V3 | 0903245450 KB5961 | 2026-08-10 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245476-1 KB5965 | BLACK | 120D | S2608MR0900A | 800 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245476 KB5965 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903245499-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 960006 | PAD+HT SUB PROCESS_V3 | 0903245499 KA4331 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903245532-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 600 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903245532 KB5959 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903248693-1 LG9666 | BLACK | 120D | S2754WAS512C | 560 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? s516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903248693 LG9666 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903248718-1 LG9675 | BLACK | 120D | S2754WAS513C | 371 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903248718 LG9675 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903248892-1 KG3189 | MAROON | 120D | S2608MR0900A | 699 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248892 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903248948-1 KG3189 | MAROON | 120D | S2608MR0900A | 453 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903248948 KG3189 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903249143-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 600000 | HT+PAD SUB PROCESS_V3 | 0903249143 KX3655 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903250899-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903250899 LG9665 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903250925-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 322 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903250925 LG9668 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903251000-1 KG3189 | MAROON | 120D | S2608MR0900A | 123 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251000 KG3189 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251073-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 1204 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 848012 | HT+PAD SUB PROCESS_V3 | 0903251073 KB5961 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903251123-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 311 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251123 LE8188 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903251133-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1072 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903251133 KX3655 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903251145-1 KA0246 | BLACK | 105D | S2608WR0902 | 132 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251145 KA0246 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251361-1 KB5960 | WHITE | 120D | S2608MR0900A | 292 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 516443 | HT+PAD SUB PROCESS_V3 | 0903251361 KB5960 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903251430-1 KA0246 | BLACK | 105D | S2608WR0902 | 309 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251430 KA0246 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251511-1 KA0246 | BLACK | 105D | S2608WR0902 | 1186 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251511 KA0246 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903251558-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 321 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251558 LD0908 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251577-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 298 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251577 LD0908 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903251656-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 148 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903251656 KX0123 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903251702-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251702 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251884-1 LF0723 | BLACK | 105D | S2754MAS511B | 297 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251884 LF0723 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903251890-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 144 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251890 LG9665 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903251904-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903251904 LG9666 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903251913-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 2026-07-12 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 512108 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903251913 IN1159 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903251930-1 KG3189 | MAROON | 120D | S2608MR0900A | 1103 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903251930 KG3189 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903251931-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 124 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903251931 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903251968-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 140 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903251968 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903252016-1 IS1413 | BLACK | 60D | S2425M405 | 1810 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252016 IS1413 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252017-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 265 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 848024 | HT+PAD SUB PROCESS_V3 | 0903252017 KB5961 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252024-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 158 | 2026-07-12 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252024 LG9661 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903252038-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1900 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 960006 | PRINT L3 SUB PROCESS_V3 | 0903252038 IU0217 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903252073-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 928 | 2026-07-11 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252073 JE0052 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252080-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252080 LG9661 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903252095-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1760 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252095 JD5302 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903252110-1 LF0727 | BLACK | 120D | S2754MAS510B | 116 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252110 LF0727 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903252125-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 1028 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903252125 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903252133-1 LG9666 | BLACK | 120D | S2754WAS512C | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903252133 LG9666 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903252140-1 JZ7711 | BLACK | 120D | S2608MR0202 | 194 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252140 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903252145-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1020 | 2026-07-11 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903252145 JE0055 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903252505-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 140 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 848012 | HT+PAD SUB PROCESS_V3 | 0903252505 KB5961 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903252541-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903252541 KD3854 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903252572-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 272 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903252572 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903252598-1 KG8547 | ONIX | 90D | S2408WR1600 | 118 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903252598 KG8547 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903252991-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 120 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903252991 KY5900 | 2026-08-10 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253066-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 542 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug. Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ETA-Kaha 07-Aug. 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253066 LD0908 | 2026-08-10 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903253138-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 381 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric. T2 Far Easten, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903253138 KY5900 | 2026-08-10 | KAHATEX CIJERAH | THAILAND | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253152-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 130 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903253152 LH3760 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253168-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 129 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903253168 LD0278 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253208-1 KD3875 | BLACK | 120D | S2608WR0201 | 108 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253208 KD3875 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903253313-1 KC5231 | HALO SILVER S21/WHITE | 90D | S2554WES421WV | 406 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? Waiting fabric. T2 LIbolon, (Body) PI Date 04-Aug, ETD ?? 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903253313 KC5231 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903253357-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 160 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253357 LF0729 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903253378-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 140 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903253378 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903253434-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 600 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903253434 IN0088 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903253436-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 490 | 2026-07-11 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903253436 JE6338 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903253467-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 512107 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253467 LG9663 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903253486-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 186 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903253486 KX3655 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253492-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253492 LH3760 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903253500-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 378 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253500 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253505-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 140 | 2026-07-12 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253505 KY9385 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903253511-1 LH3758 | BLACK | 120D | S2754WAS518B | 150 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512107 | PRINT L3+PPA SUB PROCESS_V3 | 0903253511 LH3758 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903253522-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 462 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516342 | HT SUB PROCESS_V1 | 0903253522 KX9855 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903253561-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 506 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | TRAX (MOQ Issue)-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253561 LD0909 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903253570-1 IN1157 | WHITE | 90D | S2408MR1600 | 150 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512108 | HT SUB PROCESS_V1 | 0903253570 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903253631-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 226 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Damco offline). T2 Far Easten, PI Date 25-Aug. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 688010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253631 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903253640-1 KU2430 | WHITE | 60D | S27FBGFXP510 | 356 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 516342 | PRINT L2+PAD SUB PROCESS_V3 | 0903253640 KU2430 | 26/08/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M FB NOVELTY T WHITE |  | SS27
ADIDAS | 0903253647-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 1 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253647 LK8779 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903253720-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. DRC 0064-T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903253720 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903253727-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 220 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253727 LE8181 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903253750-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 322 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903253750 KX3655 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903253760-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 268 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903253760 KX3650 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903253781-1 IL7232 | BLACK | 105D | S2408MR3202 | 800 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 826010 | PAD+HT SUB PROCESS_V3 | 0903253781 IL7232 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903253837-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 131 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903253837 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903253843-1 IN1156 | BLACK | 90D | S2408MR1600 | 150 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512108 | HT SUB PROCESS_V1 | 0903253843 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903253866-1 IN8707 | BLACK | 105D | S2408WR1601A | 150 | 2026-07-12 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 512108 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253866 IN8707 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903253892-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 1513 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903253892 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903253913-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 361 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903253913 KD3854 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903253950-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 190 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903253950 LD0278 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903253954-1 KB5960 | WHITE | 120D | S2608MR0900A | 230 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903253954 KB5960 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903253973-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 321 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903253973 LG9661 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903253978-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903253978 HK7303 |  | KAHATEX CIJERAH | TURKEY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903254007-1 LF0727 | BLACK | 120D | S2754MAS510B | 1051 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254007 LF0727 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254012-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254012 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903254059-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 109 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903254059 KX3655 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903254074-1 KG8548 | SOLAR TURBO F26 | 90D | S2408MR1600 | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254074 KG8548 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254093-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 290 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254093 KY9385 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254128-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 300 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903254128 JE6338 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903254135-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254135 KV7963 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903254152-1 LF0727 | BLACK | 120D | S2754MAS510B | 227 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254152 LF0727 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254162-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 220 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254162 JW7182 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903254186-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903254186 KD3911 |  | KAHATEX CIJERAH | TURKEY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903254208-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512108 | HT+PAD SUB PROCESS_V3 | 0903254208 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254210-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 200 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 980004 | EMBRO SUB PROCESS_V1 | 0903254210 KD3911 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | RELEASED |  | SS27
ADIDAS | 0903254229-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 151 | 15/12/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254229 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903254234-1 KG3189 | MAROON | 120D | S2608MR0900A | 130 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512109 | HT+PAD SUB PROCESS_V3 | 0903254234 KG3189 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254258-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 160 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254258 LI7657 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903254259-1 KG3189 | MAROON | 120D | S2608MR0900A | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512107 | HT+PAD SUB PROCESS_V3 | 0903254259 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903254263-1 IN1156 | BLACK | 90D | S2408MR1600 | 118 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903254263 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254271-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254271 IS1413 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254283-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 120 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254283 LI7656 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903254284-1 LH3758 | BLACK | 120D | S2754WAS518B | 125 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 826010 | PRINT L3+PPA SUB PROCESS_V3 | 0903254284 LH3758 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903254294-1 IN1173 | WHITE | 90D | S2408WR1600 | 122 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254294 IN1173 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254297-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 980004 | PRINT L3 SUB PROCESS_V3 | 0903254297 IU0217 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903254305-1 KD3875 | BLACK | 120D | S2608WR0201 | 745 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254305 KD3875 | 2026-08-10 | KAHATEX CIJERAH | HONGKONG | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903254314-1 IN1172 | BLACK | 90D | S2408WR1600 | 147 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903254314 IN1172 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254316-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 120 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | ok | ok | 859013 | PRINT L2 SUB PROCESS_V3 | 0903254316 LI7658 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903254327-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 123 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254327 KV7863 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903254339-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 100 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254339 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903254342-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 160 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 859013 | PRINT L1 SUB PROCESS_V3 | 0903254342 LI7655 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903254352-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 100 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254352 LH3760 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254359-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 175 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254359 JE0052 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254392-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 320 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254392 JD5302 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903254416-1 IN1173 | WHITE | 90D | S2408WR1600 | 270 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254416 IN1173 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254417-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903254417 JE0055 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903254447-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 160 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 859013 | PRINT L3 SUB PROCESS_V3 | 0903254447 LI7660 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903254462-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 250 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254462 LG9661 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254473-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254473 KX8875 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903254483-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 78 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903254483 LH3760 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903254496-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 350 | 2026-01-11 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | EMBRO+PPA SUB PROCESS_V3 | 0903254496 KV0458 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903254500-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 68 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254500 LC6339 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903254523-1 LF0723 | BLACK | 105D | S2754MAS511B | 100 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | (06/08/2026) | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 838103 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254523 LF0723 | 2026-08-10 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903254528-1 LC6341 | BLACK | 90D | S27GMGFX130 | 32 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903254528 LC6341 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903254540-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 1120 | 30/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903254540 LF5052 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903254654-1 LF0718 | BLACK | 105D | S2754MAS512B | 367 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254654 LF0718 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903254668-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 14-Aug, ETD ?? 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254668 JM1772 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903254676-1 IN1156 | BLACK | 90D | S2408MR1600 | 111 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903254676 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254679-1 LF0727 | BLACK | 120D | S2754MAS510B | 557 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254679 LF0727 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254694-1 KB5965 | BLACK | 120D | S2608MR0900A | 200 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903254694 KB5965 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903254704-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 100 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254704 LD0908 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903254734-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903254734 LE4307 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903254737-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 159 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 516267 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254737 KY9385 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903254782-1 IN1172 | BLACK | 90D | S2408WR1600 | 915 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 547012 | HT SUB PROCESS_V1 | 0903254782 IN1172 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903254783-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 359 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254783 LG9663 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254813-1 JZ7711 | BLACK | 120D | S2608MR0202 | 169 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254813 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903254815-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 643 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254815 LG9663 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903254818-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 242 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903254818 LD0283 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903254834-1 LF0727 | BLACK | 120D | S2754MAS510B | 140 | 15/12/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254834 LF0727 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903254837-1 LG9666 | BLACK | 120D | S2754WAS512C | 941 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254837 LG9666 | 2026-08-10 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254839-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 116 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903254839 LD0293 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903254841-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 421 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254841 LG9661 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903254883-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903254883 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903254897-1 KB5960 | WHITE | 120D | S2608MR0900A | 361 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903254897 KB5960 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903254912-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 113 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254912 LF0721 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903254954-1 LG9675 | BLACK | 120D | S2754WAS513C | 137 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254954 LG9675 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903254957-1 LG9666 | BLACK | 120D | S2754WAS512C | 428 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903254957 LG9666 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903254971-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903254971 LG9668 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255002-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 18 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 516029 | PRINT L3+PPA SUB PROCESS_V3 | 0903255002 LG9670 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27-SPOMA
ADIDAS | 0903255006-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV-MTF | 226 | 15/12/2026 |  | AN | AN10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 03-Jul, actual receives 08-Aug. T2 Kahatex, PI Date 10-Aug, actual receives 28-Jul (PO NT-347). T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255006 KZ3198 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903255036-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 123 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903255036 KX3650 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255046-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255046 LG9665 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255047-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 1203 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903255047 KG3190 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903255075-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 600 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (08/08/2026) | ok | Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? 826010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903255075 KA4914 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903255082-1 LG9666 | BLACK | 120D | S2754WAS512C | 210 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255082 LG9666 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255105-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255105 LH3760 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255106-1 IN8707 | BLACK | 105D | S2408WR1601A | 347 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255106 IN8707 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903255126-1 LH3758 | BLACK | 120D | S2754WAS518B | 210 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903255126 LH3758 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903255128-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 220 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255128 LG9668 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903255132-1 LH4535 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS421WV | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255132 LH4535 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 64 AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903255138-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255138 KX0123 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903255194-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 716 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 20-Aug, ETD ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255194 LD0908 | 2026-08-10 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255241-1 KA0246 | BLACK | 105D | S2608WR0902 | 160 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (27/08/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 27-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 27-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 30-Jul, ETD 27-Jul, ET-Kaha 07-Aug. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255241 KA0246 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903255271-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 219 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903255271 KA0544 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903255297-1 JZ7711 | BLACK | 120D | S2608MR0202 | 101 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255297 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255324-1 IN1157 | WHITE | 90D | S2408MR1600 | 493 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255324 IN1157 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255351-1 KA4331 | BLACK | 90D | S2608MR0902 | 158 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 512106 | PAD+HT SUB PROCESS_V3 | 0903255351 KA4331 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255381-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 101 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 848016 | HT+PAD SUB PROCESS_V3 | 0903255381 KB5961 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903255416-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 330 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903255416 JE6419 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903255444-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 850 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 29-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255444 JM1775 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903255455-1 IN1157 | WHITE | 90D | S2408MR1600 | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903255455 IN1157 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255472-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 116 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255472 LG9663 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903255484-1 KA4331 | BLACK | 90D | S2608MR0902 | 546 | 2026-07-12 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255484 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255493-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 301 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255493 LG9665 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255505-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A-MTF | 2661 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255505 KX3650 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255516-1 KA4331 | BLACK | 90D | S2608MR0902 | 763 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903255516 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255519-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 202 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903255519 KF5311 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903255537-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 943 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255537 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903255538-1 IN1159 | BLACK | 90D | S2408MR1601 | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255538 IN1159 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903255541-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 766 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903255541 KY5935 | 27/08/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255547-1 KA4331 | BLACK | 90D | S2608MR0902 | 4004 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255547 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255551-1 KD3875 | BLACK | 120D | S2608WR0201 | 131 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255551 KD3875 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903255562-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 4122 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 672027 | HT+PAD SUB PROCESS_V3 | 0903255562 KX3655 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255576-1 KA4331 | BLACK | 90D | S2608MR0902 | 3363 | 2026-07-12 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903255576 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903255600-1 KY5935 | SEMI SOLAR AQUA S27 | 135D | S2650MTR412 | 252 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 13-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 839062 | PAD+HT SUB PROCESS_V3 | 0903255600 KY5935 | 27/08/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | WE BAS WV SHO SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255606-1 KT4840 | ONIX | 90D | S2408MR1600 | 105 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903255606 KT4840 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903255609-1 JE6341 | DARK BLUE/WHITE | 90D | S2554MESS601FT | 472 | 2026-07-11 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903255609 JE6341 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903255612-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 137 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255612 LG9665 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255624-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 800 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 839055 | HT+PAD SUB PROCESS_V3 | 0903255624 KX3655 | 2026-08-10 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903255629-1 JZ7711 | BLACK | 120D | S2608MR0202 | 139 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255629 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255640-1 LF0727 | BLACK | 120D | S2754MAS510B | 260 | 30/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255640 LF0727 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255641-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255641 JW9678 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255645-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 289 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 547012 | HT+PAD SUB PROCESS_V3 | 0903255645 KX3654 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903255672-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 194 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255672 LG9665 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255675-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903255675 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903255687-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 848 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 960006 | HT SUB PROCESS_V1 | 0903255687 JW9678 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903255711-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255711 LF0726 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903255718-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 546 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255718 KY9384 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903255755-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 687 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255755 LG9674 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903255780-1 LG9666 | BLACK | 120D | S2754WAS512C | 285 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255780 LG9666 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903255825-1 LG9669 | BLACK | 120D | S2754WAS514C | 270 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903255825 LG9669 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903255856-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 152 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 848016 | HT+PAD SUB PROCESS_V3 | 0903255856 KB5961 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903255884-1 LC8882 | BLACK | 90D | S27SPRMGFXP0600-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 512108 | PRINT L3+PAD SUB PROCESS_V3 | 0903255884 LC8882 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M ADI RETRO T BLACK |  | SS27
ADIDAS | 0903255888-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1370 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255888 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903255911-1 IN2961 | BLACK | 105D | S2408WR2400 | 1200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903255911 IN2961 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903255932-1 KY5900 | SEMI SOLAR AQUA S27 | 105D | S2650MTR402 | 212 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  |  | ok | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date ?? 800005 | PAD+HT SUB PROCESS_V3 | 0903255932 KY5900 | 2026-08-10 | KAHATEX CIJERAH | INDONESIA | SEA |  | WE FR T SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903255936-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255936 LF0729 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903255945-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 568 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903255945 LD0292 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903255947-1 LF0727 | BLACK | 120D | S2754MAS510B | 410 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903255947 LF0727 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903255991-1 LF5052 | TEAM NAVY BLUE 2/WHITE | 90D | S2615KSWJ751 | 100 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | (NYK warehouse). 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903255991 LF5052 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | J SERE T TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903256003-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903256003 LG9665 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903256019-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 136 | 2026-07-11 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256019 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256028-1 LG9669 | BLACK | 120D | S2754WAS514C | 291 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903256028 LG9669 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903256109-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1043 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256109 KX3654 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903256111-1 IN8707 | BLACK | 105D | S2408WR1601A | 104 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256111 IN8707 | 2026-08-10 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903256140-1 KT7396 | TEAM NAVY BLUE 2 | 90D | F2625M101 | 2846 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903256140 KT7396 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG TEE TEAM NAVY BLUE 2 |  | SS27-L2L
ADIDAS | 0903256178-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 168 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (KN GLT). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 650028 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256178 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903256236-1 KZ0923 | KHAKI THREE F26/WHITE | 90D | S2754WESS421WV | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256236 KZ0923 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO 34 KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903256262-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 803 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 834012 | HT+PAD SUB PROCESS_V3 | 0903256262 KB5959 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256285-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 137 | 2026-07-12 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256285 LD0292 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903256378-1 KB5960 | WHITE | 120D | S2608MR0900A-MTF | 343 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903256378 KB5960 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256533-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 132 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903256533 KB5959 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903256569-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 120 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256569 LD0292 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903256590-1 IZ0443 | WONDER BLUE F23 | 45D | F24KLKGFX003 | 200 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903256590 IZ0443 |  | KAHATEX CIJERAH | TURKEY | SEA |  | POS TABLE LK |  | SS27
ADIDAS | 0903256615-1 JM1773 | DARK BLUE/WHITE | 90D | F2554MESS712WV | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Libolon, PI Date 14-Aug, actual receives 15-Aug. 1st Art (TC 10 pcs) 826010 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256615 JM1773 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903256636-1 LD0283 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0900-MTF | 103 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903256636 LD0283 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee W SEMI SOLAR VIOLET S27 |  | SS27-TI
ADIDAS | 0903256674-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 451 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Jiale, PI Date 20-Jul, actual receives 08-Jul. 516421 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903256674 KD0738 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903256695-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 384 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256695 KY4155 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903256734-1 KA6229 | BLACK | 120D | S2608WR0202 | 1009 | 30/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256734 KA6229 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903256808-1 KD3875 | BLACK | 120D | S2608WR0201 | 203 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256808 KD3875 | 2026-08-10 | KAHATEX CIJERAH | SPAIN | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256830-1 KD3875 | BLACK | 120D | S2608WR0201 | 454 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256830 KD3875 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256862-1 KD3875 | BLACK | 120D | S2608WR0201 | 603 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256862 KD3875 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903256873-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 113 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256873 KD3854 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903256925-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 226 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903256925 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903256933-1 JZ7711 | BLACK | 120D | S2608MR0202 | 686 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256933 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256939-1 JZ7711 | BLACK | 120D | S2608MR0202 | 319 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256939 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256944-1 KT4840 | ONIX | 90D | S2408MR1600 | 149 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903256944 KT4840 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903256969-1 KZ3066 | BLACK | 90D | S2762LHMEDR106K | 105 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | PRINT L1 SUB PROCESS_V3 | 0903256969 KZ3066 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903256981-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 120 | 2026-07-11 |  | SI | SI10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903256981 KV8005 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903256982-1 JZ7711 | BLACK | 120D | S2608MR0202 | 323 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903256982 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903256990-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 120 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903256990 KX9838 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903256991-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 250 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903256991 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903257000-1 JZ7711 | BLACK | 120D | S2608MR0202 | 556 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257000 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257005-1 KZ3208 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS422WV-MTF | 160 | 2026-07-12 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 06-Aug, ETD ?? Waiting fabric. T2 Formosa, PI Date 10-Aug, ETD 10-Aug, ETA KH 21-Aug. 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257005 KZ3208 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903257035-1 JZ7711 | BLACK | 120D | S2608MR0202 | 300 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257035 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257067-1 JZ7711 | BLACK | 120D | S2608MR0202 | 378 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257067 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257069-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 102 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257069 KX3655 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257106-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1785 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257106 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903257118-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 150 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257118 KY9385 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257136-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257136 LF0729 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903257138-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 318 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257138 KY9384 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903257149-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 200 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903257149 KX3654 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257153-1 LG9675 | BLACK | 120D | S2754WAS513C | 727 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 834012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257153 LG9675 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903257175-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 182 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257175 KY9385 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903257206-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 100 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 512108 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903257206 KY5988 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903257224-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 292 | 2026-07-12 |  | SA | SA10/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903257224 LD0277 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903257256-1 IK7442 | WHITE | 105D | S2408WR2400 | 600 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 826010 | HT SUB PROCESS_V1 | 0903257256 IK7442 | 2026-08-10 | KAHATEX CIJERAH | TURKEY | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903257282-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 267 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512102 | HT+PAD SUB PROCESS_V3 | 0903257282 KX3654 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903257305-1 KA4331 | BLACK | 90D | S2608MR0902 | 317 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 547012 | PAD+HT SUB PROCESS_V3 | 0903257305 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257308-1 LF0718 | BLACK | 105D | S2754MAS512B | 111 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257308 LF0718 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903257351-1 LK8779 | MYSTERY BROWN S17/ENERGY BLUE S17 | 120D | S2608MR0201 | 145 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257351 LK8779 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M MYSTERY BROWN S17/ENERGY BLUE S17 |  | SS27-TRAX
ADIDAS | 0903257417-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 452 | 2026-07-11 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L1 SUB PROCESS_V3 | 0903257417 LI7655 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903257458-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 239 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 512106 | HT+PAD SUB PROCESS_V3 | 0903257458 KB5961 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257584-1 LG9666 | BLACK | 120D | S2754WAS512C | 524 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257584 LG9666 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903257609-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 171 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903257609 LH3760 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257661-1 KA4331 | BLACK | 90D | S2608MR0902 | 1151 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257661 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257667-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 219 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903257667 LG9674 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903257674-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 599 | 2026-07-12 |  | SI | SI10/07/2026 |  | PANTS |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257674 KV7863 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903257681-1 IN1156 | BLACK | 90D | S2408MR1600 | 581 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903257681 IN1156 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257689-1 KA4331 | BLACK | 90D | S2608MR0902 | 1781 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516333 | PAD+HT SUB PROCESS_V3 | 0903257689 KA4331 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257711-1 KA4331 | BLACK | 90D | S2608MR0902 | 451 | 2026-07-12 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516394 | PAD+HT SUB PROCESS_V3 | 0903257711 KA4331 | 24/09/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257712-1 IN1173 | WHITE | 90D | S2408WR1600 | 540 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903257712 IN1173 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257721-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 230 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 547012 | HT+PAD SUB PROCESS_V3 | 0903257721 KX3650 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257743-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 109 | 15/12/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257743 KY9383 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903257757-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 244 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257757 KU7520 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903257770-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 322 | 2026-07-11 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257770 JE0055 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903257790-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 410 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257790 JE6417 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903257793-1 LE8187 | BLACK | 105D | S2754MAS513 | 397 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257793 LE8187 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903257797-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 148 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | Waiting fabric replacement. T2 Fu Hsun, material quality issues (shading), PI Date 14-Aug, ETD ?? (FOC 8293 yd). 547012 | HT+PAD SUB PROCESS_V3 | 0903257797 KB5961 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903257799-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 406 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257799 JE1309 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903257805-1 KZ1322 | KHAKI SIX F26/KHAKI THREE F26 | 120D | S2608MR0202 | 2388 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257805 KZ1322 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M KHAKI SIX F26/KHAKI THREE F26 |  | SS27-TRAX
ADIDAS | 0903257809-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 116 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848016 | HT SUB PROCESS_V1 | 0903257809 KX9838 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903257812-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 600 | 2026-07-12 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | 838103 | EMBRO+PPA SUB PROCESS_V3 | 0903257812 KY3737 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903257823-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 266 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848016 | HT+PAD SUB PROCESS_V3 | 0903257823 KX3655 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257827-1 HZ0747 | BLACK | 90D | F2325M414 | 1103 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/08/2026) |  | DRC 0090-early shipment customer (CRD Change). 834012 | EMBRO SUB PROCESS_V1 | 0903257827 HZ0747 | 24/09/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | PL TEE |  | SS27
ADIDAS | 0903257842-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 500 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960018 | HT+PAD SUB PROCESS_V3 | 0903257842 KX3655 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903257844-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 460 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Libolon, PI Date 14-Aug, actual receives 28-Aug. 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903257844 JM1776 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903257857-1 LF0723 | BLACK | 105D | S2754MAS511B | 1205 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257857 LF0723 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903257864-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 329 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903257864 LG9661 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903257865-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 578 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257865 KX3650 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257872-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 296 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903257872 LC6339 | 24/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903257890-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 126 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257890 KX9851 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903257921-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 157 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903257921 KX3650 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903257925-1 KA4331 | BLACK | 90D | S2608MR0902 | 253 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903257925 KA4331 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257930-1 KA4331 | BLACK | 90D | S2608MR0902 | 460 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  |  | ok | Waiting fabric. T2 Far Eastern, PI Date 26-Aug, ETD ?? Waiting fabric. T2 New Wide, PI Date 26-Aug, ETD ?? Waiting fabric. T2 Grand tex, PI Date 15-Aug, ETD ?? 516443 | PAD+HT SUB PROCESS_V3 | 0903257930 KA4331 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903257947-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 417 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 848012 | HT SUB PROCESS_V1 | 0903257947 KX9855 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903257949-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 800 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903257949 KD4872 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903257955-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 155 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257955 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903257981-1 IN1156 | BLACK | 90D | S2408MR1600 | 2281 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 516443 | HT SUB PROCESS_V1 | 0903257981 IN1156 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903257984-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 473 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903257984 LD0293 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258004-1 IN1173 | WHITE | 90D | S2408WR1600 | 314 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903258004 IN1173 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258033-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 142 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848024 | PRINT L3+PPA SUB PROCESS_V3 | 0903258033 LG9668 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903258038-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 183 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 980004 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258038 LF0726 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258065-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C | 242 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258065 LG9674 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903258100-1 IN1172 | BLACK | 90D | S2408WR1600 | 282 | 2026-07-12 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 516443 | HT SUB PROCESS_V1 | 0903258100 IN1172 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258102-1 LH3758 | BLACK | 120D | S2754WAS518B | 121 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPA SUB PROCESS_V3 | 0903258102 LH3758 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258117-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 160 | 15/12/2026 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | 859013 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258117 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903258123-1 LG9666 | BLACK | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258123 LG9666 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903258129-1 LF0727 | BLACK | 120D | S2754MAS510B | 140 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258129 LF0727 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903258144-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 116 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258144 KX9851 | 24/09/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258174-1 IL7232 | BLACK | 105D | S2408MR3202 | 684 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | ok | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? T2 Libolon, PI Date 04-Aug, actual receives 30-Jul. 547012 | PAD+HT SUB PROCESS_V3 | 0903258174 IL7232 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903258181-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 290 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258181 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903258192-1 LF0723 | BLACK | 105D | S2754MAS511B | 144 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258192 LF0723 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903258203-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 845 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO+PPA SUB PROCESS_V3 | 0903258203 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258204-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 360 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 547012 | PRINT L3+PAD SUB PROCESS_V3 | 0903258204 KA0544 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903258219-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 5500 | 2026-07-11 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258219 JD1877 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258228-1 KV0458 | BLACK/WHITE | 90D | S2754MESS659PQ | 115 | 2026-07-11 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO+PPA SUB PROCESS_V3 | 0903258228 KV0458 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS BLACK/WHITE |  | SS27-STX
ADIDAS | 0903258241-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 340 | 2026-07-11 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258241 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258249-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 319 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258249 KR3066 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258259-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 326 | 2026-07-11 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903258259 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903258280-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 5000 | 2026-07-11 |  | SA | SA10/07/2026 |  | JACKET |  | ok | ok | 823016 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903258280 JE6338 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903258290-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 305 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258290 KR3066 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903258291-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 711 | 15/11/2026 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO+PPA SUB PROCESS_V3 | 0903258291 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258294-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 300 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | ok | ok | (China). 825066 | PRINT L2 SUB PROCESS_V3 | 0903258294 LI7658 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903258324-1 KY3737 | WHITE/BLACK | 90D | S2754MESS659PQ | 115 | 2026-07-11 |  | SI | SI10/07/2026 |  | POLO SHIRT |  | (10/08/2026) | ok | (NYK warehouse). 800005 | EMBRO+PPA SUB PROCESS_V3 | 0903258324 KY3737 | 24/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M 3B PQ PS WHITE/BLACK |  | SS27-STX
ADIDAS | 0903258343-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 283 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258343 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903258404-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 461 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903258404 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258458-1 KT4840 | ONIX | 90D | S2408MR1600 | 887 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903258458 KT4840 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258484-1 KT4840 | ONIX | 90D | S2408MR1600 | 1410 | 2026-07-12 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 800187 | HT SUB PROCESS_V1 | 0903258484 KT4840 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258496-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 445 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L1 SUB PROCESS_V3 | 0903258496 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903258509-1 KT4840 | ONIX | 90D | S2408MR1600 | 611 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903258509 KT4840 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258534-1 KG8547 | ONIX | 90D | S2408WR1600 | 418 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 814006 | HT SUB PROCESS_V1 | 0903258534 KG8547 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258567-1 KT4840 | ONIX | 90D | S2408MR1600 | 470 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 814006 | HT SUB PROCESS_V1 | 0903258567 KT4840 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258605-1 KG8547 | ONIX | 90D | S2408WR1600 | 428 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 814006 | HT SUB PROCESS_V1 | 0903258605 KG8547 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258628-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 350 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L2 SUB PROCESS_V3 | 0903258628 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903258629-1 KG8547 | ONIX | 90D | S2408WR1600 | 303 | 2026-07-12 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 800187 | HT SUB PROCESS_V1 | 0903258629 KG8547 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903258682-1 LH3758 | BLACK | 120D | S2754WAS518B | 162 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258682 LH3758 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903258718-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258718 LE8188 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258746-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258746 LF0729 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903258772-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 102 | 15/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903258772 LE8181 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903258820-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 147 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848024 | HT+PAD SUB PROCESS_V3 | 0903258820 KX3655 | 2026-08-10 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903258846-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 334 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903258846 LG9675 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903258904-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 261 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903258904 LD0293 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903258907-1 KB5965 | BLACK | 120D | S2608MR0900A | 789 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258907 KB5965 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903258933-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 556 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258933 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903258954-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 420 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 630001 | HT+PAD SUB PROCESS_V3 | 0903258954 KX3654 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903259058-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 1200 | 15/12/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903259058 JD1877 |  | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903259086-1 HZ0747 | BLACK | 90D | F2325M414 | 800 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 826010 | EMBRO SUB PROCESS_V1 | 0903259086 HZ0747 |  | KAHATEX CIJERAH | TURKEY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903259111-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 180 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259111 JE1309 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903259135-1 IS1413 | BLACK | 60D | S2425M405 | 300 | 15/12/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 826010 | PRINT L3 SUB PROCESS_V3 | 0903259135 IS1413 |  | KAHATEX CIJERAH | TURKEY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903259160-1 IN1157 | WHITE | 90D | S2408MR1600 | 483 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259160 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259172-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 164 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259172 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903259177-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 437 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259177 KY9383 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259204-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 730 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903259204 KX3655 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259211-1 IN1156 | BLACK | 90D | S2408MR1600 | 167 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 547012 | HT SUB PROCESS_V1 | 0903259211 IN1156 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259212-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 316 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259212 KY9384 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259232-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 380 | 2026-07-11 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903259232 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903259252-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 529 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259252 KY9383 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903259268-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 405 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259268 KR3066 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903259305-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 302 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259305 KY9384 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259338-1 LG9666 | BLACK | 120D | S2754WAS512C | 320 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259338 LG9666 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903259343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 313 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259343 KY9384 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259378-1 KY9385 | KHAKI SIX F26 | 120D | S2608MR0201 | 479 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259378 KY9385 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M KHAKI SIX F26 |  | SS27-TRAX
ADIDAS | 0903259404-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 315 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903259404 LF0726 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903259471-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (22/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259471 KX9851 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903259524-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 125 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903259524 KY9384 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903259595-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 510 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903259595 LG9675 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903259751-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 204 | 23/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | PRINT L3+PAD SUB PROCESS_V3 | 0903259751 KA0546 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903259789-1 IN1172 | BLACK | 90D | S2408WR1600 | 760 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | 512106 | HT SUB PROCESS_V1 | 0903259789 IN1172 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903259835-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 249 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903259835 LC6339 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903259864-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 822 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 806020 | HT+PAD SUB PROCESS_V3 | 0903259864 KX3655 | 2026-08-10 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903259893-1 IN1157 | WHITE | 90D | S2408MR1600 | 138 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903259893 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903260147-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 180 | 30/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260147 LG9665 | 2026-08-10 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903260149-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 160 | 15/12/2026 |  | SI | SI10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | (06/08/2026) | 859013 | PRINT L1 SUB PROCESS_V3 | 0903260149 KZ3056 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903260166-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260166 LF0729 | 2026-08-10 | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903260179-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 252 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260179 LG9675 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903260184-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 160 | 15/12/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 859013 | PRINT L2 SUB PROCESS_V3 | 0903260184 LI7659 | 24/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903260320-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 252 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 652001 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260320 LG9661 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903260341-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 452 | 2026-07-11 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | 960029 | PRINT L3 SUB PROCESS_V3 | 0903260341 LI7660 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260374-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 139 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960026 | PRINT L3 SUB PROCESS_V3 | 0903260374 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903260383-1 LG9669 | BLACK | 120D | S2754WAS514C | 252 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric (Mexico). T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903260383 LG9669 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260461-1 LF0727 | BLACK | 120D | S2754MAS510B | 114 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512102 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260461 LF0727 | 2026-08-10 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260513-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 1062 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903260513 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903260544-1 LF0727 | BLACK | 120D | S2754MAS510B | 380 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260544 LF0727 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903260564-1 LG9669 | BLACK | 120D | S2754WAS514C | 231 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903260564 LG9669 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903260662-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 510 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825057 | PRINT L3 SUB PROCESS_V3 | 0903260662 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260775-1 LI7660 | BLACK | 90D | S2762LHMEGR105M | 631 | 15/11/2026 |  | ID | ID10/07/2026 |  | T-SHIRT |  | (10/08/2026) | ok | (China). 825056 | PRINT L3 SUB PROCESS_V3 | 0903260775 LI7660 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903260885-1 KZ3063 | BLACK | 90D | S2762LHMEDR203M | 113 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (10/08/2026) | ok | (China). 825066 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903260885 KZ3063 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA NNHD M BLACK |  | SS27-MS
ADIDAS | 0903260989-1 KZ3058 | BLACK | 90D | S2762LHMEDR107M | 600 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | ok | ok | (China). 825066 | PRINT L3 SUB PROCESS_V3 | 0903260989 KZ3058 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903261075-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 355 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | (China). (China). (China). 825057 | PRINT L1 SUB PROCESS_V3 | 0903261075 LI7655 | 24/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903261159-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1000 | 15/12/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261159 JE6414 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903261181-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 300 | 15/12/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261181 JW7182 |  | KAHATEX CIJERAH | TURKEY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903261204-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1609 | 23/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 13-Aug. T2 Libolon, PI Date 04-Aug, actual receives 28-Jul. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (PO 26021877). 960026 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261204 KV7863 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903261255-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1232 | 2026-07-11 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261255 JW7182 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903261283-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1152 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 960006 | EMBRO SUB PROCESS_V1 | 0903261283 KD3911 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | RELEASED |  | SS27
ADIDAS | 0903261414-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (Mexico). DRC 0064-T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903261414 LD0293 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903261449-1 JE1309 | BLACK/WHITE | 90D | S2554WES421WV | 298 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, (3S) PI Date 24-Aug, ETD ?? T2 Libolon, (Body) PI Date 04-Aug, actual receieves 28-Jul. 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903261449 JE1309 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903261505-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 268 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261505 JE0055 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903261530-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 800 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | T2 Gistex, material quality issues (creasemark), PI Date 09-Aug, actual receives 14-Aug (100% QC panel). 826010 | HT SUB PROCESS_V1 | 0903261530 IL4127 | 24/09/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903261559-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 1040 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (20/08/2026) | ok | 826010 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903261559 JD5302 |  | KAHATEX CIJERAH | TURKEY | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903261581-1 LF0723 | BLACK | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903261581 LF0723 | 2026-08-10 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903261610-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 550 | 2026-07-11 |  | SA | SA10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903261610 JD1877 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903262124-1 LF0718 | BLACK | 105D | S2754MAS512B-MTF | 1676 | 2026-07-11 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262124 LF0718 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903262659-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A-MTF | 100 | 15/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | ok | ok | 960006 | HT+PAD SUB PROCESS_V3 | 0903262659 KF5311 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903262680-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 550 | 30/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 980004 | HT+PAD SUB PROCESS_V3 | 0903262680 KX3655 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262708-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1006 | 15/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric (Mexico). T2 Hua Feng, PI Date 31-Aug. Waiting fabric. T2 Far Easten, PI Date 25-Aug. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262708 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903262726-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 410 | 15/12/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 980004 | HT SUB PROCESS_V1 | 0903262726 IT1469 | 24/09/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903262735-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 309 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | (05/08/2026) | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903262735 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903262802-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A-MTF | 120 | 23/11/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 960026 | HT+PAD SUB PROCESS_V3 | 0903262802 KX3655 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903262938-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B | 369 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262938 LF0726 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903262975-1 LG9665 | KHAKI THREE F26 | 120D | S2754WAS512C | 1568 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903262975 LG9665 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263005-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 410 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263005 LG9661 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903263040-1 LG9674 | KHAKI THREE F26 | 120D | S2754WAS513C-MTF | 1621 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263040 LG9674 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT KHAKI THREE F26 |  | SS27
ADIDAS | 0903263070-1 LG9669 | BLACK | 120D | S2754WAS514C | 441 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263070 LG9669 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903263086-1 LG9675 | BLACK | 120D | S2754WAS513C-MTF | 1346 | 15/11/2026 |  | AN | AN10/07/2026 |  | PANTS |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903263086 LG9675 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903263117-1 JZ7711 | BLACK | 120D | S2608MR0202 | 2362 | 15/11/2026 | 2362 | SA | SA10/07/2026 | G3D | SHORTS | G3 | ok | ok | DRC 0010-T2 Hua Feng, PI Date 31-Aug, actual receives 05-Sep. T2 Far Easten, PI Date 25-Aug, actual receives 03-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263117 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 20/11/2026 | ADI365/// 2i1 M BLACK |  | SS27-TRAX | 20/11/2026 | 26/11/2026 |  |  | 2362 |  | 2362 |  |  | 17/11/2026 | 23/11/2026 |  |  | 2362 |  | 2362 |  |  | 2026-12-11 | 18/11/2026 |  |  | 2362 |  | 2362
ADIDAS | 0903263138-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 529 | 15/11/2026 | 529 | SA | SA10/07/2026 | G3E | SHORTS | G3 | (31/08/2026) | ok | Waiting fabric. DRC 0010-T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263138 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | BRAZIL | SEA | 2026-01-10 | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX | 2026-01-10 | 2026-02-10 |  |  | 529 |  | 529 |  |  | 28/09/2026 | 29/09/2026 |  |  | 529 |  | 529 |  |  | 24/09/2026 | 25/09/2026 |  |  | 529 |  | 529
ADIDAS | 0903263306-1 KY5988 | SILVER BLUE S27/BLACK | 105D | S2650MTR436 | 430 | 2026-07-11 |  | SA | SA10/07/2026 |  | PANTS |  | ok | ok | 512106 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903263306 KY5988 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | WE ALLSET 54S PT SILVER BLUE S27/BLACK |  | SS27-TI
ADIDAS | 0903263390-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 282 | 23/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263390 LF0729 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263420-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 198 | 23/11/2026 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903263420 LF0721 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903263452-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 130 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 512106 | HT SUB PROCESS_V1 | 0903263452 KX9838 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903263473-1 KB5960 | WHITE | 120D | S2608MR0900A | 260 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 848012 | HT+PAD SUB PROCESS_V3 | 0903263473 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903263497-1 IN1157 | WHITE | 90D | S2408MR1600 | 193 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903263497 IN1157 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903263651-1 IS1413 | BLACK | 60D | S2425M405 | 376 | 2026-07-11 |  | SI | SI10/07/2026 |  | T-SHIRT |  | ok | ok | 512106 | PRINT L3 SUB PROCESS_V3 | 0903263651 IS1413 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903263677-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 574 | 2026-07-11 |  | SA | SA10/07/2026 |  | SHORTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263677 JE6414 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903263715-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 500 | 2026-07-11 |  | SI | SI10/07/2026 |  | JACKET |  | (20/08/2026) | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263715 JE0052 | 24/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903263748-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 530 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | 512106 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903263748 JD5302 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903263778-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 204 | 2026-07-11 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/08/2026) | ok | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903263778 KA5089 | 26/08/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903263840-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1055 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903263840 KY9384 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903263913-1 LH3758 | BLACK | 120D | S2754WAS518B | 246 | 15/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903263913 LH3758 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903263936-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 160 | 15/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (11/09/2026) | ok | Waiting fabric. T2 New Wide, PI Date 11-Sep. 980004 | HT SUB PROCESS_V1 | 0903263936 JW9678 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903264012-1 LG9666 | BLACK | 120D | S2754WAS512C | 135 | 23/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960026 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264012 LG9666 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903264121-1 LG9669 | BLACK | 120D | S2754WAS514C | 1 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | (22/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 960026 | PRINT L3+PPA SUB PROCESS_V3 | 0903264121 LG9669 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903264660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B-MTF | 1032 | 2026-07-11 |  | AN | AN10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI date 04-Sep. T2 Kahatex, PI date 09-Sep, actual receives 09-Jul (PO NT-365). 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264660 LE8181 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903264697-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 419 | 2026-07-11 |  | SA | SA10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 06-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264697 LF0721 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903264733-1 LE8188 | LEGEND IVY S19 | 105D | S2754MAS513 | 351 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. 804028 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903264733 LE8188 | 2026-08-10 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TP PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903266169-1 KZ3062 | BLACK | 90D | S2762LHMEDR207M | 226 | 2026-07-11 |  | SA | SA10/07/2026 |  | SWEATSHIRT |  | (09/09/2026) | ok | 960029 | PRINT L2 SUB PROCESS_V3 | 0903266169 KZ3062 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MER KA GFSWT M BLACK |  | SS27-MS
ADIDAS | 0903266211-1 KX9838 | SEMI SOLAR AQUA S27 | 90D | S2408MR1600 | 150 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (21/09/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 21-Sep. Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD ?? 960006 | HT SUB PROCESS_V1 | 0903266211 KX9838 | 24/09/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903266275-1 LG9666 | BLACK | 120D | S2754WAS512C | 100 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 960006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903266275 LG9666 | 2026-08-10 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903266343-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 172 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903266343 KY9384 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 0903266484-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 28 | 30/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903266484 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903266504-1 KX3650 | SEMI SOLAR AQUA S27 | 120D | S2608MR0900A | 100 | 23/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | (09/09/2026) | ok | 512106 | HT+PAD SUB PROCESS_V3 | 0903266504 KX3650 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M SEMI SOLAR AQUA S27 |  | SS27-TI
ADIDAS | 0903266573-1 LH3758 | BLACK | 120D | S2754WAS518B | 283 | 2026-07-12 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903266573 LH3758 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT BLACK |  | SS27
ADIDAS | 0903266636-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 164 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (07/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 07-Sep. Waiting fabric. T2 Fu Hsun, PI Date 17-Aug, ETD ?? Waiting fabric. T2 Grand Tex, PI Date 16-Aug, ETD ?? 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903266636 LD0292 | 2026-08-10 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903269380-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 352 | 23/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903269380 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903269421-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 301 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903269421 KR3066 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 0903269458-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 272 | 2026-07-12 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/09/2026) | ok | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903269458 KZ1286 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903269653-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 748 | 15/11/2026 |  | ID | ID10/07/2026 |  | SKIRT |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516443 | PRINT L3+PPA SUB PROCESS_V3 | 0903269653 LG9668 | 2026-08-10 | KAHATEX CIJERAH | ITALY | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 0903269724-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 62 | 30/11/2026 |  | SA | SA10/07/2026 |  | T-SHIRT |  | ok | ok | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903269724 LC6339 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903270268-1 LF0728 | LIGHT CINNAMON S27 | 120D | S2754MAS510B | 128 | 15/11/2026 |  | SI | SI10/07/2026 |  | JACKET |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 28-Aug, ETD ?? Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270268 LF0728 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903270294-1 LG9662 | LIGHT CINNAMON S27 | 120D | S2754WAS512C | 95 | 15/11/2026 |  | SA | SA10/07/2026 |  | JACKET |  | (30/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 30-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? 1st Art (TC 10 pcs) 516029 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903270294 LG9662 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT LIGHT CINNAMON S27 |  | SS27-SPOMA
ADIDAS | 0903271870-1 KY5870 | GREY | 90D | S2750MTR052 | 136 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271870 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271911-1 KY5870 | GREY | 90D | S2750MTR052 | 368 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 814006 | HT SUB PROCESS_V1 | 0903271911 KY5870 | 24/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271953-1 KY5870 | GREY | 90D | S2750MTR052 | 110 | 15/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 838103 | HT SUB PROCESS_V1 | 0903271953 KY5870 | 24/09/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903271991-1 KX9855 | SEMI SOLAR VIOLET S27 | 90D | S2408WR1600 | 1139 | 15/11/2026 |  | SI | SI10/07/2026 |  | T-SHIRT |  | (20/08/2026) | ok | (Mexico). 652001 | HT SUB PROCESS_V1 | 0903271991 KX9855 | 24/09/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903272018-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 261 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272018 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903272076-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 464 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272076 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903272106-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 1252 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | Waiting fabric. T2 Libolon, PI Date 04-Aug, ETD ?? T2 Kahatex, PI Date 10-Aug, actual receives 07-Aug. T2 Formosa, PI Date 29-Jul, actual receives 04-Jul (using PO 26021877). 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903272106 KZ3202 | 24/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903273766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 545 | 2026-07-11 |  | SI | SI10/07/2026 |  | PANTS |  | ok | ok | T2 Kahatex, PI Date 10-Aug, actual receives 11-Aug. T2 Libolon, PI Date 04-Aug, actual receives 08-Aug. T2 Formosa, actual receives 04-Jul (PO 26021877). 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903273766 KZ3200 | 24/09/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903276188-1 KY5870 | GREY | 90D | S2750MTR052 | 135 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (09/09/2026) | ok | Waiting fabric. T2 Kahatex, PI Date 09-Sep. Waiting fabric. T2 Gistex, PI Date 02-Sep. 800187 | HT SUB PROCESS_V1 | 0903276188 KY5870 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D74T ESS SHORTS GREY |  | SS27-TI
ADIDAS | 0903293851-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 387 | 15/12/2026 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903293851 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX
ADIDAS | 0903293875-1 KZ0027 | GREY ONE F17/GREY | 90D | F2608MR1201BUF | 1667 | 2026-07-12 |  | AN | AN10/07/2026 |  | T-SHIRT |  | (06/08/2026) | ok | Waiting fabric. T2 Sue's, PI Date 18-Aug, ETD ?? 800187 | PRINT L2+HT SUB PROCESS_V3 | 0903293875 KZ0027 | 24/09/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | ASPYRE TEE UF GREY ONE F17/GREY |  | SS27-TRAX
ADIDAS | 0903305161-1 LF1392 | CHALK PINK F27/WHITE | 90D | S2754WESS422WV-MTF | 100 | 30/11/2026 |  | AN | AN10/07/2026 |  | JACKET |  | (10/08/2026) | ok | T2 Kahatex, PI Date 10-Aug, actual receives 08-Aug. T2 Formosa, PI Date 09-Jun, actual receives 27-Jul. T2 Libolon, PI Date 06-Aug, actual receives 12-Jun (PO 26022038). 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903305161 LF1392 | 24/09/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV BOMBER CHALK PINK F27/WHITE |  | SS27
ADIDAS | 0903306650-1 KA6229 | BLACK | 120D | S2608WR0202 | 388 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 834012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306650 KA6229 | 13/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903306651-1 KA6229 | BLACK | 120D | S2608WR0202 | 222 | 15/11/2026 |  | SA | SA15/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903306651 KA6229 | 13/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903316926-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 338 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 14-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316926 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903316927-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 201 | 30/11/2026 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Easten, PI Date 14-Aug, ETD 20-Aug, ETA-Kaha 04-Sep. T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316927 JZ7715 | 28/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903316931-1 KT4839 | ONIX | 90D | S2408MR1601 | 127 | 2026-07-12 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316931 KT4839 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903316933-1 KT4839 | ONIX | 90D | S2408MR1601 | 680 | 15/12/2026 |  | SA | SA30/06/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 04-Aug, ETD ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903316933 KT4839 | 14/09/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903322462-1 IN8707 | BLACK | 105D | S2408WR1601A | 170 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (14/09/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 14-Sep. Waiting fabric. T2 Men Chuen, PI Date 24-Aug. 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322462 IN8707 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322463-1 IN1173 | WHITE | 90D | S2408WR1600 | 215 | 15/11/2026 |  | SI | SI30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322463 IN1173 | 14/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322464-1 IN1173 | WHITE | 90D | S2408WR1600 | 303 | 23/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322464 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322466-1 IN1173 | WHITE | 90D | S2408WR1600 | 318 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322466 IN1173 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322471-1 IN1172 | BLACK | 90D | S2408WR1600 | 336 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322471 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322473-1 IN8707 | BLACK | 105D | S2408WR1601A | 339 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322473 IN8707 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322475-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 154 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322475 IN1159 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322481-1 IT1469 | TEAM ROYAL BLUE | 90D | S2408MR1600 | 339 | 23/11/2026 |  | SA | SA03/07/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. 516471 | HT SUB PROCESS_V1 | 0903322481 IT1469 | 17/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322483-1 IN1172 | BLACK | 90D | S2408WR1600 | 335 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322483 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322485-1 IN1172 | BLACK | 90D | S2408WR1600 | 299 | 15/11/2026 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322485 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322487-1 IN1172 | BLACK | 90D | S2408WR1600 | 315 | 2026-07-12 |  | SI | SI07/07/2026 |  | T-SHIRT |  | (14/08/2026) | ok | 516471 | HT SUB PROCESS_V1 | 0903322487 IN1172 | 21/09/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322489-1 IN1159 | BLACK | 90D | S2408MR1601 | 1049 | 15/12/2026 |  | SA | SA26/06/2026 |  | SHORTS |  | (01/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322489 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903322494-1 IN1156 | BLACK | 105D | S2408MR1600 | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516471 | HT SUB PROCESS_V1 | 0903322494 IN1156 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903322495-1 IN1159 | BLACK | 90D | S2408MR1601 | 257 | 2026-07-12 |  | SA | SA26/06/2026 |  | SHORTS |  | (01/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 22-Sep. Waiting fabric. T2 Men Chuen, PI Date 01-Sep. 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903322495 IN1159 | 2026-10-09 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903324319-1 KT4839 | ONIX | 90D | S2408MR1601 | 320 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903324319 KT4839 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903346575-1 LC9619 | AURORA IVY F25 | 90D | S2725M920 | 104 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903346575 LC9619 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN AURORA IVY F25 |  | SS27-STX
ADIDAS | 0903348672-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 432 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903348672 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903348762-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 408 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903348762 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903348798-1 KY0907 | SILVER BLUE TINT S27 | 90D | F2625M101 | 313 | 2026-07-12 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903348798 KY0907 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE SILVER BLUE TINT S27 |  | SS27-L2L
ADIDAS | 0903349016-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 517 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903349016 KA0237 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903349056-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349056 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903349066-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903349066 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903350019-1 IN8707 | BLACK | 105D | S2408WR1601A | 1168 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903350019 IN8707 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903350099-1 IN1172 | BLACK | 105D | S2408WR1600 | 481 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903350099 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903351164-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903351164 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903351248-1 KY0907 | SILVER BLUE TINT S27 | 90D | F2625M101 | 201 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903351248 KY0907 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE SILVER BLUE TINT S27 |  | SS27-L2L
ADIDAS | 0903351281-1 LC9619 | AURORA IVY F25 | 90D | S2725M920 | 221 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903351281 LC9619 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN AURORA IVY F25 |  | SS27-STX
ADIDAS | 0903351318-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 530 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903351318 KU3270 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903351402-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 320 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903351402 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903351428-1 LH2842 | BLACK | 90D | S2725M993 | 551 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903351428 LH2842 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903351478-1 LH2841 | OFF WHITE | 90D | S2725M993 | 519 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903351478 LH2841 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903351554-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 172 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903351554 KY1335 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903352148-1 IN1172 | BLACK | 105D | S2408WR1600 | 406 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352148 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352206-1 IN1173 | WHITE | 105D | S2408WR1600 | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT SUB PROCESS_V1 | 0903352206 IN1173 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903352294-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 405 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903352294 LD0292 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903353668-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 424 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903353668 KU3269 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903353747-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 558 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903353747 KD7980 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903353928-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 442 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903353928 KU3272 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903354015-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 100 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354015 KS4777 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903354045-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 268 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354045 KD3676 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903354086-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 641 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903354086 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903354132-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 211 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903354132 KU3269 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903356178-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903356178 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903356305-1 IP2310 | BLACK | 105D | S2450MTR701 | 528 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903356305 IP2310 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903356398-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903356398 JW9678 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903356461-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903356461 KB5966 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903356572-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356572 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903356614-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 126 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903356614 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903357612-1 KZ4392 | WHITE | 120D | F2608WR1500 | 1209 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903357612 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903357878-1 KA4331 | BLACK | 90D | S2608MR0902 | 824 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357878 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357917-1 KA4331 | BLACK | 90D | S2608MR0902 | 1177 | 23/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | PAD+HT SUB PROCESS_V3 | 0903357917 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903357951-1 KB5960 | WHITE | 120D | S2608MR0900A | 638 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357951 KB5960 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903357990-1 KB5965 | BLACK | 120D | S2608MR0900A | 451 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903357990 KB5965 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358022-1 KB5965 | BLACK | 120D | S2608MR0900A | 347 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903358022 KB5965 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903358074-1 KA0246 | BLACK | 105D | S2608WR0902 | 308 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903358074 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358100-1 KA0246 | BLACK | 105D | S2608WR0902 | 434 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903358100 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358135-1 KA0246 | BLACK | 105D | S2608WR0902 | 1865 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903358135 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903358700-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 121 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358700 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903358753-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 116 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358753 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903358802-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903358802 KS1493 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903358865-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903358865 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903358895-1 IS1413 | BLACK | 60D | S2425M405 | 600 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903358895 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903358997-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 185 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903358997 KU3272 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903359060-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903359060 HB7454 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903359114-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 207 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903359114 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903359674-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903359674-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 144 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 516333 | PRINT L1 SUB PROCESS_V3 | 0903359674 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903359721-1 KZ4389 | WHITE | 120D | F2608MR1500 | 1210 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 516333 | PAD+HT SUB PROCESS_V3 | 0903359721 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903359778-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359778 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359846-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 938 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359846 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359888-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 547 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359888 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903359954-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 486 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903359954 KR3066 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360018-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 318 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360018 KR3066 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360061-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360061 KR3066 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903360101-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 112 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 516342 | PRINT L2+HT SUB PROCESS_V3 | 0903360101 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903360129-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 116 | 2026-07-12 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 516342 | PRINT L2+HT SUB PROCESS_V3 | 0903360129 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903360666-1 KA0246 | BLACK | 105D | S2608WR0902 | 351 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360666 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360696-1 KA0246 | BLACK | 105D | S2608WR0902 | 843 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360696 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360725-1 KA0246 | BLACK | 105D | S2608WR0902 | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360725 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360753-1 KA0246 | BLACK | 105D | S2608WR0902 | 360 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360753 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360794-1 KA0246 | BLACK | 105D | S2608WR0902 | 388 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360794 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360822-1 KA0246 | BLACK | 105D | S2608WR0902 | 497 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360822 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360848-1 KA0246 | BLACK | 105D | S2608WR0902 | 1003 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903360848 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903360897-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 167 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903360897 LE8186 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903360991-1 LE8187 | BLACK | 105D | S2754MAS513 | 501 | 2026-07-12 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903360991 LE8187 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361050-1 LE8187 | BLACK | 105D | S2754MAS513 | 383 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361050 LE8187 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361088-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 228 | 2026-07-12 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361088 LE8186 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903361129-1 LE8187 | BLACK | 105D | S2754MAS513 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903361129 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903361503-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 962 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361503 KF5311 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903361592-1 KB5960 | WHITE | 120D | S2608MR0900A | 1902 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903361592 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903361661-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 109 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361661 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903361766-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 121 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903361766 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903361804-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 251 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903361804 IW8374 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903361971-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 1446 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903361971 KD3683 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903362173-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 331 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903362173 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903362231-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 300 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903362231 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903362282-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 606 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903362282 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903363183-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363183 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363246-1 JZ7709 | BLACK | 120D | S2608MR0201 | 2318 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363246 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363301-1 JZ7709 | BLACK | 120D | S2608MR0201 | 340 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363301 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363352-1 JZ7709 | BLACK | 120D | S2608MR0201 | 5618 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363352 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363437-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1124 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363437 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363513-1 JZ7709 | BLACK | 120D | S2608MR0201 | 302 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363513 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363559-1 JZ7709 | BLACK | 120D | S2608MR0201 | 363 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363559 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363609-1 JZ7709 | BLACK | 120D | S2608MR0201 | 383 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363609 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903363740-1 KB5965 | BLACK | 120D | S2608MR0900A | 1741 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363740 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903363791-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 594 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903363791 KX3655 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903363855-1 KA0235 | BLACK | 105D | S2608WR0901 | 320 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903363855 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903363897-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 641 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903363897 LG9670 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903363970-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 907 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903363970 KY6616 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903364196-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 150 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364196 KU3269 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364257-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 190 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364257 KD7980 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903364361-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 838103 | PRINT L1 SUB PROCESS_V3 | 0903364361 KC8559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903364462-1 IK7442 | WHITE | 105D | S2408WR2400 | 105 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903364462 IK7442 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903364491-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 127 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903364491 KS4777 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903364570-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 300 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903364570 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903364588-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903364588 KU3270 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903364991-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903364991 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903365054-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 112 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903365054 JW9678 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903365087-1 IN2961 | BLACK | 105D | S2408WR2400 | 100 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903365087 IN2961 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903365207-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365207 KA0237 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903365256-1 IP2310 | BLACK | 105D | S2450MTR701 | 500 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903365256 IP2310 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903365665-1 JZ7709 | BLACK | 120D | S2608MR0201 | 456 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365665 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903365788-1 JZ7709 | BLACK | 120D | S2608MR0201 | 446 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365788 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903365824-1 JZ7709 | BLACK | 120D | S2608MR0201 | 308 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903365824 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903366512-1 KX8877 | WHITE | 90D | S27GMGFX100 | 246 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903366512 KX8877 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903366592-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 5 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903366592 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903366641-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 110 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903366641 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903366658-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 678 | 2026-07-11 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903366658 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903366697-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 101 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366697 KU3272 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366738-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 115 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366738 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366756-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 140 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903366756 KB0235 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366796-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 106 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366796 KU3274 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366838-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 376 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366838 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903366871-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 408 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366871 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903366911-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 142 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903366911 KU3270 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903366950-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 308 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366950 KD3684 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903366982-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 376 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903366982 KD3676 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903367017-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 221 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903367017 KD3683 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903367098-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 416 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903367098 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903367130-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 101 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903367130 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903367252-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903367252 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903367284-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 339 | 2026-08-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | EMBRO SUB PROCESS_V1 | 0903367284 KD7980 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903367372-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 417 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903367372 IT3474 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903367407-1 IK7442 | WHITE | 105D | S2408WR2400 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903367407 IK7442 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903367462-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 830009 | HT SUB PROCESS_V1 | 0903367462 IW8374 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903367498-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903367498 KC9016 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903367624-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 1464 | 2026-08-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 830009 | EMBRO SUB PROCESS_V1 | 0903367624 KD3683 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903368689-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 150 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903368689 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903368737-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 2776 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368737 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368757-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903368757 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368774-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 367 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903368774 IN1159 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903368797-1 KG3232 | MAGIC LILAC S22 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 512108 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903368797 KG3232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W MAGIC LILAC S22 |  | SS27-TRAX
ADIDAS | 0903368816-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 1661 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368816 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368842-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 1006 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 652001 | PRINT L3+PPA SUB PROCESS_V3 | 0903368842 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903368857-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 2061 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903368857 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368875-1 KZ4392 | WHITE | 120D | F2608WR1500 | 146 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848024 | PAD+HT SUB PROCESS_V3 | 0903368875 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368890-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 838 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368890 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903368903-1 KZ4392 | WHITE | 120D | F2608WR1500 | 126 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848012 | PAD+HT SUB PROCESS_V3 | 0903368903 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368930-1 IN8707 | BLACK | 105D | S2408WR1601A | 617 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903368930 IN8707 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903368937-1 KZ4392 | WHITE | 120D | F2608WR1500 | 125 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 512106 | PAD+HT SUB PROCESS_V3 | 0903368937 KZ4392 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903368963-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 323 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903368963 IT1469 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903369000-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 364 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903369000 KY9431 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903369200-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 104 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903369200 KD3684 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903369262-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 224 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903369262 KC9016 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903369687-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 123 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903369687 JW7182 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903369776-1 IK7442 | WHITE | 105D | S2408WR2400 | 238 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903369776 IK7442 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903369794-1 IS1413 | BLACK | 60D | S2425M405 | 164 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903369794 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903369828-1 IN2961 | BLACK | 105D | S2408WR2400 | 109 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369828 IN2961 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903369857-1 IK7442 | WHITE | 105D | S2408WR2400 | 132 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 800187 | HT SUB PROCESS_V1 | 0903369857 IK7442 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903369902-1 KE9870 | BLACK | 105D | S2650MTR809B | 300 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 800187 | PRINT L1 SUB PROCESS_V3 | 0903369902 KE9870 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903369942-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 300 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903369942 HB7454 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903369980-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 279 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903369980 KD3676 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903370027-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 497 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 800187 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903370027 JD9944 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903370711-1 KA0235 | BLACK | 105D | S2608WR0901 | 327 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903370711 KA0235 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370756-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903370756 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903370854-1 LF0718 | BLACK | 105D | S2754MAS512B | 547 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516342 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370854 LF0718 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903370911-1 LF0727 | BLACK | 120D | S2754MAS510B | 440 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370911 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903370963-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 196 | 2026-07-12 |  | AN | AN31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903370963 LF0726 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903371108-1 LF0727 | BLACK | 120D | S2754MAS510B | 126 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903371108 LF0727 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903371738-1 IN1172 | BLACK | 105D | S2408WR1600 | 2072 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903371738 IN1172 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371825-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 42 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903371825 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903371852-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric (Mexico). T2 Y.T.I, PI Date 10-Jul, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903371852 IT1469 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371889-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 523 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903371889 KG8553 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903371934-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1088 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903371934 IN1156 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903371971-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 300 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | (Mexico). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903371971 KC8152 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903372069-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 546 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep.ity LLT from FAR EASTERN (VNM), ETD: 12-Oct (DOL 30D). 652001 | HT SUB PROCESS_V1 | 0903372069 IN1157 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903372107-1 KA0246 | BLACK | 105D | S2608WR0902 | 460 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (Mexico). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903372107 KA0246 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903372148-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 100 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903372148 KC9016 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903372170-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 239 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903372170 IW8374 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903372265-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 192 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903372265 HB7454 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903372668-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO SUB PROCESS_V1 | 0903372668 JD1881 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372707-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3168 | 2026-07-11 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372707 JE6414 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372751-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 2064 | 2026-07-11 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO SUB PROCESS_V1 | 0903372751 JD1881 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903372792-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 1300 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372792 JD5308 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372825-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1328 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903372825 JF3604 | 15/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372860-1 JD5308 | CLEAR PINK/WHITE | 90D | S2554WES403FT | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372860 JD5308 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903372905-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 240 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 980004 | PRINT L1 SUB PROCESS_V3 | 0903372905 JF3604 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903372940-1 LE7510 | AURORA COFFEE S26/KHAKI THREE F26 | 90D | S27AAWVL701 | 3000 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903372940 LE7510 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 23S TRICOT PT AURORA COFFEE S26/KHAKI THREE F26 |  | SS27
ADIDAS | 0903372958-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 101 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 980004 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903372958 JE6414 | 15/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903372979-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 128 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903372979 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373000-1 LE5391 | SILVER LEAF S27/WHITE | 90D | S26AAWVL320 | 3600 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903373000 LE5391 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER LEAF S27/WHITE |  | SS27
ADIDAS | 0903373023-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 228 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373023 IN1156 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373054-1 LE7508 | BLACK/WHITE | 90D | S27AAWVL701 | 2400 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903373054 LE7508 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S TRICOT PT BLACK/WHITE |  | SS27
ADIDAS | 0903373065-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 193 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 848012 | HT SUB PROCESS_V1 | 0903373065 IN1172 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373102-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903373102 IN1157 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903373109-1 KS7769 | WHITE/BLACK | 90D | S26AAWVL320 | 6000 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903373109 KS7769 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WHITE/BLACK |  | SS27
ADIDAS | 0903373416-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 1200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 826010 | EMBRO SUB PROCESS_V1 | 0903373416 KD3936 |  | KAHATEX CIJERAH | TURKEY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903373455-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848016 | PRINT L3+PPA SUB PROCESS_V3 | 0903373455 LE0357 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903373496-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 115 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903373496 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903373718-1 LF0727 | BLACK | 120D | S2754MAS510B | 377 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373718 LF0727 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV TT BLACK |  | SS27
ADIDAS | 0903373765-1 LF0718 | BLACK | 105D | S2754MAS512B | 326 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903373765 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903374698-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374698 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903374782-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903374782 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903374787-1 KA0246 | BLACK | 105D | S2608WR0902 | 617 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516400 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374787 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374792-1 KA0235 | BLACK | 105D | S2608WR0901 | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374792 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903374832-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 684009 | HT+PAD SUB PROCESS_V3 | 0903374832 KB5965 |  | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903374862-1 IN8707 | BLACK | 105D | S2408WR1601A | 301 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374862 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374867-1 KA0246 | BLACK | 105D | S2608WR0902 | 346 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374867 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374899-1 KA0246 | BLACK | 105D | S2608WR0902 | 451 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 516400 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374899 KA0246 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903374900-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1505 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903374900 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374933-1 KG8547 | ONIX | 105D | S2408WR1600 | 442 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903374933 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903374934-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 197 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374934 IN1159 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374938-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 202 | 2026-07-11 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903374938 LI2667 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903374939-1 JZ7709 | BLACK | 120D | S2608MR0201 | 519 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | DRC 0090-early shipment customer (ROW - FW: Critical PODD improvement request- RDD Jan availability - LO comm). Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 516199 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374939 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903374951-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 637 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903374951 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903374962-1 IN8707 | BLACK | 105D | S2408WR1601A | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903374962 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903374969-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1297 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903374969 LC6341 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903374996-1 KA4331 | BLACK | 90D | S2608MR0902 | 321 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | PAD+HT SUB PROCESS_V3 | 0903374996 KA4331 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903375008-1 KA0235 | BLACK | 105D | S2608WR0901 | 312 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903375008 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903375019-1 IL7232 | BLACK | 105D | S2408MR3202 | 1837 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903375019 IL7232 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903375027-1 KT4839 | ONIX | 90D | S2408MR1601 | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903375027 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903375053-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 687 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903375053 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903375063-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516299 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375063 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375096-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 556 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903375096 KA2571 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903375109-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516244 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375109 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375126-1 KA0246 | BLACK | 105D | S2608WR0902 | 376 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903375126 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903375499-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 146 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375499 LG9661 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903375528-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 226 | 2026-07-12 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375528 LI2645 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903375564-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 198 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375564 LI2647 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903375575-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 181 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848024 | HT SUB PROCESS_V1 | 0903375575 IN1157 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903375595-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 136 | 2026-07-12 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375595 LI2668 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903375623-1 LF0723 | BLACK | 105D | S2754MAS511B | 126 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903375623 LF0723 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903375626-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 130 | 2026-07-12 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903375626 LI2646 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903375662-1 KS7769 | WHITE/BLACK | 90D | S26AAWVL320 | 6000 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 600000 | EMBRO SUB PROCESS_V1 | 0903375662 KS7769 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE WHITE/BLACK |  | SS27
ADIDAS | 0903375688-1 KA0235 | BLACK | 105D | S2608WR0901 | 140 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep.848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903375688 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903375714-1 KS7770 | BLACK/WHITE | 90D | S26AAWVL320 | 1800 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (22/08/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903375714 KS7770 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE BLACK/WHITE |  | SS27
ADIDAS | 0903375724-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 111 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903375724 LE0357 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903376486-1 LE8187 | BLACK | 105D | S2754MAS513 | 358 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903376486 LE8187 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903377133-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 412 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377133 LE4307 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377157-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 414 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377157 KU7520 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903377184-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 482 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377184 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903377185-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 332 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 684009 | HT+PAD SUB PROCESS_V3 | 0903377185 KB5961 |  | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903377216-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 552 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377216 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377256-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 555 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377256 KD0738 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377300-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 401 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377300 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377314-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903377314 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903377338-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 302 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377338 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377349-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 645 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT SUB PROCESS_V1 | 0903377349 KX9855 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903377350-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 488 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric (Mexico). T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 652001 | HT SUB PROCESS_V1 | 0903377350 IN1173 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377377-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 383 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377377 KA6260 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903377379-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 330 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377379 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903377398-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 756 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377398 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377403-1 KA4331 | BLACK | 90D | S2608MR0902 | 740 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 652001 | PAD+HT SUB PROCESS_V3 | 0903377403 KA4331 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903377412-1 IN1157 | WHITE | 105D | S2408MR1600 | 1894 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377412 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377437-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 729 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377437 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377443-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 975 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903377443 IN1156 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377446-1 KG8547 | ONIX | 105D | S2408WR1600 | 569 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903377446 KG8547 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377470-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1907 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903377470 KX3654 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903377476-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377476 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377486-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 2013 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377486 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377504-1 IN8707 | BLACK | 105D | S2408WR1601A | 373 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377504 IN8707 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903377510-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377510 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377530-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 463 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377530 KY4155 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903377545-1 IN1173 | WHITE | 105D | S2408WR1600 | 5142 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377545 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377583-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 381 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903377583 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903377598-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 540 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903377598 KD0738 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903377600-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 773 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377600 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377618-1 IN1157 | WHITE | 105D | S2408MR1600 | 6000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903377618 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377633-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 1048 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377633 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903377643-1 LE0357 | OLIVE ONE S27 | 105D | S2754MAS514 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 650034 | PRINT L3+PPA SUB PROCESS_V3 | 0903377643 LE0357 | 29/10/2026 | KAHATEX CIJERAH | URUGUAY | SEA |  | M SL WV CU PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903377670-1 LF0723 | BLACK | 105D | S2754MAS511B | 192 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377670 LF0723 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903377679-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377679 LG9661 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377730-1 LF0723 | BLACK | 105D | S2754MAS511B | 624 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377730 LF0723 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903377777-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | PRINT L1+PAD SUB PROCESS_V3 | 0903377777 LE7647 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903377805-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 103 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT SUB PROCESS_V1 | 0903377805 KG8548 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377842-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 194 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 848012 | HT SUB PROCESS_V1 | 0903377842 KT4840 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903377883-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 148 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903377883 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903377939-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 120 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903377939 KF5311 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903377983-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512106 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903377983 LD6542 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903378020-1 LG9666 | BLACK | 120D | S2754WAS512C | 299 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903378020 LG9666 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903378068-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 680 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378068 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903378096-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 209 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903378096 KB5961 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903378136-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 214 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903378136 KA6260 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903378176-1 IP2310 | BLACK | 105D | S2450MTR701 | 4001 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 New Wide, PI Date ?? 516318 | HT SUB PROCESS_V1 | 0903378176 IP2310 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903378295-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903378295 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903378391-1 KT4840 | ONIX | 105D | S2408MR1600 | 148 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903378391 KT4840 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903378422-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 814006 | EMBRO SUB PROCESS_V1 | 0903378422 KD3683 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903378918-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 477 | 2026-07-12 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903378918 LI2646 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903379162-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 566 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379162 KY9384 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903379219-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 320 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379219 KY9384 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903379258-1 JZ7711 | BLACK | 120D | S2608MR0202 | 7018 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379258 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379288-1 JZ7711 | BLACK | 120D | S2608MR0202 | 522 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379288 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379297-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 392 | 2026-07-11 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379297 KV8005 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379368-1 LE4307 | KHAKI THREE F26/WHITE | 90D | S2754WESS422WV | 280 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379368 LE4307 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903379458-1 KV8005 | BLACK/WHITE | 90D | S2754WESS422WV | 458 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379458 KV8005 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BOMBER BLACK/WHITE |  | SS27
ADIDAS | 0903379480-1 JZ7711 | BLACK | 120D | S2608MR0202 | 369 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379480 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379504-1 JZ7711 | BLACK | 120D | S2608MR0202 | 362 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379504 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379537-1 JZ7711 | BLACK | 120D | S2608MR0202 | 697 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379537 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379565-1 JZ7711 | BLACK | 120D | S2608MR0202 | 4347 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379565 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379589-1 JZ7711 | BLACK | 120D | S2608MR0202 | 562 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379589 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379620-1 KD3875 | BLACK | 120D | S2608WR0201 | 302 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379620 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903379629-1 JZ7711 | BLACK | 120D | S2608MR0202 | 227 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379629 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379646-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 470 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379646 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379658-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 1801 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (Mexico). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379658 IN1159 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903379677-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 362 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 650010 | HT SUB PROCESS_V1 | 0903379677 IT1469 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379694-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903379694 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903379699-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 7027 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379699 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379708-1 IN8707 | BLACK | 105D | S2408WR1601A | 461 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379708 IN8707 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903379735-1 KT4840 | ONIX | 105D | S2408MR1600 | 674 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (Mexico). T2 Far Eastern, PI Date 10-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379735 KT4840 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379774-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 1960 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379774 KB5961 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379788-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | PRINT L1+PAD SUB PROCESS_V3 | 0903379788 LE7650 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903379814-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 1260 | 15/12/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379814 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903379820-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 304 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379820 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379841-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 548 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379841 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903379843-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903379843 KB5965 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903379876-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 770 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379876 KX9855 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903379894-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 398 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903379894 LD6542 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903379909-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 401 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903379909 KG8548 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903379942-1 KT4839 | ONIX | 90D | S2408MR1601 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379942 KT4839 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903379978-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 108 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516443 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903379978 LD5446 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903379979-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 1361 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903379979 KU7520 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380015-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 1104 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903380015 LD0907 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380044-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903380044 LD0278 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903380117-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 321 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 652001 | HT SUB PROCESS_V1 | 0903380117 KX9838 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903380177-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 169 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903380177 KB5965 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380349-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 501 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903380349 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903380351-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 200 | 2026-07-12 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380351 LI2669 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903380384-1 KB5960 | WHITE | 120D | S2608MR0900A | 952 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380384 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380417-1 KB5965 | BLACK | 120D | S2608MR0900A | 897 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380417 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380454-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 154 | 23/11/2026 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516443 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380454 LI2645 |  | KAHATEX CIJERAH | ITALY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380455-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 398 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380455 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903380474-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 421 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903380474 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903380477-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 228 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380477 LI2646 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903380604-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 341 | 2026-07-12 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380604 LI2667 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903380647-1 KU3269 | SILVER BLUE TINT S27/TEAM NAVY BLUE 2 | 90D | S2625M036 | 211 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380647 KU3269 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380663-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 665 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903380663 LI2645 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903380739-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903380739-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 500 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 838103 | EMBRO+PAD SUB PROCESS_V3 | 0903380739 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903380774-1 LH2842 | BLACK | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380774 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903380833-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 828 | 30/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903380833 JW7182 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903380843-1 KG3189 | MAROON | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903380843 KG3189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903380864-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 950 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380864 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903380881-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 485 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903380881 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903380897-1 IC5188 | BLACK | 90D | S23080640 | 226 | 2026-07-11 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380897 IC5188 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380911-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903380911 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903380935-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 185 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903380935 KU0090 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903380960-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 196 | 2026-07-11 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric (NYK warehouse). T2 Gistex, PI Date 31-Aug. 800005 | HT SUB PROCESS_V1 | 0903380960 IL4127 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903380966-1 KG3190 | CARBON S18 | 120D | S2608MR0900A | 407 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903380966 KG3190 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M CARBON S18 |  | SS27-TI
ADIDAS | 0903380971-1 KU8358 | WHITE | 105D | S2750MTR051 | 174 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 05-Sep. 830009 | HT SUB PROCESS_V1 | 0903380971 KU8358 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T ESS T WHITE |  | SS27-TI
ADIDAS | 0903381006-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903381006 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903381023-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1724 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903381023 KW1543 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381034-1 LH2841 | OFF WHITE | 90D | S2725M993 | 142 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381034 LH2841 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903381091-1 JC5699 | WONDER ALUMINA S25/WHITE | 90D | S2554WES503FT | 123 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903381091 JC5699 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903381100-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 104 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903381100 LI2645 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381106-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 20/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903381106 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903381119-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 121 | 2026-07-12 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903381119 LH4744 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381127-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 156 | 2026-07-12 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903381127 LI2672 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903381143-1 LH2842 | BLACK | 90D | S2725M993 | 100 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903381143 LH2842 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903381653-1 KD3875 | BLACK | 120D | S2608WR0201 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381653 KD3875 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381658-1 JZ7711 | BLACK | 120D | S2608MR0202 | 1339 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381658 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381700-1 KD3875 | BLACK | 120D | S2608WR0201 | 982 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381700 KD3875 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381730-1 JZ7711 | BLACK | 120D | S2608MR0202 | 403 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381730 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381750-1 KD3875 | BLACK | 120D | S2608WR0201 | 315 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381750 KD3875 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381764-1 JZ7711 | BLACK | 120D | S2608MR0202 | 859 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381764 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903381802-1 KD3875 | BLACK | 120D | S2608WR0201 | 2262 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381802 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903381812-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 633 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381812 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381817-1 KX8877 | WHITE | 90D | S27GMGFX100 | 337 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 804099 | PRINT L3+PAD SUB PROCESS_V3 | 0903381817 KX8877 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381829-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381829 KV7963 | 15/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903381859-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 318 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381859 KA6260 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381892-1 KX8877 | WHITE | 90D | S27GMGFX100 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903381892 KX8877 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903381895-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1315 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903381895 KX3655 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903381903-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 344 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381903 KY9391 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903381904-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 304 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381904 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381912-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  | (02/09/2026) |  | 630001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903381912 IB8688 |  | KAHATEX CIJERAH | CANADA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903381925-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 817 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903381925 KX3653 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903381934-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 335 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381934 KY9393 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903381939-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 627 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381939 KA6260 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903381949-1 IN1156 | BLACK | 105D | S2408MR1600 | 434 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381949 IN1156 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381966-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 423 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903381966 KY9391 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903381982-1 IN1157 | WHITE | 105D | S2408MR1600 | 1157 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903381982 IN1157 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903381985-1 LF0718 | BLACK | 105D | S2754MAS512B | 328 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 516438 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903381985 LF0718 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 0903382018-1 IN1172 | BLACK | 105D | S2408WR1600 | 512 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382018 IN1172 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382031-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 261 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382031 KY9431 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382039-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516461 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382039 LD5446 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903382050-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 319 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903382050 KX3655 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382067-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 549 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382067 KY9393 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903382087-1 IN1173 | WHITE | 105D | S2408WR1600 | 1019 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382087 IN1173 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382094-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 135 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382094 KY9431 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382097-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 516400 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382097 KY9431 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903382119-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 359 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 659018 | HT SUB PROCESS_V1 | 0903382119 KX9855 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903382147-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 1601 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382147 KX3653 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903382178-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (Mexico). 652001 | HT+PAD SUB PROCESS_V3 | 0903382178 KX3655 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903382200-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 693 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382200 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903382246-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 652 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382246 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903382454-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 111 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903382454 JD9944 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903382503-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 462 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903382503 IN0088 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903382608-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 498 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903382608 IN0089 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903382642-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 117 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903382642 JW9678 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903382648-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 294 | 2026-07-11 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382648 LI2670 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903382670-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 293 | 2026-07-11 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | (12/09/2026) |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903382670 LI2671 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903382686-1 KA0235 | BLACK | 105D | S2608WR0901 | 325 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382686 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382719-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903382719 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903382747-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 315 | 2026-07-11 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | (08/09/2026) |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903382747 LI2668 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903382753-1 LH5251 | WHITE/BLACK | 105D | F2654MESS614WVB | 402 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903382753 LH5251 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 141S WV WB LND WHITE/BLACK |  | SS27
ADIDAS | 0903382780-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A | 656 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903382780 KB5961 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382781-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 1902 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382781 KB5965 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382810-1 LG9675 | BLACK | 120D | S2754WAS513C | 420 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 600000 | PRINT L3+PPA SUB PROCESS_V3 | 0903382810 LG9675 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903382812-1 KB5960 | WHITE | 120D | S2608MR0900A | 454 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382812 KB5960 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382838-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 704 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382838 KB5961 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903382866-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 496 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 650010 | HT+PAD SUB PROCESS_V3 | 0903382866 KF5311 |  | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903382881-1 KA0235 | BLACK | 105D | S2608WR0901 | 4 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382881 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903382905-1 KA0246 | BLACK | 105D | S2608WR0902 | 8 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382905 KA0246 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903382908-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 1200 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 804028 | EMBRO+PAD SUB PROCESS_V3 | 0903382908 KV3559 | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903382908-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 1200 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 804028 | EMBRO+PAD SUB PROCESS_V3 | 0903382908 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903382942-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 12 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382942 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382966-1 KG8547 | ONIX | 105D | S2408WR1600 | 70 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903382966 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903382983-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 4 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903382983 KG8553 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903383005-1 KD3875 | BLACK | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383005 KD3875 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903383011-1 KZ4389 | WHITE | 120D | F2608MR1500 | 160 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. 848016 | PAD+HT SUB PROCESS_V3 | 0903383011 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 0903383028-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 8 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383028 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903383050-1 LG9669 | BLACK | 120D | S2754WAS514C | 58 | 30/11/2026 |  | ID | ID31/07/2026 |  | SKIRT |  | (20/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 20-Sep. 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903383050 LG9669 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV SK BLACK |  | SS27
ADIDAS | 0903383053-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 100 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903383053 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903383098-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 9 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383098 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903383116-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 4 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383116 LD0292 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383141-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436-MTF | 391 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/10/2026) |  | 650010 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903383141 KC8152 |  | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903383152-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 268 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383152 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383154-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 559 | 2026-07-11 |  | SI | SI31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383154 LI2647 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903383175-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 2026-07-11 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903383175 LI2669 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903383208-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 153 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 830009 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903383208 LH4744 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903383211-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 770 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383211 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383242-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 102 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903383242 KX9855 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903383264-1 JC5699 | WONDER ALUMINA S25/WHITE | 90D | S2554WES503FT | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383264 JC5699 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903383301-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383301 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383327-1 LF4995 | OLIVE TWO S27 | 105D | S2750MTR051 | 182 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 05-Sep. 830009 | HT SUB PROCESS_V1 | 0903383327 LF4995 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T ESS T OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903383333-1 KW1544 | TEAM LIGHT BLUE | 30D | F25GFXBLANKM | 933 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903383333 KW1544 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903383370-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 662 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383370 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383385-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 800187 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383385 KA0237 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903383400-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 100 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383400 IN1159 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903383404-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 167 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903383404 KU0090 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383433-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 160 | 2026-07-12 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903383433 JE0052 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903383551-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383551 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383552-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 186 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383552 KY9391 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903383580-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 400 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903383580 IT3474 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903383585-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383585 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903383600-1 KA0235 | BLACK | 105D | S2608WR0901 | 115 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383600 KA0235 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383614-1 KA0235 | BLACK | 105D | S2608WR0901 | 135 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903383614 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903383625-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 468 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903383625 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903383639-1 IW2479 | WHITE | 45D | F24KLKGFX003 | 200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 826010 | PRINT L3+PAD SUB PROCESS_V3 | 0903383639 IW2479 |  | KAHATEX CIJERAH | TURKEY | SEA |  | POS TABLE LK |  | SS27
ADIDAS | 0903383934-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 108 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903383934 LE8186 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903383958-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (16/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Sep. 826010 | HT SUB PROCESS_V1 | 0903383958 JC9584 | 15/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903383982-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 826010 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903383982 JE6340 | 15/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903383985-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 306 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903383985 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903384003-1 KB7172 | WHITE | 60D | S26SPRWGFX023 | 200 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 826010 | PRINT L2 SUB PROCESS_V3 | 0903384003 KB7172 |  | KAHATEX CIJERAH | TURKEY | SEA |  | HOT COMMUNITY |  | SS27
ADIDAS | 0903384048-1 IN8707 | BLACK | 105D | S2408WR1601A | 329 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384048 IN8707 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384058-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 323 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384058 LH4746 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903384076-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 680 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903384076 KD0738 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903384078-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 1972 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903384078 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384085-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 269 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384085 LD5446 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903384087-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 144 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903384087 LE7647 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903384116-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384116 IN1159 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384142-1 IN1157 | WHITE | 105D | S2408MR1600 | 823 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903384142 IN1157 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384205-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 490 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384205 LD0294 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903384218-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 497 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903384218 LG9670 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903384263-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 370 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903384263 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903384268-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 414 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384268 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384290-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 348 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384290 KA6260 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903384300-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 710 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 659018 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903384300 KV7863 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903384325-1 IN1173 | WHITE | 105D | S2408WR1600-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384325 IN1173 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384351-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 551 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 684009 | HT SUB PROCESS_V1 | 0903384351 IN1172 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384354-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 384 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric (Mexico). T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Jiale, PI Date 20-Jul, actual receives 07-Jul, inspect ok 08-Jul. 652001 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903384354 KA2571 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903384380-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384380 KA0235 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903384391-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 130 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384391 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903384406-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 408 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 05-Sep. 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903384406 IN1159 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903384429-1 KX3713 | OLIVE TWO S27 | 120D | S2608MR0906A | 124 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903384429 KX3713 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903384435-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 512 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903384435 LD0278 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903384461-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 684009 | HT SUB PROCESS_V1 | 0903384461 IN1157 | 29/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903384496-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 142 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903384496 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903384678-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 389 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903384678 HB7454 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903384715-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 370 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384715 JW7182 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903384799-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 497 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903384799 KD3684 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903384839-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 300 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384839 JD9944 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903384877-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 593 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903384877 JD1881 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903384912-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 1200 | 2026-07-11 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903384912 JW7178 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903384931-1 IC5189 | WHITE | 90D | S23080640 | 394 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 814006 | HT SUB PROCESS_V1 | 0903384931 IC5189 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903384989-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 1550 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | PRINT L1 SUB PROCESS_V3 | 0903384989 JF3604 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903384992-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 510 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 830009 | HT SUB PROCESS_V1 | 0903384992 IL4127 | 15/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903385024-1 IP2310 | BLACK | 105D | S2450MTR701 | 295 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 800187 | HT SUB PROCESS_V1 | 0903385024 IP2310 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903385058-1 JM1772 | BLACK/WHITE | 90D | F2554MESS712WV | 2298 | 2026-07-11 |  | SA | SA31/07/2026 |  | JACKET |  | (03/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 03-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385058 JM1772 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV TT |  | SS27
ADIDAS | 0903385096-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 149 | 2026-07-12 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 800187 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385096 JE6414 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903385133-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 2433 | 2026-07-11 |  | SA | SA31/07/2026 |  | JACKET |  | (16/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903385133 JE6338 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903385161-1 KG8547 | ONIX | 105D | S2408WR1600 | 2190 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385161 KG8547 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385187-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 661 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385187 KT4840 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385216-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 429 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385216 KU7520 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385236-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2986 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385236 KG8548 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385265-1 KT4839 | ONIX | 90D | S2408MR1601 | 356 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385265 KT4839 | 15/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E SHORT ONIX |  | SS27-TRAX
ADIDAS | 0903385289-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600-MTF | 4617 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 650010 | HT SUB PROCESS_V1 | 0903385289 KX9838 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903385321-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 550 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385321 KY9384 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903385346-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 2915 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 650010 | HT SUB PROCESS_V1 | 0903385346 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385373-1 LD5446 | KHAKI THREE F26 | 105D | S2754MAS511B | 418 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 650010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385373 LD5446 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | M SL WV SHO KHAKI THREE F26 |  | SS27
ADIDAS | 0903385404-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 553 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 650010 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385404 LD0294 | 29/10/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385432-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 102 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 688010 | PRINT L2+PAD SUB PROCESS_V3 | 0903385432 LC8884 |  | KAHATEX CIJERAH | PANAMA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903385460-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 20 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385460 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903385648-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 331 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385648 JW7182 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903385684-1 LC9640 | BLACK/SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385684 LC9640 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365 SHO M BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385693-1 LH2842 | BLACK | 90D | S2725M993 | 106 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903385693 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903385716-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 598 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903385716 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903385723-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 620 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903385723 KB5966 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903385730-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 101 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 512102 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385730 LF9808 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385741-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 570 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385741 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903385758-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 160 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848024 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385758 LF9808 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385762-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 100 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385762 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903385764-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 669 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903385764 LD0278 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903385785-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 202 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385785 LD0294 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385792-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 311 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385792 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903385799-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 105 | 22/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | EMBRO SUB PROCESS_V1 | 0903385799 JD1881 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903385806-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 500 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 New Wide, PI Date ?? 800005 | HT SUB PROCESS_V1 | 0903385806 IW8374 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903385813-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903385813 LE8186 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903385818-1 KA0235 | BLACK | 105D | S2608WR0901 | 477 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385818 KA0235 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903385840-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 452 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385840 LF9808 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903385844-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 254 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 806020 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903385844 LD0292 | 29/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903385886-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 428 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903385886 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903385887-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 122 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385887 KD3683 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903385905-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 170 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903385905 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903385915-1 LH2841 | OFF WHITE | 90D | S2725M993 | 117 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903385915 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903385928-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 638 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385928 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903385942-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 328 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 838103 | HT SUB PROCESS_V1 | 0903385942 IW8374 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903385963-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 432 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903385963 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903385965-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 121 | 2026-07-12 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903385965 JW7182 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903385992-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 314 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | PRINT L1+HT SUB PROCESS_V3 | 0903385992 KB0235 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386004-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 479 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386004 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903386008-1 KA0235 | BLACK | 105D | S2608WR0901 | 450 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386008 KA0235 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386012-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 560 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 838103 | PRINT L1+HT SUB PROCESS_V3 | 0903386012 KB0235 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386021-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386021 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386035-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 672 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (15/09/2026) |  | Waiting fabric. T2 Sue's, PI Date 15-Sep. 672027 | PRINT L2+HT SUB PROCESS_V3 | 0903386035 KZ0028 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903386059-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 305 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 680015 | HT SUB PROCESS_V1 | 0903386059 KT4840 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386060-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386060 KY9391 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 0903386078-1 IN2961 | BLACK | 105D | S2408WR2400 | 201 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 838103 | HT SUB PROCESS_V1 | 0903386078 IN2961 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903386079-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 684009 | PAD+HT SUB PROCESS_V3 | 0903386079 LD0278 | 15/10/2026 | KAHATEX CIJERAH | PERU | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903386080-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 184 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386080 LF9808 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903386099-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 727 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386099 KD3683 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386105-1 LH2841 | OFF WHITE | 90D | S2725M993 | 463 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386105 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903386109-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 180 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 848016 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386109 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903386130-1 LH2842 | BLACK | 90D | S2725M993 | 103 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386130 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386133-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 100 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903386133 KD7980 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386166-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386166 KD3684 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903386183-1 IN1173 | WHITE | 105D | S2408WR1600 | 1024 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386183 IN1173 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386198-1 LE8186 | OLIVE ONE S27 | 105D | S2754MAS513 | 149 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386198 LE8186 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV TP PT OLIVE ONE S27 |  | SS27
ADIDAS | 0903386216-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 1447 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386216 IN1172 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386221-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 518 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386221 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386249-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 415 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386249 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903386253-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 171 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 848016 | PAD+HT SUB PROCESS_V3 | 0903386253 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903386254-1 IN8707 | BLACK | 105D | S2408WR1601A | 479 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386254 IN8707 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903386264-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386264 KD3683 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386278-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (10/07/2026) |  | IMPROVE (AP Siti FU). Waiting fabric. T2 Y.T.I, PI Date 10-Jul, ETD ?? 678002 | HT SUB PROCESS_V1 | 0903386278 IT1469 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386299-1 KA0235 | BLACK | 105D | S2608WR0901 | 510 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386299 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386301-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 659 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386301 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386304-1 KA0235 | BLACK | 105D | S2608WR0901 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386304 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386327-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 666 | 2026-07-11 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386327 KV7963 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386328-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386328 KB5961 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386337-1 LH4746 | TEAM NAVY BLUE 2 | 120D | S2754MAS510B | 170 | 30/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903386337 LH4746 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV TT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903386345-1 JE6353 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS605FT | 300 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903386345 JE6353 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386348-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 200 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386348 JD5302 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386352-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 300 | 2026-07-11 |  | SA | SA31/07/2026 |  | SHORTS |  | (02/09/2026) |  | Waiting fabric. T2 Formosa, PI Date 01-Sep, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903386352 KV7963 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903386355-1 KB5960 | WHITE | 120D | S2608MR0900A | 371 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386355 KB5960 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386367-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 400 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903386367 IN0088 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386369-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386369 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386372-1 IP2310 | BLACK | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903386372 IP2310 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903386387-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 435 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386387 KB5965 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903386391-1 KG3189 | MAROON | 120D | S2608MR0900A | 400 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903386391 KG3189 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903386400-1 KE8425 | WHITE | 120D | S2608MR0906A | 718 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903386400 KE8425 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M WHITE |  | SS27-TI
ADIDAS | 0903386413-1 LH2841 | OFF WHITE | 90D | S2725M993 | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386413 LH2841 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903386428-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 109 | 15/12/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903386428 JD1881 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386435-1 KD3875 | BLACK | 120D | S2608WR0201 | 358 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386435 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903386450-1 LH2842 | BLACK | 90D | S2725M993 | 563 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 838103 | PRINT L1 SUB PROCESS_V3 | 0903386450 LH2842 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386490-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 395 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903386490 KE8424 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903386521-1 KA0235 | BLACK | 105D | S2608WR0901 | 305 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386521 KA0235 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903386540-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 112 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 838103 | PAD+HT SUB PROCESS_V3 | 0903386540 IN0088 | 29/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386556-1 KA0246 | BLACK | 105D | S2608WR0902 | 393 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903386556 KA0246 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903386570-1 LH2842 | BLACK | 90D | S2725M993 | 451 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903386570 LH2842 |  | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903386589-1 KT4840 | ONIX | 105D | S2408MR1600 | 405 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903386589 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903386620-1 KA4331 | BLACK | 90D | S2608MR0902 | 526 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 678002 | PAD+HT SUB PROCESS_V3 | 0903386620 KA4331 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903386627-1 JD5302 | BLACK/WHITE | 90D | S2554WES403FT | 109 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386627 JD5302 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT CF PT |  | SS27
ADIDAS | 0903386672-1 JE6346 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS605FT | 2749 | 2026-07-11 |  | SA | SA31/07/2026 |  | PANTS |  | (16/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386672 JE6346 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386704-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 271 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903386704 IU0217 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903386736-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 1250 | 2026-07-11 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386736 JW7182 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903386741-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 100 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903386741 KD3684 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903386775-1 HK7319 | BLACK | 90D | F2225M403 | 2400 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | 804028 | EMBRO+PPA SUB PROCESS_V3 | 0903386775 HK7319 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903386782-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 988 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386782 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903386825-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 3178 | 2026-07-11 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386825 JD1881 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903386860-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2230 | 2026-07-11 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386860 JD1877 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903386863-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 434 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903386863 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903386894-1 KS1493 | TEAM ROYAL BLUE/WHITE | 90D | S2615KSWJ751 | 103 | 2026-07-11 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903386894 KS1493 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T TEAM ROYAL BLUE/WHITE |  | SS27-STX
ADIDAS | 0903386898-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 1250 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | ok |  | 804028 | EMBRO SUB PROCESS_V1 | 0903386898 JD7999 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903386920-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903386920 IN0088 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903386936-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 1250 | 2026-07-11 |  | SA | SA31/07/2026 |  | SHORTS |  | ok |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903386936 JE6419 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903386967-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903386967 IU0217 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903386983-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 1250 | 2026-07-11 |  | SA | SA31/07/2026 |  | JACKET |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903386983 JE6340 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903387009-1 KD7980 | BLACK/WHITE | 90D | S2625W005 | 889 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903387009 KD7980 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BLACK/WHITE |  | SS27-STX
ADIDAS | 0903387028-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2037 | 2026-07-11 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | ok |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387028 JE6374 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387045-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 397 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903387045 KC9016 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903387071-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2557 | 2026-07-11 |  | SI | SI31/07/2026 |  | SWEATSHIRT |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387071 JE6372 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903387109-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 1289 | 2026-07-11 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387109 JE6414 | 15/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903387118-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 498 | 2026-07-11 |  | SI | SI31/07/2026 |  | JACKET |  | (12/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903387118 JE0052 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903387166-1 LG9663 | SILVER BLUE S27 | 120D | S2754WAS512C | 37 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387166 LG9663 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387197-1 LG9672 | SILVER BLUE S27 | 120D | S2754WAS513C | 39 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903387197 LG9672 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV PT SILVER BLUE S27 |  | SS27
ADIDAS | 0903387223-1 LD0291 | HAZE CORAL S17 | 105D | S2608WR0901 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903387223 LD0291 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903387244-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 574 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387244 LG9661 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387298-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 75 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 547012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387298 LF0725 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903387372-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 156 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 826010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903387372 LH4744 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903387607-1 KX6445 | WHITE/WHITE | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? Waiting fabric (NYK warehuose). T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387607 KX6445 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WHITE/WHITE |  | SS27-STX
ADIDAS | 0903387643-1 KX6443 | WARM CLAY S25/WARM CLAY S25 | 90D | S27SPRWGFXP712 | 100 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). DRC 0064-T2 New Wide, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 800005 | EMBRO+PAD SUB PROCESS_V3 | 0903387643 KX6443 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | W FOLKF EYLT T WARM CLAY S25/WARM CLAY S25 |  | SS27-STX
ADIDAS | 0903387704-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 450 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387704 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903387726-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 567 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387726 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903387868-1 LG9670 | AURORA COFFEE S26 | 120D | S2754WAS513C | 111 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903387868 LG9670 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903387903-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 100 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 512108 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387903 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903387928-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 204 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 512106 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903387928 KA5090 | 16/09/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903387962-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 100 | 23/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 960006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903387962 KY6616 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388016-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 410 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388016 LD6542 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388052-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 450 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 980004 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388052 KY6616 | 29/10/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903388072-1 HK7319 | BLACK | 90D | F2225M403 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | 826010 | EMBRO+PPA SUB PROCESS_V3 | 0903388072 HK7319 |  | KAHATEX CIJERAH | TURKEY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903388124-1 LD6542 | SILVER BLUE S27/BLACK | 105D | F2654MESS614WVB | 162 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388124 LD6542 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 118S WV WB LND SILVER BLUE S27/BLACK |  | SS27
ADIDAS | 0903388150-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 1187 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 659018 | HT+PAD SUB PROCESS_V3 | 0903388150 KX3654 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388156-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388156 JE6414 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903388178-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 6 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388178 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388183-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 382 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (12/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903388183 JD9944 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903388195-1 KA4331 | BLACK | 90D | S2608MR0902 | 397 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 659018 | PAD+HT SUB PROCESS_V3 | 0903388195 KA4331 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903388205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV-MTF | 2641 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388205 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903388219-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 571 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 659018 | PAD+HT SUB PROCESS_V3 | 0903388219 JZ7775 | 15/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903388238-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 1347 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 678002 | HT SUB PROCESS_V1 | 0903388238 KX9855 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388262-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV-MTF | 1134 | 15/11/2026 |  | AN | AN31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 26-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388262 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388290-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 1800 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388290 KZ3198 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903388317-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 1096 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388317 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903388347-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 511 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 678002 | PRINT L2+PAD SUB PROCESS_V3 | 0903388347 LC8884 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903388375-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 1000 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | Request Cancel (BTP_04_09_2026 -> Req. PO Cancel & Quantity Change). MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388375 LD0292 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388415-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 823 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388415 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388488-1 KX8877 | WHITE | 90D | S27GMGFX100 | 42 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903388488 KX8877 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M CHIP T WHITE |  | SS27
ADIDAS | 0903388556-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 339 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903388556 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903388601-1 KG3189 | MAROON | 120D | S2608MR0900A | 700 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903388601 KG3189 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903388629-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehuose). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388629 LD0908 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903388646-1 IC5189 | WHITE | 90D | S23080640 | 254 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 839055 | HT SUB PROCESS_V1 | 0903388646 IC5189 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903388649-1 KB5960 | WHITE | 120D | S2608MR0900A | 1653 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388649 KB5960 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903388657-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903388657 KF5311 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903388679-1 LE8187 | BLACK | 105D | S2754MAS513 | 308 | 15/12/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903388679 LE8187 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV TP PT BLACK |  | SS27
ADIDAS | 0903388696-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 366 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903388696 KX3654 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388702-1 KD3875 | BLACK | 120D | S2608WR0201 | 610 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388702 KD3875 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903388713-1 KA0246 | BLACK | 105D | S2608WR0902 | 133 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388713 KA0246 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903388719-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 261 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903388719 KX3654 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388725-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 400 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388725 KE8424 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903388738-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 10 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388738 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388740-1 LH2842 | BLACK | 90D | S2725M993 | 131 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903388740 LH2842 |  | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903388755-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A-MTF | 1160 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388755 KX3654 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903388767-1 JZ7711 | BLACK | 120D | S2608MR0202 | 266 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388767 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903388782-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 482 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388782 KX3655 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903388797-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 183 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903388797 KE8424 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903388813-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 780 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903388813 KX3655 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903388823-1 KU7520 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1601A | 130 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388823 KU7520 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E SHORT SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903388850-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 130 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388850 KX9855 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903388859-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 492 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903388859 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903388867-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 646 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903388867 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903388876-1 KX9838 | SEMI SOLAR AQUA S27 | 105D | S2408MR1600 | 130 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 547012 | HT SUB PROCESS_V1 | 0903388876 KX9838 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE SEMI SOLAR AQUA S27 |  | SS27-YTI
ADIDAS | 0903388878-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 910 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388878 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903388910-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 380 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 678002 | HT SUB PROCESS_V1 | 0903388910 KT4840 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903388942-1 KG3189 | MAROON | 120D | S2608MR0900A | 800 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903388942 KG3189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903388957-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 795 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903388957 KZ3199 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903389019-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 321 | 15/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389019 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903389062-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 477 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903389062 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903389087-1 LH2841 | OFF WHITE | 90D | S2725M993 | 284 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903389087 LH2841 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903389159-1 IL7232 | BLACK | 105D | S2408MR3202 | 105 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389159 IL7232 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903389207-1 IS1413 | BLACK | 60D | S2425M405 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903389207 IS1413 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903389253-1 KE9870 | BLACK | 105D | S2650MTR809B | 130 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 814006 | PRINT L1 SUB PROCESS_V3 | 0903389253 KE9870 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903389297-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389297 IN0088 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903389321-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 500 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389321 IN0089 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903389360-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 1000 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903389360 KB5966 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903389399-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 419 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389399 KD3676 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903389461-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 599 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 814006 | PAD+HT SUB PROCESS_V3 | 0903389461 IT3474 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903389493-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 737 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 814006 | HT SUB PROCESS_V1 | 0903389493 IW8374 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903389563-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 400 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389563 KC9016 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903389597-1 KD3683 | WHITE/BLACK | 90D | S2625W005 | 229 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903389597 KD3683 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM WHITE/BLACK |  | SS27-STX
ADIDAS | 0903389635-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 447 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 830009 | PAD+HT SUB PROCESS_V3 | 0903389635 IN0089 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903389714-1 IC5189 | WHITE | 90D | S23080640 | 100 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | ok |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 800187 | HT SUB PROCESS_V1 | 0903389714 IC5189 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903389876-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 411 | 2026-07-12 |  | AN | AN31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903389876 LI2669 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 0903390163-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 582 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903390163 LE7650 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903390166-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 102 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 834012 | HT+PAD SUB PROCESS_V3 | 0903390166 KE8420 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903390226-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 104 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 512106 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903390226 KA6260 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903390329-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 493 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903390329 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903390359-1 KG8553 | SOLAR TURBO F26 | 90D | S2408MR1601 | 532 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (20/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 20-Oct. Waiting fabric. T2 Men Chuen, PI Date 08-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903390359 KG8553 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903390384-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 503 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390384 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903390534-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1795 | 2026-07-11 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390534 KV7863 | 15/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390588-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 642 | 23/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903390588 KV7863 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903390685-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903390685 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903390730-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | ok |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390730 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903390802-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903390802 KA5090 | 16/09/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903390874-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 223 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903390874 JW9678 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903390896-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 317 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903390896 KB5966 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903390928-1 IN2961 | BLACK | 105D | S2408WR2400 | 417 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 830009 | HT SUB PROCESS_V1 | 0903390928 IN2961 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903390966-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 150 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | ok |  | 830009 | EMBRO SUB PROCESS_V1 | 0903390966 JD7999 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903391007-1 KD3684 | CRYSTAL SKY S26/MAROON | 90D | S2625W005 | 185 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391007 KD3684 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S TEE SLIM CRYSTAL SKY S26/MAROON |  | SS27-STX
ADIDAS | 0903391036-1 KE9870 | BLACK | 105D | S2650MTR809B | 332 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 830009 | PRINT L1 SUB PROCESS_V3 | 0903391036 KE9870 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903391094-1 JD1881 | BLACK/WHITE | 90D | S2554MESS605FT | 119 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (12/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903391094 JD1881 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT TC PT |  | SS27
ADIDAS | 0903391161-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 317 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391161 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391179-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 1026 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391179 KX8875 | 15/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391201-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903391201 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391209-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 1170 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903391209 LC6339 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391236-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 741 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391236 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391240-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1356 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848012 | PAD+HT SUB PROCESS_V3 | 0903391240 IN0088 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391269-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 108 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391269 KU0073 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903391298-1 IL7232 | BLACK | 105D | S2408MR3202 | 1512 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | ok |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391298 IL7232 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903391314-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 999 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391314 LF9808 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391321-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 1080 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 848024 | PAD+HT SUB PROCESS_V3 | 0903391321 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903391350-1 LC6339 | CRYSTAL SKY S26 | 90D | S27GMGFX100 | 972 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | ok |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391350 LC6339 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M CHIP T CRYSTAL SKY S26 |  | SS27
ADIDAS | 0903391352-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 429 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391352 LF9808 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391380-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 808 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391380 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391388-1 LF9808 | SILVER BLUE S27 | 120D | S2608MR0201 | 595 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391388 LF9808 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SILVER BLUE S27 |  | SS27-L2L
ADIDAS | 0903391401-1 KX8875 | OLIVE THREE S27 | 90D | S27GMGFX130 | 864 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391401 KX8875 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO3X T OLIVE THREE S27 |  | SS27
ADIDAS | 0903391419-1 IC5188 | BLACK | 90D | S23080640 | 693 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (31/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 31-Aug. 838103 | HT SUB PROCESS_V1 | 0903391419 IC5188 | 15/10/2026 | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903391436-1 LC6341 | BLACK | 90D | S27GMGFX130 | 1080 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903391436 LC6341 | 15/10/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SEE2X SHO12X T BLACK |  | SS27
ADIDAS | 0903391467-1 LH4744 | TEAM NAVY BLUE 2 | 105D | S2754MAS512B | 235 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391467 LH4744 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV OH PT TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903391494-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 826 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391494 KY4221 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391497-1 LF0724 | LIGHT CINNAMON S27 | 105D | S2754MAS511B | 565 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903391497 LF0724 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO LIGHT CINNAMON S27 |  | SS27
ADIDAS | 0903391498-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 181 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391498 KY4221 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391515-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 102 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903391515 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391525-1 KY4221 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS614WVB | 339 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391525 KY4221 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S WV WB LND TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903391547-1 IN1173 | WHITE | 105D | S2408WR1600 | 600 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT SUB PROCESS_V1 | 0903391547 IN1173 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391589-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 100 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903391589 KU0090 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903391590-1 KE8424 | BLACK | 120D | S2608MR0906A | 694 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391590 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903391595-1 IN1156 | BLACK | 105D | S2408MR1600 | 353 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 516443 | HT SUB PROCESS_V1 | 0903391595 IN1156 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391613-1 KE8420 | MEDIUM GREY HEATHER | 120D | S2608MR0906A | 873 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (05/09/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903391613 KE8420 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M MEDIUM GREY HEATHER |  | SS27-TI
ADIDAS | 0903391641-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 403 | 2026-07-12 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903391641 KY6616 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903391828-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 318 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903391828 LD0908 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903391866-1 KG8547 | ONIX | 105D | S2408WR1600 | 109 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 814006 | HT SUB PROCESS_V1 | 0903391866 KG8547 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903391898-1 KE9870 | BLACK | 105D | S2650MTR809B | 100 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Gistex, PI Date 16-Sep. Waiting fabric. T2 Grand Tex, PI Date 06-Sep. Waiting fabric. T2 Sue's, PI Date 30-Aug. 814006 | PRINT L1 SUB PROCESS_V3 | 0903391898 KE9870 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | TECHESS 3S SHOR BLACK |  | SS27-TI
ADIDAS | 0903391982-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 101 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903391982 KF5311 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903392043-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 650 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903392043 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903392090-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 374 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903392090 KY1335 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903392298-1 KB5965 | BLACK | 120D | S2608MR0900A | 1240 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903392298 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903392317-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 303 | 23/11/2026 |  | SI | SI31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903392317 KZ3205 | 15/10/2026 | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903392385-1 KA0235 | BLACK | 105D | S2608WR0901 | 602 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Far Eastern, PI Date 26-Sep. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903392385 KA0235 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903392419-1 KB5960 | WHITE | 120D | S2608MR0900A | 578 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903392419 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903393666-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 216 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393666 KY6616 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393674-1 KE8424 | BLACK | 120D | S2608MR0906A | 1120 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903393674 KE8424 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903393679-1 LI2672 | SILVER BLUE S27/TEAM NAVY BLUE 2 | 60D | S27AOCP102 | 340 | 2026-07-12 |  | SA | SA31/07/2026 |  | ACCESSORIES |  | ok |  | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903393679 LI2672 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE SILVER BLUE S27/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 0903393700-1 KY6616 | BLACK/WHITE | 105D | F2654MESS614WVB | 410 | 15/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393700 KY6616 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 26S WV WB LND BLACK/WHITE |  | SS27
ADIDAS | 0903393729-1 LG9666 | BLACK | 120D | S2754WAS512C | 301 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393729 LG9666 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT BLACK |  | SS27
ADIDAS | 0903393736-1 KW5050 | MAROON | 90D | F2625M101 | 104 | 2026-07-11 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393736 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393740-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 600 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393740 KV7863 | 15/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903393756-1 LG9661 | AURORA COFFEE S26 | 120D | S2754WAS512C | 176 | 30/11/2026 |  | SA | SA31/07/2026 |  | JACKET |  | (27/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903393756 LG9661 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV TT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903393785-1 KZ1299 | SEMI SOLAR BLUE S27 | 105D | S2608MR0201B | 8427 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (27/09/2026) |  | Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903393785 KZ1299 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903393789-1 KW5050 | MAROON | 90D | F2625M101 | 1832 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393789 KW5050 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ESS REG |  | SS27-L2L
ADIDAS | 0903393794-1 LG9675 | BLACK | 120D | S2754WAS513C | 277 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903393794 LG9675 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903393812-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 579 | 15/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 28-Aug, ETD ?? 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903393812 KZ3200 | 15/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903393816-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 104 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393816 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393853-1 KY1335 | OFF WHITE | 90D | S27SPRMGFXH211 | 936 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | PRINT L1+PAD SUB PROCESS_V3 | 0903393853 KY1335 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | M PANCAKE T OFF WHITE |  | SS27-STX
ADIDAS | 0903393882-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 290 | 2026-07-12 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903393882 KA0237 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903393918-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 250 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903393918 KS4777 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903393950-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 109 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903393950 KB5966 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903394061-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 237 | 2026-12-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_10_09_2026 EARLY HOLD SHIPMENT). 800005 | PRINT L1 SUB PROCESS_V3 | 0903394061 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394091-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 404 | 2026-07-12 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903394091 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394210-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 400 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394210 KS4777 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903394289-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 487 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394289 KU3270 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394317-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 250 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394317 KU3274 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394356-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 498 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 814006 | PRINT L1 SUB PROCESS_V3 | 0903394356 KU3272 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903394379-1 KB0235 | WHITE/BLACK | 90D | S2615KSWJ751 | 183 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 814006 | PRINT L1+HT SUB PROCESS_V3 | 0903394379 KB0235 |  | KAHATEX CIJERAH | THAILAND | SEA |  | J SERE T WHITE/BLACK |  | SS27-STX
ADIDAS | 0903394400-1 LF0723 | BLACK | 105D | S2754MAS511B | 284 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 814006 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903394400 LF0723 | 29/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M SL WV SHO BLACK |  | SS27
ADIDAS | 0903394471-1 KU0073 | OFF WHITE/WONDER ALUMINA S25 | 90D | S2625W005 | 240 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394471 KU0073 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM OFF WHITE/WONDER ALUMINA S25 |  | SS27-STX
ADIDAS | 0903394497-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 956 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903394497 KU0090 |  | KAHATEX CIJERAH | THAILAND | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903394844-1 KA4331 | BLACK | 90D | S2608MR0902 | 1140 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394844 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903394868-1 KA4331 | BLACK | 90D | S2608MR0902 | 1142 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 630001 | PAD+HT SUB PROCESS_V3 | 0903394868 KA4331 | 15/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903395342-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 509 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Hua Feng, PI Date 09-Oct. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903395342 KA6260 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903395364-1 IN1156 | BLACK | 105D | S2408MR1600-MTF | 481 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395364 IN1156 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395391-1 IN1173 | WHITE | 105D | S2408WR1600 | 1079 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903395391 IN1173 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395411-1 IN1157 | WHITE | 105D | S2408MR1600-MTF | 333 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastrn, LLT material, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903395411 IN1157 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395435-1 IN1172 | BLACK | 105D | S2408WR1600-MTF | 477 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. Waiting fabric. T2 Far Eastern, PI Date 10-Aug, ETD ?? 672027 | HT SUB PROCESS_V1 | 0903395435 IN1172 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395456-1 KA4331 | BLACK | 90D | S2608MR0902 | 424 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Grand Tex, PI Date 27-Sep. Waiting fabric. T2 New Wide, PI Date 11-Sep. 672027 | PAD+HT SUB PROCESS_V3 | 0903395456 KA4331 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903395497-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 455 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903395497 LD0294 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903395510-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 359 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395510 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903395545-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 440 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395545 KX3655 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903395560-1 LD0292 | SILVER BLUE S27 | 105D | S2608WR0901 | 434 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric (NYK warehouse). T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903395560 LD0292 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903395572-1 LF0726 | LEGEND IVY S19 | 120D | S2754MAS510B-MTF | 442 | 15/12/2026 |  | AN | AN31/07/2026 |  | JACKET |  | (02/10/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Oct. Waiting fabric. T2 Teijin Nantong, PI Date 27-Sep. 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903395572 LF0726 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV TT LEGEND IVY S19 |  | SS27
ADIDAS | 0903395581-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 1983 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 652001 | PAD+HT SUB PROCESS_V3 | 0903395581 LD0277 | 15/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903395619-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A-MTF | 832 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903395619 KX3653 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903395640-1 KZ2984 | SOLAR TURBO F26 | 105D | S2408WR1600 | 432 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric (NYK warehouse). T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 652001 | HT SUB PROCESS_V1 | 0903395640 KZ2984 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903395784-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 238 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903395784 LE7647 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903395859-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 533 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903395859 LE7647 | 15/10/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903396155-1 KU3274 | WHITE/BLACK | 90D | S2625M036 | 204 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903396155 KU3274 | 15/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903396227-1 IN8707 | BLACK | 105D | S2408WR1601A | 322 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric (NYK warehouse). T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903396227 IN8707 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903396318-1 KC6387 | BLACK | 30D | F25GFXBLANKY | 304 | 2026-07-11 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (01/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903396318 KC6387 | 20/08/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | K BLANK TEE |  | SS27
ADIDAS | 0903396350-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric (NYK warehouse). T2 New Wide, PI Date 11-Sep. 800005 | HT SUB PROCESS_V1 | 0903396350 IN2961 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903397029-1 KE8424 | BLACK | 120D | S2608MR0906A-MTF | 475 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397029 KE8424 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903397047-1 KG8547 | ONIX | 105D | S2408WR1600 | 347 | 15/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397047 KG8547 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397069-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 892 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397069 KG8548 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397145-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 442 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397145 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903397668-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 460 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397668 KX3655 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903397694-1 LE1841 | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135 | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | SWEATSHIRT |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET ACTIVE RED S19/OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903397694-2 LE1841-B | ACTIVE RED S19/OLIVE TWO S27 | 105D | S2762LHAMG135-B | 295 | 15/11/2026 |  | SA | SA31/07/2026 |  | PANTS |  |  |  | Waiting fabric (Mexico). T2 Kahatex, PI Date ?? Waiting fabric. T2 Formosa, PI Date ?? 652001 | PRINT L1 SUB PROCESS_V3 | 0903397694 LE1841-B | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL K SET |  | SS27-MS
ADIDAS | 0903397701-1 KX9855 | SEMI SOLAR VIOLET S27 | 105D | S2408WR1600 | 2364 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 672027 | HT SUB PROCESS_V1 | 0903397701 KX9855 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE SEMI SOLAR VIOLET S27 |  | SS27-YTI
ADIDAS | 0903397762-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1097 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 02-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. Waiting fabric. T2 Best Pacific, PI Date 01-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397762 KZ1286 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903397781-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 201 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | PRINT L1+PAD SUB PROCESS_V3 | 0903397781 LE7650 |  | KAHATEX CIJERAH | THAILAND | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903397793-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1335 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397793 KF5311 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903397824-1 JZ7711 | BLACK | 120D | S2608MR0202-MTF | 1062 | 30/11/2026 |  | AN | AN31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Far Eastern, PI Date 25-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397824 JZ7711 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903397858-1 LE7650 | SILVER BLUE S27/STEEL RW S18 | 90D | S2750MTR041A | 434 | 23/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903397858 LE7650 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | D4T 60S T SILVER BLUE S27/STEEL RW S18 |  | SS27-TI
ADIDAS | 0903397879-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 300 | 30/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 672027 | HT+PAD SUB PROCESS_V3 | 0903397879 KB5965 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903397924-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 566 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | PAD+HT SUB PROCESS_V3 | 0903397924 LD0277 | 15/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903397937-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 304 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903397937 KU0090 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903397945-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Grand Tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903397945 LD0907 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903397973-1 LG9675 | BLACK | 120D | S2754WAS513C | 613 | 30/11/2026 |  | SI | SI31/07/2026 |  | PANTS |  | (26/09/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 26-Sep. 672027 | PRINT L3+PPA SUB PROCESS_V3 | 0903397973 LG9675 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | W SL WV PT BLACK |  | SS27
ADIDAS | 0903397998-1 KT4840 | ONIX | 105D | S2408MR1600-MTF | 406 | 15/11/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (10/10/2026) |  | Waiting fabric. DRC 0002-T2 Far Eastern, LLT material, PI Date 12-Oct, ETA Kaha 5-Oct. Waiting fabric. T2 Fu Hsun, PI Date 06-Sep. 672027 | HT SUB PROCESS_V1 | 0903397998 KT4840 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903398052-1 KT4840 | ONIX | 105D | S2408MR1600 | 137 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 10-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903398052 KT4840 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903398113-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398113 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398140-1 KS4777 | NIGHT INDIGO/WHITE | 90D | S2625W005 | 150 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903398140 KS4777 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM NIGHT INDIGO/WHITE |  | SS27-STX
ADIDAS | 0903398456-1 LE7647 | BLACK/CARBON S18 | 90D | S2750MTR041A | 652 | 2026-07-12 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | PRINT L1+PAD SUB PROCESS_V3 | 0903398456 LE7647 | 15/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | D4T 3S T BLACK/CARBON S18 |  | SS27-TI
ADIDAS | 0903398741-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 360 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (25/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 25-Oct. Waiting fabric. T2 Men Chuen, PI Date 07-Sep. 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903398741 KZ2988 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903399989-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 365 | 23/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903399989 KY6510 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400022-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 900 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903400022 KY6510 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903400227-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 300 | 30/11/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 New Wide, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400227 IW8374 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903400251-1 IN2961 | BLACK | 105D | S2408WR2400 | 110 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400251 IN2961 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903400316-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 121 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400316 HB7454 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903400396-1 IN0088 | DARK BLUE | 105D | S2408MR3202 | 124 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400396 IN0088 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT DARK BLUE |  | SS27-TI
ADIDAS | 0903400420-1 HB7454 | GREY SIX S19/REFLECTIVE SILVER | 105D | S22080606 | 383 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. T2 Libolon, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? 839055 | HT SUB PROCESS_V1 | 0903400420 HB7454 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN SHO GREY SIX S19/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903400450-1 IK7442 | WHITE | 105D | S2408WR2400 | 149 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (11/09/2026) |  | Waiting fabric. T2 New Wide, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400450 IK7442 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903400476-1 KC9016 | SANDY PINK F24/AURORA COFFEE S26 | 90D | S2625W005 | 200 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903400476 KC9016 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM SANDY PINK F24/AURORA COFFEE S26 |  | SS27-STX
ADIDAS | 0903400498-1 KD3676 | BETTER SCARLET S23/WHITE | 90D | S2625W005 | 200 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903400498 KD3676 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S TEE SLIM BETTER SCARLET S23/WHITE |  | SS27-STX
ADIDAS | 0903400589-1 KG8547 | ONIX | 105D | S2408WR1600 | 221 | 15/12/2026 |  | SI | SI31/07/2026 |  | T-SHIRT |  | (12/10/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 12-Oct. Waiting fabric. T2 Fu Hsun, PI Date 11-Sep. 839055 | HT SUB PROCESS_V1 | 0903400589 KG8547 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903400617-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 142 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903400617 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903400639-1 KV3559 | WHITE/KHAKI THREE F26 | 120D | OLKF26250815 | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS WHITE/KHAKI THREE F26 |  | SS27-TI
ADIDAS | 0903400639-2 KV3559-B | WHITE/KHAKI THREE F26 | 120D | OLKF26250815-B | 300 | 30/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Itochu, PI Date ?? Waiting fabric. T2 Fu Hsun, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? Waiting fabric. T2 Gistex, PI Date ?? 839055 | EMBRO+PAD SUB PROCESS_V3 | 0903400639 KV3559-B | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | LO JSY STS |  | SS27-TI
ADIDAS | 0903401845-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV-MTF | 402 | 23/11/2026 |  | AN | AN31/07/2026 |  | PANTS |  | (02/09/2026) |  | Waiting fabric. T2 Kahatex, PI Date 02-Sep. Waiting fabric. T2 Formosa, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Libolon, PI Date 27-Aug, ETD ?? 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903401845 KZ3202 | 15/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903402665-1 LH2841 | OFF WHITE | 90D | S2725M993 | 385 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903402665 LH2841 | 15/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | TIG3R OFF WHITE |  | SS27-STX
ADIDAS | 0903402717-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 118 | 15/11/2026 |  | SA | SA31/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Gistex, PI Date ?? Waiting fabric. T2 Libolon, PI Date ?? 839055 | PAD+HT SUB PROCESS_V3 | 0903402717 IT3474 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903402776-1 KU3270 | TEAM ROYAL BLUE/WHITE | 90D | S2625M036 | 131 | 15/12/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  | (02/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903402776 KU3270 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903402796-1 KC8559 | WHITE | 105D | OJS26250838 | 300 | 15/11/2026 |  | SA | SA31/07/2026 |  | T-SHIRT |  |  |  | Waiting fabric. T2 Fu Hsun, PI Date ?? 839055 | PRINT L1 SUB PROCESS_V3 | 0903402796 KC8559 | 29/10/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903408401-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 330 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408401 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408420-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516403 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408420 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408450-1 KY4155 | TEAM NAVY BLUE 2/WHITE | 105D | F2654MESS608WVB | 300 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516462 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408450 KY4155 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 TEAM NAVY BLUE 2/WHITE |  | SS27
ADIDAS | 0903408471-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 710 | 15/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 15-Sep. Waiting fabric. T2 Kahatex, PI Date 02-Sep. T2 Fu Hsun, using fabric stock. 516199 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903408471 KY6510 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903442023-1 KB5965 | BLACK | 120D | S2608MR0900A-MTF | 1217 | 15/12/2026 |  | AN | AN31/07/2026 |  | T-SHIRT |  | (02/10/2026) |  | 678002 | HT+PAD SUB PROCESS_V3 | 0903442023 KB5965 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903444660-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 2974 | 15/11/2026 |  | SA | SA04/08/2026 |  | PANTS |  | (15/10/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date ?? Waiting fabric. T2 Kahatex, PI Date ?? 857010 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903444660 LE8181 | 2026-02-11 | KAHATEX CIJERAH | INDIA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903450968-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450968 IN1159 | 27/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903450969-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 26 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450969 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450970-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 350 | 15/11/2026 |  | SA | SA12/08/2026 |  | T-SHIRT |  |  |  | 600000 | HT SUB PROCESS_V1 | 0903450970 IT1469 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E TEE |  | SS27
ADIDAS | 0903450971-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 65 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903450971 IN1159 | 27/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903450972-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 33 | 15/11/2026 |  | AN | AN12/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903450972 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903452885-1 KA6229 | BLACK | 120D | S2608WR0202 | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 684009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452885 KA6229 | 2026-12-11 | KAHATEX CIJERAH | PERU | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452887-1 KA6229 | BLACK | 120D | S2608WR0202 | 312 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452887 KA6229 | 2026-12-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452889-1 KA6229 | BLACK | 120D | S2608WR0202 | 704 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452889 KA6229 | 2026-12-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903452891-1 KA6229 | BLACK | 120D | S2608WR0202 | 6 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | (Mexico). 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903452891 KA6229 | 2026-12-11 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903466285-1 IC5188 | BLACK | 90D | S23080640 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903466285 IC5188 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903467966-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903467966 HK7319 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468003-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903468003 HR8583 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468026-1 HZ0747 | BLACK | 90D | F2325M414 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903468026 HZ0747 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PL TEE |  | SS27
ADIDAS | 0903468058-1 HK7319 | BLACK | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903468058 HK7319 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903468137-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3000 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903468137 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470160-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903470160 HR8583 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470333-1 JE6374 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903470333 JE6374 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903470363-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3000 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903470363 HR8583 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903470418-1 IC5188 | BLACK | 90D | S23080640 | 4500 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 823016 | HT SUB PROCESS_V1 | 0903470418 IC5188 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903470449-1 HK7309 | BLACK | 45D | F2225M402 | 5500 | 2026-07-11 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903470449 HK7309 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903472306-1 IP2310 | BLACK | 105D | S2450MTR701 | 300 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 800187 | HT SUB PROCESS_V1 | 0903472306 IP2310 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903472755-1 JF3606 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS675FT | 5000 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903472755 JF3606 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903473017-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 719 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903473017 JM1775 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903473064-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903473064 JP1528 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903473120-1 JF3606 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS675FT | 6350 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903473120 JF3606 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903473549-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 18 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue-PROCESS 547012 | PRINT L2+HT SUB PROCESS_V3 | 0903473549 KZ0028 | 29/10/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903473588-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 547012 | EMBRO SUB PROCESS_V1 | 0903473588 KW6443 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903473911-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903473911 JE6419 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903473952-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 1601 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903473952 IU0217 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903474040-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1749 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903474040 JC9584 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903475709-1 KG3189 | MAROON | 120D | S2608MR0900A | 400 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903475709 KG3189 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903475735-1 LC9677 | OFF WHITE | 90D | S2725M959 | 160 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903475735 LC9677 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | STENCIL TONGUE OFF WHITE |  | SS27-STX
ADIDAS | 0903475746-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 140 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 547012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475746 KZ3200 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903475786-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 100 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903475786 KY1333 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903475826-1 LC9677 | OFF WHITE | 90D | S2725M959 | 100 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1 SUB PROCESS_V3 | 0903475826 LC9677 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | STENCIL TONGUE OFF WHITE |  | SS27-STX
ADIDAS | 0903475848-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 144 | 2026-07-12 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903475848 LI7656 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903475858-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516318 | PRINT L3+PAD SUB PROCESS_V3 | 0903475858 JP1527 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903475913-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475913 JM1776 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903475934-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 1139 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903475934 KW8936 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903475971-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903475971 JM1776 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903475974-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 222 | 2026-07-12 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903475974 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903476015-1 LC9621 | OFF WHITE | 90D | S2725M920 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 1st Art (TC 10 pcs) 830009 | PRINT L1 SUB PROCESS_V3 | 0903476015 LC9621 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903476030-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903476030 JP1527 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903476078-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476078 JM1776 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903476096-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 510 | 30/11/2026 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO+PPA SUB PROCESS_V3 | 0903476096 KW9040 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903476131-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516442 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903476131 KA0247 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903476137-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 612 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903476137 LE1842 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476139-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 456 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903476139 KY1333 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903476291-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 1370 | 15/12/2026 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO+PPA SUB PROCESS_V3 | 0903476291 KW9040 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903476381-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 350 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903476381 KU3272 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903476426-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903476426 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476460-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 396 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 547012 | EMBRO SUB PROCESS_V1 | 0903476460 IB8686 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903476510-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 547012 | HT+PAD SUB PROCESS_V3 | 0903476510 KB5959 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903476565-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 148 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512106 | HT+PAD SUB PROCESS_V3 | 0903476565 KX3655 | 2026-12-11 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903476607-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903476607 JC9584 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903476632-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 198 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903476632 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903476637-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | (Mexico). 652001 | PRINT L1 SUB PROCESS_V3 | 0903476637 LE1842 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903476693-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 750 | 15/12/2026 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903476693 JE6340 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903476831-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516205 | PRINT L1 SUB PROCESS_V3 | 0903476831 JE9012 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903476845-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 2000 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (08/09/2026) |  | 516442 | PAD+HT SUB PROCESS_V3 | 0903476845 IN0089 |  | KAHATEX CIJERAH | ITALY | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903476874-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 721 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516204 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903476874 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903477003-1 KG3189 | MAROON | 120D | S2608MR0900A | 300 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903477003 KG3189 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903477015-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903477015 IW8374 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903477134-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 3500 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903477134 JE6417 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903478198-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478198 LI7656 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478236-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 1502 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478236 KA4913 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478237-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 206 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903478237 LI5438 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478243-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 133 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903478243 KU3272 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903478276-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478276 KA4914 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478279-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 628 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903478279 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478284-1 LC8943 | BLACK | 90D | S27SPRMGFXP0900-MTF | 224 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 839055 | PRINT L3+PAD SUB PROCESS_V3 | 0903478284 LC8943 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M TATTOO SPRT T BLACK |  | SS27
ADIDAS | 0903478311-1 JE6372 | BLACK/WHITE | 90D | S2554MESS612FT | 2600 | 23/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478311 JE6372 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M 3S FT SWT |  | SS27
ADIDAS | 0903478324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 351 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478328-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516205 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903478328 KA4914 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903478347-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903478347 KD3936 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903478377-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478377 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478385-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903478385 LJ4074 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903478389-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478389 KF6290 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903478417-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1010 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478417 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478424-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 229 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L2 SUB PROCESS_V3 | 0903478424 LI7658 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903478453-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 1000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 839062 | PRINT L3+PAD SUB PROCESS_V3 | 0903478453 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903478472-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903478472 HK7303 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903478482-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 150 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L2 SUB PROCESS_V3 | 0903478482 LI7659 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903478521-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 406 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903478521 LI7655 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903478661-1 JG8639 | BLACK/WHITE | 90D | S2554WES429FT | 347 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 684009 | PRINT L1 SUB PROCESS_V3 | 0903478661 JG8639 |  | KAHATEX CIJERAH | PERU | SEA |  | W LIN FT SHO |  | SS27
ADIDAS | 0903478686-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903478686 LE1843 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903478689-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 208 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903478689 LE5780 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903478701-1 LC9638 | BLACK/SEMI SOLAR BLUE S27 | 120D | S2608WR0202 | 476 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478701 LC9638 | 2026-12-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADI365/// 2i1 W BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903478720-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 101 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | (Mexico). 652001 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903478720 LI5438 | 29/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903478739-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 1198 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 678002 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478739 LE8181 | 2026-12-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478752-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 125 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903478752 JD9944 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903478756-1 KC8568 | BLACK | 105D | OJS26250839 | 331 | 2026-07-12 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 547012 | PRINT L1 SUB PROCESS_V3 | 0903478756 KC8568 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903478788-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 344 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478788 KD3854 | 2026-12-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903478852-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 387 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478852 KD3854 | 2026-12-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903478862-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903478862 KW1543 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903478873-1 KU3272 | TEAM MAROON 2/OFF WHITE | 90D | S2625M036 | 223 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 800187 | PRINT L1 SUB PROCESS_V3 | 0903478873 KU3272 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | 3S RINGER T |  | SS27-STX
ADIDAS | 0903478906-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 533 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 672027 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903478906 LE8181 | 2026-12-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903478960-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 150 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903478960 LE8189 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903478964-1 LC9638 | BLACK/SEMI SOLAR BLUE S27 | 120D | S2608WR0202 | 303 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | (Mexico). 1st Art (TC 10 pcs) 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903478964 LC9638 | 2026-12-11 | KAHATEX CIJERAH | MEXICO | SEA |  | ADI365/// 2i1 W BLACK/SEMI SOLAR BLUE S27 |  | SS27-TRAX
ADIDAS | 0903478995-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 202 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903478995 LE5780 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903479022-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 150 | 2026-07-12 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903479022 LD0293 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903479028-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 145 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903479028 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903479034-1 JM1776 | DARK BLUE/WHITE | 90D | F2554MESS711WV | 146 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479034 JM1776 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479063-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903479063 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903479077-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 133 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903479077 LD0293 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903479094-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 216 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903479094 KW8936 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903479108-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 118 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903479108 IL4127 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903479112-1 KW8936 | SILVER BLUE S27/BLACK | 90D | S2754MESS676SJ | 102 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903479112 KW8936 |  | KAHATEX CIJERAH | THAILAND | SEA |  | M 48B SJ LF T SILVER BLUE S27/BLACK |  | SS27-STX
ADIDAS | 0903479120-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903479120 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903479186-1 JD7999 | BLACK/WHITE | 90D | S2554WES502FT | 3000 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO SUB PROCESS_V1 | 0903479186 JD7999 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W SL FT CF PT |  | SS27
ADIDAS | 0903479193-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516205 | PRINT L1 SUB PROCESS_V3 | 0903479193 JC9346 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903479239-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516205 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479239 JM1775 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479246-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 1749 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516205 | HT SUB PROCESS_V1 | 0903479246 JC9584 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903479287-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479287 JP1528 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903479292-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | PRINT L1 SUB PROCESS_V3 | 0903479292 JC9346 |  | KAHATEX CIJERAH | ITALY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903479338-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 2000 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516205 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903479338 KA0247 | 2026-12-11 | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903479475-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516205 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903479475 KA4913 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903479546-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2520 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516318 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903479546 JM1775 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903479547-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 725 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 516442 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903479547 KA4913 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903479588-1 JP1527 | WHITE | 45D | S25SPRMGFX260 | 2501 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | PRINT L3+PAD SUB PROCESS_V3 | 0903479588 JP1527 |  | KAHATEX CIJERAH | ITALY | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903480160-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 113 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 547012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903480160 LD0293 | 2026-12-11 | KAHATEX CIJERAH | UKRAINE | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903480229-1 KB5960 | WHITE | 120D | S2608MR0900A | 199 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 516029 | HT+PAD SUB PROCESS_V3 | 0903480229 KB5960 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480272-1 HZ0747 | BLACK | 90D | F2325M414 | 970 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | EMBRO SUB PROCESS_V1 | 0903480272 HZ0747 |  | KAHATEX CIJERAH | CANADA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903480348-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 714 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480348 JE0055 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903480380-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/12/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 512106 | PRINT L1 SUB PROCESS_V3 | 0903480380 LE1842 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903480440-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 416 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903480440 LE8191 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903480478-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 810 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903480478 KB5959 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480562-1 KB5959 | TECH INDIGO S20 | 120D | S2608MR0900A | 774 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903480562 KB5959 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480652-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 543 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480652 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903480678-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903480678 KD3936 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480715-1 KD3936 | CHALK PEARL S18 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903480715 KD3936 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903480748-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 1750 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516205 | HT SUB PROCESS_V1 | 0903480748 KD9849 |  | KAHATEX CIJERAH | SPAIN | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903480764-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 366 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | HT+PAD SUB PROCESS_V3 | 0903480764 KB5964 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903480790-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 2000 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (17/09/2026) |  | 516442 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903480790 KA0247 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903480819-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 135 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480819 IN1156 | 2026-12-11 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480833-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 3501 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480833 JE6419 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903480868-1 IP2310 | BLACK | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516205 | HT SUB PROCESS_V1 | 0903480868 IP2310 | 2026-12-11 | KAHATEX CIJERAH | SPAIN | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903480875-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 195 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903480875 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903480885-1 JZ7711 | BLACK | 120D | S2608MR0202 | 106 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | ok |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 838103 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903480885 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903480915-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 117 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480915 IN1157 | 2026-12-11 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480916-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 1149 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903480916 KF6290 |  | KAHATEX CIJERAH | SPAIN | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903480931-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 20/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 800005 | EMBRO SUB PROCESS_V1 | 0903480931 KW1543 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903480973-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903480973 IN1172 | 2026-12-11 | KAHATEX CIJERAH | MALAYSIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903480979-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 536 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903480979 KW1543 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903481002-1 KD9097 | WHITE | 30D | F25GFXBLANKW | 350 | 2026-07-11 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481002 KD9097 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | W BLANK TEE |  | SS27
ADIDAS | 0903481003-1 KG2491 | ACTIVE MAROON F19 | 90D | F2606CHLF011 | 40 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 814006 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481003 KG2491 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC DNA SHO |  | SS27
ADIDAS | 0903481051-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 600 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903481051 KG8548 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903481052-1 KW1543 | DARK BLUE | 30D | F25GFXBLANKM | 1866 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | EMBRO SUB PROCESS_V1 | 0903481052 KW1543 | 2026-04-09 | KAHATEX CIJERAH | INDONESIA | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903481119-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 1390 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903481119 LI5438 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903481123-1 KA0235 | BLACK | 105D | S2608WR0901 | 668 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903481123 KA0235 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903481211-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 645 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481211 LE8199 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903481262-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 450 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903481262 LG1784 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903481315-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 138 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481315 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903481318-1 KB5960 | WHITE | 120D | S2608MR0900A | 1140 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903481318 KB5960 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481323-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2750 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903481323 HK7317 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903481374-1 JW7182 | BLACK/WHITE | 90D | S2554WES512FT | 5000 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903481374 JW7182 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903481398-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903481398 KC9082 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903481413-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 5000 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903481413 JF3604 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903481437-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 301 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481437 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903481501-1 KF5311 | KHAKI SIX F26 | 120D | S2608MR0900A | 1153 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903481501 KF5311 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M KHAKI SIX F26 |  | SS27-TI
ADIDAS | 0903481504-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 344 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903481504 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903481536-1 KB5966 | RAY BLUE F16 | 120D | S2608MR0900A | 104 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 830009 | HT+PAD SUB PROCESS_V3 | 0903481536 KB5966 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481568-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 318 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903481568 KB5964 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481585-1 KT7395 | AURORA IVY F25 | 90D | F2625M101 | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903481585 KT7395 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE AURORA IVY F25 |  | SS27-L2L
ADIDAS | 0903481589-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 500 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 823016 | HT+PAD SUB PROCESS_V3 | 0903481589 KB5964 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903481632-1 LC9621 | OFF WHITE | 90D | S2725M920 | 221 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903481632 LC9621 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903481635-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 102 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903481635 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903481652-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | PRINT L1 SUB PROCESS_V3 | 0903481652 JE9012 |  | KAHATEX CIJERAH | ITALY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903481790-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903481790 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903482150-1 KZ0925 | AURORA COFFEE S26/BRIGHT PINK F27 | 90D | S2754WESS421WV | 18 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  |  |  | MOQ Issue 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482150 KZ0925 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV SHO 54 AURORA COFFEE S26/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903482152-1 KB5964 | DUSKY ORANGE S26 | 120D | S2608MR0900A | 300 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 680015 | HT+PAD SUB PROCESS_V3 | 0903482152 KB5964 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903482169-1 KZ4392 | WHITE | 120D | F2608WR1500 | 19 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903482169 KZ4392 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE W WHITE |  | SS27-TRAX
ADIDAS | 0903482200-1 IN1159 | BLACK | 90D | S2408MR1601 | 23 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482200 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482201-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903482201 JM1779 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903482233-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 684009 | HT SUB PROCESS_V1 | 0903482233 KD9849 |  | KAHATEX CIJERAH | PERU | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903482238-1 IN1159 | BLACK | 90D | S2408MR1601 | 65 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482238 IN1159 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903482281-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482281 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482305-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 239 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 512106 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903482305 LF0725 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903482323-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903482323 KD3911 |  | KAHATEX CIJERAH | ITALY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903482414-1 JF3604 | BLACK/WHITE | 90D | S2554MESS675FT | 6500 | 23/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 823016 | PRINT L1 SUB PROCESS_V3 | 0903482414 JF3604 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | M WIDE PANT FT |  | SS27
ADIDAS | 0903482425-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2750 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903482425 HK7317 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482462-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 600 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903482462 KF6290 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903482511-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 2070 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903482511 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482547-1 HK7319 | BLACK | 90D | F2225M403 | 3001 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903482547 HK7319 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482561-1 HK7319 | BLACK | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903482561 HK7319 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482623-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 3781 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903482623 HK7317 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903482634-1 IC5189 | WHITE | 90D | S23080640 | 4000 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 823016 | HT SUB PROCESS_V1 | 0903482634 IC5189 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903482892-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 670 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482892 KR3066 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903482957-1 KA6229 | BLACK | 120D | S2608WR0202 | 492 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903482957 KA6229 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903483164-1 KB5960 | WHITE | 120D | S2608MR0900A | 791 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 680015 | HT+PAD SUB PROCESS_V3 | 0903483164 KB5960 |  | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903483208-1 IN1173 | WHITE | 105D | S2408WR1600 | 968 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483208 IN1173 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483237-1 JZ7711 | BLACK | 120D | S2608MR0202 | 300 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903483237 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903483311-1 KA4331 | BLACK | 90D | S2608MR0902 | 1048 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 680015 | PAD+HT SUB PROCESS_V3 | 0903483311 KA4331 |  | KAHATEX CIJERAH | CHILE | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903483320-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903483320 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483346-1 IN8707 | BLACK | 105D | S2408WR1601A | 580 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903483346 IN8707 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483362-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903483362 HK7303 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903483384-1 IN1156 | BLACK | 105D | S2408MR1600 | 968 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 680015 | HT SUB PROCESS_V1 | 0903483384 IN1156 |  | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483459-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 300 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 680015 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903483459 IN1159 | 29/10/2026 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903483478-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516205 | EMBRO+PPA SUB PROCESS_V3 | 0903483478 HK7317 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483493-1 IN1172 | BLACK | 105D | S2408WR1600 | 948 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 680015 | HT SUB PROCESS_V1 | 0903483493 IN1172 | 2026-12-11 | KAHATEX CIJERAH | CHILE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483511-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 2069 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903483511 HK7317 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903483546-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903483546 JE6414 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903483584-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 3000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903483584 KD3911 |  | KAHATEX CIJERAH | SPAIN | SEA |  | RELEASED |  | SS27
ADIDAS | 0903483666-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 144 | 2026-07-12 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L2 SUB PROCESS_V3 | 0903483666 LI7659 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903483676-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 300 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 830009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903483676 JM1775 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903483703-1 IP2310 | BLACK | 105D | S2450MTR701 | 330 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 830009 | HT SUB PROCESS_V1 | 0903483703 IP2310 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903483721-1 HZ0747 | BLACK | 90D | F2325M414 | 393 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483721 HZ0747 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PL TEE |  | SS27
ADIDAS | 0903483722-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 104 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483722 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903483757-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 226 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483757 LE8199 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903483769-1 LC9621 | OFF WHITE | 90D | S2725M920 | 177 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903483769 LC9621 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | CROWN OFF WHITE |  | SS27-STX
ADIDAS | 0903483798-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 300 | 2026-07-11 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903483798 KA5089 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903483800-1 LF5065 | LIME TINT S27 | 90D | F2625M101 | 939 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903483800 LF5065 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE LIME TINT S27 |  | SS27-L2L
ADIDAS | 0903483831-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 7 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 830009 | PRINT L3+PAD SUB PROCESS_V3 | 0903483831 LE5779 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903483841-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 100 | 2026-07-12 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903483841 JE6340 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903483884-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 139 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903483884 JE0052 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903483889-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 100 | 2026-07-12 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903483889 JC9584 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903483932-1 IN1173 | WHITE | 105D | S2408WR1600 | 423 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 830009 | HT SUB PROCESS_V1 | 0903483932 IN1173 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903483940-1 KY1333 | SILVER BLUE TINT S27 | 90D | S27SPRMGFXH211 | 311 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1+PAD SUB PROCESS_V3 | 0903483940 KY1333 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M PANCAKE T SILVER BLUE TINT S27 |  | SS27-STX
ADIDAS | 0903483981-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 120 | 2026-07-12 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 830009 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903483981 JE6340 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903483984-1 KX3653 | SILVER PURPLE S27 | 120D | S2608MR0900A | 368 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903483984 KX3653 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M SILVER PURPLE S27 |  | SS27-TI
ADIDAS | 0903484021-1 IN2961 | BLACK | 105D | S2408WR2400 | 456 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903484021 IN2961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903484027-1 KT7395 | AURORA IVY F25 | 90D | F2625M101 | 1006 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 830009 | EMBRO SUB PROCESS_V1 | 0903484027 KT7395 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ESS REG TEE AURORA IVY F25 |  | SS27-L2L
ADIDAS | 0903484055-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 400 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484055 LE8191 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903484065-1 KW9040 | TEAM NAVY BLUE 2/WHITE | 90D | S2754MESS659PQ | 246 | 2026-07-12 |  | SI | SI14/08/2026 |  | POLO SHIRT |  | (15/09/2026) |  | 830009 | EMBRO+PPA SUB PROCESS_V3 | 0903484065 KW9040 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 3B PQ PS TEAM NAVY BLUE 2/WHITE |  | SS27-STX
ADIDAS | 0903484097-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 745 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484097 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903484129-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 139 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484129 LE5779 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484522-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 1036 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903484522 KZ1286 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903484567-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 1037 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484567 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903484603-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 163 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484603 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903484610-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 2640 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484610 KZ3200 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903484626-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 302 | 30/11/2026 | 302 | SI | SI14/08/2026 | G3J | SHORTS | G3 |  |  | Waiting fabric. DRC 0084-T2 Grand Tex, Unfc material, PI Date 11-Oct. Waiting fabric. T2 Y.R.C, PI Date 25-Sep, ETD ?? 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903484626 KC9082 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA | 28/11/2026 | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX | 28/11/2026 | 30/11/2026 |  |  | 302 |  | 302 |  |  | 25/11/2026 | 25/11/2026 |  |  | 302 |  | 302 |  |  | 20/11/2026 | 20/11/2026 |  |  | 302 |  | 302
ADIDAS | 0903484639-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1599 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903484639 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903484642-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 4029 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903484642 KZ1286 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903484665-1 HK7319 | BLACK | 90D | F2225M403 | 3001 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903484665 HK7319 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484713-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516442 | EMBRO+PPA SUB PROCESS_V3 | 0903484713 HR8583 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484845-1 HK7317 | WONDER STEEL F22 | 90D | F2225M403 | 1080 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516204 | EMBRO+PPA SUB PROCESS_V3 | 0903484845 HK7317 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903484894-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3752 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | EMBRO SUB PROCESS_V1 | 0903484894 IB8686 |  | KAHATEX CIJERAH | SPAIN | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903484896-1 IP2310 | BLACK | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903484896 IP2310 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903484940-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903484940 IB8688 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485008-1 KE9656 | BLACK | 105D | S2608WR0201A | 308 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485008 KE9656 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485025-1 KF6290 | KHAKI SIX F26/WHITE | 90D | S2554WES512FT | 2101 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (25/09/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485025 KF6290 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485027-1 HK7309 | BLACK | 45D | F2225M402 | 1500 | 15/11/2026 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903485027 HK7309 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903485046-1 KE9656 | BLACK | 105D | S2608WR0201A | 300 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485046 KE9656 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485074-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1000 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516205 | HT SUB PROCESS_V1 | 0903485074 IW8374 | 2026-12-11 | KAHATEX CIJERAH | SPAIN | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903485085-1 KE9656 | BLACK | 105D | S2608WR0201A | 7387 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485085 KE9656 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485092-1 JW7178 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES512FT | 4500 | 23/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903485092 JW7178 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT OH PT |  | SS27
ADIDAS | 0903485117-1 KE9656 | BLACK | 105D | S2608WR0201A | 746 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485117 KE9656 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903485121-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 201 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903485121 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903485469-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485469 LE5780 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903485504-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 336 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485504 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485529-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 135 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903485529 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903485559-1 IN2961 | BLACK | 105D | S2408WR2400 | 131 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903485559 IN2961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903485625-1 IN8707 | BLACK | 105D | S2408WR1601A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (29/10/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903485625 IN8707 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903486162-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 129 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486162 LE8212 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903486211-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1218 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486211 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486240-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 743 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486240 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903486327-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | Waiting fabric. DRC 0084-T2 Far Eastearn, Unfc material, PI Date 12-Oct, ETD ?? T2 Hua Feng, PI Date 23-Oct, actual receives 05-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486327 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903486390-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 817 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903486390 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903486424-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 826010 | PRINT L1 SUB PROCESS_V3 | 0903486424 LE1842 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903486448-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 238 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903486448 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903486503-1 KB5960 | WHITE | 120D | S2608MR0900A | 159 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903486503 KB5960 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903486538-1 KC8568 | BLACK | 105D | OJS26250839 | 512 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 848016 | PRINT L1 SUB PROCESS_V3 | 0903486538 KC8568 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903486574-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 588 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848016 | HT+PAD SUB PROCESS_V3 | 0903486574 KX3654 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903486601-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 207 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 848012 | EMBRO SUB PROCESS_V1 | 0903486601 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903486617-1 KG3189 | MAROON | 120D | S2608MR0900A | 774 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903486617 KG3189 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903486653-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 304 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486653 KC9082 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486667-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 675 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486667 LE8199 | 29/10/2026 | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486678-1 KC9082 | GREY SIX S19 | 105D | S2608MR0201B | 428 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486678 KC9082 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486695-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 174 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903486695 LE8199 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903486712-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 4334 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486712 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486725-1 IC5188 | BLACK | 90D | S23080640 | 146 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903486725 IC5188 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486777-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 328 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903486777 IL4127 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486778-1 IN2961 | BLACK | 105D | S2408WR2400 | 106 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486778 IN2961 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903486789-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1249 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486789 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486817-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 537 | 15/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | IMPROVE (AP Siti FU). DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903486817 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903486860-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 106 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516443 | PRINT L2 SUB PROCESS_V3 | 0903486860 LI7659 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903486892-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 217 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486892 IN1172 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486900-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486900 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486938-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 313 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486938 IN1157 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903486940-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 1100 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486940 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486943-1 IC5188 | BLACK | 90D | S23080640 | 223 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903486943 IC5188 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903486967-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903486967 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903486972-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 102 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903486972 IN1172 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487011-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 500 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903487011 IL4127 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487014-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 250 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487014 IN1157 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487018-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 900 | 30/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487018 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903487045-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 1000 | 15/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487045 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487057-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 897 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487057 IN1156 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487080-1 IC5189 | WHITE | 90D | S23080640 | 282 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487080 IC5189 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487085-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 1152 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487085 KW2924 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903487088-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487088 IN1156 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903487099-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 193 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903487099 IL4127 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903487117-1 KZ3231 | SILVER BLUE S27/WHITE | 90D | S2754WESS703WV | 792 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487117 KZ3231 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 33S WV BER SHO SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903487139-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 2460 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487139 JM1775 | 29/10/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487150-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 1916 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487150 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903487175-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487175 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487213-1 KQ8640 | BLACK/GREY SIX S19 | 105D | S2608MR0201B | 456 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (11/09/2026) |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487213 KQ8640 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADI365 SHO M BLACK/GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903487239-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 180 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487239 LE8191 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487255-1 IP2310 | BLACK | 105D | S2450MTR701 | 600 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903487255 IP2310 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903487261-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 1380 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516442 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487261 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903487265-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 3752 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903487265 IB8686 |  | KAHATEX CIJERAH | ITALY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903487276-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 180 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487276 LE5780 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487306-1 IB8688 | SILVER GREEN S23 | 45D | F2225M402 | 2500 | 2026-07-11 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 823016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487306 IB8688 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903487310-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 5500 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (25/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903487310 JE0052 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903487320-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487320 LE8189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903487353-1 HK7319 | BLACK | 90D | F2225M403 | 3780 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903487353 HK7319 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903487361-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487361 LE5779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487397-1 HZ0747 | BLACK | 90D | F2325M414 | 3750 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | EMBRO SUB PROCESS_V1 | 0903487397 HZ0747 |  | KAHATEX CIJERAH | ITALY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903487403-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 210 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487403 LE8192 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487447-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 180 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 512102 | PRINT L3+PAD SUB PROCESS_V3 | 0903487447 LE8190 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487491-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 165 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 512106 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903487491 LE1843 | 29/10/2026 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903487543-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 666 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903487543 LE8190 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487580-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 672 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903487580 LE8191 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903487621-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 450 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903487621 LE8190 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903487766-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 352 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487766 KZ3200 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903487767-1 JZ7711 | BLACK | 120D | S2608MR0202 | 972 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487767 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903487796-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 500 | 30/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903487796 KV7863 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903487864-1 JZ7709 | BLACK | 120D | S2608MR0201 | 655 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | ok |  | IMPROVE. DRC 0084-T2 Hua Feng, Unfc material, PI Date 23-Oct, actual receives 04-Sep (swicth from TRAX). T2 Y.R.C, PI Date 14-Sep, actual receives 03-Sep (swicth from TRAX). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487864 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903487940-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | (By Air-Collect). 960026 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903487940 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | AIR-COLLECT |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903488043-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 637 | 23/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488043 LE8191 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488075-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 637 | 23/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488075 LE5780 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488135-1 JZ7709 | BLACK | 120D | S2608MR0201 | 125 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488135 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903488174-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 400 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903488174 LE8189 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903488196-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 219 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 516333 | PRINT L3+PPA SUB PROCESS_V3 | 0903488196 LH3759 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488207-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 200 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 826010 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903488207 LE1843 | 29/10/2026 | KAHATEX CIJERAH | TURKEY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488242-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 416 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903488242 LE5780 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903488269-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 512 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903488269 LE8189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903488273-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 283 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488273 KR3066 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488304-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 450 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903488304 LE5779 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903488315-1 KD3875 | BLACK | 120D | S2608WR0201 | 300 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488315 KD3875 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488341-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 895 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488341 KR3066 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488343-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 728 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903488343 KX3654 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903488376-1 KD3875 | BLACK | 120D | S2608WR0201 | 962 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488376 KD3875 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488379-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 195 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 848012 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903488379 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488411-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 902 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903488411 JE0055 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903488465-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 60 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903488465 LI5438 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488476-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 1402 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488476 KR3066 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-L2L
ADIDAS | 0903488504-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 848012 | HT SUB PROCESS_V1 | 0903488504 KG8548 | 2026-12-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903488561-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 275 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516443 | PRINT L1 SUB PROCESS_V3 | 0903488561 LI7655 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903488578-1 KD3875 | BLACK | 120D | S2608WR0201 | 2494 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488578 KD3875 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488621-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 209 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 672027 | PAD+HT SUB PROCESS_V3 | 0903488621 LG1784 | 2026-12-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903488668-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 91 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960006 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903488668 LE1843 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488689-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 104 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 834012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488689 LF0725 |  | KAHATEX CIJERAH | ISRAEL | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488715-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 52 | 2026-07-12 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903488715 LE1842 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488727-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 338 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 547012 | PRINT L3+PPA SUB PROCESS_V3 | 0903488727 LH3759 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488769-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 311 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 512106 | PRINT L3+PPA SUB PROCESS_V3 | 0903488769 LH3759 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903488772-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 101 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903488772 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903488783-1 KR2011 | LIGHT GREY HEATHER | 60D | F26KCNYGFX100 | 1179 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (29/09/2026) |  | 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488783 KR2011 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | BIG APPLE TEE |  | SS27
ADIDAS | 0903488800-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 102 | 15/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512106 | EMBRO SUB PROCESS_V1 | 0903488800 KW6443 |  | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488806-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 160 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488806 IN1172 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488826-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 291 | 2026-07-12 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903488826 LE1842 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903488837-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 110 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848016 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488837 LF0725 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488855-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 122 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903488855 IN1172 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903488870-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 100 | 30/11/2026 |  | AN | AN14/08/2026 |  | JACKET |  | (15/09/2026) |  | 512108 | EMBRO SUB PROCESS_V1 | 0903488870 KW6443 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903488877-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 364 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903488877 LE1843 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903488902-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 589 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516439 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488902 KZ1286 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903488910-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 260 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848012 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488910 LF0725 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488914-1 KR2013 | TEAM ROYAL BLUE | 60D | F26KCNYGFX120 | 1047 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488914 KR2013 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488933-1 KS1837 | BLACK | 60D | F26KCNYGFX120 | 272 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903488933 KS1837 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ARC OVERLAY TEE |  | SS27
ADIDAS | 0903488935-1 KE9656 | BLACK | 105D | S2608WR0201A | 394 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (09/09/2026) |  | 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903488935 KE9656 | 2026-12-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADI365 SHO W BLACK |  | SS27-TRAX
ADIDAS | 0903488952-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 400 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488952 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903488971-1 LF0725 | OLIVE ONE S27 | 105D | S2754MAS511B | 142 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (15/10/2026) |  | 848024 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903488971 LF0725 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M SL WV SHO OLIVE ONE S27 |  | SS27
ADIDAS | 0903488989-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 594 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903488989 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903489018-1 LD0293 | SEMI SOLAR AQUA S27 | 105D | S2608WR0901 | 664 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489018 LD0293 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Shor W SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903489036-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 452 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | 848012 | PRINT L3+PPA SUB PROCESS_V3 | 0903489036 LH3759 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 0903489050-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 2092 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489050 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903489070-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 116 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489070 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489077-1 LG1784 | PRELOVED INK S24 | 120D | F2608MR1500 | 125 | 15/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 600000 | PAD+HT SUB PROCESS_V3 | 0903489077 LG1784 | 2026-12-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO A TEE M PRELOVED INK S24 |  | SS27-TRAX
ADIDAS | 0903489080-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 506 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489080 LE8192 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489083-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 317 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489083 KZ1286 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 0903489098-1 JM1778 | BLACK/WHITE | 90D | F2554MESS710WV | 199 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 1st Art (TC 10 pcs) 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489098 JM1778 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903489106-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1764 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489106 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903489115-1 KA0246 | BLACK | 105D | S2608WR0902 | 375 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489115 KA0246 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489142-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 150 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903489142 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903489144-1 KA0246 | BLACK | 105D | S2608WR0902 | 890 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489144 KA0246 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903489152-1 LE5780 | ACTIVE MAROON F19 | 90D | F2606LHLF101FY | 400 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903489152 LE5780 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903489188-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 160 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 848012 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903489188 LE1843 | 29/10/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489228-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 848016 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489228 KZ3200 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903489267-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 337 | 23/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489267 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903489318-1 KC6386 | BLACK | 30D | F25GFXBLANKM | 924 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | ok |  | 839055 | EMBRO SUB PROCESS_V1 | 0903489318 KC6386 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903489329-1 LK1407 | WARM CLAY S25/WHITE | 90D | S2754WESS422WV | 510 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903489329 LK1407 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV BOMBER WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903489359-1 IL4127 | WONDER ORCHID F23 | 90D | S23080640 | 349 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903489359 IL4127 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903489634-1 JZ7711 | BLACK | 120D | S2608MR0202 | 9365 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903489634 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903489679-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L2 SUB PROCESS_V3 | 0903489679 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903489684-1 KB5965 | BLACK | 120D | S2608MR0900A | 1484 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | HT+PAD SUB PROCESS_V3 | 0903489684 KB5965 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903489712-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 939 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 630001 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903489712 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489746-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489746 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903489781-1 LG8054 | LIGHT GREY HEATHER | 90D | S2762LHME151K | 168 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489781 LG8054 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE K LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489814-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 179 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | ok |  | 630001 | PRINT L3 SUB PROCESS_V3 | 0903489814 LG8055 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903489854-1 LI7655 | BLACK | 90D | S2762LHMEKA205M | 100 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 630001 | PRINT L1 SUB PROCESS_V3 | 0903489854 LI7655 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA GFTEE M BLACK |  | SS27-MS
ADIDAS | 0903489856-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 149 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 678002 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903489856 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489883-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 60 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903489883 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489886-1 LI7658 | WHITE | 90D | S2762LHMEKA201M | 109 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 630001 | PRINT L2 SUB PROCESS_V3 | 0903489886 LI7658 | 29/10/2026 | KAHATEX CIJERAH | CANADA | SEA |  | MER KA NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903489914-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 314 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 659018 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903489914 LE1843 | 29/10/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903489924-1 IN1157 | WHITE | 105D | S2408MR1600 | 304 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 516443 | HT SUB PROCESS_V1 | 0903489924 IN1157 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903489972-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903489972 JE6414 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903490017-1 KA4331 | BLACK | 90D | S2608MR0902 | 301 | 2026-07-12 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903490017 KA4331 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903490085-1 KA4331 | BLACK | 90D | S2608MR0902 | 345 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516443 | PAD+HT SUB PROCESS_V3 | 0903490085 KA4331 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903490142-1 JM1779 | DARK BLUE/WHITE | 90D | F2554MESS710WV | 100 | 15/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (18/09/2026) |  | 848012 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490142 JM1779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M SL WV PT 1 |  | SS27
ADIDAS | 0903490211-1 JZ7709 | BLACK | 120D | S2608MR0201 | 125 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | IMPROVE. DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490211 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903490270-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490270 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903490324-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 150 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903490324 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490413-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1058 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490413 JZ7709 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903490610-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 1905 | 15/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903490610 LL1874 | 29/10/2026 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903490651-1 LK1408 | WARM CLAY S25/WHITE | 90D | S2754WESS404WV | 840 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903490651 LK1408 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT WARM CLAY S25/WHITE |  | SS27
ADIDAS | 0903490660-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 109 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 672027 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903490660 LE1843 | 29/10/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903490726-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 2524 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490726 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903490766-1 KA0246 | BLACK | 105D | S2608WR0902 | 101 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903490766 KA0246 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903490854-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 2408 | 15/12/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490854 LE8202 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903490891-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 120 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490891 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903490983-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 205 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903490983 LE8202 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903491185-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 705 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | ok |  | 825066 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903491185 LE1843 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903491231-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 301 | 2026-07-12 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491231 LE1842 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903491240-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 246 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491240 KG8548 |  | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903491398-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 672 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491398 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903491513-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 103 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903491513 IN1172 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491552-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 350 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 825057 | PRINT L1 SUB PROCESS_V3 | 0903491552 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903491598-1 JZ7711 | BLACK | 120D | S2608MR0202 | 5645 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491598 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903491612-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 358 | 2026-07-12 |  | SA | SA14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903491612 LJ4075 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903491644-1 JZ7711 | BLACK | 120D | S2608MR0202 | 2005 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491644 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903491720-1 KA0246 | BLACK | 105D | S2608WR0902 | 321 | 2026-07-12 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491720 KA0246 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491769-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 101 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903491769 IN1156 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903491790-1 KA0246 | BLACK | 105D | S2608WR0902 | 395 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491790 KA0246 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491808-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 400 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 814006 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903491808 JD9944 |  | KAHATEX CIJERAH | THAILAND | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903491821-1 KA0246 | BLACK | 105D | S2608WR0902 | 306 | 2026-07-12 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491821 KA0246 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491835-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 570 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491835 LE8199 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903491866-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 824 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491866 LE8190 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903491891-1 KB5960 | WHITE | 120D | S2608MR0900A | 379 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903491891 KB5960 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903491896-1 LJ9159 | TEAM COLLEG RED | 90D | 226205_X5UY | 15000 | 20/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903491896 LJ9159 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | PSJ H JSY FAN TEAM COLLEG RED |  | SS27-L2L
ADIDAS | 0903491932-1 KA0246 | BLACK | 105D | S2608WR0902 | 413 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903491932 KA0246 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903491960-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 800 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903491960 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903491970-1 KB5965 | BLACK | 120D | S2608MR0900A | 404 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516342 | HT+PAD SUB PROCESS_V3 | 0903491970 KB5965 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903492013-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 1000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492013 LE8202 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903492051-1 LE8191 | BETTER SCARLET S23 | 90D | F2606LHAF101YF | 112 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492051 LE8191 |  | KAHATEX CIJERAH | THAILAND | SEA |  | AFC H FY JSY SE |  | SS27-FJ
ADIDAS | 0903492057-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 488 | 30/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903492057 LI7656 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903492098-1 LE8212 | WHITE | 90D | F2606LHLF102MFL | 600 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492098 LE8212 |  | KAHATEX CIJERAH | THAILAND | SEA |  | LFC A F JSYL SE |  | SS27-FJ
ADIDAS | 0903492176-1 JZ7711 | BLACK | 120D | S2608MR0202 | 486 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 980004 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903492176 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903492207-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 766 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848024 | HT+PAD SUB PROCESS_V3 | 0903492207 KX3654 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903492214-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY-MTF | 637 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 960006 | PRINT L3+PAD SUB PROCESS_V3 | 0903492214 LE8189 |  | KAHATEX CIJERAH | AUSTRALIA | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903492245-1 KC8568 | BLACK | 105D | OJS26250839 | 357 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | DRC 0090-early shipment customer (Urgent Egypt GFO - Mid August POs: Support Required for PODD Improvement on Affected POs cb_om). 512102 | PRINT L1 SUB PROCESS_V3 | 0903492245 KC8568 | 2026-12-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903492261-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 427 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492261 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903492296-1 KB5965 | BLACK | 120D | S2608MR0900A | 144 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903492296 KB5965 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903492308-1 LI7657 | BLACK | 90D | S2762LHMEGR101M | 744 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903492308 LI7657 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER GR NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903492329-1 KG8548 | SOLAR TURBO F26 | 105D | S2408MR1600 | 1200 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 848012 | HT SUB PROCESS_V1 | 0903492329 KG8548 | 2026-12-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903492373-1 KG3189 | MAROON | 120D | S2608MR0900A | 810 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 848012 | HT+PAD SUB PROCESS_V3 | 0903492373 KG3189 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | Run Ess Tee M MAROON |  | SS27-TI
ADIDAS | 0903492599-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 312 | 2026-07-12 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 806020 | PRINT L3+HT SUB PROCESS_V3 | 0903492599 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903493200-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 184 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | (NYK warehouse). 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903493200 LD0908 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903493244-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 5000 | 23/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 823016 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903493244 JE0055 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903493287-1 IP2310 | BLACK | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493287 IP2310 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903493324-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 1200 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  |  |  | 516442 | HT SUB PROCESS_V1 | 0903493324 IW8374 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903493332-1 LE8199 | WHITE | 90D | F2606LHLF102MFN | 669 | 2026-07-12 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | (NYK warehouse). 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903493332 LE8199 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC A F JSY SE |  | SS27-FJ
ADIDAS | 0903493415-1 JE6340 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS601FT | 750 | 15/12/2026 |  | SA | SA14/08/2026 |  | JACKET |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903493415 JE6340 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903493572-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 504 | 23/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493572 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493612-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 162 | 2026-07-11 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903493612 LE4570 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903493664-1 LI5438 | OLIVE TWO S27 | 90D | S2762LHAMG125 | 301 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 825066 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903493664 LI5438 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AMG SEL GFX T OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903493721-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 502 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 825056 | PRINT L1 SUB PROCESS_V3 | 0903493721 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493751-1 JZ7711 | BLACK | 120D | S2608MR0202 | 142 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903493751 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903493752-1 KR2005 | DARK BLUE | 60D | F26KCMIAGFX100 | 1200 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493752 KR2005 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493772-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 357 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493772 LI7656 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903493807-1 KS2151 | WHITE | 60D | F26KCLAGFX100 | 364 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | ok |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493807 KS2151 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493831-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 1027 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903493831 KA6260 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903493884-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 350 | 2026-07-12 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493884 LG8052 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903493891-1 KR2006 | WHITE | 60D | F26KCMIAGFX100 | 1199 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493891 KR2006 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | SPORT GOODS T |  | SS27
ADIDAS | 0903493893-1 LD0277 | OLIVE TWO S27 | 90D | S2608MR0902 | 510 | 15/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (18/09/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903493893 LD0277 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M OLIVE TWO S27 |  | SS27-TRAX
ADIDAS | 0903493941-1 LG8051 | LIGHT GREY HEATHER | 90D | S2762LHME152M | 400 | 2026-07-12 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/10/2026) |  | 825066 | PRINT L1 SUB PROCESS_V3 | 0903493941 LG8051 | 29/10/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER L IR HD M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903493942-1 KS2152 | TEAM ROYAL BLUE | 60D | F26KCLAGFX100 | 1193 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 600000 | PRINT L3+PAD SUB PROCESS_V3 | 0903493942 KS2152 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | LA PALMS TEE |  | SS27
ADIDAS | 0903493960-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 420 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516438 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903493960 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903493998-1 LG8052 | LIGHT GREY HEATHER | 90D | S2762LHME146M | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (10/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903493998 LG8052 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC CRW M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494030-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 323 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903494030 KA6260 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903494054-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 722 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | ok |  | 600000 | PRINT L3 SUB PROCESS_V3 | 0903494054 LG8055 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494105-1 LG8056 | LIGHT GREY HEATHER | 90D | S2762LHME145M | 762 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903494105 LG8056 | 29/10/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER L TC TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903494115-1 KA6260 | GREY SIX S19 | 120D | S2608MR0202 | 365 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 1st Art (TC 10 pcs) 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903494115 KA6260 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 M GREY SIX S19 |  | SS27-TRAX
ADIDAS | 0903494146-1 LE8189 | MUFC RED | 90D | F2606LHMU101FY | 110 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 814006 | PRINT L3+PAD SUB PROCESS_V3 | 0903494146 LE8189 |  | KAHATEX CIJERAH | THAILAND | SEA |  | MUFC HFY JSY SE |  | SS27-FJ
ADIDAS | 0903494166-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 15000 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494166 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494205-1 KB5960 | WHITE | 120D | S2608MR0900A | 219 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516205 | HT+PAD SUB PROCESS_V3 | 0903494205 KB5960 |  | KAHATEX CIJERAH | SPAIN | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903494218-1 LG4333 | WHITE | 90D | F2606LEMBU207MF | 12288 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494218 LG4333 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC A JSY FAN WHITE |  | SS27-L2L
ADIDAS | 0903494219-1 KY1366 | CLOUD WHITE F18 | 90D | S2706CHRM037 | 118 | 23/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 830009 | PRINT L1 SUB PROCESS_V3 | 0903494219 KY1366 | 29/10/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | REAL 125 TEE CLOUD WHITE F18 |  | SS27-STX
ADIDAS | 0903494261-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 194 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903494261 IN1156 | 2026-12-11 | KAHATEX CIJERAH | VIETNAM | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494278-1 LG4332 | TEAM POWER RED 2 | 90D | F2606LEMBU107MF | 488 | 20/11/2026 |  | NT | NT14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). 800005 | PRINT L1 SUB PROCESS_V3 | 0903494278 LG4332 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | BUFC H JSY FAN TEAM POWER RED 2 |  | SS27-L2L
ADIDAS | 0903494292-1 IN1172 | BLACK | 105D | S2408WR1600-SLT | 109 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494292 IN1172 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494356-1 KG2925 | PURE RUBY S25 | 90D | F2606CHLF040 | 1 | 15/11/2026 |  | NT | NT14/08/2026 |  | SWEATSHIRT |  |  |  | (NYK warehouse). 800005 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903494356 KG2925 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC LF HD |  | SS27
ADIDAS | 0903494364-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 170 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494364 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494394-1 LI7659 | BLACK | 90D | S2762LHMEKA201M | 391 | 30/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | (NYK warehouse). 800005 | PRINT L2 SUB PROCESS_V3 | 0903494394 LI7659 | 29/10/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | MER KA NNTEE M BLACK |  | SS27-MS
ADIDAS | 0903494489-1 IN1156 | BLACK | 105D | S2408MR1600-SLT | 163 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494489 IN1156 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494517-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 334 | 2026-07-11 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494517 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494550-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2000 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494550 JE6419 |  | KAHATEX CIJERAH | JAPAN | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903494560-1 IN1157 | WHITE | 105D | S2408MR1600-SLT | 196 | 15/11/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903494560 IN1157 | 2026-12-11 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E TEE |  | SS27-YTI-SLT
ADIDAS | 0903494587-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1250 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 804028 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903494587 JE0055 |  | KAHATEX CIJERAH | JAPAN | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903494709-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 230 | 30/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3 SUB PROCESS_V3 | 0903494709 LE1858 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903494746-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 340 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 859013 | PRINT L3+HT SUB PROCESS_V3 | 0903494746 LE4570 | 30/09/2026 | KAHATEX CIJERAH | TAIWAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903495154-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 131 | 2026-07-11 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495154 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495200-1 JW9678 | POWDER PLUM F25 | 105D | S2408WR2400 | 124 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495200 JW9678 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE POWDER PLUM F25 |  | SS27
ADIDAS | 0903495205-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 390 | 2026-07-11 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495205 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495231-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 473 | 2026-07-11 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3 SUB PROCESS_V3 | 0903495231 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495267-1 LE1858 | UTILITY BLACK F16 | 60D | S2762LHAU373 | 422 | 15/11/2026 |  | ID | ID14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3 SUB PROCESS_V3 | 0903495267 LE1858 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | AU DNA PET JSY UTILITY BLACK F16 |  | SS27-MS
ADIDAS | 0903495304-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 100 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825066 | PRINT L3+HT SUB PROCESS_V3 | 0903495304 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495328-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 354 | 2026-07-11 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825065 | PRINT L3+HT SUB PROCESS_V3 | 0903495328 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495368-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 541 | 2026-07-11 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825056 | PRINT L3+HT SUB PROCESS_V3 | 0903495368 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495389-1 IK7442 | WHITE | 105D | S2408WR2400 | 104 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (19/09/2026) |  | (NYK warehouse). 800005 | HT SUB PROCESS_V1 | 0903495389 IK7442 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE WHITE |  | SS27
ADIDAS | 0903495436-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 732 | 15/11/2026 |  | SI | SI14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 825057 | PRINT L3+HT SUB PROCESS_V3 | 0903495436 LJ2754 | 30/09/2026 | KAHATEX CIJERAH | CHINA | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903495584-1 IN1173 | WHITE | 105D | S2408WR1600 | 390 | 30/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (11/09/2026) |  | (NYK warehouse). IMPROVE (AP Siti FU). DRC 0002/T2 Capacity LLT from Far Eastern (VNM), PI date: 20-Oct (DOL 30D). 800005 | HT SUB PROCESS_V1 | 0903495584 IN1173 | 2026-12-11 | KAHATEX CIJERAH | INDONESIA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903495692-1 KA6229 | BLACK | 120D | S2608WR0202 | 155 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495692 KA6229 | 2026-12-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903495805-1 KD3854 | GREY SIX S19 | 120D | S2608MR0201 | 146 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495805 KD3854 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M GREY SIX S19 |  | SS27-L2L
ADIDAS | 0903495847-1 KA6229 | BLACK | 120D | S2608WR0202 | 885 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495847 KA6229 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903495915-1 KA0235 | BLACK | 105D | S2608WR0901 | 373 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495915 KA0235 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903495966-1 IN1159 | BLACK | 90D | S2408MR1601-MTF | 353 | 30/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (29/10/2026) |  | DRC 0002/T2 Capacity LLT from Huafeng (VNM), PI date: 29-Oct (DOL 17D). 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903495966 IN1159 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903496004-1 KY9431 | SEMI SOLAR VIOLET S27 | 120D | S2608WR0201 | 1300 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496004 KY9431 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903496037-1 KA6229 | BLACK | 120D | S2608WR0202 | 7030 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496037 KA6229 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496061-1 KY9393 | HAZE CORAL S17 | 120D | S2608WR0201 | 1623 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (13/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496061 KY9393 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO W HAZE CORAL S17 |  | SS27-TRAX
ADIDAS | 0903496078-1 KA6229 | BLACK | 120D | S2608WR0202 | 4363 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496078 KA6229 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496125-1 KA6229 | BLACK | 120D | S2608WR0202 | 284 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | 1st Art (TC 10 pcs) 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496125 KA6229 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903496214-1 KS1838 | WHITE | 60D | F26KCNYGFX130 | 370 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496214 KS1838 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496277-1 KR2014 | DARK BLUE | 60D | F26KCNYGFX130 | 1181 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 1st Art (TC 10 pcs) 600000 | PRINT L2+PAD SUB PROCESS_V3 | 0903496277 KR2014 | 30/09/2026 | KAHATEX CIJERAH | UNITED STATES | SEA |  | RUNNING PRGM T |  | SS27
ADIDAS | 0903496289-1 JZ7709 | BLACK | 120D | S2608MR0201 | 388 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516394 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496289 JZ7709 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903496298-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 870 | 30/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 804028 | PRINT L3+HT SUB PROCESS_V3 | 0903496298 LE4570 | 30/09/2026 | KAHATEX CIJERAH | JAPAN | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903496341-1 JZ7709 | BLACK | 120D | S2608MR0201 | 3288 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496341 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903496389-1 JZ7711 | BLACK | 120D | S2608MR0202 | 100 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | DRC 0064/Customer Others Didn't receive MCAF Speed LT (NOOS). 960006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903496389 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 0903496490-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 196 | 2026-07-12 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 834012 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903496490 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ISRAEL | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903497678-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 1001 | 15/11/2026 |  | SI | SI14/08/2026 |  | JACKET |  | (29/09/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903497678 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903498196-1 JZ7709 | BLACK | 120D | S2608MR0201 | 9552 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498196 JZ7709 |  | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498235-1 JZ7709 | BLACK | 120D | S2608MR0201 | 208 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516343 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498235 JZ7709 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498251-1 KZ3056 | BLACK | 90D | S2762LHMEDR103M | 216 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498251 KZ3056 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNHD M BLACK |  | SS27-MS
ADIDAS | 0903498284-1 JZ7709 | BLACK | 120D | S2608MR0201 | 419 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498284 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498288-1 LG8055 | LIGHT GREY HEATHER | 90D | S2762LHME150M | 151 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | ok |  | 516333 | PRINT L3 SUB PROCESS_V3 | 0903498288 LG8055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER L IR TEE M LIGHT GREY HEATHER |  | SS27-MS
ADIDAS | 0903498314-1 LI7656 | WHITE | 90D | S2762LHMEGR101M | 140 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903498314 LI7656 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER GR NNTEE M WHITE |  | SS27-MS
ADIDAS | 0903498332-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1536 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498332 JZ7709 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 0903498480-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 216 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498480 LD0908 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498515-1 LD0908 | SILVER BLUE S27 | 105D | S2608WR0902 | 800 | 30/11/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903498515 LD0908 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SILVER BLUE S27 |  | SS27-TRAX
ADIDAS | 0903498576-1 KZ3055 | BLACK | 90D | S2762LHMEDR206K | 115 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516333 | PRINT L2 SUB PROCESS_V3 | 0903498576 KZ3055 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | MER KA GFTEE K BLACK |  | SS27-MS
ADIDAS | 0903499076-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 112 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 1st Art (TC 10 pcs) 516342 | HT+PAD SUB PROCESS_V3 | 0903499076 KX3654 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903499118-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 317 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 516443 | HT+PAD SUB PROCESS_V3 | 0903499118 KX3654 |  | KAHATEX CIJERAH | ITALY | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 0903499304-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1938 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499304 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499328-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 2068 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499328 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499369-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 554 | 15/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499369 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499422-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 1590 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499422 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499455-1 KU0090 | TEAM CRIMSON/WHITE | 90D | S2625W005 | 745 | 30/11/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903499455 KU0090 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | 3S TEE SLIM TEAM CRIMSON/WHITE |  | SS27-STX
ADIDAS | 0903499530-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 159 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 838103 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499530 JD9944 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903499545-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF-MTF | 454 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903499545 LE8192 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903499689-1 LE8181 | LEGEND IVY S19 | 105D | S2754MAS512B | 235 | 30/11/2026 |  | SA | SA14/08/2026 |  | PANTS |  | (15/10/2026) |  | 516333 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 0903499689 LE8181 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | M SL WV OH PT LEGEND IVY S19 |  | SS27
ADIDAS | 0903499724-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 154 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499724 KZ3199 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903499807-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 926 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499807 KZ3199 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903499822-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 3500 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516205 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499822 JE6417 | 29/10/2026 | KAHATEX CIJERAH | SPAIN | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903499855-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 101 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903499855 KZ3200 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903499864-1 JP1528 | BLACK | 45D | S25SPRMGFX260 | 2000 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (14/09/2026) |  | 516205 | PRINT L3+PAD SUB PROCESS_V3 | 0903499864 JP1528 |  | KAHATEX CIJERAH | SPAIN | SEA |  | M L G ENG TEE |  | SS27
ADIDAS | 0903499919-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 1750 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (24/09/2026) |  | 516442 | HT SUB PROCESS_V1 | 0903499919 KD9849 |  | KAHATEX CIJERAH | ITALY | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903499962-1 LE1842 | OLIVE TWO S27 | 90D | S2762LHAMG130 | 1203 | 15/11/2026 |  | SI | SI14/08/2026 |  | SWEATSHIRT |  | (15/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903499962 LE1842 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX H OLIVE TWO S27 |  | SS27-MS
ADIDAS | 0903499969-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 3499 | 15/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516442 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903499969 JE6414 |  | KAHATEX CIJERAH | ITALY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903499998-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2987 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903499998 LE1843 | 29/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500013-1 IS1413 | BLACK | 60D | S2425M405 | 1500 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 516442 | PRINT L3 SUB PROCESS_V3 | 0903500013 IS1413 |  | KAHATEX CIJERAH | ITALY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903500034-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 323 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516443 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903500034 LE1843 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903500077-1 LH2842 | BLACK | 90D | S2725M993 | 535 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 839055 | PRINT L1 SUB PROCESS_V3 | 0903500077 LH2842 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | TIG3R BLACK |  | SS27-STX
ADIDAS | 0903500135-1 IT3474 | PRELOVED CRIMSON F24 | 105D | S2408WR3202 | 193 | 30/11/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (04/09/2026) |  | Waiting fabric. T2 Gistex, PI Date 27-Sep. Waiting fabric. T2 Libolon, PI Date 04-Sep. 839055 | PAD+HT SUB PROCESS_V3 | 0903500135 IT3474 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA |  | RUN IT SHORT PRELOVED CRIMSON F24 |  | SS27-TI
ADIDAS | 0903501707-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 176 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501707 KZ3200 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903501742-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 137 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903501742 JD9944 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903501887-1 JD9944 | BLACK/WHITE | 90D | S2554WES503FT | 108 | 15/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (25/09/2026) |  | 839055 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903501887 JD9944 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | W SL FT SHO |  | SS27
ADIDAS | 0903501929-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 274 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903501929 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903501964-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 600 | 15/12/2026 |  | SA | SA14/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | 839055 | HT+PAD SUB PROCESS_V3 | 0903501964 KX3655 | 2026-12-11 | KAHATEX CIJERAH | SINGAPORE | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 0903502116-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 230 | 23/11/2026 |  | AN | AN14/08/2026 |  | SHORTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502116 KW2924 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903502119-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 144 | 15/11/2026 |  | SA | SA14/08/2026 |  | ACCESSORIES |  | (15/10/2026) |  | 848024 | PRINT L3+HT SUB PROCESS_V3 | 0903502119 LE4570 | 30/09/2026 | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903502153-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN-MTF | 725 | 15/11/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | ok |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903502153 LE8190 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903502154-1 JM1775 | BLACK/WHITE | 90D | F2554MESS711WV | 424 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (18/09/2026) |  | Waiting fabric. T2 Libolon, PI Date 18-Sep. 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903502154 JM1775 | 29/10/2026 | KAHATEX CIJERAH | ITALY | SEA |  | M SL WV PT 2 |  | SS27
ADIDAS | 0903502308-1 KY9383 | SEMI SOLAR BLUE S27 | 120D | S2608MR0201 | 1469 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502308 KY9383 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M SEMI SOLAR BLUE S27 |  | SS27-L2L
ADIDAS | 0903502411-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 391 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502411 KY9384 | 2026-12-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903502498-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1867 | 15/12/2026 |  | SI | SI14/08/2026 |  | SHORTS |  | (14/09/2026) |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903502498 KY9384 | 2026-12-11 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-L2L
ADIDAS | 0903504182-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 301 | 2026-07-12 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516443 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903504182 KV7863 |  | KAHATEX CIJERAH | ITALY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903504266-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 664 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903504266 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903504351-1 IC5188 | BLACK | 90D | S23080640 | 308 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (12/09/2026) |  | 839055 | HT SUB PROCESS_V1 | 0903504351 IC5188 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903504660-1 LE8202 | BLACK | 90D | F2606LHLF103MFN | 328 | 15/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903504660 LE8202 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC 3 F JSY SE |  | SS27-FJ
ADIDAS | 0903506204-1 KZ3199 | OLIVE FOUR S27/WHITE | 90D | S2754WESS404WV | 459 | 15/11/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (15/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903506204 KZ3199 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT OLIVE FOUR S27/WHITE |  | SS27
ADIDAS | 0903530511-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN-MTF | 594 | 15/12/2026 |  | AN | AN14/08/2026 |  | T-SHIRT |  | (20/10/2026) |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903530511 LE5779 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903530910-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 560 | 2026-07-12 |  | AN | AN18/08/2026 |  | SHORTS |  | (15/09/2026) |  | MOQ Issue 806020 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903530910 KW2924 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903530911-1 KW6443 | WHITE/BLACK | 90D | S2754MESS615WV | 824 | 15/11/2026 |  | AN | AN18/08/2026 |  | JACKET |  | (15/09/2026) |  | MOQ Issue 806020 | EMBRO SUB PROCESS_V1 | 0903530911 KW6443 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | M 19S WV WB WHITE/BLACK |  | SS27
ADIDAS | 0903530914-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 522 | 15/12/2026 |  | SI | SI18/08/2026 |  | PANTS |  |  |  | 806020 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903530914 KZ3200 | 30/10/2026 | KAHATEX CIJERAH | HONGKONG | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903535007-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 100 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 848016 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535007 KC8152 |  | KAHATEX CIJERAH | MOROCCO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903535008-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 539 | 30/11/2026 |  | SA | SA21/08/2026 |  | PANTS |  | (23/10/2026) |  | 516471 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903535008 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903541106-1 KS7771 | MEDIUM GREY HEATHER/WHITE | 90D | S26AAWVL320 | 6000 | 2026-07-12 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (10/10/2026) |  | 1st Art (TC 10 pcs) 600000 | EMBRO SUB PROCESS_V1 | 0903541106 KS7771 | 2026-10-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE MEDIUM GREY HEATHER/WHITE |  | SS27
ADIDAS | 0903541995-1 IN8707 | BLACK | 105D | S2408WR1601A | 100 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS | G1 | ok |  | Waiting fabric. DRC 0084-T2 Hua Feng, Unfc material, PI Date 30-Oct. Waiting fabric. T2 Men Chuen, PI Date 25-Sep. 839055 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903541995 IN8707 | 24/11/2026 | KAHATEX CIJERAH | SINGAPORE | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903542087-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 996 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903542087 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903542128-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 106 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903542128 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903542656-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 150 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542656 LG8616 | 2026-10-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903542705-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 400 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903542705 LL1875 | 2026-10-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903542903-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 155 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903542903 IU0217 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903544641-1 LE8198 | WHITE/BLACK | 90D | F2606LHJT101MF | 1271 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | MOQ Issue-PROCESS 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903544641 LE8198 | 2026-10-11 | KAHATEX CIJERAH | MALAYSIA | SEA |  | JUVE H F JSY SE |  | SS27-FJ
ADIDAS | 0903544653-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 377 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903544653 JE0055 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903545542-1 IN8707 | BLACK | 105D | S2408WR1601A | 320 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS | G1 | ok |  | Waiting fabric. DRC 0084-T2 Hua Feng, Unfc material, PI Date 30-Oct. Waiting fabric. T2 Men Chuen, PI Date 25-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903545542 IN8707 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903545628-1 IN8707 | BLACK | 105D | S2408WR1601A | 125 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS | G1 | ok |  | Waiting fabric. DRC 0084-T2 Hua Feng, Unfc material, PI Date 30-Oct. Waiting fabric. T2 Men Chuen, PI Date 25-Sep. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903545628 IN8707 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903546102-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 245 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903546102 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903546294-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 2 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 825054 | PRINT L1 SUB PROCESS_V3 | 0903546294 LG8616 | 2026-10-11 | KAHATEX CIJERAH | CHINA | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903547005-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 526 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903547005 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903547557-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 478 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903547557 IB8686 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903547607-1 HZ0747 | BLACK | 90D | F2325M414 | 200 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903547607 HZ0747 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | PL TEE |  | SS27
ADIDAS | 0903547791-1 IN1172 | BLACK | 105D | S2408WR1600 | 107 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516333 | HT SUB PROCESS_V1 | 0903547791 IN1172 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903547839-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 158 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516471 | HT SUB PROCESS_V1 | 0903547839 IT1469 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903547870-1 IN1157 | WHITE | 105D | S2408MR1600 | 541 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 516342 | HT SUB PROCESS_V1 | 0903547870 IN1157 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903548095-1 KX0123 | WHITE | 90D | S27SPRMGFXP0600-MTF | 129 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516471 | PRINT L3+PAD SUB PROCESS_V3 | 0903548095 KX0123 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M ADI RETRO T WHITE |  | SS27
ADIDAS | 0903548305-1 IS1413 | BLACK | 60D | S2425M405 | 175 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903548305 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548338-1 IN2961 | BLACK | 105D | S2408WR2400 | 159 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (05/10/2026) |  | 800005 | HT SUB PROCESS_V1 | 0903548338 IN2961 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903548343-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 190 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 830009 | PRINT L3 SUB PROCESS_V3 | 0903548343 IU0217 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548385-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 500 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903548385 IU0217 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548428-1 IS1413 | BLACK | 60D | S2425M405 | 501 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | PRINT L3 SUB PROCESS_V3 | 0903548428 IS1413 |  | KAHATEX CIJERAH | THAILAND | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548466-1 IS1413 | BLACK | 60D | S2425M405 | 381 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | PRINT L3 SUB PROCESS_V3 | 0903548466 IS1413 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903548545-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 306 | 2026-07-12 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903548545 LG8616 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903549325-1 HZ0747 | BLACK | 90D | F2325M414 | 982 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 838103 | EMBRO SUB PROCESS_V1 | 0903549325 HZ0747 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | PL TEE |  | SS27
ADIDAS | 0903549793-1 KA0246 | BLACK | 105D | S2608WR0902 | 863 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903549793 KA0246 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549825-1 KA0246 | BLACK | 105D | S2608WR0902 | 410 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903549825 KA0246 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549866-1 KA0246 | BLACK | 105D | S2608WR0902 | 663 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903549866 KA0246 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903549945-1 KA0246 | BLACK | 105D | S2608WR0902 | 332 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903549945 KA0246 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903550013-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 543 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903550013 KA2571 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903550204-1 HZ0747 | BLACK | 90D | F2325M414 | 269 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 839055 | EMBRO SUB PROCESS_V1 | 0903550204 HZ0747 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | PL TEE |  | SS27
ADIDAS | 0903550242-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1086 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550242 LE8190 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903550415-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 310 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550415 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903550456-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 528 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903550456 LE5779 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903551300-1 HZ0747 | BLACK | 90D | F2325M414 | 789 | 2026-07-12 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 814006 | EMBRO SUB PROCESS_V1 | 0903551300 HZ0747 |  | KAHATEX CIJERAH | THAILAND | SEA |  | PL TEE |  | SS27
ADIDAS | 0903551497-1 HZ0747 | BLACK | 90D | F2325M414 | 197 | 2026-07-12 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 800187 | EMBRO SUB PROCESS_V1 | 0903551497 HZ0747 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | PL TEE |  | SS27
ADIDAS | 0903551593-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 206 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903551593 HB7455 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903552136-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 404 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | PAD+HT SUB PROCESS_V3 | 0903552136 LD0278 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903552747-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 174 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 838103 | HT SUB PROCESS_V1 | 0903552747 HB7455 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903552812-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 189 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 838103 | PRINT L3+PAD SUB PROCESS_V3 | 0903552812 LE5779 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903553779-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 891 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800187 | PRINT L3+PAD SUB PROCESS_V3 | 0903553779 LE8192 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903553825-1 IN2961 | BLACK | 105D | S2408WR2400 | 143 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (05/10/2026) |  | 800187 | HT SUB PROCESS_V1 | 0903553825 IN2961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | OTR B TEE BLACK |  | SS27
ADIDAS | 0903553958-1 IN8707 | BLACK | 105D | S2408WR1601A | 424 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 814006 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903553958 IN8707 | 24/11/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903554171-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 120 | 2026-07-12 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516343 | PAD+HT SUB PROCESS_V3 | 0903554171 LD0278 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903554207-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554207 LL1875 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903554250-1 LL1874 | COLLEGIATE NAVY/COLLEGIATE NAVY | 90D | S2762LHRB048M | 300 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903554250 LL1874 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR MEL GRX T COLLEGIATE NAVY/COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903555046-1 IN1172 | BLACK | 105D | S2408WR1600 | 118 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 547012 | HT SUB PROCESS_V1 | 0903555046 IN1172 | 24/11/2026 | KAHATEX CIJERAH | UKRAINE | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903555100-1 KC8568 | BLACK | 105D | OJS26250839 | 1296 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 848012 | PRINT L1 SUB PROCESS_V3 | 0903555100 KC8568 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903555134-1 KC8568 | BLACK | 105D | OJS26250839 | 1072 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 848024 | PRINT L1 SUB PROCESS_V3 | 0903555134 KC8568 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | LO SHORTSBLACK |  | SS27-TI
ADIDAS | 0903555193-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 265 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903555193 KX9851 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903555271-1 LD0294 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0901 | 1437 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903555271 LD0294 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903555378-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 300 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555378 KZ3198 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555407-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 615 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903555407 KZ3205 | 2026-10-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903555925-1 HZ0747 | BLACK | 90D | F2325M414 | 2301 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903555925 HZ0747 |  | KAHATEX CIJERAH | GERMANY | SEA |  | PL TEE |  | SS27
ADIDAS | 0903555985-1 IN0089 | PUTTY GREY S24 | 105D | S2408MR3202 | 3501 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | PAD+HT SUB PROCESS_V3 | 0903555985 IN0089 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RUN IT SHORT PUTTY GREY S24 |  | SS27-TI
ADIDAS | 0903556026-1 IP2310 | BLACK | 105D | S2450MTR701 | 3000 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903556026 IP2310 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903556061-1 IP2310 | BLACK | 105D | S2450MTR701 | 4001 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903556061 IP2310 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE BLACK |  | SS27
ADIDAS | 0903556107-1 IS1413 | BLACK | 60D | S2425M405 | 3000 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903556107 IS1413 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903556277-1 JC8165 | WONDER ALUMINA S25/WHITE | 90D | S2554WES421WV | 223 | 2026-07-12 |  | SI | SI28/08/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS 830009 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903556277 JC8165 | 2026-10-11 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | W 3S WV SHO |  | SS27
ADIDAS | 0903556341-1 IL7232 | BLACK | 105D | S2408MR3202 | 100 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 830009 | PAD+HT SUB PROCESS_V3 | 0903556341 IL7232 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903556385-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 206 | 2026-07-11 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (06/08/2026) |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903556385 KB5961 | 24/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903558146-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 2400 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 516318 | PRINT L3 SUB PROCESS_V3 | 0903558146 IU0217 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903558188-1 IW8374 | SHADOW NAVY S22 | 105D | S2450MTR701 | 2501 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (13/10/2026) |  | 516318 | HT SUB PROCESS_V1 | 0903558188 IW8374 |  | KAHATEX CIJERAH | GERMANY | SEA |  | GYM+ TEE SHADOW NAVY S22 |  | SS27
ADIDAS | 0903558231-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558231 JC9346 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558277-1 JC9346 | WONDER ALUMINA S25/WHITE | 90D | S2554MESS643SJ | 385 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558277 JC9346 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558320-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558320 JE6414 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558358-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558358 JE6417 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558397-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 661 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558397 JE6419 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558412-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 110 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 516342 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903558412 KD0738 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903558444-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 5339 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558444 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903558463-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 2222 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903558463 LD0907 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903558476-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 660 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558476 JE6417 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903558515-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 5340 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903558515 JE6419 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903558517-1 KA0235 | BLACK | 105D | S2608WR0901 | 110 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903558517 KA0235 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903558541-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 303 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903558541 LD0909 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903558557-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 3116 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903558557 JE9012 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558600-1 JE9012 | BLACK/WHITE | 90D | S2554MESS643SJ | 386 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (06/10/2026) |  | 516204 | PRINT L1 SUB PROCESS_V3 | 0903558600 JE9012 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M LIN SJ SHO |  | SS27
ADIDAS | 0903558613-1 KA0235 | BLACK | 105D | S2608WR0901 | 300 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903558613 KA0235 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903559131-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 351 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 684009 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903559131 KA2571 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903560689-1 KZ2988 | SOLAR TURBO F26 | 105D | S2408WR1601A | 582 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903560689 KZ2988 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT SOLAR TURBO F26 |  | SS27-TRAX
ADIDAS | 0903560866-1 JD0957 | BLACK | 60D | S25ORISW311 | 140 | 15/11/2026 |  | ID | ID28/08/2026 |  | SHORTS |  | (30/09/2026) |  | 980004 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903560866 JD0957 |  | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | ADIC SWIMSH 5IN |  | SS27
ADIDAS | 0903561185-1 IN1172 | BLACK | 105D | S2408WR1600 | 395 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 684009 | HT SUB PROCESS_V1 | 0903561185 IN1172 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903561217-1 IN1173 | WHITE | 105D | S2408WR1600 | 406 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 684009 | HT SUB PROCESS_V1 | 0903561217 IN1173 | 24/11/2026 | KAHATEX CIJERAH | PERU | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903562067-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 413 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 659018 | PAD+HT SUB PROCESS_V3 | 0903562067 LD0278 |  | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903562117-1 KA0235 | BLACK | 105D | S2608WR0901 | 622 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 659018 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903562117 KA0235 | 24/11/2026 | KAHATEX CIJERAH | COLOMBIA | SEA |  | Run Ess Shor W BLACK |  | SS27-TRAX
ADIDAS | 0903562365-1 KA4331 | BLACK | 90D | S2608MR0902 | 412 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | PAD+HT SUB PROCESS_V3 | 0903562365 KA4331 |  | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903562644-1 IN1172 | BLACK | 105D | S2408WR1600 | 887 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903562644 IN1172 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564682-1 IN1159 | BLACK | 90D | S2408MR1601 | 1539 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903564682 IN1159 | 2026-10-11 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903564726-1 IN1173 | WHITE | 105D | S2408WR1600 | 589 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564726 IN1173 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564763-1 IN1157 | WHITE | 105D | S2408MR1600 | 454 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564763 IN1157 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903564830-1 KD9849 | PRELOVED FIG S24/WHITE | 90D | S2450WTR803 | 2340 | 30/11/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903564830 KD9849 |  | KAHATEX CIJERAH | MEXICO | SEA |  | PACER KNIT HIGH PRELOVED FIG S24/WHITE |  | SS27-TI
ADIDAS | 0903564907-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 714 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 652001 | HT SUB PROCESS_V1 | 0903564907 IT1469 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903565184-1 IN1173 | WHITE | 105D | S2408WR1600 | 3 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903565184 IN1173 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903565260-1 IN1157 | WHITE | 105D | S2408MR1600 | 472 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903565260 IN1157 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903566142-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 4 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue 848012 | PRINT L2+HT SUB PROCESS_V3 | 0903566142 KZ0028 | 2026-10-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 0903566172-1 JD0957 | BLACK | 60D | S25ORISW311 | 1200 | 2026-07-12 |  | ID | ID28/08/2026 |  | SHORTS |  | (30/09/2026) |  | 823016 | EMBRO+PPA+PPH L1+PPS SUB PROCESS_V3 | 0903566172 JD0957 |  | KAHATEX CIJERAH | SOUTH KOREA | SEA |  | ADIC SWIMSH 5IN |  | SS27
ADIDAS | 0903566214-1 HR8583 | SILVER GREEN S23 | 90D | F2225M403 | 1500 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516318 | EMBRO+PPA SUB PROCESS_V3 | 0903566214 HR8583 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SWTP |  | SS27
ADIDAS | 0903567116-1 IN1172 | BLACK | 105D | S2408WR1600 | 1453 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903567116 IN1172 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903567234-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 239 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567234 LE8190 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567294-1 IL7232 | BLACK | 105D | S2408MR3202 | 126 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903567294 IL7232 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | RUN IT SHORT BLACK |  | SS27-TI
ADIDAS | 0903567332-1 LE8190 | MUFC RED | 90D | F2606LHMU101MFN | 1976 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567332 LE8190 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | MUFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567429-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 211 | 2026-07-12 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567429 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567468-1 KA0247 | TECH INDIGO S20 | 105D | S2608WR0902 | 3500 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516318 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903567468 KA0247 | 24/11/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903567514-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 301 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516204 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567514 KA4913 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567535-1 KA0246 | BLACK | 105D | S2608WR0902 | 111 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 800005 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903567535 KA0246 | 24/11/2026 | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903567549-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 4000 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567549 KA4913 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567578-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 2395 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567578 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567590-1 KA4913 | OLIVE STRATA S23/WHITE | 105D | F25SSW0313 | 1201 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567590 KA4913 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567620-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 1910 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903567620 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903567630-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 301 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516204 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903567630 KA4914 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903567986-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 390 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 652001 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903567986 KV7863 |  | KAHATEX CIJERAH | MEXICO | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903568176-1 IN8707 | BLACK | 105D | S2408WR1601A | 144 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 848012 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903568176 IN8707 | 24/11/2026 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569208-1 IN1173 | WHITE | 105D | S2408WR1600 | 1052 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569208 IN1173 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569251-1 KA4331 | BLACK | 90D | S2608MR0902 | 526 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903569251 KA4331 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903569338-1 IN1157 | WHITE | 105D | S2408MR1600 | 1803 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569338 IN1157 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569377-1 IN1159 | BLACK | 90D | S2408MR1601 | 1365 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903569377 IN1159 | 2026-10-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569427-1 IN8707 | BLACK | 105D | S2408WR1601A | 836 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903569427 IN8707 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903569472-1 IT1469 | TEAM ROYAL BLUE | 105D | S2408MR1600 | 547 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (02/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903569472 IT1469 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903569590-1 JE0055 | MEDIUM GREY HEATHER/BLACK | 90D | S2554WES402FT | 385 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (10/10/2026) |  | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903569590 JE0055 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903569610-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 300 | 2026-07-12 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516254 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903569610 KV7863 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903569670-1 KA4914 | LUCID CYAN F23/WHITE | 105D | F25SSW0313 | 1200 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (25/09/2026) |  | 516318 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903569670 KA4914 |  | KAHATEX CIJERAH | GERMANY | SEA |  | ESS SH 8IN |  | SS27
ADIDAS | 0903569709-1 KC8559 | WHITE | 105D | OJS26250838 | 2400 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516318 | PRINT L1 SUB PROCESS_V3 | 0903569709 KC8559 |  | KAHATEX CIJERAH | GERMANY | SEA |  | OS TEE WHITE |  | SS27
ADIDAS | 0903569748-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1300 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569748 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569785-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 1200 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (06/10/2026) |  | 516318 | EMBRO SUB PROCESS_V1 | 0903569785 KD3911 |  | KAHATEX CIJERAH | GERMANY | SEA |  | RELEASED |  | SS27
ADIDAS | 0903569826-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 2499 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 1st Art (TC 10 pcs) 516318 | EMBRO SUB PROCESS_V1 | 0903569826 HK7303 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903570113-1 LE5779 | ACTIVE MAROON F19 | 90D | F2606LHLF101MFN | 155 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (31/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903570113 LE5779 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | LFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903570120-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 2976 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903570120 KV7863 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903570368-1 JC9584 | BLISS LILAC F22/WHITE | 90D | S2450WTR803 | 424 | 2026-07-12 |  | SI | SI28/08/2026 |  | SHORTS |  | (10/10/2026) |  | 830009 | HT SUB PROCESS_V1 | 0903570368 JC9584 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | PACER KNIT HIGH BLISS LILAC F22/WHITE |  | SS27-TI
ADIDAS | 0903571229-1 KA4331 | BLACK | 90D | S2608MR0902 | 764 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903571229 KA4331 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903571671-1 LG8616 | OFF WHITE | 90D | S2762LHAU1410M | 300 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (26/09/2026) |  | 400147 | PRINT L1 SUB PROCESS_V3 | 0903571671 LG8616 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | AU MI GFX TEE OFF WHITE |  | SS27-MS
ADIDAS | 0903571753-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 328 | 15/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571753 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903571791-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 290 | 30/11/2026 |  | ID | ID28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 980004 | HT+PAD SUB PROCESS_V3 | 0903571791 KB5965 | 24/11/2026 | KAHATEX CIJERAH | NEW ZEALAND | SEA |  | Run Ess Tee M |  | SS27-TI-SLT
ADIDAS | 0903572059-1 KA4331 | BLACK | 90D | S2608MR0902 | 327 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572059 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572081-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572081 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572124-1 KA4331 | BLACK | 90D | S2608MR0902 | 1163 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572124 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572145-1 KA4331 | BLACK | 90D | S2608MR0902 | 639 | 2026-07-12 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903572145 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903572154-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1052 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 672027 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903572154 KV7863 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903572157-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 119 | 30/11/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (26/10/2026) |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903572157 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903572221-1 KZ3198 | GREY FIVE F17/WHITE | 90D | S2754WESS404WV | 833 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903572221 KZ3198 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV OH PT GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903572804-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 902 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 960026 | PRINT L1 SUB PROCESS_V3 | 0903572804 LL1875 | 2026-10-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903572864-1 LL1875 | OFF WHITE/OFF WHITE | 90D | S2762LHRB048M | 180 | 30/11/2026 |  | NT | NT28/08/2026 |  | T-SHIRT |  |  |  | 960006 | PRINT L1 SUB PROCESS_V3 | 0903572864 LL1875 | 2026-10-11 | KAHATEX CIJERAH | AUSTRALIA | SEA |  | ORBR MEL GRX T OFF WHITE/OFF WHITE |  | SS27-MS
ADIDAS | 0903573116-1 KA4331 | BLACK | 90D | S2608MR0902 | 188 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 800005 | PAD+HT SUB PROCESS_V3 | 0903573116 KA4331 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903573217-1 IN1159 | BLACK | 90D | S2408MR1601 | 311 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 678002 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903573217 IN1159 | 2026-10-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903573341-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 2879 | 15/12/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 672027 | PAD+HT SUB PROCESS_V3 | 0903573341 LD0278 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903573350-1 KA2571 | BLACK/WHITE | 105D | S2650MTR437 | 2496 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903573350 KA2571 | 24/11/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 3SSHO BLACK/WHITE |  | SS27-TI
ADIDAS | 0903573378-1 LD0909 | SEMI SOLAR AQUA S27 | 105D | S2608WR0902 | 1555 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903573378 LD0909 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903573381-1 KD0738 | DARK BLUE/WHITE | 105D | S2650MTR437 | 2496 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 650010 | HT+PPA+PPH L1 SUB PROCESS_V3 | 0903573381 KD0738 | 24/11/2026 | KAHATEX CIJERAH | PANAMA | SEA |  | WE ALLSET 19SSHO DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903573403-1 KA0237 | TECH INDIGO S20 | 105D | S2608WR0901 | 2333 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (13/10/2026) |  | 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903573403 KA0237 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess Shor W TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 0903573411-1 LD0907 | SEMI SOLAR VIOLET S27 | 105D | S2608WR0902 | 1042 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 672027 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903573411 LD0907 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | Run Ess 21 S SEMI SOLAR VIOLET S27 |  | SS27-TRAX
ADIDAS | 0903573434-1 KA0246 | BLACK | 105D | S2608WR0902 | 500 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903573434 KA0246 | 24/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | Run Ess 21 S BLACK |  | SS27-TRAX
ADIDAS | 0903573458-1 HB7455 | LEGEND INK F17/REFLECTIVE SILVER | 105D | S22080606 | 2340 | 15/12/2026 |  | SI | SI28/08/2026 |  | SHORTS |  | (26/10/2026) |  | 652001 | HT SUB PROCESS_V1 | 0903573458 HB7455 |  | KAHATEX CIJERAH | MEXICO | SEA |  | OWN THE RUN SHO LEGEND INK F17/REFLECTIVE SILVER |  | SS27-TI
ADIDAS | 0903573472-1 KZ3205 | GREY FIVE F17/WHITE | 90D | S2754WESS422WV | 786 | 30/11/2026 |  | SI | SI28/08/2026 |  | JACKET |  | (29/09/2026) |  | 678002 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903573472 KZ3205 | 2026-10-11 | KAHATEX CIJERAH | ARGENTINA | SEA |  | W 3S WV BOMBER GREY FIVE F17/WHITE |  | SS27
ADIDAS | 0903574124-1 IN1159 | BLACK | 90D | S2408MR1601 | 318 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903574124 IN1159 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903574442-1 LE5389 | SILVER DAWN S23/WHITE | 90D | S26AAWVL320 | 6000 | 2026-07-12 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/09/2026) |  | 600000 | EMBRO SUB PROCESS_V1 | 0903574442 LE5389 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W CO BOXY TEE SILVER DAWN S23/WHITE |  | SS27
ADIDAS | 0903574568-1 LE7509 | BLACK/BRIGHT PINK F27 | 90D | S27AAWVL701 | 6000 | 2026-07-12 |  | AN | AN28/08/2026 |  | PANTS |  | (26/10/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903574568 LE7509 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 13S TRICOT PT BLACK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903574589-1 KD9094 | WHITE | 30D | F25GFXBLANKM | 425 | 30/11/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 814006 | EMBRO SUB PROCESS_V1 | 0903574589 KD9094 | 16/09/2026 | KAHATEX CIJERAH | THAILAND | SEA |  | M BLANK TEE |  | SS27
ADIDAS | 0903574668-1 KA4331 | BLACK | 90D | S2608MR0902 | 968 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (21/10/2026) |  | 516333 | PAD+HT SUB PROCESS_V3 | 0903574668 KA4331 |  | KAHATEX CIJERAH | GERMANY | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903574807-1 KG8547 | ONIX | 105D | S2408WR1600 | 579 | 15/12/2026 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (19/11/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 672027 | HT SUB PROCESS_V1 | 0903574807 KG8547 | 24/11/2026 | KAHATEX CIJERAH | BRAZIL | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903574863-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 800187 | PAD+HT SUB PROCESS_V3 | 0903574863 KA4331 | 2026-10-11 | KAHATEX CIJERAH | VIETNAM | SEA | 21/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 100 |  | 100 |  |  | 18/11/2026 | 18/11/2026 |  |  | 100 |  | 100 |  |  | 17/11/2026 | 17/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903574889-1 KA4331 | BLACK | 90D | S2608MR0902 | 100 | 30/11/2026 | 100 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 830009 | PAD+HT SUB PROCESS_V3 | 0903574889 KA4331 | 2026-10-11 | KAHATEX CIJERAH | PHILIPPINES | SEA | 21/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 100 |  | 100 |  |  | 18/11/2026 | 18/11/2026 |  |  | 100 |  | 100 |  |  | 17/11/2026 | 17/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903575054-1 IN1157 | WHITE | 105D | S2408MR1600 | 683 | 15/12/2026 |  | SA | SA28/08/2026 |  | T-SHIRT |  | (15/10/2026) |  | IMPROVE (AP Siti FU). DRC 0002/T2 Capacity Long LT from Far Eastern (VNM), PI date: 19-Nov (15D). 678002 | HT SUB PROCESS_V1 | 0903575054 IN1157 | 24/11/2026 | KAHATEX CIJERAH | ARGENTINA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 0903576131-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 500 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516343 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903576131 KZ0922 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903576180-1 IN1159 | BLACK | 90D | S2408MR1601 | 730 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903576180 IN1159 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903576204-1 IN1159 | BLACK | 90D | S2408MR1601 | 357 | 2026-07-12 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903576204 IN1159 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903576238-1 IN1159 | BLACK | 90D | S2408MR1601 | 226 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (30/10/2026) |  | 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903576238 IN1159 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903577174-1 IC5188 | BLACK | 90D | S23080640 | 375 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903577174 IC5188 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903577190-1 IC5188 | BLACK | 90D | S23080640 | 125 | 2026-07-12 |  | SI | SI28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 814006 | HT SUB PROCESS_V1 | 0903577190 IC5188 |  | KAHATEX CIJERAH | THAILAND | SEA |  | OWN THE RUN TEE |  | SS27
ADIDAS | 0903577664-1 KZ0922 | TEAM CRIMSON/WHITE | 90D | S2754WESS421WV | 716 | 30/11/2026 |  | SA | SA28/08/2026 |  | SHORTS |  | (29/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903577664 KZ0922 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 24 TEAM CRIMSON/WHITE |  | SS27
ADIDAS | 0903578729-1 KA4331 | BLACK | 90D | S2608MR0902 | 625 | 30/11/2026 | 625 | SA | SA28/08/2026 | G1C | SHORTS | G1 | (21/10/2026) |  | 29/09: ex-fty. DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS). 1st Art (TC 10 pcs) 516394 | PAD+HT SUB PROCESS_V3 | 0903578729 KA4331 | 2026-10-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA | 21/11/2026 | Run Ess 21 S M BLACK |  | SS27-TRAX | 21/11/2026 | 23/11/2026 |  |  | 625 |  | 625 |  |  | 18/11/2026 | 18/11/2026 |  |  | 625 |  | 625 |  |  | 17/11/2026 | 17/11/2026 |  |  | 625 |  | 625
ADIDAS | 0903578772-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 7 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516029 | PRINT L1 SUB PROCESS_V3 | 0903578772 LI6133 | 2026-10-11 | KAHATEX CIJERAH | GERMANY | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903578813-1 LI6133 | ACTIVE PURPLE S19 | 90D | SMSUFWWC27V6W | 4673 | 30/11/2026 |  | AN | AN28/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | 516027 | PRINT L1 SUB PROCESS_V3 | 0903578813 LI6133 | 2026-10-11 | KAHATEX CIJERAH | BRAZIL | SEA |  | FWWC27 LS TW ACTIVE PURPLE S19 |  | SS27-SPOMA
ADIDAS | 0903580788-1 KZ3200 | KHAKI THREE F26/WHITE | 90D | S2754WESS404WV | 458 | 15/12/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580788 KZ3200 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT KHAKI THREE F26/WHITE |  | SS27
ADIDAS | 0903580940-1 KZ3202 | SILVER BLUE S27/WHITE | 90D | S2754WESS404WV | 369 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580940 KZ3202 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT SILVER BLUE S27/WHITE |  | SS27
ADIDAS | 0903580989-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1772 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903580989 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581028-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 416 | 2026-07-12 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516394 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581028 KV7863 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581080-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 305 | 2026-07-12 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581080 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903581132-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1657 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903581132 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903582940-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 1357 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 600000 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903582940 KV7863 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903583205-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 608 | 30/11/2026 |  | SI | SI28/08/2026 |  | PANTS |  | (26/09/2026) |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903583205 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903595557-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 643 | 30/11/2026 |  | SI | SI03/09/2026 |  | T-SHIRT |  | (10/10/2026) |  | 857010 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903595557 LE1843 | 16/11/2026 | KAHATEX CIJERAH | INDIA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903595627-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 666 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 678002 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903595627 KC8152 |  | KAHATEX CIJERAH | ARGENTINA | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903595632-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 736 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903595632 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598944-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 314 | 14/11/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598944 KC8152 | 27/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598947-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 107 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 516394 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598947 KC8152 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598950-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 209 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 516333 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598950 KC8152 |  | KAHATEX CIJERAH | GERMANY | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598954-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 495 | 14/11/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | DRC 0090-early shipment customer (BTP_14_09_2026 EARLY HOLD SHIPMENT). 1st Art (TC 10 pcs) 652001 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598954 KC8152 | 27/11/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598958-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 139 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 848012 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598958 KC8152 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903598960-1 KC8152 | DARK BLUE/WHITE | 105D | S2650MTR436 | 1179 | 15/12/2026 |  | SA | SA02/09/2026 |  | PANTS |  |  |  | 672027 | HT+PPH L1+PPA SUB PROCESS_V3 | 0903598960 KC8152 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | WE ALLSET 20S PT DARK BLUE/WHITE |  | SS27-TI
ADIDAS | 0903600165-1 KY6510 | BLACK/WHITE | 105D | F2654MESS608WVB | 254 | 2026-07-11 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/08/2026) | ok | Waiting fabric. T2 Gistex, PI Date 24-Aug, ETD ?? Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Fu Hsun, PI Date 08-Aug, ETD 10-Aug, ETA-Kaha 21-Aug. 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903600165 KY6510 | 2026-08-10 | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S CHELSEA B7 |  | SS27
ADIDAS | 0903600283-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 177 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600283 LI2646 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600284-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 162 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600284 LI2667 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600285-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 324 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600285 LI2668 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600286-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 201 | 2026-07-11 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600286 LI2646 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 0903600287-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 132 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600287 LI2670 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600288-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 155 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600288 LI2670 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 0903600289-1 LI2668 | TEAM NAVY BLUE 2/TEAM LIGHT BLUE | 60D | S27AOCP103 | 194 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok |  | 516394 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600289 LI2668 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET SWEATSHIRT TEAM NAVY BLUE 2/TEAM LIGHT BLUE |  | SS27
ADIDAS | 0903600290-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 126 | 2026-07-11 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | 516333 | PRINT L3+PPH L1 SUB PROCESS_V3 | 0903600290 LI2667 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 0903600291-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 157 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | 516333 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600291 LI2671 | 2026-10-08 | KAHATEX CIJERAH | GERMANY | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903600292-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 137 | 2026-07-11 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) |  | 516394 | PRINT L3+EMBRO SUB PROCESS_V3 | 0903600292 LI2671 | 2026-10-08 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 0903603357-1 JM6495 | BLACK | 60D | F25SPRMGFX041 | 1272 | 15/11/2026 |  | SI | SI16/09/2026 |  | T-SHIRT |  |  |  | 516318 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903603357 JM6495 | 22/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M DDL BIKE T |  | SS27 | [11 empty] | 2026-12-04 | 2026-12-04 |  | 1272 |  | 1272
ADIDAS | 0903603358-1 JM6496 | WHITE | 60D | F25SPRMGFX041 | 1128 | 15/11/2026 |  | SI | SI16/09/2026 |  | T-SHIRT |  |  |  | 516318 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | 0903603358 JM6496 | 22/10/2026 | KAHATEX CIJERAH | GERMANY | SEA |  | M DDL BIKE T |  | SS27 | [11 empty] | 2026-08-04 | 2026-08-04 |  | 1128 |  | 1128
ADIDAS | 0903608631-1 IS1413 | BLACK | 60D | S2425M405 | 572 | 2026-07-12 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903608631 IS1413 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610429-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 496 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903610429 IU0217 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610469-1 IS1413 | BLACK | 60D | S2425M405 | 526 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 839055 | PRINT L3 SUB PROCESS_V3 | 0903610469 IS1413 |  | KAHATEX CIJERAH | SINGAPORE | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903610504-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 100 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610504 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610537-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 203 | 30/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903610537 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610597-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 348 | 2026-07-12 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 814006 | HT+PAD SUB PROCESS_V3 | 0903610597 KB5960 |  | KAHATEX CIJERAH | THAILAND | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610638-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 305 | 2026-07-12 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903610638 KB5960 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903610663-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 518 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 838103 | PRINT L3 SUB PROCESS_V3 | 0903610663 IU0217 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903611060-1 KX9851 | SEMI SOLAR AQUA S27 | 90D | S2408MR1601 | 180 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS 516254 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903611060 KX9851 | 2026-11-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO E SHORT SEMI SOLAR AQUA S27 |  | SS27-TRAX
ADIDAS | 0903611230-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 150 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 630001 | PRINT L3 SUB PROCESS_V3 | 0903611230 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | CANADA | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | [11 empty] | 17/09/2026 | 17/09/2026 |  | 125 |  | 125
ADIDAS | 0903611417-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 652 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611417 KA0544 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611448-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 125 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903611448 LJ4075 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903611450-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 592 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611450 KA0546 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611477-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 846 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3+PAD SUB PROCESS_V3 | 0903611477 LE8192 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903611492-1 IN1159 | BLACK | 90D | S2408MR1601 | 1212 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516254 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903611492 IN1159 | 2026-11-11 | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903611507-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 522 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611507 LE8192 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903611531-1 KA0544 | BLACK | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611531 KA0544 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611537-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 300 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611537 KA5088 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611554-1 JE6338 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS601FT | 1682 | 15/12/2026 |  | SA | SA11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903611554 JE6338 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903611561-1 KA0546 | WHITE | 60D | S26KJUGFX009 | 688 | 15/11/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848024 | PRINT L3+PAD SUB PROCESS_V3 | 0903611561 KA0546 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | J FOOTBALL T |  | SS27
ADIDAS | 0903611568-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 2669 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611568 KA5090 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611584-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 1542 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903611584 JE0052 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903611604-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 2492 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611604 KA5089 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611616-1 JD1877 | BLACK/WHITE | 90D | S2554MESS601FT | 2873 | 15/12/2026 |  | SA | SA11/09/2026 |  | JACKET |  |  |  | 600000 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | 0903611616 JD1877 |  | KAHATEX CIJERAH | UNITED STATES | SEA |  | M 3S FT FZ HD |  | SS27
ADIDAS | 0903611635-1 KA5089 | WONDER SAGE S26 | 60D | S26SPRWGFX004 | 308 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903611635 KA5089 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903611652-1 HK2890 | BLACK | 90D | F2225M270 | 2 | 14/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 825054 | HT+PPH L1 SUB PROCESS_V3 | 0903611652 HK2890 |  | KAHATEX CIJERAH | CHINA | SEA |  | C TEE |  | SS27
ADIDAS | 0903611729-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 100 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 857010 | PRINT L3 SUB PROCESS_V3 | 0903611729 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | INDIA | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | [11 empty] | 17/09/2026 | 17/09/2026 |  | 94 |  | 94
ADIDAS | 0903612070-1 JE0052 | BLACK/WHITE | 90D | S2554WES402FT | 532 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 672027 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612070 JE0052 |  | KAHATEX CIJERAH | BRAZIL | SEA |  | W 3S FT FZ HD |  | SS27
ADIDAS | 0903612091-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 652001 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612091 IT1467 | 2026-11-11 | KAHATEX CIJERAH | MEXICO | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903612328-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 181 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903612328 LJ4073 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903612449-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 1080 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848012 | EMBRO SUB PROCESS_V1 | 0903612449 HK7303 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612487-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 1080 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848012 | EMBRO SUB PROCESS_V1 | 0903612487 IB8686 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612500-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 2750 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L3 SUB PROCESS_V3 | 0903612500 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | [11 empty] | 17/09/2026 | 17/09/2026 |  | 2279 |  | 2279
ADIDAS | 0903612510-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1224 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 848012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612510 KD4872 |  | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612512-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 238 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516471 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612512 IT1467 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903612524-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 300 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903612524 LJ4074 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903612540-1 HK7303 | HALO SILVER S21 | 90D | F2225M400 | 900 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848024 | EMBRO SUB PROCESS_V1 | 0903612540 HK7303 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612561-1 IB8686 | SILVER GREEN S23 | 90D | F2225M400 | 900 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 848024 | EMBRO SUB PROCESS_V1 | 0903612561 IB8686 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | ESS TEE |  | SS27
ADIDAS | 0903612582-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 269 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 512106 | PRINT L3 SUB PROCESS_V3 | 0903612582 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | KAZAKHSTAN | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | [11 empty] | 17/09/2026 | 17/09/2026 |  | 219 |  | 219
ADIDAS | 0903612596-1 IN1159 | BLACK | 90D | S2408MR1601 | 352 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 600000 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612596 IN1159 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ADIZERO E SHORT BLACK |  | SS27-TRAX
ADIDAS | 0903612689-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 157 | 15/12/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903612689 KB5961 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612720-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 402 | 2026-07-12 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800187 | HT+PAD SUB PROCESS_V3 | 0903612720 KE8424 |  | KAHATEX CIJERAH | VIETNAM | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903612744-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 500 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 547012 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612744 KD4872 |  | KAHATEX CIJERAH | UKRAINE | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612815-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 132 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903612815 LE1843 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903612816-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 350 | 2026-07-12 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612816 KB5965 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612835-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1008 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 848024 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903612835 KD4872 |  | KAHATEX CIJERAH | SAUDI ARABIA | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903612868-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 311 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 652001 | PRINT L2+PPH L1 SUB PROCESS_V3 | 0903612868 LE1843 | 2026-11-11 | KAHATEX CIJERAH | MEXICO | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 0903612871-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 442 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612871 KB5961 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612931-1 KB5960 | WHITE | 120D | S2608MR0900A-SLT | 368 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 830009 | HT+PAD SUB PROCESS_V3 | 0903612931 KB5960 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903612957-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 220 | 15/12/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS), PI date from Huafeng: 21-Nov, follow garment LT: 120D. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612957 KA6229 | 23/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903612972-1 JZ7775 | MEDIUM GREY HEATHER | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903612972 JZ7775 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M MEDIUM GREY HEATHER |  | SS27-TRAX
ADIDAS | 0903612977-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 201 | 15/12/2026 |  | ID | ID11/09/2026 |  | SHORTS |  |  |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS), PI date from Huafeng: 21-Nov, follow garment LT: 120D. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903612977 KA6229 | 23/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 0903612991-1 KA4331 | BLACK | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903612991 KA4331 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M BLACK |  | SS27-TRAX
ADIDAS | 0903613017-1 KD3911 | AURORA ONIX S26 | 60D | S2525M200 | 790 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 630001 | EMBRO SUB PROCESS_V1 | 0903613017 KD3911 |  | KAHATEX CIJERAH | CANADA | SEA |  | RELEASED |  | SS27
ADIDAS | 0903613111-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 513 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 848012 | PRINT L3 SUB PROCESS_V3 | 0903613111 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | UNITED ARAB EMIRATES | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS | [11 empty] | 17/09/2026 | 17/09/2026 |  | 432 |  | 432
ADIDAS | 0903613123-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 630001 | PAD+HT SUB PROCESS_V3 | 0903613123 LD0278 |  | KAHATEX CIJERAH | CANADA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 0903613329-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 301 | 15/12/2026 | 301 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS), PI date from Huafeng: 21-Nov, follow garment LT: 120D. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903613329 KA6229 | 23/11/2026 | KAHATEX CIJERAH | GERMANY | SEA | 26/11/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 26/11/2026 | 27/11/2026 |  |  | 301 |  | 301 |  |  | 23/11/2026 | 24/11/2026 |  |  | 301 |  | 301 |  |  | 18/11/2026 | 19/11/2026 |  |  | 301 |  | 301
ADIDAS | 0903613410-1 LL3375 | AURORA COFFEE S26/CHALK PINK F27 | 90D | S2754WESS422WV | 720 | 15/12/2026 |  | SI | SI11/09/2026 |  | JACKET |  |  |  | 516342 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903613410 LL3375 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BOMBER AURORA COFFEE S26/CHALK PINK F27 |  | SS27
ADIDAS | 0903613500-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 114 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903613500 LJ4073 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903613504-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 2671 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613504 JE6419 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903613540-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 4449 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613540 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903613548-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 101 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 600000 | PRINT L1 SUB PROCESS_V3 | 0903613548 LJ4075 | 2026-11-11 | KAHATEX CIJERAH | UNITED STATES | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903613575-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 300 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613575 JE6417 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903613612-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 551 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613612 JE6414 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903613665-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 1700 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516318 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613665 KA5088 |  | KAHATEX CIJERAH | GERMANY | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903613678-1 JC5282 | WHITE | 60D | S25SPRMGFX233 | 497 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 838103 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | 0903613678 JC5282 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | M L SLIDE PKT T |  | SS27
ADIDAS | 0903613692-1 KA5090 | WHITE | 60D | S26SPRWGFX004 | 329 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516204 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903613692 KA5090 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903613721-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 1098 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613721 KD4872 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903613777-1 KD4872 | WONDER SAGE S26/COLLEGIATE GREEN | 90D | S2554MESS611FT | 8900 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903613777 KD4872 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 45S FT SHO WONDER SAGE S26/COLLEGIATE GREEN |  | SS27
ADIDAS | 0903614230-1 HK7309 | BLACK | 45D | F2225M402 | 2400 | 2026-07-11 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 804028 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614230 HK7309 |  | KAHATEX CIJERAH | JAPAN | SEA |  | ESS HDY |  | SS27
ADIDAS | 0903614393-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 100 | 15/12/2026 | 100 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS), PI date from Huafeng: 21-Nov, follow garment LT: 120D. 830009 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614393 KA6229 | 23/11/2026 | KAHATEX CIJERAH | PHILIPPINES | SEA | 26/11/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 26/11/2026 | 27/11/2026 |  |  | 100 |  | 100 |  |  | 23/11/2026 | 24/11/2026 |  |  | 100 |  | 100 |  |  | 18/11/2026 | 19/11/2026 |  |  | 100 |  | 100
ADIDAS | 0903614477-1 KB5961 | MEDIUM GREY HEATHER | 120D | S2608MR0900A-SLT | 101 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614477 KB5961 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903614507-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 116 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903614507 LJ4073 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903614548-1 LE8192 | BETTER SCARLET S23 | 90D | F2606LHAF101MF | 172 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 800005 | PRINT L3+PAD SUB PROCESS_V3 | 0903614548 LE8192 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | AFC H F JSY SE |  | SS27-FJ
ADIDAS | 0903614550-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 148 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 830009 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903614550 JE6419 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903614552-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 301 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516471 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614552 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903614583-1 KV7963 | BLACK/WHITE | 90D | S2754WESS421WV | 247 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903614583 KV7963 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV SHO 4 BLACK/WHITE |  | SS27
ADIDAS | 0903614597-1 KA5088 | DARK BLUE | 60D | S26SPRWGFX004 | 150 | 15/11/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 830009 | EMBRO+PAD+HT+PPH L1 SUB PROCESS_V3 | 0903614597 KA5088 |  | KAHATEX CIJERAH | PHILIPPINES | SEA |  | MINI EMB T |  | SS27
ADIDAS | 0903614654-1 LC8884 | BLACK | 90D | S27SPRMGFXP0800-MTF | 300 | 15/12/2026 |  | AN | AN11/09/2026 |  | T-SHIRT |  |  |  | 630001 | PRINT L2+PAD SUB PROCESS_V3 | 0903614654 LC8884 |  | KAHATEX CIJERAH | CANADA | SEA |  | M RESORT T BLACK |  | SS27
ADIDAS | 0903614814-1 KA6229 | BLACK | 120D | S2608WR0202-SLT | 451 | 15/12/2026 | 451 | ID | ID11/09/2026 | G1B | SHORTS | G1 |  |  | DRC 0084/a.Unfc Material SLT - Not received MCAF Speed LT (NOOS), PI date from Huafeng: 21-Nov, follow garment LT: 120D. 516333 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903614814 KA6229 | 23/11/2026 | KAHATEX CIJERAH | GERMANY | SEA | 25/11/2026 | ADI365/// 2i1 W BLACK |  | SS27-TRAX | 25/11/2026 | 26/11/2026 |  |  | 451 |  | 451 |  |  | 20/11/2026 | 23/11/2026 |  |  | 451 |  | 451 |  |  | 17/11/2026 | 18/11/2026 |  |  | 451 |  | 451
ADIDAS | 0903614843-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 200 | 15/11/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903614843 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903615339-1 JE6414 | BLACK/WHITE | 90D | S2554MESS611FT | 285 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516342 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615339 JE6414 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 3S FT SHO BLACK/WHITE |  | SS27
ADIDAS | 0903615648-1 JE6417 | DARK BLUE/WHITE | 90D | S2554MESS611FT | 1700 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516318 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615648 JE6417 |  | KAHATEX CIJERAH | GERMANY | SEA |  | M 17S FT SHO DARK BLUE/WHITE |  | SS27
ADIDAS | 0903615680-1 JE6419 | MEDIUM GREY HEATHER/BLACK | 90D | S2554MESS611FT | 330 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516204 | EMBRO+PPH L1 SUB PROCESS_V3 | 0903615680 JE6419 |  | KAHATEX CIJERAH | UNITED KINGDOM | SEA |  | M 31S FT SHO MEDIUM GREY HEATHER/BLACK |  | SS27
ADIDAS | 0903615732-1 KE8424 | BLACK | 120D | S2608MR0906A-SLT | 101 | 15/12/2026 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 838103 | HT+PAD SUB PROCESS_V3 | 0903615732 KE8424 |  | KAHATEX CIJERAH | MALAYSIA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 0903615872-1 KB5965 | BLACK | 120D | S2608MR0900A-SLT | 120 | 2026-07-11 |  | ID | ID11/09/2026 |  | T-SHIRT |  |  |  | 800005 | HT+PAD SUB PROCESS_V3 | 0903615872 KB5965 |  | KAHATEX CIJERAH | INDONESIA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 0903616174-1 IT1467 | TEAM ROYAL BLUE | 90D | S2408MR1601 | 308 | 15/12/2026 |  | SA | SA11/09/2026 |  | SHORTS |  |  |  | 516342 | HT+PAD+PPH L1 SUB PROCESS_V3 | 0903616174 IT1467 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ADIZERO E SHORT TEAM ROYAL BLUE |  | SS27-TRAX
ADIDAS | 0903617338-1 KW2924 | BLACK/WHITE | 90D | S2754WESS703WV | 124 | 15/12/2026 |  | AN | AN11/09/2026 |  | SHORTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903617338 KW2924 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV BER SHO BLACK/WHITE |  | SS27
ADIDAS | 0903617380-1 LJ4073 | COLLEGIATE NAVY | 90D | S2762LHRB047M | 299 | 15/12/2026 |  | SA | SA11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617380 LJ4073 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903617441-1 LJ4075 | COLLEGIATE NAVY | 90D | S2762LHRB045M | 201 | 15/12/2026 |  | SA | SA11/09/2026 |  | SWEATSHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617441 LJ4075 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX H M COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903617477-1 LJ4074 | COLLEGIATE NAVY | 90D | S2762LHRB046Y | 206 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L1 SUB PROCESS_V3 | 0903617477 LJ4074 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | ORBR GRX T Y COLLEGIATE NAVY |  | SS27-MS
ADIDAS | 0903624240-1 IU0217 | WONDER WHITE F21 | 60D | S2425M405 | 580 | 2026-07-12 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516342 | PRINT L3 SUB PROCESS_V3 | 0903624240 IU0217 |  | KAHATEX CIJERAH | GERMANY | SEA |  | IN RANGE |  | SS27
ADIDAS | 0903626403-1 LJ2754 | BLACK | 60D | S2762LHMR399 | 751 | 15/11/2026 |  | SI | SI11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626403 LJ2754 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | MER DNA PT JSY BLACK |  | SS27-MS
ADIDAS | 0903626428-1 LE4570 | SIMPLE BROWN | 60D | S2762LHAU334 | 751 | 15/11/2026 |  | SA | SA11/09/2026 |  | ACCESSORIES |  |  |  | 652001 | PRINT L3+HT SUB PROCESS_V3 | 0903626428 LE4570 | 17/10/2026 | KAHATEX CIJERAH | MEXICO | SEA |  | AU TW PET JSY SIMPLE BROWN |  | SS27-MS
ADIDAS | 0903627485-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 3037 | 15/12/2026 |  | SI | SI11/09/2026 |  | PANTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903627485 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903627519-1 KV7863 | BLACK/WHITE | 90D | S2754WESS404WV | 348 | 15/12/2026 |  | SI | SI11/09/2026 |  | PANTS |  |  |  | 516333 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 0903627519 KV7863 |  | KAHATEX CIJERAH | GERMANY | SEA |  | W 3S WV OH PT BLACK/WHITE |  | SS27
ADIDAS | 0903637773-1 LZ9161 | BLACK/SEMI MINT RUSH S22 | 90D | F2662LHME165 | 567 | 15/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | 516333 | PRINT L3 SUB PROCESS_V3 | 0903637773 LZ9161 | 2026-11-11 | KAHATEX CIJERAH | GERMANY | SEA |  | MER C CHAMP TEE BLACK/SEMI MINT RUSH S22 |  | SS27-MS
ADIDAS | 4501928388-1 LG9668 | KHAKI THREE F26 | 120D | S2754WAS514C | 100 | 14/11/2026 |  | ID | ID29/05/2026 |  | SKIRT |  | (15/07/2026) | (22/06/2026) | Waiting fabric. T2 Teijin Nantong, PI date 15-Jul, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4501928388 LG9668 | 31/08/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV SK KHAKI THREE F26 |  | SS27
ADIDAS | 4502065732-2 KX7715 | GREY FIVE F17/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 14/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) |  | T2 Libolon, PI Date 23-Jul, actual receives 30-Jul. T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Gistex, PI Date 16-Aug, actual receives 17-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502065732 KX7715 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT GREY FIVE F17/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066730-1 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 30 | 21/11/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) | (04/08/2026) | Waiting fabric. T2 Gistex, PI Date 27-Jul, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 22-Jul, actual receives 28-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502066730 KX7716 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066730-2 KX7716 | BLACK/LIGHT GREY HEATHER | 105D | S2754JKTM534B | 100 | 14/12/2026 |  | SA | SA26/06/2026 |  | JACKET |  | (16/08/2026) |  | Waiting fabric. T2 Gistex, PI Date 16-Aug, ETD ?? T2 Kahatex, PI Date 12-Aug, actual receives 28-Jul. T2 Libolon, PI Date 23-Jul, actual receives 28-Jul. ZA30 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | 4502066730 KX7716 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ESS REVERSI JKT BLACK/LIGHT GREY HEATHER |  | SS27-RVS
ADIDAS | 4502066741-1 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 926 | 2026-07-12 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066741 KX3655 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 4502066741-2 KX3655 | TEAM NAVY BLUE 2 | 120D | S2608MR0900A | 1135 | 14/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066741 KX3655 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M TEAM NAVY BLUE 2 |  | SS27-TI
ADIDAS | 4502066831-1 LF0729 | OLIVE ONE S27 | 120D | S2754MAS510B | 171 | 14/12/2026 |  | SI | SI26/06/2026 |  | JACKET |  | (28/08/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502066831 LF0729 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV TT OLIVE ONE S27 |  | SS27
ADIDAS | 4502066844-2 KB5965 | BLACK | 120D | S2608MR0900A | 100 | 14/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066844-3 KB5965 | BLACK | 120D | S2608MR0900A | 100 | 2026-07-12 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066844 KB5965 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066850-1 KX3654 | OLIVE TWO S27 | 120D | S2608MR0900A | 327 | 14/12/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) | ok | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066850 KX3654 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M OLIVE TWO S27 |  | SS27-TI
ADIDAS | 4502066871-2 KE8424 | BLACK | 120D | S2608MR0906A | 100 | 14/11/2026 |  | SI | SI26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066871 KE8424 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess LS M BLACK |  | SS27-TI
ADIDAS | 4502066873-2 KB5960 | WHITE | 120D | S2608MR0900A | 72 | 2026-07-11 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502066873-3 KB5960 | WHITE | 120D | S2608MR0900A | 385 | 21/11/2026 |  | SA | SA26/06/2026 |  | T-SHIRT |  | (28/08/2026) |  | ZA30 | HT+PAD SUB PROCESS_V3 | 4502066873 KB5960 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess Tee M |  | SS27-TI
ADIDAS | 4502069351-1 LI2667 | BLACK/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502069351 LI2667 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT BLACK/WHITE |  | SS27
ADIDAS | 4502070211-1 LF0721 | OLIVE ONE S27 | 105D | S2754MAS512B | 193 | 14/12/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) | (04/08/2026) | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070211 LF0721 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV OH PT OLIVE ONE S27 |  | SS27
ADIDAS | 4502070409-2 LF0718 | BLACK | 105D | S2754MAS512B | 50 | 14/11/2026 |  | SA | SA26/06/2026 |  | PANTS |  | (28/08/2026) |  | Waiting fabric. T2 Teijin Nantong, PI Date 18-Aug, ETD ?? T2 Kahatex, PI Date 28-Aug, actual receives 12-Aug. ZA30 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | 4502070409 LF0718 | 24/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | M SL WV OH PT BLACK |  | SS27
ADIDAS | 4502070657-1 LI2670 | BLACK/WHITE | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070657 LI2670 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE BLACK/WHITE |  | SS27
ADIDAS | 4502070658-1 LI2671 | CLEAR PINK/BRIGHT PINK F27 | 60D | S27AOCP102 | 100 | 30/11/2026 |  | SA | SA26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+EMBRO SUB PROCESS_V3 | 4502070658 LI2671 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RUFFLE TEE CLEAR PINK/BRIGHT PINK F27 |  | SS27
ADIDAS | 4502070659-1 LI2645 | TEAM LIGHT BLUE/TEAM NAVY BLUE 2 | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070659 LI2645 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE TEAM LIGHT BLUE/TEAM NAVY BLUE 2 |  | SS27
ADIDAS | 4502070898-1 LI2669 | TEAM MAROON 2/WHITE | 60D | S27AOCP103 | 100 | 30/11/2026 |  | AN | AN26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070898 LI2669 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET SWEATSHIRT TEAM MAROON 2/WHITE |  | SS27
ADIDAS | 4502070899-1 LI2646 | BRIGHT PINK F27/CLEAR PINK | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | (08/08/2026) | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070899 LI2646 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE BRIGHT PINK F27/CLEAR PINK |  | SS27
ADIDAS | 4502070901-1 LI2647 | CLOUD WHITE F18/COLLEGIATE GREEN | 60D | S27AOCP101 | 100 | 30/11/2026 |  | SI | SI26/06/2026 |  | ACCESSORIES |  | ok | ok | ZA30 | PRINT L3+PPH L1 SUB PROCESS_V3 | 4502070901 LI2647 | 2026-10-08 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | PET RAGLAN TEE CLOUD WHITE F18/COLLEGIATE GREEN |  | SS27
ADIDAS | 4502075076-1 KT4840 | ONIX | 90D | S2408MR1600 | 859 | 21/11/2026 |  | SA | SA30/06/2026 |  | T-SHIRT |  | (10/07/2026) | ok | Waiting fabric. T2 Y.T.I, ETD 10-Jul, ETA-Kaha 08-Aug. ZA30 | HT SUB PROCESS_V1 | 4502075076 KT4840 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO E TEE |  | SS27-YTI
ADIDAS | 4502075079-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 100 | 2026-07-11 |  | SI | SI30/06/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075079 KR3066 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502075080-1 KZ1286 | SILVER DAWN S23 | 120D | S2608WR0201 | 260 | 21/11/2026 |  | SI | SI30/06/2026 |  | SHORTS |  | (15/09/2026) |  | Waiting fabric. T2 Far Eastern, PI Date 15-Sep. Waiting fabric. T2 Hua Feng, PI Date 14-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 10-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 09-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502075080 KZ1286 | 28/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W SILVER DAWN S23 |  | SS27-TRAX
ADIDAS | 4502075930-1 KZ0028 | ONIX/NIGHT GREY | 90D | F2608MR1201BUF | 140 | 14/11/2026 |  | AN | AN30/06/2026 |  | T-SHIRT |  | (31/07/2026) | ok | Waiting fabric. T2 Sue's, material quality issues (moir膿), PI Date 27-Jul, actual receives ? ZA30 | PRINT L2+HT SUB PROCESS_V3 | 4502075930 KZ0028 | 14/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ASPYRE TEE UF ONIX/NIGHT GREY |  | SS27-TRAX
ADIDAS | 4502076909-1 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 2026-07-11 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 2026-01-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502076909-2 JZ7709 | BLACK | 120D | S2608MR0201 | 300 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502076909 JZ7709 | 2026-01-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502077373-1 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 2026-07-11 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077373-2 LD0278 | TEAM NAVY BLUE 2 | 90D | S2608MR0902 | 100 | 14/11/2026 |  | SA | SA03/07/2026 |  | SHORTS |  |  |  | Waiting fabric. T2 Grand tex, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 New Wide, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502077373 LD0278 | 17/09/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | Run Ess 21 S M TEAM NAVY BLUE 2 |  | SS27-TRAX
ADIDAS | 4502077374-1 KY9384 | VISTA GREEN S14 | 120D | S2608MR0201 | 1193 | 21/11/2026 |  | SI | SI03/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502077374 KY9384 | 2026-01-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M VISTA GREEN S14 |  | SS27-TRAX
ADIDAS | 4502347325-1 LH3760 | KHAKI THREE F26 | 120D | S2754WAS518B | 249 | 14/11/2026 |  | SI | SI10/07/2026 |  | PANTS |  | (04/09/2026) | ok | Waiting fabric. T2 Teijin Nantong, PI Date 04-Sep. Waiting fabric. T2 Kahatex, PI Date 10-Aug, ETD ?? ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4502347325 LH3760 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV BR PT KHAKI THREE F26 |  | SS27
ADIDAS | 4502347613-1 JZ7709 | BLACK | 120D | S2608MR0201 | 1094 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347613 JZ7709 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502347613-2 JZ7709 | BLACK | 120D | S2608MR0201 | 100 | 2026-07-12 |  | SI | SI10/07/2026 |  | SHORTS |  | (15/08/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 31-Jul, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347613 JZ7709 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-TRAX
ADIDAS | 4502347632-1 JZ7711 | BLACK | 120D | S2608MR0202 | 130 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502347632 JZ7711 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 4502348815-1 KR3066 | ONIX/REFLECTIVE SILVER | 120D | S2608MR0201 | 116 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Y.R.C, PI Date 15-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502348815 KR3066 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M ONIX/REFLECTIVE SILVER |  | SS27-TRAX
ADIDAS | 4502349090-1 KD3875 | BLACK | 120D | S2608WR0201 | 142 | 14/11/2026 |  | SI | SI10/07/2026 |  | SHORTS |  | (24/07/2026) | ok | Waiting fabric. T2 Trax, PI Date 27-Jul, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349090 KD3875 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W BLACK |  | SS27-TRAX
ADIDAS | 4502349403-1 KA6229 | BLACK | 120D | S2608WR0202 | 112 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (28/08/2026) | ok | Waiting fabric. T2 Hua Feng, PI Date 31-Aug, ETD ?? Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? Waiting fabric. T2 Best Pacific, PI Date 14-Aug, ETD ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349403 KA6229 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502349501-1 JZ7715 | TECH INDIGO S20 | 120D | S2608MR0202 | 141 | 14/11/2026 |  | SA | SA10/07/2026 |  | SHORTS |  | (31/08/2026) | ok | Waiting fabric. T2 Far Easten, PI Date 25-Aug, ETD ?? T2 Hua Feng, PI Date 31-Aug, actual receives 04-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502349501 JZ7715 | 2026-08-10 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M TECH INDIGO S20 |  | SS27-TRAX
ADIDAS | 4502364155-1 KZ4389 | WHITE | 120D | F2608MR1500 | 15 | 30/11/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | Waiting fabric. T2 Men Chuen, PI Date 24-Sep. ZA30 | PAD+HT SUB PROCESS_V3 | 4502364155 KZ4389 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M WHITE |  | SS27-TRAX
ADIDAS | 4502364164-1 KZ4388 | BLACK | 120D | F2608MR1500 | 15 | 15/12/2026 |  | ID | ID31/07/2026 |  | T-SHIRT |  | (24/09/2026) |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Men Chuen, PI Date ?? ZA30 | PAD+HT SUB PROCESS_V3 | 4502364164 KZ4388 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M BLACK |  | SS27-TRAX
ADIDAS | 4502368096-1 KY9391 | SEMI FROZEN AQUA S27 | 120D | S2608WR0201 | 169 | 15/12/2026 |  | SI | SI31/07/2026 |  | SHORTS |  |  |  | MOQ Issue-PROCESS Waiting fabric. DRC 0064-T2 Hua Feng, PI Date ?? Waiting fabric. T2 Far Eastern, PI Date ?? Waiting fabric. T2 Y.R.C, PI Date ?? Waiting fabric. T2 Best Pacific, PI Date ?? ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502368096 KY9391 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO W SEMI FROZEN AQUA S27 |  | SS27-TRAX
ADIDAS | 4502368741-1 JZ7709 | BLACK | 120D | S2608MR0201 | 208 | 30/11/2026 |  | SI | SI31/07/2026 |  | SHORTS |  | (04/10/2026) |  | Waiting fabric. T2 Hua Feng, PI Date 04-Oct. Waiting fabric. T2 Y.R.C, PI Date 02-Sep. ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502368741 JZ7709 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// SHO M BLACK |  | SS27-L2L
ADIDAS | 4502369618-1 KV0333 | GREY TWO F17 | 120D | F2608MR1500 | 15 | 14/12/2026 |  | ID | ID14/08/2026 |  | T-SHIRT |  |  |  | MOQ Issue ZA30 | PAD+HT SUB PROCESS_V3 | 4502369618 KV0333 | 2026-12-11 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADIZERO A TEE M GREY TWO F17 |  | SS27-TRAX
ADIDAS | 4502369661-1 LH3759 | AURORA COFFEE S26 | 120D | S2754WAS518B | 100 | 14/12/2026 |  | SI | SI14/08/2026 |  | PANTS |  | (05/10/2026) |  | ZA30 | PRINT L3+PPA SUB PROCESS_V3 | 4502369661 LH3759 |  | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | W SL WV BR PT AURORA COFFEE S26 |  | SS27
ADIDAS | 4502369662-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 251 | 21/11/2026 |  | SI | SI14/08/2026 |  | T-SHIRT |  | (25/09/2026) |  | ZA30 | PRINT L2+PPH L1 SUB PROCESS_V3 | 4502369662 LE1843 | 29/10/2026 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | 4502369990-1 KA6229 | BLACK | 120D | S2608WR0202 | 1 | 14/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (29/09/2026) |  | ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502369990 KA6229 | 2026-12-11 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502370031-1 JZ7711 | BLACK | 120D | S2608MR0202 | 56 | 14/12/2026 |  | SA | SA14/08/2026 |  | SHORTS |  | (12/10/2026) |  | 1st Art (TC 10 pcs) ZA30 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502370031 JZ7711 | 2026-12-11 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | ADI365/// 2i1 M BLACK |  | SS27-TRAX
ADIDAS | 4502374523-1 KA6229 | BLACK | 120D | S2608WR0202 | 867 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502374523 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502374524-1 KA6229 | BLACK | 120D | S2608WR0202 | 2969 | 15/11/2026 |  | SA | SA18/08/2026 |  | SHORTS |  |  |  | 516443 | HT+PAD+PPH L1 SUB PROCESS_V3 | 4502374524 KA6229 | 13/11/2026 | KAHATEX CIJERAH | ITALY | SEA |  | ADI365/// 2i1 W BLACK |  | SS27-TRAX
ADIDAS | 4502375402-1 LE1843 | CREAM WHITE | 90D | S2762LHAMG125 | 2 | 14/12/2026 |  | SI | SI11/09/2026 |  | T-SHIRT |  |  |  | ZA30 | PRINT L2+PPH L1 SUB PROCESS_V3 | 4502375402 LE1843 | 2026-11-11 | KAHATEX CIJERAH | SOUTH AFRICA | SEA |  | AMG SEL GFX T CREAM WHITE |  | SS27-MS
ADIDAS | OFC-07092026-013 | MULTI COLOR | 45D | F2225M402 | 465 | 30/11/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-013 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-017 | MULTI COLOR | 90D | F2225M403 | 400 | 15/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA SUB PROCESS_V3 | OFC-07092026-017 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-021 | MULTI COLOR | 90D | F2325M414 | 11 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-021 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-025 | MULTI COLOR | 75D | F2325M421 | 360 | 30/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPS SUB PROCESS_V3 | OFC-07092026-025 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-026 | MULTI COLOR | 105D | F2408MR1606 | 709 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-026 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-033 | MULTI COLOR | 45D | F24KLKGFX003 | 2546 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-033 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-034 | MULTI COLOR | 45D | F24KLKGFX003 | 5 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-034 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-035 | MULTI COLOR | 60D | F2525M432 | 594 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-035 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-036 | MULTI COLOR | 60D | F2550WTR422 | 4 | 15/11/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L3+PAD+HT SUB PROCESS_V3 | OFC-07092026-036 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-037 | MULTI COLOR | 90D | F2554MESS710WV | 90 | 30/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-037 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-038 | MULTI COLOR | 90D | F2554MESS710WV | 600 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-038 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-040 | MULTI COLOR | 30D | F25GFXBLANKM | 5909 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-040 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-044 | MULTI COLOR | 60D | F25KIUGFX010 | 1697 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-044 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-045 | MULTI COLOR | 60D | F25KIUGFX010 | 5948 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-045 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-049 | MULTI COLOR | 60D | F25KLKGFX011 | 178 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-049 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-050 | MULTI COLOR | 60D | F25KLKGFX011 | 150 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-050 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-055 | MULTI COLOR | 60D | F25SPRMGFX040 | 1166 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-055 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-057 | MULTI COLOR | 105D | F25SSW0313 | 5 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-057 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1005 | MULTI COLOR | 90D | S2762LHAMG125 | 503 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1005 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1009 | MULTI COLOR | 90D | S2762LHAMG130 | 301 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1009 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1013-B | MULTI COLOR | 105D | S2762LHAMG135-B | 20 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1013-B |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1013-T | MULTI COLOR | 105D | S2762LHAMG135 | 20 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1013-T |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1016 | MULTI COLOR | 90D | S2762LHAU1410M | 357 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1016 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1075 | MULTI COLOR | 90D | S2762LHME145M | 300 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1075 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1076 | MULTI COLOR | 90D | S2762LHME146M | 300 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1076 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1077 | MULTI COLOR | 90D | S2762LHME150M | 170 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1077 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1078 | MULTI COLOR | 90D | S2762LHME151K | 132 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1078 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1079 | MULTI COLOR | 90D | S2762LHME152M | 300 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1079 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1080 | MULTI COLOR | 90D | S2762LHMEDR103M | 300 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1080 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1083 | MULTI COLOR | 90D | S2762LHMEDR106K | 255 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1083 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1088 | MULTI COLOR | 90D | S2762LHMEDR107M | 300 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1088 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-110 | MULTI COLOR | 90D | F2606LHAF101MF | 144 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-110 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1105 | MULTI COLOR | 90D | S2762LHMEKA201M | 6 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-1105 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-111 | MULTI COLOR | 90D | F2606LHAF101YF | 229 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-111 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-112 | MULTI COLOR | 90D | F2606LHBM101MF | 478 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-112 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1130 | MULTI COLOR | 60D | S27FBGFXP101 | 355 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1130 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1131 | MULTI COLOR | 60D | S27FBGFXP102 | 318 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1132 | MULTI COLOR | 60D | S27FBGFXP102 | 181 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD PRINT SUB PROCESS | OFC-07092026-1132 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1135 | MULTI COLOR | 60D | S27FBGFXP510 | 171 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1135 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1136 | MULTI COLOR | 60D | S27FBGFXP510 | 1054 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1136 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1137 | MULTI COLOR | 60D | S27FBGFXP510 | 268 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1137 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1139 | MULTI COLOR | 60D | S27FBGFXP600 | 324 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT SUB PROCESS | OFC-07092026-1139 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-114 | MULTI COLOR | 90D | F2606LHLF101FY | 238 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-114 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1142 | MULTI COLOR | 90D | S27SPRMGFXP0600 | 210 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-1142 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1143 | MULTI COLOR | 90D | S27SPRMGFXP0800 | 74 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD SUB PROCESS_V3 | OFC-07092026-1143 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1144 | MULTI COLOR | 90D | S27SPRMGFXP0900 | 442 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-1144 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-115 | MULTI COLOR | 90D | F2606LHLF101FYL | 244 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-115 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-116 | MULTI COLOR | 90D | F2606LHLF101MFL | 880 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-116 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1176 | MULTI COLOR | 60D | S2762LHAU334 | 564 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1176 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1177 | MULTI COLOR | 60D | S2762LHAU334 | 340 | 15/12/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1177 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-118 | MULTI COLOR | 90D | F2606LHLF101MFN | 112 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-118 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1180 | MULTI COLOR | 60D | S2762LHAU373 | 34 | 15/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1180 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1181 | MULTI COLOR | 60D | S2762LHAU373 | 38 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1181 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1182 | MULTI COLOR | 60D | S2762LHAU373 | 230 | 15/12/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3 SUB PROCESS_V3 | OFC-07092026-1182 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1185 | MULTI COLOR | 60D | S2762LHMR399 | 661 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+HT SUB PROCESS_V3 | OFC-07092026-1185 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1186 | MULTI COLOR | 60D | S27AOCP101 | 1370 | 15/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1186 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1187 | MULTI COLOR | 60D | S27AOCP101 | 15361 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1187 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1188 | MULTI COLOR | 60D | S27AOCP102 | 1171 | 15/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1188 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1189 | MULTI COLOR | 60D | S27AOCP102 | 9098 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+EMBRO SUB PROCESS_V3 | OFC-07092026-1189 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1190 | MULTI COLOR | 60D | S27AOCP103 | 840 | 15/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1190 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-1191 | MULTI COLOR | 60D | S27AOCP103 | 1380 | 30/11/2026 |  |  | 2026-07-09 |  | ACCESSORIES |  |  |  | SP5 BP | PRINT L3+PPH L1 SUB PROCESS_V3 | OFC-07092026-1191 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-121 | MULTI COLOR | 90D | F2606LHLF102FY | 642 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-121 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-122 | MULTI COLOR | 90D | F2606LHLF102FYL | 241 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-122 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-123 | MULTI COLOR | 90D | F2606LHLF102MFL | 248 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-123 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-124 | MULTI COLOR | 90D | F2606LHLF102MFN | 282 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-124 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-125 | MULTI COLOR | 90D | F2606LHLF103FY | 100 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-125 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-126 | MULTI COLOR | 90D | F2606LHLF103FYL | 318 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-126 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-127 | MULTI COLOR | 90D | F2606LHLF103MFL | 646 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-127 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-128 | MULTI COLOR | 90D | F2606LHMU101FY | 262 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-128 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-129 | MULTI COLOR | 90D | F2606LHMU101MFN | 22 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-129 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-131 | MULTI COLOR | 90D | F2608MR1201BUF | 374 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-131 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-132 | MULTI COLOR | 90D | F2608MR1201BUF | 185 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-132 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-143 | MULTI COLOR | 90D | F2625M101 | 594 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-143 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-144 | MULTI COLOR | 90D | F2625M101 | 536 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-144 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-145 | MULTI COLOR | 90D | F2625M101 | 602 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-145 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-150 | MULTI COLOR | 90D | F2625W233 | 54 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-150 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-151 | MULTI COLOR | 90D | F2625W233 | 1 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-151 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-152 | MULTI COLOR | 105D | F2654MESS614WVB | 37 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-152 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-157 | MULTI COLOR | 60D | F26FBGFXP101 | 410 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-157 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-158 | MULTI COLOR | 60D | F26FBGFXP104 | 1800 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-158 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-159 | MULTI COLOR | 60D | F26FBGFXP105 | 451 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-159 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-298 | MULTI COLOR | 60D | PH_F_BKB_A | 185 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-298 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-299 | MULTI COLOR | 60D | PH_F_SPW_A | 100 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-299 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-300 | MULTI COLOR | 60D | PH_F_SPW_A | 308 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-300 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-304 | MULTI COLOR | 60D | PH_F_SWK_A | 283 | 30/11/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-304 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-305 | MULTI COLOR | 60D | PH_F_SWK_A | 260 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-305 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-309 | MULTI COLOR | 60D | PH_F_TRA_A | 254 | 15/11/2026 |  |  | 2026-07-09 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-309 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-310 | MULTI COLOR | 60D | PH_F_TRA_A | 376 | 30/11/2026 |  |  | 2026-07-09 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-310 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-311 | MULTI COLOR | 90D | PH_MOTORSPR_APP | 233 | 15/12/2026 |  |  | 2026-07-09 |  | POLO SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-311 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-340 | MULTI COLOR | 90D | PHORIGMEN | 4447 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-340 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-350 | MULTI COLOR | 90D | PHORIGWMN | 25 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-350 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-356 | MULTI COLOR | 90D | PHRUN | 1545 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-356 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-357 | MULTI COLOR | 90D | PHRUN | 6813 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-357 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-367 | MULTI COLOR | 90D | PHRUNWMN | 1445 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-367 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-376 | MULTI COLOR | 90D | PHSPWK | 1223 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-376 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-385 | MULTI COLOR | 90D | PHSPWM | 720 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-385 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-386 | MULTI COLOR | 90D | PHSPWM | 2303 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-386 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-396 | MULTI COLOR | 90D | PHSPWW | 271 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-396 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-404 | MULTI COLOR | 90D | PHSWIM | 2 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-404 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-410 | MULTI COLOR | 90D | PHTRNMEN | 38 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-410 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-411 | MULTI COLOR | 90D | PHTRNMEN | 345 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-411 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-419 | MULTI COLOR | 90D | PHTRNWMN | 30 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT+EMBRO+PAD PRINT SUB PROCESS | OFC-07092026-419 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-426 | MULTI COLOR | 60D | S1954WC511 | 336 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-426 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-428 | MULTI COLOR | 60D | S211CSIM120FLTC | 2 | 15/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-428 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-436 | MULTI COLOR | 60D | S2307M501 | 2 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD+HT+PPA+PPH SUB PROCESS_V3 | OFC-07092026-436 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-437 | MULTI COLOR | 90D | S23080640 | 462 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-437 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-438 | MULTI COLOR | 90D | S23080640 | 1648 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-438 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-440-B | MULTI COLOR | 90D | S2315KSWLK102-B | 7383 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-440-B |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-440-T | MULTI COLOR | 90D | S2315KSWLK102 | 7383 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-440-T |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-445 | MULTI COLOR | 45D | S2315KSWU324A | 260 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-445 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-447 | MULTI COLOR | 105D | S2408MR1600 | 495 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-447 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-448 | MULTI COLOR | 105D | S2408MR1600 | 103 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-448 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-449 | MULTI COLOR | 105D | S2408MR1600 | 1244 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-449 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-459 | MULTI COLOR | 90D | S2408MR1601 | 405 | 15/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-459 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-460 | MULTI COLOR | 90D | S2408MR1601 | 1013 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-460 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-461 | MULTI COLOR | 90D | S2408MR1601 | 1016 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-461 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-476 | MULTI COLOR | 105D | S2408WR1600 | 238 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-476 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-477 | MULTI COLOR | 105D | S2408WR1600 | 203 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-477 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-487 | MULTI COLOR | 105D | S2408WR1601A | 109 | 15/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-487 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-488 | MULTI COLOR | 105D | S2408WR1601A | 368 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-488 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-497 | MULTI COLOR | 105D | S2408WR1603 | 87 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-497 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-504 | MULTI COLOR | 60D | S2425M405 | 1295 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-504 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-505 | MULTI COLOR | 60D | S2425M405 | 8325 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-505 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-506 | MULTI COLOR | 60D | S2425M405 | 7642 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3 SUB PROCESS_V3 | OFC-07092026-506 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-514 | MULTI COLOR | 90D | S2450WTR803 | 81 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-514 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-518 | MULTI COLOR | 90D | S2506GHTM400M | 218 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-518 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-519 | MULTI COLOR | 90D | S2506GHTM400Y | 1 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-519 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-520 | MULTI COLOR | 90D | S2506GHTM401M | 643 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-520 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-523 | MULTI COLOR | 60D | S2525M200 | 790 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-523 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-524 | MULTI COLOR | 60D | S2525M200 | 8189 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-524 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-530 | MULTI COLOR | 90D | S2554MESS601FT | 1 | 30/11/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-530 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-531 | MULTI COLOR | 90D | S2554MESS601FT | 13842 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-531 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-536 | MULTI COLOR | 90D | S2554MESS605FT | 5 | 15/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-536 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-537 | MULTI COLOR | 90D | S2554MESS605FT | 655 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-537 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-541 | MULTI COLOR | 90D | S2554MESS611FT | 91 | 15/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-541 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-542 | MULTI COLOR | 90D | S2554MESS611FT | 10 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-542 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-546 | MULTI COLOR | 90D | S2554MESS612FT | 1941 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-546 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-549 | MULTI COLOR | 90D | S2554MESS642WV | 76 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L1+PPH L1 SUB PROCESS_V3 | OFC-07092026-549 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-550 | MULTI COLOR | 90D | S2554MESS663SJ | 1 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-550 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-551 | MULTI COLOR | 90D | S2554MESS663SJ | 279 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-551 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-554 | MULTI COLOR | 90D | S2554MESS675FT | 1158 | 15/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-554 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-555 | MULTI COLOR | 90D | S2554MESS675FT | 29 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-555 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-561 | MULTI COLOR | 90D | S2554WES402FT | 14 | 30/11/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-561 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-562 | MULTI COLOR | 90D | S2554WES402FT | 9710 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-562 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-566 | MULTI COLOR | 90D | S2554WES403FT | 6 | 30/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-566 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-567 | MULTI COLOR | 90D | S2554WES403FT | 874 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-567 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-570 | MULTI COLOR | 90D | S2554WES413FTB | 22 | 30/11/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-570 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-571 | MULTI COLOR | 90D | S2554WES413FTB | 2852 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-571 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-574 | MULTI COLOR | 90D | S2554WES421WV | 38 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-574 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-575 | MULTI COLOR | 90D | S2554WES421WV | 3706 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-575 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-584 | MULTI COLOR | 90D | S2554WES428FT | 319 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-584 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-586 | MULTI COLOR | 90D | S2554WES503FT | 102 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-586 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-587 | MULTI COLOR | 90D | S2554WES512FT | 120 | 30/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-587 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-588 | MULTI COLOR | 90D | S2554WES512FT | 4034 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPH L1 SUB PROCESS_V3 | OFC-07092026-588 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-593 | MULTI COLOR | 60D | S25SPRMGFX230 | 40 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PPH L1+PAD SUB PROCESS_V3 | OFC-07092026-593 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-594 | MULTI COLOR | 60D | S25SPRMGFX233 | 36 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-594 | 13/10/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-595 | MULTI COLOR | 60D | S25SPRMGFX233 | 432 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO+PAD+HT+PPA SUB PROCESS_V3 | OFC-07092026-595 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-601 | MULTI COLOR | 60D | S25SPRMGFX313 | 957 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-601 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-602 | MULTI COLOR | 90D | S25TEGFX501A | 27 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+PAD+HT SUB PROCESS_V3 | OFC-07092026-602 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-606 | MULTI COLOR | 90D | S2606GHTM302M | 310 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO+HT+PAD SUB PROCESS_V3 | OFC-07092026-606 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-608 | MULTI COLOR | 120D | S2608MR0201 | 173 | 15/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-608 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-609 | MULTI COLOR | 120D | S2608MR0201 | 101 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-609 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-610 | MULTI COLOR | 120D | S2608MR0201 | 646 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-610 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-621 | MULTI COLOR | 105D | S2608MR0201B | 375 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-621 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-647 | MULTI COLOR | 120D | S2608MR0900A | 910 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-647 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-648 | MULTI COLOR | 120D | S2608MR0900A | 37 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-648 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-649 | MULTI COLOR | 120D | S2608MR0900A | 1747 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-649 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-660 | MULTI COLOR | 105D | S2608MR0901 | 209 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-660 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-668 | MULTI COLOR | 90D | S2608MR0902 | 1018 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-668 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-669 | MULTI COLOR | 90D | S2608MR0902 | 253 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-669 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-680 | MULTI COLOR | 120D | S2608MR0906A | 1 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT+PAD SUB PROCESS_V3 | OFC-07092026-680 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-693 | MULTI COLOR | 120D | S2608WR0201 | 587 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-693 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-708 | MULTI COLOR | 120D | S2608WR0202 | 546 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PAD+PPH L1 SUB PROCESS_V3 | OFC-07092026-708 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-732 | MULTI COLOR | 105D | S2608WR0901 | 30 | 15/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-732 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-733 | MULTI COLOR | 105D | S2608WR0901 | 1844 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-733 | 18/11/2026 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-745 | MULTI COLOR | 105D | S2608WR0902 | 101 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-745 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-746 | MULTI COLOR | 105D | S2608WR0902 | 3685 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-746 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-756 | MULTI COLOR | 90D | S2608WR0910 | 117 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2+HT SUB PROCESS_V3 | OFC-07092026-756 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-759 | MULTI COLOR | 90D | S2615KSWJ751 | 1975 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-759 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-764 | MULTI COLOR | 90D | S2615KSWJ753 | 864 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-764 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-770 | MULTI COLOR | 90D | S2625M018 | 586 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-770 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-771 | MULTI COLOR | 90D | S2625M018 | 923 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-771 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-775 | MULTI COLOR | 90D | S2625M036 | 101 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-775 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-776 | MULTI COLOR | 90D | S2625M036 | 404 | 30/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-776 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-777 | MULTI COLOR | 90D | S2625M036 | 18 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-777 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-783 | MULTI COLOR | 30D | S2625W005 | 239 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-783 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-787 | MULTI COLOR | 90D | S2625W005 | 587 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-787 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-794 | MULTI COLOR | 90D | S2650MTR402 | 13 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-794 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-810 | MULTI COLOR | 105D | S2650MTR436 | 2466 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | HT+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-810 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-817 | MULTI COLOR | 105D | S2650MTR437 | 647 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-817 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-820 | MULTI COLOR | 90D | S2650MTR805A | 40 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-820 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-825 | MULTI COLOR | 105D | S2650WTR339 | 204 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PAD+HT SUB PROCESS_V3 | OFC-07092026-825 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-834 | MULTI COLOR | 90D | S2654MSERENO742 | 926 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-834 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-839 | MULTI COLOR | 90D | S2654MSERENO743 | 685 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L1+HT SUB PROCESS_V3 | OFC-07092026-839 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-843 | MULTI COLOR | 90D | S26AAWVL320 | 2 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-843 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-846 | MULTI COLOR | 60D | S26KJGGFX020 | 145 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-846 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-861 | MULTI COLOR | 60D | S26SPRWGFX005 | 829 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD+PPH L1+EMBRO SUB PROCESS_V3 | OFC-07092026-861 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-862 | MULTI COLOR | 60D | S26SPRWGFX023 | 1 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L2 SUB PROCESS_V3 | OFC-07092026-862 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-866 | MULTI COLOR | 60D | S26SPRWGFX110 | 1120 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-866 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-867 | MULTI COLOR | 60D | S26SPRWGFX111 | 117 | 15/11/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L3+PAD SUB PROCESS_V3 | OFC-07092026-867 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-870 | MULTI COLOR | 90D | S2706CHLF022 | 134 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-870 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-871 | MULTI COLOR | 75D | S2706CHRM031 | 1203 | 30/11/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | PRINT L2+EMBRO SUB PROCESS_V3 | OFC-07092026-871 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-875 | MULTI COLOR | 90D | S2725M920 | 351 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-875 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-876 | MULTI COLOR | 90D | S2725M926A | 1604 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-876 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-878 | MULTI COLOR | 90D | S2725M993 | 758 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1 SUB PROCESS_V3 | OFC-07092026-878 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-882 | MULTI COLOR | 105D | S2750MTR041A | 552 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | PRINT L1+PAD SUB PROCESS_V3 | OFC-07092026-882 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-885 | MULTI COLOR | 105D | S2750MTR052 | 287 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | HT SUB PROCESS_V1 | OFC-07092026-885 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-893 | MULTI COLOR | 105D | S2754JKTM534B | 60 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | PRINT L3+EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-893 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-907 | MULTI COLOR | 105D | S2754MAS511B | 48 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-907 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-914 | MULTI COLOR | 105D | S2754MAS512B | 44 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-914 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-920 | MULTI COLOR | 105D | S2754MAS513 | 124 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | PRINT L3+PPH L1+PPA SUB PROCESS_V3 | OFC-07092026-920 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-933 | MULTI COLOR | 90D | S2754MESS659PQ | 975 | 15/12/2026 |  |  | 2026-07-09 |  | POLO SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-933 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-935 | MULTI COLOR | 90D | S2754MESS674DK | 706 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-935 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-937 | MULTI COLOR | 90D | S2754MESS676SJ | 2904 | 15/12/2026 |  |  | 2026-07-09 |  | T-SHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-937 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-942 | MULTI COLOR | 105D | S2754MESS708WV | 2455 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-942 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-945 | MULTI COLOR | 105D | S2754MESS710WV | 152 | 15/12/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-945 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-963 | MULTI COLOR | 90D | S2754WESS404WV | 4515 | 30/11/2026 |  |  | 2026-07-09 |  | PANTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-963 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-973 | MULTI COLOR | 90D | S2754WESS420WV | 132 | 30/11/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-973 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-974 | MULTI COLOR | 90D | S2754WESS420WV | 240 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-974 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-979 | MULTI COLOR | 90D | S2754WESS421WV | 1632 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-979 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-988 | MULTI COLOR | 90D | S2754WESS422WV | 108 | 30/11/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-988 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-989 | MULTI COLOR | 90D | S2754WESS422WV | 722 | 15/12/2026 |  |  | 2026-07-09 |  | JACKET |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-989 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-995 | MULTI COLOR | 90D | S2754WESS501DK | 1342 | 15/12/2026 |  |  | 2026-07-09 |  | SWEATSHIRT |  |  |  | SP5 | EMBRO SUB PROCESS_V1 | OFC-07092026-995 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-998 | MULTI COLOR | 90D | S2754WESS703WV | 49 | 30/11/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-998 |  | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
ADIDAS | OFC-07092026-999 | MULTI COLOR | 90D | S2754WESS703WV | 437 | 15/12/2026 |  |  | 2026-07-09 |  | SHORTS |  |  |  | SP5 | EMBRO+PPA+PPH L1 SUB PROCESS_V3 | OFC-07092026-999 | 2026-06-11 | KAHATEX CIJERAH |  | SEA |  |  |  | SS27
Total |  |  |  |  | 2060779 |  | 8234 | [22 empty] | 8234 | 112 | 8122 | [6 empty] | 8234 | 6121 | 7662 | 5550 | [5 empty] | 8122 | 459 | 7663